## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 2f4854e1-7269-4795-a63c-8cc4bb2f4ead |  | checklist | POST - S - Internal Lining - Ceilings |  |  |  |  | Yes | POST - S - Internal Lining - Ceilings | 0021e162-5d5f-45f2-bc28-bcf996a4860c
checkpoint-status | ac18fa03-fba1-4a7e-a53d-fe1976e9119f |  | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status | 666d56ea-c8a3-4f23-ab9d-e4e11bb4e5be |  | checkpoint | Consider bracing, adhesive/sealant & lining layer(s) requirements (consider fire stopping between layers)
checkpoint-status | 55c6fdcb-0d93-48ef-901f-688b1224994a |  | checkpoint | Services/Penetrations, correctly formed & located (consider cutout tolerances and access hatches (location & size) where applicable)
checkpoint-status | 5dafc999-01a7-4b02-8794-1726e88d9b06 |  | checkpoint | Correct fixing pattern/sealant (consider fire)/adhesive/layers installed to align with consented design and specifications
checkpoint-status | 8670c759-d2fc-49d0-b65c-461a5413d987 |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status | 6ed8f1e1-e227-48ea-875d-11a1060158f7 |  | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checkpoint-status | 5c0dfef6-675a-4847-b87b-2f13b788d1b9 |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 4acc3f4c-d596-4c76-a0c5-8194b90f7edf |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 8394e9c9-167a-4209-b5fb-91898ec52483 |  | checklist | POST - S - Internal Lining - Walls |  |  |  |  | Yes | SYS - POST - S - Internal Lining - Walls (old version) | 10921ddb-ed00-4b1d-b144-8013e2b65d72
checkpoint-status | 2cebf342-cddc-4ce2-9f61-05e6ddea5044 |  | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status | 17d3546f-5ae9-4fb9-aa46-5e78100ef333 |  | checkpoint | Consider bracing, adhesive/sealant & lining layer(s) requirements (consider fire stopping between layers)
text | fc2d3360-9a86-53e6-a0db-4c3fe244146c |  | textbox | Specific products used (photos Required)
checkpoint-status | 6d2fb974-aa72-4e9f-8f9e-df5f2c40ef15 |  | checkpoint | Services/penetrations, correctly formed & located (consider cut-out tolerances where applicable)
checkpoint-status | 54af7d83-88e0-48c1-83ec-4a76343bcdbd |  | checkpoint | Correct fixing pattern/sealant (consider fire)/adhesive/layers installed to align with consented design and specifications
checkpoint-status | 35ba3d35-fd94-4d10-9cd3-0d5787464a39 |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status | 9d653e97-6f58-4f8d-991f-e52d21df803e |  | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checklist-flat | 1490cc5b-5ee7-4665-a80c-531fe59306b5 |  | checklist | Patch up |  |  |  |  | Yes | Patch up | 15258860-47b9-488a-8a38-b6272405eed6
checkpoint-status | c0eee994-ea4e-4ebe-9d80-97824ca333eb |  | checkpoint | All patch ups completed to site guidelines (Photos attached)
checklist-flat | 92c7aa88-998f-487e-a4e4-d9009d228088 |  | checklist | POST - S - Stopping |  |  |  |  | Yes | SYS - POST - S - Stopping (old version) | 27e1c4ff-60a4-4dd0-976e-67142b292777
checkpoint-status | fc8005d9-22c1-4624-8c47-d98f1ba2a08b |  | checkpoint | Consider fire stopping between layers of lining & apply compound(s) as specified
checkpoint-status | bd2dfe09-9a3a-4283-b0c2-230314b95c3f |  | checkpoint | Openings/penetrations/corners & bulkheads, correctly formed (consider tolerances where applicable)
checkpoint-status | 0c3bd280-8fc3-4874-84aa-3a2c09f73b65 |  | checkpoint | Consider square stopping, slimlines, joints checked & acceptable
checkpoint-status | c40d6ea4-fcbe-4aa6-850d-2772a29bd671 |  | checkpoint | Correct compound(s) used to align with consented specifications
checkpoint-status | 07a74464-91d3-49f2-9915-9fc29735df6f |  | checkpoint | Adequate drying time between coats, no visible bubbling/deforms & each coat is sanded as applicable
checkpoint-status | f5535cc5-1197-4edd-ab6f-38ab411c037f |  | checkpoint | Light check completed to ensure no sheet joins stand out
checkpoint-status | e177f0dc-50de-4c18-9fc2-f16fa236ec8c |  | checkpoint | Stopping work completed - specified level of finish achieved
checkpoint-status | 3a1ed4bf-ea86-4dd1-9490-92e78eebe299 |  | checkpoint | Cove Installed, checked and acceptable
checklist-flat | 6dc2ab5e-eae7-4f57-8264-43f9c74db1f5 |  | checklist | POST - S - Internal Lining - Walls |  |  |  |  | Yes | POST - S - Internal Lining - Walls | 2c440c5b-7c97-4447-aca0-6a6312b9c751
checkpoint-status | fc7a2cc7-20e6-4069-8277-2e046cb9ec0e |  | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status | b8986e11-a8f1-4328-831a-89d42e11e3b5 |  | checkpoint | Consider bracing, adhesive/sealant & lining layer(s) requirements (consider fire stopping between layers)
text | b8a7b3f5-d4a1-5008-851e-dabd56aff2ff |  | textbox | Specific products used (photos Required)
checkpoint-status | be66f57c-255e-4937-ae2f-678f5b178cfb |  | checkpoint | Services/penetrations, correctly formed & located (consider cut-out tolerances where applicable)
checkpoint-status | c4f7873a-7a4c-44ec-af3a-d4aea2cd059e |  | checkpoint | Correct fixing pattern/sealant (consider fire)/adhesive/layers installed to align with consented design and specifications
checkpoint-status | 5bdbd56e-9a6b-422d-a296-e6ada4f790bb |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status | 64b030ce-84fc-4b52-b2d9-33d7bdfcf586 |  | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checkpoint-status | 9806f700-d947-4fca-a419-4d7a75a226cc |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | e75e1b64-358d-4f27-8fac-4d05fec78a48 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | e8f79a7d-cef3-41e3-bd53-f08bb9dc8907 |  | checklist | SYS - Fixing (Lining) |  |  |  |  | Yes | QA Fixing (Lining) - (V1) | 409f71a6-65f4-4f48-8aef-50e1b4a03e15
checkpoint-status | a13f2e62-9f3d-433a-8b81-5a39faac294a |  | checkpoint | Area accessible and substrate acceptable and approval to start fixing
boolean | cf51cf0f-454f-4382-9b55-8b6634b574af |  | tickbox | Exterior Cladding completed
boolean | e82c0b6a-ae9a-4eac-b5dd-02808fb93aac |  | tickbox | Joinery installed
boolean | 409c532e-2f16-4ff4-911e-578e8904765d |  | tickbox | Doors liners installed including cavity sliders
boolean | e7949516-a4f4-4f2e-9f67-fdbd834aac04 |  | tickbox | Metal ceiling battens running in the same direction and in consideration of critical light
boolean | b82a27b3-3f70-469a-9271-099b441f3efa |  | tickbox | No missing hangers or clips on Metal ceiling battens
boolean | 0f1287cb-1a63-4890-8f9e-268e3b69c02f |  | tickbox | No proud screws on any of the metal ceiling battens or wall strapping
boolean | bfab980a-81c6-4547-9fca-a00241cdb296 |  | tickbox | Wall angle fixed off completely and corners fixed
boolean | 8d14d4df-9a09-4a23-846b-4ed440ebd842 |  | tickbox | All battens secure
boolean | b76a033e-0f55-4553-a011-3ad131545e1e |  | tickbox | Batten joins offset
checkpoint-status | 2d24e1af-c88e-4fae-87d7-b0ad0b9e25f8 |  | checkpoint | Fire rating, bracing elements and wet areas are screwed off to manufacturers specifications and have been checked against plan
checkpoint-status | 421378e9-1618-4b4b-843f-1a6321c5e5f2 |  | checkpoint | All sheets have had centre screws on packers
checkpoint-status | 535c19b7-2b68-413f-b64a-805cb8b9f892 |  | checkpoint | Butt joins, ceiling taper edges and stairwell taper edges are back blocked as per guidelines
checkpoint-status | 0c5788e4-d98f-4d45-9c55-4af0a700d608 |  | checkpoint | Pipes are market on the face of the sheet. Wires within nailing distance marked
checkpoint-status | b4a49a48-e26d-47e6-8b48-3514e4e716ee |  | checkpoint | All plugs and penetrations have been cut neatly and correctly
checkpoint-status | 7e5ffa2a-6bdd-48f6-aca9-e00816805654 |  | checkpoint | All plasterboard correctly fitted
checkpoint-status | 9b39b0fe-3f56-4a8a-bbb2-138bba7d4961 |  | checkpoint | All sheets 5-10mm above floor (unless specified)
checkpoint-status | ebf8173f-7b00-4ed7-b44c-b682fd197553 |  | checkpoint | Site left clean and tidy (attach photos)
checkpoint-status | d48b68da-76fb-4006-b282-0293f266f202 |  | checkpoint | Work Completed as per specifications
boolean | 0ae3c80b-96d7-4635-88a9-a6d8a01ded9f |  | tickbox | All work completed to GIB Site Guidelines
boolean | e30416d8-f783-4e57-87e6-0d5b338ed12e |  | tickbox | Council inspection completed and approved to continue with work
holdpoint | 96ac23e7-1803-4a8b-9e3a-b7cac50ad6c9 |  | signoff | Request Sign off
checklist-flat | 41e1b895-fa3c-4cb1-9ab4-19d5bd870c69 |  | checklist | Stopping (Plaster) |  |  |  |  | Yes | QA Stopping (Plaster) - (V2) | 551a4e88-8d9a-419a-b169-075caa50f204
checkpoint-status | 719cd07c-9290-4912-9975-24b683d0431c |  | checkpoint | Stopping (Plaster) Prestart - Area accessible and substrate acceptatble and approval to start stopping
boolean | 5cc6f702-96ec-40df-a7f6-3a6d9ce0a6d2 |  | tickbox | No proud screws
boolean | ca58257b-13f7-479f-81ee-bee294ed8a0a |  | tickbox | No overdriven screws
boolean | f63cfd13-2bdc-4fce-bc2f-4efcbe342763 |  | tickbox | All areas of broken GIB dug out and ready for pre-filling
boolean | 026b16d7-2dec-412b-8ea3-d292dbe2802c |  | tickbox | Sheets layout correct and in consideration of critical light
boolean | 5407dac8-0bc4-4a53-86bb-f472a30ee34a |  | tickbox | All joins as per GIB site Guide above windows and doors etc
checkpoint-status | c2c16d75-faa0-47f2-8c84-a9bc0ebdb7c8 |  | checkpoint | Screws adequately covered
checkpoint-status | 067bbd19-14ba-4340-a676-3387066ad396 |  | checkpoint | Joints flat and level
checkpoint-status | 484fe5a4-d628-45d2-ad6a-2506acbb096a |  | checkpoint | Square stop and corner joints square/ straight to the eye
checkpoint-status | 82ab8105-dda7-45fc-abda-2f8052135f88 |  | checkpoint | Floors scraped clean
checkpoint-status | 9163d280-0442-469e-85ed-59622b51b04b |  | checkpoint | All slimlines, J-moulds, negative detail or any other finishing completed plumb, level square and straight to the eye
checkpoint-status | 676093b6-6413-47e8-a4bb-7b8a8d079380 |  | checkpoint | Light check completed
holdpoint | 1a709aaa-1b54-4c8e-b24b-2fbcdebe4723 |  | signoff | Request Sign Off
checkpoint-status | 40ca2016-9176-49b9-b3e9-47def74e8048 |  | checkpoint | Materials to be picked up from site & Site left clean and tidy (attach photos)
checkpoint-status | b22fd41e-fe4f-47a0-b9be-20495da79b79 |  | checkpoint | All stopping works completed as per specifications
boolean | a3b287f7-a16e-47fd-8735-e378ac3cc9c0 |  | tickbox | All work completed to GIB® Site Guidelines
checkpoint-status | 9911137a-32d5-4e36-a667-16c5d675126c |  | checkpoint | Cove installed checked and acceptable
boolean | 7f22a647-69fd-488f-bc60-a333ed156dd9 |  | tickbox | GIB Cove joints acceptable
holdpoint | f4eee996-8ebc-4e16-8364-42d66eba14fb |  | signoff | Request Sign Off
checklist-flat | 18cd4f05-0731-48f9-9acf-bd643813a35f |  | checklist | Completion Documents - |  |  |  |  | Yes | Completion Documents - (V1) | 688bdb8b-be66-4fba-a160-9a7aa5694c10
checkpoint-status | 22a7776a-a8fe-4491-be71-334af4b5c84e |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | 0d759c4d-0a75-4623-8eaf-e2b901372ec5 |  | button | LBP Memorandum/ Record of works filled out, signed and attached | YES, N/A
button | d4086758-f5c8-4a9f-bd52-f10d5d32e15d |  | button | Any Additional Compliance Documentation - Completed and Attached | YES, N/A
label | 91e77982-aa3f-49fa-a74f-9d5e42a16e0e |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | 69913102-3ca1-4081-b1e6-af94686e4ac7 |  | signoff | Request Signoff
checklist-flat | ea684077-7520-41af-9baf-0923c2547f92 |  | checklist | POST - S - Stopping |  |  |  |  | Yes | POST - S - Stopping | 6fbdc756-30bf-495e-ac34-d31ef389c6d0
checkpoint-status | 08bd7c44-59db-42f0-903b-e6bb2938b977 |  | checkpoint | Consider fire stopping between layers of lining & apply compound(s) as specified
checkpoint-status | ab8d2c78-1e19-4f55-9d38-cc76ae0f8837 |  | checkpoint | Openings/penetrations/corners & bulkheads, correctly formed (consider tolerances where applicable)
checkpoint-status | 775ff90e-9a1a-4240-88fb-57ddf016821c |  | checkpoint | Consider square stopping, slimlines, joints checked & acceptable
checkpoint-status | a7857cce-d2ae-49bf-90b1-f0e9d5ae7751 |  | checkpoint | Correct compound(s) used to align with consented specifications
checkpoint-status | 0e463c79-8ac9-4e43-9ea7-b01ef5ca705c |  | checkpoint | Adequate drying time between coats, no visible bubbling/deforms & each coat is sanded as applicable
checkpoint-status | 388a172b-71b8-4703-9b89-fe439bed660f |  | checkpoint | Light check completed to ensure no sheet joins stand out
checkpoint-status | 3c1db7ef-a824-4cae-9f75-50fd64b90134 |  | checkpoint | Stopping work completed - specified level of finish achieved
checkpoint-status | 4198e8df-9633-453c-9ca2-d2585908953f |  | checkpoint | Inspections completed and issued to Foreman
holdpoint | 950eea3c-7386-41c3-a5c0-6951832af331 |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat | 3149d09d-45a7-43c3-8935-115405ee8199 |  | checklist | POST - S - Internal Lining - Ceilings |  |  |  |  | Yes | SYS - POST - S - Internal Lining - Ceilings (old version) | b31c39a1-8ab7-460e-86a6-9dd453ca1b3f
checkpoint-status | 1441e155-3f6f-4d39-8a1a-3f7bd7e84cdd |  | checkpoint | All preline services & passive fire (where required) completed, area accessible and substrate acceptable
checkpoint-status | 62bdf606-1ad7-4f8a-953f-5ca6221f1d9e |  | checkpoint | Consider bracing, adhesive/sealant & lining layer(s) requirements (consider fire stopping between layers)
checkpoint-status | 6e8bcb45-353c-40c4-8ea7-8a55a37e876a |  | checkpoint | Services/Penetrations, correctly formed & located (consider cutout tolerances and access hatches (location & size) where applicable)
checkpoint-status | 66bb9d9b-bb0c-413f-9c9f-a1d6b314f490 |  | checkpoint | Correct fixing pattern/sealant (consider fire)/adhesive/layers installed to align with consented design and specifications
checkpoint-status | 39a4a572-e1df-4e0a-b7f7-a70213a71b2e |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status | caf5b50c-af30-42db-9b22-1413763bc9b9 |  | checkpoint | All lining(s) completed correctly to specification & level of finish acceptable in respective area(s)
checklist-flat | cf325850-ce3b-43b3-bffe-d6d32bd2e46a |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | cb9dcef6-4abc-4873-9948-96d433163fbe
checkpoint-status | 52b0e5ea-c000-489c-9ed7-2d6e60b21199 |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | 03217161-4788-5048-9ab0-cf2c1844016e |  | tickbox | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | f7d600d8-ff9c-56ca-8bb5-8eba6c5c463e |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | 1c6f68f4-050b-4787-9f60-e748eb4d8c5d |  | signoff | Request Signoff
checklist-flat | b86918d2-cca2-4d9c-b41a-386077c6b15e |  | checklist | Fixing (Lining) |  |  |  |  | Yes | QA Fixing (Lining) - (V2) | d71131d0-b9b3-4111-8bbd-cc427d877df6
checkpoint-status | a0fb46f0-d766-4e80-9165-291b7c5be12a |  | checkpoint | Area accessible and substrate acceptable and approval to start fixing
boolean | 31b05077-74dd-47fe-bf1b-57762d8e5309 |  | tickbox | Exterior Cladding completed
boolean | 22010254-0e03-4be0-a557-3a037a280ec2 |  | tickbox | Joinery installed
boolean | 3468ff2e-0d14-4b00-8c6b-dfa4a8911b58 |  | tickbox | Doors liners installed including cavity sliders
boolean | cbb950a1-f75e-46a1-bd0a-0e127c2b9c23 |  | tickbox | Metal ceiling battens running in the same direction and in consideration of critical light
boolean | 4a69df85-ffa1-4fd1-8a4c-24be8ff219c8 |  | tickbox | No missing hangers or clips on Metal ceiling battens
boolean | de68dd70-5eb3-46e9-af23-4224b7e89b5a |  | tickbox | No proud screws on any of the metal ceiling battens or wall strapping
boolean | 12719fd5-3c33-453e-8353-1e42abbaa676 |  | tickbox | Wall angle fixed off completely and corners fixed
boolean | ac2e97bd-e69c-4852-ad61-a099771e01b5 |  | tickbox | All battens secure
boolean | 0b389032-c00c-4e58-8f33-11f7b918b5f5 |  | tickbox | Batten joins offset
checkpoint-status | 8a8bcc4b-12a9-4d1e-b287-73e1088c493a |  | checkpoint | Fire rating, bracing elements and wet areas are screwed off to manufacturers specifications and have been checked against plan
checkpoint-status | c3c2a809-944b-4259-8d0e-5a2d0993e55d |  | checkpoint | All sheets have had centre screws (Photos attached)
checkpoint-status | 71770865-e716-41ea-a1a2-b5fced9d40fc |  | checkpoint | Pipes are marked on the face of the sheet. Wires within nailing distance marked
checkpoint-status | e57abf61-4fbe-42bb-a93f-0368e03ffd53 |  | checkpoint | All plugs and penetrations have been cut neatly and correctly
checkpoint-status | 0890c42d-e18e-47bd-9493-c7ec871fc8bd |  | checkpoint | All plasterboard correctly fitted
checkpoint-status | bef22f41-25be-4622-9d00-cb64486084f3 |  | checkpoint | All sheets 5-10mm above floor (unless specified)
checkpoint-status | 710879f9-5e6b-40cd-a068-4a72b16a807f |  | checkpoint | Site left clean and tidy (attach photos)
checkpoint-status | 0aee5acf-18fc-4dd2-867e-5e2a8d01d374 |  | checkpoint | Work Completed as per specifications
boolean | d0b91b12-ef24-47d2-8cbb-79710f0d3114 |  | tickbox | All work completed to GIB Site Guidelines
boolean | 753e7fc5-fac6-46df-9d16-f4e6078e9cce |  | tickbox | Council inspection completed and approved to continue with work
holdpoint | 1f47db07-6dd7-4cc4-956d-c8d293dec332 |  | signoff | Request Sign Off