## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | f4606171-cf94-4d6a-b8a7-530ab413ade7 |  | checklist | Intumescent for Area: |  |  |  |  | Yes | QA - Intumescent Paint | 1f60aa10-493e-4aa4-94a3-eca809367001
checkpoint-status | 73d3f1bd-c7ff-4e7b-8ac3-b3253319e324 |  | checkpoint | Specification & mark-up received & reviewed
checkpoint-status | b7590295-5ebf-44a5-a619-686467de5269 |  | checkpoint | Q.A. from steel fabricator received & reviewed
checkpoint-status | 56b8541f-cf2c-4f46-afe1-ccc073ef9f4c |  | checkpoint | Cleaning/washing of substrate
checkpoint-status | 956ded6a-4921-4b90-9dc0-3ccf126263c5 |  | checkpoint | Substrate acceptable
checkpoint-status | 3e85708e-40a2-4271-9802-1f841021df03 |  | checkpoint | Base DFT readings on primers
checkpoint-status | 0058b69c-a2df-48a3-b2be-bcfe10ac2d54 |  | checkpoint | Intumescent applied
checkpoint-status | 9e7f5fc8-d965-44a2-af32-23f98cfe92c2 |  | checkpoint | Dry film inspection completed
checkpoint-status | aa8692b2-ddf7-49eb-bae4-b6cba705d467 |  | checkpoint | Topcoats applied in accordance with specification
checklist-flat | b3a6cd26-05a5-4ad5-bdca-3e0b6be8e4e8 |  | checklist | Miscellaneous/Attach Drawings |  |  |  |  | Yes | Miscellaneous/Attach Drawings | 7b2b96ab-2e8d-4a06-ac71-17e12338886b
checkpoint-status | 1c625852-8607-4a67-b7d6-8697d8946d9c |  | checkpoint | Document Attached
checklist-flat | dd3f2e14-78ab-4b9b-bca2-310af0a2a088 |  | checklist | Variation # |  |  |  |  | Yes | Variation # | a2168b26-984f-44fe-be5f-3c67a35aa73c
checkpoint-status | cf50e155-6423-439f-ab06-f00bbcc56e30 |  | checkpoint | Variation completed with photos of work
text | 925806c4-b4cf-5c7a-9e24-33669f4c117a |  | textbox | Details (Level/Unit/Area)
text | 3d7554eb-6c5e-5869-b380-7774ef2ff50b |  | textbox | Hours/Minutes
checklist-flat | ccb50b26-22b8-436e-b31e-3c93257e1184 |  | checklist | QA - Interior Painting |  |  |  |  | Yes | QA - Interior Painting | a6358122-fedb-4649-848c-fb503fa6d668
checkpoint-status | 99ed6a60-000e-4bf1-a83d-8dbb59923aa9 |  | checkpoint | Area accessible, substrates acceptable
checkpoint-status | e4204b86-7ac5-406a-ab45-40753df2e06d |  | checkpoint | Plaster work complete to lifting eyes, drossbachs & defects
checkpoint-status | 9a085231-5638-4fdd-8829-7ff3ff7302d5 |  | checkpoint | Stopping complete
checkpoint-status | 015c518d-12a0-4598-9c8a-ec832c646f7e |  | checkpoint | Washing complete
checkpoint-status | f89db632-4ab7-41db-b44a-9b59fb87fd27 |  | checkpoint | Approval given to paint
text | d98df7a9-fe71-58ae-b597-d172e1d9f0b2 |  | textbox | Who has given approval to paint
checkpoint-status | ce4e919e-a6e9-4a60-ad04-fdf315383d31 |  | checkpoint | Paint specifications and colour checked & correct to specification
checkpoint-status | f7362fcd-5953-4388-937c-9272adb35930 |  | checkpoint | First coat/ sealant coat completed
checkpoint-status | a03ec492-4115-4dbc-ac0d-66d8c2950244 |  | checkpoint | Light inspection completed and approved to continue
label | 5198f252-baf0-5755-b361-d6f603d59d1e |  | note | Any issues "FAIL" and document remedial work - "Pass" once completed
checkpoint-status | 7da3bc1d-9871-45a3-b0ee-7af07b6d6ea6 |  | checkpoint | General comments and photos of additional paint application
checkpoint-status | 42a9865b-e885-4c67-9531-301fb9783640 |  | checkpoint | Final coat completed, no overpainting, finish acceptable as per specification
holdpoint | 0b773e31-2639-47b1-a3c6-9131f25f54db |  | signoff | Request Signoff
checklist-sectioned | 010c6b64-c925-4d30-ad10-8c7908f73af5 |  | checklist | QA - Painting |  |  |  |  | Yes | QA - Painting | e2776441-7ab2-4dff-b6f8-d2baaabedb8e
checkpoint-group | d073c74c-0ea0-4e29-9d42-5b6569f0ff8e |  | section | Precommencment
checkpoint-status | 03b8572c-de40-4e90-b3b4-1de456704243 |  | checkpoint | Handover from Stopping crew
checkpoint-status | a261e6ae-8df9-4c74-96c3-acbca1a271f1 |  | checkpoint | Work area clean & tidy
checkpoint-status | 553a9166-2346-4c87-a81a-35265e2ca7b5 |  | checkpoint | Skirting doors & Architraves installed
checkpoint-status | 56dcb1b0-4e29-4046-92e3-1c4799ba7897 |  | checkpoint | Architrave mitres sanded flush
checkpoint-group | d0bcd248-6962-42f2-9eb3-f99f87c7cf8a |  | section | Sealer coat
checkpoint-status | 7220757c-32e9-4151-9c33-8f0f2313b16d |  | checkpoint | Apply Sealer coat to walls, ceiling & trims
checkpoint-status | 9b7f6d16-269d-43f5-b979-8e8c92630db4 |  | checkpoint | Handover back to Stopping crew for 1st QA light check surfaces for stopping defects.
checkpoint-status | 2e4dc5f3-9eb9-4ef3-8259-f77bdb796858 |  | checkpoint | Handover from Stopping crew
checkpoint-group | e7c74898-e833-415f-9ef1-d54907768d32 |  | section | First Coat
checkpoint-status | c663c7b7-d81e-4b90-923e-9e83c5c0ee62 |  | checkpoint | Apply first coat of colour to walls, Ceilings & timber trim.
checkpoint-status | 0fd1ec33-2d4a-4fbf-baa4-16e65ea474b3 |  | checkpoint | 2ND QA check surfaces for stopping defects corrected by Stopping crew
checkpoint-status | a3d7d41e-45bc-41ab-9bdb-f90f1e5b80da |  | checkpoint | Surfaces free of defects – Accept hand over from Interiors team
checkpoint-status | e0b70926-007b-42d7-a741-b2000b041def |  | checkpoint | Apply x2 topcoats to ceiling
checkpoint-status | eb22d4d9-2eb6-4abf-ad78-cfe83cac6507 |  | checkpoint | Apply 1st Coat to walls, doors & timber trim
checkpoint-group | 35ae50e5-bb10-4fa4-ae18-cf563701e2c9 |  | section | Final Coat Trims
checkpoint-status | d5919a0b-eef9-4118-8fdf-932a11ccd0e9 |  | checkpoint | Final coat timber doors, architraves, skirtings & window frames
checkpoint-status | f5851391-1cf3-47e8-a3aa-2ad82f1ffc33 |  | checkpoint | Apply final topcoat to timber doors, architraves, skirtings & window frames.
checkpoint-status | 409efc68-c8ff-4586-b788-4e6fddd7f03a |  | checkpoint | Light check walls in preparation of final coat
checkpoint-group | b9b2c3d0-ab33-4e1a-afe3-b250973d1ac0 |  | section | Final Coat Walls
checkpoint-status | a8f7d400-c21f-4e06-b4d4-58e49404ae3a |  | checkpoint | Apply final coat on walls.
checkpoint-status | 18950d79-24b3-4a44-a310-2cab75e2b48e |  | checkpoint | Notification signage in place notifying final coats have been applied.
checkpoint-status | 260eaa59-8617-4750-9efe-c1ac19b13024 |  | checkpoint | Completion check, rectify defects
label | 2446cae7-8606-5918-b2c7-16ab84ec7b2d |  | note | Touch ups / Extras identified & agreed
label | b355b555-a698-59ff-861c-7c4c81b58e3b |  | note | Touch ups/ Extras completed