## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-007 - Concrete Track Slab Pour | itp |  |  |  |  | ITP-007 - Concrete Track Slab Pour Rev2
section | 1 - Preliminary Works
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Ensure that all employees and subcontractors are:
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.2 Submission & Approval of Concrete Mix Design Prior to Commencement of Project
note | FREQUENCY: Prior to first concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Concrete mix design submitted and approved at least 2 weeks prior to first pour.
note | • Mix shall be minimum 460 kg/m3 cement content (for special 50 mix).
note | • Concrete shall be manufactured, transported and handled in accordance with the requirements of AS 3600 & AS 1379
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Mix Design ITP
note | – – – – – – – – –
note | HP*
note | – – – – – – – – –
note | RESPONSIBILITY: FH Engineer / Superintendent
note | – – – – – – – – –
textbox | DATE:
section | 2 - Construction Works
checkpoint | 2.1 Weather Monitoring
note | FREQUENCY: Prior to start
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Placing of concrete shall not occur while ambient air temperature is <5°C or > 35°C without permission of the Superintendent
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.10
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | HP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
note | – – – – – – – – –
textbox | DATE:
holdpoint | HOLD POINT AUTHORITY
checkpoint | 2.2 Surface Preparation
note | FREQUENCY: Prior to start
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Crush rock surfaces shall be moist and thouroughly cleaned of all foreign and loose matter prior to pour
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer / Foreman
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.3 Setting Out
note | FREQUENCY: Prior to start
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Set out work in accordance with drawings, concrete shall be constructed accurately to these specifications.
note | • No survey/level pegs to be removed by any persons until completion of works.
note | • Screed heights shall be set out to achieve the design levels specified in the drawings, and the correct pavement layer thickness
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.4 Preliminary Works Formwork
note | FREQUENCY: Prior to start
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Formwork shall be straight, free from kinks and bends, and shall be secured to eliminate possibility of movement during concrete placement.
note | • The formwork shall be placed true to shape, alignment, grade and level to the concrete shown in the construction drawings.
note | • Forms shall not be stripped until the concrete has hardened to the satisfaction of the Superintendent
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.9
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.5 Reinforcement
note | FREQUENCY: Where Required
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Ensure that all reinforcement is placed as specified by construction drawings.
note | • All placed reinforcement shall be clean and free from grease, tar, oil, paint, mud, loose or thick rust, etc.
note | • Reinforcing fabric sheets shall be handled so that they remain free from distortion. They shall be lapped and tied with wire at a maximum spacing of 500 mm.
note | • Reinforcement shall be terminated 75 to 80 mm from dowelled contraction joints.
note | • Reinforcement shall terminate at least 40 mm and not more than 80 mm from longitudinal construction joints, or pavement edges.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.7
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.6 Dowels
note | FREQUENCY: Where Required
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Ensure that all dowels are placed as specified in the construction drawings
note | • All dowels shall be one-piece, straight, plain round steel bars complying with the requirements of AS 1302 and of the size shown on the drawings
note | • Dowels shall be clean and free from mill scale, loose rust or oil.
note | • Ensure that all dowels are securely held in their correct position until the concrete has set.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.8
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.7 Pre Pour Inspection
note | FREQUENCY: Prior to start
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Verification of track gauge calibration; a site test shall be conducted by checking measurement accuracy in a 180 degree diference in gauge placement
note | • Verification of track geometry, heights and levels shall be ascertained by inspection of track and underlying structure
note | • Contractor and Superintendent shall verify dimensions, levels and alignments of all formworks, reinforcement, rail levels, rail joint welding, track bonding, track drainage are satisfactory
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Inspection / Test Method
note | – – – – – – – – –
note | RECORD OF CONFORMITY: FH Track Inspection
note | – – – – – – – – –
note | HP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer / YT Superintendent
note | – – – – – – – – –
textbox | DATE:
holdpoint | HOLD POINT AUTHORITY
checkpoint | 2.8 Preliminary Works Carry out sampling of concrete
note | FREQUENCY: Each concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | Slump:
note | ○ Concrete Slump shall be 100mm +/-20 Compressive Strength:
note | • Shall be measured in accordance with CE-019-ST-0033
note | ○ Testing frquency =
note | • 0-50m3, 1 sample
note | • 50-100m3, 2 samples
note | • 100m3+, 3 samples
note | ○ Each sample shall consist of 4 cylinders
note | ○ Test Results will be provided to the Superintendent
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5 & 4.7.18.4
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Concrete supplier test sheet
note | – – – – – – – – –
note | TP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer / Superintendent
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.9 Concrete Placement
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Ensure formwork is clean
note | • Concrete shall be entirely discharged 60 minutes after batching,
note | • Ensure that pouring does not occur from a height greater than 1200mm
note | • Concrete shall be placed outside each of the tracks before placing the concrete between the tracks. Each part shall be poured as a monolithic section in one continuous operation
note | • The Contractor shall ensure that there is a minimum of 125 mm under the foot of the rail for the placement of new concrete. If this cannot be achieved, then SL82 reinforcement shall be placed under the foot of the rail with at least 50 mm coverage.
note | • There shall be no addition of water or any other material to the concrete at the site without the approval of the Superintendent.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.6
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.10 Compaction
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Immediately after concrete placement, compaction shall take place with an approved vibrator
note | • Vibration shall take place until exposed concrete surface is free from air voids
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.11 Record location of each batch
note | FREQUENCY: Each concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Batch location recorded and noted on CL001D Load Batch Traceability
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Checklist
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.12 Curing
note | FREQUENCY: Each concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Special 50 MPa Concrete' is to be cured a minimum of five hours after last load placed, prior to tram services resuming concrete less than 4 hours old shall be protected by covering with waterproof covers where appropriate (concrete to surface).
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.5
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Checklist
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.13 Tolerances
note | FREQUENCY: Each concrete pour
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | All concrete shall finish true to the dimensions, the following tolerances apply:
note | • Plan dimension of slab +10,-10mm
note | • Thickness of slab +10,-10mm
note | • Cover to reinforcement +5,-3mm
note | • Finished level of slab +3,-3mm
note | • Foundation level of slab +0,-20mm
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.16
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Checklist
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.14 Preliminary Works Slab finish
note | FREQUENCY: Where appilcable - if track is Type 1 structure
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Slab surface shall be uniformly level, flat and free from bumps, hollows and other irregularities.
note | • All exposed concrete surfaces shall be true, even and free from stone pockets, depressions and projections.
note | • A groove shall be formed along the running edge of each rail in accordance with Standard Drawing STD_T9010 Rev. C.
note | • The slab surfaces shall be broomed to provide a non-slip finish.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL 4.7.17
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Checklist
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.15 Post Pour Inspection
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Ensure finished surface of concrete is of high standard, with a uniform and level surface in accordance with pavement thickness and levels specified in the drawings
note | • Ensure no defects are present in slab
note | • Complete Fulton Hogan Post Pour Checklist
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Post pour checklist
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications
text | Print Name:
text | Position:
text | Date: