## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-001 - Subgrade Preparation | itp |  |  |  |  | ITP-001 - Subgrade Preparation Rev2
section | 1 - Preliminary Works
checkpoint | 1.1 Prior to commencing any activity
note | FREQUENCY:
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Ensure that all employees and subcontractors are:
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Visual Inspection
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan
note | – – – – – – – – –
textbox | DATE:
checkpoint | 1.3 Selection and approval of Disposal Site
note | FREQUENCY: Prior to commencing any activity
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Material removed from the site for disposal shall be moved to a site conforming to all statutory requirements & in accorance with Yarra Trams site classification report.
note | • It shall be the Contractor's responsibility to locate a site and to arrange with and obtain permission from the Authorities controlling disposal of material at that location.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: Site Classification Report, CE-019ST-0033 CL. 4.2.1.5.
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP signed off
note | – – – – – – – – –
note | WP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan
note | – – – – – – – – –
textbox | DATE:
section | 2 - Construction Works
checkpoint | 2.1 Excavation
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Plant and equipment shall be appropriate for the task.
note | • Excavation operations shall not disturb areas outside the limit of works
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.1.3., 4.2.4. Subgrade Preparation Work Procedure
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.2 Reinstatement of bonds
note | FREQUENCY: –
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • Extreme care shall be taken when excavating near bonds connected to electrical assets or negative feeder cables.
note | • All bonds excavated during track repair or earthworks shall be reinstated as per the relevant Standard Drawing.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.4.1.
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan
note | – – – – – – – – –
textbox | DATE:
checkpoint | 2.3 Inspection of Subgrade Material
note | FREQUENCY: Each lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA: Soft areas identified by the Superintendent shall be removed and replaced with approved fill and compacted in accordance with the Standard.
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.5.1.
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Verify
note | – – – – – – – – –
note | RECORD OF CONFORMITY: This ITP Signed Off
note | – – – – – – – – –
note | HP
note | – – – – – – – – –
note | RESPONSIBILITY: Fulton Hogan Engineer & YarraTrams Superintendent
note | – – – – – – – – –
textbox | DATE:
holdpoint | HOLD POINT AUTHORITY
checkpoint | 2.4 Width and Level conformity
note | FREQUENCY: Each Lot
note | – – – – – – – – –
note | ACCEPTANCE CRITERIA:
note | • The finished surface level of the completed formation shall not vary more than 25 mm above or below the levels shown on the drawings.
note | • No point in the general surface shall vary more than 12mm from a 3m straight edge.
note | • Finished formation widths shall not vary more than - 0 mm, + 50mm from dimensions shown on the Drawings
note | – – – – – – – – –
note | REFERENCE DOCUMENTS: CE-019-ST-0033 CL. 4.2.2.
note | – – – – – – – – –
note | INSPECTION/TEST METHOD: Survey Report
note | – – – – – – – – –
note | RECORD OF CONFORMITY: Survey Record
note | – – – – – – – – –
note | IP
note | – – – – – – – – –
note | RESPONSIBILITY: Surveyor/ Fulton Hogan Engineer
note | – – – – – – – – –
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: