## Cambridge Stage 3
Cambridge
Stage 3 (B50 - B55)
|  | B50 |  | Pre Wire | Area is left clean and tidy, and approval to start work is obtained
|  |  | Townhouse Unit 16 |  | Internal cabling complete
|  |  | Townhouse Unit 18 |  | Main cabling complete (Photos Attached)
Building entry point (Photos Attached)
|  | B51 |  |  | Fire boxes installed (Photos Attached)
|  |  | Townhouse Unit 20 |  | Flush boxes installed
|  |  | Townhouse Unit 22 |  | Sub-reticulation installed (Attach Photos)
Townhouse Unit 24
Townhouse Unit 26
|  |  | Plinth 5 Commissioning | Termination and Testing | Area is left clean and tidy, and approval to start work is obtained
Install DB
|  | B52 |  |  | Fit off DB (Photos Attached)
|  |  | Townhouse Unit 28 |  | LAN test internals (Add signature)
Townhouse Unit 30
Townhouse Unit 32
|  |  | Townhouse Unit 34 | Fit Off | Area is left clean and tidy, and approval to start work is obtained
TV/DATA Fit Off (Photos Attached)
|  | B53 |  |  | Nurse Call Fit Off (Photos Attached)
|  |  | Townhouse Unit 31 |  | Smoke Alarms and CO detectors (Photos Attached)
|  |  | Townhouse Unit 33 |  | 6 core Fibre spliced (Photos Attached)
Townhouse Unit 35
Townhouse Unit 37
|  |  |  | Plinth Commissioning | Nurse Call Terminated (Photos Attached)
|  | B54 |  |  | MATV Terminated (Photos Attached)
|  |  | Townhouse Unit 23 |  | Fibre spliced (Photos Attached)
|  |  | Townhouse Unit 25 |  | Power Supply installed (Photos Attached)
|  |  | Townhouse Unit 27 |  | Krone module terminated (Photos Attached)
Townhouse Unit 29
Plinth 7 Commissioning
B55
Townhouse Unit 15
Townhouse Unit 17
Townhouse Unit 19
Townhouse Unit 21