## Shoreline Surfers ITP
QA Folder Structure |  |  | Checklists
Site QA
GROUND
|  | DETENTION TANK | Trafficable Liquid Membrane Checklist
|  | WATER METER HYDRANT METER | Trafficable Liquid Membrane Checklist
|  | LIFT LOBBY | External Liquid Membrane Checklist
|  | ENTRY HALL | External Liquid Membrane Checklist
|  | EXPOSED TERRACE | Balconies Checklist
LEVEL 01
|  | PLANTER | Planters Checklist
|  | SERVICE | Trafficable Liquid Membrane Checklist
|  | BO | External Liquid Membrane Checklist
LEVEL 02
|  | PLANTER | Planters Checklist
|  | SERVICE | Trafficable Liquid Membrane Checklist
|  | BO | External Liquid Membrane Checklist
LEVEL 03
|  | PLANTER | Planters Checklist
|  | BALCONY | Balconies Checklist
|  | POOL | 2 Coat Checklist
|  | SERVICE | Internal Wet Areas Checklist
|  | PWD | Internal Wet Areas Checklist
|  | BATH | Internal Wet Areas Checklist
|  | L/DRY | Internal Wet Areas Checklist
|  | ENS | Internal Wet Areas Checklist
|  | PDR | Internal Wet Areas Checklist
|  | PDR | Internal Wet Areas Checklist
|  | L/DRY | Internal Wet Areas Checklist
|  | BATH | Internal Wet Areas Checklist
|  | ENS | Internal Wet Areas Checklist
LEVEL 4
|  | BALCONY | Balconies Checklist
|  | CONCRETE ROOF | External Liquid Membrane Checklist
|  | BATH | Internal Wet Areas Checklist
|  | L/DRY | Internal Wet Areas Checklist
|  | ENS | Internal Wet Areas Checklist
|  | HYD | Internal Wet Areas Checklist
|  | PDR | Internal Wet Areas Checklist
|  | PDR | Internal Wet Areas Checklist
|  | L/DRY | Internal Wet Areas Checklist
|  | BATH | Internal Wet Areas Checklist
|  | ENS | Internal Wet Areas Checklist
|  | SERVICE | Trafficable Liquid Membrane Checklist
|  | BO | External Liquid Membrane Checklist
LEVEL 5-15
|  | BATH | Internal Wet Areas Checklist
|  | L/DRY | Internal Wet Areas Checklist
|  | ENS | Internal Wet Areas Checklist
|  | PDR | Internal Wet Areas Checklist
|  | PDR | Internal Wet Areas Checklist
|  | HYD | Internal Wet Areas Checklist
|  | L/DRY | Internal Wet Areas Checklist
|  | BATH | Internal Wet Areas Checklist
|  | ENS | Internal Wet Areas Checklist
|  | SERVICE | Trafficable Liquid Membrane Checklist
|  | BALCONY | Balconies Checklist
LEVEL 16
|  | SAUNA | Internal Wet Areas Checklist
|  | WELLNESS | Internal Wet Areas Checklist
|  | SPA | Internal Wet Areas Checklist
|  | PWD | Internal Wet Areas Checklist
|  | BALCONY | Balconies Checklist
|  | HYD | Internal Wet Areas Checklist
|  | PDR | Internal Wet Areas Checklist
|  | L/DRY | Internal Wet Areas Checklist
|  | BATH | Internal Wet Areas Checklist
|  | ENS | Internal Wet Areas Checklist
|  | SERVICE | Trafficable Liquid Membrane Checklist
LEVEL 17
|  | MASTER BALCONY 1 | Balconies Checklist
|  | BALCONY 2 | Balconies Checklist
|  | BALCONY 3 | Balconies Checklist
|  | ENS 1 | Internal Wet Areas Checklist
|  | DRYING ROOM & IRONING | Internal Wet Areas Checklist
|  | L'DRY | Internal Wet Areas Checklist
|  | BATH | Internal Wet Areas Checklist
|  | PDR | Internal Wet Areas Checklist
|  | ENS 4 | Internal Wet Areas Checklist
|  | SERVICE | Trafficable Liquid Membrane Checklist
ROOF
External Liquid Membrane Checklist

## Master ITPs Checklists
type | name | values | prefix | postfix
checklist-flat | 3 Coat Checklist
checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint | Moisture test complete - result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint | Application of Primer as per specification
checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint | Application of membrane as per project specification - 1st Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint | Application of reinforcement sheet (if pedestal pavers)
checkpoint | Application of membrane as per project specification - 2nd Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint | Application of membrane as per project specification - 3rd Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint | Additional products / elements installed - selected all that apply below
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
checkpoint | Final DFT Thickness of Membrane
checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint | Test 1 Flood Test
checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat | 2 Coat Checklist
checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint | Moisture test complete - result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint | Application of Primer as per specification
label | Cementious Coving completed (if required)
checkpoint | Application of Caulking / Bond Breaker / Bandage (if required) completed
checkpoint | Application of membrane as per project specification - 1st Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint | Application of membrane as per project specification - 2nd Coat
select | Product Used | Mapei AquaDefense waterproofing membrane,Mapelastic Smart cementitious waterproofing membrane,Mapei Purtop Easy polyurethane waterproofing membrane,Penetron Peneseal FH,PVC Tank Liner,Mapei Mapecoat I24 epoxy flooring,SikaTite WPU,SikaTite 2 Part,Sikalastic 488,Sikalastic 777,Sikalastic 1K,Polyurea,Epoxy flooring system,Mapecoat PU 20N
checkpoint | Additional products / elements installed - selected all that apply below
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
select | Product Used | None,Non slip UV resistant top coat,Corflute protection board,Drainage Cell,Waterstop Angle
checkpoint | Final DFT Thickness of Membrane
checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint | Test 1 Flood Test Pass/Fail
checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat | Screed Checklist
checkpoint | Mixing of Topcem Pronto
checkpoint | Application of Topcem Pronto
checkpoint | Final Walk over and inspection by main contractor, Applicator and Supplier if Applicable.
checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat | PVC Tanks Checklist
checkpoint | Surface conditions suitable for installation - details in comments below
checkpoint | Moisture test complete - result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint | Application of Geofabric to substrate
checkpoint | Application of PVC Sheet Membrane
checkpoint | PVC Sheet Membrane detailing as required
checkpoint | Final Walk over and inspection by main contractor, Supplier and Appliactor if Applicable.
checkpoint | Test 1 Probe Test
checkpoint | Test 2 Air Test Test (if double seam weld is done otherwise revert test 1)
checkpoint | Works completed, area Tidy - builder signature attached below if applicable
checklist-flat | Balconies Checklist
checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint | Moisture test complete-result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate has fall is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint | Application of Primer as per spec
checkpoint | Application of Caulking or Bandage (if required) completed
checkpoint | Application of membrane as per project spec-1st Coat
checkpoint | Application of reinforcement sheet (if pedestal pavers)
checkpoint | Application of membrane as per project spec-2nd Coat
checkpoint | Application of membrane as per project spec-3rd Coat
checkpoint | Final DFT Thickness of Membrane
checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable.
checkpoint | Test 1 Flood Test Pass/Fail?
checklist-flat | External Liquid Membrane Checklist
checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint | Moisture test complete-result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate has fall is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint | Application of Primer (if required) as per specification
checkpoint | Application of Caulking and or Bandage (if required) completed
checkpoint | Application of membrane as per project specification-1st coat
checkpoint | Application of membrane as per project specification-2nd coat
checkpoint | Application of Anti-slip UV stable top coat (if required)
checkpoint | Final DFT Thickness of Membrane
checkpoint | Installation of Corlute Protection Board completed (if required)
checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint | Test 1 Flood Test Pass/Fail
checklist-flat | Internal Wet Areas Checklist
checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint | Moisture test complete-result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate has fall is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint | Application of Primer as per specification
checkpoint | Application of Caulking and or Bandage (if required)
checkpoint | Application of membrane as per project specification-1st coat
checkpoint | Application of membrane as per project specification-2nd coat
checkpoint | Final DFT Thickness of Membrane
checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint | Test 1 Flood Test Pass/Fail
checklist-flat | Planters Checklist
checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint | Moisture test complete-result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate has fall is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint | Application of Primer (if required) as per specification
checkpoint | Application of Cementitious Coving (if required) completed
checkpoint | Application of Caulking and or Bandage (if required) completed
checkpoint | Application of Membrane as per project specification-1st coat
checkpoint | Application of Membrane as per project specification-2nd coat
checkpoint | Final DFT Thickness of Membrane
checkpoint | Installation of Corflute Protection Board Completed
checkpoint | Installation of Drainage Cell Completed
checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint | Test 1 Flood Test Pass/Fail
checklist-flat | PVC Sheet Membrane
checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint | Moisture test complete-result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint | Application of Geofabric to substrate
checkpoint | Application of PVC Sheet Membrane
checkpoint | PVC Sheet Membrane Detailing as required
checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint | Test 1 Probe Test Pass/Fail
checkpoint | Test 2 Air Test Pass/Fail (if double seam weld is done otherwise revert test 1)
checklist-flat | Trafficable Liquid Membrane
checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint | Moisture test complete-result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate has fall, is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint | Application of Primer (if required) as per specification
checkpoint | Application of Cementitious Coving (if required) completed
checkpoint | Application of Membrane as per project specification-1st coat
checkpoint | Application of Membrane as per project specification-2nd coat
checkpoint | Final DFT Thickness of Membrane
checkpoint | Installation of Corlute Protection Board Completed
checkpoint | Installation of Drainage Cell Completed
checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint | Flood Test Pass/Fail
checklist-flat | Windows and Doors
checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint | Substrate has fall (if required) is sound and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
label | Must be below 5% to pass
checkpoint | Application of Primer as per specification
checkpoint | Application of Caulking and or Bandage (if required) completed
checkpoint | Application of Membrane as per project specification -1st coat
checkpoint | Application of Membrane as per project specification-2nd coat
checkpoint | Final DFT Thickness of Membrane
checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint | Flood Test Pass/Fail
checklist-flat | Waterstop-Penebar
checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint | Substrate inspected and accepted. Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed.
checkpoint | Application of Penetron Penebar SW55
checkpoint | Ensure all Butt Joints are completed as per TDS
checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint | Test 1 Probe Test Pass/Fail
checklist-flat | Sika Sarnafil PVC Sheet Membrane Checklist
checkpoint | Surface conditions suitable for installation-details in comments below
checkpoint | Moisture test complete-result in comments below
label | Must be below 5% to pass
checkpoint | Substrate inspected and accepted
label | Substrate must be clean, smooth, dry and free from dust or contaminants. All sharp points and loose material to be removed
checkpoint | Application of Sarnacol Adhesive to substrate
checkpoint | Application of Felt PVC Sheet Membrane
checkpoint | Application of Non-Felt PVC Sheet Membrane
checkpoint | PVC Sheet Membrane Detailing as required
checkpoint | Sarnabar Termination
checkpoint | Final Walk over and inspection by main contractor, Supplier and Applicator if Applicable
checkpoint | Test 1 Probe Test Pass/Fail
checkpoint | Test 2 Air Test Pass/Fail (if double seam weld is done otherwise revert test 1)

## Color Coding
3 Coat Checklist
2 Coat Checklist
Screed Checklist
PVC Tanks Checklist
Balconies Checklist
External Liquid Membrane Checklist
Internal Wet Areas Checklist
Planters Checklist
PVC Sheet Membrane Checklist
Trafficable Liquid Membrane Checklist
Windows and Doors Checklist
Waterstop Checklist
Sika Sarnafil PVC Sheet Membrane Checklist