## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Site QA
| step |  |  |  | Earthworks
| step |  |  |  |  | Anchors
| step |  |  |  |  | Basement 1
| step | [5 empty] | Shoring Piles
Excavation & Shoring | checklist | [6 empty] | Shoring Wall 1
Excavation & Shoring | checklist | [6 empty] | Shoring Wall 2
Excavation & Shoring | checklist | [6 empty] | Shoring Wall 3
Excavation & Shoring | checklist | [6 empty] | Shoring Wall 4
| step | [5 empty] | Sheet Piles
Sheet Pile ITP | checklist | [6 empty] | Sheet Pile Wall 1
Sheet Pile ITP | checklist | [6 empty] | Sheet Pile Wall 2
Sheet Pile ITP | checklist | [6 empty] | Sheet Pile Wall 3
Sheet Pile ITP | checklist | [6 empty] | Sheet Pile Wall 4
Sheet Pile ITP | checklist | [6 empty] | Sheet Pile Wall 5
Sheet Pile ITP | checklist | [6 empty] | Sheet Pile Wall 6
Sheet Pile ITP | checklist | [6 empty] | Sheet Pile Wall 7
Sheet Pile ITP | checklist | [6 empty] | Sheet Pile Wall 8
Sheet Pile ITP | checklist | [6 empty] | Sheet Pile Wall 9
Sheet Pile ITP | checklist | [6 empty] | Crane Base 1
Sheet Pile ITP | checklist | [6 empty] | Crane Base 2
Sheet Pile ITP | checklist | [6 empty] | Lift Pit
| step | [5 empty] | Shotcrete
Shotcrete | checklist | [6 empty] | Shoring Wall 1
Shotcrete | checklist | [6 empty] | Shoring Wall 2
Shotcrete | checklist | [6 empty] | Shoring Wall 3
Shotcrete | checklist | [6 empty] | Shoring Wall 4
Shotcrete | checklist | [6 empty] | Sheet Pile Wall 1
Shotcrete | checklist | [6 empty] | Sheet Pile Wall 2
Shotcrete | checklist | [6 empty] | Sheet Pile Wall 3
Shotcrete | checklist | [6 empty] | Sheet Pile Wall 4
Shotcrete | checklist | [6 empty] | Sheet Pile Wall 5
Shotcrete | checklist | [6 empty] | Sheet Pile Wall 6
Shotcrete | checklist | [6 empty] | Sheet Pile Wall 7
Shotcrete | checklist | [6 empty] | Sheet Pile Wall 8
Shotcrete | checklist | [6 empty] | Sheet Pile Wall 9
| step | [5 empty] | Anchors
Rock Anchoring | checklist | [6 empty] | Shoring Wall 1
Rock Anchoring | checklist | [6 empty] | Shoring Wall 2
Rock Anchoring | checklist | [6 empty] | Shoring Wall 3
Rock Anchoring | checklist | [6 empty] | Shoring Wall 4
Rock Anchoring | checklist | [6 empty] | Sheet Pile Wall 1
Rock Anchoring | checklist | [6 empty] | Sheet Pile Wall 2
Rock Anchoring | checklist | [6 empty] | Sheet Pile Wall 3
Rock Anchoring | checklist | [6 empty] | Sheet Pile Wall 4
Rock Anchoring | checklist | [6 empty] | Sheet Pile Wall 5
Rock Anchoring | checklist | [6 empty] | Sheet Pile Wall 6
Rock Anchoring | checklist | [6 empty] | Sheet Pile Wall 7
Rock Anchoring | checklist | [6 empty] | Sheet Pile Wall 8
Rock Anchoring | checklist | [6 empty] | Sheet Pile Wall 9
Rock Anchoring | checklist | [6 empty] | Crane Base 1
Rock Anchoring | checklist | [6 empty] | Crane Base 2
Rock Anchoring | checklist | [6 empty] | Lift Pit
Bulk Excavation | checklist | [5 empty] | Bulk Excavation
| step | [5 empty] | Tanking
Basement Tanking | checklist | [6 empty] | Shoring Wall 1
Basement Tanking | checklist | [6 empty] | Shoring Wall 2
Basement Tanking | checklist | [6 empty] | Shoring Wall 3
Basement Tanking | checklist | [6 empty] | Shoring Wall 4
Basement Tanking | checklist | [6 empty] | Sheet Pile Wall 1
Basement Tanking | checklist | [6 empty] | Sheet Pile Wall 2
Basement Tanking | checklist | [6 empty] | Sheet Pile Wall 3
Basement Tanking | checklist | [6 empty] | Sheet Pile Wall 4
Basement Tanking | checklist | [6 empty] | Sheet Pile Wall 5
Basement Tanking | checklist | [6 empty] | Sheet Pile Wall 6
Basement Tanking | checklist | [6 empty] | Sheet Pile Wall 7
Basement Tanking | checklist | [6 empty] | Sheet Pile Wall 8
Basement Tanking | checklist | [6 empty] | Sheet Pile Wall 9
| step |  |  |  | Structure
| step |  |  |  |  | West Tower
| step | [5 empty] | Footings - Shotcrete
| step | [5 empty] | Slab on Ground
Capping Beam (V140421) | checklist | [6 empty] | Capping Beams
Bulk Excavation | checklist | [6 empty] | Bulk Excavation
| step | [5 empty] | Basement 1
Detailed Excavations | checklist | [6 empty] | Detailed Excavation
Formwork & Reinforcing | checklist | [6 empty] | Formwork & Reinforcing
Pad Footings, Strip Footings, Lift Pits & Piles | checklist | [6 empty] | Lift Pit
Pad Footings | checklist | [6 empty] | Pad footings
Pad Footings, Strip Footings, Lift Pits & Piles | checklist | [6 empty] | Strip footings
Ground Beams | checklist | [6 empty] | Ground Beams
Pad Footings | checklist | [6 empty] | Pad footings
SOG | checklist | [6 empty] | SOG
Columns | checklist | [6 empty] | Columns
Hydraulic Groundwork | checklist | [6 empty] | Hydraulic Groundwork
| step | [5 empty] | Ground
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 1
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 2
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 3
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 4
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 5
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
step
| step | [5 empty] | Level 6
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 7
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 8
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 9
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 10
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 11
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 12
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 13
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 14
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 15
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 16
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 17
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 18
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 19
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 20
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 21
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 22
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 23
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 24
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 25
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 26
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 27
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Roof
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step |  |  |  |  | East Tower
| step | [5 empty] | Level 6
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 7
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 8
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 9
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 10
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 11
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 12
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 13
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 14
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 15
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 16
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 17
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 18
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 19
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 20
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 21
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 22
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 23
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 24
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 25
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 26
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 27
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Level 28
Precast | checklist | [6 empty] | Precast
Suspended Slab | checklist | [6 empty] | Concrete Pour
Columns | checklist | [6 empty] | Columns
Jump Form | checklist | [6 empty] | Jump Form
| step | [5 empty] | Roof
Suspended Slab | checklist | [6 empty] | Concrete Pour
| step |  |  |  | Fit Out
| step |  |  |  |  | Basement 1
KONE - Lifts | checklist | [5 empty] | Lift 01, 02, 03
KONE - Lifts | checklist | [5 empty] | Lift 04, 05, 06
KONE - Lifts | checklist | [5 empty] | Lift 07, 08, 09
Infinity Lifts - Lifts | checklist | [5 empty] | Lift 10
Contractor TBC - Lifts | checklist | [5 empty] | Lift 11
Stairs | checklist | [5 empty] | FS01
Stairs | checklist | [5 empty] | FS02
Stairs | checklist | [5 empty] | FS03
Carpark & Line Markings | checklist | [5 empty] | Carpark & Line Markings
OSD | checklist | [5 empty] | Rainwater Tank
OSD | checklist | [5 empty] | Stormwater Tank
Grease Arrestor Room (v040521) | checklist | [5 empty] | Grease Arrestor
Cold Water Pump Room | checklist | [5 empty] | CW Booster Pump Set
Storage Room | checklist | [5 empty] | Pub Storage
Mechanical Fan Room | checklist | [5 empty] | Fan Room
Garbage Room (V90421) | checklist | [5 empty] | Residential Garbage
Garbage Room (V90421) | checklist | [5 empty] | Hotel Bin Room
Storage Room | checklist | [5 empty] | Hotel Storage
Storage Room | checklist | [5 empty] | Hotel Linen & Housekeeping
Bike Rack | checklist | [5 empty] | Bike Rack
Plumbing Rough-In | checklist | [5 empty] | Plumbing
Electrical Rough In | checklist | [5 empty] | Electrical
Mechanical Rough In | checklist | [5 empty] | Mechanical
Basement Fire System | checklist | [5 empty] | Fire Services
| step |  |  |  |  | Ground Floor
| step | [5 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [6 empty] | Framing
Plumbing Rough-In | checklist | [6 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [6 empty] | Fire Rough-In
Electrical Rough In | checklist | [6 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [6 empty] | Mechanical Rough-In
| step | [6 empty] | Linings
Pre Wall Linings | checklist | [7 empty] | Pre-Lining
Post Wall Linings | checklist | [7 empty] | Post-Lining
| step | [6 empty] | Floor Coverings
Tiling | checklist | [7 empty] | Tiling
Carpet | checklist | [7 empty] | Carpet
Joinery Fit Out | checklist | [6 empty] | Joinery Fit-Out
Services Fit Out | checklist | [6 empty] | Services Fit-Out
Internal Painting | checklist | [6 empty] | Internal Painting
| step | [5 empty] | Hotel Lobby, Lift, Stairs
Framing | checklist | [6 empty] | Framing
Plumbing Rough-In | checklist | [6 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [6 empty] | Fire Rough-In
Electrical Rough In | checklist | [6 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [6 empty] | Mechanical Rough-In
| step | [6 empty] | Linings
Pre Wall Linings | checklist | [7 empty] | Pre-Lining
Post Wall Linings | checklist | [7 empty] | Post-Lining
| step | [6 empty] | Floor Coverings
Tiling | checklist | [7 empty] | Tiling
Carpet | checklist | [7 empty] | Carpet
Joinery Fit Out | checklist | [6 empty] | Joinery Fit-Out
Services Fit Out | checklist | [6 empty] | Services Fit-Out
Internal Painting | checklist | [6 empty] | Internal Painting
Fire Pump Room (V90421) | checklist | [5 empty] | Fire Pump Room
Garbage Room (V90421) | checklist | [5 empty] | Waste Room
Garbage Room (V90421) | checklist | [5 empty] | Bulky Waste
Grease Arrestor Room (v040521) | checklist | [5 empty] | Grease Arrestor Access
Gas Connection | checklist | [5 empty] | Gas Meter
| step | [5 empty] | CW Water/Gas Plant
Water Connection | checklist | [6 empty] | Water
Gas Connection | checklist | [5 empty] | Commercial Pub | Gas
| step | [5 empty] | Commercial Pub Kitchen
| step | [5 empty] | Commercial Staff Cafeteria/Lunchroom
| step | [5 empty] | Gaming Room
| step | [5 empty] | Gaming Room Lift
| step | [5 empty] | Empty Commercial Space
| step | [5 empty] | BOH Toilets
| step | [5 empty] | Business Office
| step | [5 empty] | HR Office
| step | [5 empty] | Front Office
| step | [5 empty] | GM Office
Planter Box Waterproofing | checklist | [5 empty] | Porte Cochere
KONE - Lifts | checklist |  |  |  |  | Level 1 | Lift 01, 02, 03
KONE - Lifts | checklist | [5 empty] | Lift 04, 05, 06
KONE - Lifts | checklist | [5 empty] | Lift 07, 08, 09
Stairs | checklist | [5 empty] | FS01
Stairs | checklist | [5 empty] | FS02
Stairs | checklist | [5 empty] | FS03
Carpark & Line Markings | checklist | [5 empty] | Carpark & Line Markings
| step | [5 empty] | Maintenance Room
Storage Lockers | checklist | [5 empty] | Storage Cages
Bike Rack | checklist | [5 empty] | Bike Rack
Plumbing Rough-In | checklist | [5 empty] | Plumbing
Electrical Rough In | checklist | [5 empty] | Electrical
Mechanical Rough In | checklist | [5 empty] | Mechanical
Basement Fire System | checklist | [5 empty] | Fire Services
step
KONE - Lifts | checklist |  |  |  |  | Level 2 | Lift 01, 02, 03
KONE - Lifts | checklist | [5 empty] | Lift 04, 05, 06
KONE - Lifts | checklist | [5 empty] | Lift 07, 08, 09
Stairs | checklist | [5 empty] | FS01
Stairs | checklist | [5 empty] | FS02
Stairs | checklist | [5 empty] | FS03
Carpark & Line Markings | checklist | [5 empty] | Carpark & Line Markings
Bike Rack | checklist | [5 empty] | Bike Rack
Plumbing Rough-In | checklist | [5 empty] | Plumbing
Electrical Rough In | checklist | [5 empty] | Electrical
Mechanical Rough In | checklist | [5 empty] | Mechanical
Basement Fire System | checklist | [5 empty] | Fire Services
| step |  |  |  |  | Level 3
KONE - Lifts | checklist | [5 empty] | Lift 01, 02, 03
KONE - Lifts | checklist | [5 empty] | Lift 04, 05, 06
KONE - Lifts | checklist | [5 empty] | Lift 07, 08, 09
Stairs | checklist | [5 empty] | FS01
Stairs | checklist | [5 empty] | FS02
Stairs | checklist | [5 empty] | FS03
Carpark & Line Markings | checklist | [5 empty] | Carpark & Line Markings
Bike Rack | checklist | [5 empty] | Bike Rack
Plumbing Rough-In | checklist | [5 empty] | Plumbing
Electrical Rough In | checklist | [5 empty] | Electrical
Mechanical Rough In | checklist | [5 empty] | Mechanical
Basement Fire System | checklist | [5 empty] | Fire Services
| step |  |  |  |  | Level 4
KONE - Lifts | checklist | [5 empty] | Lift 01, 02, 03
KONE - Lifts | checklist | [5 empty] | Lift 04, 05, 06
KONE - Lifts | checklist | [5 empty] | Lift 07, 08, 09
Stairs | checklist | [5 empty] | FS01
Stairs | checklist | [5 empty] | FS02
Stairs | checklist | [5 empty] | FS03
Carpark & Line Markings | checklist | [5 empty] | Carpark & Line Markings
| step | [5 empty] | Mech Plant
Bike Rack | checklist | [5 empty] | Bike Rack
Plumbing Rough-In | checklist | [5 empty] | Plumbing
Electrical Rough In | checklist | [5 empty] | Electrical
Mechanical Rough In | checklist | [5 empty] | Mechanical
Basement Fire System | checklist | [5 empty] | Fire Services
Planter Box Waterproofing | checklist |  |  |  |  | Level 5 Podium
| step |  |  |  |  | West Tower
| step | [5 empty] | Level 5
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 501
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Apartment Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
Bathroom & Laundry Waterproofing | checklist | [7 empty] | Internal Waterproofing
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
Floor Wastes | checklist | [7 empty] | Floor Wastes
| step | [7 empty] | Balcony
Balcony & Podium Waterproofing | checklist | [8 empty] | External Waterproofing
Tiling | checklist | [8 empty] | Tiling
| step | [6 empty] | 502
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Apartment Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
Bathroom & Laundry Waterproofing | checklist | [7 empty] | Internal Waterproofing
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
Floor Wastes | checklist | [7 empty] | Floor Wastes
| step | [7 empty] | Balcony
Balcony & Podium Waterproofing | checklist | [8 empty] | External Waterproofing
Tiling | checklist | [8 empty] | Tiling
| step | [6 empty] | 503
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Apartment Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
Bathroom & Laundry Waterproofing | checklist | [7 empty] | Internal Waterproofing
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
Floor Wastes | checklist | [7 empty] | Floor Wastes
| step | [7 empty] | Balcony
Balcony & Podium Waterproofing | checklist | [8 empty] | External Waterproofing
Tiling | checklist | [8 empty] | Tiling
| step | [6 empty] | 504
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Apartment Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
Bathroom & Laundry Waterproofing | checklist | [7 empty] | Internal Waterproofing
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
Floor Wastes | checklist | [7 empty] | Floor Wastes
| step | [7 empty] | Balcony
Balcony & Podium Waterproofing | checklist | [8 empty] | External Waterproofing
Tiling | checklist | [8 empty] | Tiling
| step | [6 empty] | 505
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Apartment Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
Bathroom & Laundry Waterproofing | checklist | [7 empty] | Internal Waterproofing
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
Floor Wastes | checklist | [7 empty] | Floor Wastes
| step | [7 empty] | Balcony
Balcony & Podium Waterproofing | checklist | [8 empty] | External Waterproofing
Tiling | checklist | [8 empty] | Tiling
| step | [6 empty] | 506
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Apartment Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
Bathroom & Laundry Waterproofing | checklist | [7 empty] | Internal Waterproofing
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
Floor Wastes | checklist | [7 empty] | Floor Wastes
| step | [7 empty] | Balcony
Balcony & Podium Waterproofing | checklist | [8 empty] | External Waterproofing
Tiling | checklist | [8 empty] | Tiling
| step | [6 empty] | 507
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Apartment Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
Bathroom & Laundry Waterproofing | checklist | [7 empty] | Internal Waterproofing
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
Floor Wastes | checklist | [7 empty] | Floor Wastes
| step | [7 empty] | Balcony
Balcony & Podium Waterproofing | checklist | [8 empty] | External Waterproofing
Tiling | checklist | [8 empty] | Tiling
| step | [6 empty] | 508
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Apartment Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
Bathroom & Laundry Waterproofing | checklist | [7 empty] | Internal Waterproofing
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
Floor Wastes | checklist | [7 empty] | Floor Wastes
| step | [7 empty] | Balcony
Balcony & Podium Waterproofing | checklist | [8 empty] | External Waterproofing
Tiling | checklist | [8 empty] | Tiling
| step | [6 empty] | 509
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Apartment Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
Bathroom & Laundry Waterproofing | checklist | [7 empty] | Internal Waterproofing
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
Floor Wastes | checklist | [7 empty] | Floor Wastes
| step | [7 empty] | Balcony
Balcony & Podium Waterproofing | checklist | [8 empty] | External Waterproofing
Tiling | checklist | [8 empty] | Tiling
| step | [5 empty] | Level 6
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 601
| step | [6 empty] | 602
| step | [6 empty] | 603
| step | [6 empty] | 604
| step | [6 empty] | 605
| step | [6 empty] | 606
| step | [6 empty] | 607
| step | [6 empty] | 608
| step | [6 empty] | 609
| step | [5 empty] | Level 7
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 701
| step | [6 empty] | 702
| step | [6 empty] | 703
| step | [6 empty] | 704
| step | [6 empty] | 705
| step | [6 empty] | 706
| step | [6 empty] | 707
| step | [6 empty] | 708
| step | [6 empty] | 709
| step | [5 empty] | Level 8
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 801
| step | [6 empty] | 802
| step | [6 empty] | 803
| step | [6 empty] | 804
| step | [6 empty] | 805
| step | [6 empty] | 806
| step | [6 empty] | 807
| step | [6 empty] | 808
| step | [6 empty] | 809
| step | [5 empty] | Level 9
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 901
| step | [6 empty] | 902
| step | [6 empty] | 903
| step | [6 empty] | 904
| step | [6 empty] | 905
| step | [6 empty] | 906
| step | [6 empty] | 907
| step | [6 empty] | 908
| step | [6 empty] | 909
| step | [5 empty] | Level 10
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 1001
| step | [6 empty] | 1001
| step | [6 empty] | 1001
| step | [6 empty] | 1001
| step | [6 empty] | 1001
| step | [6 empty] | 1001
| step | [6 empty] | 1001
| step | [6 empty] | 1001
| step | [6 empty] | 1001
| step | [5 empty] | Level 11
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 1101
| step | [6 empty] | 1102
| step | [6 empty] | 1103
| step | [6 empty] | 1104
| step | [6 empty] | 1105
| step | [6 empty] | 1106
| step | [6 empty] | 1107
| step | [6 empty] | 1108
| step | [6 empty] | 1109
| step | [5 empty] | Level 12
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 1201
| step | [6 empty] | 1202
| step | [6 empty] | 1203
| step | [6 empty] | 1204
| step | [6 empty] | 1205
| step | [6 empty] | 1206
| step | [6 empty] | 1207
| step | [6 empty] | 1208
| step | [6 empty] | 1209
| step | [5 empty] | Level 13
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 1301
| step | [6 empty] | 1302
| step | [6 empty] | 1303
| step | [6 empty] | 1304
| step | [6 empty] | 1305
| step | [6 empty] | 1306
| step | [6 empty] | 1307
| step | [6 empty] | 1308
| step | [6 empty] | 1309
| step | [5 empty] | Level 14
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 1401
| step | [6 empty] | 1402
| step | [6 empty] | 1403
| step | [6 empty] | 1404
| step | [6 empty] | 1405
| step | [6 empty] | 1406
| step | [6 empty] | 1407
| step | [6 empty] | 1408
| step | [6 empty] | 1409
| step | [5 empty] | Level 15
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 1501
| step | [6 empty] | 1502
| step | [6 empty] | 1503
| step | [6 empty] | 1504
| step | [6 empty] | 1505
| step | [6 empty] | 1506
| step | [6 empty] | 1507
| step | [6 empty] | 1508
| step | [6 empty] | 1509
| step | [5 empty] | Level 16
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 1601
| step | [6 empty] | 1602
| step | [6 empty] | 1603
| step | [6 empty] | 1604
| step | [6 empty] | 1605
| step | [6 empty] | 1606
| step | [6 empty] | 1607
| step | [6 empty] | 1608
| step | [6 empty] | 1609
| step | [5 empty] | Level 17
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 1701
| step | [6 empty] | 1702
| step | [6 empty] | 1703
| step | [6 empty] | 1705
| step | [6 empty] | 1706
| step | [6 empty] | 1707
| step | [6 empty] | 1708
| step | [6 empty] | 1709
| step | [5 empty] | Level 18
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 1801
| step | [6 empty] | 1802
| step | [6 empty] | 1803
| step | [6 empty] | 1805
| step | [6 empty] | 1806
| step | [6 empty] | 1807
| step | [6 empty] | 1808
| step | [6 empty] | 1809
| step | [5 empty] | Level 19
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 1901
| step | [6 empty] | 1902
| step | [6 empty] | 1903
| step | [6 empty] | 1905
| step | [6 empty] | 1906
| step | [6 empty] | 1907
| step | [6 empty] | 1908
| step | [6 empty] | 1909
| step | [5 empty] | Level 20
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 2001
| step | [6 empty] | 2002
| step | [6 empty] | 2003
| step | [6 empty] | 2004
| step | [6 empty] | 2005
| step | [6 empty] | 2006
| step | [6 empty] | 2007
| step | [6 empty] | 2008
| step | [6 empty] | 2009
| step | [5 empty] | Level 21
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 2101
| step | [6 empty] | 2102
| step | [6 empty] | 2103
| step | [6 empty] | 2104
| step | [6 empty] | 2105
| step | [6 empty] | 2106
| step | [6 empty] | 2107
| step | [6 empty] | 2108
| step | [6 empty] | 2109
| step | [5 empty] | Level 22
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 2201
| step | [6 empty] | 2202
| step | [6 empty] | 2203
| step | [6 empty] | 2204
| step | [6 empty] | 2205
| step | [6 empty] | 2206
| step | [6 empty] | 2207
| step | [6 empty] | 2208
| step | [6 empty] | 2209
| step | [5 empty] | Level 23
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 2301
| step | [6 empty] | 2302
| step | [6 empty] | 2303
| step | [6 empty] | 2304
| step | [6 empty] | 2305
| step | [6 empty] | 2306
| step | [6 empty] | 2307
| step | [6 empty] | 2308
| step | [6 empty] | 2309
| step | [5 empty] | Level 24
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 2401
| step | [6 empty] | 2402
| step | [6 empty] | 2403
| step | [6 empty] | 2404
| step | [6 empty] | 2405
| step | [6 empty] | 2406
| step | [6 empty] | 2407
| step | [6 empty] | 2408
| step | [6 empty] | 2409
| step | [5 empty] | Level 25
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 2501
| step | [6 empty] | 2502
| step | [6 empty] | 2503
| step | [6 empty] | 2504
| step | [6 empty] | 2505
| step | [6 empty] | 2506
| step | [6 empty] | 2507
| step | [6 empty] | 2508
| step | [6 empty] | 2509
| step | [5 empty] | Level 26
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 2601
| step | [6 empty] | 2602
| step | [6 empty] | 2603
| step | [6 empty] | 2604
| step | [6 empty] | 2605
| step | [5 empty] | Level 27
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 2701
| step | [6 empty] | 2702
| step | [6 empty] | 2703
| step | [6 empty] | 2704
| step | [6 empty] | 2705
| step |  |  |  |  | East Tower
| step | [5 empty] | Level 12
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 1201
| step | [6 empty] | 1202
| step | [6 empty] | 1203
| step | [6 empty] | 1204
| step | [6 empty] | 1205
| step | [6 empty] | 1206
| step | [6 empty] | 1207
| step | [5 empty] | Level 13
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 1301
| step | [6 empty] | 1302
| step | [6 empty] | 1303
| step | [6 empty] | 1304
| step | [6 empty] | 1305
| step | [6 empty] | 1306
| step | [6 empty] | 1307
| step | [6 empty] | 1308
| step | [6 empty] | 1309
| step | [5 empty] | Level 14
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 1401
| step | [6 empty] | 1402
| step | [6 empty] | 1403
| step | [6 empty] | 1404
| step | [6 empty] | 1405
| step | [6 empty] | 1406
| step | [6 empty] | 1407
| step | [6 empty] | 1408
| step | [6 empty] | 1409
| step | [5 empty] | Level 15
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 1501
| step | [6 empty] | 1502
| step | [6 empty] | 1503
| step | [6 empty] | 1504
| step | [6 empty] | 1505
| step | [6 empty] | 1506
| step | [6 empty] | 1507
| step | [6 empty] | 1508
| step | [6 empty] | 1509
| step | [5 empty] | Level 16
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 1601
| step | [6 empty] | 1602
| step | [6 empty] | 1603
| step | [6 empty] | 1604
| step | [6 empty] | 1605
| step | [6 empty] | 1606
| step | [6 empty] | 1607
| step | [6 empty] | 1608
| step | [5 empty] | Level 17
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 1701
| step | [6 empty] | 1702
| step | [6 empty] | 1703
| step | [6 empty] | 1704
| step | [6 empty] | 1705
| step | [6 empty] | 1706
| step | [6 empty] | 1707
| step | [6 empty] | 1708
| step | [5 empty] | Level 18
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 1801
| step | [6 empty] | 1802
| step | [6 empty] | 1803
| step | [6 empty] | 1804
| step | [6 empty] | 1805
| step | [6 empty] | 1806
| step | [6 empty] | 1807
| step | [6 empty] | 1808
| step | [5 empty] | Level 19
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 1901
| step | [6 empty] | 1902
| step | [6 empty] | 1903
| step | [6 empty] | 1904
| step | [6 empty] | 1905
| step | [6 empty] | 1906
| step | [6 empty] | 1907
| step | [6 empty] | 1908
| step | [5 empty] | Level 20
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 2001
| step | [6 empty] | 2002
| step | [6 empty] | 2003
| step | [6 empty] | 2004
| step | [6 empty] | 2005
| step | [6 empty] | 2006
| step | [6 empty] | 2007
| step | [6 empty] | 2008
| step | [5 empty] | Level 21
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 2101
| step | [6 empty] | 2102
| step | [6 empty] | 2103
| step | [6 empty] | 2104
| step | [6 empty] | 2105
| step | [6 empty] | 2106
| step | [6 empty] | 2107
| step | [6 empty] | 2108
| step | [5 empty] | Level 22
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 2201
| step | [6 empty] | 2202
| step | [6 empty] | 2203
| step | [6 empty] | 2204
| step | [6 empty] | 2205
| step | [6 empty] | 2206
| step | [6 empty] | 2207
| step | [6 empty] | 2208
| step | [5 empty] | Level 23
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 2301
| step | [6 empty] | 2302
| step | [6 empty] | 2303
| step | [6 empty] | 2304
| step | [6 empty] | 2305
| step | [6 empty] | 2306
| step | [6 empty] | 2307
| step | [6 empty] | 2308
| step | [5 empty] | Level 24
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 2401
| step | [6 empty] | 2402
| step | [6 empty] | 2403
| step | [6 empty] | 2404
| step | [6 empty] | 2405
| step | [6 empty] | 2406
| step | [6 empty] | 2407
| step | [6 empty] | 2408
| step | [5 empty] | Level 25
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 2501
| step | [6 empty] | 2502
| step | [6 empty] | 2503
| step | [6 empty] | 2504
| step | [6 empty] | 2505
| step | [6 empty] | 2506
| step | [6 empty] | 2507
| step | [6 empty] | 2508
| step | [5 empty] | Level 26
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 2601
| step | [6 empty] | 2602
| step | [6 empty] | 2603
| step | [6 empty] | 2604
| step | [6 empty] | 2605
| step | [5 empty] | Level 27
| step | [6 empty] | Residential Lobby, Lift & Stairs
Framing | checklist | [7 empty] | Framing
Plumbing Rough-In | checklist | [7 empty] | Plumbing Rough-In
Common Area Fire System | checklist | [7 empty] | Fire Rough-In
Electrical Rough In | checklist | [7 empty] | Electrical Rough-In
Mechanical Rough In | checklist | [7 empty] | Mechanical Rough-In
| step | [7 empty] | Linings
Pre Wall Linings | checklist | [8 empty] | Pre-Lining
Post Wall Linings | checklist | [8 empty] | Post-Lining
| step | [7 empty] | Floor Coverings
Tiling | checklist | [8 empty] | Tiling
Carpet | checklist | [8 empty] | Carpet
Joinery Fit Out | checklist | [7 empty] | Joinery Fit-Out
Services Fit Out | checklist | [7 empty] | Services Fit-Out
Internal Painting | checklist | [7 empty] | Internal Painting
| step | [6 empty] | 2701
| step | [6 empty] | 2702
| step | [6 empty] | 2703
| step | [6 empty] | 2704
| step | [6 empty] | 2705
| step |  |  |  | Facade
| step |  |  |  |  | Ground Floor
External Facade | checklist | [5 empty] | North Elevation
External Facade | checklist | [5 empty] | East Elevation
External Facade | checklist | [5 empty] | South Elevation
External Facade | checklist | [5 empty] | West Elevation
| step |  |  |  |  | Level 1
External Facade | checklist | [5 empty] | North Elevation
External Facade | checklist | [5 empty] | East Elevation
External Facade | checklist | [5 empty] | South Elevation
External Facade | checklist | [5 empty] | West Elevation
| step |  |  |  |  | Level 2
External Facade | checklist | [5 empty] | North Elevation
External Facade | checklist | [5 empty] | East Elevation
External Facade | checklist | [5 empty] | South Elevation
External Facade | checklist | [5 empty] | West Elevation
| step |  |  |  |  | Level 3
External Facade | checklist | [5 empty] | North Elevation
External Facade | checklist | [5 empty] | East Elevation
External Facade | checklist | [5 empty] | South Elevation
External Facade | checklist | [5 empty] | West Elevation
| step |  |  |  |  | Level 4
External Facade | checklist | [5 empty] | North Elevation
External Facade | checklist | [5 empty] | East Elevation
External Facade | checklist | [5 empty] | South Elevation
External Facade | checklist | [5 empty] | West Elevation
| step |  |  |  |  | West Tower
| step | [5 empty] | Level 5
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 6
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 7
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 8
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 9
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 10
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 11
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 12
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 13
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 14
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 15
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 16
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 17
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 18
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 19
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 20
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 21
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 22
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 23
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 25
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 26
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 27
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 28
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step |  |  |  |  | East Tower
| step | [5 empty] | Level 5
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 6
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 7
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 8
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 9
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 10
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 11
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 12
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 13
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 14
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 15
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 16
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 17
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 18
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 19
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 20
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 21
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 22
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 23
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 25
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 26
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 27
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 28
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step | [5 empty] | Level 29
External Facade | checklist | [6 empty] | North Elevation
External Facade | checklist | [6 empty] | East Elevation
External Facade | checklist | [6 empty] | South Elevation
External Facade | checklist | [6 empty] | West Elevation
| step |  |  | Service Connections
NBN Connection | checklist |  |  |  | NBN Connection
Gas Connection | checklist |  |  |  | Gas Connection
Power connection | checklist |  |  |  | Power Connection
Water Connection | checklist |  |  |  | Water Connection
| step |  |  | External Works
Courtyard Surfaces ITP | checklist |  |  |  | Hard Landscaping
Driveways /Footpaths /Hard surfaces | checklist |  |  |  | Driveways
Soft Landscaping | checklist |  |  |  | Soft Landscaping
| step |  |  | Commissioning & Compliance
Commissioning Documentation | checklist |  |  |  | Commissioning Documentation
Building Authority Checklist | checklist |  |  |  | Compliance Documentation
| step |  |  | Inspections
Inspection Checklist | checklist |  |  |  | Geotechnical Engineer
Inspection Checklist | checklist |  |  |  | Structural Engineer
Inspection Checklist | checklist |  |  |  | Building Surveyor
Mandatory Inspections | checklist |  |  |  | Mandatory Inspections