## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | b3d7ab85-d6c6-4da7-9176-56144d2fdc0f |  | checklist | Gutter Flood Test |  |  |  |  | Yes | Gutter Flood Test | 030ec18b-0115-4a99-84fe-c69cddd19849
checkpoint-status | 4b42e314-5b07-4d8b-9158-180e3e2efdb2 |  | checkpoint | Sleeves installed
checkpoint-status | 257b3c15-a00c-44b7-ab8b-69e8d93d1a9e |  | checkpoint | Sleeves completely sealed/cured
checkpoint-status | 38be5c12-2681-4cc6-99ce-e134679ce412 |  | checkpoint | Test Result
checklist-sectioned | 55294404-1972-48a4-98a1-db21e0367897 |  | checklist | Decorative Fins |  |  |  |  | Yes | Decorative Fins | 06b4a523-92b3-4e9c-9b89-653f8ea420c6
checkpoint-group | 984ccdbd-6f85-4228-9d2e-428f45e9de10 |  | section | Pre-Installation QA Check
checkpoint-status | 11bdf693-8abd-4405-83ac-e8fb9df47f7a |  | checkpoint | Is CW panel aligned/levelled
label | 795c8e57-e8bb-50d9-87c0-f7738af5e27a |  | note | If not - do not proceed Fin install
checkpoint-status | 7c77c21a-1494-45b2-a040-34e0217e154c |  | checkpoint | S/S brackets complete & at correct location
checkpoint-status | b070a41f-6356-4c47-b75b-127c50ccad6e |  | checkpoint | Fins received in good condition
checkpoint-status | 915ea394-5b35-497c-89de-f715e36e7617 |  | checkpoint | Fin panels assembled as per approved dwg
checkpoint-status | 59118fc2-a4a3-4c03-ba8a-6bbfa2282c38 |  | checkpoint | Fins received complete & secured with bolts/nuts
checkpoint-status | dede99ee-891e-45c4-8369-17c98602fa9c |  | checkpoint | Protection tape/stickers removed prior to install
checkpoint-group | aa4be56f-2f3c-465f-8905-0ae615e2976c |  | section | Installation QA Check
checkpoint-status | 75fd0e70-8045-43a3-9a45-50cd3a55398a |  | checkpoint | Fins aligned & levelled
checkpoint-status | 7e0b1607-8aaf-4f7f-8c24-234256f37c34 |  | checkpoint | Fins installed according to module & make-up
checkpoint-status | 0343a1f3-1c7d-497f-a9c3-74db1cfe69b0 |  | checkpoint | Connecting bolts complete & tightened
checkpoint-status | a98b8608-baf4-4b57-9db6-b4b59eb3cc8c |  | checkpoint | Any defects found i.e., scratch, dents reed
select | 5ba112f6-beef-5318-bd25-01d5039a3510 |  | dropdown | Has the Fins been checked by SG accepted preliminary handover | yes,no
checklist-flat | 9dd6e31b-e430-46f2-a090-f4881ae99639 |  | checklist | Pull Test |  |  |  |  | Yes | Pull Test | 1e24a030-96e1-4a33-a7e4-b753e56ae96c
checkpoint-status | 64d3a11c-17ec-4cd2-95a0-600ea7b9e5a3 |  | checkpoint | Concrete cured / No cracks
checkpoint-status | 4f0e9b87-ac08-4ba1-85bf-c6041c30f8fb |  | checkpoint | Bolt applied as per approval
checkpoint-status | 9ffdd087-02c3-47ef-8d3f-a084fac75648 |  | checkpoint | Test Result
checklist-flat | f67b38bd-c559-43c8-84ac-13c736509f59 |  | checklist | Water Test |  |  |  |  | Yes | Water Test | 2d307afe-afbb-4b69-96db-d4d0e154a0f0
checkpoint-status | 024bec2e-df6a-4649-8c71-75136361ec0b |  | checkpoint | Test Kit complete & working properly
checkpoint-status | bd7f1646-37ec-48c5-abe1-f39820655a35 |  | checkpoint | Test conducted as per standards
checkpoint-status | fd7a139b-2a65-4657-b7e0-b0b27e782bdb |  | checkpoint | Test Result
checklist-sectioned | ee6cc1da-42c4-455c-8feb-db6373470148 |  | checklist | Balustrades |  |  |  |  | Yes | Balustrades | 32ac151d-9e15-4311-8ce6-155d6402b888
checkpoint-group | df30b9da-55cf-4ed5-9274-b81ad75de30d |  | section | Pre-Installation QA Check
checkpoint-status | 259c8b58-42a4-424d-94e9-204048cd932a |  | checkpoint | Floor rebates been handover by MC
checkpoint-status | 593c709f-6dda-4534-8c97-5ab57d16b7a3 |  | checkpoint | Floor rebates as per agreed level
checkpoint-status | 8aff31b1-3ee6-44ce-b5c7-239efbd666f2 |  | checkpoint | Has the floor brackets been installed
select | 55b84297-7c44-58e7-b75e-9d280a883e0f |  | dropdown | Has the floor brackets been grouted | Yes,No
checkpoint-group | 041b6b79-4863-4422-a209-1b4498c3529a |  | section | Installation QA Check
checkpoint-status | 72a6fa1f-3b9d-4510-897d-64934dfe57c3 |  | checkpoint | Balustrade panels installed line and leveled
checkpoint-status | b934e64d-0887-41f3-be5b-379925811636 |  | checkpoint | Top horizontal steel support installed/secured
checkpoint-status | b116e057-9f7e-46eb-b486-028bcfdf4331 |  | checkpoint | Has the bottom bracket been installed and leveled
checkpoint-status | ff950b94-e443-497c-a5d8-354f1380fa07 |  | checkpoint | Has the top and bottom cover been installed
checkpoint-status | fb2e74d5-c329-4025-8965-5ed129b1c6d0 |  | checkpoint | Has the balustrade panels been sealed internal.external
select | 0988803d-57a2-55ad-9782-dd73eeb24225 |  | dropdown | Panel has any missing/broken glass/defects | Yes,No
checklist-sectioned | 5cbdd994-f416-49c9-802c-223f119d34ee |  | checklist | Louvre Install |  |  |  |  | Yes | Louvre Install | 64540264-a6f0-4999-a2d3-5e6564a3b9e4
checkpoint-group | 97992750-8f53-46ba-a620-4410d41453c7 |  | section | Pre-Installation QA Check
checkpoint-status | 22c8a154-3c23-4bb6-b33a-89908bf4f5b4 |  | checkpoint | Workface clean & tidy
checkpoint-status | bec93381-a43f-4020-b465-4c5632330137 |  | checkpoint | Extrusions checked as per factory sheet size
checkpoint-status | ce8f5e9c-7633-4d87-8770-d9a4686b60e6 |  | checkpoint | Seismic installed at correct position/setout/RL
checkpoint-status | c4507034-e8f6-4765-ac3e-df925b27c0bd |  | checkpoint | Seismic frame align & plumb
checkpoint-status | f80e809d-7540-44b6-92ed-d4a1cc5f0add |  | checkpoint | Fixing applied as per schedule
checkpoint-status | 771a23a2-7408-4253-816c-3429ee268fa9 |  | checkpoint | All fixings over-sealed
checkpoint-status | c127c6ec-48c1-476f-8e3c-598a4cd73bea |  | checkpoint | Air-seals applied properly with PEF rod
checkpoint-group | 1d9fe0b8-28e6-467b-807e-c09979a914fa |  | section | Louvre panel QA Check
checkpoint-status | 474e7799-af6b-4d7e-b348-d8e1b918cfda |  | checkpoint | Correct panel installed (align/plumb)
checkpoint-status | 167fc499-8003-47a8-a061-0909d263aa71 |  | checkpoint | Panel installed with correct fixings
checkpoint-status | 9c467d4a-8e6d-4942-9f56-e6aa25f744b1 |  | checkpoint | Louvre free of any defects
checkpoint-status | 136e5e63-8e1a-4abb-8a0e-b60b2f3c6ef5 |  | checkpoint | Weather-seal applied with PEF rod
checkpoint-status | f5d9032a-aaeb-46c3-a2ae-d13faa7ed119 |  | checkpoint | 50x25 angle rainshield installed
checkpoint-status | 340764b6-a584-4a13-b41b-4d1d07253eeb |  | checkpoint | Head flashing installed
checkpoint-status | 63ae5dbd-01b0-49f1-9899-b65d4872c859 |  | checkpoint | Trade clean complete
checkpoint-status | 7b12a1a8-7db1-4231-8379-80e9be1734d0 |  | checkpoint | Louvre checked/accepted by MC as preliminary
checklist-flat | a373e063-bd50-4155-8fea-fa18cd3ee49d |  | checklist | Floor Handover |  |  |  |  | Yes | Floor Handover | 7d2597c8-b68f-4beb-8ee0-fd2b34a5301e
checkpoint-status | c3f34a0a-cc3c-4e90-8beb-c42270cb86ee |  | checkpoint | QA check sheet/marked up plan drawing received from Main Contractor for the whole foor level.
checkpoint-status | 6a1efc3b-b57f-4235-a6fe-903617876b83 |  | checkpoint | Waterproof fashing tape applied as per drawing
checkpoint-status | 39426904-18b3-4620-9fed-a5686bf3386c |  | checkpoint | Grid lines required & clearly marked on floor
checkpoint-status | edeba8b1-407d-4aca-89c2-b7b1d90f400d |  | checkpoint | RL to be provided at 2 or 3 locations on each level
checkpoint-status | 85c3acf6-b1d2-4d42-b77b-d89a3f1006e4 |  | checkpoint | All timber framing completed and waterproofed
checkpoint-status | d94bc8eb-49ad-486f-98ab-3478bbe2009e |  | checkpoint | Structural opening trim size within tolerance
checkpoint-status | 0c9eaee5-6aa5-4236-b89c-225b331ad18a |  | checkpoint | Nibs / Rebate at correct location, RL, Size.
checkpoint-status | f415361a-f5fa-4149-b1b9-d4da22b5a329 |  | checkpoint | Precast erected aligned, plumbed & leveled (Wall Cladding/Punch window/Door)
checkpoint-status | 116d20c5-45df-4efd-8ab4-390a4cffa172 |  | checkpoint | Slab-edge is within tolerance from the grid line
checkpoint-status | 75a5c2ff-e309-4483-b38e-98543043b834 |  | checkpoint | Slab-edge is free from concrete slurries, cracks or any other penetrations.
checkpoint-status | a3daeed0-08be-4401-b11f-7851d8e8d671 |  | checkpoint | Has Alwin install team checked and accepted
checklist-sectioned | 37c84bff-db31-4d20-a8f1-1ee6c1988889 |  | checklist | Seismic Frame |  |  |  |  | Yes | Seismic Frame | 8dad524d-b49c-47b0-affb-67513a870e40
checkpoint-group | c374ec66-5d39-470c-90c6-eb546e95e952 |  | section | Pre-Installation QA Check
checkpoint-status | e7a0b533-9ae7-438a-aa29-cbfd62966f15 |  | checkpoint | QA check sheet received from MC for the whole floor level
checkpoint-status | 3fc7bd03-6fbd-41e8-b31d-af3089f94a21 |  | checkpoint | Does the seismic frame has the gaskets and mohair.
checkpoint-status | de0b399e-da0e-4e6c-8e0d-20d279d691bf |  | checkpoint | Does the sill qot suffcient drain holes
checkpoint-status | 0af7a45a-2ac7-4375-939b-6e11738d6913 |  | checkpoint | Have you qot suffcient sleeves
checkpoint-status | 5bf4be99-e782-4844-b721-56cc6a13f10d |  | checkpoint | Has the rubber packer been inserted and sealed
checkpoint-group | b85d857b-af53-46d0-945d-3eeb5d80d6e9 |  | section | Installation QA Check
checkpoint-status | 74c8a915-5dff-452c-888f-04ecbc116895 |  | checkpoint | Is the structural opening as per shop drawing size/make-up
checkpoint-status | 689fecf1-9305-4d6a-8ca1-ddd170f8957e |  | checkpoint | Is gap between frame & trim - silicone within tolerance.
checkpoint-status | ea79a563-7597-430e-a7ed-3e31fe963da7 |  | checkpoint | Sill tray/Head track/Jamb installed aligned and leveled
checkpoint-status | d0ce1729-3211-4455-8835-d3971297395a |  | checkpoint | Make sure all packing are covered within head, sill and jamb and not exposed. Packing to be placed next to structural fxings.
checkpoint-status | 3ea1d35b-a584-49e3-8a13-a8d57584fdb4 |  | checkpoint | Chemical bolt M12x160 used at Sill tray and ST5.5x75 on Jamb and ST 5.5x80 on head track
checkpoint-status | 8623d2bb-4637-43ec-9c44-4698f1f33703 |  | checkpoint | Has the top frame sleeve installed and sealed
checkpoint-status | 13b13901-b661-475a-b4e3-760d549f0d69 |  | checkpoint | Has all the screw heads over-sealed
checkpoint-status | d499d6ce-280a-45d9-84e1-bc193de6a8b7 |  | checkpoint | Silicon applied external / internal and all mechanical fixings complete.
checklist-sectioned | cdfcbdc4-48d0-4215-a7dd-b0d1a0376f61 |  | checklist | Hinged Doors |  |  |  |  | Yes | Hinged Doors | 9259c8e8-6497-4688-8854-c00f2a260db7
checkpoint-group | 5554b52b-3875-409c-8edd-8ce252971978 |  | section | Pre-Installation QA Check
checkpoint-status | e6e4e298-797b-4d7d-98b0-310df4746be7 |  | checkpoint | Seismic frame installed/aligned/plumb
checkpoint-status | 0bebf09e-c6ae-4896-ad90-879c386483ca |  | checkpoint | Bolts/screw head over-sealed
checkpoint-status | d1e205cb-af26-498f-b7b1-5090435e5bbd |  | checkpoint | Trim opening size checked vs door panel
checkpoint-group | 6996e94c-e573-4d60-bf3f-7a4f83faedd3 |  | section | Hinged Door QA Check
checkpoint-status | 3c1176d1-23fb-4114-b987-ce4f794d79b2 |  | checkpoint | End plates been installed and sealed
checkpoint-status | eaa2eabd-9334-4253-bff6-0b085a993803 |  | checkpoint | Door hardware/accessories complete (handle, lock body, strike plate, cylinder, keys)
checkpoint-status | f35e51eb-22dc-4c28-8811-dd7af759d6a5 |  | checkpoint | Door installed with heavy duty hinges
checkpoint-status | 73563f15-135e-40e4-bff1-a92327686b09 |  | checkpoint | Door frame installed/aligned/levelled
checkpoint-status | 924ba101-fd0b-4518-8e60-531655ba5ac0 |  | checkpoint | Ocor glazed/heel & toe/beats/rubber
checkpoint-status | adec7a64-5d5c-449b-a891-d3918a8b3e86 |  | checkpoint | Has the door been smoothly without scratching floors and head
checkpoint-status | c5b0e307-9601-4803-aa26-8b5850c89d53 |  | checkpoint | Door lock/key working properly
checkpoint-status | 7baa4433-cd70-4b57-9d59-a7021b652ae2 |  | checkpoint | Door closer installed and functioning
checkpoint-status | b1668ea5-48bd-48ae-b5c6-e754528dfdc1 |  | checkpoint | Threshold installed at correct level
select | 2cb4fed5-2271-5719-b314-07e76ab04b4a |  | dropdown | Keys handed over to MC | Yes / No
select | c1b6caab-c73b-5ab1-a66a-9a1310a13966 |  | dropdown | Has due Hinged Door been check by MC accepted preliminary handover | Yes / No
checklist-sectioned | d477f0b3-83c1-4ca1-969d-6cbd75557bfd |  | checklist | Aluminum Cladding |  |  |  |  | Yes | Aluminum Cladding | 97393956-d706-4895-987e-efb756ab77c6
checkpoint-group | 0b27b063-7596-4279-b494-9aac13dd54a7 |  | section | Main Contractor Handover
checkpoint-status | 00796187-cdd4-40a0-8e88-1af586d26fec |  | checkpoint | Substrate/membrane applied as per approved dwg
checkpoint-status | e4595839-16c7-437a-91d9-27dfa2ce6ffe |  | checkpoint | Structure plumb/levelled & correct setting out
checkpoint-status | c29bd334-9205-4b91-8d2d-45b5af196cdc |  | checkpoint | Workface clear from any obstruction/penetration
checkpoint-group | cf405158-7b3d-4d08-b9dc-735a9e96041c |  | section | Pre-Installation QA Check
checkpoint-status | df5a358f-8850-4bd0-bf66-54f5340a2150 |  | checkpoint | Grid datum Iin / RL visible & accessible
checkpoint-status | b99b1c74-7822-4dcc-ad54-d240b412e6cc |  | checkpoint | Cladding rails / panels / other components complete
checkpoint-status | 55233c68-232a-462f-af40-a7801a5970af |  | checkpoint | Cladding free of any defects
checkpoint-group | 05070f99-2b62-4694-a5f4-6476fc53a188 |  | section | Installation QA Check
checkpoint-status | 6afbdcd5-5305-4264-879c-a15970756b92 |  | checkpoint | Protection tape/stickers removed / cleaned
checkpoint-status | e5e5f4a6-b9f4-407e-a639-de386c357f02 |  | checkpoint | Channel / rails installed (plumb/levelled)
checkpoint-status | 4ac4a11b-4bfa-4ad7-b537-734317ee2c99 |  | checkpoint | Correct cladding size installed (align/plumb)
checkpoint-status | c0f542ae-d679-40b7-a62e-dd6e90a72ca5 |  | checkpoint | Cladding installed as per fixing schedule
checkpoint-status | 627b672d-17ff-492b-b979-0644426d1c63 |  | checkpoint | Sealant joint applied with PEF rod
checkpoint-status | a61135bc-d935-4c7f-8607-95f7bdf28780 |  | checkpoint | Weather-seal applied with PEF rod
checkpoint-status | 4b1d7d9e-adbf-456a-97e3-4c04b55faef9 |  | checkpoint | Cladding free of any defects i.e.scratch / dents
select | d2b14473-8e08-5809-9c44-41afe9f6cc2e |  | dropdown | Cladding checked/accepted by MC as preliminary handover | Yes,No
checklist-sectioned | 48248e37-1907-442a-a2d5-2b92fc323fdd |  | checklist | UCW Panels |  |  |  |  | Yes | UCW Panels | a25f9a2e-a35f-49e8-923d-73e049e064eb
checkpoint-group | 4c7e6f5c-bbc5-4302-827b-c013eac1b3d6 |  | section | Pre-Installation QA Check
checkpoint-status | 3ae7e65b-0320-4411-bcf1-e7cfe64ef0e9 |  | checkpoint | Has the sill trays/bracket, soaker or EPDM rubber installed on both ends
checkpoint-status | 30d6c17d-d8a3-4809-be0b-4806c333260f |  | checkpoint | Has the bolts and serrated washer installed and tighten
checkpoint-status | 8d12b186-6985-48b4-82af-0be177836375 |  | checkpoint | Is the CW bracket installed within tolerance.
checkpoint-status | 016f5ab6-d0e0-4b71-b2a8-1b7958eb7505 |  | checkpoint | CW glass panel received in good condition, any glass broken /missing or aluminium mullion/transom dented or scratched
checkpoint-status | bbadb46a-582f-4fea-833f-f173c56bb117 |  | checkpoint | CW panel received with hook brackets, gaskets, beads and sealed well. IF any gasket is short replace with new full length gasket.
checkpoint-status | becd1d7b-7a1b-48ad-83d4-fcbf8a427ab5 |  | checkpoint | Cladding or Louvre panel pre-fitted are all in good conditions. No damage found.
checkpoint-status | 41043b0d-42ff-4776-8449-494eb31344ef |  | checkpoint | All components installed i.e., beads, gasket, etc.
checkpoint-status | f496ae2b-6724-4ca3-90f0-59c103f2a794 |  | checkpoint | Protection tape at external face removed before lifting
checkpoint-group | 37b53811-b5cc-4106-bbcd-6ebc39f5b879 |  | section | Installation QA Check
checkpoint-status | 6e5598b8-9fc9-4f7b-968e-98d8e276e05a |  | checkpoint | UCW panels installed at correct position, aligned, and levelled
checkpoint-status | faef4751-5647-4001-9e0e-9b719e5dbfc6 |  | checkpoint | Glass or alum cladding panel free of any damages/defects.
checkpoint-status | 5cf45edd-c63b-4770-ada1-ee6c39306312 |  | checkpoint | Gutter sleeves installed and sealed in-place
checkpoint-status | 87865095-252f-43db-984f-d4ac8ed1d7c1 |  | checkpoint | Alignment screw on hook bracket tightened
checkpoint-status | 0749fbbe-e028-42ac-a948-065ccba45bbf |  | checkpoint | L stopper been installed on the bracket to stop panel movement
checkpoint-status | a9e3dab3-20b3-4b16-ae82-f6393935bb64 |  | checkpoint | Seismic beads/rubbers properly installed
checkpoint-status | b0d996a5-dab8-41db-80c0-56440224fd2a |  | checkpoint | Curtain Wall System been check by MC accepted preliminary handover
checklist-sectioned | 1d78d2d1-ca49-4ecb-b5cb-686f0ff918af |  | checklist | UCW Brackets |  |  |  |  | Yes | UCW Brackets | a7121b73-ce39-4ded-ac56-c5fd9ca99661
checkpoint-group | 83730b9c-1d46-4415-b437-994499c60e05 |  | section | Pre-Installation QA Check
checkpoint-status | a6c339e1-3302-4bce-97d3-cd5d35e6fb3d |  | checkpoint | Cast-in channel at correct location/level/set-out
checkpoint-status | 4d6df5fd-c069-466a-8864-e26205c576e1 |  | checkpoint | CW bracket pocket level and within tolerance
checkpoint-status | 75392b1b-a2f2-49dd-aa5d-ff2bfad5fbaa |  | checkpoint | Cast-in channel at correct location/level/set-out
checkpoint-status | 61bfc027-aeeb-466d-93ee-5a3281c0af6c |  | checkpoint | Is the thread slot of cast-in channel clean for T-bolt insertion without damaging thread.
checkpoint-group | 154af2bf-9477-4814-b5cd-1327846116ca |  | section | Installation QA Check
checkpoint-status | c8bfa386-2e53-494f-a465-0341dd95b837 |  | checkpoint | Has the bracket installed as per tag drawing i.e., type, size, quantity.
checkpoint-status | cbbd3b67-df2e-4a2f-9c8d-0d585e2847c5 |  | checkpoint | Has the bracket installed with shims for isolation from steel.
checkpoint-status | 76972da7-cad6-48bf-9e9b-7d5331080b22 |  | checkpoint | Has the bolt been installed with serrated washer and tighten
checkpoint-status | 05595fbe-1c43-4de7-96b3-1549aeda3ce8 |  | checkpoint | Has the alignment screw tighten
checkpoint-status | 851eec27-2917-48cb-b016-a85b3b598dcd |  | checkpoint | Has the L-stopper (Movement stopper) installed on to bracket
checklist-sectioned | 66eaaeba-e800-42bf-a545-148236ad6c96 |  | checklist | Rockwool/Smoke Barrier |  |  |  |  | Yes | Rockwool/Smoke Barrier | b09eac37-f0af-459a-9bb6-1ad7404d1330
checkpoint-group | 304e0e7b-cb61-4dfa-93e7-c4dd083724c7 |  | section | Pre-Installation QA Check
checkpoint-status | 6ab5393d-917b-4a5e-af2d-32dfd4441687 |  | checkpoint | AWF Handover of Rebates/Brackets to MC
checkpoint-status | d69a2721-d2a6-40e9-b69a-ea8c4b685016 |  | checkpoint | Has the bracket rebates grouted by MC
checkpoint-status | 29d9a82b-5256-49fa-ac05-189785393a1f |  | checkpoint | Slab edge free of any debris & dry prior to mineral wool installation
checkpoint-group | e7036fa0-8b7b-4938-a08f-cfdbd9fe8034 |  | section | Installation QA Check
checkpoint-status | 09053303-69c1-44da-94ce-fef731e1263e |  | checkpoint | Z angle carrier has been installed at slab edge
checkpoint-status | 0391cd2a-130e-470e-ae92-2993f404e535 |  | checkpoint | A minimum 150mm tickness fire insluation seated to Z angles without breaks or gaps
checkpoint-status | 00049f61-b94f-4c38-a786-b9fe27f80b35 |  | checkpoint | Fire insulation seated on top/front of bracket/ flushed with floor surface
checkpoint-status | bcf9c27d-84b8-43a1-ac4b-bcd270dce515 |  | checkpoint | Minimum 2mm tick wet HILTI CFS-SP SIL firestop join spray applied completely covering mineral wool overlapping minimum 1/2" onto concrete floor and curtain wall panel
boolean | e1727c17-13f4-552a-9f6b-253e85c4ab60 |  | tickbox | Has the smoke barrier been checked by MC | Yes,No
checklist-sectioned | 555c35c1-bad3-441a-9303-b0826cd892f1 |  | checklist | Parapet Capping |  |  |  |  | Yes | Parapet Capping | b4a32118-f737-4da9-b214-77a0fd795468
checkpoint-group | 0098ef67-0be3-40a8-a9bb-eaa694b0f359 |  | section | Pre-Installation QA Check
checkpoint-no-status | a98ab559-e1ac-4c9e-9644-4be2215faf50 |  | checkpoint | Pre-Installation QA
select | 7c143c3e-2b5c-575c-be5a-84c9a8af9908 |  | dropdown | Is the whole level been handover from MC | Yes,No
checkpoint-status | eb68fa75-c2c3-405e-ad01-89d3516cb7ef |  | checkpoint | Has the structure been completed by Main Contractor
checkpoint-status | 422f1a78-38fb-443f-af7e-610a312a9d99 |  | checkpoint | Has the timber been installed and wrapped with waterproof
checkpoint-status | 6ff282a1-3c94-4a58-9e1b-2f802f3222a6 |  | checkpoint | Is the structure built at correct setting-out as per shop drawing
checkpoint-group | ffb25086-8ea6-45af-92da-97e79166b4f0 |  | section | Installation QA Check
checkpoint-status | 34c90d02-f33a-4a45-b495-6609dbdc2fd2 |  | checkpoint | Has the epdm rubber been installed
checkpoint-status | 071c800a-7257-4399-98da-6d21f65bdb5d |  | checkpoint | Has the rails been installed
checkpoint-status | 01cdf3e7-2d81-461f-8846-d1a28f20c317 |  | checkpoint | Parapet capping installed and leveled
checkpoint-status | d7248e1e-610f-4e8a-bad7-be69516e516b |  | checkpoint | Has the silicon been applied completely
select | c745f6df-0a34-5576-8d73-b5cf445a227a |  | dropdown | Has the parapet capping been check by MC accepted preliminary handover | Yes,No
checklist-flat | e27c9bfb-c76b-48d0-a1a9-9783fc790477 |  | checklist | Peel Adhesion Test |  |  |  |  | Yes | Peel Adhesion Test | b4a40028-ed54-4d96-b52a-da1e0e62b0cd
checkpoint-status | 8af70585-e5d3-4519-be6c-84ab27503c0d |  | checkpoint | Silicone cured prior to test
checkpoint-status | 91d9d9a6-e4f3-44fc-895c-e3f522bea415 |  | checkpoint | Silicone HxW ratio as per standard
checkpoint-status | 4ec615bc-e4de-45c5-8605-e86cc1a360a5 |  | checkpoint | Test Result
checklist-sectioned | 5123d15b-ddd8-4cf3-86b4-90dda9a86c47 |  | checklist | Ranch Sliders |  |  |  |  | Yes | Ranch Sliders | c5010a00-7c3b-4d63-9d7c-fe0c90a5d56f
checkpoint-group | 5a4fed31-525b-4d58-a227-5a4ba6d6b430 |  | section | Main Contractor Handover
checkpoint-status | d617f97c-7a1e-4582-88f9-996ff7afea6a |  | checkpoint | Substrate/membrane applied as per approved dwg
checkpoint-status | 8d456ace-b92c-45de-b10d-9f6e56ddf840 |  | checkpoint | Structure plumb/levelled & correct setting out
checkpoint-status | 60e6a9e1-b00a-495c-9f2d-9779d57a067f |  | checkpoint | Structural opening as per shop drawing
checkpoint-status | 1ebc9315-0da0-4433-b17e-a1e420b588b7 |  | checkpoint | Workface clear from any obstruction/penetration
checkpoint-group | 727499b1-55ac-4780-96f4-d366ed294629 |  | section | Pre-Installation QA Check
checkpoint-status | 97553bbe-e308-4453-9a31-234cd69fae37 |  | checkpoint | Seismic frames installed at correct location
checkpoint-status | d1ed0e48-e943-4f34-8a92-08e679b9d364 |  | checkpoint | Bolts/screws installed and over-sealed
checkpoint-status | 14ff263a-1634-448d-9a2d-790e888835f8 |  | checkpoint | Door panel received in good condition. Any glass broken/ missing or aluminium dented or scratched
checkpoint-status | 28ad7400-a139-4d94-ae42-4180aa215bc2 |  | checkpoint | Glass panel complete with gaskets, beads and sealed. IF any gasket is short replace with new full-length gasket.
checkpoint-status | 2d1810e6-bc0e-480a-882e-b5ac21fc8f45 |  | checkpoint | Door frame received damage free, all mohair and gasket in place. IF any mohair/gasket is short replace with new full-length gasket.
checkpoint-group | a4d4dea7-50df-4cef-95af-fb14b4eefc37 |  | section | Installation QA Check
checkpoint-status | 0ed0c4f8-2b3c-40e3-958a-3d554d036e74 |  | checkpoint | Glass and alum panels installed, aligned, and levelled
checkpoint-status | 1027889b-f798-4801-8a2f-cee176ab06ee |  | checkpoint | Fixings/Packers installed as per schedule
checkpoint-status | cf230d63-c80e-4c91-a28c-59d605aad288 |  | checkpoint | Packers installed with 10mm recessed for PEF rod and sealant application
checkpoint-status | d4167e9b-5f52-4bec-a898-47d9f2385adc |  | checkpoint | Has the sliding door frame installed properly
checkpoint-status | bc9edaa2-305d-4e06-bd98-7547cad07c5a |  | checkpoint | Door panels installed as per shop drawing
checkpoint-status | 19a609d4-5bd1-4067-b7c2-f92ed8b90b6d |  | checkpoint | Wedge rubber/hole caps installed to the frame
checkpoint-status | ff241e66-9dc7-474c-a16b-d2fdbdcfd831 |  | checkpoint | Glass or alum joinery free of any defects
checkpoint-status | 5fcbb83f-a95c-48a5-8b6d-e2372f14c053 |  | checkpoint | Has the door stopper/ bumper installed
checkpoint-status | eca19e12-763d-496f-b3ca-357295f47955 |  | checkpoint | Sliding panel open/close properly
checkpoint-status | beb2e420-b4ab-4f8e-9a66-d779510095fe |  | checkpoint | Hardware/accessories functional (locking)
select | 818ea94f-7927-5a67-a606-04e11281c6bd |  | dropdown | Slider unit checked by MC accepted preliminary handover | Yes,No