## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Consolidation and Packing Checklist |  |  |  |  | Yes | Add Consolidation and Packing Checklist | 90fe9b60-a4d1-4238-b447-63bb6ff58a3d
checkpoint-no-status |  |  | checkpoint | Collate manufactured product and package as specified in the Logistics Plan. After closing each case attach a "Contents Schedule" and verify the following as a part of the QA Process
checkpoint-status |  |  | checkpoint | Confirm the case is clearly labelled and has "Contents" schedule attached. The contents schedule should identify each product individually to ensure we have full traceability of product
checkpoint-status |  |  | checkpoint | Confirm the product inside the case has adequate protection to avoid transit damage
checkpoint-status |  |  | checkpoint | Confirm the case is sturdy and will not rack or twist during shipping and movement
checkpoint-status |  |  | checkpoint | Confirm the case is loaded safely and securely inside the shipping container
checklist-flat |  |  | checklist | Variation Details - |  |  |  |  | Yes | Add Variation | 84730ab7-413b-4f1b-9cb6-63e00e64ffc4
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 28d26279-c304-4689-8317-1deb797dc8fe |  | textbox | Reference/Drawing/Instruction Number
text | 2247155b-6de8-434c-a1e1-058d724a6a62 |  | textbox | Variation Area
text | ae7fc046-dca9-4fab-98f8-374caeb044ec |  | textbox | Materials & labour breakdown
holdpoint |  | Invalid dependant | signoff | Request Variation Acknowledgement
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  | Invalid dependant | signoff | Request Variation Signoff
checklist-flat |  |  | checklist | AWF Handover |  |  |  |  | Yes | AWF Handover Checklist | 01c89271-cc74-459e-bcf9-2eecd9beb689
checkpoint-status |  |  | checkpoint | Has the gutter sill been installed lined and leveled as per approved SD
checkpoint-status |  |  | checkpoint | Has the Bracket been Installed lined and leveled as per approved SD
checkpoint-status |  |  | checkpoint | Has the seismic frame been installed lined and leveled as per approved SD
checkpoint-status |  |  | checkpoint | Has all the jambs been installed and sealed
checkpoint-status |  |  | checkpoint | Has the CW panels been Installed lined and leveled as per approved SD
checkpoint-status |  |  | checkpoint | Has the BAL panels been Installed lined and leveled as per approved SD
checkpoint-status |  |  | checkpoint | Has the BLU panels been Installed lined and leveled as per approved SD
checkpoint-status |  |  | checkpoint | All end flashing installed with EPDM membrane and sealed
checkpoint-status |  |  | checkpoint | Has the rockwool been installed and covered with smoke barrier
checkpoint-status |  |  | checkpoint | Has all the bottom window sill been installed.
checkpoint-status |  |  | checkpoint | Has all the protection tapes been removed
checkpoint-status |  |  | checkpoint | All the doors and windows handles and locks are working smoothly
checkpoint-status |  |  | checkpoint | Final handover check sheet issued to Main Contractor with photos
checklist-sectioned |  |  | checklist | Corner Facade Installation - |  |  |  |  | Yes | Corner Facade Installation Checklist - Int | 27b403d6-8936-440d-9dc1-d733522a4a8f
checkpoint-group |  |  | section | Prestart QA
checkpoint-status |  |  | checkpoint | Handover of openings from DCL to AWF
checkpoint-status |  |  | checkpoint | AWF QA of openings following handover from DCL
checkpoint-group |  |  | section | Corner Facade Installation QA
checkpoint-status |  |  | checkpoint | AWF QA Water proofing to columns
checkpoint-status |  |  | checkpoint | DCL QA of water proofing
checkpoint-status |  |  | checkpoint | AWF install glazing complete
checkpoint-group |  |  | section | Completion/Inspection & Handover
checkpoint-status |  |  | checkpoint | Handover AWF to DCL as complete - All Items inspected & approved
holdpoint |  |  | signoff | Request DCL Signoff
checklist-sectioned |  |  | checklist | Swing Door |  |  |  |  | Yes | Swing Door Checklist | 53d2d978-b1ce-4b2d-bd5e-65a441244bcd
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area tidy and accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-group |  |  | section | Swing Door QA
checkpoint-status |  |  | checkpoint | Door received damaged free from transportation
checkpoint-status |  |  | checkpoint | All four hinges are installed on frame or door
checkpoint-status |  |  | checkpoint | Has the handle been installed to the door
checkpoint-status |  |  | checkpoint | Door has all gaskets/ mohair in place and no damaged found on gaskets/mohair.
checkpoint-status |  |  | checkpoint | Has all the door lock and keys are functioning
checkpoint-status |  |  | checkpoint | Doors installed leveled and closing smoothly.
checkpoint-status |  |  | checkpoint | Check sheet send to Main Contractor with photos
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left tidy and accessible
checklist-sectioned |  |  | checklist | Window - |  |  |  |  | Yes | Add Window Install QA | ce323baf-7bbc-4ce4-819a-43c29b5bb5fe
checkpoint-group |  |  | section | Pre-Install QA
checkpoint-status |  |  | checkpoint | Opening acceptable and ready for window
boolean | 973f4546-a998-4880-92b8-a7772c54c8af |  | tickbox | Position of opening relative to grid line
boolean | c0cf99a6-180f-4df3-b0b4-dca465726dfc |  | tickbox | Height of opening relative to RL
boolean | c4831ef1-0e90-49f5-980b-9f7fdce052a2 |  | tickbox | Timber sub-frame fully complete
boolean | f352fdd3-321c-4c15-b35c-68f13548ecf7 |  | tickbox | All waterproofing elements & flashing tape completed
checkpoint-group |  |  | section | Window Install QA
checkpoint-status |  |  | checkpoint | Frame delivered on site, checked and damage free
checkpoint-status |  |  | checkpoint | Waterproofing membranes correctly seated and fully sealed
checkpoint-status |  |  | checkpoint | Seismic frame lined, leveled and at correct height
checkpoint-status |  |  | checkpoint | Packing does not exceed 15mm / packers correctly seated
checkpoint-status |  |  | checkpoint | Horizontal and vertical air seals applied / tooled to a smooth, neat finish
checkpoint-status |  |  | checkpoint | Window installed plumb and square within seismic frame
checkpoint-status |  |  | checkpoint | Framing completed checked, correct and approved
checkpoint-group |  |  | section | Glazing Install QA
checkpoint-status |  |  | checkpoint | Glass toe and healed correctly
checkpoint-status |  |  | checkpoint | Gaskets engaged/corner neatly mitred
checkpoint-status |  |  | checkpoint | Glazing completed checked, correct and approved
checkpoint-group |  |  | section | Post-Install & Handover
checkpoint-status |  |  | checkpoint | Hardware correctly installed and functioning
checkpoint-status |  |  | checkpoint | Protective tapes & labels
checkpoint-status |  |  | checkpoint | Aluminium surfaces dry wiped to remove light debris and dust
checkpoint-status |  |  | checkpoint | Glass dry wiped to remove dust and marks
checkpoint-status |  |  | checkpoint | All surfaces damage free
checkpoint-status |  |  | checkpoint | Doors commissioned, hardware functioning correctly
checkpoint-status |  |  | checkpoint | All defect work completed and closed out
checkpoint-status |  |  | checkpoint | Final inspection completed, reviewed and approved
checklist-sectioned |  |  | checklist | CC Slab |  |  |  |  | Yes | CC Slab Checklist | 66f24c99-34e5-4dc7-8ef2-d8c0b119e74d
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area tidy and accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-group |  |  | section | CC Slab QA
checkpoint-status |  |  | checkpoint | Access to whole floor
checkpoint-status |  |  | checkpoint | Grid Lines and datum levels are visible and accessible
checkpoint-status |  |  | checkpoint | Handrail and Edge protection fully provided in floor
checkpoint-status |  |  | checkpoint | Concrete surface is clear and no obstructions
checkpoint-status |  |  | checkpoint | Timber rebate boxes are removed by MC
checkpoint-status |  |  | checkpoint | Rebate is smooth and level
checkpoint-status |  |  | checkpoint | Foam inlay still intact with no concrete inside channel
checkpoint-status |  |  | checkpoint | Cast in Channel installed lined/leveled from GL/RL
checkpoint-status |  |  | checkpoint | Power DB box and sufficient lighting provided at this floor
checkpoint-status |  |  | checkpoint | Any location at this floor not handed over
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left tidy and accessible
checklist-flat |  |  | checklist | H&S Week Starting: |  |  |  |  | Yes | Add Weekly H&S Checklist | f8fef88f-426c-4510-9e61-95a7151f7f2a
checkpoint-status |  |  | checkpoint | Task Analysis/JSA
checkpoint-status |  |  | checkpoint | Toolbox Minutes
checkpoint-status |  |  | checkpoint | Hot Works Permits/Confined Spaces/Working at heights
checkpoint-status |  |  | checkpoint | Site Safety Inspection Checklists
checkpoint-status |  |  | checkpoint | Hazard ID
checkpoint-status |  |  | checkpoint | Accident/Incident/Near Miss Investigation Report
checkpoint-status |  |  | checkpoint | Notice/Record of Serious Harm Accident
checkpoint-status |  |  | checkpoint | Additional Heath & Safety Documentation
checklist-sectioned |  |  | checklist | Curtain Wall QA - |  |  |  |  | Yes | Add Curtain Wall Checklist | 5f2d5b08-ace4-47d0-ab44-d903cb90e39b
checkpoint-group |  |  | section | Pre Install QA
checkpoint-status |  |  | checkpoint | Opening acceptable and ready for Curtain Wall
boolean | ed92aa26-4977-4926-96e8-06d43c428e58 |  | tickbox | Position of opening relative to grid line
boolean | e579dcf9-f116-43f8-b7f4-329342c97202 |  | tickbox | Height of opening relative to RL
boolean | 6a6bcbbd-94f5-472a-8b18-226b7481e1d2 |  | tickbox | Timber sub-frame fully complete
boolean | 62c675bf-cc5d-4d45-abb7-26ab58aa7ccf |  | tickbox | All waterproofing elements & flashing tape completed
checkpoint-group |  |  | section | Curtain Wall Install QA
checkpoint-status |  |  | checkpoint | All materials are free from damage / exposed aluminium surfaces are covered with protective tape
checkpoint-status |  |  | checkpoint | Welds cleaned and protective paint applied
checkpoint-status |  |  | checkpoint | Brackets lined, leveled and at correct height
checkpoint-status |  |  | checkpoint | Packing does not exceed 20mm / packers correctly seated
checkpoint-status |  |  | checkpoint | Panel brackets fully engaged on PFC slab brackets
checkpoint-status |  |  | checkpoint | Panels lines, leveled and at correct height
checkpoint-status |  |  | checkpoint | Vertical and horizontal panel joint widths correct
checkpoint-status |  |  | checkpoint | Soakers correctly positioned, fully sealed and neatly tooled
checkpoint-status |  |  | checkpoint | Slab edge smoke stop brackets correctly installed
checkpoint-status |  |  | checkpoint | Fire safe Rockwool installed and compressed by 25%
checkpoint-status |  |  | checkpoint | Sills lined, leveled and at correct height
checkpoint-group |  |  | section | Post Install & Handover
checkpoint-status |  |  | checkpoint | Protective tapes and label removed
checkpoint-status |  |  | checkpoint | Aluminium surfaces dry wiped to remove light debris and dust
checkpoint-status |  |  | checkpoint | Glass dry wiped to remove dust and marks
checkpoint-status |  |  | checkpoint | All surfaces damage free
checkpoint-status |  |  | checkpoint | Defects review carried out and schedule issued to installation team
checkpoint-status |  |  | checkpoint | All defect work completed and closed out
checkpoint-status |  |  | checkpoint | Final inspection competed & approved
checklist-sectioned |  |  | checklist | Alum Panels |  |  |  |  | Yes | Alum Panels Checklist | d5f0e62f-641a-4e23-a1f1-f10f95d520f3
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area tidy and accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-group |  |  | section | Alum Panels QA
checkpoint-status |  |  | checkpoint | Received Handover from Main Contractor
checkpoint-status |  |  | checkpoint | Has waterproof / vapour shield been applied on surface and handed over
checkpoint-status |  |  | checkpoint | Is the applied waterproof / vapour shield compatible with silicon
checkpoint-status |  |  | checkpoint | Grid lines / RL visible and accessible
checkpoint-status |  |  | checkpoint | Panels / Fins received damaged free from transportation
checkpoint-status |  |  | checkpoint | Has the omega bracket installed
checkpoint-status |  |  | checkpoint | Has the alum panel Installed and sealed
checkpoint-status |  |  | checkpoint | Has the protection tape been removed
checkpoint-status |  |  | checkpoint | Has the Vertical fins installed to bracket on CW panel
checkpoint-status |  |  | checkpoint | Has all the U channels installed on the vertical fins
checkpoint-status |  |  | checkpoint | Has the Horizontal fin installed
checkpoint-status |  |  | checkpoint | Check sheet send to Main Contractor with photos
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left tidy and accessible
checklist-sectioned |  |  | checklist | Spandrel Install - |  |  |  |  | Yes | Spandrel Install Checklist - Int | b3ac3978-d3e9-4a80-a769-69b9e03518a4
checkpoint-group |  |  | section | Prestart QA
checkpoint-status |  |  | checkpoint | Handover of openings from DCL to AWF
checkpoint-status |  |  | checkpoint | AWF QA of openings following handover from DCL
checkpoint-group |  |  | section | Spandrel Install QA
checkpoint-status |  |  | checkpoint | Inspect water proofing wrap AWF QA
checkpoint-status |  |  | checkpoint | Inspect aluminium back pan, insulation and seal
checkpoint-status |  |  | checkpoint | Install ducts (by others)
checkpoint-status |  |  | checkpoint | Air seal ducts (by AWF)
checkpoint-status |  |  | checkpoint | Install air seals to perimeter of EXO nodes
checkpoint-status |  |  | checkpoint | DCL QA of air sealed penetrations to spandrel
checkpoint-status |  |  | checkpoint | Hang Panels
checkpoint-status |  |  | checkpoint | Seal Panels
checkpoint-group |  |  | section | Completion/Inspection & Handover
checkpoint-status |  |  | checkpoint | Trade clean completed
checkpoint-status |  |  | checkpoint | Handover AWF to DCL as complete - All Items inspected & approved
holdpoint |  |  | signoff | Request DCL Signoff
checklist-sectioned |  |  | checklist | Brackets |  |  |  |  | Yes | Brackets Checklist | 6a8c1586-d95e-46b6-8611-4458180a2a53
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area tidy and accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-group |  |  | section | Brackets QA
checkpoint-status |  |  | checkpoint | Received Handover from Main Contractor
checkpoint-status |  |  | checkpoint | Rebate is smooth and level
checkpoint-status |  |  | checkpoint | Foam inlay still intact with no concrete inside channel
label | a5cc8a41-3e3b-4194-af84-8f48f79e8db2 |  | note | If concrete inside CC need to use expansion/chem set
checkpoint-status |  |  | checkpoint | Installation area free from obstructions
checkpoint-status |  |  | checkpoint | Bracket installed lined/leveled from GL & RL
checkpoint-status |  |  | checkpoint | Bracket provided with solid packing/shims
checkpoint-status |  |  | checkpoint | Serrated washer engaged correctly and flat washers installed
checkpoint-status |  |  | checkpoint | Bracket installed with T bolt or expansion bolt
checkpoint-status |  |  | checkpoint | Bolt torqued to 80 NM
checkpoint-status |  |  | checkpoint | Has the steel been holed with 14mmDia
label | 13ccc7a2-c2e3-4e47-bc77-c9a14d07f37b |  | note | Only fill this for Balustrade brackets
checkpoint-status |  |  | checkpoint | Check sheet send to Main Contractor with photos
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left tidy and accessible
checklist-flat |  |  | checklist | Ballustrade - |  |  |  |  | Yes | Add Ballustrade Installation Checklist | 5ec71ee7-005c-4d15-a74b-51c91967817e
checkpoint-status |  |  | checkpoint | Waterproofed opening hand-over
checkpoint-status |  |  | checkpoint | Channel/Chem set-out
checkpoint-status |  |  | checkpoint | Glazing
checkpoint-status |  |  | checkpoint | Top rail flashing
checkpoint-status |  |  | checkpoint | Aluminium capping
checkpoint-status |  |  | checkpoint | Seal/Trade clean
checklist-sectioned |  |  | checklist | Gutters |  |  |  |  | Yes | Gutters Checklist | ed286308-3663-40a7-a085-624bb9bbf2f5
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area tidy and accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-group |  |  | section | Gutters QA
checkpoint-status |  |  | checkpoint | Received Handover from Main Contractor
checkpoint-status |  |  | checkpoint | Grid lines visible and accessible
checkpoint-status |  |  | checkpoint | Structure slab floor surface prepration completed with Waterproofing or vapour shied
checkpoint-status |  |  | checkpoint | Floor structure is compatible for sealant application
checkpoint-status |  |  | checkpoint | Gutters received damaged free from transportation
checkpoint-status |  |  | checkpoint | Gutter has suitable weep holes for drainage
checkpoint-status |  |  | checkpoint | Gutter installed lined/leveled from GL & RL
checkpoint-status |  |  | checkpoint | Gutter provided with solid packing
checkpoint-status |  |  | checkpoint | Gutter installed with suitable chem bolt
checkpoint-status |  |  | checkpoint | Bolt torqued to 80 NM
checkpoint-status |  |  | checkpoint | Has all the mechanical fixings been sealed properly
checkpoint-status |  |  | checkpoint | Has gutter been sealed for water bund test.
checkpoint-status |  |  | checkpoint | Gutter water test conducted and witnessed
checkpoint-status |  |  | checkpoint | Check sheet send to Main Contractor with photos
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left tidy and accessible
checklist-sectioned |  |  | checklist | Door - |  |  |  |  | Yes | Add Door Install QA | 3d562249-276b-4919-b54b-ebc0a0f84a01
checkpoint-group |  |  | section | Pre Install QA
checkpoint-status |  |  | checkpoint | Opening Acceptable and ready for door
boolean | 8899be65-62f8-4754-b8bb-49ac7b511d4d |  | tickbox | Position of opening relative to grid line
boolean | e84fdbbd-c2a6-4552-a2a1-b3320e814c90 |  | tickbox | Height of opening relative to RL
boolean | 8c93e877-d4df-4437-9fe8-cbf54805484f |  | tickbox | Timber sub-frame fully complete
boolean | 21933b79-503c-43e8-be38-2f61e18551d9 |  | tickbox | All waterproofing elements & flashing tape completed
checkpoint-group |  |  | section | Install QA
checkpoint-status |  |  | checkpoint | Materials inspected on arrival and damage free
checkpoint-status |  |  | checkpoint | Waterproofing membranes correctly seated and fully sealed
checkpoint-status |  |  | checkpoint | Seismic frame lines, leveled and at correct height
checkpoint-status |  |  | checkpoint | Packing does not exceed 15mm/packers correctly sealed
checkpoint-status |  |  | checkpoint | Horizontal and vertical air seals applied/tooled to a smooth, neat finish
checkpoint-status |  |  | checkpoint | Door installed plumb and square within seismic frame
checkpoint-status |  |  | checkpoint | Glass toe and healed correctly
checkpoint-status |  |  | checkpoint | Gaskets engaged/corners neatly mitred
checkpoint-status |  |  | checkpoint | Hardware correct installed and functioning
checkpoint-group |  |  | section | Post-Install & Handover
checkpoint-status |  |  | checkpoint | Protective tapes & labels removed
checkpoint-status |  |  | checkpoint | Aluminium surfaces dry wiped to remove light debris and dust
checkpoint-status |  |  | checkpoint | Glass dry wiped to remove dust and marks
checkpoint-status |  |  | checkpoint | All surfaces damage free
checkpoint-status |  |  | checkpoint | Doors commissioned, hardware functioning correctly
checkpoint-status |  |  | checkpoint | All defect work completed and closed out
checkpoint-status |  |  | checkpoint | Final inspection completed, reviewed and approved
checklist-sectioned |  |  | checklist | Jambs |  |  |  |  | Yes | Jambs Checklist | c0b17e3c-023f-4158-8d0e-aa59986d942f
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area tidy and accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-group |  |  | section | Gutters QA
checkpoint-status |  |  | checkpoint | Received Handover from Main Contractor
checkpoint-status |  |  | checkpoint | Grid lines visible and accessible
checkpoint-status |  |  | checkpoint | Jambs received damaged free from transportation
checkpoint-status |  |  | checkpoint | Structure surface prepration completed with Waterproofing or vapour shied
checkpoint-status |  |  | checkpoint | Structure is compatible for seleant application
checkpoint-status |  |  | checkpoint | Jambs installed lined/leveled from GL & RL
checkpoint-status |  |  | checkpoint | Jambs provided with solid packing
checkpoint-status |  |  | checkpoint | EPDM Membrane fixed without wear / tear where applicable
checkpoint-status |  |  | checkpoint | EPDM Membrane mechanically fixed and sealed where applicable
checkpoint-status |  |  | checkpoint | Jambs installed with suitable fixings
checkpoint-status |  |  | checkpoint | Has the side L angle flashing been fixed
checkpoint-status |  |  | checkpoint | Has all the mechanical fixings been sealed properly
checkpoint-status |  |  | checkpoint | Check sheet send to Main Contractor with photos
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left tidy and accessible
checklist-sectioned |  |  | checklist | Glass Balustrade Installation - |  |  |  |  | Yes | Glass Balustrade Installation Checklist - Int | cc4e1c08-4463-4836-bb9b-a5068d4847db
checkpoint-group |  |  | section | Prestart QA
checkpoint-status |  |  | checkpoint | Glass Balustrade area and item ready for install
checkpoint-group |  |  | section | Glass Balustrade Installation QA
checkpoint-status |  |  | checkpoint | Install channel and bolted connections
checkpoint-status |  |  | checkpoint | Install glass
checkpoint-status |  |  | checkpoint | Install top channel
checkpoint-group |  |  | section | Completion/Inspection & Handover
checkpoint-status |  |  | checkpoint | Trade Clean Completed
checkpoint-status |  |  | checkpoint | Handover AWF to DCL as complete - All Items inspected & approved
holdpoint |  |  | signoff | Request DCL Signoff
checklist-sectioned |  |  | checklist | Curtain Wall Panels |  |  |  |  | Yes | Curtain Wall Panels Checklist | 52b876ed-d3cf-46dc-b6c1-cfcf37291a93
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area tidy and accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-group |  |  | section | Curtain Walls QA
checkpoint-status |  |  | checkpoint | Received Handover from Main Contractor
checkpoint-status |  |  | checkpoint | Grid lines visible and accessible
checkpoint-status |  |  | checkpoint | Panels received damaged free from transportation
checkpoint-status |  |  | checkpoint | Panel gutter chamber has suitable weep holes for drainage
checkpoint-status |  |  | checkpoint | Panel gutter chamber has suitable weep holes for drainage
checkpoint-status |  |  | checkpoint | Panel has all gaskets in place and free from wear and tear. No damaged gaskets.
checkpoint-status |  |  | checkpoint | Panel has gutter splice
checkpoint-status |  |  | checkpoint | Panel has any missing glass / broken glass
checkpoint-status |  |  | checkpoint | Has the starter gutter been installed lined and leveled.
label | 3b0ee03f-cac2-4538-b063-3a2a70d9e608 |  | note | Only at starting point of UCW. GF or Level 1
checkpoint-status |  |  | checkpoint | Panel gutter provided with close cell form
checkpoint-status |  |  | checkpoint | Panel gutter splice sealed top/ bottom and sides.
checkpoint-status |  |  | checkpoint | Panels installed lined/leveled from GL & RL
checkpoint-status |  |  | checkpoint | Has the panel alignment screw been installed
checkpoint-status |  |  | checkpoint | Has the sealing on joint between CW panel completed
checkpoint-status |  |  | checkpoint | Check sheet send to Main Contractor with photos
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left tidy and accessible
checklist-sectioned |  |  | checklist | Spandrel - |  |  |  |  | Yes | Add Spandrel QA Checklist | da3ac9f9-3536-4145-8fa1-5751976f1067
checkpoint-group |  |  | section | Pre-Install QA
checkpoint-status |  |  | checkpoint | Opening acceptable and ready for Spandrel
boolean | 5823a5d8-86d4-42a0-aea3-03c1ca6746b4 |  | tickbox | Position of opening relative to grid line
boolean | 27ed9988-c9e2-44cd-8cb5-cd349416b0b8 |  | tickbox | Height of opening relative to RL
boolean | daaa7dae-e378-4d61-a7b7-a3815743910c |  | tickbox | Timber sub-frame fully complete
boolean | 1664f643-d2a0-4d98-9aba-4a8762770138 |  | tickbox | All waterproofing elements & flashing tape completed
checkpoint-group |  |  | section | Spandrel Install QA
checkpoint-status |  |  | checkpoint | All materials are free from damage / exposed aluminium surfaces are covered with protective tape
checkpoint-status |  |  | checkpoint | Welds cleaned and protective paint applied
checkpoint-status |  |  | checkpoint | Brackets lined, leveled and at correct height
checkpoint-status |  |  | checkpoint | Tie rods lined, leveled and at correct height
checkpoint-status |  |  | checkpoint | Packing does not exceed 20mm / packers correctly seated
checkpoint-status |  |  | checkpoint | Panel brackets fully engaged on supporting structure
checkpoint-status |  |  | checkpoint | Panels lined, leveled and at correct height
checkpoint-status |  |  | checkpoint | Vertical and horizontal panel joint widths correct
checkpoint-status |  |  | checkpoint | Soakers correctly positioned, fully sealed and neatly tooled
checkpoint-status |  |  | checkpoint | Slab edge smoke stop brackets correctly installed
checkpoint-status |  |  | checkpoint | Fire safe Rockwool installed and compressed by 25%
checkpoint-group |  |  | section | Post-Install & Handover
checkpoint-status |  |  | checkpoint | Hardware correctly installed and functioning
checkpoint-status |  |  | checkpoint | Protective tapes & labels
checkpoint-status |  |  | checkpoint | Aluminium surfaces dry wiped to remove light debris and dust
checkpoint-status |  |  | checkpoint | Glass dry wiped to remove dust and marks
checkpoint-status |  |  | checkpoint | All surfaces damage free
checkpoint-status |  |  | checkpoint | Doors commissioned, hardware functioning correctly
checkpoint-status |  |  | checkpoint | All defect work completed and closed out
checkpoint-status |  |  | checkpoint | Final inspection completed, reviewed and approved
checklist-sectioned |  |  | checklist | Balustrade Glass Panels |  |  |  |  | Yes | Balustrade Glass Panels Checklist | 44b2da85-a880-48a1-9436-d137a2d302d3
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area tidy and accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-group |  |  | section | Balustrade Glass QA
checkpoint-status |  |  | checkpoint | Received Handover from Main Contractor
checkpoint-status |  |  | checkpoint | Grid lines visible and accessible
checkpoint-status |  |  | checkpoint | Glass received damaged free from transportation
checkpoint-status |  |  | checkpoint | Has the bracket been installed and all component screwed
checkpoint-status |  |  | checkpoint | Are there any missing glass / broken glass
checkpoint-status |  |  | checkpoint | Glass panels installed lined/leveled from GL & RL
checkpoint-status |  |  | checkpoint | Has the cover flashing (external / internal) been installed
checkpoint-status |  |  | checkpoint | Has the capping rail been installed sealed completely.
checkpoint-status |  |  | checkpoint | Check sheet send to Main Contractor with photos
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left tidy and accessible
checklist-sectioned |  |  | checklist | Internal Sliding Door Installation - |  |  |  |  | Yes | Internal Sliding Door Installation Checklist - Int | 2075bf9a-118a-4c46-a9de-c35527be7706
checkpoint-group |  |  | section | Prestart QA
checkpoint-status |  |  | checkpoint | Handover of openings from DCL to AWF
checkpoint-group |  |  | section | Internal Sliding Door Installation QA
checkpoint-status |  |  | checkpoint | Install tracking and level
checkpoint-status |  |  | checkpoint | Glaze openings
checkpoint-group |  |  | section | Completion/Inspection & Handover
checkpoint-status |  |  | checkpoint | Trade Clean Completed
checkpoint-status |  |  | checkpoint | Handover AWF to DCL as complete - All Items inspected & approved
holdpoint |  |  | signoff | Request DCL Signoff
checklist-sectioned |  |  | checklist | Balcony Panels |  |  |  |  | Yes | Balcony Panels Checklist | fbf7e51f-66ab-46f0-acf2-c79791bea74c
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area tidy and accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-group |  |  | section | Balcony Panels QA
checkpoint-status |  |  | checkpoint | Received Handover from Main Contractor
checkpoint-status |  |  | checkpoint | Grid lines visible and accessible
checkpoint-status |  |  | checkpoint | Panels received damaged free from transportation
checkpoint-status |  |  | checkpoint | Panel has all gaskets / Mohair in place and free from wear and tear. No damaged gaskets / Mohair.
checkpoint-status |  |  | checkpoint | Panel has any missing glass / broken glass
checkpoint-status |  |  | checkpoint | Has the bracket been installed Line and leveled
checkpoint-status |  |  | checkpoint | Has the timber supporting form installed by Main Contractor
checkpoint-status |  |  | checkpoint | Has the bottom flashing installed and first layer of waterproofing installed
checkpoint-status |  |  | checkpoint | Panels installed lined/leveled from GL & RL
checkpoint-status |  |  | checkpoint | Has secondary bottom flashing installed above waterproofing
checkpoint-status |  |  | checkpoint | Has all the top / bottom / side flashing installed and sealed.
checkpoint-status |  |  | checkpoint | Has the BAL-AL panel omega bracket installed and sealed
checkpoint-status |  |  | checkpoint | Has the BAL-AL panel Installed and sealed
checkpoint-status |  |  | checkpoint | Has the BLU panel bracket fixed and sealed
checkpoint-status |  |  | checkpoint | Check sheet send to Main Contractor with photos
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left tidy and accessible
checklist-sectioned |  |  | checklist | Balustrade Panels |  |  |  |  | Yes | Balustrade Panels Checklist | 2c1236ba-a1ad-473a-a9aa-4120be09102a
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area tidy and accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-group |  |  | section | Balustrade QA
checkpoint-status |  |  | checkpoint | Received Handover from Main Contractor
checkpoint-status |  |  | checkpoint | Grid lines visible and accessible
checkpoint-status |  |  | checkpoint | Panels received damaged free from transportation
checkpoint-status |  |  | checkpoint | Panel has all gaskets in place and free from wear and tear. No damaged gaskets.
checkpoint-status |  |  | checkpoint | Panel has gutter splice
checkpoint-status |  |  | checkpoint | Panel has any missing glass / broken glass
checkpoint-status |  |  | checkpoint | Balcony alum panel installed leveled and sealed
checkpoint-status |  |  | checkpoint | Cast-in channel/ bracket installed and inspected.
checkpoint-status |  |  | checkpoint | Panels installed lined/leveled from GL & RL
checkpoint-status |  |  | checkpoint | Has the panel alignment screw been installed.
checkpoint-status |  |  | checkpoint | Has the panel top / bottom cover been installed sealed completely.
checkpoint-status |  |  | checkpoint | Check sheet send to Main Contractor with photos
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left tidy and accessible
checklist-flat |  |  | checklist | Aluminium Panel - |  |  |  |  | Yes | Add Aluminium Panel Installation Checklist | 01a2c6d8-7e29-4f5a-9e8e-f5dd84ac92d9
checkpoint-status |  |  | checkpoint | Wall is waterproofed and hand-over
checkpoint-status |  |  | checkpoint | Rail is installed according to panel lay out
checkpoint-status |  |  | checkpoint | Panel install plumb and rigth gap
checkpoint-status |  |  | checkpoint | Gap/joint is sealed
checkpoint-status |  |  | checkpoint | Defects fixed
checkpoint-status |  |  | checkpoint | Trade cleaned
checklist-sectioned |  |  | checklist | Floors |  |  |  |  | Yes | Floors Checklist | 92a62c5c-f3f6-4b4a-9b1e-ad80612234c8
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area tidy and accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-group |  |  | section | Floor QA
checkpoint-status |  |  | checkpoint | Access to whole floor
checkpoint-status |  |  | checkpoint | Grid Lines and datum levels are visible and accessible
checkpoint-status |  |  | checkpoint | Handrail and Edge protection fully provided in floor
checkpoint-status |  |  | checkpoint | Concrete surface is clear and no obstructions
checkpoint-status |  |  | checkpoint | Concrete floor surface preparation completed with Waterproofing or vapour shied
checkpoint-status |  |  | checkpoint | Surface preparation at floor structure is compatible for sealant application
checkpoint-status |  |  | checkpoint | Power DB box and sufficient lighting provided at this floor
checkpoint-status |  |  | checkpoint | Any location at this floor not handed over
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left tidy and accessible
checklist-sectioned |  |  | checklist | Seismic Frame |  |  |  |  | Yes | Seismic Frame Checklist | 7f80e06d-47df-45d9-8c1e-0e1ebd4f6dff
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area tidy and accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-group |  |  | section | Seismic Frame QA
checkpoint-status |  |  | checkpoint | Received Handover from Main Contractor
checkpoint-status |  |  | checkpoint | Has the water proof completed top / bottom and handed over
checkpoint-status |  |  | checkpoint | Floor structure is compatible for sealant application
checkpoint-status |  |  | checkpoint | Nib/ Upstand is smooth and level
checkpoint-status |  |  | checkpoint | Frame installed lined/leveled from GL & RL
checkpoint-status |  |  | checkpoint | Splice been installed to the frame and sealed all around
checkpoint-status |  |  | checkpoint | Frame provided with solid packing and top/bottom gap is within tolerance (15mm)
checkpoint-status |  |  | checkpoint | Has all the screws heads been sealed
checkpoint-status |  |  | checkpoint | Has the side and head flashing been fitted in front of seismic frame and sealed top and bottom.
checkpoint-status |  |  | checkpoint | Check sheet send to Main Contractor with photos
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left tidy and accessible
checklist-sectioned |  |  | checklist | Receipt of Materials into Fabrication Facility Checklist |  |  |  |  | Yes | Add Receipt of Materials into Fabrication Facility Checklist | 6bfd3f61-33e5-403a-89cc-c2f5d2e51915
checkpoint-group |  |  | section | Receipt of Extrusion
checkpoint-status |  |  | checkpoint | Reconcile delivery to order
checkpoint-status |  |  | checkpoint | Confirm lengths & dimensions are accurate
checkpoint-status |  |  | checkpoint | Confirm extrusion profiles are accurate
checkpoint-status |  |  | checkpoint | Confirm no damage or deformation
checkpoint-status |  |  | checkpoint | Confirm surface finish to specification
checkpoint-group |  |  | section | Receipt of Glass
checkpoint-status |  |  | checkpoint | Reconcile delivery to order checks
checkpoint-status |  |  | checkpoint | Check glass type and thickness
checkpoint-status |  |  | checkpoint | Confirm correct dimensions, holes and any engineering details
checkpoint-status |  |  | checkpoint | Visual check of all glass surfaces and edges - damage free
checkpoint-group |  |  | section | Receipt of Panels
checkpoint-status |  |  | checkpoint | Reconcile delivery to order checks
checkpoint-status |  |  | checkpoint | Confirm accuracy of dimensions and configuration
checkpoint-status |  |  | checkpoint | Confirm surface finish to specification
checkpoint-status |  |  | checkpoint | Check surface for damage or scratches
checkpoint-group |  |  | section | Receipt of Hardware and Fittings
checkpoint-status |  |  | checkpoint | Reconcile delivery to order
checkpoint-status |  |  | checkpoint | Confirm product is correct to control sample and specification
checkpoint-group |  |  | section | Receipt of Sealant
checkpoint-status |  |  | checkpoint | Reconcile delivery to order
checkpoint-status |  |  | checkpoint | Confirm product is within shelf life expectations
checklist-sectioned |  |  | checklist | Sliding Door |  |  |  |  | Yes | Sliding Door Checklist | d5aba917-9875-4c19-b195-ea7eec613595
checkpoint-group |  |  | section | Pre Start
checkpoint-status |  |  | checkpoint | Area tidy and accessible
checkpoint-status |  |  | checkpoint | Substrate acceptable
checkpoint-group |  |  | section | Sliding Door QA
checkpoint-status |  |  | checkpoint | Seismic Frame / door slider installed.
checkpoint-status |  |  | checkpoint | Panels / frames received damaged free from transportation
checkpoint-status |  |  | checkpoint | Panel has all gaskets/ mohair in place and free from wear and tear. No damaged gaskets.
checkpoint-status |  |  | checkpoint | Panel has any missing glass / broken glass
checkpoint-status |  |  | checkpoint | Sliding door has handles / locks and free from damages.
checkpoint-status |  |  | checkpoint | Has the door lock catcher been installed on the frame.
checkpoint-status |  |  | checkpoint | Doors installed leveled and closing smoothly.
checkpoint-status |  |  | checkpoint | Check sheet send to Main Contractor with photos
checkpoint-group |  |  | section | Handover
checkpoint-status |  |  | checkpoint | Area left tidy and accessible
checklist-sectioned |  |  | checklist | Steel Post/Water Proofing/External Sliding Door/Base Nodes Checklist - |  |  |  |  | Yes | Steel Post/Water Proofing/External Sliding Door/Base Nodes Checklist | 59e36f3f-9b1f-45d8-8094-3c382bec5e95
checkpoint-group |  |  | section | Prestart QA
checkpoint-status |  |  | checkpoint | Handover of openings from DCL to AWF
checkpoint-status |  |  | checkpoint | AWF QA of openings following handover from DCL
checkpoint-group |  |  | section | Steel Post/Water Proofing/External Sliding Doors/Base Nodes QA
checkpoint-status |  |  | checkpoint | Install steel posts and check for level
checkpoint-status |  |  | checkpoint | Install water proofing
checkpoint-status |  |  | checkpoint | AWF QA of installed water proofing
holdpoint |  |  | signoff | Request DCL Approval/Signoff
checkpoint-status |  |  | checkpoint | Install perimeter frames
checkpoint-status |  |  | checkpoint | AWF QA of perimeter frames
checkpoint-status |  |  | checkpoint | AWF/DCL QA flood test cills and report
checkpoint-status |  |  | checkpoint | Air seal internal perimeter
checkpoint-status |  |  | checkpoint | AWF/DC QA air seal lines
holdpoint |  |  | signoff | Request Signoff
checkpoint-status |  |  | checkpoint | Adjust rollers
checkpoint-status |  |  | checkpoint | Install door stops
checkpoint-status |  |  | checkpoint | Install threshold trims
checkpoint-status |  |  | checkpoint | Adjust locks
checkpoint-status |  |  | checkpoint | Install external sliding doors and fixed panles
checkpoint-status |  |  | checkpoint | Install base nodes within +-10mm
checkpoint-status |  |  | checkpoint | DCL water test
checkpoint-group |  |  | section | Completion/Inspection & Handover
checkpoint-status |  |  | checkpoint | Trade clean completed
checkpoint-status |  |  | checkpoint | Handover AWF to DCL as complete - All Items inspected, approved and functioning
holdpoint |  |  | signoff | Request DCL Signoff
checklist-sectioned |  |  | checklist | Manufacturing & Fabrication Checklist |  |  |  |  | Yes | Add Manufacturing & Fabrication Checklist | 72db1373-2a18-4de6-91a5-894d4b862abc
checkpoint-group |  |  | section | Cutting of Extrusions
checkpoint-status |  |  | checkpoint | Check angles and square cuts as designed
checkpoint-status |  |  | checkpoint | Check length (point to point measurement)
checkpoint-status |  |  | checkpoint | Check cut quality
checkpoint-status |  |  | checkpoint | Check labelling of bars
checkpoint-status |  |  | checkpoint | Check appropriate extrusion protection is in place
checkpoint-group |  |  | section | Machining and Preparation
checkpoint-status |  |  | checkpoint | Check milling depths are correct
checkpoint-status |  |  | checkpoint | Check hole centres and positions
checkpoint-status |  |  | checkpoint | Check hole sizes
checkpoint-group |  |  | section | Assembly
checkpoint-status |  |  | checkpoint | Check SJS applied to required joints
checkpoint-status |  |  | checkpoint | Check gaskets are correct types
checkpoint-status |  |  | checkpoint | Check gaskets are not stretched
checkpoint-status |  |  | checkpoint | Check platform sealing is correct to detail
checkpoint-status |  |  | checkpoint | Check screws / crimping is to appropriate tolerances
checkpoint-group |  |  | section | Hardware Fitting
checkpoint-status |  |  | checkpoint | Check correct components, mohair and hardware is fitted
checkpoint-status |  |  | checkpoint | Check hardware fixing is secure and that hardware functions correctly
checkpoint-group |  |  | section | Glazing
checkpoint-status |  |  | checkpoint | Check setting blocks are in the correct positions
checkpoint-status |  |  | checkpoint | Check glass installed to the correct orientation
checkpoint-status |  |  | checkpoint | Check glazing beads are notched for drainage
checkpoint-status |  |  | checkpoint | Check correct glazing wedge is used
checkpoint-status |  |  | checkpoint | Check glazing wedge is not stretched
checkpoint-status |  |  | checkpoint | Check bead gaps are to acceptable tolerances
checkpoint-group |  |  | section | Final Assembly
checkpoint-status |  |  | checkpoint | Check clean and damage free
checkpoint-status |  |  | checkpoint | Check protection is in place
checklist-sectioned |  |  | checklist | Exo Installation Installation - |  |  |  |  | Yes | Exo Installation Checklist - Int | 07816465-aa0c-4b93-a9dd-89ff66cd8b96
checkpoint-group |  |  | section | Prestart QA
checkpoint-status |  |  | checkpoint | Handover of openings from DCL to AWF
checkpoint-status |  |  | checkpoint | AWF QA of openings following handover from DCL
checkpoint-group |  |  | section | Exo Installation QA
checkpoint-status |  |  | checkpoint | Set out completed and accurate
checkpoint-status |  |  | checkpoint | Bolt and fix brackets to nodes
checkpoint-status |  |  | checkpoint | Install and adjust struts and bolts fix to node brackets
checkpoint-status |  |  | checkpoint | Check isolation disks are installed
checkpoint-status |  |  | checkpoint | Install rear cover
checkpoint-status |  |  | checkpoint | install internal cover
checkpoint-status |  |  | checkpoint | Adjust covers
checkpoint-group |  |  | section | Completion/Inspection & Handover
checkpoint-status |  |  | checkpoint | Handover AWF to DCL as complete - All Items inspected & approved
holdpoint |  |  | signoff | Request DCL Signoff
folder-normal |  | folder-normal must be display normal but was flat | checklist | Material Procurement Checklist |  |  |  |  | Yes | Add Material Procurement Checklist | fe1fe78d-cd6b-462a-a31e-c08f2d400725
checklist-flat |  |  | checklist-flat | Material Procurement
checkpoint-status |  | checkpoint-status must be display normal but was flat Not allowed as a child of folder-normal. | checkpoint | Orders are placed with our respective suppliers in China
checkpoint-status |  | checkpoint-status must be display normal but was flat Not allowed as a child of folder-normal. | checkpoint | Aluminium Extrusions
checkpoint-status |  | checkpoint-status must be display normal but was flat Not allowed as a child of folder-normal. | checkpoint | Aluminium Panels and Flashings
checkpoint-status |  | checkpoint-status must be display normal but was flat Not allowed as a child of folder-normal. | checkpoint | Sealants
checkpoint-status |  | checkpoint-status must be display normal but was flat Not allowed as a child of folder-normal. | checkpoint | Glass
checkpoint-status |  | Not allowed as a child of folder-normal. | checkpoint | Hardware and Components
checkpoint-status |  | Not allowed as a child of folder-normal. | checkpoint | Gaskets
checkpoint-status |  | Not allowed as a child of folder-normal. | checkpoint | Fixings
checklist-flat |  |  | checklist | Transitional Facility and NZ Warehouse Checklist |  |  |  |  | Yes | Add Transitional Facility and NZ Warehouse Checklist | 5adbeb5d-8d85-4381-901b-d024badd952f
checkpoint-no-status |  |  | checkpoint | Receive the shipping containers in NZ and unload, ensuring the following QA Procedures are followed and checked
checkpoint-status |  |  | checkpoint | Check that the case is complete and has no visible damage or distortion/breakage
checkpoint-status |  |  | checkpoint | Confirm that contents marked on the COntents Schedule are reconciled and logged in as "In Warehouse"
checkpoint-status |  |  | checkpoint | Unpack and store items appropriately, and carry out a visual check for any transit damage, (rubbing of surfaces etc.)