## 0.5 FBS - Baldwin Rd
|  | Central Waikato NOC - Inspection & Test Plan - Catalogue Foam Stabilisation | [6 empty] | Document Number: | Pavement Renewals - Foam Stabilisation
|  | Site Name: | Earthquake Gully 1 23 - 24 | [5 empty] | Revision Number: | 0.9A | Number of Pages: |  | 10
|  | Location: | SH1 01N-0613 7099 7935 | [5 empty] | Prepared: | M Owens | Date: |  | 2022-10-17
[9 empty] | Approved: | G Apiti | Date: |  | 2022-10-04
ITEM NUMBER | ACTIVITY DESCRIPTION |  | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | INSPECTORATE V/W/H |  |  |  | RESPONSIBLE PERSON | Sign & date if appropriate | RECORDS / REMARKS
[7 empty] | V=VERIFICATION, W=WITNESS, H =HOLD |  |  |  | As per Quality Plan
[7 empty] | Type | Assessor signature | Description |  |  |  | incl NCR ref
1 | Preliminary and General
1.1 | Construction Programme Completion |  | Confirmation | Best Practice Contract Specific MMP | Before work commences | Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date | V |  |  |  | Renewals Manager
1.2 | Approved RQP |  | Confirmation | Contract Specification | At least 24hrs before establishment or work commences | Principal's Acceptance according to guidelines in Appendix 6.3 | H |  | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours before establishing on site. |  | Renewals Manager |  | NZTA to approve.
1.3 | Notification of Intention to Start Work |  | Notification |  | Before work commences | Letter drop to local residents | H |  | Hold point - No physical work is to be commenced on site until notification has been sent to residents - no later than 24 hours prior to establishing on site. |  | Construction Supervisor / Renewals Engineer |  | NZTA to approve letter drop before distribution to residents.
1.4 | Traffic Management | TMP | Visual check | CoPTTM | Before work commences | TMP checked and approved Plans approved Current EED (if applicable) Size of site area to be checked to allow machinery to operate safely | H |  | Hold point - No traffic management is to be set up until TMP has been checked and approved |  | STMS |  | CAR No.
TMP No.
1.5 | Design Report Approval |  | Confirmation | NZTA NOC Rehab Catalogue Design & Treatment Approach | Before work commences | Principal Acceptance's acceptance according to NZTA Catalogue Design Approach document | H |  | Hold point - Review meeting with NZTA National & Regional Leads and Downer NOC Managers & Pavement Designers/Reviewers |  | NZTA Network Manager & Accreditied Designer |  | NZTA Approval to Proceed NTC No.
1.6 | Seal Design Approval |  | Confirmation | Review and Sign off by Downer Regional Sealing Manager | Before work commences | Downer Regional Sealing Manager reviews and signs off on Seal Design proposed. | H |  | Hold point - Review and approval of seal design completed |  | Regional Sealing Manager
1.7 | Project Manager Handover |  | Confirmation | Review and Sign off by Downer Designer to PM | Before work commences | Downer Technical Services Team Designer reviews and signs off on Handover. | H |  | Hold point - Handover completed |  | Regional Engineering Team Designer
1.8 | Crew Pack |  |  | Items to be included: | Before work commences | Approved TMP | H |  |  |  | Downer PM
Services location plans / Marked out
Approved RQP
Approved for Construction drawings & Pavement Design
Ramm data
Approved ITP
Crew Briefing Plan
2 | Setout / Site Preparation
2.1 | Setout |  | Survey | As per approved drawings | Per installation / Site | Design strings /design surface model loaded for machine control | V |  | Machine control requirement. Downer surveyor required for MC upload and verification of model operation |  | Downer Approved Surveyor
2.2 | Services (includes Traffic Count Loops and Traffic Signal Detector Loops) |  | Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth) | NZAUAG Guide to Working on the Road | Before work commences | Zero service strikes | H |  | Hold point - No excavation is to be commenced until services are located and accounted for |  | Construction Supervisor
2.3 | Cultural/Heritage Risk Assessment |  | Notification | NZTA Cultural & Heritage Risk Model | Before work commences | Local iwi has been notified of intent to start work | H |  | Where risk of cultural discovery |  | Renewals Engineer / Manager
2.4 | Archaeological Risk |  | Toolbox meeting | NZTA Cultural & Heritage Risk Model | Before work commences | Toolbox meeting held covering accidental discovery protocol | H |  | Hold point - No excavation is to be commenced until toolbox meeting is held |  | Construction Supervisor
2.5 | Traffic Management | Signs Setup | Visual check | Traffic Management Plan | Before work commences each day | Traffic management complies with TMP | H |  | Hold point - No physical works are to be commenced until necessary traffic management is in place |  | STMS |  | Daily site record sheet
2.6 | Pre-Construction walkover |  | Visual check | Approved Crew pack on site 2 weeks prior to work comencing | Before work commences | Principal / Highways / Downer Acceptance | H |  | Hold point - Walkover required ahead of Highways establishment |  | Renewals Manager / Highways PM / MCM |  | Invite for NZTA to carry out joint site visit to complete visual inspection
Hold point - No physical works are to be commenced until walkover completed
3 | Preliminary Works
3.1 | Shoulder Stripping / Vegetation clearing |  | Visual check | On site |  | Shoulder stripping as per drawings completed | V |  |  |  | Construction Supervisor / NZTA |  | Invite for NZTA to carry out joint site visit to complete visual inspection
3.2 | Site pavement A/C digouts |  | Visual check | Check RAMM records for depths | Before Stabilisation work commences | Work completed prior to stablisation contractor onsite | V |  | A/C Mill & Fills to be cut to waste & replaced with M/4 AP40 compacted & sealed |  | Site Foreman
4 | Culvert extensions / Headwalls / Flumes
4.1 | Excavation Inlet / Outlet Gradients |  | Survey | NZTA F/3 | Once | Consistent gradient in and out | H |  | Hold Point – Visual check prior to pipe placement |  | Site foreman |  | Required Yes / No
4.2 | Pipe materials / class |  | Visual Check | NZTA F/3 2.1 | Once | Meets appropriate AS/NZ standard reletive to specified type | V |  |  |  | Site foreman |  | Required Yes / No
4.3 | Bedding contact |  | Visual Check | NZTA F/3 5.1 | continuous | uniform contact over full length of pipe | V |  |  |  | Site foreman |  | Required Yes / No
5 | Subsoil drainage
5.1 | Trench |  | Visual |  | each site | Depth minimum 1.0m Width minimum 300mm, fall > 1:100, free from rocks etc. Position as per the design drawings +/- 100mm | H |  | Hold Point – Visual check prior to pipe placement |  | Site foreman |  | Required Yes / No
5.2 | Drainage material |  | Visual |  | each site | 7-12mm clean filter material ( grade 2 - 4 Sealing chip | H |  | Hold Point – Visual check prior to pipe placement |  | Site foreman |  | Required Yes / No
5.3 | Pipe type |  | Visual | Diameter as per the design drawings | Use outside traffic Lane | Docket to confirm | V |  | "Nova flow" |  | Site foreman |  | Required Yes / No
|  |  | Visual |  | Under traffic lane | Docket to confirm | V |  | Nexus |  | Site foreman |  | Required Yes / No
5.4 | Filter Fabric |  | Visual |  |  | 150mm lap, top of fabric minimum 150mm below FSL | H |  | Hold Point – Visual check prior to reinstatement |  | Site foreman |  | Required Yes / No
5.5 | Outlet |  | Visual |  |  | Connect to sump barrel, culvert of construct Concrete Apron | H |  | Hold Point – Visual check prior to reinstatement |  | Site foreman |  | Required Yes / No
5.6 | Flushing / Cleaning eyes |  | Visual | To be placed & constructed as per Approved Drawings | Each free end | [7 empty] | Required Yes / No
5.7 | Reinstatement |  | Sealed Pavement |  |  | Pavement matches surrounding, surface with AC or 3/5 chip | V |  |  |  | Site foreman |  | Required Yes / No
|  |  | Berms and shoulder |  |  | Top min 150mm impermiable backfill | V |  |  |  | Site foreman |  | Required Yes / No
6 | Preteatment of Insitu Materials
6.1.1 | Pretreatment Stabilising Agent (where applicable) | Quick / Hydrated Lime or KOBM | Mat Test 1m² canvas | Pavement design report | Every 400m² | Within ±0.5kg/m² of the specified rate | V |  | Tonnage/m² records shall be kept, including mat results |  | Highways Site Foreman |  | Daily Job Record
6.1.2 |  |  | Average usage test | Pavement design report | Upon emptying the spreader and bulk tanker | Withn ±2.5% of the specified rate | V
6.2 | Stabilising Depth | Hoe Depth | Depth measurement | Design drawings | At both ends & sides of cut and every 200m | -5mm +15mm of design depth | W |  |  |  | Highways Site Foreman |  | Daily Job Record
6.3.1 | Pre-Hoe |  | Visual Inspection |  | Each Subsection | No unsuitable material found to be sampled | H |  | Hold point - Hoed material to be checked to ensure consistencey and no unsuitable material found, Sample to be taken for future testing if required |  | Renewals Manager / Highways Site Foreman
6.3.2 | Visual Inspection post Hoe | Proof Roll and Joint Inspection | Visual Inspection | 6x4 truck fully loaded or similar equivalent | Each Subsection | No significant movement of the pavement under proof rolling and/or trafficing, for subgrade contamination | V |  | Testing to be carried out imediately after compaction |  | Highways Site Foreman / Downer PM
6.3.3 |  | Material FBS Suitability | Visual Inspection | Particle size to be 50mm or less | Each Subsection, as required | No large slabs of existing wearing course or strongly bound base | V
6.3.4 | Undercut unsuitable areas |  | Visual Inspection/ measurements | Depth to be determined on site from investigations as per fig 15 Undercut & Reconstruct table | Where required | All unsuitable material removed. Excavated hole to be backfilled with M/4 AP40 & compacted to | H |  |  |  | Renewals Manager
6.3.5 | Shape & Compact Hoed layer |  | Check for 75mm overlay | Shape to correct as per the existing surface | Every 20m | Max 200mm layer depth to achieve compaction & trimmed to match existing shape and trafficable |  |  | Verified min 75mm overlay depth with no removal of pre hoed material in the traffic lane |  | Highways Site Foreman / Downer PM /Downer Surveyor |  | Joint inspection
7 | Imported Basecourse Materials Testing
7.1.1 | Imported Basecourse Materials Source Property Testing | Crushing Resistance | NZTA M/4 Crushing Resistance (CR130) Test | NZS 4407 Test 3.10 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve | V |  | Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old |  | Renewals PM |  | All source aggregate test results to be submitted to NZTA for review and verification
|  |  |  | NZTA M/4 |  |  | H
7.1.2 |  | Weathering Quality | Weathering Quality Index (WQI) Test | NZS 4407 Test 3.11 |  | Must have quality index of AA, AB, AC, BA, BB or CA | V
H
NZTA M/4
7.1.3 |  | Bearing Strength | Californian Bearing Ratio (CBR) | NZS 4407 T3.15 NZS 4402 T4.1.3 |  | Soaked CBR ≥ 80% when compacted/tested in accordance with both tests | V
|  |  |  | NZTA M/4 |  |  | H
7.2 | Imported Basecourse Materials Production Property Testing |  | Comply with project specification, PSD, Broken Faces, Quality of Fines (QoF) | Refer project specification and NZTA M/4 | 1 - 400m3 – 2 tests 400 - 1500m3 - 3 tests 1500 - 4000m3 – 4 tests >4000m3 – 1 test per 1000m3 | Refer project specification | V |  | Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old |  | Renewals PM |  | All production aggregate test results to be submitted to NZTA for review and verification
H
7.3 | Nominal 75mm Make-up Metal |  | Quantity of material used | 75mm depth over high spots | Each Subsection | Correct amount of material used (M³Solid) as per geometric design / MC | V |  | Spot checks to be taken |  | Downer surveyor
8 | Foamed Bitumen Stabilisation
8.1.1 | Stabilisation Agents | Foam Bitumen | Laboratory testing | NZTA B/5 NZTA M/1 (B/7) | Per batch | 80/100 or 180/200 Pen Grade Minimum expansion of 10 times original volume, & half-life of at least 6 seconds | V |  | Hold Point -No Bitumen shall be used on site with out a pass result as per Lab test results |  | Renewals Engineer |  | All stabilisation material and laboratory testing results to be submitted to NZTA for review and verification.
H
8.1.2 |  | Cement | See NZS 3122 | NZS 3122 NZTA B/5 Cl. 4.1.2 | Per batch | Cement must comply with NZS 3122 | V |  | Hold Point - No cement shall be spread on site with out a pass result, obtainable from supplier (this is to be done once for contract)
H
8.1.3 |  | Delivery | Visual Inspection | NZTA B/2 | Upon delivery | Stabilising agents to be delivered in tanks or trucks with Certificate of Loading | W |  | Certificate of loading to be checked on site |  | Highways Site Foreman
8.1.4 |  | Bitumen Storage | 80/100 Pen Grade | NZTA B/5 | 2 hours before use | Max storage temp: not exceed 125°C for > 24 hours & 175°C for < 24 hours Application temp: min 175°C - max 190°C | H |  | Any bitumen that has been heated above the maximum shall be removed from site
|  |  | 180/200 Pen Grade | NZTA B/5 | 2 hours before use | Max storage temp: not exceed 120°C for > 24 hours & 170°C for < 24 hours Application temp: min 170°C - max 185°C | H
8.2 | Water |  | Obtained from a suitable source | NZTA B/5(B7) Portable PH testing | Ongoing | Water for stabilisation, construction and curing is tested for correct PH for each site | W |  | Certification required for each site (PH 5.5 -7.0) |  | Downer PM
8.3.1 | Weather Limitations | Temperature | Measure Temperature | NZTA B/5 | Daily | Stabilised material before compaction 20°C | W |  | Work shall not be started if temperature is below the respective minimums. |  | Highways Site Foreman / Downer PM |  | Joint Inspection
8.3.2 |  | Wind | Assessment | NZTA B/5 | Daily (SEE remarks) | Maximum windspeed of 25km/hr checked from metservice website | W |  | Work shall not be started if windspeed exceeds the maximum |  |  |  | Not applicable if direct injection used
6.3.3 |  | Rain | Check forecast | NZTA B/5 | Daily | Low likelihood of rain | W |  | Work shall not be started if rain is forecast for the immediate work day and the following day for the aftercare.
8.4.1 | Spreading | Cement | Mat Test 1m² canvas | NZTA B/5 | Every 400m² | Within ±0.5km/m² of the specified rate | V |  | Tonnage/m² records shall be kept, including mat results |  | Highways Site Foreman |  | Not applicable if direct injection used
|  |  | Average usage test | NZTA B/5 | Upon emptying the spreader and bulk tanker | Withn ±2.5% of the specified rate | V
8.4.2 |  | Bituminous Agents | Flow meter display | NZTA B/5 | Continuous | Withn ±5% of the specified rate | W |  | Tonnage/m² records shall be kept, including mat results
|  |  | Microprocessors reading | NZTA B/5 | End of each run | Withn ±3.0% of the specified rate | W
|  |  | Average usage test | NZTA B/5 | Upon emptying the bulk tanker | Withn ±2.5% of the specified rate | W
8.5.1 | Time Limitations | Cement | The maximum time period from mixing to primary compaction | NZTA B/5 | Post stabilisation | 2 hours - Time start to time end to be recorded | H |  | Where time the time limit is exceeded, details of the remedial action shall be prepared for assessment, and procedures for further stabilisations sections must be agreed to avoid further occurances |  | Downer PM
8.5.2 |  | Foam Bitumen |  | NZTA B/5 |  | 4 hours - Time start to time end to be recorded | H
8.5.3 |  | Combination |  | NZTA B/5 |  | The shorter of the individual agents | H
8.6.1 | Insitu Mixing | Cut Depth | Depth measurement | NZTA B/5 | At start & end of cut and every 200m | -5mm +15mm of design depth | W |  |  |  | Highways Site Foreman
8.6.2 |  | Join Overlap | Inspection | NZTA B/5 | Continuous | 100mm overlap | W |  | All cuts shall overlap by the minimum acceptance criteria
8.6.3 |  | Particle Breakdown | Inspection | NZTA B/5 | Within the first 20m of each run, and where ever material changes | Well mixed material with acceptable particle size distribution | W |  | Where breakdown is excessive, method of milling should be altered to avoid such breakdown
8.6.4 |  | FBS Quality | Inspection | Visual Inspection | Continuous while stabilisation is progressing | No bitumen stringers or blobs observed (See Assessment of hoe'd materials) | W |  | If bitumen blobs or stringers are found the the construction of FBS stops and the equipement is fixed so that there are no bitumen blobs or stringers found
9 | Construction Quality Assurance (QA)
9.1 | Field Compaction Target |  | NDM - Plateau | NZTA B/5 | 1 Every 3000m2 or once daily | Plateau testing done each shift / as required depending on the material variability throughout the site to determine compaction pattern. | V |  | Avg 98% plateau with min 95%. Plateau testing to be completed to determine Field Compaction Target |  | Highways Site Foreman |  | Verified test results of plateau to be supplied
9.2 | Lab testing |  | ITS/ UCS test | NZTA B/5 | 1 Every 3000m2 or once daily | Testing to be completed each shift / as required depending on the material variability throughout the site to verify compaction. | V |  | Tests to be cured & achieve as per specification. |  | Highways Site Foreman / Renewals PM
9.3 | Compaction Testing |  | NDM | NZTA T23: 2021 Direct Transmission | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | Average ≥ 98% Plateau Minimum ≥ 95% Plateau | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Plateau) Compaction equipment shall be sufficent to achieve 98% MDD |  | Highways Site Foreman / Renewals Engineer |  | Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
H
9.4 | Surface Set Up / Clegg Hammer |  | Clegg Hammer | Certified Clegg hammer (Current Certification sticker) & calibrated prior to use | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | CIV ≥ 40 | V |  | Hold point - membrane / chipseal placed once CIV ≥ 40 |  | Construction Supervisor/ Renewals Engineer |  | All test results to be submitted to NZTA for review and verification
H
9.5 | Degree of Saturation (DOS) |  | DOS | NZS 4407 Test 4.2.2 NZTA B/5 Cl. 7.12 | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | For information only | V |  | Soild density to be measured. |  | Downer Lab technician
9.6 | NDM moisture correction |  | NDM & Lab MC |  | 3x Moisture contents per single plateau test carried out | Information only | V |  | Correction offset to be applied per site |  | Highways Site Foreman / Renewals Engineer - Relates to field plateau testing by the laboratory
9.7 | Surface Shape / Profile Layer Thickness |  | NZTA B/5 | Visual inspection Cut/fill tolerance check String records Straight edge | 1 test per 20m | ≤10mm variance from 3m straight edge | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved. Hiways Retain the right to override Machine Control requirement when required. Documentation and Record to supplement reasoning and affected area |  | Highways Site Foreman/ Renewals PM/ Downer surveyor |  | Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
Gradual deviations
Crossfall > 1%
[6 empty] | Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design | H
-5mm +15mm or ±5mm at lip of concrete channel where applicable
9.8.1 | Tolerances | Width Unconstrained | TNZ B/2 | Confirm offset from lift pegs | 2 at every lift peg or per 180 m2 | - 20mm + 100mm | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved |  | Highways Site Foreman / Renewals PM |  | 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
H
9.8.2 |  | Width Constrained | TNZ B/2 | Stringline/lift pegs | 3 at every lift peg or per 180 m2 | Zero | V
H
9.9 | Ride Quality |  | Owner acceptance test | As per Contract Documents OPM42 | 1 ride test for each lane following Basecourse completion prior to surfacing | Rolling 100m average NAASRA <75 counts/km | W |  | Hold Point – no surfacing layer is to be applied until acceptance of ride quality, No exceptionsa |  | Road Science/ Downer PM |  | NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
H
9.10 | Mosaic Surface |  | Visual inspection | A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ | Overview of site for tight mosaic surface | The large aggregate is held in place by a matrix of smaller aggregates The smaller aggregate is held firmly in place by fine material The matrix does not displace under normal trafficking or sweeping | W |  | Hold Point – no surfacing layer is to be applied until passing results are achieved |  | NZTA Network Manager / Renewals Manager/ Highways Site Foreman / Downer PM / Downer Sealing Foreman
H
9.11 | Preseal Check |  | Visual check | NZTA B/5 | Before sealing | All prior ITP checks have been completed and signed off | V |  | Hold Point – no surfacing layer is to be applied until all results are verified & approved as per ITP
[6 empty] | No caking layers present | H
9.12 | Pavement Surface As-Built |  | Survey | As per approved drawings | Per installation / Site | Accurate survey of all topograpgical features required | V |  |  |  | Downer Approved Surveyor
10 | Sealing
10.1 | Sealing |  | See Sealing ITP |  |  |  | W |  | Hold Point – All hold points and checks in ITP to be completed before physical works continue |  | Downer Sealing Contract Manager
10.2 | Sealing TMP and Aftercare Process |  | See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site |  |  |  | W |  | Hold Point – 24 hour trafficking and aftercare of sealing works are described and confirmed in TMP for sealing works before physical sealing works proceed. |  | Downer Sealing Supervisor
H
10.3 | Sweeping of Sealing Works and Handover to Roadmarkers |  | Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor. |  |  |  | W |  | Hold Point – All sweeping activities, roadmarking and install of RPM's to be completed before handover of site from surfacing to construction supervisor.a |  | Downer Sealing Supervisor
H
11 | Shoulders
11.1 | Slope |  | Visual check | Visual inspection with smart level |  | Slopes consistent & to 5:1 grade. Excessive shoulder construction to be carried out ahead of pavement operation | V |  | Hold Point – no surfacing layer is to be applied until all necessary results are achieved |  | Construction Supervisor/ NZTA |  | Invite NZTA to carry out joint site inspection to inspect site.
H
11.2 | Compaction |  | Visual check | Drive over 4 tonne, check wheeltracks | All shoulders | Vehicles can drive on shoulders without becoming stuck | V |  | Hold Point – physical works cannot be completed until all necessary results are achieved |  | Construction Supervisor/ NZTA
H
11.3 | Soiling |  | Visual check | Approved Design Drawings | All areas requiring grassing | Soiling has been done where required | W |  | As per the design drawings |  | Construction Supervisor
12 | Site Reinstatement / Clearance
12.1 | Traffic Services | Marker Pegs/ Signs/Markings/RRPMs Replaced | TNZ C/20: 2003 | Visual Inspection | All signs/markers | Replaced in same position, height etc | V |  | Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced |  | Construction Supervisor/ NZTA |  | Invite NZTA to carry out joint site inspection to inspect site.
H
12.2 | Grassing |  | Visual check |  | All areas requiring grassing | Grassing has been done where required | W |  |  |  | Construction Supervisor
12.3 | Drains Cleared |  | Visual check |  | All drains, after all other works | Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated | W |  |  |  | Construction Supervisor
12.4 | Traffic Management Removed |  | Visual check |  | When safe, after all physical works completed | All traffic management removed from site safely | W |  | Hold Point – TMP cannot be removed until site Audited by Downer Construction Supervisor |  | Construction Supervisor
12.5 | Site Left Clean and Tidy |  | Visual check |  | After vacating site | · Stockpiles removed | V |  |  |  | Construction Supervisor/ NZTA |  | Invite NZTA to carry out joint site inspection to inspect site.
· Plant removed
· Litter cleared from site
13 | As-built Records
13.1 | Collect Asset Data |  | SHDOM (SM050) |  | During construction | All relevant as built information collected | V |  |  |  | Renewals Engineer
13.2 | Enter Asset Data into RAMM and/or Register(s) |  | SHDOM (SM050) | RAMM | At completion of work | All data entered into RAMM and/or register(s). Design report & drawings attached to RAMM site record as a media file. | H |  | Hold Point – project cannot be closed until data entered. |  | Renewals Engineer/ WSP Information Manager |  | Submit all RAMM Data to Data Quality Manager for review and verification
13.3 | Construction Completion Report |  | Confirmation | Contract Specification | At completion of work | Checked and approved | V |  |  |  | Renewals Engineer/ Renewals Manager |  | Submit Pavement Design Report, Construction Compliance, QMP, Site test results / inspections / activity records, Lessons Learnt, As-built Plans
| Quality Assurance Close Out By: | _________________________________________ |  |  | Date: ___________________ |  | _________________________________________________________
(signature)
_________________________________________________________
(name)
THIS RECORD TO CONTRACT FILE
Note on C37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Might pay to add a requird yes/no feild here to make it clear. Same for subsoils, dont want someone reviewing this to thik we didnt do it

## FBS sites
Site Work Order | Section Name |  | RP start | RP end | Length | Width | Current Const. | Current Surfacing Date | Current Surfacing Type | Current Surfacing | Seal Layers | MIS CODE | AADT | HCV | Lanes | Lane | Area | Lane.km | 22/23 | Reas 22/23 | Calc area
| 005-0008 | Mamaku Passing Lane | 11.35 | 11.996 | 836 | 11.1 | 2008-11-09 | 2014-02-28 | 2CHIP | 2_4 | 3 | N | 10959 | 16 | All | 3 | 11951 | 2.508 | FBSMUP | CR | 9279.6 | SH1 01N-0613 7099 7935 | SH1 Baldwin Rd 01N-0613 7099 7935
| 005-0111 | Dicks Hill | 6.996 | 7.671 | 306 | 10.6 |  | 2017-03-21 | 2CHIP | 2_4 | 3 | RS | 10324 | 17 | All | 2 | 4065 | 0.612 | FBSMUP | FL | 3243.6 | SH1 01N-0625 3842 5143 | SH1 Puriri Curves & Passing Lane 01N-0625 3842 4492
| 005-0111 | Palmer Mill Rd | 8.167 | 8.77 | 995 | 13.07 | 2003-02-14 | 2017-03-22 | 2CHIP | 2_4 | 4 | RS | 10324 | 17 | All | 2.9 | 13222 | 2.8855 | FBSMUP | RU | 13004.65
| 005-0150 | Iwitahi | 8.374 | 9.144 | 937 | 10.81 |  | 2017-03-02 | 2CHIP | 2_4 | 6 | RS | 6178 | 22 | All | 2 | 10112 | 1.874 | FBS | CR | 10128.97 | SH1 01N-0664 9085 9553 | SH1 Tuahu Wall & Rd Sth 01N-0664 9085 9553
| 01N-0680 | Circle S | 2.175 | 2.455 | 350
| 01N-0713 | Earthquake Gully 1 23 - 24 | 10.784 | 12.423 | 272
| 01N-0680 | Double "D" Passing Lane | 11.136 | 11.781 | 1548 | 10.1 | 1985-12-25 | 2017-03-02 | 2 CHIP | 3_5 | 6 | RS | 6381 | 14 | All | 2 | 15954 | 3.096 | FBSMUP | FL | 15634.8 | SH1 01N-0713 8500 9274 | SH1 Earthquake Gully 01N-0713 8500 9274
| 01N-0664 | Tuahu Wall | 9.085 | 10.022 | 330 | 7.7 | 1988-12-25 | 2018-03-14 | 2CHIP | 2_4 | 7 | P | 6381 | 14 | All | 2 | 2541 | 0.66 | FBSMUP | FL | 2541 | SH1 01N-0726 3500 3830 | SH1 Hallets Bay 01N-0726 3500 3830
| 01N-0625 | Te Rere Passing Lane | 1.275 | 2.687 | 295 | 9.5 | 2001-04-20 | 2015-02-27 | 2CHIP | 2_4 | 5 | N | 3896 | 24 | All | 2 | 2585 | 0.59 | FBSMUP | FL | 2802.5 | SH1 01N-0763 2074 - 2369 | SH1 Rangipo South 01N-0763 2074 - 2369
| 01N-0815 | Hihitahi | 9.311 | 9.92 | 402 | 11.1 | 2007-03-22 | 2018-02-16 | COMB | 2_5 | 4 | P | 3896 | 24 | All | 2 | 4472 | 0.804 | FBSMUP | FL | 4462.2 | SH1 01N-0777 13794 - 14196 | SH1 Waikato North 01N-0777 13794 - 14196
| 004-0114 | Makatoke Viaduct | 9.994 | 10.608 | 609 | 10.1 | 1990-04-27 | 2018-02-07 | 2CHIP | 2_4 | 5 | P | 5339 | 18 | All | 2 | 6028 | 1.218 | FBSMUP | FL | 6150.9 | SH1 01N-0815 9311 - 9920 | SH1 Hihitahi 01N-0815 9311 - 9920
| 01N-0763 | Puketarata | 7.867 | 8.677 | 614 | 8.21 | 2001-05-20 | 2016-03-20 | 2CHIP | 2_4 | 6 | RS | 2154 | 14 | All | 2 | 5160 | 1.228 | FBS | FL | 5040.94 | SH4 04-114 9994 10608 | SH4 Makatoke Viaduct 04-114 9994 10608
| 01N-0777 | Oterere Hill Nth | 0.88 | 1.83
15.4755

## Info Boards
Work Order | Section Name | Treatment Name | location From | location To
631455 | 005-0008 | Mamaku Passing Lane | 11.35 | 11.996 | 11350 | 11996 | SH5 | SH5 Mamaku Passing Lane 005-0008 11350 11996 | SH5 Mamaku Passing Lane 005-0008 11350 11996
655953 | 005-0111 | Dicks Hill | 6.996 | 7.671 | 6996 | 7671 | SH5 | SH5 Dicks Hill 005-0111 6996 7671 | SH5 Dicks Hill 005-0111 6996 7671
655954 | 005-0111 | Palmer Mill Rd | 8.167 | 8.77 | 8167 | 8770 | SH5 | SH5 Palmer Mill Rd 005-0111 8167 8770 | SH5 Palmer Mill Rd 005-0111 8167 8770
626261 | 005-0150 | Iwitahi | 8.374 | 9.144 | 8374 | 9144 | SH5 | SH5 Iwitahi 005-0150 8374 9144 | SH5 Iwitahi 005-0150 8374 9144
662525 | 01N-0680 | Circle S | 2.175 | 2.455 | 2175 | 2455 | SH1 | SH1 Circle S 01N-0680 2175 2455 | SH1 Circle S 01N-0680 2175 2455
655946 | 01N-0713 | Earthquake Gully 1 23 - 24 | 10.784 | 12.423 | 10784 | 12423 | SH1 | SH1 Earthquake Gully 1 23 - 24 01N-0713 10784 12423 | SH1 Earthquake Gully 1 23 - 24 01N-0713 10784 12423
655945 | 01N-0680 | Double "D" Passing Lane | 11.136 | 11.781 | 11136 | 11781 | SH1 | SH1 Double "D" Passing Lane 01N-0680 11136 11781 | SH1 Double "D" Passing Lane 01N-0680 11136 11781
621344 | 01N-0664 | Tuahu Wall | 9.085 | 10.022 | 9085 | 10022 | SH1 | SH1 Tuahu Wall 01N-0664 9085 10022 | SH1 Tuahu Wall 01N-0664 9085 10022
655942 | 01N-0625 | Te Rere Passing Lane | 1.275 | 2.687 | 1275 | 2687 | SH1 | SH1 Te Rere Passing Lane 01N-0625 1275 2687 | SH1 Te Rere Passing Lane 01N-0625 1275 2687
631552 | 01N-0815 | Hihitahi | 9.311 | 9.92 | 9311 | 9920 | SH1 | SH1 Hihitahi 01N-0815 9311 9920 | SH1 Hihitahi 01N-0815 9311 9920
621330 | 004-0114 | Makatoke Viaduct | 9.994 | 10.608 | 9994 | 10608 | SH4 | SH4 Makatoke Viaduct 004-0114 9994 10608 | SH4 Makatoke Viaduct 004-0114 9994 10608
662524 | 01N-0763 | Puketarata | 7.867 | 8.677 | 7867 | 8677 | SH1 | SH1 Puketarata 01N-0763 7867 8677 | SH1 Puketarata 01N-0763 7867 8677
662526 | 01N-0777 | Oterere Hill Nth | 0.88 | 1.83 | 880 | 1830 | SH1 | SH1 Oterere Hill Nth 01N-0777 880 1830 | SH1 Oterere Hill Nth 01N-0777 880 1830

## CAR Status
Order | Job/Location: | TMNZ Number: CAR No. | TMP Status | CAR Status
1 | SH01N-613 (Baldwin Rd) | TMNZ-ROT-220073 - E887911 | Received | Approved
2 | SH028-0009 (Harwoods Rd) | TMNZ-ROT-220074 - E887914 | Received | Approved
3 | SH005-0008 (Mamaku Passing Lane) | TMNZ-ROT-220075 - E887677 | Received | Approved
4 | SH005-0150 (Iwitahi) | TMNZ-ROT-220076 - E887916 | Received | Approved
5 | SH01N-0625 (Puriri Curves and Passing Lane) | TMNZ-ROT-220077 | Being amended | Under Review
6 | SH01N-0713 (Earthquake Gully) | TMNZ-ROT-220079 - E892742 | Received | Approved
7 | SH01N-0726 (Hallets Bay) | TMNZ-ROT-220080 | Submitted to TMC. | Under Review
8 | 01N-0763 (Rangipo South) | TMNZ-ROT-220081 | Requested
9 | SH01N-0777 (Waikato North) | TMNZ-ROT-220082 | Requested
10 | SH01N-0815 (Hihitahi) | TMNZ-ROT-220083 | Requested
11 | SH004-0114 (Makatoke Viaduct) | TMNZ-ROT-220084 | Requested
12 | SH01N-0664 (Tuahu Wall) | TMNZ-ROT-220078 | Requested

## 0.5 RenewalFoam - Puriri Curves
|  | Central Waikato NOC - Inspection & Test Plan - Catalogue Foam Stabilisation | [6 empty] | Document Number: | Pavement Renewals - Foam Stabilisation
|  | Site Name: | Puriri Curves | [5 empty] | Revision Number: | 0.9 | Number of Pages: |  | 9
|  | Location: | SH1 01N-0625 3842 4492 | [5 empty] | Prepared: | M Owens | Date: |  | 2022-10-10
[9 empty] | Approved: | G Apiti | Date: |  | 2022-10-04
ITEM NUMBER | ACTIVITY DESCRIPTION |  | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | INSPECTORATE V/W/H |  |  |  | RESPONSIBLE PERSON | Sign & date if appropriate | RECORDS / REMARKS
[7 empty] | V=VERIFICATION, W=WITNESS, H =HOLD |  |  |  | As per Quality Plan
[7 empty] | Type | Assessor signature | Description |  |  |  | incl NCR ref
1 | Preliminary and General
1.1 | Construction Programme Completion |  | Confirmation | Best Practice Contract Specific MMP | Before work commences | Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date | V |  |  |  | Renewals Manager
1.2 | Approved RQP |  | Confirmation | Contract Specification | At least 24hrs before establishment or work commences | Principal's Acceptance according to guidelines in Appendix 6.3 | H |  | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours before establishing on site. |  | Renewals Manager |  | NZTA to approve.
1.3 | Notification of Intention to Start Work |  | Notification |  | Before work commences | Letter drop to local residents | H |  | Hold point - No physical work is to be commenced on site until notification has been sent to residents - no later than 24 hours prior to establishing on site. |  | Construction Supervisor / Renewals Engineer |  | NZTA to approve letter drop before distribution to residents.
1.4 | Traffic Management | TMP | Visual check | CoPTTM | Before work commences | TMP checked and approved Plans approved Current EED (if applicable) Size of site area to be checked to allow machinery to operate safely | H |  | Hold point - No traffic management is to be set up until TMP has been checked and approved |  | STMS |  | CAR No.
TMP No.
1.5 | Design Report Approval |  | Confirmation | NZTA NOC Rehab Catalogue Design & Treatment Approach | Before work commences | Principal Acceptance's acceptance according to NZTA Catalogue Design Approach document | H |  | Hold point - Review meeting with NZTA National & Regional Leads and Downer NOC Managers & Pavement Designers/Reviewers |  | NZTA Network Manager & Accreditied Designer |  | NZTA Approval to Proceed NTC No.
1.6 | Seal Design Approval |  | Confirmation | Review and Sign off by Downer Regional Sealing Manager | Before work commences | Downer Regional Sealing Manager reviews and signs off on Seal Design proposed. | H |  | Hold point - Review and approval of seal design completed |  | Regional Sealing Manager |  | Approval email from Nippun
1.7 | Project Manager Handover |  | Confirmation | Review and Sign off by Downer Designer to PM | Before work commences | Downer Technical Services Team Designer reviews and signs off on Handover. | H |  | Hold point - Handover completed |  | Regional Engineering Team Designer
1.8 | Crew Pack |  |  | Items to be included: | Before work commences | Approved TMP | H
Services location plans / Marked out
Approved RQP
Approved for Construction drawings & Pavement Design
Ramm data
Approved ITP
Crew Briefing Plan
2 | Setout / Site Preparation
2.1 | Setout |  | Survey | As per approved drawings | Per installation / Site | Design strings /design surface model loaded for machine control | V |  | Machine control requirement. Downer surveyor required for MC upload and verification of model operation |  | Downer Approved Surveyor
2.2 | Services (includes Traffic Count Loops and Traffic Signal Detector Loops) |  | Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth) | NZAUAG Guide to Working on the Road | Before work commences | Zero service strikes | H |  | Hold point - No excavation is to be commenced until services are located and accounted for |  | Construction Supervisor
2.3 | Cultural/Heritage Risk Assessment |  | Notification | NZTA Cultural & Heritage Risk Model | Before work commences | Local iwi has been notified of intent to start work | H |  | Where risk of cultural discovery |  | Renewals Engineer / Manager
2.4 | Archaeological Risk |  | Toolbox meeting | NZTA Cultural & Heritage Risk Model | Before work commences | Toolbox meeting held covering accidental discovery protocol | H |  | Hold point - No excavation is to be commenced until toolbox meeting is held |  | Construction Supervisor
2.5 | Traffic Management | Signs Setup | Visual check | Traffic Management Plan | Before work commences each day | Traffic management complies with TMP | H |  | Hold point - No physical works are to be commenced until necessary traffic management is in place |  | STMS |  | Daily site record sheet
2.6 | Pre-Construction walkover |  | Visual check | Approved Crew pack on site 2 weeks prior | Before work commences | Principal / Highways / Downer Acceptance | H |  | Hold point - Walkover required ahead of Highways establishment |  | Renewals Manager / Highways PM / MCM |  | Invite for NZTA to carry out joint site visit to complete visual inspection
Hold point - No physical works are to be commenced until walkover completed
3 | Preliminary Works
3.1 | Shoulder Stripping / Vegetation clearing |  | Visual check | On site |  | Shoulder stripping as per drawings completed | V |  |  |  | Construction Supervisor / NZTA |  | Invite for NZTA to carry out joint site visit to complete visual inspection
3.2 | Site pavement A/C digouts |  | Visual check | Check RAMM records for depths | Before Stabilisation work commences | Work completed prior to stablisation contractor onsite | V |  | A/C Mill & Fills to be cut to waste & replaced with M/4 AP40 compacted & sealed |  | Site Foreman
4 | Culvert extensions / Headwalls / Flumes
4.1 | Excavation Inlet / Outlet Gradients |  | Survey | NZTA F/3 | Once | Consistent gradient in and out | H |  | Hold Point – Visual check prior to pipe placement |  | Site foreman
4.2 | Pipe materials / class |  | Visual Check | NZTA F/3 2.1 | Once | Meets appropriate AS/NZ standard reletive to specified type | V |  |  |  | Site foreman
4.3 | Bedding contact |  | Visual Check | NZTA F/3 5.1 | continuous | uniform contact over full length of pipe | V |  |  |  | Site foreman
5 | Subsoil drainage
5.1 | Trench |  | Visual |  | each site | Depth minimum 1.0m Width minimum 300mm, fall > 1:100, free from rocks etc. Position as per the design drawings +/- 100mm | H |  | Hold Point – Visual check prior to pipe placement |  | Site foreman
5.2 | Drainage material |  | Visual |  | each site | 7-12mm clean filter material ( grade 2 - 4 Sealing chip | H |  | Hold Point – Visual check prior to pipe placement |  | Site foreman
5.3 | Pipe type |  | "Nova flow" | Diameter as per the design drawings | Use outside traffic Lane | Docket to confirm | V |  |  |  | Site foreman
|  |  | Nexus |  | Under traffic lane | Docket to confirm | V |  |  |  | Site foreman
5.4 | Filter Fabric |  | Visual |  |  | 150mm lap, top of fabric minimum 150mm below FSL | H |  | Hold Point – Visual check prior to reinstatement |  | Site foreman
5.5 | Outlet |  | Visual |  |  | Connect to sump barrel, culvert of construct Concrete Apron | H |  | Hold Point – Visual check prior to reinstatement |  | Site foreman
5.6 | Flushing / Cleaning eyes |  | Visual | To be placed & constructed as per Approved Drawings | Each free end
5.7 | Reinstatement |  | Sealed Pavement |  |  | Pavement matches surrounding, surface with AC or 3/5 chip | V |  |  |  | Site foreman
|  |  | Berms and shoulder |  |  | Top min 150mm impermiable backfill | V |  |  |  | Site foreman
6 | Kerb & Channel / Dish drain
6.1 | Setout |  | Visual | As per approved drawings | Daily | Design stringsline | V |  | Visually inspect alignment and fall daily. |  | Site Foreman
6.2 | Excavation |  | Stringlines |  | When required | 300mm below base of kerb | V |  |  |  | Site Foreman |  | String sheet.
6.3 | Subgrade |  | Visual |  | When required | Free from poor material | V |  | Visual inspection with photos. |  | Site Foreman
6.4 | Kerb & Channel bedding | Compaction | Clegg Tests | On site | Clegg Tests at regular intervals | Minimum CIV 25. +/- 5mm | H |  | Hold Point – Visual check prior placement |  | Site Foreman
6.5 | Kerb & Channel alignment | Compaction | Visual | Survey | Pre Pour | Kerb setout is still in alignment, fall is correct | H |  | Hold Point – Visual check prior placement |  | Site Foreman / Kerbing supplier
6.6 | Concrete Supply | Compaction | Visual | Supplied Docket | When required | 25mPa Concrete | V |  |  |  | Kerbing Supplier
6.7 | Contraction/Expansion Joints | Compaction | Visual | Site Measure | When required | Spacing <3m and penetration >50mm with mortar dressing | V |  |  |  | Site Foreman / Kerbing supplier
7 | Preteatment of Insitu Materials
7.1 | Pretreatment Stabilising Agent (where applicable) | Quick / Hydrated Lime or KOBM | Mat Test 1m² canvas | Pavement design report 1% additive | Every 400m² | Within ±0.5kg/m² of the specified rate | V |  | Tonnage/m² records shall be kept, including mat results |  | Highways Site Foreman |  | Daily Job Record
7.2 |  |  | Average usage test | Pavement design report 1% additive | Upon emptying the spreader and bulk tanker | Withn ±2.5% of the specified rate | V
7.3 | Stabilising Depth | Hoe Depth | Depth measurement | Design drawings | At both ends & sides of cut and every 200m | -5mm +15mm of design depth | W |  |  |  | Highways Site Foreman |  | Daily Job Record
7.4 | Pre-Hoe |  | Visual Inspection |  | Each Subsection | No unsuitable material found to be sampled | H |  | Hold point - Hoed material to be checked to ensure consistencey and no unsuitable material found |  | Renewals Manager
7.5 | Pre-Hoe sample
7.6 | Visual Inspection post Hoe | Proof Roll and Joint Inspection | Visual Inspection | 6x4 truck fully loaded or similar equivalent | Each Subsection | No significant movement of the pavement under proof rolling and/or trafficing, for subgrade contamination | V |  | A proof rolling plan to be produced & testing to be carried out imediately after compaction |  | Highways Site Foreman / Downer PM
7.7 |  | Material FBS Suitability | Visual Inspection | Particle size to be 50mm or less | Each Subsection, as required | No large slabs of existing wearing course or strongly bound base | V
7.8 | Undercut unsuitable areas |  | Visual Inspection/ measurements | Depth to be determined on site from investigations | Where required | All unsuitable material removed. Excavated hole to be backfilled with M/4 AP40 & compacted to | H |  |  |  | Renewals Manager
7.9 | Shape & Compact Hoed layer |  | Check measurements | Shape to correct as per the design | Every 20m | Max 200mm layer depth to achieve compaction |  |  | M/4 AP 40 Verified min 75mm overlay depth with no removal of pre hoed material in the traffic lane |  | Highways Site Foreman / Downer PM
8 | Imported Basecourse Materials Testing
8.1.1 | Imported Basecourse Materials Source Property Testing | Crushing Resistance | NZTA M/4 Crushing Resistance (CR130) Test | NZS 4407 Test 3.10 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve | V |  | Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old |  | Renewals Engineer |  | All source aggregate test results to be submitted to NZTA for review and verification
|  |  |  | NZTA M/4 |  |  | H
8.1.2 |  | Weathering Quality | Weathering Quality Index (WQI) Test | NZS 4407 Test 3.11 |  | Must have quality index of AA, AB, AC, BA, BB or CA | V
H
NZTA M/4
8.1.3 |  | Bearing Strength | Californian Bearing Ratio (CBR) | NZS 4407 T3.15 NZS 4402 T4.1.3 |  | Soaked CBR ≥ 80% when compacted/tested in accordance with both tests | V
|  |  |  | NZTA M/4 |  |  | H
8.2 | Imported Basecourse Materials Production Property Testing |  | Comply with project specification, PSD, Broken Faces, Quality of Fines (QoF) | Refer project specification and NZTA M/4 | 1 - 400m3 – 2 tests 400 - 1500m3 - 3 tests 1500 - 4000m3 – 4 tests >4000m3 – 1 test per 1000m3 | Refer project specification | V |  | Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old |  | Renewals Engineer |  | All production aggregate test results to be submitted to NZTA for review and verification
H
8.3 | Nominal 75mm Make-up Metal |  | Quantity of material used | 75mm depth over high spots | Each Subsection | Correct amount of material used (M³Solid) as per geometric design / MC | V |  | Check Quarry Dockets and Stabilisation QA |  | Downer surveyor
9 | Foamed Bitumen Stabilisation
9.1.1 | Stabilisation Agents | Foam Bitumen | Laboratory testing | NZTA B/5 NZTA M/1 (B/7) | Per batch or at least weekly | 80/100 or 180/200 Pen Grade Minimum expansion of 10 times original volume, & half-life of at least 6 seconds | V |  | Hold Point -No Bitumen shall be used on site with out a pass result as per Lab test results |  | Renewals Engineer |  | All stabilisation material and laboratory testing results to be submitted to NZTA for review and verification.
H
9.1.2 |  | Cement | See NZS 3122 | NZS 3122 NZTA B/5 Cl. 4.1.2 | Per batch | Cement must comply with NZS 3122 | V |  | Hold Point - No cement shall be spread on site with out a pass result, obtainable from supplier (this is to be done once for contract)
H
9.1.3 |  | Delivery | Visual Inspection | NZTA B/2 | Upon delivery | Stabilising agents to be delivered in tanks or trucks with Certificate of Loading | W |  | Certificate of loading to be checked on site |  | Site Foreman
9.1.4 |  | Bitumen Storage | 80/100 Pen Grade | NZTA B/2 | 2 hours before use | Max storage temp: not exceed 125°C for > 24 hours & 175°C for < 24 hours Application temp: min 175°C - max 190°C | H |  | Any bitumen that has been heated above the maximum shall be removed from site
|  |  | 180/200 Pen Grade | NZTA B/2 | 2 hours before use | Max storage temp: not exceed 120°C for > 24 hours & 170°C for < 24 hours Application temp: min 170°C - max 185°C | H
9.2 | Water |  | Obtained from a suitable source | NZTA B/5(B7) Portable PH testing | Ongoing | Water for stabilisation, construction and curing is tested for correct PH for each site | W |  | Certification required for each site (PH 5.5 -7.0) |  | Downer PM
9.3.1 | Weather Limitations | Temperature | Measure Temperature | NZTA B/5 | Daily | Stabilised material before compaction 20°C | W |  | Work shall not be started if temperature is below the respective minimums. |  | Site Foreman
9.3.2 |  | Wind | Assessment | NZTA B/5 | Daily (SEE remarks) | Maximum windspeed of 25km/hr checked from metservice website | W |  | Work shall not be started if windspeed exceeds the maximum |  |  |  | Not applicable if direct injection used
9.3.3 |  | Rain | Check forecast | NZTA B/5 | Daily | Low likelihood of rain | W |  | Work shall not be started if rain is forecast for the immediate work day and the following day for the aftercare.
9.4.1 | Spreading | Cement | Mat Test 1m² canvas | NZTA B/5 | Every 400m² | Within ±0.5km/m² of the specified rate | V |  | Tonnage/m² records shall be kept, including mat results |  | Site Foreman |  | Not applicable if direct injection used
|  |  | Average usage test | NZTA B/5 | Upon emptying the spreader and bulk tanker | Withn ±2.5% of the specified rate | V
9.4.2 |  | Bituminous Agents | Flow meter display | NZTA B/5 | Continuous | Withn ±5% of the specified rate | W |  | Tonnage/m² records shall be kept, including mat results
|  |  | Microprocessors reading | NZTA B/5 | End of each run | Withn ±3.0% of the specified rate | W
|  |  | Average usage test | NZTA B/5 | Upon emptying the bulk tanker | Withn ±2.5% of the specified rate | W
9.5.1 | Time Limitations | Cement | The maximum time period from mixing to primary compaction | NZTA B/5 | Post stabilisation | 2 hours - Time start to time end to be recorded | H |  | Where time the time limit is exceeded, details of the remedial action shall be prepared for assessment, and procedures for further stabilisations sections must be agreed to avoid further occurances |  | Downer PM
9.5.2 |  | Foam Bitumen |  | NZTA B/5 |  | 4 hours - Time start to time end to be recorded | H
9.5.3 |  | Combination |  | NZTA B/5 |  | The shorter of the individual agents | H
9.6.1 | Insitu Mixing | Cut Depth | Depth measurement | NZTA B/5 | At both ends of cut and every 200m | -5mm +15mm of design depth | W |  |  |  | Site Foreman
9.6.2 |  | Join Overlap | Inspection | NZTA B/5 | Continuous | 100mm overlap | W |  | All cuts shall overlap by the minimum acceptance criteria
9.6.3 |  | Particle Breakdown | Inspection | NZTA B/5 | Within the first 20m of each run, and where ever material changes | Well mixed material with acceptable particle size distribution | W |  | Where breakdown is excessive, method of milling should be altered to avoid such breakdown
9.6.4 |  | FBS Quality | Inspection | Visual Inspection | Continuous while stabilisation is progressing | No bitumen stringers or blobs observed (See Assessment of hoe'd materials) | W |  | If bitumen blobs or stringers are found the the construction of FBS stops and the equipement is fixed so that there are no bitumen blobs or stringers found
10 | Construction Quality Assurance (QA)
10.1 | Field Compaction Target |  | NDM - Plateau | NZTA B/5 | 1 Every 3000m2 or once daily | Plateau testing done each shift / as required depending on the material variability throughout the site to determine compaction pattern. | V |  | Avg 98% plateau with min 95% |  | Construction Supervisor
10.2 | Lab testing |  | ITS/ UCS test | NZTA B/5 | 1 Every 3000m2 or once daily | Testing to be completed each shift / as required depending on the material variability throughout the site to verify compaction. | V |  | Tests to be cured & achieve as per specification. |  | Construction Supervisor / Renewals Engineer
10.3
10.3 | Compaction Testing |  | NDM | NZTA T23: 2021 Direct Transmission | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | Average ≥ 98% Plateau Minimum ≥ 95% Plateau | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Plateau) Compaction equipment shall be sufficent to achieve 98% MDD |  | Construction Supervisor / Renewals Engineer |  | Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
10.4 | [6 empty] | H
10.5
10.4 | Surface Set Up / Clegg Hammer |  | Clegg Hammer | Certified Clegg hammer (Current Certification sticker) & calibrated prior to use | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | CIV ≥ 40 | V |  | Hold point - membrane / chipseal placed once CIV ≥ 40 |  | Construction Supervisor/ Renewals Engineer |  | All test results to be submitted to NZTA for review and verification
H
10.5 | Degree of Saturation (DOS) |  | DOS | NZS 4407 Test 4.2.2 NZTA B/5 Cl. 7.12 | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | For information only | V |  | Target Solid Density to be determined on site
10.6 | NDM moisture correction |  | NDM & Lab MC |  | Start of works | Information only | V |  | Correction offset to be applied per site
10.7 | Surface Shape / Profile Layer Thickness |  | NZTA B/5 | Visual inspection Cut/fill tolerance check String records Straight edge | 1 test per 20m | ≤10mm variance from 3m straight edge | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved |  | Construction Supervisor/ Renewals PM/ Downer surveyor |  | Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
Gradual deviations
Crossfall > 1%
[6 empty] | Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design | H
-5mm +15mm or ±5mm at lip of concrete channel where applicable
10.8.1 | Tolerances | Width Unconstrained | TNZ B/2 | Confirm offset from lift pegs | 2 at every lift peg or per 180 m2 | - 20mm + 100mm | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved |  | Construction Supervisor/ Renewals Engineer |  | 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
H
10.8.2 |  | Width Constrained | TNZ B/2 | Stringline/lift pegs | 3 at every lift peg or per 180 m2 | Zero | V
H
10.9 | Ride Quality |  | Owner acceptance test | As per Contract Documents OPM42 | 1 ride test for each lane following Basecourse completion prior to surfacing | Rolling 100m average NAASRA <75 counts/km | W |  | Hold Point – no surfacing layer is to be applied until acceptance of ride quality, No exceptions |  | Road Science/ Downer PM |  | NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
H
10.1 | Mosaic Surface |  | Visual inspection | A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ | Overview of site for tight mosaic surface | The large aggregate is held in place by a matrix of smaller aggregates The smaller aggregate is held firmly in place by fine material The matrix does not displace under normal trafficking or sweeping | W |  | Hold Point – no surfacing layer is to be applied until passing results are achieved |  | NZTA Network Manager CWNOC Project Manager/Engineer Subcontractor/ Downer Construction Supervisor/Foreman Downer Sealing Supervisor/ Renewals Engineer/NZTA
H
10.11 | Preseal Check |  | Visual check | NZTA B/5 | Before sealing | All prior ITP checks have been completed and signed off | V |  | Hold Point – no surfacing layer is to be applied until all results are verified & approved as per ITP
[6 empty] | No caking layers present | H
10.12 | Pavement Surface As-Built
11 | Sealing
11.1 | Sealing |  | See Sealing ITP |  |  |  | W |  | Hold Point – All hold points and checks in ITP to be completed before physical works continue |  | Sealing Contract Manager
11.2 | Sealing TMP and Aftercare Process |  | See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site |  |  |  | W |  | Hold Point – 24 hour trafficking and aftercare of sealing works are described and confirmed in TMP for sealing works before physical sealing works proceed. |  | Construction Supervisor/ Sealing Supervisor
H
11.3 | Sweeping of Sealing Works and Handover to Roadmarkers |  | Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor. |  |  |  | W |  | Hold Point – All sweeping activities, roadmarking and install of RPM's to be completed before handover of site from surfacing to construction supervisor. |  | Construction Supervisor/ Sealing Supervisor
H
12 | Shoulders
12.1 | Slope |  | Visual check | Visual inspection with smart level |  | Slopes consistent & to 5:1 grade | V |  | Hold Point – no surfacing layer is to be applied until all necessary results are achieved |  | Construction Supervisor/ NZTA |  | Invite NZTA to carry out joint site inspection to inspect site.
H
12.2 | Compaction |  | Visual check | Drive over 4 tonne, check wheeltracks | All shoulders | Vehicles can drive on shoulders without becoming stuck | V |  | Hold Point – physical works cannot be completed until all necessary results are achieved |  | Construction Supervisor/ NZTA
H
12.3 | Soiling |  | Visual check | Approved Design Drawings | All areas requiring grassing | Soiling has been done where required | W |  | As per the design drawings |  | Construction Supervisor
13 | Site Reinstatement / Clearance
13.1 | Traffic Services | Marker Pegs/ Signs/Markings/RRPMs Replaced | TNZ C/20: 2003 | Visual Inspection | All signs/markers | Replaced in same position, height etc | V |  | Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced |  | Construction Supervisor/ NZTA |  | Invite NZTA to carry out joint site inspection to inspect site.
H
13.2 | Grassing |  | Visual check |  | All areas requiring grassing | Grassing has been done where required | W |  |  |  | Construction Supervisor
13.3 | Drains Cleared |  | Visual check |  | All drains, after all other works | Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated | W |  |  |  | Construction Supervisor
13.4 | Traffic Management Removed |  | Visual check |  | When safe, after all physical works completed | All traffic management removed from site safely | W |  | Hold Point – TMP cannot be removed until site Audited by Downer Construction Supervisor |  | Construction Supervisor
13.5 | Site Left Clean and Tidy |  | Visual check |  | After vacating site | · Stockpiles removed | V |  |  |  | Construction Supervisor/ NZTA |  | Invite NZTA to carry out joint site inspection to inspect site.
· Plant removed
· Litter cleared from site
14 | As-built Records
14.1 | Collect Asset Data |  | SHDOM (SM050) |  | During construction | All relevant as built information collected | V |  |  |  | Renewals Engineer
14.2 | Enter Asset Data into RAMM and/or Register(s) |  | SHDOM (SM050) | RAMM | At completion of work | All data entered into RAMM and/or register(s). Design report & drawings attached to RAMM site record as a media file. | H |  | Hold Point – project cannot be closed until data entered. |  | Renewals Engineer/ WSP Information Manager |  | Submit all RAMM Data to Data Quality Manager for review and verification
14.3 | Construction Completion Report |  | Confirmation | Contract Specification | At completion of work | Checked and approved | V |  |  |  | Renewals Engineer/ Renewals Manager |  | Submit Pavement Design Report, Construction Compliance, QMP, Site test results / inspections / activity records, Lessons Learnt, As-built Plans
| Quality Assurance Close Out By: | _________________________________________ |  |  | Date: ___________________ |  | _________________________________________________________
(signature)
_________________________________________________________
(name)
THIS RECORD TO CONTRACT FILE

## 0.5 FBS - Earthquake Gully
|  | Central Waikato NOC - Inspection & Test Plan - Catalogue Foam Stabilisation | [6 empty] | Document Number: | Pavement Renewals - Foam Stabilisation
|  | Site Name: | Earthquake Gully | [5 empty] | Revision Number: | 0.10 | Number of Pages: |  | 8
|  | Location: | SH1 01N-0713 8500 9274 | [5 empty] | Prepared: | M Owens | Date: |  | 2022-10-17
[9 empty] | Approved: | G Apiti | Date: |  | 2022-10-04
ITEM NUMBER | ACTIVITY DESCRIPTION |  | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | INSPECTORATE V/W/H |  |  |  | RESPONSIBLE PERSON | Sign & date if appropriate | RECORDS / REMARKS
[7 empty] | V=VERIFICATION, W=WITNESS, H =HOLD |  |  |  | As per Quality Plan
[7 empty] | Type | Assessor signature | Description |  |  |  | incl NCR ref
1 | Preliminary and General
1.1 | Construction Programme Completion |  | Confirmation | Best Practice Contract Specific MMP | Before work commences | Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date | V |  |  |  | Renewals Manager
1.2 | Approved RQP |  | Confirmation | Contract Specification | At least 24hrs before establishment or work commences | Principal's Acceptance according to guidelines in Appendix 6.3 | H |  | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours before establishing on site. |  | Renewals Manager |  | NZTA to approve.
1.3 | Notification of Intention to Start Work |  | Notification |  | Before work commences | Letter drop to local residents | H |  | Hold point - No physical work is to be commenced on site until notification has been sent to residents - no later than 24 hours prior to establishing on site. |  | Construction Supervisor / Renewals Engineer |  | NZTA to approve letter drop before distribution to residents.
1.4 | Traffic Management | TMP | Visual check | CoPTTM | Before work commences | TMP checked and approved Plans approved Current EED (if applicable) Size of site area to be checked to allow machinery to operate safely | H |  | Hold point - No traffic management is to be set up until TMP has been checked and approved |  | STMS |  | CAR No.
TMP No.
1.5 | Design Report Approval |  | Confirmation | NZTA NOC Rehab Catalogue Design & Treatment Approach | Before work commences | Principal Acceptance's acceptance according to NZTA Catalogue Design Approach document | H |  | Hold point - Review meeting with NZTA National & Regional Leads and Downer NOC Managers & Pavement Designers/Reviewers |  | NZTA Network Manager & Accreditied Designer |  | NZTA Approval to Proceed NTC No.
1.6 | Seal Design Approval |  | Confirmation | Review and Sign off by Downer Regional Sealing Manager | Before work commences | Downer Regional Sealing Manager reviews and signs off on Seal Design proposed. | H |  | Hold point - Review and approval of seal design completed |  | Regional Sealing Manager
1.7 | Project Manager Handover |  | Confirmation | Review and Sign off by Downer Designer to PM | Before work commences | Downer Technical Services Team Designer reviews and signs off on Handover. | H |  | Hold point - Handover completed |  | Regional Engineering Team Designer
1.8 | Crew Pack |  |  | Items to be included: | Before work commences | Approved TMP | H |  |  |  | Downer PM
Services location plans / Marked out
Approved RQP
Approved for Construction drawings & Pavement Design
Ramm data
Approved ITP
Crew Briefing Plan
2 | Setout / Site Preparation
2.1 | Setout |  | Survey | As per approved drawings | Per installation / Site | Design strings /design surface model loaded for machine control | V |  | Machine control requirement. Downer surveyor required for MC upload and verification of model operation |  | Downer Approved Surveyor
2.2 | Services (includes Traffic Count Loops and Traffic Signal Detector Loops) |  | Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth) | NZAUAG Guide to Working on the Road | Before work commences | Zero service strikes | H |  | Hold point - No excavation is to be commenced until services are located and accounted for |  | Construction Supervisor
2.3 | Cultural/Heritage Risk Assessment |  | Notification | NZTA Cultural & Heritage Risk Model | Before work commences | Local iwi has been notified of intent to start work | H |  | Where risk of cultural discovery |  | Renewals Engineer / Manager
2.4 | Archaeological Risk |  | Toolbox meeting | NZTA Cultural & Heritage Risk Model | Before work commences | Toolbox meeting held covering accidental discovery protocol | H |  | Hold point - No excavation is to be commenced until toolbox meeting is held |  | Construction Supervisor
2.5 | Traffic Management | Signs Setup | Visual check | Traffic Management Plan | Before work commences each day | Traffic management complies with TMP | H |  | Hold point - No physical works are to be commenced until necessary traffic management is in place |  | STMS |  | Daily site record sheet
2.6 | Pre-Construction walkover |  | Visual check | Approved Crew pack on site 2 weeks prior to work comencing | Before work commences | Principal / Highways / Downer Acceptance | H |  | Hold point - Walkover required ahead of Highways establishment |  | Renewals Manager / Highways PM / MCM |  | Invite for NZTA to carry out joint site visit to complete visual inspection
Hold point - No physical works are to be commenced until walkover completed
3 | Preliminary Works
3.1 | Shoulder Stripping / Vegetation clearing |  | Visual check | On site |  | Shoulder stripping as per drawings completed | V |  |  |  | Construction Supervisor / NZTA |  | Invite for NZTA to carry out joint site visit to complete visual inspection
3.2 | Site pavement A/C digouts |  | Visual check | Check RAMM records for depths | Before Stabilisation work commences | Work completed prior to stablisation contractor onsite | V |  | A/C Mill & Fills to be cut to waste & replaced with M/4 AP40 compacted & sealed |  | Site Foreman
4 | Culvert extensions / Headwalls / Flumes
4.1 | Excavation Inlet / Outlet Gradients |  | Survey | NZTA F/3 | Once | Consistent gradient in and out | H |  | Hold Point – Visual check prior to pipe placement |  | Site foreman |  | Required Yes / No
4.2 | Pipe materials / class |  | Visual Check | NZTA F/3 2.1 | Once | Meets appropriate AS/NZ standard reletive to specified type | V |  |  |  | Site foreman |  | Required Yes / No
4.3 | Bedding contact |  | Visual Check | NZTA F/3 5.1 | continuous | uniform contact over full length of pipe | V |  |  |  | Site foreman |  | Required Yes / No
5 | Subsoil drainage
5.1 | Trench |  | Visual |  | each site | Depth minimum 1.0m Width minimum 300mm, fall > 1:100, free from rocks etc. Position as per the design drawings +/- 100mm | H |  | Hold Point – Visual check prior to pipe placement |  | Site foreman |  | Required Yes / No
5.2 | Drainage material |  | Visual |  | each site | 7-12mm clean filter material ( grade 2 - 4 Sealing chip | H |  | Hold Point – Visual check prior to pipe placement |  | Site foreman |  | Required Yes / No
5.3 | Pipe type |  | Visual | Diameter as per the design drawings | Use outside traffic Lane | Docket to confirm | V |  | "Nova flow" |  | Site foreman |  | Required Yes / No
|  |  | Visual |  | Under traffic lane | Docket to confirm | V |  | Nexus |  | Site foreman |  | Required Yes / No
5.4 | Filter Fabric |  | Visual |  |  | 150mm lap, top of fabric minimum 150mm below FSL | H |  | Hold Point – Visual check prior to reinstatement |  | Site foreman |  | Required Yes / No
5.5 | Outlet |  | Visual |  |  | Connect to sump barrel, culvert of construct Concrete Apron | H |  | Hold Point – Visual check prior to reinstatement |  | Site foreman |  | Required Yes / No
5.6 | Flushing / Cleaning eyes |  | Visual | To be placed & constructed as per Approved Drawings | Each free end | [7 empty] | Required Yes / No
5.7 | Reinstatement |  | Sealed Pavement |  |  | Pavement matches surrounding, surface with AC or 3/5 chip | V |  |  |  | Site foreman |  | Required Yes / No
|  |  | Berms and shoulder |  |  | Top min 150mm impermiable backfill | V |  |  |  | Site foreman |  | Required Yes / No
6 | Preteatment of Insitu Materials
6.1.1 | Pretreatment Stabilising Agent (where applicable) | Quick / Hydrated Lime or KOBM | Mat Test 1m² canvas | Pavement design report 1% additive | Every 400m² | Within ±0.5kg/m² of the specified rate | V |  | Tonnage/m² records shall be kept, including mat results |  | Highways Site Foreman |  | Daily Job Record
6.1.2 |  |  | Average usage test | Pavement design report 1% additive | Upon emptying the spreader and bulk tanker | Withn ±2.5% of the specified rate | V
6.2 | Stabilising Depth | Hoe Depth | Depth measurement | Design drawings | At both ends & sides of cut and every 200m | -5mm +15mm of design depth | W |  |  |  | Highways Site Foreman |  | Daily Job Record
6.3.1 | Pre-Hoe |  | Visual Inspection |  | Each Subsection | No unsuitable material found to be sampled | H |  | Hold point - Hoed material to be checked to ensure consistencey and no unsuitable material found, Sample to be taken for future testing if required |  | Renewals Manager
6.3.2 | Visual Inspection post Hoe | Proof Roll and Joint Inspection | Visual Inspection | 6x4 truck fully loaded or similar equivalent | Each Subsection | No significant movement of the pavement under proof rolling and/or trafficing, for subgrade contamination | V |  | Testing to be carried out imediately after compaction |  | Highways Site Foreman / Downer PM
6.3.3 |  | Material FBS Suitability | Visual Inspection | Particle size to be 50mm or less | Each Subsection, as required | No large slabs of existing wearing course or strongly bound base | V
6.3.4 | Undercut unsuitable areas |  | Visual Inspection/ measurements | Depth to be determined on site from investigations as per fig 15 Undercut & Reconstruct table | Where required | All unsuitable material removed. Excavated hole to be backfilled with M/4 AP40 & compacted to | H |  |  |  | Renewals Manager
6.3.5 | Shape & Compact Hoed layer |  | Check measurements | Shape to correct as per the design | Every 20m | Max 200mm layer depth to achieve compaction |  |  | M/4 AP 40 Verified min 75mm overlay depth with no removal of pre hoed material in the traffic lane |  | Highways Site Foreman / Downer PM /Downer Surveyor
7 | Imported Basecourse Materials Testing
7.1.1 | Imported Basecourse Materials Source Property Testing | Crushing Resistance | NZTA M/4 Crushing Resistance (CR130) Test | NZS 4407 Test 3.10 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve | V |  | Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old |  | Renewals Engineer |  | All source aggregate test results to be submitted to NZTA for review and verification
|  |  |  | NZTA M/4 |  |  | H
7.1.2 |  | Weathering Quality | Weathering Quality Index (WQI) Test | NZS 4407 Test 3.11 |  | Must have quality index of AA, AB, AC, BA, BB or CA | V
H
NZTA M/4
7.1.3 |  | Bearing Strength | Californian Bearing Ratio (CBR) | NZS 4407 T3.15 NZS 4402 T4.1.3 |  | Soaked CBR ≥ 80% when compacted/tested in accordance with both tests | V
|  |  |  | NZTA M/4 |  |  | H
7.2 | Imported Basecourse Materials Production Property Testing |  | Comply with project specification, PSD, Broken Faces, Quality of Fines (QoF) | Refer project specification and NZTA M/4 | 1 - 400m3 – 2 tests 400 - 1500m3 - 3 tests 1500 - 4000m3 – 4 tests >4000m3 – 1 test per 1000m3 | Refer project specification | V |  | Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old |  | Renewals Engineer |  | All production aggregate test results to be submitted to NZTA for review and verification
H
7.3 | Nominal 75mm Make-up Metal |  | Quantity of material used | 75mm depth over high spots | Each Subsection | Correct amount of material used (M³Solid) as per geometric design / MC | V |  | Spot checks to be taken |  | Downer surveyor
8 | Foamed Bitumen Stabilisation
8.1.1 | Stabilisation Agents | Foam Bitumen | Laboratory testing | NZTA B/5 NZTA M/1 (B/7) | Per batch | 80/100 or 180/200 Pen Grade Minimum expansion of 10 times original volume, & half-life of at least 6 seconds | V |  | Hold Point -No Bitumen shall be used on site with out a pass result as per Lab test results |  | Renewals Engineer |  | All stabilisation material and laboratory testing results to be submitted to NZTA for review and verification.
H
8.1.2 |  | Cement | See NZS 3122 | NZS 3122 NZTA B/5 Cl. 4.1.2 | Per batch | Cement must comply with NZS 3122 | V |  | Hold Point - No cement shall be spread on site with out a pass result, obtainable from supplier (this is to be done once for contract)
H
8.1.3 |  | Delivery | Visual Inspection | NZTA B/2 | Upon delivery | Stabilising agents to be delivered in tanks or trucks with Certificate of Loading | W |  | Certificate of loading to be checked on site |  | Site Foreman
8.1.4 |  | Bitumen Storage | 80/100 Pen Grade | NZTA B/5 | 2 hours before use | Max storage temp: not exceed 125°C for > 24 hours & 175°C for < 24 hours Application temp: min 175°C - max 190°C | H |  | Any bitumen that has been heated above the maximum shall be removed from site
|  |  | 180/200 Pen Grade | NZTA B/5 | 2 hours before use | Max storage temp: not exceed 120°C for > 24 hours & 170°C for < 24 hours Application temp: min 170°C - max 185°C | H
8.2 | Water |  | Obtained from a suitable source | NZTA B/5(B7) Portable PH testing | Ongoing | Water for stabilisation, construction and curing is tested for correct PH for each site | W |  | Certification required for each site (PH 5.5 -7.0) |  | Downer PM
8.3.1 | Weather Limitations | Temperature | Measure Temperature | NZTA B/5 | Daily | Stabilised material before compaction 20°C | W |  | Work shall not be started if temperature is below the respective minimums. |  | Site Foreman / Downer PM
8.3.2 |  | Wind | Assessment | NZTA B/5 | Daily (SEE remarks) | Maximum windspeed of 25km/hr checked from metservice website | W |  | Work shall not be started if windspeed exceeds the maximum |  |  |  | Not applicable if direct injection used
6.3.3 |  | Rain | Check forecast | NZTA B/5 | Daily | Low likelihood of rain | W |  | Work shall not be started if rain is forecast for the immediate work day and the following day for the aftercare.
8.4.1 | Spreading | Cement | Mat Test 1m² canvas | NZTA B/5 | Every 400m² | Within ±0.5km/m² of the specified rate | V |  | Tonnage/m² records shall be kept, including mat results |  | Site Foreman |  | Not applicable if direct injection used
|  |  | Average usage test | NZTA B/5 | Upon emptying the spreader and bulk tanker | Withn ±2.5% of the specified rate | V
8.4.2 |  | Bituminous Agents | Flow meter display | NZTA B/5 | Continuous | Withn ±5% of the specified rate | W |  | Tonnage/m² records shall be kept, including mat results
|  |  | Microprocessors reading | NZTA B/5 | End of each run | Withn ±3.0% of the specified rate | W
|  |  | Average usage test | NZTA B/5 | Upon emptying the bulk tanker | Withn ±2.5% of the specified rate | W
8.5.1 | Time Limitations | Cement | The maximum time period from mixing to primary compaction | NZTA B/5 | Post stabilisation | 2 hours - Time start to time end to be recorded | H |  | Where time the time limit is exceeded, details of the remedial action shall be prepared for assessment, and procedures for further stabilisations sections must be agreed to avoid further occurances |  | Downer PM
8.5.2 |  | Foam Bitumen |  | NZTA B/5 |  | 4 hours - Time start to time end to be recorded | H
8.5.3 |  | Combination |  | NZTA B/5 |  | The shorter of the individual agents | H
8.6.1 | Insitu Mixing | Cut Depth | Depth measurement | NZTA B/5 | At start & end of cut and every 200m | -5mm +15mm of design depth | W |  |  |  | Site Foreman
8.6.2 |  | Join Overlap | Inspection | NZTA B/5 | Continuous | 100mm overlap | W |  | All cuts shall overlap by the minimum acceptance criteria
8.6.3 |  | Particle Breakdown | Inspection | NZTA B/5 | Within the first 20m of each run, and where ever material changes | Well mixed material with acceptable particle size distribution | W |  | Where breakdown is excessive, method of milling should be altered to avoid such breakdown
8.6.4 |  | FBS Quality | Inspection | Visual Inspection | Continuous while stabilisation is progressing | No bitumen stringers or blobs observed (See Assessment of hoe'd materials) | W |  | If bitumen blobs or stringers are found the the construction of FBS stops and the equipement is fixed so that there are no bitumen blobs or stringers found
9 | Construction Quality Assurance (QA)
9.1 | Field Compaction Target |  | NDM - Plateau | NZTA B/5 | 1 Every 3000m2 or once daily | Plateau testing done each shift / as required depending on the material variability throughout the site to determine compaction pattern. | V |  | Avg 98% plateau with min 95%. Plateau testing to be completed to determine Field Compaction Target |  | Construction Supervisor |  | Verified test results of plateau to be supplied
9.2 | Lab testing |  | ITS/ UCS test | NZTA B/5 | 1 Every 3000m2 or once daily | Testing to be completed each shift / as required depending on the material variability throughout the site to verify compaction. | V |  | Tests to be cured & achieve as per specification. |  | Construction Supervisor / Renewals Engineer
9.3 | Compaction Testing |  | NDM | NZTA T23: 2021 Direct Transmission | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | Average ≥ 98% Plateau Minimum ≥ 95% Plateau | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Plateau) Compaction equipment shall be sufficent to achieve 98% MDD |  | Construction Supervisor / Renewals Engineer |  | Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
H
9.4 | Surface Set Up / Clegg Hammer |  | Clegg Hammer | Certified Clegg hammer (Current Certification sticker) & calibrated prior to use | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | CIV ≥ 40 | V |  | Hold point - membrane / chipseal placed once CIV ≥ 40 |  | Construction Supervisor/ Renewals Engineer |  | All test results to be submitted to NZTA for review and verification
H
9.5 | Degree of Saturation (DOS) |  | DOS | NZS 4407 Test 4.2.2 NZTA B/5 Cl. 7.12 | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | For information only | V |  | Soild density to be measured. |  | Downer Lab technician
9.6 | NDM moisture correction |  | NDM & Lab MC |  | 3x Moisture contents per single plateau test carried out | Information only | V |  | Correction offset to be applied per site |  | Construction Supervisor / Renewals Engineer - Relates to field plateau testing by the laboratory
9.7 | Surface Shape / Profile Layer Thickness |  | NZTA B/5 | Visual inspection Cut/fill tolerance check String records Straight edge | 1 test per 20m | ≤10mm variance from 3m straight edge | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved. Hiways Retain the right to override Machine Control requirement when required. Documentation and Record to supplement reasoning and affected area |  | Construction Supervisor/ Renewals PM/ Downer surveyor |  | Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
Gradual deviations
Crossfall > 1%
[6 empty] | Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design | H
-5mm +15mm or ±5mm at lip of concrete channel where applicable
9.6.1 | Tolerances | Width Unconstrained | TNZ B/2 | Confirm offset from lift pegs | 2 at every lift peg or per 180 m2 | - 20mm + 100mm | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved |  | Construction Supervisor/ Renewals Engineer |  | 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
H
9.6.2 |  | Width Constrained | TNZ B/2 | Stringline/lift pegs | 3 at every lift peg or per 180 m2 | Zero | V
H
9.8 | Ride Quality |  | Owner acceptance test | As per Contract Documents OPM42 | 1 ride test for each lane following Basecourse completion prior to surfacing | Rolling 100m average NAASRA <75 counts/km | W |  | Hold Point – no surfacing layer is to be applied until acceptance of ride quality, No exceptions |  | Road Science/ Downer PM |  | NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
H
9.9 | Mosaic Surface |  | Visual inspection | A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ | Overview of site for tight mosaic surface | The large aggregate is held in place by a matrix of smaller aggregates The smaller aggregate is held firmly in place by fine material The matrix does not displace under normal trafficking or sweeping | W |  | Hold Point – no surfacing layer is to be applied until passing results are achieved |  | NZTA Network Manager CWNOC Project Manager/Engineer Subcontractor/ Downer Construction Supervisor/Foreman Downer Sealing Supervisor/ Renewals Engineer/NZTA
H
9.10 | Preseal Check |  | Visual check | NZTA B/5 | Before sealing | All prior ITP checks have been completed and signed off | V |  | Hold Point – no surfacing layer is to be applied until all results are verified & approved as per ITP
[6 empty] | No caking layers present | H
9.11 | Pavement Surface As-Built |  | Survey | As per approved drawings | Per installation / Site | Accurate survey of all topograpgical features required | V |  |  |  | Downer Approved Surveyor
10 | Sealing
10.1 | Sealing |  | See Sealing ITP |  |  |  | W |  | Hold Point – All hold points and checks in ITP to be completed before physical works continue |  | Sealing Contract Manager
10.2 | Sealing TMP and Aftercare Process |  | See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site |  |  |  | W |  | Hold Point – 24 hour trafficking and aftercare of sealing works are described and confirmed in TMP for sealing works before physical sealing works proceed. |  | Construction Supervisor/ Sealing Supervisor
H
10.3 | Sweeping of Sealing Works and Handover to Roadmarkers |  | Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor. |  |  |  | W |  | Hold Point – All sweeping activities, roadmarking and install of RPM's to be completed before handover of site from surfacing to construction supervisor. |  | Construction Supervisor/ Sealing Supervisor
H
11 | Shoulders
11.1 | Slope |  | Visual check | Visual inspection with smart level |  | Slopes consistent & to 5:1 grade. Excessive shoulder construction to be carried out ahead of pavement operation | V |  | Hold Point – no surfacing layer is to be applied until all necessary results are achieved |  | Construction Supervisor/ NZTA |  | Invite NZTA to carry out joint site inspection to inspect site.
H
11.2 | Compaction |  | Visual check | Drive over 4 tonne, check wheeltracks | All shoulders | Vehicles can drive on shoulders without becoming stuck | V |  | Hold Point – physical works cannot be completed until all necessary results are achieved |  | Construction Supervisor/ NZTA
H
11.3 | Soiling |  | Visual check | Approved Design Drawings | All areas requiring grassing | Soiling has been done where required | W |  | As per the design drawings |  | Construction Supervisor
12 | Site Reinstatement / Clearance
12.1 | Traffic Services | Marker Pegs/ Signs/Markings/RRPMs Replaced | TNZ C/20: 2003 | Visual Inspection | All signs/markers | Replaced in same position, height etc | V |  | Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced |  | Construction Supervisor/ NZTA |  | Invite NZTA to carry out joint site inspection to inspect site.
H
12.2 | Grassing |  | Visual check |  | All areas requiring grassing | Grassing has been done where required | W |  |  |  | Construction Supervisor
12.3 | Drains Cleared |  | Visual check |  | All drains, after all other works | Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated | W |  |  |  | Construction Supervisor
12.4 | Traffic Management Removed |  | Visual check |  | When safe, after all physical works completed | All traffic management removed from site safely | W |  | Hold Point – TMP cannot be removed until site Audited by Downer Construction Supervisor |  | Construction Supervisor
12.5 | Site Left Clean and Tidy |  | Visual check |  | After vacating site | · Stockpiles removed | V |  |  |  | Construction Supervisor/ NZTA |  | Invite NZTA to carry out joint site inspection to inspect site.
· Plant removed
· Litter cleared from site
13 | As-built Records
13.1 | Collect Asset Data |  | SHDOM (SM050) |  | During construction | All relevant as built information collected | V |  |  |  | Renewals Engineer
13.2 | Enter Asset Data into RAMM and/or Register(s) |  | SHDOM (SM050) | RAMM | At completion of work | All data entered into RAMM and/or register(s). Design report & drawings attached to RAMM site record as a media file. | H |  | Hold Point – project cannot be closed until data entered. |  | Renewals Engineer/ WSP Information Manager |  | Submit all RAMM Data to Data Quality Manager for review and verification
13.3 | Construction Completion Report |  | Confirmation | Contract Specification | At completion of work | Checked and approved | V |  |  |  | Renewals Engineer/ Renewals Manager |  | Submit Pavement Design Report, Construction Compliance, QMP, Site test results / inspections / activity records, Lessons Learnt, As-built Plans
| Quality Assurance Close Out By: | _________________________________________ |  |  | Date: ___________________ |  | _________________________________________________________
(signature)
_________________________________________________________
(name)
THIS RECORD TO CONTRACT FILE
Note on C37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Might pay to add a requird yes/no feild here to make it clear. Same for subsoils, dont want someone reviewing this to thik we didnt do it

## 0.5 FBS - Puriri Curves
|  | Central Waikato NOC - Inspection & Test Plan - Catalogue Foam Stabilisation | [6 empty] | Document Number: | Pavement Renewals - Foam Stabilisation
|  | Site Name: | Puriri Curves | [5 empty] | Revision Number: | 0.9A | Number of Pages: |  | 10
|  | Location: | SH1 01N-0625 3842 5143 | [5 empty] | Prepared: | M Owens | Date: |  | 2022-10-17
[9 empty] | Approved: | G Apiti | Date: |  | 2022-10-04
ITEM NUMBER | ACTIVITY DESCRIPTION |  | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | INSPECTORATE V/W/H |  |  |  | RESPONSIBLE PERSON | Sign & date if appropriate | RECORDS / REMARKS
[7 empty] | V=VERIFICATION, W=WITNESS, H =HOLD |  |  |  | As per Quality Plan
[7 empty] | Type | Assessor signature | Description |  |  |  | incl NCR ref
1 | Preliminary and General
1.1 | Construction Programme Completion |  | Confirmation | Best Practice Contract Specific MMP | Before work commences | Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date | V |  |  |  | Renewals Manager
1.2 | Approved RQP |  | Confirmation | Contract Specification | At least 24hrs before establishment or work commences | Principal's Acceptance according to guidelines in Appendix 6.3 | H |  | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours before establishing on site. |  | Renewals Manager |  | NZTA to approve.
1.3 | Notification of Intention to Start Work |  | Notification |  | Before work commences | Letter drop to local residents | H |  | Hold point - No physical work is to be commenced on site until notification has been sent to residents - no later than 24 hours prior to establishing on site. |  | Construction Supervisor / Renewals Engineer |  | NZTA to approve letter drop before distribution to residents.
1.4 | Traffic Management | TMP | Visual check | CoPTTM | Before work commences | TMP checked and approved Plans approved Current EED (if applicable) Size of site area to be checked to allow machinery to operate safely | H |  | Hold point - No traffic management is to be set up until TMP has been checked and approved |  | STMS |  | CAR No.
TMP No.
1.5 | Design Report Approval |  | Confirmation | NZTA NOC Rehab Catalogue Design & Treatment Approach | Before work commences | Principal Acceptance's acceptance according to NZTA Catalogue Design Approach document | H |  | Hold point - Review meeting with NZTA National & Regional Leads and Downer NOC Managers & Pavement Designers/Reviewers |  | NZTA Network Manager & Accreditied Designer |  | NZTA Approval to Proceed NTC No.
1.6 | Seal Design Approval |  | Confirmation | Review and Sign off by Downer Regional Sealing Manager | Before work commences | Downer Regional Sealing Manager reviews and signs off on Seal Design proposed. | H |  | Hold point - Review and approval of seal design completed |  | Regional Sealing Manager
1.7 | Project Manager Handover |  | Confirmation | Review and Sign off by Downer Designer to PM | Before work commences | Downer Technical Services Team Designer reviews and signs off on Handover. | H |  | Hold point - Handover completed |  | Regional Engineering Team Designer
1.8 | Crew Pack |  |  | Items to be included: | Before work commences | Approved TMP | H |  |  |  | Downer PM
Services location plans / Marked out
Approved RQP
Approved for Construction drawings & Pavement Design
Ramm data
Approved ITP
Crew Briefing Plan
2 | Setout / Site Preparation
2.1 | Setout |  | Survey | As per approved drawings | Per installation / Site | Design strings /design surface model loaded for machine control | V |  | Machine control requirement. Downer surveyor required for MC upload and verification of model operation |  | Downer Approved Surveyor
2.2 | Services (includes Traffic Count Loops and Traffic Signal Detector Loops) |  | Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth) | NZAUAG Guide to Working on the Road | Before work commences | Zero service strikes | H |  | Hold point - No excavation is to be commenced until services are located and accounted for |  | Construction Supervisor
2.3 | Cultural/Heritage Risk Assessment |  | Notification | NZTA Cultural & Heritage Risk Model | Before work commences | Local iwi has been notified of intent to start work | H |  | Where risk of cultural discovery |  | Renewals Engineer / Manager
2.4 | Archaeological Risk |  | Toolbox meeting | NZTA Cultural & Heritage Risk Model | Before work commences | Toolbox meeting held covering accidental discovery protocol | H |  | Hold point - No excavation is to be commenced until toolbox meeting is held |  | Construction Supervisor
2.5 | Traffic Management | Signs Setup | Visual check | Traffic Management Plan | Before work commences each day | Traffic management complies with TMP | H |  | Hold point - No physical works are to be commenced until necessary traffic management is in place |  | STMS |  | Daily site record sheet
2.6 | Pre-Construction walkover |  | Visual check | Approved Crew pack on site 2 weeks prior to work comencing | Before work commences | Principal / Highways / Downer Acceptance | H |  | Hold point - Walkover required ahead of Highways establishment |  | Renewals Manager / Highways PM / MCM |  | Invite for NZTA to carry out joint site visit to complete visual inspection
Hold point - No physical works are to be commenced until walkover completed
3 | Preliminary Works
3.1 | Shoulder Stripping / Vegetation clearing |  | Visual check | On site |  | Shoulder stripping as per drawings completed | V |  |  |  | Construction Supervisor / NZTA |  | Invite for NZTA to carry out joint site visit to complete visual inspection
3.2 | Site pavement A/C digouts |  | Visual check | Check RAMM records for depths | Before Stabilisation work commences | Work completed prior to stablisation contractor onsite | V |  | A/C Mill & Fills to be cut to waste & replaced with M/4 AP40 compacted & sealed |  | Site Foreman
4 | Culvert extensions / Headwalls / Flumes
4.1 | Excavation Inlet / Outlet Gradients |  | Survey | NZTA F/3 | Once | Consistent gradient in and out | H |  | Hold Point – Visual check prior to pipe placement |  | Site foreman |  | Required Yes / No
4.2 | Pipe materials / class |  | Visual Check | NZTA F/3 2.1 | Once | Meets appropriate AS/NZ standard reletive to specified type | V |  |  |  | Site foreman |  | Required Yes / No
4.3 | Bedding contact |  | Visual Check | NZTA F/3 5.1 | continuous | uniform contact over full length of pipe | V |  |  |  | Site foreman |  | Required Yes / No
5 | Subsoil drainage
5.1 | Trench |  | Visual |  | each site | Depth minimum 1.0m Width minimum 300mm, fall > 1:100, free from rocks etc. Position as per the design drawings +/- 100mm | H |  | Hold Point – Visual check prior to pipe placement |  | Site foreman |  | Required Yes / No
5.2 | Drainage material |  | Visual |  | each site | 7-12mm clean filter material ( grade 2 - 4 Sealing chip | H |  | Hold Point – Visual check prior to pipe placement |  | Site foreman |  | Required Yes / No
5.3 | Pipe type |  | Visual | Diameter as per the design drawings | Use outside traffic Lane | Docket to confirm | V |  | "Nova flow" |  | Site foreman |  | Required Yes / No
|  |  | Visual |  | Under traffic lane | Docket to confirm | V |  | Nexus |  | Site foreman |  | Required Yes / No
5.4 | Filter Fabric |  | Visual |  |  | 150mm lap, top of fabric minimum 150mm below FSL | H |  | Hold Point – Visual check prior to reinstatement |  | Site foreman |  | Required Yes / No
5.5 | Outlet |  | Visual |  |  | Connect to sump barrel, culvert of construct Concrete Apron | H |  | Hold Point – Visual check prior to reinstatement |  | Site foreman |  | Required Yes / No
5.6 | Flushing / Cleaning eyes |  | Visual | To be placed & constructed as per Approved Drawings | Each free end | [7 empty] | Required Yes / No
5.7 | Reinstatement |  | Sealed Pavement |  |  | Pavement matches surrounding, surface with AC or 3/5 chip | V |  |  |  | Site foreman |  | Required Yes / No
|  |  | Berms and shoulder |  |  | Top min 150mm impermiable backfill | V |  |  |  | Site foreman |  | Required Yes / No
6 | Kerb & Channel / Dish drain
6.1 | Setout |  | Visual | As per approved drawings | Daily | Design stringsline | V |  | Visually inspect alignment and fall daily. |  | Site Foreman
6.2 | Excavation |  | Stringlines |  | When required | 300mm below base of kerb | V |  |  |  | Site Foreman |  | String sheet.
6.3 | Subgrade |  | Visual |  | When required | Free from poor material | V |  | Visual inspection with photos. |  | Site Foreman
6.4 | Kerb & Channel bedding | Compaction | Clegg Tests | On site | Clegg Tests at regular intervals | Minimum CIV 25. +/- 5mm | H |  | Hold Point – Visual check prior placement |  | Site Foreman
6.5 | Kerb & Channel alignment | Compaction | Visual | Survey | Pre Pour | Kerb setout is still in alignment, fall is correct | H |  | Hold Point – Visual check prior placement |  | Site Foreman / Kerbing supplier
6.6 | Concrete Supply | Compaction | Visual | Supplied Docket | When required | 25mPa Concrete | V |  |  |  | Kerbing Supplier
6.7 | Contraction/Expansion Joints | Compaction | Visual | Site Measure | When required | Spacing <3m and penetration >50mm with mortar dressing | V |  |  |  | Site Foreman / Kerbing supplier
7 | Preteatment of Insitu Materials
7.1.1 | Pretreatment Stabilising Agent (where applicable) | Quick / Hydrated Lime or KOBM | Mat Test 1m² canvas | Pavement design report | Every 400m² | Within ±0.5kg/m² of the specified rate | V |  | Tonnage/m² records shall be kept, including mat results |  | Highways Site Foreman |  | Daily Job Record
7.1.2 |  |  | Average usage test | Pavement design report | Upon emptying the spreader and bulk tanker | Withn ±2.5% of the specified rate | V
7.2 | Stabilising Depth | Hoe Depth | Depth measurement | Design drawings | At both ends & sides of cut and every 200m | -5mm +15mm of design depth | W |  |  |  | Highways Site Foreman |  | Daily Job Record
7.3.1 | Pre-Hoe |  | Visual Inspection |  | Each Subsection | No unsuitable material found to be sampled | H |  | Hold point - Hoed material to be checked to ensure consistencey and no unsuitable material found, Sample to be taken for future testing if required |  | Renewals Manager / Highways Site Foreman
7.3.2 | Visual Inspection post Hoe | Proof Roll and Joint Inspection | Visual Inspection | 6x4 truck fully loaded or similar equivalent | Each Subsection | No significant movement of the pavement under proof rolling and/or trafficing, for subgrade contamination | V |  | Testing to be carried out imediately after compaction |  | Highways Site Foreman / Downer PM
7.3.3 |  | Material FBS Suitability | Visual Inspection | Particle size to be 50mm or less | Each Subsection, as required | No large slabs of existing wearing course or strongly bound base | V
7.3.4 | Undercut unsuitable areas |  | Visual Inspection/ measurements | Depth to be determined on site from investigations as per fig 15 Undercut & Reconstruct table | Where required | All unsuitable material removed. Excavated hole to be backfilled with M/4 AP40 & compacted to | H |  |  |  | Renewals Manager
7.3.5 | Shape & Compact Hoed layer |  | Check for 75mm overlay | Shape to correct as per the existing surface | Every 20m | Max 200mm layer depth to achieve compaction & trimmed to match existing shape and trafficable |  |  | Verified min 75mm overlay depth with no removal of pre hoed material in the traffic lane |  | Highways Site Foreman / Downer PM /Downer Surveyor |  | Joint inspection
8 | Imported Basecourse Materials Testing
8.1.1 | Imported Basecourse Materials Source Property Testing | Crushing Resistance | NZTA M/4 Crushing Resistance (CR130) Test | NZS 4407 Test 3.10 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve | V |  | Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old |  | Renewals PM |  | All source aggregate test results to be submitted to NZTA for review and verification
|  |  |  | NZTA M/4 |  |  | H
8.1.2 |  | Weathering Quality | Weathering Quality Index (WQI) Test | NZS 4407 Test 3.11 |  | Must have quality index of AA, AB, AC, BA, BB or CA | V
H
NZTA M/4
8.1.3 |  | Bearing Strength | Californian Bearing Ratio (CBR) | NZS 4407 T3.15 NZS 4402 T4.1.3 |  | Soaked CBR ≥ 80% when compacted/tested in accordance with both tests | V
|  |  |  | NZTA M/4 |  |  | H
8.2 | Imported Basecourse Materials Production Property Testing |  | Comply with project specification, PSD, Broken Faces, Quality of Fines (QoF) | Refer project specification and NZTA M/4 | 1 - 400m3 – 2 tests 400 - 1500m3 - 3 tests 1500 - 4000m3 – 4 tests >4000m3 – 1 test per 1000m3 | Refer project specification | V |  | Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old |  | Renewals PM |  | All production aggregate test results to be submitted to NZTA for review and verification
H
8.3 | Nominal 75mm Make-up Metal |  | Quantity of material used | 75mm depth over high spots | Each Subsection | Correct amount of material used (M³Solid) as per geometric design / MC | V |  | Spot checks to be taken |  | Downer surveyor
9 | Foamed Bitumen Stabilisation
9.1.1 | Stabilisation Agents | Foam Bitumen | Laboratory testing | NZTA B/5 NZTA M/1 (B/7) | Per batch | 80/100 or 180/200 Pen Grade Minimum expansion of 10 times original volume, & half-life of at least 6 seconds | V |  | Hold Point -No Bitumen shall be used on site with out a pass result as per Lab test results |  | Renewals Engineer |  | All stabilisation material and laboratory testing results to be submitted to NZTA for review and verification.
H
9.1.2 |  | Cement | See NZS 3122 | NZS 3122 NZTA B/5 Cl. 4.1.2 | Per batch | Cement must comply with NZS 3122 | V |  | Hold Point - No cement shall be spread on site with out a pass result, obtainable from supplier (this is to be done once for contract)
H
9.1.3 |  | Delivery | Visual Inspection | NZTA B/2 | Upon delivery | Stabilising agents to be delivered in tanks or trucks with Certificate of Loading | W |  | Certificate of loading to be checked on site |  | Highways Site Foreman
9.1.4 |  | Bitumen Storage | 80/100 Pen Grade | NZTA B/5 | 2 hours before use | Max storage temp: not exceed 125°C for > 24 hours & 175°C for < 24 hours Application temp: min 175°C - max 190°C | H |  | Any bitumen that has been heated above the maximum shall be removed from site
|  |  | 180/200 Pen Grade | NZTA B/5 | 2 hours before use | Max storage temp: not exceed 120°C for > 24 hours & 170°C for < 24 hours Application temp: min 170°C - max 185°C | H
9.2 | Water |  | Obtained from a suitable source | NZTA B/5(B7) Portable PH testing | Ongoing | Water for stabilisation, construction and curing is tested for correct PH for each site | W |  | Certification required for each site (PH 5.5 -7.0) |  | Downer PM
9.3.1 | Weather Limitations | Temperature | Measure Temperature | NZTA B/5 | Daily | Stabilised material before compaction 20°C | W |  | Work shall not be started if temperature is below the respective minimums. |  | Highways Site Foreman / Downer PM |  | Joint Inspection
9.3.2 |  | Wind | Assessment | NZTA B/5 | Daily (SEE remarks) | Maximum windspeed of 25km/hr checked from metservice website | W |  | Work shall not be started if windspeed exceeds the maximum |  |  |  | Not applicable if direct injection used
9.3.3 |  | Rain | Check forecast | NZTA B/5 | Daily | Spreading has not commenced during rainfall. Spreading has not commenced if rainfall is due prior to completion of mixing. | W |  | No spreading of binding agents shall commence if it is raining. If rain is likely to start before the binding agent(s) can be mixed into the aggregate, then spreading of the binding agent(s) shall not take place.
9.4.1 | Spreading | Cement | Mat Test 1m² canvas | NZTA B/5 | Every 400m² | Within ±0.5km/m² of the specified rate | V |  | Tonnage/m² records shall be kept, including mat results |  | Highways Site Foreman |  | Not applicable if direct injection used
|  |  | Average usage test | NZTA B/5 | Upon emptying the spreader and bulk tanker | Withn ±2.5% of the specified rate | V
9.4.2 |  | Bituminous Agents | Flow meter display | NZTA B/5 | Continuous | Withn ±5% of the specified rate | W |  | Tonnage/m² records shall be kept, including mat results
|  |  | Microprocessors reading | NZTA B/5 | End of each run | Withn ±3.0% of the specified rate | W
|  |  | Average usage test | NZTA B/5 | Upon emptying the bulk tanker | Withn ±2.5% of the specified rate | W
9.5.1 | Time Limitations | Cement | The maximum time period from mixing to primary compaction | NZTA B/5 | Post stabilisation | 2 hours - Time start to time end to be recorded | H |  | Where time the time limit is exceeded, details of the remedial action shall be prepared for assessment, and procedures for further stabilisations sections must be agreed to avoid further occurances |  | Downer PM
9.5.2 |  | Foam Bitumen |  | NZTA B/5 |  | 4 hours - Time start to time end to be recorded | H
9.5.3 |  | Combination |  | NZTA B/5 |  | The shorter of the individual agents | H
9.6.1 | Insitu Mixing | Cut Depth | Depth measurement | NZTA B/5 | At start & end of cut and every 200m | -5mm +15mm of design depth | W |  |  |  | Highways Site Foreman
9.6.2 |  | Join Overlap | Inspection | NZTA B/5 | Continuous | 100mm overlap | W |  | All cuts shall overlap by the minimum acceptance criteria
9.6.3 |  | Particle Breakdown | Inspection | NZTA B/5 | Within the first 20m of each run, and where ever material changes | Well mixed material with acceptable particle size distribution | W |  | Where breakdown is excessive, method of milling should be altered to avoid such breakdown
9.6.4 |  | FBS Quality | Inspection | Visual Inspection | Continuous while stabilisation is progressing | No bitumen stringers or blobs observed (See Assessment of hoe'd materials) | W |  | If bitumen blobs or stringers are found the the construction of FBS stops and the equipement is fixed so that there are no bitumen blobs or stringers found
10 | Construction Quality Assurance (QA)
10.1 | Field Compaction Target |  | NDM - Plateau | NZTA B/5 | 1 Every 3000m2 or once daily | Plateau testing done each shift / as required depending on the material variability throughout the site to determine compaction pattern. | V |  | Avg 98% plateau with min 95%. Plateau testing to be completed to determine Field Compaction Target |  | Highways Site Foreman |  | Verified test results of plateau to be supplied
10.2 | Lab testing |  | ITS/ UCS test | NZTA B/5 | 1 Every 3000m2 or once daily | Testing to be completed each shift / as required depending on the material variability throughout the site to verify compaction. | V |  | Tests to be cured & achieve as per specification. |  | Highways Site Foreman / Renewals PM
10.3 | Compaction Testing |  | NDM | NZTA T23: 2021 Direct Transmission | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | Average ≥ 98% Plateau Minimum ≥ 95% Plateau | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Plateau) Compaction equipment shall be sufficent to achieve 98% MDD |  | Highways Site Foreman / Renewals Engineer |  | Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
H
10.4 | Surface Set Up / Clegg Hammer |  | Clegg Hammer | Certified Clegg hammer (Current Certification sticker) & calibrated prior to use | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | CIV ≥ 40 | V |  | Hold point - membrane / chipseal placed once CIV ≥ 40 |  | Construction Supervisor/ Renewals Engineer |  | All test results to be submitted to NZTA for review and verification
H
10.5 | Degree of Saturation (DOS) |  | DOS | NZS 4407 Test 4.2.2 NZTA B/5 Cl. 7.12 | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | For information only | V |  | Soild density to be measured. |  | Downer Lab technician
10.6 | NDM moisture correction |  | NDM & Lab MC |  | 3x Moisture contents per single plateau test carried out | Information only | V |  | Correction offset to be applied per site |  | Highways Site Foreman / Renewals Engineer - Relates to field plateau testing by the laboratory
10.7 | Surface Shape / Profile Layer Thickness |  | NZTA B/5 | Visual inspection Cut/fill tolerance check String records Straight edge | 1 test per 20m | ≤10mm variance from 3m straight edge | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved. Hiways Retain the right to override Machine Control requirement when required. Documentation and Record to supplement reasoning and affected area |  | Highways Site Foreman/ Renewals PM/ Downer surveyor |  | Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
Gradual deviations
Crossfall > 1%
[6 empty] | Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design | H
-5mm +15mm or ±5mm at lip of concrete channel where applicable
10.8.1 | Tolerances | Width Unconstrained | TNZ B/2 | Confirm offset from lift pegs | 2 at every lift peg or per 180 m2 | - 20mm + 100mm | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved |  | Highways Site Foreman / Renewals PM |  | 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
H
10.8.2 |  | Width Constrained | TNZ B/2 | Stringline/lift pegs | 3 at every lift peg or per 180 m2 | Zero | V
H
10.9 | Ride Quality |  | Owner acceptance test | As per Contract Documents OPM42 | 1 ride test for each lane following Basecourse completion prior to surfacing | Rolling 100m average NAASRA <75 counts/km | W |  | Hold Point – no surfacing layer is to be applied until acceptance of ride quality, No exceptions |  | Road Science/ Downer PM |  | NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
H
10.10 | Mosaic Surface |  | Visual inspection | A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ | Overview of site for tight mosaic surface | The large aggregate is held in place by a matrix of smaller aggregates The smaller aggregate is held firmly in place by fine material The matrix does not displace under normal trafficking or sweeping | W |  | Hold Point – no surfacing layer is to be applied until passing results are achieved |  | NZTA Network Manager / Renewals Manager/ Highways Site Foreman / Downer PM / Downer Sealing Foreman
H
10.11 | Preseal Check |  | Visual check | NZTA B/5 | Before sealing | All prior ITP checks have been completed and signed off | V |  | Hold Point – no surfacing layer is to be applied until all results are verified & approved as per ITP
[6 empty] | No caking layers present | H
10.12 | Pavement Surface As-Built |  | Survey | As per approved drawings | Per installation / Site | Accurate survey of all topograpgical features required | V |  |  |  | Downer Approved Surveyor
11 | Sealing
11.1 | Seal Extent |  | Inspection | Mark offsets from Lift pegs | Before sealing | Full site extent marked | V |  | All extents to be marked, start, end, width and driveways to boundary. |  | Downer PM / Downer Sealing Foreman
11.2 | Sealing |  | See Sealing ITP |  |  |  | W |  | Hold Point – All hold points and checks in ITP to be completed before physical works continue |  | Downer Sealing Contract Manager
11.3 | Sealing TMP and Aftercare Process |  | See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site |  |  |  | W |  | Hold Point – 24 hour trafficking and aftercare of sealing works are described and confirmed in TMP for sealing works before physical sealing works proceed. |  | Downer Sealing Supervisor
H
11.4 | Sweeping of Sealing Works and Handover to Roadmarkers |  | Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor. |  |  |  | W |  | Hold Point – All sweeping activities, roadmarking and install of RPM's to be completed before handover of site from surfacing to construction supervisor. |  | Downer Sealing Supervisor
H
12 | Shoulders
12.1 | Slope |  | Visual check | Visual inspection with smart level |  | Slopes consistent & to 5:1 grade. Excessive shoulder construction to be carried out ahead of pavement operation | V |  | Hold Point – no surfacing layer is to be applied until all necessary results are achieved |  | Construction Supervisor/ NZTA |  | Invite NZTA to carry out joint site inspection to inspect site.
H
12.2 | Compaction |  | Visual check | Drive over 4 tonne, check wheeltracks | All shoulders | Vehicles can drive on shoulders without becoming stuck | V |  | Hold Point – physical works cannot be completed until all necessary results are achieved |  | Construction Supervisor/ NZTA
H
12.3 | Soiling |  | Visual check | Approved Design Drawings | All areas requiring grassing | Soiling has been done where required | W |  | As per the design drawings |  | Construction Supervisor
13 | Site Reinstatement / Clearance
13.1 | Traffic Services | Marker Pegs/ Signs/Markings/RRPMs Replaced | TNZ C/20: 2003 | Visual Inspection | All signs/markers | Replaced in same position, height etc | V |  | Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced |  | Construction Supervisor/ NZTA |  | Invite NZTA to carry out joint site inspection to inspect site.
H
13.2 | Grassing |  | Visual check |  | All areas requiring grassing | Grassing has been done where required | W |  |  |  | Construction Supervisor
13.3 | Drains Cleared |  | Visual check |  | All drains, after all other works | Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated | W |  |  |  | Construction Supervisor
13.4 | Traffic Management Removed |  | Visual check |  | When safe, after all physical works completed | All traffic management removed from site safely | W |  | Hold Point – TMP cannot be removed until site Audited by Downer Construction Supervisor |  | Construction Supervisor
13.5 | Site Left Clean and Tidy |  | Visual check |  | After vacating site | · Stockpiles removed | V |  |  |  | Construction Supervisor/ NZTA |  | Invite NZTA to carry out joint site inspection to inspect site.
· Plant removed
· Litter cleared from site
14 | As-built Records
14.1 | Collect Asset Data |  | SHDOM (SM050) |  | During construction | All relevant as built information collected | V |  |  |  | Renewals Engineer
14.2 | Enter Asset Data into RAMM and/or Register(s) |  | SHDOM (SM050) | RAMM | At completion of work | All data entered into RAMM and/or register(s). Design report & drawings attached to RAMM site record as a media file. | H |  | Hold Point – project cannot be closed until data entered. |  | Renewals Engineer/ WSP Information Manager |  | Submit all RAMM Data to Data Quality Manager for review and verification
14.3 | Construction Completion Report |  | Confirmation | Contract Specification | At completion of work | Checked and approved | V |  |  |  | Renewals Engineer/ Renewals Manager |  | Submit Pavement Design Report, Construction Compliance, QMP, Site test results / inspections / activity records, Lessons Learnt, As-built Plans
| Quality Assurance Close Out By: | _________________________________________ |  |  | Date: ___________________ |  | _________________________________________________________
(signature)
_________________________________________________________
(name)
THIS RECORD TO CONTRACT FILE
Note on C37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Might pay to add a requird yes/no feild here to make it clear. Same for subsoils, dont want someone reviewing this to thik we didnt do it

## 0.5 FBS - Hallets
|  | Central Waikato NOC - Inspection & Test Plan - Catalogue Foam Stabilisation | [6 empty] | Document Number: | Pavement Renewals - Foam Stabilisation
|  | Site Name: | Hallets Bay | [5 empty] | Revision Number: | 0.9B | Number of Pages: |  | 10
|  | Location: | SH1 01N-0726 3500 3830 | [5 empty] | Prepared: | M Owens | Date: |  | 2022-10-17
[9 empty] | Approved: | G Apiti | Date: |  | 2022-10-04
ITEM NUMBER | ACTIVITY DESCRIPTION |  | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | INSPECTORATE V/W/H |  |  |  | RESPONSIBLE PERSON | Sign & date if appropriate | RECORDS / REMARKS
[7 empty] | V=VERIFICATION, W=WITNESS, H =HOLD |  |  |  | As per Quality Plan
[7 empty] | Type | Assessor signature | Description |  |  |  | incl NCR ref
1 | Preliminary and General
1.1 | Construction Programme Completion |  | Confirmation | Best Practice Contract Specific MMP | Before work commences | Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date | V |  |  |  | Renewals Manager
1.2 | Approved RQP |  | Confirmation | Contract Specification | At least 24hrs before establishment or work commences | Principal's Acceptance according to guidelines in Appendix 6.3 | H |  | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours before establishing on site. |  | Renewals Manager |  | NZTA to approve.
1.3 | Notification of Intention to Start Work |  | Notification |  | Before work commences | Letter drop to local residents | H |  | Hold point - No physical work is to be commenced on site until notification has been sent to residents - no later than 24 hours prior to establishing on site. |  | Construction Supervisor / Renewals Engineer |  | NZTA to approve letter drop before distribution to residents.
1.4 | Traffic Management | TMP | Visual check | CoPTTM | Before work commences | TMP checked and approved Plans approved Current EED (if applicable) Size of site area to be checked to allow machinery to operate safely | H |  | Hold point - No traffic management is to be set up until TMP has been checked and approved |  | STMS |  | CAR No.
TMP No.
1.5 | Design Report Approval |  | Confirmation | NZTA NOC Rehab Catalogue Design & Treatment Approach | Before work commences | Principal Acceptance's acceptance according to NZTA Catalogue Design Approach document | H |  | Hold point - Review meeting with NZTA National & Regional Leads and Downer NOC Managers & Pavement Designers/Reviewers |  | NZTA Network Manager & Accreditied Designer |  | NZTA Approval to Proceed NTC No.
1.6 | Seal Design Approval |  | Confirmation | Review and Sign off by Downer Regional Sealing Manager | Before work commences | Downer Regional Sealing Manager reviews and signs off on Seal Design proposed. | H |  | Hold point - Review and approval of seal design completed |  | Regional Sealing Manager
1.7 | Project Manager Handover |  | Confirmation | Review and Sign off by Downer Designer to PM | Before work commences | Downer Technical Services Team Designer reviews and signs off on Handover. | H |  | Hold point - Handover completed |  | Regional Engineering Team Designer
1.8 | Crew Pack |  |  | Items to be included: | Before work commences | Approved TMP | H |  |  |  | Downer PM
Services location plans / Marked out
Approved RQP
Approved for Construction drawings & Pavement Design
Ramm data
Approved ITP
Crew Briefing Plan
2 | Setout / Site Preparation
2.1 | Setout |  | Survey | As per approved drawings | Per installation / Site | Design strings /design surface model loaded for machine control | V |  | Machine control requirement. Downer surveyor required for MC upload and verification of model operation |  | Downer Approved Surveyor
2.2 | Services (includes Traffic Count Loops and Traffic Signal Detector Loops) |  | Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth) | NZAUAG Guide to Working on the Road | Before work commences | Zero service strikes | H |  | Hold point - No excavation is to be commenced until services are located and accounted for |  | Construction Supervisor
2.3 | Cultural/Heritage Risk Assessment |  | Notification | NZTA Cultural & Heritage Risk Model | Before work commences | Local iwi has been notified of intent to start work | H |  | Where risk of cultural discovery |  | Renewals Engineer / Manager
2.4 | Archaeological Risk |  | Toolbox meeting | NZTA Cultural & Heritage Risk Model | Before work commences | Toolbox meeting held covering accidental discovery protocol | H |  | Hold point - No excavation is to be commenced until toolbox meeting is held |  | Construction Supervisor
2.5 | Traffic Management | Signs Setup | Visual check | Traffic Management Plan | Before work commences each day | Traffic management complies with TMP | H |  | Hold point - No physical works are to be commenced until necessary traffic management is in place |  | STMS |  | Daily site record sheet
2.6 | Pre-Construction walkover |  | Visual check | Approved Crew pack on site 2 weeks prior to work comencing | Before work commences | Principal / Highways / Downer Acceptance | H |  | Hold point - Walkover required ahead of Highways establishment |  | Renewals Manager / Highways PM / MCM |  | Invite for NZTA to carry out joint site visit to complete visual inspection
Hold point - No physical works are to be commenced until walkover completed
3 | Preliminary Works
3.1 | Shoulder Stripping / Vegetation clearing |  | Visual check | On site |  | Shoulder stripping as per drawings completed | V |  |  |  | Construction Supervisor / NZTA |  | Invite for NZTA to carry out joint site visit to complete visual inspection
3.2 | Site pavement A/C digouts |  | Visual check | Check RAMM records for depths | Before Stabilisation work commences | Work completed prior to stablisation contractor onsite | V |  | A/C Mill & Fills to be cut to waste & replaced with M/4 AP40 compacted & sealed |  | Site Foreman
4 | Culvert extensions / Headwalls / Flumes
4.1 | Excavation Inlet / Outlet Gradients |  | Survey | NZTA F/3 | Once | Consistent gradient in and out | H |  | Hold Point – Visual check prior to pipe placement |  | Site foreman |  | Required Yes / No
4.2 | Pipe materials / class |  | Visual Check | NZTA F/3 2.1 | Once | Meets appropriate AS/NZ standard reletive to specified type | V |  |  |  | Site foreman |  | Required Yes / No
4.3 | Bedding contact |  | Visual Check | NZTA F/3 5.1 | continuous | uniform contact over full length of pipe | V |  |  |  | Site foreman |  | Required Yes / No
5 | Subsoil drainage
5.1 | Trench |  | Visual |  | each site | Depth minimum 1.0m Width minimum 300mm, fall > 1:100, free from rocks etc. Position as per the design drawings +/- 100mm | H |  | Hold Point – Visual check prior to pipe placement |  | Site foreman |  | Required Yes / No
5.2 | Drainage material |  | Visual |  | each site | 7-12mm clean filter material ( grade 2 - 4 Sealing chip | H |  | Hold Point – Visual check prior to pipe placement |  | Site foreman |  | Required Yes / No
5.3 | Pipe type |  | Visual | Diameter as per the design drawings | Use outside traffic Lane | Docket to confirm | V |  | "Nova flow" |  | Site foreman |  | Required Yes / No
|  |  | Visual |  | Under traffic lane | Docket to confirm | V |  | Nexus |  | Site foreman |  | Required Yes / No
5.4 | Filter Fabric |  | Visual |  |  | 150mm lap, top of fabric minimum 150mm below FSL | H |  | Hold Point – Visual check prior to reinstatement |  | Site foreman |  | Required Yes / No
5.5 | Outlet |  | Visual |  |  | Connect to sump barrel, culvert of construct Concrete Apron | H |  | Hold Point – Visual check prior to reinstatement |  | Site foreman |  | Required Yes / No
5.6 | Flushing / Cleaning eyes |  | Visual | To be placed & constructed as per Approved Drawings | Each free end | [7 empty] | Required Yes / No
5.7 | Reinstatement |  | Sealed Pavement |  |  | Pavement matches surrounding, surface with AC or 3/5 chip | V |  |  |  | Site foreman |  | Required Yes / No
|  |  | Berms and shoulder |  |  | Top min 150mm impermiable backfill | V |  |  |  | Site foreman |  | Required Yes / No
6 | Preteatment of Insitu Materials
6.1.1 | Pretreatment Stabilising Agent (where applicable) | Quick / Hydrated Lime or KOBM | Mat Test 1m² canvas | Pavement design report | Every 400m² | Within ±0.5kg/m² of the specified rate | V |  | Tonnage/m² records shall be kept, including mat results |  | Highways Site Foreman |  | Daily Job Record
6.1.2 |  |  | Average usage test | Pavement design report | Upon emptying the spreader and bulk tanker | Withn ±2.5% of the specified rate | V
6.2 | Stabilising Depth | Hoe Depth | Depth measurement | Design drawings | At both ends & sides of cut and every 200m | -5mm +15mm of design depth | W |  |  |  | Highways Site Foreman |  | Daily Job Record
6.3.1 | Pre-Hoe |  | Visual Inspection |  | Each Subsection | No unsuitable material found to be sampled | H |  | Hold point - Hoed material to be checked to ensure consistencey and no unsuitable material found, Sample to be taken for future testing if required |  | Renewals Manager / Highways Site Foreman
6.3.2 | Visual Inspection post Hoe | Proof Roll and Joint Inspection | Visual Inspection | 6x4 truck fully loaded or similar equivalent | Each Subsection | No significant movement of the pavement under proof rolling and/or trafficing, for subgrade contamination | V |  | Testing to be carried out imediately after compaction |  | Highways Site Foreman / Downer PM
6.3.3 |  | Material FBS Suitability | Visual Inspection | Particle size to be 50mm or less | Each Subsection, as required | No large slabs of existing wearing course or strongly bound base | V
6.3.4 | Undercut unsuitable areas |  | Visual Inspection/ measurements | Depth to be determined on site from investigations as per fig 15 Undercut & Reconstruct table | Where required | All unsuitable material removed. Excavated hole to be backfilled with M/4 AP40 & compacted to | H |  |  |  | Renewals Manager
6.3.5 | Shape & Compact Hoed layer |  | Check for 75mm overlay | Shape to correct as per the existing surface | Every 20m | Max 200mm layer depth to achieve compaction & trimmed to match existing shape and trafficable |  |  | Verified min 75mm overlay depth with no removal of pre hoed material in the traffic lane |  | Highways Site Foreman / Downer PM /Downer Surveyor |  | Joint inspection
7 | Imported Basecourse Materials Testing
7.1.1 | Imported Basecourse Materials Source Property Testing | Crushing Resistance | NZTA M/4 Crushing Resistance (CR130) Test | NZS 4407 Test 3.10 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve | V |  | Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old |  | Renewals PM |  | All source aggregate test results to be submitted to NZTA for review and verification
|  |  |  | NZTA M/4 |  |  | H
7.1.2 |  | Weathering Quality | Weathering Quality Index (WQI) Test | NZS 4407 Test 3.11 |  | Must have quality index of AA, AB, AC, BA, BB or CA | V
H
NZTA M/4
7.1.3 |  | Bearing Strength | Californian Bearing Ratio (CBR) | NZS 4407 T3.15 NZS 4402 T4.1.3 |  | Soaked CBR ≥ 80% when compacted/tested in accordance with both tests | V
|  |  |  | NZTA M/4 |  |  | H
7.2 | Imported Basecourse Materials Production Property Testing |  | Comply with project specification, PSD, Broken Faces, Quality of Fines (QoF) | Refer project specification and NZTA M/4 | 1 - 400m3 – 2 tests 400 - 1500m3 - 3 tests 1500 - 4000m3 – 4 tests >4000m3 – 1 test per 1000m3 | Refer project specification | V |  | Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old |  | Renewals PM |  | All production aggregate test results to be submitted to NZTA for review and verification
H
7.3 | Nominal 75mm Make-up Metal |  | Quantity of material used | 75mm depth over high spots | Each Subsection | Correct amount of material used (M³Solid) as per geometric design / MC | V |  | Spot checks to be taken |  | Downer surveyor
8 | Foamed Bitumen Stabilisation
8.1.1 | Stabilisation Agents | Foam Bitumen | Laboratory testing | NZTA B/5 NZTA M/1 (B/7) | Per batch | 80/100 or 180/200 Pen Grade Minimum expansion of 10 times original volume, & half-life of at least 6 seconds | V |  | Hold Point -No Bitumen shall be used on site with out a pass result as per Lab test results |  | Renewals Engineer |  | All stabilisation material and laboratory testing results to be submitted to NZTA for review and verification.
H
8.1.2 |  | Cement | See NZS 3122 | NZS 3122 NZTA B/5 Cl. 4.1.2 | Per batch | Cement must comply with NZS 3122 | V |  | Hold Point - No cement shall be spread on site with out a pass result, obtainable from supplier (this is to be done once for contract)
H
8.1.3 |  | Delivery | Visual Inspection | NZTA B/2 | Upon delivery | Stabilising agents to be delivered in tanks or trucks with Certificate of Loading | W |  | Certificate of loading to be checked on site |  | Highways Site Foreman
8.1.4 |  | Bitumen Storage | 80/100 Pen Grade | NZTA B/5 | 2 hours before use | Max storage temp: not exceed 125°C for > 24 hours & 175°C for < 24 hours Application temp: min 175°C - max 190°C | H |  | Any bitumen that has been heated above the maximum shall be removed from site
|  |  | 180/200 Pen Grade | NZTA B/5 | 2 hours before use | Max storage temp: not exceed 120°C for > 24 hours & 170°C for < 24 hours Application temp: min 170°C - max 185°C | H
8.2 | Water |  | Obtained from a suitable source | NZTA B/5(B7) Portable PH testing | Ongoing | Water for stabilisation, construction and curing is tested for correct PH for each site | W |  | Certification required for each site (PH 5.5 -7.0) |  | Downer PM
8.3.1 | Weather Limitations | Temperature | Measure Temperature | NZTA B/5 | Daily | Stabilised material before compaction 20°C | W |  | Work shall not be started if temperature is below the respective minimums. |  | Highways Site Foreman / Downer PM |  | Joint Inspection
8.3.2 |  | Wind | Assessment | NZTA B/5 | Daily (SEE remarks) | Maximum windspeed of 25km/hr checked from metservice website | W |  | Work shall not be started if windspeed exceeds the maximum |  |  |  | Not applicable if direct injection used
6.3.3 |  | Rain | Check forecast | NZTA B/5 | Daily | Spreading has not commenced during rainfall. Spreading has not commenced if rainfall is due prior to completion of mixing. | W |  | No spreading of binding agents shall commence if it is raining. If rain is likely to start before the binding agent(s) can be mixed into the aggregate, then spreading of the binding agent(s) shall not take place.
8.4.1 | Spreading | Cement | Mat Test 1m² canvas | NZTA B/5 | Every 400m² | Within ±0.5km/m² of the specified rate | V |  | Tonnage/m² records shall be kept, including mat results |  | Highways Site Foreman |  | Not applicable if direct injection used
|  |  | Average usage test | NZTA B/5 | Upon emptying the spreader and bulk tanker | Withn ±2.5% of the specified rate | V
8.4.2 |  | Bituminous Agents | Flow meter display | NZTA B/5 | Continuous | Withn ±5% of the specified rate | W |  | Tonnage/m² records shall be kept, including mat results
|  |  | Microprocessors reading | NZTA B/5 | End of each run | Withn ±3.0% of the specified rate | W
|  |  | Average usage test | NZTA B/5 | Upon emptying the bulk tanker | Withn ±2.5% of the specified rate | W
8.5.1 | Time Limitations | Cement | The maximum time period from mixing to primary compaction | NZTA B/5 | Post stabilisation | 2 hours - Time start to time end to be recorded | H |  | Where time the time limit is exceeded, details of the remedial action shall be prepared for assessment, and procedures for further stabilisations sections must be agreed to avoid further occurances |  | Downer PM
8.5.2 |  | Foam Bitumen |  | NZTA B/5 |  | 4 hours - Time start to time end to be recorded | H
8.5.3 |  | Combination |  | NZTA B/5 |  | The shorter of the individual agents | H
8.6.1 | Insitu Mixing | Cut Depth | Depth measurement | NZTA B/5 | At start & end of cut and every 200m | -5mm +15mm of design depth | W |  |  |  | Highways Site Foreman
8.6.2 |  | Join Overlap | Inspection | NZTA B/5 | Continuous | 100mm overlap | W |  | All cuts shall overlap by the minimum acceptance criteria
8.6.3 |  | Particle Breakdown | Inspection | NZTA B/5 | Within the first 20m of each run, and where ever material changes | Well mixed material with acceptable particle size distribution | W |  | Where breakdown is excessive, method of milling should be altered to avoid such breakdown
8.6.4 |  | FBS Quality | Inspection | Visual Inspection | Continuous while stabilisation is progressing | No bitumen stringers or blobs observed (See Assessment of hoe'd materials) | W |  | If bitumen blobs or stringers are found the the construction of FBS stops and the equipement is fixed so that there are no bitumen blobs or stringers found
9 | Construction Quality Assurance (QA)
9.1 | Field Compaction Target |  | NDM - Plateau | NZTA B/5 | 1 Every 3000m2 or once daily | Plateau testing done each shift / as required depending on the material variability throughout the site to determine compaction pattern. | V |  | Avg 98% plateau with min 95%. Plateau testing to be completed to determine Field Compaction Target |  | Highways Site Foreman |  | Verified test results of plateau to be supplied
9.2 | Lab testing |  | ITS/ UCS test | NZTA B/5 | 1 Every 3000m2 or once daily | Testing to be completed each shift / as required depending on the material variability throughout the site to verify compaction. | V |  | Tests to be cured & achieve as per specification. |  | Highways Site Foreman / Renewals PM
9.3 | Compaction Testing |  | NDM | NZTA T23: 2021 Direct Transmission | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | Average ≥ 98% Plateau Minimum ≥ 95% Plateau | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Plateau) Compaction equipment shall be sufficent to achieve 98% MDD |  | Highways Site Foreman / Renewals Engineer |  | Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
H
9.4 | Surface Set Up / Clegg Hammer |  | Clegg Hammer | Certified Clegg hammer (Current Certification sticker) & calibrated prior to use | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | CIV ≥ 40 | V |  | Hold point - membrane / chipseal placed once CIV ≥ 40 |  | Construction Supervisor/ Renewals Engineer |  | All test results to be submitted to NZTA for review and verification
H
9.5 | Degree of Saturation (DOS) |  | DOS | NZS 4407 Test 4.2.2 NZTA B/5 Cl. 7.12 | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | For information only | V |  | Soild density to be measured. |  | Downer Lab technician
9.6 | NDM moisture correction |  | NDM & Lab MC |  | 3x Moisture contents per single plateau test carried out | Information only | V |  | Correction offset to be applied per site |  | Highways Site Foreman / Renewals Engineer - Relates to field plateau testing by the laboratory
9.7 | Surface Shape / Profile Layer Thickness |  | NZTA B/5 | Visual inspection Cut/fill tolerance check String records Straight edge | 1 test per 20m | ≤10mm variance from 3m straight edge | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved. Hiways Retain the right to override Machine Control requirement when required. Documentation and Record to supplement reasoning and affected area |  | Highways Site Foreman/ Renewals PM/ Downer surveyor |  | Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
Gradual deviations
Crossfall > 1%
[6 empty] | Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design | H
-5mm +15mm or ±5mm at lip of concrete channel where applicable
9.8.1 | Tolerances | Width Unconstrained | TNZ B/2 | Confirm offset from lift pegs | 2 at every lift peg or per 180 m2 | - 20mm + 100mm | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved |  | Highways Site Foreman / Renewals PM |  | 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
H
9.8.2 |  | Width Constrained | TNZ B/2 | Stringline/lift pegs | 3 at every lift peg or per 180 m2 | Zero | V
H
9.9 | Ride Quality |  | Owner acceptance test | As per Contract Documents OPM42 | 1 ride test for each lane following Basecourse completion prior to surfacing | Rolling 100m average NAASRA <75 counts/km | W |  | Hold Point – no surfacing layer is to be applied until acceptance of ride quality, No exceptions |  | Road Science/ Downer PM |  | NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
H
9.10 | Mosaic Surface |  | Visual inspection | A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ | Overview of site for tight mosaic surface | The large aggregate is held in place by a matrix of smaller aggregates The smaller aggregate is held firmly in place by fine material The matrix does not displace under normal trafficking or sweeping | W |  | Hold Point – no surfacing layer is to be applied until passing results are achieved |  | NZTA Network Manager / Renewals Manager/ Highways Site Foreman / Downer PM / Downer Sealing Foreman
H
9.11 | Preseal Check |  | Visual check | NZTA B/5 | Before sealing | All prior ITP checks have been completed and signed off | V |  | Hold Point – no surfacing layer is to be applied until all results are verified & approved as per ITP
[6 empty] | No caking layers present | H
9.12 | Pavement Surface As-Built |  | Survey | As per approved drawings | Per installation / Site | Accurate survey of all topograpgical features required | V |  |  |  | Downer Approved Surveyor
10 | Sealing
10.1 | Sealing |  | See Sealing ITP |  |  |  | W |  | Hold Point – All hold points and checks in ITP to be completed before physical works continue |  | Downer Sealing Contract Manager
10.2 | Sealing TMP and Aftercare Process |  | See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site |  |  |  | W |  | Hold Point – 24 hour trafficking and aftercare of sealing works are described and confirmed in TMP for sealing works before physical sealing works proceed. |  | Downer Sealing Supervisor
H
10.3 | Sweeping of Sealing Works and Handover to Roadmarkers |  | Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor. |  |  |  | W |  | Hold Point – All sweeping activities, roadmarking and install of RPM's to be completed before handover of site from surfacing to construction supervisor. |  | Downer Sealing Supervisor
H
11 | Shoulders
11.1 | Slope |  | Visual check | Visual inspection with smart level |  | Slopes consistent & to 5:1 grade. Excessive shoulder construction to be carried out ahead of pavement operation | V |  | Hold Point – no surfacing layer is to be applied until all necessary results are achieved |  | Construction Supervisor/ NZTA |  | Invite NZTA to carry out joint site inspection to inspect site.
H
11.2 | Compaction |  | Visual check | Drive over 4 tonne, check wheeltracks | All shoulders | Vehicles can drive on shoulders without becoming stuck | V |  | Hold Point – physical works cannot be completed until all necessary results are achieved |  | Construction Supervisor/ NZTA
H
11.3 | Soiling |  | Visual check | Approved Design Drawings | All areas requiring grassing | Soiling has been done where required | W |  | As per the design drawings |  | Construction Supervisor
12 | Site Reinstatement / Clearance
12.1 | Traffic Services | Marker Pegs/ Signs/Markings/RRPMs Replaced | TNZ C/20: 2003 | Visual Inspection | All signs/markers | Replaced in same position, height etc | V |  | Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced |  | Construction Supervisor/ NZTA |  | Invite NZTA to carry out joint site inspection to inspect site.
H
12.2 | Grassing |  | Visual check |  | All areas requiring grassing | Grassing has been done where required | W |  |  |  | Construction Supervisor
12.3 | Drains Cleared |  | Visual check |  | All drains, after all other works | Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated | W |  |  |  | Construction Supervisor
12.4 | Traffic Management Removed |  | Visual check |  | When safe, after all physical works completed | All traffic management removed from site safely | W |  | Hold Point – TMP cannot be removed until site Audited by Downer Construction Supervisor |  | Construction Supervisor
12.5 | Site Left Clean and Tidy |  | Visual check |  | After vacating site | · Stockpiles removed | V |  |  |  | Construction Supervisor/ NZTA |  | Invite NZTA to carry out joint site inspection to inspect site.
· Plant removed
· Litter cleared from site
13 | As-built Records
13.1 | Collect Asset Data |  | SHDOM (SM050) |  | During construction | All relevant as built information collected | V |  |  |  | Renewals Engineer
13.2 | Enter Asset Data into RAMM and/or Register(s) |  | SHDOM (SM050) | RAMM | At completion of work | All data entered into RAMM and/or register(s). Design report & drawings attached to RAMM site record as a media file. | H |  | Hold Point – project cannot be closed until data entered. |  | Renewals Engineer/ WSP Information Manager |  | Submit all RAMM Data to Data Quality Manager for review and verification
13.3 | Construction Completion Report |  | Confirmation | Contract Specification | At completion of work | Checked and approved | V |  |  |  | Renewals Engineer/ Renewals Manager |  | Submit Pavement Design Report, Construction Compliance, QMP, Site test results / inspections / activity records, Lessons Learnt, As-built Plans
| Quality Assurance Close Out By: | _________________________________________ |  |  | Date: ___________________ |  | _________________________________________________________
(signature)
_________________________________________________________
(name)
THIS RECORD TO CONTRACT FILE
Note on C37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Might pay to add a requird yes/no feild here to make it clear. Same for subsoils, dont want someone reviewing this to thik we didnt do it

## 0.5 FBS - Rangipo
|  | Central Waikato NOC - Inspection & Test Plan - Catalogue Foam Stabilisation | [6 empty] | Document Number: | Pavement Renewals - Foam Stabilisation
|  | Site Name: | Rangipo South | [5 empty] | Revision Number: | 0.9B | Number of Pages: |  | 10
|  | Location: | SH1 01N-0763 2074 - 2369 | [5 empty] | Prepared: | M Owens | Date: |  | 2022-10-17
[9 empty] | Approved: | G Apiti | Date: |  | 2022-10-04
ITEM NUMBER | ACTIVITY DESCRIPTION |  | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY | ACCEPTANCE CRITERIA | INSPECTORATE V/W/H |  |  |  | RESPONSIBLE PERSON | Sign & date if appropriate | RECORDS / REMARKS
[7 empty] | V=VERIFICATION, W=WITNESS, H =HOLD |  |  |  | As per Quality Plan
[7 empty] | Type | Assessor signature | Description |  |  |  | incl NCR ref
1 | Preliminary and General
1.1 | Construction Programme Completion |  | Confirmation | Best Practice Contract Specific MMP | Before work commences | Construction Completion will be the lesser of the completion date according to the pavement classificaiton risk profile (documented in the contract specific MMP) or the contract completion date | V |  |  |  | Renewals Manager
1.2 | Approved RQP |  | Confirmation | Contract Specification | At least 24hrs before establishment or work commences | Principal's Acceptance according to guidelines in Appendix 6.3 | H |  | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours before establishing on site. |  | Renewals Manager |  | NZTA to approve.
1.3 | Notification of Intention to Start Work |  | Notification |  | Before work commences | Letter drop to local residents | H |  | Hold point - No physical work is to be commenced on site until notification has been sent to residents - no later than 24 hours prior to establishing on site. |  | Construction Supervisor / Renewals Engineer |  | NZTA to approve letter drop before distribution to residents.
1.4 | Traffic Management | TMP | Visual check | CoPTTM | Before work commences | TMP checked and approved Plans approved Current EED (if applicable) Size of site area to be checked to allow machinery to operate safely | H |  | Hold point - No traffic management is to be set up until TMP has been checked and approved |  | STMS |  | CAR No.
TMP No.
1.5 | Design Report Approval |  | Confirmation | NZTA NOC Rehab Catalogue Design & Treatment Approach | Before work commences | Principal Acceptance's acceptance according to NZTA Catalogue Design Approach document | H |  | Hold point - Review meeting with NZTA National & Regional Leads and Downer NOC Managers & Pavement Designers/Reviewers |  | NZTA Network Manager & Accreditied Designer |  | NZTA Approval to Proceed NTC No.
1.6 | Seal Design Approval |  | Confirmation | Review and Sign off by Downer Regional Sealing Manager | Before work commences | Downer Regional Sealing Manager reviews and signs off on Seal Design proposed. | H |  | Hold point - Review and approval of seal design completed |  | Regional Sealing Manager
1.7 | Project Manager Handover |  | Confirmation | Review and Sign off by Downer Designer to PM | Before work commences | Downer Technical Services Team Designer reviews and signs off on Handover. | H |  | Hold point - Handover completed |  | Regional Engineering Team Designer
1.8 | Crew Pack |  |  | Items to be included: | Before work commences | Approved TMP | H |  |  |  | Downer PM
Services location plans / Marked out
Approved RQP
Approved for Construction drawings & Pavement Design
Ramm data
Approved ITP
Crew Briefing Plan
2 | Setout / Site Preparation
2.1 | Setout |  | Survey | As per approved drawings | Per installation / Site | Design strings /design surface model loaded for machine control | V |  | Machine control requirement. Downer surveyor required for MC upload and verification of model operation |  | Downer Approved Surveyor
2.2 | Services (includes Traffic Count Loops and Traffic Signal Detector Loops) |  | Visual plan BeforeUDig Cable locate (electronic or pothole for line & depth) | NZAUAG Guide to Working on the Road | Before work commences | Zero service strikes | H |  | Hold point - No excavation is to be commenced until services are located and accounted for |  | Construction Supervisor
2.3 | Cultural/Heritage Risk Assessment |  | Notification | NZTA Cultural & Heritage Risk Model | Before work commences | Local iwi has been notified of intent to start work | H |  | Where risk of cultural discovery |  | Renewals Engineer / Manager
2.4 | Archaeological Risk |  | Toolbox meeting | NZTA Cultural & Heritage Risk Model | Before work commences | Toolbox meeting held covering accidental discovery protocol | H |  | Hold point - No excavation is to be commenced until toolbox meeting is held |  | Construction Supervisor
2.5 | Traffic Management | Signs Setup | Visual check | Traffic Management Plan | Before work commences each day | Traffic management complies with TMP | H |  | Hold point - No physical works are to be commenced until necessary traffic management is in place |  | STMS |  | Daily site record sheet
2.6 | Pre-Construction walkover |  | Visual check | Approved Crew pack on site 2 weeks prior to work comencing | Before work commences | Principal / Highways / Downer Acceptance | H |  | Hold point - Walkover required ahead of Highways establishment |  | Renewals Manager / Hiways PM / MCM |  | Invite for NZTA to carry out joint site visit to complete visual inspection
Hold point - No physical works are to be commenced until walkover completed
3 | Preliminary Works
3.1 | Shoulder Stripping / Vegetation clearing |  | Visual check | On site |  | Shoulder stripping as per drawings completed | V |  |  |  | Construction Supervisor / NZTA |  | Invite for NZTA to carry out joint site visit to complete visual inspection
3.2 | Site pavement A/C digouts |  | Visual check | Check RAMM records for depths | Before Stabilisation work commences | Work completed prior to stablisation contractor onsite | V |  | A/C Mill & Fills to be cut to waste & replaced with M/4 AP40 compacted & sealed |  | Site Foreman
4 | Culvert extensions / Headwalls / Flumes
4.1 | Excavation Inlet / Outlet Gradients |  | Survey | NZTA F/3 | Once | Consistent gradient in and out | H |  | Hold Point – Visual check prior to pipe placement |  | Site foreman |  | Required Yes / No
4.2 | Pipe materials / class |  | Visual Check | NZTA F/3 2.1 | Once | Meets appropriate AS/NZ standard reletive to specified type | V |  |  |  | Site foreman |  | Required Yes / No
4.3 | Bedding contact |  | Visual Check | NZTA F/3 5.1 | continuous | uniform contact over full length of pipe | V |  |  |  | Site foreman |  | Required Yes / No
5 | Subsoil drainage
5.1 | Trench |  | Visual |  | each site | Depth minimum 1.0m Width minimum 300mm, fall > 1:100, free from rocks etc. Position as per the design drawings +/- 100mm | H |  | Hold Point – Visual check prior to pipe placement |  | Site foreman |  | Required Yes / No
5.2 | Drainage material |  | Visual |  | each site | 7-12mm clean filter material ( grade 2 - 4 Sealing chip | H |  | Hold Point – Visual check prior to pipe placement |  | Site foreman |  | Required Yes / No
5.3 | Pipe type |  | Visual | Diameter as per the design drawings | Use outside traffic Lane | Docket to confirm | V |  | "Nova flow" |  | Site foreman |  | Required Yes / No
|  |  | Visual |  | Under traffic lane | Docket to confirm | V |  | Nexus |  | Site foreman |  | Required Yes / No
5.4 | Filter Fabric |  | Visual |  |  | 150mm lap, top of fabric minimum 150mm below FSL | H |  | Hold Point – Visual check prior to reinstatement |  | Site foreman |  | Required Yes / No
5.5 | Outlet |  | Visual |  |  | Connect to sump barrel, culvert of construct Concrete Apron | H |  | Hold Point – Visual check prior to reinstatement |  | Site foreman |  | Required Yes / No
5.6 | Flushing / Cleaning eyes |  | Visual | To be placed & constructed as per Approved Drawings | Each free end | [7 empty] | Required Yes / No
5.7 | Reinstatement |  | Sealed Pavement |  |  | Pavement matches surrounding, surface with AC or 3/5 chip | V |  |  |  | Site foreman |  | Required Yes / No
|  |  | Berms and shoulder |  |  | Top min 150mm impermiable backfill | V |  |  |  | Site foreman |  | Required Yes / No
6 | Preteatment of Insitu Materials
6.1.1 | Pretreatment Stabilising Agent (where applicable) | Quick / Hydrated Lime or KOBM | Mat Test 1m² canvas | Pavement design report | Every 400m² | Within ±0.5kg/m² of the specified rate | V |  | Tonnage/m² records shall be kept, including mat results |  | Highways Site Foreman |  | Daily Job Record
6.1.2 |  |  | Average usage test | Pavement design report | Upon emptying the spreader and bulk tanker | Withn ±2.5% of the specified rate | V
6.2 | Stabilising Depth | Hoe Depth | Depth measurement | Design drawings | At both ends & sides of cut and every 200m | -5mm +15mm of design depth | W |  |  |  | Highways Site Foreman |  | Daily Job Record
6.3.1 | Pre-Hoe |  | Visual Inspection |  | Each Subsection | No unsuitable material found to be sampled | H |  | Hold point - Hoed material to be checked to ensure consistencey and no unsuitable material found, Sample to be taken for future testing if required |  | Renewals Manager / Highways Site Foreman
6.3.2 | Visual Inspection post Hoe | Proof Roll and Joint Inspection | Visual Inspection | 6x4 truck fully loaded or similar equivalent | Each Subsection | No significant movement of the pavement under proof rolling and/or trafficing, for subgrade contamination | V |  | Testing to be carried out imediately after compaction |  | Highways Site Foreman / Downer PM
6.3.3 |  | Material FBS Suitability | Visual Inspection | Particle size to be 50mm or less | Each Subsection, as required | No large slabs of existing wearing course or strongly bound base | V
6.3.4 | Undercut unsuitable areas |  | Visual Inspection/ measurements | Depth to be determined on site from investigations as per fig 15 Undercut & Reconstruct table | Where required | All unsuitable material removed. Excavated hole to be backfilled with M/4 AP40 & compacted to | H |  |  |  | Renewals Manager
6.3.5 | Shape & Compact Hoed layer |  | Check for 75mm overlay | Shape to correct as per the existing surface | Every 20m | Max 200mm layer depth to achieve compaction & trimmed to match existing shape and trafficable |  |  | Verified min 75mm overlay depth with no removal of pre hoed material in the traffic lane |  | Highways Site Foreman / Downer PM /Downer Surveyor |  | Joint inspection
7 | Imported Basecourse Materials Testing
7.1.1 | Imported Basecourse Materials Source Property Testing | Crushing Resistance | NZTA M/4 Crushing Resistance (CR130) Test | NZS 4407 Test 3.10 | 1 test per 10,000 m3 of source material per source, or when a variation occurs in the rock geology e.g. new seam of rock | Crushing resistance must reach 130 kN with less than 10% fines passing 2.36mm sieve | V |  | Hold Point – All source testing results to be provided prior to placement of material on road for a source <2 years old |  | Renewals PM |  | All source aggregate test results to be submitted to NZTA for review and verification
|  |  |  | NZTA M/4 |  |  | H
7.1.2 |  | Weathering Quality | Weathering Quality Index (WQI) Test | NZS 4407 Test 3.11 |  | Must have quality index of AA, AB, AC, BA, BB or CA | V
H
NZTA M/4
7.1.3 |  | Bearing Strength | Californian Bearing Ratio (CBR) | NZS 4407 T3.15 NZS 4402 T4.1.3 |  | Soaked CBR ≥ 80% when compacted/tested in accordance with both tests | V
|  |  |  | NZTA M/4 |  |  | H
7.2 | Imported Basecourse Materials Production Property Testing |  | Comply with project specification, PSD, Broken Faces, Quality of Fines (QoF) | Refer project specification and NZTA M/4 | 1 - 400m3 – 2 tests 400 - 1500m3 - 3 tests 1500 - 4000m3 – 4 tests >4000m3 – 1 test per 1000m3 | Refer project specification | V |  | Hold Point – All production testing results to be provided prior to placement of material on road for a source <1 years old |  | Renewals PM |  | All production aggregate test results to be submitted to NZTA for review and verification
H
7.3 | Nominal 75mm Make-up Metal |  | Quantity of material used | 75mm depth over high spots | Each Subsection | Correct amount of material used (M³Solid) as per geometric design / MC | V |  | Spot checks to be taken |  | Downer surveyor
8 | Foamed Bitumen Stabilisation
8.1.1 | Stabilisation Agents | Foam Bitumen | Laboratory testing | NZTA B/5 NZTA M/1 (B/7) | Per batch | 80/100 or 180/200 Pen Grade Minimum expansion of 10 times original volume, & half-life of at least 6 seconds | V |  | Hold Point -No Bitumen shall be used on site with out a pass result as per Lab test results |  | Renewals Engineer |  | All stabilisation material and laboratory testing results to be submitted to NZTA for review and verification.
H
8.1.2 |  | Cement | See NZS 3122 | NZS 3122 NZTA B/5 Cl. 4.1.2 | Per batch | Cement must comply with NZS 3122 | V |  | Hold Point - No cement shall be spread on site with out a pass result, obtainable from supplier (this is to be done once for contract)
H
8.1.3 |  | Delivery | Visual Inspection | NZTA B/2 | Upon delivery | Stabilising agents to be delivered in tanks or trucks with Certificate of Loading | W |  | Certificate of loading to be checked on site |  | Highways Site Foreman
8.1.4 |  | Bitumen Storage | 80/100 Pen Grade | NZTA B/5 | 2 hours before use | Max storage temp: not exceed 125°C for > 24 hours & 175°C for < 24 hours Application temp: min 175°C - max 190°C | H |  | Any bitumen that has been heated above the maximum shall be removed from site
|  |  | 180/200 Pen Grade | NZTA B/5 | 2 hours before use | Max storage temp: not exceed 120°C for > 24 hours & 170°C for < 24 hours Application temp: min 170°C - max 185°C | H
8.2 | Water |  | Obtained from a suitable source | NZTA B/5(B7) Portable PH testing | Ongoing | Water for stabilisation, construction and curing is tested for correct PH for each site | W |  | Certification required for each site (PH 5.5 -7.0) |  | Downer PM
8.3.1 | Weather Limitations | Temperature | Measure Temperature | NZTA B/5 | Daily | Stabilised material before compaction 20°C | W |  | Work shall not be started if temperature is below the respective minimums. |  | Highways Site Foreman / Downer PM |  | Joint Inspection
8.3.2 |  | Wind | Assessment | NZTA B/5 | Daily (SEE remarks) | Maximum windspeed of 25km/hr checked from metservice website | W |  | Work shall not be started if windspeed exceeds the maximum |  |  |  | Not applicable if direct injection used
6.3.3 |  | Rain | Check forecast | NZTA B/5 | Daily | Spreading has not commenced during rainfall. Spreading has not commenced if rainfall is due prior to completion of mixing. | W |  | No spreading of binding agents shall commence if it is raining. If rain is likely to start before the binding agent(s) can be mixed into the aggregate, then spreading of the binding agent(s) shall not take place.
8.4.1 | Spreading | Cement | Mat Test 1m² canvas | NZTA B/5 | Every 400m² | Within ±0.5km/m² of the specified rate | V |  | Tonnage/m² records shall be kept, including mat results |  | Highways Site Foreman |  | Not applicable if direct injection used
|  |  | Average usage test | NZTA B/5 | Upon emptying the spreader and bulk tanker | Withn ±2.5% of the specified rate | V
8.4.2 |  | Bituminous Agents | Flow meter display | NZTA B/5 | Continuous | Withn ±5% of the specified rate | W |  | Tonnage/m² records shall be kept, including mat results
|  |  | Microprocessors reading | NZTA B/5 | End of each run | Withn ±3.0% of the specified rate | W
|  |  | Average usage test | NZTA B/5 | Upon emptying the bulk tanker | Withn ±2.5% of the specified rate | W
8.5.1 | Time Limitations | Cement | The maximum time period from mixing to primary compaction | NZTA B/5 | Post stabilisation | 2 hours - Time start to time end to be recorded | H |  | Where time the time limit is exceeded, details of the remedial action shall be prepared for assessment, and procedures for further stabilisations sections must be agreed to avoid further occurances |  | Downer PM
8.5.2 |  | Foam Bitumen |  | NZTA B/5 |  | 4 hours - Time start to time end to be recorded | H
8.5.3 |  | Combination |  | NZTA B/5 |  | The shorter of the individual agents | H
8.6.1 | Insitu Mixing | Cut Depth | Depth measurement | NZTA B/5 | At start & end of cut and every 200m | -5mm +15mm of design depth | W |  |  |  | Highways Site Foreman
8.6.2 |  | Join Overlap | Inspection | NZTA B/5 | Continuous | 100mm overlap | W |  | All cuts shall overlap by the minimum acceptance criteria
8.6.3 |  | Particle Breakdown | Inspection | NZTA B/5 | Within the first 20m of each run, and where ever material changes | Well mixed material with acceptable particle size distribution | W |  | Where breakdown is excessive, method of milling should be altered to avoid such breakdown
8.6.4 |  | FBS Quality | Inspection | Visual Inspection | Continuous while stabilisation is progressing | No bitumen stringers or blobs observed (See Assessment of hoe'd materials) | W |  | If bitumen blobs or stringers are found the the construction of FBS stops and the equipement is fixed so that there are no bitumen blobs or stringers found
9 | Construction Quality Assurance (QA)
9.1 | Field Compaction Target |  | NDM - Plateau | NZTA B/5 | 1 Every 3000m2 or once daily | Plateau testing done each shift / as required depending on the material variability throughout the site to determine compaction pattern. | V |  | Avg 98% plateau with min 95%. Plateau testing to be completed to determine Field Compaction Target |  | Highways Site Foreman |  | Verified test results of plateau to be supplied
9.2 | Lab testing |  | ITS/ UCS test | NZTA B/5 | 1 Every 3000m2 or once daily | Testing to be completed each shift / as required depending on the material variability throughout the site to verify compaction. | V |  | Tests to be cured & achieve as per specification. |  | Highways Site Foreman / Renewals PM
9.3 | Compaction Testing |  | NDM | NZTA T23: 2021 Direct Transmission | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | Average ≥ 98% Plateau Minimum ≥ 95% Plateau | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved (ie average & minimum of Plateau) Compaction equipment shall be sufficent to achieve 98% MDD |  | Highways Site Foreman / Renewals Engineer |  | Invite NZTA to carry out joint site inspection to inspect NDM Testing onsite. Results to be submitted to NZTA for verification
H
9.4 | Surface Set Up / Clegg Hammer |  | Clegg Hammer | Certified Clegg hammer (Current Certification sticker) & calibrated prior to use | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | CIV ≥ 40 | V |  | Hold point - membrane / chipseal placed once CIV ≥ 40 |  | Construction Supervisor/ Renewals Engineer |  | All test results to be submitted to NZTA for review and verification
H
9.5 | Degree of Saturation (DOS) |  | DOS | NZS 4407 Test 4.2.2 NZTA B/5 Cl. 7.12 | 5 tests per homogeneous lot of up to 1000m2 of laid pavement | For information only | V |  | Soild density to be measured. |  | Downer Lab technician
9.6 | NDM moisture correction |  | NDM & Lab MC |  | 3x Moisture contents per single plateau test carried out | Information only | V |  | Correction offset to be applied per site |  | Highways Site Foreman / Renewals Engineer - Relates to field plateau testing by the laboratory
9.7 | Surface Shape / Profile Layer Thickness |  | NZTA B/5 | Visual inspection Cut/fill tolerance check String records Straight edge | 1 test per 20m | ≤10mm variance from 3m straight edge | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved. Hiways Retain the right to override Machine Control requirement when required. Documentation and Record to supplement reasoning and affected area |  | Highways Site Foreman/ Renewals PM/ Downer surveyor |  | Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
Gradual deviations
Crossfall > 1%
[6 empty] | Finished crossfall between any 2 points more than 2m apart transverse to centreline ±0.5% of design | H
-5mm +15mm or ±5mm at lip of concrete channel where applicable
9.8.1 | Tolerances | Width Unconstrained | TNZ B/2 | Confirm offset from lift pegs | 2 at every lift peg or per 180 m2 | - 20mm + 100mm | V |  | Hold Point – no surfacing layer is to be applied until passing results are achieved |  | Highways Site Foreman / Renewals PM |  | 24hrs prior to inspection, Invite NZTA to carry out joint site inspection to inspect surface shape/profile of pavement layer(s) onsite. Results to be submitted to NZTA for verification.
H
9.8.2 |  | Width Constrained | TNZ B/2 | Stringline/lift pegs | 3 at every lift peg or per 180 m2 | Zero | V
H
9.9 | Ride Quality |  | Owner acceptance test | As per Contract Documents OPM42 | 1 ride test for each lane following Basecourse completion prior to surfacing | Rolling 100m average NAASRA <75 counts/km | W |  | Hold Point – no surfacing layer is to be applied until acceptance of ride quality, No exceptions |  | Road Science/ Downer PM |  | NZTA to carry out joint site inspection to inspect newly constructed pavement surface before sealing. NZTA to approve newly constructed surface before any seasling works to be carried out.
H
9.10 | Mosaic Surface |  | Visual inspection | A clean macro texture with a tight mosaic surface as per Chapter 7 Chipsealing in NZ | Overview of site for tight mosaic surface | The large aggregate is held in place by a matrix of smaller aggregates The smaller aggregate is held firmly in place by fine material The matrix does not displace under normal trafficking or sweeping | W |  | Hold Point – no surfacing layer is to be applied until passing results are achieved |  | NZTA Network Manager / Renewals Manager/ Highways Site Foreman / Downer PM / Downer Sealing Foreman
H
9.11 | Preseal Check |  | Visual check | NZTA B/5 | Before sealing | All prior ITP checks have been completed and signed off | V |  | Hold Point – no surfacing layer is to be applied until all results are verified & approved as per ITP
[6 empty] | No caking layers present | H
9.12 | Pavement Surface As-Built |  | Survey | As per approved drawings | Per installation / Site | Accurate survey of all topograpgical features required | V |  |  |  | Downer Approved Surveyor
10 | Sealing
10.1 | Sealing |  | See Sealing ITP |  |  |  | W |  | Hold Point – All hold points and checks in ITP to be completed before physical works continue |  | Downer Sealing Contract Manager
10.2 | Sealing TMP and Aftercare Process |  | See Sealing TMP to confirm 24 hour trafficking and aftercare processess are in place for site |  |  |  | W |  | Hold Point – 24 hour trafficking and aftercare of sealing works are described and confirmed in TMP for sealing works before physical sealing works proceed. |  | Downer Sealing Supervisor
H
10.3 | Sweeping of Sealing Works and Handover to Roadmarkers |  | Sealing Supervisor to organise sweeping of sealed surface and roadmarking of site including installation of RPM,s before handover of completed surfacing and roadmarked (including RPMinstalls) back to Downer Construction Supervisor. |  |  |  | W |  | Hold Point – All sweeping activities, roadmarking and install of RPM's to be completed before handover of site from surfacing to construction supervisor. |  | Downer Sealing Supervisor
H
11 | Shoulders
11.1 | Slope |  | Visual check | Visual inspection with smart level |  | Slopes consistent & to 5:1 grade. Excessive shoulder construction to be carried out ahead of pavement operation | V |  | Hold Point – no surfacing layer is to be applied until all necessary results are achieved |  | Construction Supervisor/ NZTA |  | Invite NZTA to carry out joint site inspection to inspect site.
H
11.2 | Compaction |  | Visual check | Drive over 4 tonne, check wheeltracks | All shoulders | Vehicles can drive on shoulders without becoming stuck | V |  | Hold Point – physical works cannot be completed until all necessary results are achieved |  | Construction Supervisor/ NZTA
H
11.3 | Soiling |  | Visual check | Approved Design Drawings | All areas requiring grassing | Soiling has been done where required | W |  | As per the design drawings |  | Construction Supervisor
12 | Site Reinstatement / Clearance
12.1 | Traffic Services | Marker Pegs/ Signs/Markings/RRPMs Replaced | TNZ C/20: 2003 | Visual Inspection | All signs/markers | Replaced in same position, height etc | V |  | Hold point – Site cannot be cleared until marker pegs, signs, markings and RRPMs replaced |  | Construction Supervisor/ NZTA |  | Invite NZTA to carry out joint site inspection to inspect site.
H
12.2 | Grassing |  | Visual check |  | All areas requiring grassing | Grassing has been done where required | W |  |  |  | Construction Supervisor
12.3 | Drains Cleared |  | Visual check |  | All drains, after all other works | Drains are cleared and culvert ends and side (accessway) culverts installed or reinstated | W |  |  |  | Construction Supervisor
12.4 | Traffic Management Removed |  | Visual check |  | When safe, after all physical works completed | All traffic management removed from site safely | W |  | Hold Point – TMP cannot be removed until site Audited by Downer Construction Supervisor |  | Construction Supervisor
12.5 | Site Left Clean and Tidy |  | Visual check |  | After vacating site | · Stockpiles removed | V |  |  |  | Construction Supervisor/ NZTA |  | Invite NZTA to carry out joint site inspection to inspect site.
· Plant removed
· Litter cleared from site
13 | As-built Records
13.1 | Collect Asset Data |  | SHDOM (SM050) |  | During construction | All relevant as built information collected | V |  |  |  | Renewals Engineer
13.2 | Enter Asset Data into RAMM and/or Register(s) |  | SHDOM (SM050) | RAMM | At completion of work | All data entered into RAMM and/or register(s). Design report & drawings attached to RAMM site record as a media file. | H |  | Hold Point – project cannot be closed until data entered. |  | Renewals Engineer/ WSP Information Manager |  | Submit all RAMM Data to Data Quality Manager for review and verification
13.3 | Construction Completion Report |  | Confirmation | Contract Specification | At completion of work | Checked and approved | V |  |  |  | Renewals Engineer/ Renewals Manager |  | Submit Pavement Design Report, Construction Compliance, QMP, Site test results / inspections / activity records, Lessons Learnt, As-built Plans
| Quality Assurance Close Out By: | _________________________________________ |  |  | Date: ___________________ |  | _________________________________________________________
(signature)
_________________________________________________________
(name)
THIS RECORD TO CONTRACT FILE
Note on C37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Might pay to add a requird yes/no feild here to make it clear. Same for subsoils, dont want someone reviewing this to thik we didnt do it