## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Steel Stud Framing |  |  |  |  | Yes | Steel Stud Framing | 2946e443-d8da-4024-9d77-aea0fdcb552d
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached
text | d099f902-8af6-4898-81ad-50db87e797ac |  | textbox | Drawing no. and revision
checkpoint-status |  |  | checkpoint | Dimensions / locations checked and accurate
checkpoint-status |  |  | checkpoint | All frames are square
checkpoint-status |  |  | checkpoint | Frames are straight and level
checkpoint-status |  |  | checkpoint | Fixings are correct
checkpoint-status |  |  | checkpoint | Any bracing requirements installed
checkpoint-status |  |  | checkpoint | Nogs/ service nogs installed correctly as per plan
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | All framing completed correctly within tolerance in respective area
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-sectioned | 7d6db0fa-b047-459c-a321-73c1780ae5ea |  | checklist | Concrete Pour Checklist |  |  |  |  | Yes | Concrete Pour Checklist | 83f8b173-dc9a-4c55-a090-a04bf47d29a0
checkpoint-group | 630c3762-c7c3-47af-bd4f-d301ae48ac5e |  | section | Formwork and embedded items
checkpoint-status | 0a07b5a9-e95c-4c18-a04b-20468e23c61b |  | checkpoint | Grids and RLs clearly marked fore reference
checkpoint-status | 078ae8a3-d026-47f4-bd14-58f54325b887 |  | checkpoint | Formwork - location, heights, falls and dimensinos checked and accurate
checkpoint-status | f6dfe821-8f05-4365-a833-52233d618687 |  | checkpoint | Formwork sufficiently fixed and braced
checkpoint-status | 2839e3f7-2d9b-432a-975b-0ffef5fcb34d |  | checkpoint | Any rebates / nibs / cast in items are correctly positioned, sized and appropriately fixed in place.
boolean | 756e6816-f125-50d2-bf10-c5e36d755f64 |  | tickbox | Hold down bolts checked and correct
boolean | 655563fa-33fc-572a-b9ec-cb35d5f8da8c |  | tickbox | Precast panel starters checked and correct
checkpoint-status | b667fef7-5fd8-4b69-8f87-13949ec557ab |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status | 9894226b-8e61-4b48-a2ea-d88d75cc9de6 |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork, etc.)
checkpoint-status | 0e324ab3-50f9-4296-8e4f-06620d7aa5d6 |  | checkpoint | Any control joints / stop ends installed accurately and correctly braced
checkpoint-status | 3f36cf2c-c0b2-4c40-b097-f3cf29193698 |  | checkpoint | DPM & Connection to other waterproofing completed
checkpoint-status | 112eff82-2ee3-4b13-8e72-970521a72149 |  | checkpoint | Any additional formwork photos and observations
checkpoint-status | 17db4d7d-bf7b-4958-8448-d18e98dcd1d0 |  | checkpoint | All formwork elements completed and ready for concrete pour (excess debris removed)
checkpoint-status | 0fb8f0b6-a0c1-40ba-a9a8-e35a5f19b8aa |  | checkpoint | Concrete ordered - correct mix and strength
text | 4b5c37b3-160f-514e-ad06-6df84d326bee |  | textbox | Mix
text | e1d1bd5d-db1f-5e60-8950-7330c447f880 |  | textbox | Strength:
checkpoint-group | 6bff7ca7-36ce-4c57-92f3-b616e54e4f2b |  | section | Placement Method
checkpoint-status | 216849ec-dbcc-418e-8ec8-3a2152bf5065 |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
text | 0af99b15-2592-578d-a5b2-20577356f27f |  | textbox | Date of pour
text | e6a56291-0c8b-5e83-8e40-62815c034d0b |  | textbox | Who is placing the concrete
checkpoint-status | f98d729c-6b47-4f8d-8f05-385d40092a41 |  | checkpoint | Height and falls checked / confirmed before placement
checkpoint-status | 201f04c5-7537-4f23-8898-8f8269be641e |  | checkpoint | Cover correct to specification
checkpoint-status | 45a21073-9d40-4345-9f22-80237b34b659 |  | checkpoint | All concrete checked and correct on arrival (mix and strength)
boolean | 6779d659-81c5-58a8-b246-14302b5284fe |  | tickbox | All concrete dockets attached
checkpoint-status | ce06a9a6-aa64-4ab6-8d7c-867c19990f50 |  | checkpoint | General photos and observations of concrete placement attached
checkpoint-status | ab9ddaf2-b49e-48e4-998b-bbe7343120ff |  | checkpoint | Heights and falls checked / confirmed after placement
checkpoint-status | 7d97f107-cf4e-4ef3-a643-63e67ecc1fda |  | checkpoint | Any curing compound applied correctly
checkpoint-status | e28fab9b-32b7-47f2-aab5-1522853f6738 |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-status | 7d18eeef-6469-4502-89d3-66f684109016 |  | checkpoint | Area left clean and tidy
checkpoint-group | 0fe0ae2e-0c0a-4487-b692-377d3c005389 |  | section | Post Pour Checks / Signoff
checkpoint-status | 1ca0d3c8-9b79-4724-9b6c-365009ead1f8 |  | checkpoint | Any remedial work completed
checkpoint-status | 5e9974b1-0c81-4682-ab46-ff5388e01ae8 |  | checkpoint | Concrete Pour completed - all final checks and documentation completed and attached
checkpoint-status | 246df07b-89e0-49ab-a2da-44a47ced058f |  | checkpoint | Report sent through to client
checklist-flat | e1375c52-77cf-4e9c-9b45-37fd09fb1185 |  | checklist | External Wall Framing |  |  |  |  | Yes | External Wall Framing | 89a48f47-62c7-425e-8c20-e461911e3c87
checkpoint-status | 35abbf51-70d1-4d61-96ca-601d80ea687c |  | checkpoint | All relevant drawings and revision numbers checked and attached.
checkpoint-status | a35176e6-cc68-4cee-8651-cf835e086486 |  | checkpoint | DPC installed, checked, and correct as per specifications.
checkpoint-status | 1436d26c-fffc-4f4c-b2b0-98cfd729ac2a |  | checkpoint | Wall locations checked, correct, and approved as per latest revised drawing.
checkpoint-status | 0711abb9-3212-4caa-ab7c-447ed2f31c69 |  | checkpoint | Fixings and hold down bolts checked and correct.
checkpoint-status | bc159478-275d-4910-9f7c-2793fc21e624 |  | checkpoint | All openings (doors/windows, etc) checked, correct and approved.
checkpoint-status | 25852199-b239-4821-8f7e-402afcf19d92 |  | checkpoint | Sliding joint checked, correct and approved.
checkpoint-status | 6fd2e590-44fc-4dfb-a365-35793947157f |  | checkpoint | Wall type checked (straight and plumb) and within tolerance.
checkpoint-status | a42ba5e2-d9ac-4ff7-868e-5319c04764d6 |  | checkpoint | All relevant nogs (service, and special fixtures) installed, checked and correct.
checkpoint-status | e1b4184d-bbd3-448d-aae4-25ee4a2760c4 |  | checkpoint | All other nogs checked and approved.
boolean | 3940c8d5-0557-5eff-bf8f-a0cec219f5cf |  | tickbox | L1-L2
boolean | f276b11e-3f33-57c3-91d7-98ef920d9d5a |  | tickbox | L3-Roof
checkpoint-status | 58d3bdc6-c119-4544-af23-e25116ba95f0 |  | checkpoint | Moisture reading checked, recorded and acceptable.
checkpoint-status | fe3a018a-20ec-4965-b021-e4e7e8b9131b |  | checkpoint | All wall framing checks completed and inspections carried out.
checkpoint-status | 58092bc2-918c-4d7f-a242-09a3febd1bad |  | checkpoint | Report sent to client.
checklist-flat | 4ed69782-2744-4eb2-8291-9be273317e2a |  | checklist | RAB Checklist |  |  |  |  | Yes | RAB Checklist | cddd9e30-ae6f-4f9b-83a5-d8e66e5c808b
checkpoint-status | 9b7902d1-d2e6-49fc-98a4-5eccde5a3c1d |  | checkpoint | Wall type as specified
checkpoint-status | 8070cc1b-2c53-43b2-9110-e56f32083a81 |  | checkpoint | 20mm gap from flat slab to allow seismic movement
checkpoint-status | 8441db6d-22eb-4001-9cae-76bde525e297 |  | checkpoint | Correct fixing centres for wall type
checkpoint-status | fc10b1ce-e402-4ea2-8afa-7a502ad2c6f5 |  | checkpoint | All nails flat and not puncturing board
checkpoint-status | fb315206-5437-4ebd-90e5-782199f8c977 |  | checkpoint | Gaps are 3mm max
checkpoint-status | 725e82f8-c790-42f4-8e0e-09d78333b723 |  | checkpoint | Flashings in place
checkpoint-status | 1598ebfa-0570-4285-8a0e-e224dd240b03 |  | checkpoint | Overhang correct as per specification
checkpoint-status | 74899d01-70e9-4cfe-af66-f1259b542204 |  | checkpoint | Area RAB complete
checkpoint-status | c8eed8b8-9271-405c-ba9f-84e153172117 |  | checkpoint | RAB Report sent to client
checklist-flat | 889a7c8d-07ff-4580-86b6-e470303d2c0c |  | checklist | Precast Panel Installation |  |  |  |  | Yes | Precast Panel Installation | ec00d226-fb69-473a-8411-3f16212dd0f7
checkpoint-status | cd6e72f4-ed7c-4a30-bc4b-74f02612ed38 |  | checkpoint | Precast panel / column received and damage free
checkpoint-status | 9a299c34-164a-4eb1-a30f-1651b37f697c |  | checkpoint | Setout completed and clearly marked (heights and locations) ready for installation
checkpoint-status | 4a1389c3-8c7b-47eb-a16a-2db7451ae75f |  | checkpoint | Installed in correct location with adequate seating
checkpoint-status | d4381942-7400-4a1e-bd77-79c8089d8b0c |  | checkpoint | Adequately braced
checkpoint-status | 1fdbe7c8-5007-41de-9298-782511f37276 |  | checkpoint | Panel / column install complete (checked location, height and level)
checkpoint-status | 96687789-08d2-4b9a-9e16-f753fb7bfaba |  | checkpoint | All props removed for respective panels and stacked neatly
boolean | 6ca0cd17-5a5e-53ef-b1b2-e6cf0d9adc1d |  | tickbox | Panel surface checked and all Livefirm responsibilities completed
checkpoint-status | db00b089-a76a-4455-9996-5befb9b82456 |  | checkpoint | Report sent through to client
checklist-flat | c6c1e914-5c3d-44dc-994b-9f18939993bb |  | checklist | Cavity Battens |  |  |  |  | Yes | Cavity Battens Checklist | fc49ae5f-6e1f-429c-86c7-d6912f6ceaf0
checkpoint-status | 9b2e85aa-7b5b-47c6-924e-0b6aa5ddfec8 |  | checkpoint | All relevant drawings and revision numbers checked and attached.
checkpoint-status | e1332367-2f9a-4e73-a58b-c7767192ce95 |  | checkpoint | Battens type, spacing centres (600mm) checked and correct.
checkpoint-status | ee0192a5-2c3f-476b-8661-756670c3102c |  | checkpoint | Battens fixings used and fixing centres (250mm/300mm) checked and correct.
checkpoint-status | 16d89632-2990-4218-a785-7f0e8edc5a93 |  | checkpoint | All flashings – 9mm aluminium external box corner, horizontal flashing, head flashing, internal flashing, corner flashing and cavity closer checked and installed correctly.
checkpoint-status | 12cf7333-7610-4402-ab1a-ef6528035e93 |  | checkpoint | Flashing tape checked and installed correctly.
checkpoint-status | 635029fd-08a0-43a2-bbbd-7a82786259ca |  | checkpoint | Report sent through to client.