## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Structural Steel for Area: |  |  |  |  | Yes | QA - Structural Steel | 02177a37-e3bb-4a19-a0f6-44120304482c
checkpoint-group |  |  | section | Pre installation
checkpoint-status |  |  | checkpoint | Structural steel items checked
label | f7725ee9-d154-53c3-8cab-67d95f3171fd |  | note | Type/Size Checked
label | 667eab58-51c6-5b15-be9a-23ccb81a5d0e |  | note | Finishing checked (ie. Painted, Galvanised, etc)
checkpoint-status |  |  | checkpoint | Cast in/anchor bolts and plates installed
checkpoint-status |  |  | checkpoint | All pre installation work completed
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Alignment and levels checked/correct
checkpoint-status |  |  | checkpoint | All dry packing completed
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Structural steel work completed within tolerance in respective area
boolean | d1ac5ab6-9e1c-5d89-a74f-a53a5e4028f3 |  | tickbox | Trades QA received, reviewed, attached and approved
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Underslab for Area: |  |  |  |  | Yes | QA - Underslab Services Install | 1257f1c4-d6aa-4eac-a1fd-cfd2e7c67e4f
checkpoint-status |  |  | checkpoint | ELECTRICAL services/ conduits installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | HYDRAULIC services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | GAS services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | MECHANICAL services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | DATA/COMMS services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | Any other services installed, fixed in correct location, backfilled and correct as per design
checkpoint-status |  |  | checkpoint | Underslab Services completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
checklist-flat |  |  | checklist | Concrete Slab on Grade for Area: |  |  |  |  | Yes | QA - Concrete Slab on Grade | 13dc4c18-7a4c-45b1-bd13-fd3173cc4c7c
checkpoint-status |  |  | checkpoint | Plans showing RLs / set downs / nibs / rebates / slab thickness.
checkpoint-status |  |  | checkpoint | Slab on grade – top of metal RL.
checkpoint-status |  |  | checkpoint | Formwork in place.
checkpoint-status |  |  | checkpoint | Reinforcing steel – mesh size and lap.
checkpoint-status |  |  | checkpoint | Starter bars in correct position and size.
checkpoint-status |  |  | checkpoint | Holding bolts in place.
checkpoint-status |  |  | checkpoint | Floor thickness in place (random slab check areas).
checkpoint-status |  |  | checkpoint | Cover to reinforcing correct.
checkpoint-status |  |  | checkpoint | Construction joints / control joints installed.
checkpoint-status |  |  | checkpoint | Correct MPA / slump.
checkpoint-status |  |  | checkpoint | Council inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Structural engineer inspection or confirmation received to proceed
checkpoint-status |  |  | checkpoint | Levels of finish confirmed.
checkpoint-status |  |  | checkpoint | Curing – water spray / membrane ordered.
checkpoint-status |  |  | checkpoint | Check overspray / clean.
checkpoint-status |  |  | checkpoint | Control joints / saw-cuts and depth.
checklist-flat |  |  | checklist | Comfloor for Area: |  |  |  |  | Yes | QA - Comfloor | 158d6ccc-bed3-44b9-a751-f5ba3979f6c6
checkpoint-status |  |  | checkpoint | Relevant falsework/propping, netting & edge protection installed, checked and acceptable
checkpoint-status |  |  | checkpoint | Setout and heights checked
checkpoint-status |  |  | checkpoint | All perimeter/edges installed & any penetrations correctly formed
checkpoint-status |  |  | checkpoint | Comfloor installation completed, reviewed and approved
checklist-sectioned |  |  | checklist | Precast for Area: |  |  |  |  | Yes | QA - Precast Walls/Stairs/Balconies/Floors | 5abac006-ffb7-4c07-9fe3-4283a8913818
checkpoint-group |  |  | section | Pre installation
checkpoint-status |  |  | checkpoint | Precast walls manufacturing completed and transported safely to the site
boolean | bfc1de35-9617-535d-b533-cf8865f87ec1 |  | tickbox | Trades QA received, reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Site Setout completed
checkpoint-status |  |  | checkpoint | Precast elements inspected, correct and damage free before placement
checkpoint-status |  |  | checkpoint | All pre installation work completed
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Alignment and levels of the panel checked/correct
checkpoint-status |  |  | checkpoint | Panel propping checked
checkpoint-status |  |  | checkpoint | Checked rebar requirements for any insitu stich joints
checkpoint-status |  |  | checkpoint | Any additional photos, comments and observations
checkpoint-status |  |  | checkpoint | Panel installation completed within tolerance in respective area
checklist-flat |  |  | checklist | Grout for Area: |  |  |  |  | Yes | QA - Grout | 665c7347-7f32-4ac2-89ed-90acf537b4fc
checkpoint-status |  |  | checkpoint | Grouting works completed
label | d0caebbb-52b7-5d3c-b58f-ed830cf968e9 |  | note | Photos
checklist-flat |  |  | checklist | Waterproofing for Area: |  |  |  |  | Yes | QA - Waterproofing | 6e64fc1b-833e-408c-876a-66e758175de8
checkpoint-status |  |  | checkpoint | Preparation / Substrate acceptable
checkpoint-status |  |  | checkpoint | Correct product delivered and checked - approval given to install
checkpoint-status |  |  | checkpoint | General photos/comments during install
checkpoint-status |  |  | checkpoint | Any inspections / observations documented, reviewed and closed out
checkpoint-status |  |  | checkpoint | Waterproofing install completed, reviewed and approved to meet required specifications
checklist-flat |  |  | checklist | QA - Roof Framing TEST |  |  |  |  | Yes | QA - Roof Framing TEST | a07646be-3cef-4c40-8192-a810557e4a7f
checkpoint-status |  |  | checkpoint | Correct rafter sizes
checkpoint-status |  |  | checkpoint | Correct timber treatment
checkpoint-status |  |  | checkpoint | Correct rafter centres
checkpoint-status |  |  | checkpoint | Bracing correct
checkpoint-status |  |  | checkpoint | Correct fixings
checkpoint-status |  |  | checkpoint | Hold down fixings
checkpoint-status |  |  | checkpoint | Connections to masonry
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
label | 001b62bd-b7a5-546d-bdbf-5d96b85075bf |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | QA - Exterior Finishes |  |  |  |  | Yes | QA - Exterior Finishes | b909d0bf-5f1d-47f2-8d30-007229f7b6d6
checkpoint-group |  |  | section | Exterior wall framing
checkpoint-status |  |  | checkpoint | Window opening dimension (check agreed sizes with NZ windows)
checkpoint-status |  |  | checkpoint | Bottom plate H3.2 (All other timber frame H1.2)
checkpoint-status |  |  | checkpoint | DPC
checkpoint-status |  |  | checkpoint | Stud , Nog spacing & Bracing
checkpoint-status |  |  | checkpoint | Fixing (type & spacing)
checkpoint-status |  |  | checkpoint | Connectors (type & fixing)
label | 300d5bb6-28c1-545a-9829-4c596d4361de |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Building Wrap
checkpoint-status |  |  | checkpoint | RAB board (thickness & gaps)
checkpoint-status |  |  | checkpoint | RAB board fixings
checkpoint-status |  |  | checkpoint | RAB board taping
checkpoint-status |  |  | checkpoint | All cuts primed
checkpoint-status |  |  | checkpoint | Penetration detailed
checkpoint-status |  |  | checkpoint | Sealant
checkpoint-status |  |  | checkpoint | Vaproshield (when required)
checkpoint-status |  |  | checkpoint | Check for junction flashings as required
label | ec1620c0-3e20-5ad5-97fb-aa4a8a57bfc0 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Cavity System
checkpoint-status |  |  | checkpoint | Head flashings
checkpoint-status |  |  | checkpoint | Cavity battens offset 10mm from the opening refer to arch detail 2/AD834
checkpoint-status |  |  | checkpoint | Cavity batten fixings in accordance with James Hardie Linea Oblique manual
checkpoint-status |  |  | checkpoint | Verman strips
checkpoint-status |  |  | checkpoint | For installation of the 3M 8067 All weather flashing tape in:
label | 1e9f7413-b857-5228-916a-3580448e5a59 |  | note | The sliding door opening
label | c011d890-d740-50b7-81f2-fd23edfe2209 |  | note | Lap over the top edge of the
label | f483dc0c-e5b2-5397-b7d8-3a94ba2f0d30 |  | note | Membrane at the jamb - to stop short from the sill
label | 0b6a99bb-0c7f-5565-b854-4ec1f3fee798 |  | note | Provide photos of the above
label | 77a301e6-fe3d-5559-9078-17d5f277dff5 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior Joinery
checkpoint-status |  |  | checkpoint | Correct sizes
checkpoint-status |  |  | checkpoint | Correct jamb sizes
checkpoint-status |  |  | checkpoint | AT façade sealant 2022 12 in the sliding door openings
label | df36b72b-8c29-540d-8036-a4171b37b9af |  | note | This is Soudal Gorilla MS - refer to the architectural details
checkpoint-status |  |  | checkpoint | PEF backing rod
checkpoint-status |  |  | checkpoint | Flashings
label | 4ea8bf15-3d0c-55a7-b75e-ef9665e22786 |  | note | Trades QA received & attached as applicable
label | a9d349ec-5123-5f5a-9dcc-81c7d607a571 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior 1st fix
checkpoint-status |  |  | checkpoint | Plumbing drains for deck
checkpoint-status |  |  | checkpoint | Fire collars (when required)
checkpoint-status |  |  | checkpoint | Lights wiring
checkpoint-status |  |  | checkpoint | Mechanical ducts
checkpoint-status |  |  | checkpoint | Hose taps pipework
checkpoint-status |  |  | checkpoint | Alarms
checkpoint-status |  |  | checkpoint | Air-con
checkpoint-status |  |  | checkpoint | Roof penetrations
label | 18ae0355-a044-53ce-ad04-a13a87c049ad |  | note | Trades QA received & attached as applicable
label | 9164a289-be6a-57f6-b41f-2cd1daab8d75 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior soffit framing & lining
checkpoint-status |  |  | checkpoint | Framing - DPC
checkpoint-status |  |  | checkpoint | Framing - Stud , Nog spacing & Bracing
checkpoint-status |  |  | checkpoint | Framing - Fixing (type & spacing)
checkpoint-status |  |  | checkpoint | Building paper
checkpoint-status |  |  | checkpoint | Lining - Type & Joins
checkpoint-status |  |  | checkpoint | Lining - Fixing
label | 32715d32-e5ba-5e62-a41a-846a48b97aa1 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior cladding Linea Oblique Weatherboard
checkpoint-status |  |  | checkpoint | Correct layout
checkpoint-status |  |  | checkpoint | Correct sizes
checkpoint-status |  |  | checkpoint | Correct fixings
checkpoint-status |  |  | checkpoint | Correct fixing spacing in accordance with James Hardie Linea Oblique manual
checkpoint-status |  |  | checkpoint | Boards plumb
checkpoint-status |  |  | checkpoint | Boards level
checkpoint-status |  |  | checkpoint | All joints acceptable/sealed
checkpoint-status |  |  | checkpoint | All cuts primed with 2 coats of stain
checkpoint-status |  |  | checkpoint | Correct moldings/flashings
label | 2a56c3d2-d270-5f7a-9cc9-40c7709d6aa4 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Balustrades
checkpoint-status |  |  | checkpoint | Correct type
checkpoint-status |  |  | checkpoint | Correct sizes
label | 4e253bc1-e665-5973-9299-87c0228a1126 |  | note | Trades QA received & attached as applicable
label | 64e19f34-1cf8-5e1d-8991-fd78ba95e3a5 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Fins
checkpoint-status |  |  | checkpoint | Correct type
checkpoint-status |  |  | checkpoint | Correct sizes
label | 26506a45-a780-51f4-be4b-f7241589f20d |  | note | Trades QA received & attached as applicable
label | 2d466bf4-9d7b-5eb4-a7bb-fb00690e1b5b |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Gutters/downpipes
checkpoint-status |  |  | checkpoint | Correct size gutters
checkpoint-status |  |  | checkpoint | Correct downpipe sizes
checkpoint-status |  |  | checkpoint | Correct colours
checkpoint-status |  |  | checkpoint | Gutters straight
checkpoint-status |  |  | checkpoint | Downpipes straight
label | c9f72abf-83f8-5d5d-8dbc-a82ee8d8ef74 |  | note | Trades QA received & attached as applicable
label | 35c40b2e-bc15-58b7-a351-52930857f520 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior painting
checkpoint-status |  |  | checkpoint | Concrete repairs
checkpoint-status |  |  | checkpoint | Join sealant
checkpoint-status |  |  | checkpoint | Window preparation
checkpoint-status |  |  | checkpoint | Ecotone stain
checkpoint-status |  |  | checkpoint | Dulux White on white
checkpoint-status |  |  | checkpoint | Soffit colours
label | ac1aec12-4aab-5191-98ea-ae0045ffb723 |  | note | Trades QA received & attached as applicable
label | 7b26f8e3-8413-5c05-8d29-2649a67ed767 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Deck membrane
checkpoint-status |  |  | checkpoint | Correct membrane - please specify what membrane was used
checkpoint-status |  |  | checkpoint | Correct laps
checkpoint-status |  |  | checkpoint | Correct upstands
checkpoint-status |  |  | checkpoint | No damage
label | c2e2d8e5-1e52-57e2-9514-638768278819 |  | note | Trades QA received & attached as applicable
label | f7ab0323-7d9c-586e-a81d-06f2d012d4ce |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Decking
checkpoint-status |  |  | checkpoint | Correct timber (treatment)
checkpoint-status |  |  | checkpoint | Timber on correct jacks
checkpoint-status |  |  | checkpoint | Fixing (type & spacing)
checkpoint-status |  |  | checkpoint | Even gaps @ wall / balustrade
checkpoint-status |  |  | checkpoint | Request Sign Off
checkpoint-group |  |  | section | Exterior 2nd fix services
checkpoint-status |  |  | checkpoint | Plumbing drains for decks
checkpoint-status |  |  | checkpoint | Downpipes
checkpoint-status |  |  | checkpoint | Lights
checkpoint-status |  |  | checkpoint | Hose taps
checkpoint-status |  |  | checkpoint | Alarms
checkpoint-status |  |  | checkpoint | Air-con
checkpoint-status |  |  | checkpoint | Roof penetrations complete
checkpoint-status |  |  | checkpoint | Clothes line
label | 2e8b2ae7-e0e5-5e6d-9d92-6def8ced7450 |  | note | Trades QA received & attached as applicable
label | 46d00083-af3b-5ebb-adf6-063227d51170 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Exterior Masonry (Ground level only)
checkpoint-status |  |  | checkpoint | Set out
checkpoint-status |  |  | checkpoint | Straight
checkpoint-status |  |  | checkpoint | Plumb
label | 1d14cda2-d444-54dd-9bfa-4a6053c7b306 |  | note | Trades QA received & attached as applicable
label | 8b9b9ab9-96a1-5e2d-86e4-506c395d7ce6 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | QA - Interior Fitout |  |  |  |  | Yes | QA - Interior Fitout | c2331ae0-aefc-40f2-9dca-2260df454c57
checkpoint-group |  |  | section | Interior framing
checkpoint-status |  |  | checkpoint | All studs are set out correct, and are plumb level, square & installed as per manufacturer's recommendations
checkpoint-group |  |  | section | Steel Stud
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Plumbing First Fix
checkpoint-status |  |  | checkpoint | Plumbing first fix complete
boolean | f2396e70-9249-52ce-a881-69569d29379a |  | tickbox | Mixers are in correct position (hole allowance to work with tiles)
boolean | 2e52586c-828f-5c1b-9cd3-b1aae9d24a4c |  | tickbox | All water & gas risers are complete
boolean | 530084c9-949a-573c-b71e-edf847fa6672 |  | tickbox | All stacks are level/plumb
boolean | 08174c28-b3df-51eb-95b3-617539edc4a0 |  | tickbox | All pipe insulated
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-status |  |  | checkpoint | Plumbing fitout have been tested & commissioned
checkpoint-group |  |  | section | Electrical First Fix
checkpoint-status |  |  | checkpoint | Electrical first fix complete
boolean | e8b42197-3748-5da7-9eae-9cafd8eac677 |  | tickbox | Power points have been installed as per the electrical plans
boolean | 7edb057b-b9f6-5565-a4b1-e63d7e3286f9 |  | tickbox | All comms are installed to allow for good detailing around
boolean | 78e5cad6-60e1-55cb-b533-661c03ec2d55 |  | tickbox | GPO's are correct for air conditioning & functional
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-status |  |  | checkpoint | Electrical fitout have been tested & commissioned
checkpoint-group |  |  | section | Mechanical First Fix
checkpoint-status |  |  | checkpoint | Electrical first fix complete
boolean | 4b0ab0e2-10d7-5217-a01d-701321f88a55 |  | tickbox | All aircon has been roughed in & tested
boolean | ac51cddb-1546-5a81-bc5c-52309abbb8c7 |  | tickbox | All mech has been roughed in & completed
boolean | 4fd57640-b899-5c1a-b81a-805b23513f5d |  | tickbox | All services that go through fire rated walls to be treated with collars/fire rated sealant
boolean | 9f1bd908-4323-51a3-a122-5ac8dc0da861 |  | tickbox | Service going through exterior wall on a slope
boolean | 2f414d9b-1f68-59b2-b141-eeb5cc9a8987 |  | tickbox | Duct work to be tear free & sealed prior to cleaning
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-status |  |  | checkpoint | Air Conditioning / Mech fitout have been tested & commissioned
checkpoint-group |  |  | section | Passive Fire
checkpoint-status |  |  | checkpoint | Ensure all penetrations have been installed as per specifications
checkpoint-status |  |  | checkpoint | Ensure all fire collars have been installed in accordance with manufacturer's specifications
checkpoint-status |  |  | checkpoint | Ensure that mechanical ductwork is suitably sealed when passing through firewalls
checkpoint-status |  |  | checkpoint | Ensure that suitable access is provided to mechanical fire dampers
checkpoint-status |  |  | checkpoint | Ensure electrical cables have been suitably sealed when passing through a fire element in
checkpoint-status |  |  | checkpoint | Check that fire doors have been filled
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Preline/ Wall Linings
checkpoint-status |  |  | checkpoint | Ensure installation guide has been followed for insulation
checkpoint-status |  |  | checkpoint | Ensure installation guide has been followed for fire rated walls
boolean | 994c79ad-1df3-532f-8d1c-b86462511bdb |  | tickbox | All insulation fitting snug
checkpoint-status |  |  | checkpoint | All service noggs and fixing noggs complete
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Postline/Wall Linings
checkpoint-status |  |  | checkpoint | Plywood in bathrooms correctly installed
checkpoint-status |  |  | checkpoint | Gib screwed off correctly
checkpoint-status |  |  | checkpoint | Gib in bathroom correct
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Gib stopping
checkpoint-status |  |  | checkpoint | All stopping completed and specified level of finish achieved
boolean | 2c5a2ed8-ec97-551c-83d6-e17432993f2e |  | tickbox | Light check complete
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Painting
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Bathroom & Laundry Waterproofing
checkpoint-status |  |  | checkpoint | Waterproofing completed as per specifications
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Joinery Fit Out
checkpoint-status |  |  | checkpoint | All bathroom joinery installed as per specifications
checkpoint-status |  |  | checkpoint | All kitchen joinery installed as per specifications
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Floor coverings
checkpoint-status |  |  | checkpoint | Vinyl installed as per specifications
checkpoint-status |  |  | checkpoint | Carpet installed as per specifications
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Fire System
checkpoint-status |  |  | checkpoint | Smoke detectors & sensors fit off completed
checkpoint-status |  |  | checkpoint | Smoke detectors & sensors tested as per manufacturer's instructions
checkpoint-status |  |  | checkpoint | Sprinkler rough fit off completed
checkpoint-status |  |  | checkpoint | Sprinklers commissioned
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Woodview Final Sign - Off
checkpoint-status |  |  | checkpoint | All apartment work is completed as per specifications / drawings. All relevant trade QA reviewed & approved
boolean | f0aaa5da-93b2-59ef-bcf2-64dfdff78d5c |  | tickbox | Woodview - apartment final sign off
label | f1b3b44f-a620-5b8f-b08a-d0539cfe542a |  | note | Click to attach signature sign off below
checklist-sectioned |  |  | checklist | QA - Interior Fitout |  |  |  |  | Yes | QA - Interior Fitout (Building A & B) | d42a97cc-6314-4498-af6c-02cd97d0858b
checkpoint-group |  |  | section | Interior framing
checkpoint-status |  |  | checkpoint | All studs are set out correct, and are plumb level, square & installed as per manufacturer's recommendations
checkpoint-status |  |  | checkpoint | H3.2 bottom plate used
checkpoint-status |  |  | checkpoint | Studs are correctly fixed to pre-cast panels
checkpoint-status |  |  | checkpoint | Ceiling fixing installed
checkpoint-status |  |  | checkpoint | Lintels above window openings
label | c26beb39-7786-55cd-a9fa-34e4f7a061ec |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Interior strapping
checkpoint-status |  |  | checkpoint | All studs are set out correct, and are plumb level, square & installed as per manufacturer's recommendations
checkpoint-status |  |  | checkpoint | H3.2 bottom plate used
checkpoint-status |  |  | checkpoint | Studs are correctly fixed to pre-cast panels
checkpoint-status |  |  | checkpoint | Ceiling fixing installed
label | 6a006bc1-5187-5718-8889-4ab96c593db1 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off
checkpoint-group |  |  | section | Steel Stud
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Plumbing First Fix
checkpoint-status |  |  | checkpoint | Plumbing first fix complete
boolean | 7ae6be3b-41f4-5a38-a2e6-82602252701f |  | tickbox | Mixers are in correct position (hole allowance to work with tiles)
boolean | 13e24f0c-e8b4-5b6f-a5b8-aa28a7fe9ff8 |  | tickbox | All water & gas risers are complete
boolean | d3a84685-733e-5180-b9b7-37e5349958bd |  | tickbox | All stacks are level/plumb
boolean | ba36eb65-74e0-501d-9920-581584b1c296 |  | tickbox | All pipe insulated
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-status |  |  | checkpoint | Plumbing fitout have been tested & commissioned
checkpoint-group |  |  | section | Electrical First Fix
checkpoint-status |  |  | checkpoint | Electrical first fix complete
boolean | c6f4845d-ac9b-50a9-b789-ff279baf76d1 |  | tickbox | Power points have been installed as per the electrical plans
boolean | ec7c915c-b322-5471-8520-6e0c4290a771 |  | tickbox | All comms are installed to allow for good detailing around
boolean | 161a2dd9-ac0c-59bb-ad8d-c60ae34603b9 |  | tickbox | GPO's are correct for air conditioning & functional
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-status |  |  | checkpoint | Electrical fitout have been tested & commissioned
checkpoint-group |  |  | section | Mechanical First Fix
checkpoint-status |  |  | checkpoint | Electrical first fix complete
boolean | 75e66a89-0c53-53bb-8918-a8f418c50772 |  | tickbox | All aircon has been roughed in & tested
boolean | c9692955-e2de-5ea4-b65b-22995deb5449 |  | tickbox | All mech has been roughed in & completed
boolean | ba3cfc9d-6755-50dd-b621-5891b88fbded |  | tickbox | All services that go through fire rated walls to be treated with collars/fire rated sealant
boolean | bf71cf6b-6d38-582f-a2cc-3d950fe285e9 |  | tickbox | Service going through exterior wall on a slope
boolean | 0f5076ff-837c-5e79-936d-3e943f8c986d |  | tickbox | Duct work to be tear free & sealed prior to cleaning
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-status |  |  | checkpoint | Air Conditioning / Mech fitout have been tested & commissioned
checkpoint-group |  |  | section | Passive Fire
checkpoint-status |  |  | checkpoint | Ensure all penetrations have been installed as per specifications
checkpoint-status |  |  | checkpoint | Ensure all fire collars have been installed in accordance with manufacturer's specifications
checkpoint-status |  |  | checkpoint | Ensure that mechanical ductwork is suitably sealed when passing through firewalls
checkpoint-status |  |  | checkpoint | Ensure that suitable access is provided to mechanical fire dampers
checkpoint-status |  |  | checkpoint | Ensure electrical cables have been suitably sealed when passing through a fire element in
checkpoint-status |  |  | checkpoint | Check that fire doors have been filled
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Preline/ Wall Linings
checkpoint-status |  |  | checkpoint | Ensure installation guide has been followed for insulation
checkpoint-status |  |  | checkpoint | Ensure installation guide has been followed for fire rated walls
boolean | 773a91e7-afa8-5469-9d2c-a594022c98b3 |  | tickbox | All insulation fitting snug
checkpoint-status |  |  | checkpoint | All service noggs and fixing noggs complete
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Postline/Wall Linings
checkpoint-status |  |  | checkpoint | Plywood in bathrooms correctly installed
checkpoint-status |  |  | checkpoint | Gib screwed off correctly
checkpoint-status |  |  | checkpoint | Gib in bathroom correct
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Gib stopping
checkpoint-status |  |  | checkpoint | All stopping completed and specified level of finish achieved
boolean | 0c59df38-1145-5a32-afef-b879c34a01a2 |  | tickbox | Light check complete
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Painting
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Bathroom & Laundry Waterproofing
checkpoint-status |  |  | checkpoint | Waterproofing completed as per specifications
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Joinery Fit Out
checkpoint-status |  |  | checkpoint | All bathroom joinery installed as per specifications
checkpoint-status |  |  | checkpoint | All kitchen joinery installed as per specifications
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Floor coverings
checkpoint-status |  |  | checkpoint | Vinyl installed as per specifications
checkpoint-status |  |  | checkpoint | Carpet installed as per specifications
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Fire System
checkpoint-status |  |  | checkpoint | Smoke detectors & sensors fit off completed
checkpoint-status |  |  | checkpoint | Smoke detectors & sensors tested as per manufacturer's instructions
checkpoint-status |  |  | checkpoint | Sprinkler rough fit off completed
checkpoint-status |  |  | checkpoint | Sprinklers commissioned
checkpoint-status |  |  | checkpoint | Trades QA received & attached as applicable
checkpoint-group |  |  | section | Woodview Final Sign - Off
checkpoint-status |  |  | checkpoint | All apartment work is completed as per specifications / drawings. All relevant trade QA reviewed & approved
boolean | ab8d9e06-315c-550a-b22a-d8d9fa859dda |  | tickbox | Woodview - apartment final sign off
label | 6e5de6b1-7f98-557e-b235-1931e5f6c638 |  | note | Click to attach signature sign off below
checklist-flat |  |  | checklist | QA - Roof Framing |  |  |  |  | Yes | QA - Roof Framing | dc9b4a75-5433-4526-9479-8e7affdfeb2f
checkpoint-status |  |  | checkpoint | Correct timber treatment
checkpoint-status |  |  | checkpoint | Correct fixings (incl spacing)
checkpoint-status |  |  | checkpoint | Hold down fixings
checkpoint-status |  |  | checkpoint | Connections to masonry
checkpoint-status |  |  | checkpoint | Correct flashing sizes
checkpoint-status |  |  | checkpoint | Correct flashing types
checkpoint-status |  |  | checkpoint | Roof penetrations sealed
checkpoint-status |  |  | checkpoint | Roof penetrations back flashed
checkpoint-status |  |  | checkpoint | Vaproshield (when required)
checkpoint-status |  |  | checkpoint | Trades QA received, reviewed, attached and approved
label | 2f28bb0e-d969-5220-917b-9455ec4a6185 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request holdpoint
checklist-sectioned |  |  | checklist | Concrete Pour for Area: |  |  |  |  | Yes | QA - Concrete Pours and Slabs | e0f8db5e-d9ad-44c4-9a8e-2e5d5fdb7691
checkpoint-group |  |  | section | Concrete - Pre Pour
checkpoint-status |  |  | checkpoint | Area Accessible & Approval to start
checkpoint-status |  |  | checkpoint | Formwork - Correct Dimensions & Heights
checkpoint-status |  |  | checkpoint | Formwork cleaned, oiled and braced sufficiently
checkpoint-status |  |  | checkpoint | Any/All cast in items checked / correct (location and size)
checkpoint-status |  |  | checkpoint | Penetrations correctly formed/located, checked and accurate
checkpoint-status |  |  | checkpoint | Reinforcing checked and correct
button | 4746d3b9-af2c-53ca-bef1-03ee77a1ca28 |  | button | Size and type correct to specification | Yes, No
boolean | 5a82f304-aa6d-52b5-8051-0b99323d6b07 |  | tickbox | Reinforcing spacing and location correct | Yes, N/A
boolean | 58c77393-dc2a-5040-980d-768868150d77 |  | tickbox | Specified covers checked/correct | Yes, N/A
boolean | 9e4607b0-3b82-590a-bdcc-0b9196917776 |  | tickbox | Splice laps checked/correct | Yes, N/A
boolean | cbb2eab7-e151-5daa-a6bc-bb31854a3942 |  | tickbox | Any starter bars are installed correctly (location, size and spacing ) | Yes, N/A
boolean | adf8a497-c74c-5c93-9be5-159ec1c39e17 |  | tickbox | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed | Yes, N/A
checkpoint-status |  |  | checkpoint | Waterproofing (checked and correct)
checkpoint-status |  |  | checkpoint | Bottom of concrete pour is clean and free of debris/roughened
checkpoint-status |  |  | checkpoint | Engineer informed of pour checks completed (see consultant folder and ensure observations are closed out)
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Concrete - Pour /Post Pour
checkpoint-status |  |  | checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
boolean | 7a06dc70-161f-556e-9a20-4389d8d58e21 |  | tickbox | All concrete dockets photographed/attached here
checkpoint-status |  |  | checkpoint | General photos/comments/observations during placement
checkpoint-status |  |  | checkpoint | Concrete surface finish to specifications
checkpoint-status |  |  | checkpoint | Concrete Pour completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
label | ea588747-a9a4-503b-bcd1-22c8b54eb4c9 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
boolean | 17d87d49-05d5-50b8-a371-7b32e01c9423 |  | tickbox | Trades QA received & attached as applicable
checklist-flat |  |  | checklist | Footings for Area: |  |  |  |  | Yes | QA - Footings | e46f039a-1870-4649-a54a-f4c2d9d7d8ec
checkpoint-status |  |  | checkpoint | Drawings photo with location
checkpoint-status |  |  | checkpoint | Set out correct
checkpoint-status |  |  | checkpoint | Boxing correct
checkpoint-status |  |  | checkpoint | Reinforcing
checkpoint-status |  |  | checkpoint | Starter setout
checkpoint-status |  |  | checkpoint | Inspect
checkpoint-status |  |  | checkpoint | Pour
checklist-flat |  |  | checklist | QA - Exterior Fitout |  |  |  |  | Yes | QA - Exterior Fitout | f157220e-a1d1-471c-a94e-90b88a2e8344
checkpoint-status |  |  | checkpoint | Panel joints with in tolerances
checkpoint-status |  |  | checkpoint | Panel damage
checkpoint-status |  |  | checkpoint | Panel defects
checkpoint-status |  |  | checkpoint | Panel joints cleaned
checkpoint-status |  |  | checkpoint | Panel PEF Rod in joints
checkpoint-status |  |  | checkpoint | Panel joints primed
checkpoint-status |  |  | checkpoint | Panel joint sealant correct type
checkpoint-status |  |  | checkpoint | Panel joint sealant correct
checkpoint-status |  |  | checkpoint | Panel joint sealant peel test
label | 19162d8d-da87-5b22-bb34-667f020a4839 |  | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
holdpoint |  |  | signoff | Request Sign Off