## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1210-026 ITP Pavements Type 1A | itp |  |  |  |  | DN1210-026 ITP Pavements Type 1A Rev 1
section | SECTION 1 – PRE-CONSTRUCTION HOLD POINTS (MATERIAL & THIRD PARTY APPROVALS)
checkpoint | 1.1.1 - Geogrid
label | Detail - The Contractor shall submit the full details of the geogrid they propose to use to the Engineer for approval prior to installation.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 20.5.2, PS 16.5.13
label | Verifying Document - Data Sheets and Approval
label | Testing Quantity Required (based from schedule qtys) - Results to Engineer for Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.1.2 - Geotextile Fabric
label | Detail - The Contractor shall submit the full details of the geotextile fabric they propose to use to the Engineer for approval prior to installation.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 20.5.2, PS 16.5.14
label | Verifying Document - Data Sheets and Approval
label | Testing Quantity Required (based from schedule qtys) - Results to Engineer for Approval
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.2 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Max Particle Size 53mm
label | ○ Max 10% passing 13.2mm sieve
label | Standard / Specification - Appendix XVIII
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test per 100m3
label | ○ Results to Engineer 2wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - CA or better
label | Standard / Specification - Appendix XVIII, PS 16.5.5, Appendix V
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - >100KN
label | Standard / Specification - NZS4407:2015 Test 3.10
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - >60%
label | Standard / Specification - NZS4407:2015 Test 3.15
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB, or CA
label | Standard / Specification - NZS4407:2015 Test 3.11
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4.1 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 63.0mm ¦¦ 100% passing
label | 37.5mm ¦¦ 68-90% passing
label | 19.0mm ¦¦ 42-76% passing
label | 9.5mm ¦¦ 26-58% passing
label | 4.75mm ¦¦ 16-44% passing
label | 2.36mm ¦¦ 10-33% passing
label | 1.18mm ¦¦ 6-24% passing
label | 0.425mm ¦¦ 3-14% passing
label | 0.075mm ¦¦ 1-6% passing
label | Standard / Specification - NZS4407:2015 Test 3.8.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4.2 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - ≥ 25
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4.3 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - NZS4402:1986 Test 4.1.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5.1 - Crushing Resistance
label | Detail - NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load
label | Acceptance / Conformance Criteria - < 10% fines passing 2.36mm under a load of 130kN
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5.2 - Soaked CBR
label | Detail - NZS4407:2015, Test 3.15 The California Bearing Ratio (CBR)
label | Acceptance / Conformance Criteria - ≥ 60%
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5.3 - Weathering Resistance
label | Detail - NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate
label | Acceptance / Conformance Criteria - CA or better
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.1
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test Per Material, Per Source every 10,000m3
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6.1 - Particle Size Distribution
label | Detail - NZS4407:2015, Test 3.8.1 - Particle Size Distribution
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Passing
label | 63.0mm ¦¦ 100% passing
label | 37.5mm ¦¦ 55-85% passing
label | 19.0mm ¦¦ 33-65% passing
label | 9.5mm ¦¦ 20-50% passing
label | 4.75mm ¦¦ 10-36% passing
label | 2.36mm ¦¦ 5-27% passing
label | 1.18mm ¦¦ 2-20% passing
label | 0.425mm ¦¦ 1-13% passing
label | 0.075mm ¦¦ 6% max passing
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6.2 - Shape Control
label | Detail - Tolerance allowed from approved grading curve (%)
label | Acceptance / Conformance Criteria - Sieve Size ¦¦ % Tolerance
label | 37.5 – 9.5 ¦¦ 34-50%
label | 19.0 – 4.75 ¦¦ 18-40%
label | 9.5 – 2.36 ¦¦ 12-32%
label | 4.75 – 1.18 ¦¦ 6-24%
label | 2.36 – 0.6 ¦¦ 2-20%
label | 1.18 – 0.3 ¦¦ 0-15%
label | 0.6 – 0.15 ¦¦ 0-12%
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6.3 - Sand Equivalent
label | Detail - NZS4407:2015, Test 3.6 Sand Equivalent
label | Acceptance / Conformance Criteria - ≥ 30
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6.4 - Cone Penetrometer Limit
label | Detail - NZS4407:2015, Test 3.2 Cone Penetration
label | Acceptance / Conformance Criteria - Cone Penetrometer ≤ 25
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6.5 - Plasticity Index
label | Detail - NZS4407:2015, Test 3.4 Plasticity Index
label | Acceptance / Conformance Criteria - Plasticity Index ≤ 8
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6.6 - Accelerated Weathering
label | Detail - NZTA T/20 Ethylene Glycol Accelerated Weathering Test
label | Acceptance / Conformance Criteria - ≤ 30% increase in fines
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - Number of Tests Required Stockpile Size (m3):
label | ○ 0-400 - 2 tests
label | ○ 400-1,500 - 3 tests
label | ○ 1,500-4,000 - 4 tests
label | ○ >4,000 - 1 test for each additional 1,000m3
label | – Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6.7 - Maximum Dry Density and Optimum Water Content
label | Detail - NZS4402:1986, Test 4.1.2 - Heavy Compaction Test
label | Acceptance / Conformance Criteria - Report Value Only
label | Standard / Specification - PS 20.7.1, TCC-IDC IT-4.7.2
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 2 Tests Per Material, Per Source
label | ○ Results to Engineer 2 wks before importing
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 2 – CONSTRUCTION - SUBSOIL DRAINS
checkpoint | 2.1.1 - Subsoil Drain inspection
label | Detail - Subsoils to be placed below kerb lines and inspected by Engineer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - PS 17.6.3
label | Verifying Document - Release of hold point
label | Testing Quantity Required (based from schedule qtys) - No less than 24 hours prior to placement of backfill
label | Verification Activity: Activity - I
label | Verification Activity: By - ENG
checkpoint | 2.1.1 - Excavation
label | Detail - Excavtion of Trench should be within tolerances.
label | Acceptance / Conformance Criteria - 335mm deep x 300mm wide
label | Standard / Specification - Drawings
label | Verifying Document - Subsoil Checksheet
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 2.1.2 - Placement of Bidim
label | Detail - A29 Bidim to be placed andd wrapped around Trench.
label | Acceptance / Conformance Criteria - Minimum Width 300mm.
label | Standard / Specification - Drawings
label | Verifying Document - Subsoil Checksheet
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 2.1.3 - Cushion (Bedding)
label | Detail - Pipe must have 75mm of Cushion. Drainage 20:40 Material to be used.
label | Acceptance / Conformance Criteria - Minimum 75mm
label | Standard / Specification - Drawings
label | Verifying Document - Subsoil Checksheet
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 2.1.4 - Placement of Pipe
label | Detail - 110mm Perforated Pipe to be laid Down
label | Acceptance / Conformance Criteria - As Per Drawings
label | Standard / Specification - Drawings
label | Verifying Document - Subsoil Checksheet
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
checkpoint | 2.1.5 - Backfill
label | Detail - Pipe Must have a 150mm cover from Bottom of Pavement.
label | ○ Drainage 20:40 Material to be used.
label | Acceptance / Conformance Criteria - >150mm Cover
label | Standard / Specification - Drawings
label | Verifying Document - Subsoil Checksheet
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - M
label | Verification Activity: By - SE
section | SECTION 3 – CONSTRUCTION - PLACEMENT OF GEOGRID AND GEOTEXTILE FABRIC
checkpoint | 3.1.1 - Placement of Geotextile Fabric
label | Detail - Place Geotextile Fabric Strength Class B across pavement area, with 500mm overlaps
label | Acceptance / Conformance Criteria - Visual inspection
label | Standard / Specification - NTC0097
label | Verifying Document - Visual inspection
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - WP
label | Verification Activity: By - ENG
checkpoint | 3.1.2 - Onsite Check by Engineer on Geogrid
label | Detail - Installation of Geogrid shall not commence until the Engineer has inspected the proposed geogrid on site and confirmed that the correct types of geogrid have been supplied.
label | Acceptance / Conformance Criteria - Visual inspection
label | Standard / Specification - NTC0100
label | Verifying Document - Release of hold point
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1.3 - Placement of Geogrid
label | Detail - The Duragrid X 30/30 Geogrid shall be placed on top of the Geotextile Fabric, and overlap areas of structural fill by a minimum of 2m, or as directed by the Engineer on site where the layer depth of structural fill is insufficient to limit deflections from the subgrade.
label | Acceptance / Conformance Criteria - Visual inspection
label | Standard / Specification - NTC0100
label | Verifying Document - Visual inspection
label | Testing Quantity Required (based from schedule qtys) - During Construction
label | Verification Activity: Activity - WP
label | Verification Activity: By - ENG
section | SECTION 4 – CONSTRUCTION - SUBGRADE IMPROVEMENT LAYER TESTING
checkpoint | 4.1.1 - Plateau Density Test
label | Detail - Using a 14T Roller carry out plateau density test to determine optimum rolling pattern using static and vibratory passes
label | Acceptance / Conformance Criteria - Plateau Density Report
label | Standard / Specification - NZTA B/02 7.5
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.1 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - -25mm + 5mm
label | Standard / Specification - NZTA B/02 5.1
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.2.2 - 3m Straight Edge
label | Detail - Formation to ensure Surface is Smooth
label | Acceptance / Conformance Criteria - 10mm (-/+)
label | Standard / Specification - TNZ B/2 7.7
label | Verifying Document - Checksheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.3.1 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD, Min >92% of MDD
label | Standard / Specification - NZTA B/02 7.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 4.3.2 - Benkelmen Beam
label | Detail - As directed by Engineer 15m staggered by wheel path for each lane.
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - NTC0160
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - As directed by Engineer
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 5 – CONSTRUCTION - SUBBASE LAYER CONSTRUCTION
checkpoint | 5.1.1 - Plateau Density Test
label | Detail - Using a 14T Roller carry out plateau density test to determine optimum rolling pattern using static and vibratory passes
label | Acceptance / Conformance Criteria - Plateau Density Report
label | Standard / Specification - NZTA B/06 7.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.1.2 - 3m Straight Edge
label | Detail - Formation to ensure Surface is Smooth
label | Acceptance / Conformance Criteria - 10mm (-/+)
label | Standard / Specification - TNZ B/2 7.7
label | Verifying Document - Checksheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.2.1 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check finished height of surface
label | Acceptance / Conformance Criteria - -25mm + 5mm
label | Standard / Specification - NZTA B/02 5.1
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Set Every 20m Centres
label | ○ 1 set = 5 tests
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.3.1 - Compaction - NDM
label | Detail - NZS4407:2015, Test 4.3 Nuclear Moisture Density Gauge (Backscatter Mode)
label | Acceptance / Conformance Criteria - Ave >95% of MDD, Min >92% of MDD
label | Standard / Specification - NZTA B/02 7.6
label | Verifying Document - IANZ Accredited Report
label | Testing Quantity Required (based from schedule qtys) - 1 set (5 tests) 1000m2
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 5.4.1 - Benkelmen Beam
label | Detail - As directed by Engineer 15m staggered by wheel path for each lane.
label | Acceptance / Conformance Criteria - 90th Percentile: 1.65mm
label | ○ Maximum: 1.82mm
label | Standard / Specification - PS 20.14.5, NTC0160
label | Verifying Document - Test Report
label | Testing Quantity Required (based from schedule qtys) - As directed by Engineer
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5.1 - QA Submission
label | Detail - Submit all Subbase QA before proceeding with next pavement layer
label | Acceptance / Conformance Criteria - Engineers Approval
label | Standard / Specification - Appendix V
label | Verifying Document - All test reports
label | ○ Material Test Results
label | ○ Laboratory MDD
label | ○ NDM results
label | ○ Proof Roll - hold point release
label | Testing Quantity Required (based from schedule qtys) - Once
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 6 – KERB & CHANNEL PREPARATION
checkpoint | 6.1.1 - Stringlines or equivalent
label | Detail - Stringlines or equivalent to check height of surface prep
label | Acceptance / Conformance Criteria - +/-5mm
label | Standard / Specification - PS 21.7.6
label | Verifying Document - Check Sheet
label | Testing Quantity Required (based from schedule qtys) - 1 Test along kerb line @ 20m centres
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
checkpoint | 6.2.1 - Compaction - Clegg Hammer
label | Detail - ASTM D5874-16:2016 Clegg Hammer Testing
label | Acceptance / Conformance Criteria - Min 25 CIV
label | Standard / Specification -
label | Verifying Document - Clegg Hammer Report
label | Testing Quantity Required (based from schedule qtys) - 1 Test along kerb line @ 20m centres
label | Verification Activity: Activity - I
label | Verification Activity: By - SE
section | SECTION 7 – AS-BUILTS / REDPEN MARKUPS
checkpoint | 7.1 - As-Builts/ Red pen markup
label | Detail - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
label | Acceptance / Conformance Criteria - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
label | Standard / Specification - PS 16.7.6
label | Verifying Document - Red pen markups
label | Testing Quantity Required (based from schedule qtys) - During Earthworks
label | Verification Activity: Activity - D
label | Verification Activity: By - SV
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature