## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
750feedc-02fc-4433-b4dd-1e4dd205e9fb | checklist | Checkers Checklist |  | Checkers Checklist
0f4b6d09-26ff-45c9-9c49-9e54bb6b2be5 | section | Details
fce26bc9-af8a-4c83-a5dd-fdab63672a87 | checkpoint | Site Safety / Workers Safety
71f62746-6040-4410-b826-13f1e5837062 | checkpoint | Availability of updated shop drawing
5e45a913-07f1-4656-bc06-b9fcbb803254 | checkpoint | Overall Measurements of construction Eliment
c448611d-938e-46fe-a3ed-2618ccf6b8c8 | checkpoint | Embeded Item - Void - Position,Size,Orientation
6bb364f9-ae77-4b95-b618-64e1ee507c7c | checkpoint | Embeded Item - Cogged Bars
915758ef-1d8a-4d90-b0b3-50579078f6e7 | checkpoint | Embeded Item - Lifters Correct - Position,Size,Orientation
f6324bd1-fe05-42ed-88ae-ba727d7be1b9 | checkpoint | Embeded Item - Fillet / Chamfer instasllation
3b7e932f-92f1-48d9-ac31-ebe96a857dcd | checkpoint | Concrete cover check minimum 30mm
f66ce11b-1cf2-4db5-a165-a63c831c7e0c | checkpoint | Panel Thickness check,alignment check
45c17107-d087-5f98-b9f1-c674d60a135d | dropdown | Panel Thickness: | 150mm,200mm
4cf50fc4-1a85-44df-b561-db03cd335dcb | checkpoint | Panel length check, alignment check
6e23ea70-afe4-5edc-aa69-db396d50f083 | dropdown | Panel Length: | 2534 mm,1175 mm
61c90513-1b07-44d2-956a-33a106a531c4 | checkpoint | Formwork Check - Magnets are 100% Secure,All supports,Ties,Bracing
c3484e4c-fe90-4f8b-8fc8-c4b12a466acb | checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
daa58225-7290-48e7-a339-1c956b766354 | checkpoint | Reinforcement (Reo) placed, cleaned, tightned
a15dfb6b-3dab-402b-86b8-bc44f79d3262 | checkpoint | Curing Procedure arranged
caf9f795-c123-43e3-a3e4-3206afcd29d1 | checkpoint | Photo Taken
ab556db4-3397-4353-b145-e51d5cb2d5de | checklist | Installers Checklist |  | Installers Checklist
158107c9-3ff5-4f2f-b139-b79883e3f9c3 | section | Job Aproval Documents/Constrction Documents
09d452a1-3e88-42a7-84ff-c8d51404495b | checkpoint | Complete Material "Bucket List"
a3d5925a-7757-4363-858f-fdeee43117c8 | checkpoint | Eye Anchor
5550ae83-9c6f-5d22-855f-12bd0748567a | textbox | Eye Anchor:
66dc6355-729f-422b-8dec-5adbe3adbaff | checkpoint | Ferrules / Cogged Bars / Extentions
fa25696c-770c-521a-9347-363cfe49cbfd | textbox | Ferrules / Cogged Bars / Extentions:
9eee2f2c-6bab-48f3-83db-0124255cdeb4 | checkpoint | ID Plate
40f8abbd-bca1-536a-98bd-0baab7683e4a | textbox | ID Plate:
5f12dd8f-408f-4746-b328-9f90ff4f473c | section | Pre-Pour Check Approvals
5a03da8a-1e17-45bd-8691-2299e2d0eb30 | checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
b96fc310-75b7-4160-ac10-e755fbcca078 | checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
a41f1c3a-f7a2-44e7-a9a6-b7f2a28f7fbe | checkpoint | Temporary Fix ID Plate to Formwork
7b9ec6d7-e786-472f-9261-cdf2d81d52f3 | checkpoint | Use Required Mould,Supports,Ties
89875927-578e-48e0-81e1-74c249a1ba26 | checkpoint | Reinforcment Check - Reo as-per Shop Drawing
f5cf9194-e33c-4041-ade9-7b2bb3c3d966 | checkpoint | Reinforcment Check - Reo as-per Shop Drawing
742f67ed-8861-4a68-a503-e17d3ad3a2c1 | checkpoint | Lifters, Ferrules, Tubes Fixed Firm & alligned -Check
609d338d-133c-44f1-91b6-dca5709c512b | checkpoint | Concrete cover Check - minimum xx mm
586bdf9f-936d-5e2c-a258-f53b283b5f59 | textbox | Concrete cover Check:
4e868732-db69-4a83-8ed2-51613e46a119 | section | Quality Assuarance
e5fe1e3a-5a47-48e3-b13c-39ab542727bd | checkpoint | QA - Final Check of ALL measurerments
2ec21566-a37c-448a-a9c5-7e6d6c50c4d2 | checkpoint | QA - Concrete N40 Panel Mix - Special Adjustments
3f289975-6163-4eeb-a497-2700836ba441 | checkpoint | QA - Concrete mixdesign ,veriations%, adjustments%,mix time
c1e36ada-a07b-46ee-87db-9a39f208a336 | checkpoint | QA - All main & other Requirement to do Concreting -DOUBLE CHECK
3f0ee4e9-9f7b-5ffb-98c7-bcbca47f116b | date | Pour Date:
8de1e483-04fa-4046-83b6-690ad82306a8 | checkpoint | CONCRETE TEST Procedure
6012926f-4ce2-43f9-b6cc-4735f85a54b5 | checkpoint | APPROVAL FROM ENGINEER
0e71bdba-8b01-461d-aabb-704b2176988d | section | Other Arangments
6b12667c-fc40-4cff-9aa1-67e5030d26e1 | checkpoint | Concrete surface Finish Requirement arranged
083ffc05-21b5-5767-8766-992834b80c8e | dropdown | Finish: | Fine finish,Broom finish
8c0db820-b5d0-44b5-9de5-dba535fef908 | checkpoint | Curing Procedure arranged
ae203791-aafc-48e1-a645-fda3f1a6d6b5 | checklist | Precast Components ITP |  | Precast Components ITP
8066b215-5c41-49dd-81ff-960f3dbfa23f | section | Job Aproval Documents/Construction Documents
7229084a-b29d-48e6-8724-d765bdfe09fa | checkpoint | Received Construction drawing from Client
6aeb7e9c-43d6-4cef-922f-6de1cc39e182 | checkpoint | Shop drawingsPrepaired, reviewed and updated. Issued "As For Construction"
8467ee44-a39d-4a00-9c43-01eb6786fd84 | checkpoint | Shop Drawings For Lifting arrangments
29e7e379-4b23-4ced-b05e-3e575d6fa3f9 | checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
1917f51e-e968-4350-b920-261383c4d0df | section | Pre-Pour Check Approvals
0edb11af-7a76-41f9-948b-0133d5ee657d | checkpoint | Form Work
785d210b-3299-4440-aa56-719b37f6a0f4 | checkpoint | Reinforcement (Reo)
0419329b-163d-441e-9328-c8aaf153317a | checkpoint | Embeded Items and their placment
f43a03cd-dc3b-4efe-9ff2-3554c10f5396 | checkpoint | Concreting (mix design)
75f096af-ac89-489a-af63-b83f3b19e166 | section | Test on Concrete (requests and approvals)
e4586604-de1d-4241-88b8-1cf77cc3d7f9 | checkpoint | Request From Client
eb5f2946-2c53-4e4d-865c-c4f7f397701f | checkpoint | Test schedule and Test Results
3f93dd14-806b-4111-ac4b-95892bbbe0ee | section | Transport 01
4bec7838-04ba-4e56-a235-e5e0bbdad629 | checkpoint | Any Lifting, Loading, Transport Instructions from Client
5ccb0ca4-0265-4ab6-bd21-798f02f52b81 | checkpoint | Transport Vehical Approvals
ab2b0d6c-9f37-48fd-b2cb-3ab46ab6f487 | checkpoint | Ensure loads are glutted correctly and chains are over gluts.
46afceed-426e-415c-8431-a7a9a3dfcb47 | section | Transport 02
b6864781-69a4-4025-b403-991c821f4ab4 | checkpoint | Any Lifting, Loading, Transport Instructions from Client
737a38a6-de67-4534-a50a-3b760893864b | checkpoint | Transport Vehical Approvals
dc55072d-ed44-450c-98c9-1e426fa77700 | checkpoint | Ensure loads are glutted correctly and chains are over gluts.
e4b5f107-ddb9-4c83-bda3-6af6bd1490c8 | section | Other Documentations
59abbd42-2c48-4113-bd46-571489b3e5aa | checkpoint | Special Instructions
6ab0c22e-279b-4844-86ef-3f5223928972 | checkpoint | Other