## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DTM-ITP-013- Retaining Wall Backfill | itp |  |  |  |  | DTM-ITP-013- Retaining Wall Backfill Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PMP, EMP, TMP, JSEA, SWMS & Work Pack
label | REFERENCE DOCUMENTS: PMP, EMP, TMP, JSEA, SWMS, Work Pack
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Survey Set-Out
label | FREQUENCY: Prior to commencement of excavation
label | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer/ Surveyor
date | Date Completed:
checkpoint | 2.2 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Placing Fill
label | FREQUENCY: Prior to Commencing Fill
label | ACCEPTANCE CRITERIA: Placing fill shall not commence on the prepared areas until the area has been reviewed by the Superintendent
label | REFERENCE DOCUMENTS: DSG Spec. Cl. 204.10(b)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Area reviewed by Superintendent, Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer / QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Groundwater
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: HOLD POINT
label | ○ Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
label | REFERENCE DOCUMENTS: 204.06 (h)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off, Work Procedure
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Fill Placement next to Structures
label | FREQUENCY: Prior to Placement
label | ACCEPTANCE CRITERIA: HOLD POINT
label | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Superintendent.
label | REFERENCE DOCUMENTS: DSG Spec. Cl. 204.11(b)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer / QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Compaction of Fill next to Structures
label | FREQUENCY: Placement of Fill
label | ACCEPTANCE CRITERIA: The permeable fill material shall be placed in conjunction with the adjacent fill in layers not exceeding 150 mm compacted thickness, and compacted to refusal using hand operated 120Kg vibratory plate compactor.
label | ○ Compaction plant shall not be operated within the minimum distances from structures shown in Table 204.111
label | ○ The difference in level of any fill being placed on opposite sides of a structure or structural component shall not exceed H/4 or 500 mm, whichever is the lesser, where H is the height of the structure.
label | REFERENCE DOCUMENTS: DSG Spec. Cl. 204.11(b), Drawing 0320-0321
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off, Work Procedure
label | IP
label | RESPONSIBILITY: Site Engineer / QAV
date | Date Completed:
checkpoint | 2.7 - Topsoiling (Behind Wall)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Supply of Imported Topsoil meets requirements of Specification Section 720 and Table 720.03, at a minimum depth of 75mm
label | REFERENCE DOCUMENTS: DSG Spec. Cl. 720.03, Table 720.031, Table 720.051
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.8 - Landscape Works (Behind Wall)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Landscaping and/or Grassing as per NOAW Agreements, drawings
label | REFERENCE DOCUMENTS: Notice of Acommodation Works, Drawing 0320-0321
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 3 - Testing
checkpoint | 3.1 - Proof Rolling
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173, before proceeding to subbase construction.
label | ○ The Contractor shall submit a test rolling procedure to the Superintendent including the method of preparing an area for test rolling, the extent of test rolling and a requirement to provide not less than 24 hours notice of the location and commencement time for the test rolling to the Superintendent.
label | REFERENCE DOCUMENTS: 173.03, 204.12
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*, WP
label | RESPONSIBILITY: Site Engineer/ QAV
date | Date Completed:
checkpoint | 3.2 - Materials Property Testing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Refer to Reference Documents for particular Frequency of Testing and Material Properties Testing Requirements.
label | ○ Table 204.161 for Project Specific Scales for each applicable Road Name or Area.
label | REFERENCE DOCUMENTS: Tables 204.141, 204.142, 204.161
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed, Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | QAV - Print Name:
textbox | QAV - Position:
textbox | Fulton Hogan - Print Name:
textbox | Fulton Hogan - Position:
date | Work Completed On:
signoff | Add Signature
checklist | DTM-ITP-014- Water Main Relocation | itp |  |  |  |  | DTM-ITP-014- Water Main Relocation Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 - Obtain the TasWater Engineering Design Approval
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that project drawings are listed on the engineering design approval document and that it has not expired during time of construction
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Pre job-start meeting with TasWater
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Prior to receiving the permit to construct, a pre-start meeting between responsible contractor and TasWater relevant project manager and ground crew is to be held on site.
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Apply for and obtain permit to construct
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: prepare and submit application for a permit to construct no less than 10 business days before commencing any activities.
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Preparation and submission of construction management plan
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Prepare a construction management plan. This must detail how the new TasWater infrastructure will be constructed while maintaining current levels of services provided by TasWater to the community.
label | ○ The construction plan must also include a risk assessment and contingency plans covering major risks to TasWater during any works.
label | ○ The construction plan must be to the satisfaction of TasWater.
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: verify
label | RECORD OF CONFORMITY: This ITP signed off
label | AP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Request and schedule booking for a witness pressure test with TasWater
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: After new section of main is installed, TasWater must witness a pressure test of the new section of main.
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP, HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.6 - Request and schedule the isolation and cuttover to new infrastructure
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: A permit for shutdown must be applied for through the TasWater Application for Development Services portal. A minimum of 2 weeks notice must be given to TasWater before required service isolation so that affected residents and businesses can be made aware through a letter drop
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.7 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.8 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PMP, EMP, TMP, JSEA, SWMS & Work Pack
label | REFERENCE DOCUMENTS: PMP, EMP, TMP, JSEA, SWMS, Work Pack
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Survey Set-Out
label | FREQUENCY: Prior to commencement of excavation
label | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer/ Surveyor
date | Date Completed:
checkpoint | 2.2 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Vacuum excavation of trench
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: As above with excavation permit. Ensure any known and previously proven services are marked on the ground prior to excavation commencing.
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.4 - Installation of pipework (including new property connection).
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pipework is installed as per certified and approved Water Main Relocation design drawings
label | REFERENCE DOCUMENTS: A1071.005 Sheet 0240,0241
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*, WP
label | RESPONSIBILITY:
date | Date Completed:
checkpoint | 2.5 - Installation of thrust blocks (temporary and permanent)
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Thrust blocks are installed as per MRWA-W-204
label | REFERENCE DOCUMENTS: MRWA-W-204
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off, TasWater written approval
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.6 - TasWater Inspection
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Installation of pipes/valves/hydrants/thrust blocks prior to backfill
label | REFERENCE DOCUMENTS: TasWater Permit to Construct
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*, WP
label | RESPONSIBILITY: Site Engineer, TW representative
date | Date Completed:
checkpoint | 2.7 - Back-fill of trench for purpose of pressure testing
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Pipework is back-filled as per A0171.005 using pipe embedment to either WSA-PS-361 if 5mm clean back-fill or WSA-PS-360 if sand to 70% compaction and 20mm crushed rock to 95%R compaction above.
label | REFERENCE DOCUMENTS: A0171.005 Sheet 0240, 0241, WSA-PS-360 OR WSA-PS-361
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off, Delivery dockets, Compaction test results
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.8 - Removal of old section of water main
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Removal of existing water main following successful cuttover to new section of water main. Method of removal will be mechanical excavation.
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*, WP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 3 - Testing
checkpoint | 3.1 - Pressure Testing of new pipework
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Hydrostatic Pressure testing 1.25 times the designed working pressure as claculated by the Supervising Engineer in accordance with section 19.4 of WSA 03-2011-3.1 Water Supply Code of Australia Part 2: Construction Third Version 3.1
label | REFERENCE DOCUMENTS: WSA 03-2011-3.1
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed, Test Records, TasWater written approval
label | TP, WP, HP*
label | RESPONSIBILITY: Site Engineer, TW representative
date | Date Completed:
checkpoint | 3.2 - Cut-Over
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: TasWater to isolate existing watermain to allow for the cut-over from the existing section of water main to new.
label | REFERENCE DOCUMENTS: A1071.005 Sheet 0240,0241
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed, Test Records, TasWater written approval
label | TP, WP, HP*
label | RESPONSIBILITY: Site Engineer, TW representative
date | Date Completed:
checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | QAV - Print Name:
textbox | QAV - Position:
textbox | Fulton Hogan - Print Name:
textbox | Fulton Hogan - Position:
date | Work Completed On:
signoff | Add Signature