## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Tile Wall
section | Details
checkpoint | Check the current revision of drawings, for set out, specification of finishes and extent
checkpoint | Check the waterproofing (by others) – proceed once verified
checkpoint | Load the tiles – check shade numbers and record
checkpoint | Load Materials – Check used by dates and batch
checkpoint | Cut and fit approved trims, finishing angles, install tile spacers and wedges to have tile achieve neat jointing
checkpoint | Apply the grout as per manufacturer's recommendations
checkpoint | Clean internal joints, apply silicone jointing compound
button | Did manufacturer conduct any testing | Yes,No
checklist | Floor Tiles
section | Details
checkpoint | Check the current revision of drawings, for set out, specification of finishes and extent. Check finish heights and locations
checkpoint | Check the waterproofing (by others) – proceed once verified
checkpoint | Load the tiles – check shade numbers and record
checkpoint | Load Materials – Check used by dates and batch
checkpoint | Insert Floor waste protection (test Plug)
checkpoint | Install Acoustic Underlay
checkpoint | Mix mortar Mix to 3:1 mix ratio and screed to falls as per Australian Standards (AS 3958.1)
text | Record if any additives where used
checkpoint | Clean and prime floor , check for 3mm in 3m with straight Edge
checkpoint | Check floor preparation. Ie level or correct falls
checkpoint | Check notch trowel size and ware for use
checkpoint | Cut and fit approved trims, finishing angles
checkpoint | Apply approved grout in accordance with manufacturer’s recommendations
checkpoint | Apply a trade clean to the floor tiling, using fresh water to wash down the tile surface, removing cementitious smear
label | Special note, the tile surface will retain the cementitious smear as tilers sponges retain this
checkpoint | Apply floor protection if required
button | Did adhesive manufacturer conduct any testing | Yes,No
checklist | Pedestals
section | Details
checkpoint | Check the current revision of drawings, for set out, specification of finishes and extent
checkpoint | Check the waterproofing (by others) – proceed once verified
checkpoint | Load the tiles – check shade numbers and record
checkpoint | Load Materials – Check used by dates and batch
checkpoint | Insert floor waste protection
checkpoint | Set out Pedestal locations and spot mark
checkpoint | Cut and fit 200x200 Acoustic underlay to pedestal locations
checkpoint | Locate starting point / set laser up, install pedestals (less thickness of paver)
checkpoint | Fit tiles to the pedestals
checkpoint | Check finish heights and locations and wipe clean
checklist | Main Floors
section | Details
checkpoint | Check the current revision of drawings, for set out, specification of finishes and extent. Check finish heights and locations
checkpoint | Load the tiles – check shade numbers and record
checkpoint | Load Materials – Check used by dates and batch
checkpoint | Install Acoustic Underlay
checkpoint | Clean and prime floor, check for 3mm in 3m with straight Edge
checkpoint | Check floor preparation. Ie level or correct falls
checkpoint | Cut and fit approved trims, finishing angles
checkpoint | Apply approved grout in accordance with manufacturer’s recommendations
checkpoint | Apply a trade clean to the floor tiling, using fresh water to wash down the tile surface, removing cementitious smear
label | Special note, the tile surface will retain the cementitious smear as tilers sponges retain this
checkpoint | Install expansion joint as per Australia Standard (AS 3958.1)
checkpoint | Apply floor protection if required
button | Did adhesive manufacturer conduct any testing | Yes,No
checklist | Lift Lobby
section | Details
checkpoint | Check the current revision of drawings, for set out, specification of finishes and extent. Check finish heights and locations
checkpoint | Load the tiles – check shade numbers and record
checkpoint | Load Materials – Check used by dates and batch
checkpoint | Install Acoustic Underlay
checkpoint | Clean and prime floor, check for 3mm in 3m with straight Edge
checkpoint | Check floor preparation. Ie level or correct falls
checkpoint | Check notch trowel size and ware for use
checkpoint | Cut and fit approved trims, finishing angles
checkpoint | Apply approved grout in accordance with manufacturer’s recommendations
checkpoint | Apply a trade clean to the floor tiling, using fresh water to wash down the tile surface, removing cementitious smear
label | Special note, the tile surface will retain the cementitious smear as tilers sponges retain this
checkpoint | Install expansion joint as per Australia Standard (AS 3958.1)
checkpoint | Apply floor protection if required
button | Did adhesive manufacturer conduct any testing | Yes,No