## ITP Cover Page
Wetland 2 Stormwater Drainage Directional Drilling
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2-019-002 - Rev 0
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Tauriko Enabling Project - SP2 |  |  |  |  | ITP Number: |  |  | SP2-019-002
Project Number: |  |  | DN1210 |  |  |  |  | ITP Status: |  |  | IFC
ITP Description: |  |  | Wetland 2 Stormwater Drainage Directional Drilling |  |  |  |  | Revision: | 1000 |  | 0
Contract Number: |  |  | NZTA 8287 |  |  |  |  | Drawing Sets: |  |  | 232735.02-WSP-DR-STW 0003,00010,0011,0113,0211,0302,0403,0404,0405,0407,0408,0411,0422
Customer: |  |  | Waka Kotahi |  |  |  |  | Specification: |  |  | SM031 project specifications 21.1- 21.7.8
Quality Specified: |  |  | ISO 9001:2015
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
0 | Draft for Approval |  |  | Cordelia Girdler-Brown and Nick Adams | [5 empty] | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM |  | NICK ADAMS | [5 empty] | Downer PM |  | NICK ADAMS
Downer QM |  | CORDELIA GIRDLER-BROWN |  |  |  |  | 21/08/2025 | Downer QM |  | CORDELIA GIRDLER-BROWN
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Wetland 2 Stormwater Drainage Directional Drilling
Project: Tauriko Enabling Project - SP2
Number and Revision: DN1210 - SP2-019-002 - Rev 0
Item No. | Inspection and Test Point | Detail | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Testing Quantity Required (based from schedule qtys) | Verification Activity |  | Downer Conformance of Compliance Signoff
[7 empty] | Activity | By | Downer Signature | Date | Comments / Closeout Details | ENGINEERS COMMENTS - Date: | DOWNER RESPONSE - Date:
SECTION 3 – PRE-CONSTRUCTION HOLD POINTS - MATERIALS, PERSONELL & THIRD PARTY APPROVALS
3.1 | Extent of Line Setout | Ensure line and level of Stormwater has been marked out and agreed with Engineer in accordance with Stormwater drawings. Identify any clashes before construction. Lot - Markup | As Per Drawings & Markup drawing | Design Drawings | ITP Sign Off | Prior to Construction & Every Revision of IFC Drawings/Data. | M | SE
3.2 | Material grading: Materials (Gap65/AP65) | NZS4407:2015, Test 3.8.1 - Particle Size Distribution | No Particles >200mm Maximum fines 10% passing 75micron sieve | Appendix XVIII PS 16.5.5 Appendix V | IANZ Accredited Report | Stockpile Size (m3): 0-400 - 2 tests 400-1,500 - 3 tests 1,500-4,000 - 4 tests >4,000 - 1 test for each additional 1,000m3 Results to Engineer 2 wks before importing | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.3 | Weathering index: Materials (Gap65/AP65) | NZS4407:2015, Test 3.11 - The Weathering Quality Index of Coarse Aggregate | AA, AB, AC, BA, BB, or CA | Appendix XVIII PS 16.5.5 Appendix V | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG | `
3.4 | Crushing Resistance: Materials (Gap65/AP65) | NZS4407:2015, Test 3.10 - The Crushing Resistance of Coarse Aggregate Under a Specified Load | >100KN | Appendix XVIII Appendix V | IANZ Accredited Report | 2 Tests Per Material, Per Source Results to Engineer 2 wks before importing | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.5 | Material grading: Materials (Sand) | Bedding/Side Zone/ Overlay Zone/Embedment Zone | Sieve Size % Passing 19.0mm 85-100% passing 9.5mm 25-55% passing 4.75mm 0-10% passing 2.36mm 0-5% passing 0.075mm 0-2% passing | AS/NZS 2566.2 PS 22.4.5 | Lab Test Report NZS 4407.2015 Test3.8.1 | 0-400m3 2 Test 400-1500m3 3 Test 1500-4000m3 4 Test >4000 1 Test Additional 1000m3 | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.6 | Pipes (PE) | Name of the proposed PE resin, the manufacturer, production information on the properties of resin. Full Traceability information and certification of analysis for the resin batch. | Full Traceability information and certification of Material | PS-22.4.1 (d) AS/NZS 1477 | Delivery Dockets | Prior to construction | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
3.7 | Pipe and fittings. | Confirm diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition. | Confirm diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition. | Design Drawings | Delivery Dockets / Inspection Checksheet | Each Delivery to site | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
[7 empty] | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
[7 empty] | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
3.8 | Granular Material (Sand, GAP65/AP65) | Confirm Specification and material in good condition. | Confirm Specification and material in good condition. | PS-22.4.1 | Delivery Dockets / Inspection Checksheet(DG-QA-TP019) | Each Delivery to site | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
3.9 | Bidim/Geogrid | BIDIM A29 Durogrid 30/30 or similar. | Site Engineer Approval | PS-22.4.1 | Delivery Dockets / Inspection Checksheet(DG-QA-TP019) | Each Delivery to site | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
3.1 | Tracer wire | Lay a conductive signal strip or tracer wire along the full length of all non-metallic pressure pipelines as shown on the Drawings. Mark fire hydrant positions in accordance with SNZ PAS 4509 | Lay a conductive signal strip or tracer wire along the full length of all non-metallic pressure pipelines as shown on the Drawings. Mark fire hydrant positions in accordance with SNZ PAS 4509 | PS 22.7.3 a | Docket | Every Line | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
3.11 | Drilling Fluid mix | Fluid design to be submitted to engineer before start of works. | Fluid design to be submitted to engineer before start of works. | PS 21.6.6 | Visual Inspection | Prior to construction | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
3.12 | Reinforcing steel (Stilling Well) | Wetland 02 Stilling well detail (SDMH11.1.1) | LAPS TO THE 16mm DIAMETER LONGITUDINAL BARS TO BE MIN. 825mm AS REQUIRED. REFER TO CONCRETE SPECIFICATION FOR FURTHER REQUIREMENTS AND HOLD POINTS. DRILL AND FIX 6 No. M30 HDG G8.8 THREADED ROD ANCHOR STUDS WITH NUT AND WASHER USING EPCON C8 EPOXY OR SIMILAR APPROVED. MIN. EMBEDMENT OF 210mm IN CONCRETE PAD. LENGTH TO SUIT MIN. EMBEDMENT AND THICKNESS OF MANHOLE FLANGE BASE. ANCHORS TO BE EQUALLY SPACED. | PS -IFC STW 0411 | Material docket | Each Delivery to site | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
3.13 | Concrete | Wetland 02 Stilling well detail (SDMH11.1.1) | Concrete should have 40MPA 28 day strength | PS -IFC STW 0411 | Material docket | Each Delivery to site | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
3.14 | Stormwater- Structure (SWMH, SDMH) | Confirm diameter, class & jointing type as shown on the drawings, and that the Structure are correct and in good condition. | Confirm diameter and size as shown on the drawings, and that the Structure are correct and in good condition. | PS- 21.5.4 NZS 3109:1997 | Delivery Dockets | Each Delivery to site | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
SECTION 4 –STORMWATER MANHOLE INSTALLATION
4.1 | Foundation Compliance | On Granular or Cohesive Material | Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa | Appendix V Table 21:11 | Shear vane or Scala test result | 1 Test/Manhole | W | SE
4.2 | Undercut approval | On Subgrade | Subgrade CBR between 3.5% <5%: Undercut 150mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between 2% <3.5%: Undercut 300mm and Replace with Compacted AP65 or Approved Granular material. Subgrade CBR between <2%: Engineer to advise or Undercut 450mm and Replace with Compacted AP65 or Approved Granular material. | Table 21.5 | Lab Test Report | If Undercut required | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
4.3 | Undercut Backfill Compliance AP65 | On Granular Material | Average 95% MDD, min >92% OR Clegg 25% CIV | PS- 16.5.12 | Lab Test Report | 1 Test per Undercut | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
4.4 | Bedding Compaction Testing AP65 | On Granular Material | Average 95% MDD, min >92% OR Clegg 25% CIV | PS- 16.5.12 PS- 21.6.11 | Lab Test Report | 1 Test/Manhole | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
4.5 | Stilling Well SDMH 11.1.1 | Wetland 02 Stilling well detail (SDMH11.1.1) | DN1800mm Sump depth>750mm Concrete structure Concrete slab constructed | PS -IFC STW 0411 | Material docket | Each Delivery to site | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
4.6 | Survey | Inspection of Structure | Horizontal Alignment: The permissible deviation of the horizontal alignment between manholes or structures shall be ± 30mm. | PS- 21.7.6 | Survey Data | 1 Test/Manhole | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SV
4.7 | Backfill Compaction Testing | From Overlay layer to the subgrade layer | AP65 Testing to be completed on maximum 200mm lifts of backfill - 92% (Average 95%) of MDD on metal. AP65-Clegg28%CIV | PS- 16.5.12 | Lab Test Report | 4 Density test per layer at Quarter Points around the Structure. | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
4.8 | Inspection | Inspection of Structure | Inspection of Structure prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the Structure. | PS- 21.6.11 | Manhole/Catchpit Record | 1 Checksheet per manhole/catchpit | I | SE
SECTION 5-STORMATER PE PIPELINE CONSTRUCTION
5.1 | Survey | Surveyor to Setout | Horizontal +-100mm Vertical +-200mm | PS-25.13.5 | Survey Data | Every 100m or at Chambers (whichever distance is the lesser) | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SV
6 | STORMWATER PE PIPELINE (Butt-Fusion Welding)
6.1 | Butt-Fusion Welding | Use only semi-automatic or automatic welding machines. Maintain a site record for all butt-fusion welds. The lead welder or supervisor must verify on the site record form that all welds have been made in accordance with the WMS and that the information on the record form is correct. | Site Butt Fusion Welding record to be filled out. (Refer to CWP) WMS Report | Appendix 22. PS 22.9.4 C | Visual Inspection / Butt Fusion welding records checklist. WMS Report | Every Welding Point | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
6.2 | Survey | Inspection of Pipeline Inverts | Horizontal +-100mm Vertical +-200mm | PS-25.13.5 | Survey Data / As-built record | Pipeline invert to be surveyed at chainages as indicated in the drawings. | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE
7 | STORMWATER PIPELINE DIRECTIONAL DRILLING
7.1 | Drilling level checks | Inspection of Pipeline Inverts | Horizontal +-100mm Vertical +-200mm | PS-25.13.5 | Survey Data / As-built record | Pipeline invert to be surveyed at chainages as indicated in the drawings. | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
7.2 | Drilling Fluid Mix | Viscosity record | Pump rate on eam 450L/min | PS 21.6.6 | Viscosity record /checksheet | Every shot | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
7.3 | Correct Reamer used | Reamer size to confirm on site | Reamer size to confirm on site Reamer must be >1000mm | PS 21.6.6 | Checksheet | 1 per drill shot | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
7.4 | Pipe Damage | Damage <10% of wall thickness | Damage <10% of wall thickness | PS 21.6.6 | Visual inspection | Each pipe | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
7.5 | Tracer Wire | Lay a conductive signal strip or tracer wire along the full length of all non-metallic pressure pipelines as shown on the Drawings. Mark fire hydrant positions in accordance with SNZ PAS 4509 | Lay a conductive signal strip or tracer wire along the full length of all non-metallic pressure pipelines as shown on the Drawings. Mark fire hydrant positions in accordance with SNZ PAS 4509 | PS 22.7.3 a | Visual Inspection | Every Line | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
7.6 | Drill Report | Drill reportr to be submitted | Drill reportr to be submitted which shows the all information of the drill works in one report | PS 21.6.6 | Report | Every Line | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
7.7 | Settlement monitoring and ground deformation (Baseline measurements) | Topo survey completed before and after drill shot | Topo survey completed before and after drill shot | PS 21.6.6 | Survey data | Every 6m | HP Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | ENG
SECTION 8 - CCTV
8.1 | CCTV Inspection | CCTV stormwater pipes at completion of trench backfill but prior to final surfacing (pavements, etc.) | Every stormwater pipeline 225mm diameter or greater. | PS- 21.7.6 PS- 21.7.8 | CCTV Report | 1 per line | S | SE
SECTION 9 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
9.1 | As-Builts / Redpen markups | Quality Check on New Works based on the tolerances in RITS | Meets spec and thickness requirements as per drawings | Project Specifications | Red pen markup only | Post works completion of a lot | H Work Shall not proceed past the Hold Point until released by the organisation imposing the Hold Point. | SE