## Sheet 1
|  |  |  | Project: | Wilton Street Foul Sewer |  |  | Lot Number
|  |  |  | Project Location | Winlton Street Invercargill |  |  | Scope Of ITP
|  |  |  | Job # | Contract C1815 |  |  | Sub Contractor |  | N/A
Inspection & Test Plan / Checklist
|  |  |  | Signatory |  | Role |  | Person(s) Responsible
|  |  |  | Requiring FH Signature |  | Site Engineer |  | Brendon Ferguson
| Action | H | Hold Point for Engineers Representative | Requiring FH Manager Representative |  | FH Job Manager |  | Joe Findley
|  | W | Witness | Requiring Engineers Representative |  | Engineers Representative |  | Tom Andersen
|  | H | Hold Point |  |  | Contractors Foreman |  | Navjot Bal
|  | M | Monitor |  |  | Environmental Advisor |  | Ciccone Tweedie
[6 empty] | STMS |  | FH STMS
No: | Inspection / Test Point | ACTION (W, M, H) | Conformance Criteria (What's Required) | Detail | Frequency | Inspection / Test Method | Verification Records | Standard | Signatory | Date(s) | Signature
1.0 Pre-construction
1.1 General
D1.5 | Pre-work site inspection/Existing asset assessment | H | Carry out inspection of existing assets including SWMH01 to assess whether needs replacement | Existing asset assessment completed | Pre-Construction | Inspection | Copy on file | — | Engineers Representative
1.2 Project Plans
D1.19 | Contract Programme | H | The Contractor shall submit to the Engineer an appropriately detailed programme for approval. | — | — | Submission | Approved Contract Programme | — | Engineers Representative
D1.3 | Site Management plan | H | Engineer to accept the CMP prior to any work commencing on site | CMP including safety, quality and environmental plans submitted for approval | Prior to any work commencing on site | Submission | NTC | — | Engineers Representative
C1.7 | Traffic management Plan | H | Approved by road controlling authority | Traffic Management Plan to be approved Pre-construction | Pre-Construction | Submission | TMP on file | — | Engineers Representative
D1.6 | Heritage Authority induction | H | Heritage induction to be completed | All personnel who are undertaking work are required to be present at archaeological induction | Pre-Construction | — | — | — | Engineers Representative
D1.3.3 | Inspection Test plans | H | Approved by the Engineer | The ITP is a Contractor-generated document that outlines the specific inspection and testing requirements used by the Engineer’s Representative to monitor the Contractor’s quality. | Pre-Construction | Submission | NTC,Copy on file | — | Engineers Representative
D1.11 | Residents notification | H | Enginer approved letter distributed 48hrs prior to construction commencing. | Residents notifications completed | Per block | — | Letter on file | — | Engineers Representative
1.3 Service Location/Potholing
D1.8 | Service Plans | H | All Service Plans onsite and understood by all | Apply for BeforeUDig, contact anyone not on BeforeUDig | Pre-Construction | Witness | Plans Onsite & Signed ITP | — | Site Engineer
D1.8 | Service Location Investigation Completed | H | Complete the service locate with the authorised people | Inform Engineer about any significant clash | Pre-Construction | Witness | Plans Onsite & Signed ITP | — | Engineers Representative
2.0 Pre Commencement checks
2.1 Material checks
D1.29.3 | AP 65 Tests | H | In accordance with NZS 4407 | AP65 Subbase particle size and sand equivalent | one initially | Testing | Test result | NZS 4407:1991 | Engineers Representative
D1.29.3 | AP 65 Tests | H | In accordance with NZS 4407 | AP65 Subbase MDD | one initially | Testing | Test result | NZS 4407:1991 | Engineers Representative
D1.29.4 | AP 40 Tests | H | In accordance with NZS 4407 | AP40 Basecourse particle size and sand equivalent | one initially | Testing | Test result | NZS 4407:1991 | Engineers Representative
D1.29.4 | AP 40 Tests | H | In accordance with NZS 4407 | AP40 Basecourse MDD | one initially | Testing | Test result | NZS 4407:1991 | Engineers Representative
D2.4.1 | uPVC pipe visual assessments | H | All pipe to be assessed on delivery to ensure no damage or manufacturing issues | Should meet the requiremnts of AS/NZS 1260 | each pipe length | Visual | Photos/inspection | NZS 1260 | Site Engineer
D2.4.1 | Concrete manhole visual assessments | H | All manholes to be assessed on delivery to ensure no damage or manufacturing issues | Should meet the requiremnts of AS/NZS 3109 | each manhole/riser | Visual | Photos/inspection | NZS 3109 | Site Engineer
3.0 FSMH 25395 - FSMH 25396
D18.3 | FSMH 25395 | W | Location, depth and foundation | The manhole shall be constructed to design depth and location, founded on suitable base of material | Per manhole | Inspection | Photos | — | Site Engineer
D15.3.3 | FSMH 25395 | W | The entry shaft shall not be greater than 500mm | The entry shaft from the top of the proposed manhole lid to the underside of the MH concrete slab, shall not be greater than 500mm. | Per manhole | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25395 (1) | W | Manhole step rungs | The steps shall be installed on the u/s side with the vertical height between steps being 300mm | As required | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25395 (2) | W | Benching and plastering within the structure | Confirm benching/plastering completed to appropriate standard | Per manhole | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25395 (3) | W | External concrete haunching | Corbel poured to suitable depth and width as per typical details | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D18.3 | FSMH 25395 (4) | W | Concrete Ballast | Additional volume of concrete required for anti-flotation ballast if corbel volume does not excced 1.2m3 | Per manhole | Inspection | Photos | — | Site Engineer
D18.3 | 225mmØ Starter pipe | W | Flexible joint | All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure. | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D2.4.1 | 225mm uPVC pipe laying CH0 - CH97 (1) | W | Pipes laid and joined to witness marks | As per AS/NZS 2566.2 Buried flexible pipelines | As required | Inspection | Photos | AS/NZS 2566.2 | Site Engineer
D2.4.1 | 225mm uPVC pipe laying CH0 - CH97 (2) | W | Pipe grade | All pipes laid using calibrated laser to deisgn gradient | As required | Inspection | As built records | — | —
D2.7.6 | Bedding material (1) | W | Well graded granular material complying with table G3.AS/NZS 2566.2 | Particle size distribition from material test report | as required | Testing | Test result | AS/NZS 2566.2 | Site Engineer
D2.7.6 | Bedding material (2) | W | Pipe embedment | Bedding material shall be compacted adequately and uniformly and meet the requirements of Type 3 support detail in Fig. D24 and requirements of NZS 2566 | Layer depth as required | Inspection | Onsite inspections | AS/NZS 2566 | Site Engineer
D2.7.7 | Sub base | W | Layer thickness | Uncompacted thickness should be less than 200mm | Layer depth as required | Inspection | Onsite inspections | — | Site Engineer
D2.7.7.1 | Sub base | W | NDM Testing | At every 120m intervals for open trench at every layer | At 120m | Testing | Test Result | — | Engineers Representative
D2.7.7.2 | Base course | W | Layer thickness | Basecourse layer shall be minimum of 150mm depth | Layer depth as required | Inspection | Onsite inspections | NZTA B/2 | Site Engineer
D2.7.7.1 | Base course | W | Clegg hammer testing | At every 6m intervals for open trench | At every 6m | Testing | Test Result | — | Engineers Representative
D2.7.7.2 | Base course | W | NDM Testing | At every 20m intervals for open trench at every layer | At 20m | Testing | Test Result | NZTA B/2 | Engineers Representative
D4.4.2 | Service connection to property 132 Bourke Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 132 Bourke Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 8 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 8 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 12 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 12 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 129 George Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 129 George Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D2.9.2 | Pressure testing | H | Pressure testing of mainline | Contractor shall undertake pressure testing of sewer main | As required | Testing | Test Result | NZS 2566.2 | Engineers Representative
D2.9.3 | CCTV inspection | H | Flushing, cleaning and CCTV | Contractor shall undertake cleaning and CCTV inspection of all new gravity mains as per the New Zealand Pipe Inspection Manual. | As required | CCTV | CCTV report | New zealand inspection manual | Engineers Representative
D9.6 | Kerb and Channel | W | Kerb and channel reinstatement | Kerb and channel to be prepared and staked for laying, and installed as per ICC specification | As required | Inspection | Photos | — | Site Engineer
D9.6.2 | Kerb and Channel | H | Compaction testing | Kerb and channel prep to be clegg tested at 10m intervals to a CIV of 35 | At every 10m | Inspection | Test result | — | Engineers Representative
D2.8.3,D2.8.2 | Surface Reinstatement | H | Engineer's Approval | Mark out the trench including overcuts | Prior to surfacing | Inspection | Email | — | Engineers Representative
D1.24 | Engineer's inspections | H | Inspection report | Enginer's inspection for pipe, concrete pre pour, pre sealing. Minimum 2 working days notice for inspection requirements | As required | Inspection | Email | — | Engineers Representative
4.0 FSMH 25396 - FSMH 25397
D18.3 | FSMH 25396 | W | Location, depth and foundation | The manhole shall be constructed to design depth and location, founded on suitable base of material | Per manhole | Inspection | Photos | — | Site Engineer
D15.3.3 | FSMH 25396 | W | The entry shaft shall not be greater than 500mm | The entry shaft from the top of the proposed manhole lid to the underside of the MH concrete slab, shall not be greater than 500mm. | Per manhole | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25396 (1) | W | Manhole step rungs | The steps shall be installed on the u/s side with the vertical height between steps being 300mm | As required | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25396 (2) | W | Benching and plastering within the structure | Confirm benching/plastering completed to appropriate standard | Per manhole | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25396 (3) | W | External concrete haunching | Corbel poured to suitable depth and width as per typical details | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D18.3 | FSMH 25396 (4) | W | Concrete Ballast | Additional volume of concrete required for anti-flotation ballast if corbel volume does not excced 1.2m3 | Per manhole | Inspection | Photos | — | Site Engineer
D18.3 | 225mmØ finisher pipe | W | Flexible joint | All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure. | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D18.3 | 225mmØ Starter pipe | W | Flexible joint | All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure. | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D2.4.1 | 225mm uPVC pipe laying CH97 - CH137 (1) | W | As per AS/NZS 2566.2 Buried flexible pipelines | Pipes laid and joined to witness marks | As required | Inspection | Photos | AS/NZS 2566.2 | Site Engineer
D2.4.1 | 225mm uPVC pipe laying CH97 - CH137 (2) | W | Pipe grade | All pipes laid using calibrated laser to deisgn gradient | As required | Inspection | As built records | — | —
D2.7.6 | Bedding material (1) | W | Well graded granular material complying with table G3.AS/NZS 2566.2 | Particle size distribition from material test report | as required | Testing | Test result | AS/NZS 2566.2 | Site Engineer
D2.7.6 | Bedding material (2) | W | Pipe embedment | Bedding material shall be compacted adequately and uniformly and meet the requirements of Type 3 support detail in Fig. D24 and requirements of NZS 2566 | Layer depth as required | Inspection | Onsite inspections | AS/NZS 2566 | Site Engineer
D2.7.7 | Sub base | W | Layer thickness | Uncompacted thickness should be less than 200mm | Layer depth as required | Inspection | Onsite inspections | — | Site Engineer
D2.7.7.1 | Sub base | W | NDM Testing | At every 120m intervals for open trench at every layer | At 120m | Testing | Test Result | — | Engineers Representative
D2.7.7.2 | Base course | W | Layer thickness | Basecourse layer shall be minimum of 150mm depth | Layer depth as required | Inspection | Onsite inspections | NZTA B/2 | Site Engineer
D2.7.7.1 | Base course | W | Clegg hammer testing | At every 6m intervals for open trench | At every 6m | Testing | Test Result | — | Engineers Representative
D2.7.7.2 | Base course | W | NDM Testing | At every 20m intervals for open trench at every layer | At 20m | Testing | Test Result | NZTA B/2 | Engineers Representative
D4.4.2 | Service connection to property 128 George Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 128 George Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 126 George Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 126 George Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D2.7.4.1 | Watermain service support CH103 | W | Watermain support | Concrete haunching and sand fill around cast iron watermain crossing sewer trench as per typical detail D26 | Per crossing | Inspection | Photos | — | Site Engineer
D2.9.2 | Pressure testing | H | Pressure testing of mainline | Contractor shall undertake pressure testing of sewer main | As required | Testing | Test Result | NZS 2566.2 | Engineers Representative
D2.9.3 | CCTV inspection | H | Flushing, cleaning and CCTV | Contractor shall undertake cleaning and CCTV inspection of all new gravity mains as per the New Zealand Pipe Inspection Manual. | As required | CCTV | CCTV report | New zealand inspection manual | Engineers Representative
D9.6 | Kerb and Channel | W | Kerb and channel reinstatement | Kerb and channel to be prepared and staked for laying, and installed as per ICC specification | As required | Inspection | Photos | — | Site Engineer
D9.6.2 | Kerb and Channel | H | Compaction testing | Kerb and channel prep to be clegg tested at 10m intervals to a CIV of 35 | At every 10m | Inspection | Test result | — | Engineers Representative
D2.8.3,D2.8.2 | Surface Reinstatement | H | Engineer's Approval | Mark out the trench including overcuts | Prior to surfacing | Inspection | Email | — | Engineers Representative
D1.24 | Engineer's inspections | H | Inspection report | Enginer's inspection for pipe, concrete pre pour, pre sealing. Minimum 2 working days notice for inspection requirements | As required | Inspection | Email | — | Engineers Representative
5.0 FSMH 25397 - FSMH 25398
D18.3 | FSMH 25397 | W | Location, depth and foundation | The manhole shall be constructed to design depth and location, founded on suitable base of material | Per manhole | Inspection | Photos | — | Site Engineer
D15.3.3 | FSMH 25397 | W | The entry shaft shall not be greater than 500mm | The entry shaft from the top of the proposed manhole lid to the underside of the MH concrete slab, shall not be greater than 500mm. | Per manhole | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25397 (1) | W | Manhole step rungs | The steps shall be installed on the u/s side with the vertical height between steps being 300mm | As required | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25397 (2) | W | Benching and plastering within the structure | Confirm benching/plastering completed to appropriate standard | Per manhole | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25397 (3) | W | External concrete haunching | Corbel poured to suitable depth and width as per typical details | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D18.3 | FSMH 25397 (4) | W | Concrete Ballast | Additional volume of concrete required for anti-flotation ballast if corbel volume does not excced 1.2m3 | Per manhole | Inspection | Photos | — | Site Engineer
D18.3 | 225mmØ finisher pipe | W | Flexible joint | All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure. | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D18.3 | 225mmØ Starter pipe | W | Flexible joint | All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure. | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D2.4.1 | 225mm uPVC pipe laying CH137 - CH192 (1) | W | As per AS/NZS 2566.2 Buried flexible pipelines | Pipes laid and joined to witness marks | As required | Inspection | Photos | AS/NZS 2566.2 | Site Engineer
D2.4.1 | 225mm uPVC pipe laying CH137 - CH192 (2) | W | Pipe grade | All pipes laid using calibrated laser to deisgn gradient | As required | Inspection | As built records | — | —
D2.7.6 | Bedding material (1) | W | Well graded granular material complying with table G3.AS/NZS 2566.2 | Particle size distribition from material test report | as required | Testing | Test result | AS/NZS 2566.2 | Site Engineer
D2.7.6 | Bedding material (2) | W | Pipe embedment | Bedding material shall be compacted adequately and uniformly and meet the requirements of Type 3 support detail in Fig. D24 and requirements of NZS 2566 | Layer depth as required | Inspection | Onsite inspections | AS/NZS 2566 | Site Engineer
D2.7.7 | Sub base | W | Layer thickness | Uncompacted thickness should be less than 200mm | Layer depth as required | Inspection | Onsite inspections | — | Site Engineer
D2.7.7.1 | Sub base | W | NDM Testing | At every 120m intervals for open trench at every layer | At 120m | Testing | Test Result | — | Engineers Representative
D2.7.7.2 | Base course | W | Layer thickness | Basecourse layer shall be minimum of 150mm depth | Layer depth as required | Inspection | Onsite inspections | NZTA B/2 | Site Engineer
D2.7.7.1 | Base course | W | Clegg hammer testing | At every 6m intervals for open trench | At every 6m | Testing | Test Result | — | Engineers Representative
D2.7.7.2 | Base course | W | NDM Testing | At every 20m intervals for open trench at every layer | At 20m | Testing | Test Result | NZTA B/2 | Engineers Representative
D4.4.2 | Service connection to property 127 Catherine Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 127 Catherine Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D2.9.2 | Pressure testing | H | Pressure testing of mainline | Contractor shall undertake pressure testing of sewer main | As required | Testing | Test Result | NZS 2566.2 | Engineers Representative
D2.9.3 | CCTV inspection | H | Flushing, cleaning and CCTV | Contractor shall undertake cleaning and CCTV inspection of all new gravity mains as per the New Zealand Pipe Inspection Manual. | As required | CCTV | CCTV report | New zealand inspection manual | Engineers Representative
D9.6 | Kerb and Channel | W | Kerb and channel reinstatement | Kerb and channel to be prepared and staked for laying, and installed as per ICC specification | As required | Inspection | Photos | — | Site Engineer
D9.6.2 | Kerb and Channel | H | Compaction testing | Kerb and channel prep to be clegg tested at 10m intervals to a CIV of 35 | At every 10m | Inspection | Test result | — | Engineers Representative
D2.8.3,D2.8.2 | Surface Reinstatement | H | Engineer's Approval | Mark out the trench including overcuts | Prior to surfacing | Inspection | Email | — | Engineers Representative
D1.24 | Engineer's inspections | H | Inspection report | Enginer's inspection for pipe, concrete pre pour, pre sealing. Minimum 2 working days notice for inspection requirements | As required | Inspection | Email | — | Engineers Representative
6.0 FSMH 25398 - FSMH 25399
D18.3 | FSMH 25398 | W | Location, depth and foundation | The manhole shall be constructed to design depth and location, founded on suitable base of material | Per manhole | Inspection | Photos | — | Site Engineer
D15.3.3 | FSMH 25398 | W | The entry shaft shall not be greater than 500mm | The entry shaft from the top of the proposed manhole lid to the underside of the MH concrete slab, shall not be greater than 500mm. | Per manhole | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25398 (1) | W | Manhole step rungs | The steps shall be installed on the u/s side with the vertical height between steps being 300mm | As required | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25398 (2) | W | Benching and plastering within the structure | Confirm benching/plastering completed to appropriate standard | Per manhole | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25398 (3) | W | External concrete haunching | Corbel poured to suitable depth and width as per typical details | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D18.3 | FSMH 25398 (4) | W | Concrete Ballast | Additional volume of concrete required for anti-flotation ballast if corbel volume does not excced 1.2m3 | Per manhole | Inspection | Photos | — | Site Engineer
D18.3 | 225mmØ finisher pipe | W | Flexible joint | All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure. | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D18.3 | 225mmØ Starter pipe | W | Flexible joint | All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure. | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D2.4.1 | 225mm uPVC pipe laying CH192 - CH295 (1) | W | As per AS/NZS 2566.2 Buried flexible pipelines | Pipes laid and joined to witness marks | As required | Inspection | Photos | AS/NZS 2566.2 | Site Engineer
D2.4.1 | 225mm uPVC pipe laying CH192 - CH295 (2) | W | Pipe grade | All pipes laid using calibrated laser to deisgn gradient | As required | Inspection | As built records | — | —
D2.7.6 | Bedding material (1) | W | Well graded granular material complying with table G3.AS/NZS 2566.2 | Particle size distribition from material test report | as required | Testing | Test result | AS/NZS 2566.2 | Site Engineer
D2.7.6 | Bedding material (2) | W | Pipe embedment | Bedding material shall be compacted adequately and uniformly and meet the requirements of Type 3 support detail in Fig. D24 and requirements of NZS 2566 | Layer depth as required | Inspection | Onsite inspections | AS/NZS 2566 | Site Engineer
D2.7.7 | Sub base | W | Layer thickness | Uncompacted thickness should be less than 200mm | Layer depth as required | Inspection | Onsite inspections | — | Site Engineer
D2.7.7.1 | Sub base | W | NDM Testing | At every 120m intervals for open trench at every layer | At 120m | Testing | Test Result | — | Engineers Representative
D2.7.7.2 | Base course | W | Layer thickness | Basecourse layer shall be minimum of 150mm depth | Layer depth as required | Inspection | Onsite inspections | NZTA B/2 | Site Engineer
D2.7.7.1 | Base course | W | Clegg hammer testing | At every 6m intervals for open trench | At every 6m | Testing | Test Result | — | Engineers Representative
D2.7.7.2 | Base course | W | NDM Testing | At every 20m intervals for open trench at every layer | At 20m | Testing | Test Result | NZTA B/2 | Engineers Representative
D2.7.4.1 | Watermain service support CH198 | W | Watermain support | Concrete haunching and sand fill around cast iron watermain crossing sewer trench as per typical detail D26 | Per crossing | Inspection | Photos | — | Site Engineer
D4.4.2 | Service connection to property 126 Catherine Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 126 Catherine Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 40 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 40 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 47 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 47 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D2.7.4.1 | Watermain service support CH293 | W | Watermain support | Concrete haunching and sand fill around cast iron watermain crossing sewer trench as per typical detail D26 | Per crossing | Inspection | Photos | — | Site Engineer
D2.9.2 | Pressure testing | H | Pressure testing of mainline | Contractor shall undertake pressure testing of sewer main | As required | Testing | Test Result | NZS 2566.2 | Engineers Representative
D2.9.3 | CCTV inspection | H | Flushing, cleaning and CCTV | Contractor shall undertake cleaning and CCTV inspection of all new gravity mains as per the New Zealand Pipe Inspection Manual. | As required | CCTV | CCTV report | New zealand inspection manual | Engineers Representative
D9.6 | Kerb and Channel | W | Kerb and channel reinstatement | Kerb and channel to be prepared and staked for laying, and installed as per ICC specification | As required | Inspection | Photos | — | Site Engineer
D9.6.2 | Kerb and Channel | H | Compaction testing | Kerb and channel prep to be clegg tested at 10m intervals to a CIV of 35 | At every 10m | Inspection | Test result | — | Engineers Representative
D2.8.3,D2.8.2 | Surface Reinstatement | H | Engineer's Approval | Mark out the trench including overcuts | Prior to surfacing | Inspection | Email | — | Engineers Representative
D1.24 | Engineer's inspections | H | Inspection report | Enginer's inspection for pipe, concrete pre pour, pre sealing. Minimum 2 working days notice for inspection requirements | As required | Inspection | Email | — | Engineers Representative
7.0 FSMH 25399 - FSMH 25401
D18.3 | FSMH 25399 | W | Location, depth and foundation | The manhole shall be constructed to design depth and location, founded on suitable base of material | Per manhole | Inspection | Photos | — | Site Engineer
D15.3.3 | FSMH 25399 | W | The entry shaft shall not be greater than 500mm | The entry shaft from the top of the proposed manhole lid to the underside of the MH concrete slab, shall not be greater than 500mm. | Per manhole | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25399 (1) | W | Manhole step rungs | The steps shall be installed on the u/s side with the vertical height between steps being 300mm | As required | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25399 (2) | W | Benching and plastering within the structure | Confirm benching/plastering completed to appropriate standard | Per manhole | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25399 (3) | W | External concrete haunching | Corbel poured to suitable depth and width as per typical details | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D18.3 | FSMH 25399 (4) | W | Concrete Ballast | Additional volume of concrete required for anti-flotation ballast if corbel volume does not excced 1.2m3 | Per manhole | Inspection | Photos | — | Site Engineer
D18.3 | 225mmØ finisher pipe | W | Flexible joint | All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure. | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D18.3 | 150mmØ Starter pipe | W | Flexible joint | All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure. | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D2.4.1 | 150mm uPVC pipe laying CH295 - CH384 (1) | W | As per AS/NZS 2566.2 Buried flexible pipelines | Pipes laid and joined to witness marks | As required | Inspection | Photos | AS/NZS 2566.2 | Site Engineer
D2.4.1 | 150mm uPVC pipe laying CH295 - CH384 (2) | W | Pipe grade | All pipes laid using calibrated laser to deisgn gradient | As required | Inspection | As built records | — | —
D2.7.6 | Bedding material (1) | W | Well graded granular material complying with table G3.AS/NZS 2566.2 | Particle size distribition from material test report | as required | Testing | Test result | AS/NZS 2566.2 | Site Engineer
D2.7.6 | Bedding material (2) | W | Pipe embedment | Bedding material shall be compacted adequately and uniformly and meet the requirements of Type 3 support detail in Fig. D24 and requirements of NZS 2566 | Layer depth as required | Inspection | Onsite inspections | AS/NZS 2566 | Site Engineer
D2.7.7 | Sub base | W | Layer thickness | Uncompacted thickness should be less than 200mm | Layer depth as required | Inspection | Onsite inspections | — | Site Engineer
D2.7.7.1 | Sub base | W | NDM Testing | At every 120m intervals for open trench at every layer | At 120m | Testing | Test Result | — | Engineers Representative
D2.7.7.2 | Base course | W | Layer thickness | Basecourse layer shall be minimum of 150mm depth | Layer depth as required | Inspection | Onsite inspections | NZTA B/2 | Site Engineer
D2.7.7.1 | Base course | W | Clegg hammer testing | At every 6m intervals for open trench | At every 6m | Testing | Test Result | — | Engineers Representative
D2.7.7.2 | Base course | W | NDM Testing | At every 20m intervals for open trench at every layer | At 20m | Testing | Test Result | NZTA B/2 | Engineers Representative
D2.7.4.1 | Watermain service support CH302 | W | Watermain support | Concrete haunching and sand fill around cast iron watermain crossing sewer trench as per typical detail D26 | Per crossing | Inspection | Photos | — | Site Engineer
D2.7.4.1 | Watermain service support CH312 | W | Watermain support | Concrete haunching and sand fill around cast iron watermain crossing sewer trench as per typical detail D26 | Per crossing | Inspection | Photos | — | Site Engineer
D4.4.2 | Service connection to property 340 Herbert Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 340 Herbert Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 57 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 57 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 56 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 56 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 59 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 59 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 58 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 58 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 60 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 60 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 64 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 64 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 64 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Potentially redundant/double up
D4.4.3 | Service connection to property 64 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | —
D4.4.2 | Service connection to property 65 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 65 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D2.9.2 | Pressure testing | H | Pressure testing of mainline | Contractor shall undertake pressure testing of sewer main | As required | Testing | Test Result | NZS 2566.2 | Engineers Representative
D2.9.3 | CCTV inspection | H | Flushing, cleaning and CCTV | Contractor shall undertake cleaning and CCTV inspection of all new gravity mains as per the New Zealand Pipe Inspection Manual. | As required | CCTV | CCTV report | New zealand inspection manual | Engineers Representative
D9.6 | Kerb and Channel | W | Kerb and channel reinstatement | Kerb and channel to be prepared and staked for laying, and installed as per ICC specification | As required | Inspection | Photos | — | Site Engineer
D9.6.2 | Kerb and Channel | H | Compaction testing | Kerb and channel prep to be clegg tested at 10m intervals to a CIV of 35 | At every 10m | Inspection | Test result | — | Engineers Representative
D2.8.3,D2.8.2 | Surface Reinstatement | H | Engineer's Approval | Mark out the trench including overcuts | Prior to surfacing | Inspection | Email | — | Engineers Representative
D1.24 | Engineer's inspections | H | Inspection report | Enginer's inspection for pipe, concrete pre pour, pre sealing. Minimum 2 working days notice for inspection requirements | As required | Inspection | Email | — | Engineers Representative
8.0 FSMH 25401 - FSMH 25400
D18.3 | FSMH 25401 | W | Location, depth and foundation | The manhole shall be constructed to design depth and location, founded on suitable base of material | Per manhole | Inspection | Photos | — | Site Engineer
D15.3.3 | FSMH 25401 | W | The entry shaft shall not be greater than 500mm | The entry shaft from the top of the proposed manhole lid to the underside of the MH concrete slab, shall not be greater than 500mm. | Per manhole | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25401 (1) | W | Manhole step rungs | The steps shall be installed on the u/s side with the vertical height between steps being 300mm | As required | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25401 (2) | W | Benching and plastering within the structure | Confirm benching/plastering completed to appropriate standard | Per manhole | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25401 (3) | W | External concrete haunching | Corbel poured to suitable depth and width as per typical details | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D18.3 | FSMH 25401 (4) | W | Concrete Ballast | Additional volume of concrete required for anti-flotation ballast if corbel volume does not excced 1.2m3 | Per manhole | Inspection | Photos | — | Site Engineer
D18.3 | 150mmØ finisher pipe | W | Flexible joint | All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure. | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D18.3 | 150mmØ Starter pipe | W | Flexible joint | All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure. | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D2.4.1 | 150mm uPVC pipe laying CH384 - CH510 (1) | W | As per AS/NZS 2566.2 Buried flexible pipelines | Pipes laid and joined to witness marks | As required | Inspection | Photos | AS/NZS 2566.2 | Site Engineer
D2.4.1 | 150mm uPVC pipe laying CH384 - CH510 (2) | W | Pipe grade | All pipes laid using calibrated laser to deisgn gradient | As required | Inspection | As built records | — | —
D2.7.6 | Bedding material (1) | W | Well graded granular material complying with table G3.AS/NZS 2566.2 | Particle size distribition from material test report | as required | Testing | Test result | AS/NZS 2566.2 | Site Engineer
D2.7.6 | Bedding material (2) | W | Pipe embedment | Bedding material shall be compacted adequately and uniformly and meet the requirements of Type 3 support detail in Fig. D24 and requirements of NZS 2566 | Layer depth as required | Inspection | Onsite inspections | AS/NZS 2566 | Site Engineer
D2.7.7 | Sub base | W | Layer thickness | Uncompacted thickness should be less than 200mm | Layer depth as required | Inspection | Onsite inspections | — | Site Engineer
D2.7.7.1 | Sub base | W | NDM Testing | At every 120m intervals for open trench at every layer | At 120m | Testing | Test Result | — | Engineers Representative
D2.7.7.2 | Base course | W | Layer thickness | Basecourse layer shall be minimum of 150mm depth | Layer depth as required | Inspection | Onsite inspections | NZTA B/2 | Site Engineer
D2.7.7.1 | Base course | W | Clegg hammer testing | At every 6m intervals for open trench | At every 6m | Testing | Test Result | — | Engineers Representative
D2.7.7.2 | Base course | W | NDM Testing | At every 20m intervals for open trench at every layer | At 20m | Testing | Test Result | NZTA B/2 | Engineers Representative
D4.4.2 | Service connection to property 66 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Potentially redundant/double up
D4.4.3 | Service connection to property 66 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | —
D4.4.2 | Service connection to property 67 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 67 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 70 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 70 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 71 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 71 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 74 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 74 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 75 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 75 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 76 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 76 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 77 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 77 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 78 Wilton Street | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 78 Wilton Street | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.2 | Service connection to property 79 Wilton Street/123 Chelmsford Street (shared) | W | Connection to main and riser | Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends | Each property | Inspection | Individual inspection sheet | — | Site Engineer
D4.4.3 | Service connection to property 79 Wilton Street/123 Chelmsford Street (shared) | W | Service lateral | Laid at minimum 1 in 100 grade and minimum 1m depth at boundary | As required | Inspection | Individual inspection sheet | — | Site Engineer
D18.3 | New FS Maintenance Shaft F20804 | W | Location, depth and foundation | Maintenance shaft shall be constructed to design depth and location, founded on suitable base of material | Per feature | Inspection | Photos | — | Site Engineer
D15.3.3 | New FS Maintenance Shaft F20804 | W | Depth of top of shaft under cap | The entry pipe to the shaft is to be within 100 to 150mm from the surface level | Per feature | Inspection | Individual inspection sheet | Fig. D22 | Site Engineer
D18.3 | FSMH 25400 | W | Location, depth and foundation | The manhole shall be constructed to design depth and location, founded on suitable base of material | Per manhole | Inspection | Photos | — | Site Engineer
D15.3.3 | FSMH 25400 | W | The entry shaft shall not be greater than 500mm | The entry shaft from the top of the proposed manhole lid to the underside of the MH concrete slab, shall not be greater than 500mm. | Per manhole | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25400 (1) | W | Manhole step rungs | The steps shall be installed on the u/s side with the vertical height between steps being 300mm | As required | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25400 (2) | W | Benching and plastering within the structure | Confirm benching/plastering completed to appropriate standard | Per manhole | Inspection | Individual inspection sheet | Fig. D15 | Site Engineer
D18.3 | FSMH 25400 (3) | W | External concrete haunching | Corbel poured to suitable depth and width as per typical details | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D18.3 | FSMH 25400 (4) | W | Concrete Ballast | Additional volume of concrete required for anti-flotation ballast if corbel volume does not excced 1.2m3 | Per manhole | Inspection | Photos | — | Site Engineer
D18.3 | 150mmØ finisher pipe | W | Flexible joint | All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure. | Per connection | Inspection | Photos | Fig. D15 | Site Engineer
D2.9.2 | Pressure testing | H | Pressure testing of mainline | Contractor shall undertake pressure testing of sewer main | As required | Testing | Test Result | NZS 2566.2 | Engineers Representative
D2.9.3 | CCTV inspection | H | Flushing, cleaning and CCTV | Contractor shall undertake cleaning and CCTV inspection of all new gravity mains as per the New Zealand Pipe Inspection Manual. | As required | CCTV | CCTV report | New zealand inspection manual | Engineers Representative
D9.6 | Kerb and Channel | W | Kerb and channel reinstatement | Kerb and channel to be prepared and staked for laying, and installed as per ICC specification | As required | Inspection | Photos | — | Site Engineer
D9.6.2 | Kerb and Channel | H | Compaction testing | Kerb and channel prep to be clegg tested at 10m intervals to a CIV of 35 | At every 10m | Inspection | Test result | — | Engineers Representative
D2.8.3,D2.8.2 | Surface Reinstatement | H | Engineer's Approval | Mark out the trench including overcuts | Prior to surfacing | Inspection | Email | — | Engineers Representative
D1.24 | Engineer's inspections | H | Inspection report | Enginer's inspection for pipe, concrete pre pour, pre sealing. Minimum 2 working days notice for inspection requirements | As required | Inspection | Email | — | Engineers Representative
9.0 Completion documents
D17.2 | As-built | H | Ensure as-built data recorded and submitted | Red pen markup drawing | At completion | Submission | As built drawings/markup | — | Engineers Representative
D17.2 | PS3 submission | H | Producer statement for construction to be supplied to client | As per schedule 6 3910:2013 | Prior to PCC application | Submission | Email of notice | — | Engineers Representative
D17.2 | WCN and CAR close out | H | To be submitted at completion of works | Submission to ICC of completion of works in road corridor and close out of CAR | Prior to PCC application | Submission | PS3 document | — | Engineers Representative
D17.2 | QA documents submitted | H | All required documents submitted throughout and at conclusion of project | All connection sheets, NDM results, encountered services sheets, construction photographs, any outstanding H&S or non conformance reporting | Prior to PCC application | Submission | Various | — | Engineers Representative
Accepted By :_____________________________________________ |  |  | Sub-contractor | Accepted By :_____________________________________________ |  | Project Manager |  | Accepted By :_____________________________________________ |  |  |  | Quality Manager
Signature:_____________________________ |  |  |  | Signature:________________________________________________ |  |  |  | Signature:________________________________________________