## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | 1.0 Pre-construction | itp |  |  |  |  | ITP - Wilton Street (1.0 Pre-construction)
section | 1.1 General
checkpoint | D1.5 - Pre-work site inspection/Existing asset assessment
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Carry out inspection of existing assets including SWMH01 to assess whether needs replacement
label | Detail - Existing asset assessment completed
label | Frequency - Pre-Construction
label | Inspection / Test Method - Inspection
label | Verification Records - Copy on file
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
section | 1.2 Project Plans
checkpoint | D1.19 - Contract Programme
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - The Contractor shall submit to the Engineer an appropriately detailed programme for approval.
label | Inspection / Test Method - Submission
label | Verification Records - Approved Contract Programme
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D1.3 - Site Management plan
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Engineer to accept the CMP prior to any work commencing on site
label | Detail - CMP including safety, quality and environmental plans submitted for approval
label | Frequency - Prior to any work commencing on site
label | Inspection / Test Method - Submission
label | Verification Records - NTC
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | C1.7 - Traffic management Plan
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Approved by road controlling authority
label | Detail - Traffic Management Plan to be approved Pre-construction
label | Frequency - Pre-Construction
label | Inspection / Test Method - Submission
label | Verification Records - TMP on file
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D1.6 - Heritage Authority induction
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Heritage induction to be completed
label | Detail - All personnel who are undertaking work are required to be present at archaeological induction
label | Frequency - Pre-Construction
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D1.3.3 - Inspection Test plans
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Approved by the Engineer
label | Detail - The ITP is a Contractor-generated document that outlines the specific inspection and testing requirements used by the Engineer’s Representative to monitor the Contractor’s quality.
label | Frequency - Pre-Construction
label | Inspection / Test Method - Submission
label | Verification Records - NTC,Copy on file
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D1.11 - Residents notification
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Enginer approved letter distributed 48hrs prior to construction commencing.
label | Detail - Residents notifications completed
label | Frequency - Per block
label | Verification Records - Letter on file
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
section | 1.3 Service Location/Potholing
checkpoint | D1.8 - Service Plans
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - All Service Plans onsite and understood by all
label | Detail - Apply for BeforeUDig, contact anyone not on BeforeUDig
label | Frequency - Pre-Construction
label | Inspection / Test Method - Witness
label | Verification Records - Plans Onsite & Signed ITP
label | Signatory - Site Engineer
holdpoint | HOLD POINT
checkpoint | D1.8 - Service Location Investigation Completed
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Complete the service locate with the authorised people
label | Detail - Inform Engineer about any significant clash
label | Frequency - Pre-Construction
label | Inspection / Test Method - Witness
label | Verification Records - Plans Onsite & Signed ITP
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checklist | 2.0 Pre Commencement checks | itp |  |  |  |  | ITP - Wilton Street (2.0 Pre Commencement checks)
section | 2.1 Material checks
checkpoint | D1.29.3 - AP 65 Tests
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - In accordance with NZS 4407
label | Detail - AP65 Subbase particle size and sand equivalent
label | Frequency - one initially
label | Inspection / Test Method - Testing
label | Verification Records - Test result
label | Standard - NZS 4407:1991
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D1.29.3 - AP 65 Tests
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - In accordance with NZS 4407
label | Detail - AP65 Subbase MDD
label | Frequency - one initially
label | Inspection / Test Method - Testing
label | Verification Records - Test result
label | Standard - NZS 4407:1991
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D1.29.4 - AP 40 Tests
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - In accordance with NZS 4407
label | Detail - AP40 Basecourse particle size and sand equivalent
label | Frequency - one initially
label | Inspection / Test Method - Testing
label | Verification Records - Test result
label | Standard - NZS 4407:1991
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D1.29.4 - AP 40 Tests
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - In accordance with NZS 4407
label | Detail - AP40 Basecourse MDD
label | Frequency - one initially
label | Inspection / Test Method - Testing
label | Verification Records - Test result
label | Standard - NZS 4407:1991
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D2.4.1 - uPVC pipe visual assessments
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - All pipe to be assessed on delivery to ensure no damage or manufacturing issues
label | Detail - Should meet the requiremnts of AS/NZS 1260
label | Frequency - each pipe length
label | Inspection / Test Method - Visual
label | Verification Records - Photos/inspection
label | Standard - NZS 1260
label | Signatory - Site Engineer
holdpoint | HOLD POINT
checkpoint | D2.4.1 - Concrete manhole visual assessments
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - All manholes to be assessed on delivery to ensure no damage or manufacturing issues
label | Detail - Should meet the requiremnts of AS/NZS 3109
label | Frequency - each manhole/riser
label | Inspection / Test Method - Visual
label | Verification Records - Photos/inspection
label | Standard - NZS 3109
label | Signatory - Site Engineer
holdpoint | HOLD POINT
checklist | 3.0 FSMH 25395 - FSMH 25396 | itp |  |  |  |  | ITP - Wilton Street (3.0 FSMH 25395 - FSMH 25396)
section | 3.0 FSMH 25395 - FSMH 25396
checkpoint | D18.3 - FSMH 25395
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Location, depth and foundation
label | Detail - The manhole shall be constructed to design depth and location, founded on suitable base of material
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D15.3.3 - FSMH 25395
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - The entry shaft shall not be greater than 500mm
label | Detail - The entry shaft from the top of the proposed manhole lid to the underside of the MH concrete slab, shall not be greater than 500mm.
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25395 (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Manhole step rungs
label | Detail - The steps shall be installed on the u/s side with the vertical height between steps being 300mm
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25395 (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Benching and plastering within the structure
label | Detail - Confirm benching/plastering completed to appropriate standard
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25395 (3)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - External concrete haunching
label | Detail - Corbel poured to suitable depth and width as per typical details
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25395 (4)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Concrete Ballast
label | Detail - Additional volume of concrete required for anti-flotation ballast if corbel volume does not excced 1.2m3
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D18.3 - 225mmØ Starter pipe
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Flexible joint
label | Detail - All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure.
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D2.4.1 - 225mm uPVC pipe laying CH0 - CH97 (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Pipes laid and joined to witness marks
label | Detail - As per AS/NZS 2566.2 Buried flexible pipelines
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - AS/NZS 2566.2
label | Signatory - Site Engineer
checkpoint | D2.4.1 - 225mm uPVC pipe laying CH0 - CH97 (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Pipe grade
label | Detail - All pipes laid using calibrated laser to deisgn gradient
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - As built records
checkpoint | D2.7.6 - Bedding material (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Well graded granular material complying with table G3.AS/NZS 2566.2
label | Detail - Particle size distribition from material test report
label | Frequency - as required
label | Inspection / Test Method - Testing
label | Verification Records - Test result
label | Standard - AS/NZS 2566.2
label | Signatory - Site Engineer
checkpoint | D2.7.6 - Bedding material (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Pipe embedment
label | Detail - Bedding material shall be compacted adequately and uniformly and meet the requirements of Type 3 support detail in Fig. D24 and requirements of NZS 2566
label | Frequency - Layer depth as required
label | Inspection / Test Method - Inspection
label | Verification Records - Onsite inspections
label | Standard - AS/NZS 2566
label | Signatory - Site Engineer
checkpoint | D2.7.7 - Sub base
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Layer thickness
label | Detail - Uncompacted thickness should be less than 200mm
label | Frequency - Layer depth as required
label | Inspection / Test Method - Inspection
label | Verification Records - Onsite inspections
label | Signatory - Site Engineer
checkpoint | D2.7.7.1 - Sub base
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - NDM Testing
label | Detail - At every 120m intervals for open trench at every layer
label | Frequency - At 120m
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Signatory - Engineers Representative
checkpoint | D2.7.7.2 - Base course
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Layer thickness
label | Detail - Basecourse layer shall be minimum of 150mm depth
label | Frequency - Layer depth as required
label | Inspection / Test Method - Inspection
label | Verification Records - Onsite inspections
label | Standard - NZTA B/2
label | Signatory - Site Engineer
checkpoint | D2.7.7.1 - Base course
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Clegg hammer testing
label | Detail - At every 6m intervals for open trench
label | Frequency - At every 6m
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Signatory - Engineers Representative
checkpoint | D2.7.7.2 - Base course
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - NDM Testing
label | Detail - At every 20m intervals for open trench at every layer
label | Frequency - At 20m
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Standard - NZTA B/2
label | Signatory - Engineers Representative
checkpoint | D4.4.2 - Service connection to property 132 Bourke Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 132 Bourke Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 8 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 8 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 12 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 12 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 129 George Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 129 George Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D2.9.2 - Pressure testing
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Pressure testing of mainline
label | Detail - Contractor shall undertake pressure testing of sewer main
label | Frequency - As required
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Standard - NZS 2566.2
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D2.9.3 - CCTV inspection
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Flushing, cleaning and CCTV
label | Detail - Contractor shall undertake cleaning and CCTV inspection of all new gravity mains as per the New Zealand Pipe Inspection Manual.
label | Frequency - As required
label | Inspection / Test Method - CCTV
label | Verification Records - CCTV report
label | Standard - New zealand inspection manual
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D9.6 - Kerb and Channel
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Kerb and channel reinstatement
label | Detail - Kerb and channel to be prepared and staked for laying, and installed as per ICC specification
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D9.6.2 - Kerb and Channel
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Compaction testing
label | Detail - Kerb and channel prep to be clegg tested at 10m intervals to a CIV of 35
label | Frequency - At every 10m
label | Inspection / Test Method - Inspection
label | Verification Records - Test result
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D2.8.3,D2.8.2 - Surface Reinstatement
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Engineer's Approval
label | Detail - Mark out the trench including overcuts
label | Frequency - Prior to surfacing
label | Inspection / Test Method - Inspection
label | Verification Records - Email
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D1.24 - Engineer's inspections
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Inspection report
label | Detail - Enginer's inspection for pipe, concrete pre pour, pre sealing. Minimum 2 working days notice for inspection requirements
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Email
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checklist | 4.0 FSMH 25396 - FSMH 25397 | itp |  |  |  |  | ITP - Wilton Street (4.0 FSMH 25396 - FSMH 25397)
section | 4.0 FSMH 25396 - FSMH 25397
checkpoint | D18.3 - FSMH 25396
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Location, depth and foundation
label | Detail - The manhole shall be constructed to design depth and location, founded on suitable base of material
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D15.3.3 - FSMH 25396
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - The entry shaft shall not be greater than 500mm
label | Detail - The entry shaft from the top of the proposed manhole lid to the underside of the MH concrete slab, shall not be greater than 500mm.
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25396 (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Manhole step rungs
label | Detail - The steps shall be installed on the u/s side with the vertical height between steps being 300mm
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25396 (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Benching and plastering within the structure
label | Detail - Confirm benching/plastering completed to appropriate standard
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25396 (3)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - External concrete haunching
label | Detail - Corbel poured to suitable depth and width as per typical details
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25396 (4)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Concrete Ballast
label | Detail - Additional volume of concrete required for anti-flotation ballast if corbel volume does not excced 1.2m3
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D18.3 - 225mmØ finisher pipe
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Flexible joint
label | Detail - All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure.
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - 225mmØ Starter pipe
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Flexible joint
label | Detail - All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure.
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D2.4.1 - 225mm uPVC pipe laying CH97 - CH137 (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - As per AS/NZS 2566.2 Buried flexible pipelines
label | Detail - Pipes laid and joined to witness marks
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - AS/NZS 2566.2
label | Signatory - Site Engineer
checkpoint | D2.4.1 - 225mm uPVC pipe laying CH97 - CH137 (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Pipe grade
label | Detail - All pipes laid using calibrated laser to deisgn gradient
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - As built records
checkpoint | D2.7.6 - Bedding material (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Well graded granular material complying with table G3.AS/NZS 2566.2
label | Detail - Particle size distribition from material test report
label | Frequency - as required
label | Inspection / Test Method - Testing
label | Verification Records - Test result
label | Standard - AS/NZS 2566.2
label | Signatory - Site Engineer
checkpoint | D2.7.6 - Bedding material (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Pipe embedment
label | Detail - Bedding material shall be compacted adequately and uniformly and meet the requirements of Type 3 support detail in Fig. D24 and requirements of NZS 2566
label | Frequency - Layer depth as required
label | Inspection / Test Method - Inspection
label | Verification Records - Onsite inspections
label | Standard - AS/NZS 2566
label | Signatory - Site Engineer
checkpoint | D2.7.7 - Sub base
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Layer thickness
label | Detail - Uncompacted thickness should be less than 200mm
label | Frequency - Layer depth as required
label | Inspection / Test Method - Inspection
label | Verification Records - Onsite inspections
label | Signatory - Site Engineer
checkpoint | D2.7.7.1 - Sub base
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - NDM Testing
label | Detail - At every 120m intervals for open trench at every layer
label | Frequency - At 120m
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Signatory - Engineers Representative
checkpoint | D2.7.7.2 - Base course
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Layer thickness
label | Detail - Basecourse layer shall be minimum of 150mm depth
label | Frequency - Layer depth as required
label | Inspection / Test Method - Inspection
label | Verification Records - Onsite inspections
label | Standard - NZTA B/2
label | Signatory - Site Engineer
checkpoint | D2.7.7.1 - Base course
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Clegg hammer testing
label | Detail - At every 6m intervals for open trench
label | Frequency - At every 6m
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Signatory - Engineers Representative
checkpoint | D2.7.7.2 - Base course
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - NDM Testing
label | Detail - At every 20m intervals for open trench at every layer
label | Frequency - At 20m
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Standard - NZTA B/2
label | Signatory - Engineers Representative
checkpoint | D4.4.2 - Service connection to property 128 George Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 128 George Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 126 George Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 126 George Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D2.7.4.1 - Watermain service support CH103
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Watermain support
label | Detail - Concrete haunching and sand fill around cast iron watermain crossing sewer trench as per typical detail D26
label | Frequency - Per crossing
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D2.9.2 - Pressure testing
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Pressure testing of mainline
label | Detail - Contractor shall undertake pressure testing of sewer main
label | Frequency - As required
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Standard - NZS 2566.2
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D2.9.3 - CCTV inspection
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Flushing, cleaning and CCTV
label | Detail - Contractor shall undertake cleaning and CCTV inspection of all new gravity mains as per the New Zealand Pipe Inspection Manual.
label | Frequency - As required
label | Inspection / Test Method - CCTV
label | Verification Records - CCTV report
label | Standard - New zealand inspection manual
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D9.6 - Kerb and Channel
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Kerb and channel reinstatement
label | Detail - Kerb and channel to be prepared and staked for laying, and installed as per ICC specification
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D9.6.2 - Kerb and Channel
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Compaction testing
label | Detail - Kerb and channel prep to be clegg tested at 10m intervals to a CIV of 35
label | Frequency - At every 10m
label | Inspection / Test Method - Inspection
label | Verification Records - Test result
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D2.8.3,D2.8.2 - Surface Reinstatement
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Engineer's Approval
label | Detail - Mark out the trench including overcuts
label | Frequency - Prior to surfacing
label | Inspection / Test Method - Inspection
label | Verification Records - Email
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D1.24 - Engineer's inspections
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Inspection report
label | Detail - Enginer's inspection for pipe, concrete pre pour, pre sealing. Minimum 2 working days notice for inspection requirements
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Email
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checklist | 5.0 FSMH 25397 - FSMH 25398 | itp |  |  |  |  | ITP - Wilton Street (5.0 FSMH 25397 - FSMH 25398)
section | 5.0 FSMH 25397 - FSMH 25398
checkpoint | D18.3 - FSMH 25397
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Location, depth and foundation
label | Detail - The manhole shall be constructed to design depth and location, founded on suitable base of material
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D15.3.3 - FSMH 25397
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - The entry shaft shall not be greater than 500mm
label | Detail - The entry shaft from the top of the proposed manhole lid to the underside of the MH concrete slab, shall not be greater than 500mm.
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25397 (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Manhole step rungs
label | Detail - The steps shall be installed on the u/s side with the vertical height between steps being 300mm
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25397 (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Benching and plastering within the structure
label | Detail - Confirm benching/plastering completed to appropriate standard
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25397 (3)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - External concrete haunching
label | Detail - Corbel poured to suitable depth and width as per typical details
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25397 (4)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Concrete Ballast
label | Detail - Additional volume of concrete required for anti-flotation ballast if corbel volume does not excced 1.2m3
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D18.3 - 225mmØ finisher pipe
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Flexible joint
label | Detail - All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure.
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - 225mmØ Starter pipe
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Flexible joint
label | Detail - All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure.
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D2.4.1 - 225mm uPVC pipe laying CH137 - CH192 (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - As per AS/NZS 2566.2 Buried flexible pipelines
label | Detail - Pipes laid and joined to witness marks
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - AS/NZS 2566.2
label | Signatory - Site Engineer
checkpoint | D2.4.1 - 225mm uPVC pipe laying CH137 - CH192 (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Pipe grade
label | Detail - All pipes laid using calibrated laser to deisgn gradient
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - As built records
checkpoint | D2.7.6 - Bedding material (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Well graded granular material complying with table G3.AS/NZS 2566.2
label | Detail - Particle size distribition from material test report
label | Frequency - as required
label | Inspection / Test Method - Testing
label | Verification Records - Test result
label | Standard - AS/NZS 2566.2
label | Signatory - Site Engineer
checkpoint | D2.7.6 - Bedding material (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Pipe embedment
label | Detail - Bedding material shall be compacted adequately and uniformly and meet the requirements of Type 3 support detail in Fig. D24 and requirements of NZS 2566
label | Frequency - Layer depth as required
label | Inspection / Test Method - Inspection
label | Verification Records - Onsite inspections
label | Standard - AS/NZS 2566
label | Signatory - Site Engineer
checkpoint | D2.7.7 - Sub base
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Layer thickness
label | Detail - Uncompacted thickness should be less than 200mm
label | Frequency - Layer depth as required
label | Inspection / Test Method - Inspection
label | Verification Records - Onsite inspections
label | Signatory - Site Engineer
checkpoint | D2.7.7.1 - Sub base
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - NDM Testing
label | Detail - At every 120m intervals for open trench at every layer
label | Frequency - At 120m
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Signatory - Engineers Representative
checkpoint | D2.7.7.2 - Base course
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Layer thickness
label | Detail - Basecourse layer shall be minimum of 150mm depth
label | Frequency - Layer depth as required
label | Inspection / Test Method - Inspection
label | Verification Records - Onsite inspections
label | Standard - NZTA B/2
label | Signatory - Site Engineer
checkpoint | D2.7.7.1 - Base course
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Clegg hammer testing
label | Detail - At every 6m intervals for open trench
label | Frequency - At every 6m
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Signatory - Engineers Representative
checkpoint | D2.7.7.2 - Base course
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - NDM Testing
label | Detail - At every 20m intervals for open trench at every layer
label | Frequency - At 20m
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Standard - NZTA B/2
label | Signatory - Engineers Representative
checkpoint | D4.4.2 - Service connection to property 127 Catherine Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 127 Catherine Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D2.9.2 - Pressure testing
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Pressure testing of mainline
label | Detail - Contractor shall undertake pressure testing of sewer main
label | Frequency - As required
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Standard - NZS 2566.2
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D2.9.3 - CCTV inspection
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Flushing, cleaning and CCTV
label | Detail - Contractor shall undertake cleaning and CCTV inspection of all new gravity mains as per the New Zealand Pipe Inspection Manual.
label | Frequency - As required
label | Inspection / Test Method - CCTV
label | Verification Records - CCTV report
label | Standard - New zealand inspection manual
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D9.6 - Kerb and Channel
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Kerb and channel reinstatement
label | Detail - Kerb and channel to be prepared and staked for laying, and installed as per ICC specification
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D9.6.2 - Kerb and Channel
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Compaction testing
label | Detail - Kerb and channel prep to be clegg tested at 10m intervals to a CIV of 35
label | Frequency - At every 10m
label | Inspection / Test Method - Inspection
label | Verification Records - Test result
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D2.8.3,D2.8.2 - Surface Reinstatement
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Engineer's Approval
label | Detail - Mark out the trench including overcuts
label | Frequency - Prior to surfacing
label | Inspection / Test Method - Inspection
label | Verification Records - Email
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D1.24 - Engineer's inspections
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Inspection report
label | Detail - Enginer's inspection for pipe, concrete pre pour, pre sealing. Minimum 2 working days notice for inspection requirements
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Email
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checklist | 6.0 FSMH 25398 - FSMH 25399 | itp |  |  |  |  | ITP - Wilton Street (6.0 FSMH 25398 - FSMH 25399)
section | 6.0 FSMH 25398 - FSMH 25399
checkpoint | D18.3 - FSMH 25398
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Location, depth and foundation
label | Detail - The manhole shall be constructed to design depth and location, founded on suitable base of material
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D15.3.3 - FSMH 25398
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - The entry shaft shall not be greater than 500mm
label | Detail - The entry shaft from the top of the proposed manhole lid to the underside of the MH concrete slab, shall not be greater than 500mm.
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25398 (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Manhole step rungs
label | Detail - The steps shall be installed on the u/s side with the vertical height between steps being 300mm
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25398 (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Benching and plastering within the structure
label | Detail - Confirm benching/plastering completed to appropriate standard
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25398 (3)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - External concrete haunching
label | Detail - Corbel poured to suitable depth and width as per typical details
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25398 (4)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Concrete Ballast
label | Detail - Additional volume of concrete required for anti-flotation ballast if corbel volume does not excced 1.2m3
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D18.3 - 225mmØ finisher pipe
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Flexible joint
label | Detail - All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure.
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - 225mmØ Starter pipe
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Flexible joint
label | Detail - All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure.
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D2.4.1 - 225mm uPVC pipe laying CH192 - CH295 (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - As per AS/NZS 2566.2 Buried flexible pipelines
label | Detail - Pipes laid and joined to witness marks
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - AS/NZS 2566.2
label | Signatory - Site Engineer
checkpoint | D2.4.1 - 225mm uPVC pipe laying CH192 - CH295 (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Pipe grade
label | Detail - All pipes laid using calibrated laser to deisgn gradient
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - As built records
checkpoint | D2.7.6 - Bedding material (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Well graded granular material complying with table G3.AS/NZS 2566.2
label | Detail - Particle size distribition from material test report
label | Frequency - as required
label | Inspection / Test Method - Testing
label | Verification Records - Test result
label | Standard - AS/NZS 2566.2
label | Signatory - Site Engineer
checkpoint | D2.7.6 - Bedding material (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Pipe embedment
label | Detail - Bedding material shall be compacted adequately and uniformly and meet the requirements of Type 3 support detail in Fig. D24 and requirements of NZS 2566
label | Frequency - Layer depth as required
label | Inspection / Test Method - Inspection
label | Verification Records - Onsite inspections
label | Standard - AS/NZS 2566
label | Signatory - Site Engineer
checkpoint | D2.7.7 - Sub base
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Layer thickness
label | Detail - Uncompacted thickness should be less than 200mm
label | Frequency - Layer depth as required
label | Inspection / Test Method - Inspection
label | Verification Records - Onsite inspections
label | Signatory - Site Engineer
checkpoint | D2.7.7.1 - Sub base
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - NDM Testing
label | Detail - At every 120m intervals for open trench at every layer
label | Frequency - At 120m
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Signatory - Engineers Representative
checkpoint | D2.7.7.2 - Base course
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Layer thickness
label | Detail - Basecourse layer shall be minimum of 150mm depth
label | Frequency - Layer depth as required
label | Inspection / Test Method - Inspection
label | Verification Records - Onsite inspections
label | Standard - NZTA B/2
label | Signatory - Site Engineer
checkpoint | D2.7.7.1 - Base course
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Clegg hammer testing
label | Detail - At every 6m intervals for open trench
label | Frequency - At every 6m
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Signatory - Engineers Representative
checkpoint | D2.7.7.2 - Base course
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - NDM Testing
label | Detail - At every 20m intervals for open trench at every layer
label | Frequency - At 20m
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Standard - NZTA B/2
label | Signatory - Engineers Representative
checkpoint | D2.7.4.1 - Watermain service support CH198
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Watermain support
label | Detail - Concrete haunching and sand fill around cast iron watermain crossing sewer trench as per typical detail D26
label | Frequency - Per crossing
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 126 Catherine Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 126 Catherine Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 40 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 40 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 47 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 47 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D2.7.4.1 - Watermain service support CH293
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Watermain support
label | Detail - Concrete haunching and sand fill around cast iron watermain crossing sewer trench as per typical detail D26
label | Frequency - Per crossing
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D2.9.2 - Pressure testing
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Pressure testing of mainline
label | Detail - Contractor shall undertake pressure testing of sewer main
label | Frequency - As required
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Standard - NZS 2566.2
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D2.9.3 - CCTV inspection
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Flushing, cleaning and CCTV
label | Detail - Contractor shall undertake cleaning and CCTV inspection of all new gravity mains as per the New Zealand Pipe Inspection Manual.
label | Frequency - As required
label | Inspection / Test Method - CCTV
label | Verification Records - CCTV report
label | Standard - New zealand inspection manual
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D9.6 - Kerb and Channel
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Kerb and channel reinstatement
label | Detail - Kerb and channel to be prepared and staked for laying, and installed as per ICC specification
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D9.6.2 - Kerb and Channel
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Compaction testing
label | Detail - Kerb and channel prep to be clegg tested at 10m intervals to a CIV of 35
label | Frequency - At every 10m
label | Inspection / Test Method - Inspection
label | Verification Records - Test result
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D2.8.3,D2.8.2 - Surface Reinstatement
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Engineer's Approval
label | Detail - Mark out the trench including overcuts
label | Frequency - Prior to surfacing
label | Inspection / Test Method - Inspection
label | Verification Records - Email
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D1.24 - Engineer's inspections
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Inspection report
label | Detail - Enginer's inspection for pipe, concrete pre pour, pre sealing. Minimum 2 working days notice for inspection requirements
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Email
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checklist | 7.0 FSMH 25399 - FSMH 25401 | itp |  |  |  |  | ITP - Wilton Street (7.0 FSMH 25399 - FSMH 25401)
section | 7.0 FSMH 25399 - FSMH 25401
checkpoint | D18.3 - FSMH 25399
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Location, depth and foundation
label | Detail - The manhole shall be constructed to design depth and location, founded on suitable base of material
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D15.3.3 - FSMH 25399
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - The entry shaft shall not be greater than 500mm
label | Detail - The entry shaft from the top of the proposed manhole lid to the underside of the MH concrete slab, shall not be greater than 500mm.
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25399 (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Manhole step rungs
label | Detail - The steps shall be installed on the u/s side with the vertical height between steps being 300mm
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25399 (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Benching and plastering within the structure
label | Detail - Confirm benching/plastering completed to appropriate standard
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25399 (3)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - External concrete haunching
label | Detail - Corbel poured to suitable depth and width as per typical details
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25399 (4)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Concrete Ballast
label | Detail - Additional volume of concrete required for anti-flotation ballast if corbel volume does not excced 1.2m3
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D18.3 - 225mmØ finisher pipe
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Flexible joint
label | Detail - All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure.
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - 150mmØ Starter pipe
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Flexible joint
label | Detail - All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure.
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D2.4.1 - 150mm uPVC pipe laying CH295 - CH384 (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - As per AS/NZS 2566.2 Buried flexible pipelines
label | Detail - Pipes laid and joined to witness marks
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - AS/NZS 2566.2
label | Signatory - Site Engineer
checkpoint | D2.4.1 - 150mm uPVC pipe laying CH295 - CH384 (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Pipe grade
label | Detail - All pipes laid using calibrated laser to deisgn gradient
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - As built records
checkpoint | D2.7.6 - Bedding material (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Well graded granular material complying with table G3.AS/NZS 2566.2
label | Detail - Particle size distribition from material test report
label | Frequency - as required
label | Inspection / Test Method - Testing
label | Verification Records - Test result
label | Standard - AS/NZS 2566.2
label | Signatory - Site Engineer
checkpoint | D2.7.6 - Bedding material (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Pipe embedment
label | Detail - Bedding material shall be compacted adequately and uniformly and meet the requirements of Type 3 support detail in Fig. D24 and requirements of NZS 2566
label | Frequency - Layer depth as required
label | Inspection / Test Method - Inspection
label | Verification Records - Onsite inspections
label | Standard - AS/NZS 2566
label | Signatory - Site Engineer
checkpoint | D2.7.7 - Sub base
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Layer thickness
label | Detail - Uncompacted thickness should be less than 200mm
label | Frequency - Layer depth as required
label | Inspection / Test Method - Inspection
label | Verification Records - Onsite inspections
label | Signatory - Site Engineer
checkpoint | D2.7.7.1 - Sub base
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - NDM Testing
label | Detail - At every 120m intervals for open trench at every layer
label | Frequency - At 120m
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Signatory - Engineers Representative
checkpoint | D2.7.7.2 - Base course
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Layer thickness
label | Detail - Basecourse layer shall be minimum of 150mm depth
label | Frequency - Layer depth as required
label | Inspection / Test Method - Inspection
label | Verification Records - Onsite inspections
label | Standard - NZTA B/2
label | Signatory - Site Engineer
checkpoint | D2.7.7.1 - Base course
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Clegg hammer testing
label | Detail - At every 6m intervals for open trench
label | Frequency - At every 6m
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Signatory - Engineers Representative
checkpoint | D2.7.7.2 - Base course
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - NDM Testing
label | Detail - At every 20m intervals for open trench at every layer
label | Frequency - At 20m
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Standard - NZTA B/2
label | Signatory - Engineers Representative
checkpoint | D2.7.4.1 - Watermain service support CH302
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Watermain support
label | Detail - Concrete haunching and sand fill around cast iron watermain crossing sewer trench as per typical detail D26
label | Frequency - Per crossing
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D2.7.4.1 - Watermain service support CH312
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Watermain support
label | Detail - Concrete haunching and sand fill around cast iron watermain crossing sewer trench as per typical detail D26
label | Frequency - Per crossing
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 340 Herbert Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 340 Herbert Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 57 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 57 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 56 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 56 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 59 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 59 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 58 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 58 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 60 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 60 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 64 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 64 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 64 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Potentially redundant/double up
checkpoint | D4.4.3 - Service connection to property 64 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
checkpoint | D4.4.2 - Service connection to property 65 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 65 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D2.9.2 - Pressure testing
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Pressure testing of mainline
label | Detail - Contractor shall undertake pressure testing of sewer main
label | Frequency - As required
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Standard - NZS 2566.2
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D2.9.3 - CCTV inspection
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Flushing, cleaning and CCTV
label | Detail - Contractor shall undertake cleaning and CCTV inspection of all new gravity mains as per the New Zealand Pipe Inspection Manual.
label | Frequency - As required
label | Inspection / Test Method - CCTV
label | Verification Records - CCTV report
label | Standard - New zealand inspection manual
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D9.6 - Kerb and Channel
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Kerb and channel reinstatement
label | Detail - Kerb and channel to be prepared and staked for laying, and installed as per ICC specification
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D9.6.2 - Kerb and Channel
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Compaction testing
label | Detail - Kerb and channel prep to be clegg tested at 10m intervals to a CIV of 35
label | Frequency - At every 10m
label | Inspection / Test Method - Inspection
label | Verification Records - Test result
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D2.8.3,D2.8.2 - Surface Reinstatement
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Engineer's Approval
label | Detail - Mark out the trench including overcuts
label | Frequency - Prior to surfacing
label | Inspection / Test Method - Inspection
label | Verification Records - Email
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D1.24 - Engineer's inspections
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Inspection report
label | Detail - Enginer's inspection for pipe, concrete pre pour, pre sealing. Minimum 2 working days notice for inspection requirements
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Email
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checklist | 8.0 FSMH 25401 - FSMH 25400 | itp |  |  |  |  | ITP - Wilton Street (8.0 FSMH 25401 - FSMH 25400)
section | 8.0 FSMH 25401 - FSMH 25400
checkpoint | D18.3 - FSMH 25401
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Location, depth and foundation
label | Detail - The manhole shall be constructed to design depth and location, founded on suitable base of material
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D15.3.3 - FSMH 25401
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - The entry shaft shall not be greater than 500mm
label | Detail - The entry shaft from the top of the proposed manhole lid to the underside of the MH concrete slab, shall not be greater than 500mm.
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25401 (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Manhole step rungs
label | Detail - The steps shall be installed on the u/s side with the vertical height between steps being 300mm
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25401 (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Benching and plastering within the structure
label | Detail - Confirm benching/plastering completed to appropriate standard
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25401 (3)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - External concrete haunching
label | Detail - Corbel poured to suitable depth and width as per typical details
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25401 (4)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Concrete Ballast
label | Detail - Additional volume of concrete required for anti-flotation ballast if corbel volume does not excced 1.2m3
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D18.3 - 150mmØ finisher pipe
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Flexible joint
label | Detail - All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure.
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - 150mmØ Starter pipe
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Flexible joint
label | Detail - All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure.
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D2.4.1 - 150mm uPVC pipe laying CH384 - CH510 (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - As per AS/NZS 2566.2 Buried flexible pipelines
label | Detail - Pipes laid and joined to witness marks
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - AS/NZS 2566.2
label | Signatory - Site Engineer
checkpoint | D2.4.1 - 150mm uPVC pipe laying CH384 - CH510 (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Pipe grade
label | Detail - All pipes laid using calibrated laser to deisgn gradient
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - As built records
checkpoint | D2.7.6 - Bedding material (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Well graded granular material complying with table G3.AS/NZS 2566.2
label | Detail - Particle size distribition from material test report
label | Frequency - as required
label | Inspection / Test Method - Testing
label | Verification Records - Test result
label | Standard - AS/NZS 2566.2
label | Signatory - Site Engineer
checkpoint | D2.7.6 - Bedding material (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Pipe embedment
label | Detail - Bedding material shall be compacted adequately and uniformly and meet the requirements of Type 3 support detail in Fig. D24 and requirements of NZS 2566
label | Frequency - Layer depth as required
label | Inspection / Test Method - Inspection
label | Verification Records - Onsite inspections
label | Standard - AS/NZS 2566
label | Signatory - Site Engineer
checkpoint | D2.7.7 - Sub base
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Layer thickness
label | Detail - Uncompacted thickness should be less than 200mm
label | Frequency - Layer depth as required
label | Inspection / Test Method - Inspection
label | Verification Records - Onsite inspections
label | Signatory - Site Engineer
checkpoint | D2.7.7.1 - Sub base
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - NDM Testing
label | Detail - At every 120m intervals for open trench at every layer
label | Frequency - At 120m
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Signatory - Engineers Representative
checkpoint | D2.7.7.2 - Base course
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Layer thickness
label | Detail - Basecourse layer shall be minimum of 150mm depth
label | Frequency - Layer depth as required
label | Inspection / Test Method - Inspection
label | Verification Records - Onsite inspections
label | Standard - NZTA B/2
label | Signatory - Site Engineer
checkpoint | D2.7.7.1 - Base course
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Clegg hammer testing
label | Detail - At every 6m intervals for open trench
label | Frequency - At every 6m
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Signatory - Engineers Representative
checkpoint | D2.7.7.2 - Base course
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - NDM Testing
label | Detail - At every 20m intervals for open trench at every layer
label | Frequency - At 20m
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Standard - NZTA B/2
label | Signatory - Engineers Representative
checkpoint | D4.4.2 - Service connection to property 66 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Potentially redundant/double up
checkpoint | D4.4.3 - Service connection to property 66 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
checkpoint | D4.4.2 - Service connection to property 67 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 67 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 70 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 70 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 71 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 71 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 74 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 74 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 75 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 75 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 76 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 76 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 77 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 77 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 78 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 78 Wilton Street
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.2 - Service connection to property 79 Wilton Street/123 Chelmsford Street (shared)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Connection to main and riser
label | Detail - Reducing junction, bends and riser installed as per modified typical detail including site concrete around junctions and bends
label | Frequency - Each property
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D4.4.3 - Service connection to property 79 Wilton Street/123 Chelmsford Street (shared)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Service lateral
label | Detail - Laid at minimum 1 in 100 grade and minimum 1m depth at boundary
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Signatory - Site Engineer
checkpoint | D18.3 - New FS Maintenance Shaft F20804
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Location, depth and foundation
label | Detail - Maintenance shaft shall be constructed to design depth and location, founded on suitable base of material
label | Frequency - Per feature
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D15.3.3 - New FS Maintenance Shaft F20804
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Depth of top of shaft under cap
label | Detail - The entry pipe to the shaft is to be within 100 to 150mm from the surface level
label | Frequency - Per feature
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D22
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25400
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Location, depth and foundation
label | Detail - The manhole shall be constructed to design depth and location, founded on suitable base of material
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D15.3.3 - FSMH 25400
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - The entry shaft shall not be greater than 500mm
label | Detail - The entry shaft from the top of the proposed manhole lid to the underside of the MH concrete slab, shall not be greater than 500mm.
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25400 (1)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Manhole step rungs
label | Detail - The steps shall be installed on the u/s side with the vertical height between steps being 300mm
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25400 (2)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Benching and plastering within the structure
label | Detail - Confirm benching/plastering completed to appropriate standard
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Individual inspection sheet
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25400 (3)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - External concrete haunching
label | Detail - Corbel poured to suitable depth and width as per typical details
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D18.3 - FSMH 25400 (4)
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Concrete Ballast
label | Detail - Additional volume of concrete required for anti-flotation ballast if corbel volume does not excced 1.2m3
label | Frequency - Per manhole
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D18.3 - 150mmØ finisher pipe
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Flexible joint
label | Detail - All pipe protrusions from the manhole shall have flexible joint located within 1 metre of the edge of corbel or manhole structure.
label | Frequency - Per connection
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Standard - Fig. D15
label | Signatory - Site Engineer
checkpoint | D2.9.2 - Pressure testing
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Pressure testing of mainline
label | Detail - Contractor shall undertake pressure testing of sewer main
label | Frequency - As required
label | Inspection / Test Method - Testing
label | Verification Records - Test Result
label | Standard - NZS 2566.2
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D2.9.3 - CCTV inspection
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Flushing, cleaning and CCTV
label | Detail - Contractor shall undertake cleaning and CCTV inspection of all new gravity mains as per the New Zealand Pipe Inspection Manual.
label | Frequency - As required
label | Inspection / Test Method - CCTV
label | Verification Records - CCTV report
label | Standard - New zealand inspection manual
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D9.6 - Kerb and Channel
label | ACTION (W, M, H) - W
label | Conformance Criteria (What's Required) - Kerb and channel reinstatement
label | Detail - Kerb and channel to be prepared and staked for laying, and installed as per ICC specification
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Photos
label | Signatory - Site Engineer
checkpoint | D9.6.2 - Kerb and Channel
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Compaction testing
label | Detail - Kerb and channel prep to be clegg tested at 10m intervals to a CIV of 35
label | Frequency - At every 10m
label | Inspection / Test Method - Inspection
label | Verification Records - Test result
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D2.8.3,D2.8.2 - Surface Reinstatement
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Engineer's Approval
label | Detail - Mark out the trench including overcuts
label | Frequency - Prior to surfacing
label | Inspection / Test Method - Inspection
label | Verification Records - Email
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D1.24 - Engineer's inspections
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Inspection report
label | Detail - Enginer's inspection for pipe, concrete pre pour, pre sealing. Minimum 2 working days notice for inspection requirements
label | Frequency - As required
label | Inspection / Test Method - Inspection
label | Verification Records - Email
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checklist | 9.0 Completion documents | itp |  |  |  |  | ITP - Wilton Street (9.0 Completion documents)
section | 9.0 Completion documents
checkpoint | D17.2 - As-built
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Ensure as-built data recorded and submitted
label | Detail - Red pen markup drawing
label | Frequency - At completion
label | Inspection / Test Method - Submission
label | Verification Records - As built drawings/markup
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D17.2 - PS3 submission
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - Producer statement for construction to be supplied to client
label | Detail - As per schedule 6 3910:2013
label | Frequency - Prior to PCC application
label | Inspection / Test Method - Submission
label | Verification Records - Email of notice
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D17.2 - WCN and CAR close out
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - To be submitted at completion of works
label | Detail - Submission to ICC of completion of works in road corridor and close out of CAR
label | Frequency - Prior to PCC application
label | Inspection / Test Method - Submission
label | Verification Records - PS3 document
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | D17.2 - QA documents submitted
label | ACTION (W, M, H) - H
label | Conformance Criteria (What's Required) - All required documents submitted throughout and at conclusion of project
label | Detail - All connection sheets, NDM results, encountered services sheets, construction photographs, any outstanding H&S or non conformance reporting
label | Frequency - Prior to PCC application
label | Inspection / Test Method - Submission
label | Verification Records - Various
label | Signatory - Engineers Representative
holdpoint | HOLD POINT
checkpoint | Sub-contractor / Project Manager / Quality Manager - Accepted By:
signoff | Signature: