## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Aluminium Vertical & Horizontal PFC School |  | Aluminium Vertical & Horizontal PFC School | a6812c66-af21-4a4a-b358-63158c65642c
| section | Details
| checkpoint | All PFCs are installed level and as per approved shop drawing and engineer's certificate
| checkpoint | All end plates on bhorizontal and vertical pfc have fully welded
| checkpoint | Any existing scratches have been touched up
| checkpoint | PFCs are clean and free of any dust and dirt
| checkpoint | All fixings were M12 GAL MONUMENT, PFCs were installed as per shop drawing
| checkpoint | Chemset used for bolt fixing was VFpro22 + as per shop drawings, bolt min EMBD 100mm
| checkpoint | 20mm packer is been used as per shops
| checkpoint | Color of PFC is Monument Flatt Matt(YP229A)- All touch up paints match the actual powdercoat color
| checkpoint | ABL-SHP-0200 REV06 were used for installation on site
88537d32-ca5e-500f-b421-6788d762fd94 | note | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REQULARLY ( FORTHNIGHTLY ) TO SIGN OFF ON THE CHEKLIST
| checklist | Aluminium Vertical Screens School |  | Aluminium Vertical Screens School | 4fafcb3a-a63c-44bb-858c-baf2d2c39849
| section | Details
| checkpoint | All screens are installed level and as per approved shop drawing and engineer's certificate
| checkpoint | All blades have fully welded end caps with weep holes
| checkpoint | Any existing scratches have been touched up
| checkpoint | Screens are clean and free of any dust and dirt
| checkpoint | All fixings were M12 GAL MONUMENT, screens were installed as per shop drawing
| checkpoint | Chemset used for bolt fixing was VFpro22 + as per shop drawings, bolt min EMBD 100mm
| checkpoint | Color of RHS blades is Coastal Spotted gum Timberlook as per shops, Color of flat bars is Monument Flatt Matt(YP229A)- All touch up paints match the actual powdercoat color
| checkpoint | ABL-SHP-0300 REV05 were used for installation on site
a30c04ed-a35c-5e7b-abf3-f0a1c770fc3b | note | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REQULARLY ( FORTHNIGHTLY ) TO SIGN OFF ON THE CHEKLIST
| checklist | BAL03B ALUM. FENCING |  | BAL03B ALUM. FENCING | bbd1778a-9eb6-4f38-91ee-9bfd3fc93b2f
| checkpoint | All fences are installed level and as per approved shop drawing and engineer's certificate
| checkpoint | All blades have fully welded end caps with weep holes
| checkpoint | Any existing scratches have been touched up
| checkpoint | Fences are clean and free of any dust and dirt
| checkpoint | All fixings were M12 GAL MONUMENT, fences were installed as per shop drawing
| checkpoint | Chemset used for bolt fixing was VFpro22 + as per shop drawings, bolt min EMBD 120mm
| checkpoint | [object Object]
| checkpoint | ABL-SHP-3150 REV08 were used for installation on site
| checklist | Glass Balustrade School |  | Glass Balustrade School | 60491aa6-3447-49a8-bcd2-fe2cbc510dec
| section | Details
| checkpoint | Glass balustrades are installed level
| checkpoint | Glass balustrades are installed as per approved shop drawing.
| checkpoint | All gaps are following approved set out drawing and comply with BCA being less than 125mm
| checkpoint | Grout under posts are filled properly
| checkpoint | Top channels are connected properly and welded properly as per engineer's certificate
| checkpoint | All rubbers are installed properly
| checkpoint | VFPRO22+ chemset was used for fixing glass posts
| checkpoint | Alum. Cover plates Monumnet color is used for concealing base plates
| checkpoint | 4M12 SS316 Hex head anchors 150mm EMBD was used
| checkpoint | End caps are installed properly
| checkpoint | ABL-SHP-4300 REV06 were used for installation on site
a8af3d45-a71e-503f-a2f6-ff74904ba83e | note | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REQULARLY ( FORTHNIGHTLY ) TO SIGN OFF ON THE CHEKLIST
| checklist | Stainless Steel Wires School |  | Stainless Steel Wires School | 3201c97c-33f7-4f73-b6de-a487c6f62bc3
| section | Details
| checkpoint | All wires are installed level and as per approved shop drawing
| checkpoint | All stainless steel wires have been installed as per approved shop drawing, 80mm CTS as per engineer certificate
| checkpoint | Fla bars are Alum. Powdercoted Monumnet
| checkpoint | Fixings wires to PFC and bottom FB is all stainless steel 316
| checkpoint | All fixing method were installed as per shop drawing
| checkpoint | Fixings bottom FB to floor is GAL powdercoated Monumenet
| checkpoint | Chemset used to fix anchors to floor is VF22pro +
| checkpoint | ABL-SHP-1000 REV04 were used for installation on site
e160ca5c-40da-5d55-bcd7-a4a11a155024 | note | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REQULARLY ( FORTHNIGHTLY ) TO SIGN OFF ON THE CHEKLIST