## Project Structure
Folder Structure |  |  |  | Checklists
Site QA
School
Lower Ground
|  |  | Aluminium Vertical & Horizontal PFC School | Aluminium Vertical & Horizontal PFC School
|  |  | Aluminium Vertical Screens School | Aluminium Vertical Screens School
|  |  | Glass Balustrade School | Glass Balustrade School
|  |  | Stainless Steel Wires School | Stainless Steel Wires School
Upper Ground
Level 1
Level 2
Level 3
Level 4
Parish
Lower Ground
Upper Ground
Level 1
Level 2
Level 3
Level 4
RAC (Residential Aged Care)
Level 1
Level 2
Level 3
Level 4
RL (Retired Living)
Level 5
Unit 0601
Unit 0602
Unit 0603
Unit 0604 (Communal Lounge)
Unit 0605
Unit 0606
Level 7
Unit 0701
Unit 0702
Unit 0703
Unit 0704
Unit 0705
Unit 0706
Unit 0707
Unit 0708
Level 8
Unit 0801
Unit 0802
Unit 0803
Unit 0804
Unit 0805
Unit 0806
Unit 0807
Unit 0808
Level 9
Unit 0901
Unit 0902
Unit 0903
Unit 0904
Unit 0905
Unit 0906
Unit 0907
Unit 0908
Level 10
Unit 1001
Unit 1002
Unit 1003
Unit 1004
Unit 1005
Unit 1006
Unit 1007
Unit 1008
Level 11
Unit 1101
Unit 1102
Unit 1103
Unit 1104
Unit 1105
Unit 1106
Unit 1107
Unit 1108
Level 12
Unit 1201
Unit 1202
Unit 1203
Unit 1204
Unit 1205
Unit 1206
Unit 1207
Unit 1208
Level 13
Unit 1301
Unit 1302
Unit 1303
Unit 1304
Unit 1305
Unit 1306
Unit 1307
Unit 1308
Level 14
Unit 1401
Unit 1402
Unit 1403
Unit 1404
Unit 1405
Unit 1406
Unit 1407
Unit 1408
Level 15
Unit 1501
Unit 1502
Unit 1503
Unit 1504
Unit 1505
Unit 1506
Unit 1507
Unit 1508
Level 16
Unit 1601
Unit 1602
Unit 1603
Unit 1604
Unit 1605
Unit 1606
Unit 1607
Unit 1608
Level 17
Unit 1701
Unit 1702
Unit 1703
Unit 1704
Unit 1705
Unit 1706
Unit 1707
Unit 1708
Level 18
Unit 1801
Unit 1802
Unit 1803
Unit 1804
Unit 1805
Unit 1806
Unit 1807
Unit 1808
Level 19
Unit 1901
Unit 1902
Unit 1903
Unit 1904
Unit 1905
Unit 1906
Unit 1907
Unit 1908
Level 20
Unit 2001
Unit 2002
Unit 2003
Unit 2004
Unit 2005
Unit 2006
Unit 2007
Unit 2008
Level 21
Unit 2101
Unit 2102
Unit 2103
Unit 2104
Unit 2105
Unit 2106
Unit 2107
Unit 2108
Level 22
Unit 2201
Unit 2202
Unit 2203
Unit 2204
Unit 2205
Unit 2206
Unit 2207
Unit 2208
Level 23
Unit 2301
Unit 2302
Unit 2303
Unit 2304
Unit 2305
Unit 2306
Unit 2307
Unit 2308
Level 24
Unit 2401
Unit 2402
Unit 2403
Unit 2404
Unit 2405
Unit 2406
Unit 2407
Unit 2408
Level 25
Unit 2501
Unit 2502
Unit 2503
Unit 2504
Unit 2505
Unit 2506
Unit 2507
Unit 2508
Level 26
Unit 2601
Unit 2602
Unit 2603
Unit 2604
Unit 2605
Unit 2606
Unit 2607
Unit 2608
Level 27
Unit 2701
Unit 2702
Unit 2703
Unit 2704
Unit 2705
Unit 2706
Level 28
Unit 2801
Unit 2802
Unit 2803
Unit 2804
Roof

## Checklists
type | name | values
checklist | Aluminium Vertical & Horizontal PFC School
checkpoint | All PFCs are installed level and as per approved shop drawing and engineer's certificate
checkpoint | All end plates on horizontal and vertical pfc have fully welded
checkpoint | Any existing scratches have been touched up
checkpoint | PFCs are clean and free of any dust and dirt
checkpoint | All fixings were M12 GEL MONUMENT, PFCs were installed as per shop drawing
checkpoint | Chemset used for bolt fixing was VFpro22 + as per shop drawings, bolt min EMBD 100mm
checkpoint | 20mm packer is been used as per shops
checkpoint | Color of PFC is Monument Flatt Matt(YP229A)- All touch up paints match the actual powder coat color
checkpoint | ABL-SHP-0200 REV06 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REGULARLY ( FORTNIGHTLY ) TO SIGN OFF ON THE CHECKLIST
checklist | Aluminium Vertical Screens School
checkpoint | All screens are installed level and as per approved shop drawing and engineer's certificate
checkpoint | All blades have fully welded end caps with weep holes
checkpoint | Any existing scratches have been touched up
checkpoint | Screens are clean and free of any dust and dirt
checkpoint | All fixings were M12 GEL MONUMENT, screens were installed as per shop drawing
checkpoint | Chemset used for bolt fixing was VFpro22 + as per shop drawings, bolt min EMBD 100mm
checkpoint | Color of RHS blades is Coastal Spotted gum Timber Look as per shops, Color of flat bars is Monument Flatt Matt(YP229A)- All touch up paints match the actual powder coat color
checkpoint | ABL-SHP-0300 REV05 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REGULARLY ( FORTNIGHTLY ) TO SIGN OFF ON THE CHECKLIST
checklist | Glass Balustrade School
checkpoint | Glass balustrades are installed level
checkpoint | Glass balustrades are installed as per approved shop drawing.
checkpoint | All gaps are following approved set out drawing and comply with BCA being less than 125mm
checkpoint | Grout under posts are filled properly
checkpoint | Top channels are connected properly and welded properly as per engineer's certificate
checkpoint | All rubbers are installed properly
checkpoint | VFPRO22+ chemset was used for fixing glass posts
checkpoint | Alum. Cover plates Monument color is used for concealing base plates
checkpoint | 4M12 SS316 Hex head anchors 150mm EMBD was used
checkpoint | End caps are installed properly
checkpoint | ABL-SHP-4300 REV06 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REGULARLY ( FORTNIGHTLY ) TO SIGN OFF ON THE CHECKLIST
checklist | Stainless Steel Wires School
checkpoint | All wires are installed level and as per approved shop drawing
checkpoint | All stainless steel wires have been installed as per approved shop drawing, 80mm CTS as per engineer certificate
checkpoint | Fla bars are Alum. Powder Coated Monument
checkpoint | Fixings wires to PFC and bottom FB is all stainless steel 316
checkpoint | All fixing method were installed as per shop drawing
checkpoint | Fixings bottom FB to floor is GEL powder coated Monumenet
checkpoint | Chemset used to fix anchors to floor is VF22pro +
checkpoint | ABL-SHP-1000 REV04 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REGULARLY ( FORTNIGHTLY ) TO SIGN OFF ON THE CHECKLIST
checklist | AM01B ALUM. SCREENS & GATE
checkpoint | All screens are installed level and as per approved shop drawing and engineer's certificate
checkpoint | All blades have fully welded end caps with weep holes
checkpoint | Any existing scratches have been touched up
checkpoint | Screens are clean and free of any dust and dirt
checkpoint | All bolt fixings were M12 GEL BRILLIANCE, all screw fixings are G12 GEL BRILLINACE, screens were installed as per shop drawing
checkpoint | Chemset used for bolt fixing was VFpro22 + as per shop drawings, bolt min EMBD 100mm
checkpoint | Color of RHS blades is Interpon D2525 Flat Matt brilliance (YY23TA) as per shops- All touch up paints match the actual powder coat color
checkpoint | ABL-SHP-0200 REV06 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REGULARLY ( FORTNIGHTLY ) TO SIGN OFF ON THE CHECKLIST
checklist | BAL04 GLASS BALUSTRADE
checkpoint | Glass balustrades are installed level
checkpoint | Glass balustrades are installed as per approved shop drawing.
checkpoint | All gaps are following approved set out drawing and comply with BCA being less than 8mm
checkpoint | SS accessories and handrail to be Brushed #4 Linish finish
checkpoint | Top channels are connected properly and welded properly as per engineer's certificate
checkpoint | All rubbers are installed properly
checkpoint | VFPRO22+ chemset was used for fixing glass spigots
checkpoint | 4M12 SS316 Chemical anchors 100mm EMBD was used
checkpoint | ABL-SHP-3200 REV06 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REGULARLY ( FORTNIGHTLY ) TO SIGN OFF ON THE CHECKLIST
checklist | BAL07 GLASS BALUSTRADE
checkpoint | Glass balustrades are installed level
checkpoint | Glass balustrades are installed as per approved shop drawing.
checkpoint | All gaps are following approved set out drawing and comply with BCA being less than 125mm
checkpoint | Grout under posts are filled properly
checkpoint | Top channels are connected properly and welded properly as per engineer's certificate
checkpoint | All rubbers are installed properly
checkpoint | VFPRO22+ chemset was used for fixing glass posts
checkpoint | Alum. Cover plates Monument color is used for concealing base plates
checkpoint | 4M12 SS316 Hex head anchors 150mm EMBD was used
checkpoint | End caps are installed properly
checkpoint | ABL-SHP-4350 REV05 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REGULARLY ( FORTNIGHTLY ) TO SIGN OFF ON THE CHECKLIST
checklist | AM01D ALUM. Timber Look SCREENS - PARISH
checkpoint | All screens are installed level and as per approved shop drawing and engineer's certificate
checkpoint | All blades have fully welded end caps with weep holes
checkpoint | Any existing scratches have been touched up
checkpoint | Screens are clean and free of any dust and dirt
checkpoint | All fixings were M12 GEL MONUMENT, screens were installed as per shop drawing
checkpoint | Chemset used for bolt fixing was VFpro22 + as per shop drawings, bolt min EMBD 100mm
checkpoint | Color of RHS blades is Coastal Spotted gum Timber Look as per shops, Color of flat bars is Monument Flatt Matt(YP229A)- All touch up paints match the actual powder coat color
checkpoint | ABL-SHP-0400 REV04 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REGULARLY ( FORTNIGHTLY ) TO SIGN OFF ON THE CHECKLIST
checklist | AM01A ALUM. SCREENS - RL
checkpoint | All screens are installed level and as per approved shop drawing and engineer's certificate
checkpoint | All blades have fully welded to bottom flat bar
checkpoint | Any existing scratches have been touched up
checkpoint | Screens are clean and free of any dust and dirt
checkpoint | All bolt fixings were M10 GEL ROD AND DOME NUT MONUMENT, screens were installed as per shop drawing
checkpoint | Chemset used for bolt fixing was VFpro22 + as per shop drawings, bolt min EMBD 100mm
checkpoint | Color of RHS blades is Interpon D2525 Flat Matt Monument as per shops- All touch up paints match the actual powder coat color
checkpoint | ABL-SHP-0100 REV01 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REGULARLY ( FORTNIGHTLY ) TO SIGN OFF ON THE CHECKLIST
checklist | AM02 ALUM. SCREENS - RL
checkpoint | All screens are installed level and as per approved shop drawing and engineer's certificate
checkpoint | All blades have fully welded end caps with weep holes
checkpoint | Any existing scratches have been touched up
checkpoint | Screens are clean and free of any dust and dirt
checkpoint | All bolt fixings were M12 SS316 CONCRETE SCREWS MONUMENT, all screw fixings are G12 GEL MONUMENT, screens were installed as per shop drawing
checkpoint | Chemset used for bolt fixing was VFpro22 + as per shop drawings, bolt min EMBD 100mm
checkpoint | Color of RHS blades is Interpon D2525 Flat Matt Monument as per shops- All touch up paints match the actual powder coat color
checkpoint | ABL-SHP-0500 REV07 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REGULARLY ( FORTNIGHTLY ) TO SIGN OFF ON THE CHECKLIST
checklist | BAL01A ALUM. HANDRAIL - RL
checkpoint | All handrails are installed level and as per approved shop drawing and engineer's certificate
checkpoint | All vertical fb posts have fully welded to bottom flat bar
checkpoint | Any existing scratches have been touched up
checkpoint | Handrails are clean and free of any dust and dirt
checkpoint | All bolt fixings were M10 GEL ROD AND DOME NUT MONUMENT, handrails were installed as per shop drawing
checkpoint | Chemset used for bolt fixing was VFpro22 + as per shop drawings, bolt min EMBD 80mm
checkpoint | Mid Horizontal 25x3 CHS is welded to 2 vertical FB at both ends and rest of posts, CHS only run through a round hole with no welding
checkpoint | Color of handrail is Interpon D2525 Flat Matt Monument as per shops- All touch up paints match the actual powder coat color
checkpoint | ABL-SHP-3000 REV03 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REGULARLY ( FORTNIGHTLY ) TO SIGN OFF ON THE CHECKLIST
checklist | BAL02 GLASS BALUSTRADE - RL
checkpoint | Glass balustrades are installed level
checkpoint | Glass balustrades are installed as per approved shop drawing.
checkpoint | All gaps are following approved set out drawing and comply with BCA being less than 8mm
checkpoint | SS accessories and handrail to be Brushed #4 Linish finish
checkpoint | Top channels are connected properly and welded properly as per engineer's certificate
checkpoint | All rubbers are installed properly
checkpoint | VFPRO22+ chemset was used for fixing glass spigots
checkpoint | 4M12 SS316 Chemical anchors 100mm EMBD was used
checkpoint | ABL-SHP-4100 REV03 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REGULARLY ( FORTNIGHTLY ) TO SIGN OFF ON THE CHECKLIST
checklist | BAL03A ALUM. BALUSTRADE - RL
checkpoint | All balustrades are installed level and as per approved shop drawing and engineer's certificate
checkpoint | All vertical blades have fully welded to bottom backing flat bar for North and South balustrades, and welded to backing RHS for West balustrades
checkpoint | Any existing scratches have been touched up
checkpoint | Balustrades are clean and free of any dust and dirt
checkpoint | All bolt fixings were M12 GEL ROD AND DOME NUT MONUMENT, handrails were installed as per shop drawing
checkpoint | Chemset used for bolt fixing was VFpro22 + as per shop drawings, bolt min EMBD 100mm
checkpoint | Top folded sheet to be welded front and back with laser weld to all RHS blades neatly
checkpoint | Color of balustrade is Interpon D2525 Flat Matt Monument as per shops- All touch up paints match the actual powder coat color
checkpoint | ABL-SHP-3100 REV05 ( North & South) and ABL-SHP-0500 REV07 ( West) were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REGULARLY ( FORTNIGHTLY ) TO SIGN OFF ON THE CHECKLIST
checklist | BAL04 GLASS BALUSTRADE - RL
checkpoint | Glass balustrades are installed level
checkpoint | Glass balustrades are installed as per approved shop drawing.
checkpoint | All gaps are following approved set out drawing and comply with BCA being less than 8mm
checkpoint | SS accessories and handrail to be Brushed #4 Linish finish
checkpoint | Top channels are connected properly and welded properly as per engineer's certificate
checkpoint | All rubbers are installed properly
checkpoint | VFPRO22+ chemset was used for fixing glass spigots
checkpoint | 4M12 SS316 Chemical anchors 100mm EMBD was used
checkpoint | ABL-SHP-3250 REV02 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REGULARLY ( FORTNIGHTLY ) TO SIGN OFF ON THE CHECKLIST