## LVL
Inspection and Test Plan
Project: | 6-14 Cambridge street, Epping NSW 2121
AREA : | RL
ITP TEMPLATE CREATED : | 30.09.2024
CURRENT VERSION/DATE : | 1
Item : | BAL01B GLASS BALUSTRADE
Item | S.NO | Activity | Anjie Sign Off | REV 1 | REV 2 | COMMENT | RCC Sign Off | Date | COMMENT
GLASS BALUSTRADE | 1 | Glass balustrades are installed level | M.S
| 2 | Glass balustrades are installed as per approved shop drawing. | M.S
| 3 | All gaps are following approved set out drawing and comply with BCA being less than 125mm | M.S
| 4 | SS accessories and handrail to be Brushed #4 Linish finish | M.S
| 5 | Top channels are connected properly and welded properly as per engineer's certificate | M.S
| 6 | All rubbers are installed properly | M.S
| 7 | VFPRO22+ chemset was used for fixing glass spigots | M.S
| 8 | 4M12 SS316 Chemical anchors 100mm EMBD was used | M.S
| 9 | ABL-SHP-4000 REV04 were used for installation on site | M.S
INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REQULARLY ( FORTHNIGHTLY ) TO SIGN OFF ON THE CHEKLIST
Signoff Section
Full Name |  |  | Company | Position |  |  | Signature
MARJAN SOLTANI |  |  | ANJIE | PROJECT MANAGER |  |  | M.S