## LVL
Inspection and Test Plan
Project: | 6-14 Cambridge street, Epping NSW 2121
AREA : | RL
ITP TEMPLATE CREATED : | 30.09.2024
CURRENT VERSION/DATE : | 1
Item : | BAL03A ALUM. ALUMINIUM BALUSTRADE
Item | S.NO | Activity | Anjie Sign Off | REV 1 | REV 2 | COMMENT | RCC Sign Off | Date | COMMENT
ALUM. VERTICAL SCREENS | 1 | All balustrades are installed level and as per approved shop drawing and engineer's certificate | M.S | - | -
| 2 | All vertical blades have fully welded to bottom backing flat bar for North and South balustrades, and welded to backing RHS for West balustrades | M.S | - | -
| 3 | Any existing scratches have been touched up | M.S | - | -
| 4 | Balustrades are clean and free of any dust and dirt | M.S | - | -
| 5 | All bolt fixings were M12 GAL ROD AND DOME NUT MONUMENT, handrails were installed as per shop drawing | M.S | - | -
| 6 | Chemset used for bolt fixing was VFpro22 + as per shop drawings, bolt min EMBD 100mm | M.S | - | -
| 7 | Top folded sheet to be welded front and back with laser weld to all RHS blades neatly | M.S | - | -
| 8 | Color of balustrade is Interpon D2525 Flat Matt Monument as per shops- All touch up paints match the actual powdercoat color | M.S | - | -
| 9 | ABL-SHP-3100 REV05 ( North & South) and ABL-SHP-0500 REV07 ( West) were used for installation on site | M.S | - | -
INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REQULARLY ( FORTHNIGHTLY ) TO SIGN OFF ON THE CHEKLIST
Signoff Section
Full Name |  |  | Company | Position |  |  | Signature
MARJAN SOLTANI |  |  | ANJIE | PROJECT MANAGER |  |  | M.S