## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | AM01A ALUM. VERTICAL SCREENS
section | Details
checkpoint | All screens are installed level and as per approved shop drawing and engineer's certificate
checkpoint | All blades have fully welded to bottom flat bar
checkpoint | Any existing scratches have been touched up
checkpoint | Screens are clean and free of any dust and dirt
checkpoint | All bolt fixings were M10 GAL ROD AND DOME NUT MONUMENT, screens were installed as per shop drawing
checkpoint | Chemset used for bolt fixing was VFpro22 + as per shop drawings, bolt min EMBD 100mm
checkpoint | Color of RHS blades is Interpon D2525 Flat Matt Monument as per shops- All touch up paints match the actual powdercoat color
checkpoint | ABL-SHP-0100 REV01 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REQULARLY ( FORTHNIGHTLY ) TO SIGN OFF ON THE CHEKLIST
checklist | AM02 ALUM, VERTICAL SCREENS
section | Details
checkpoint | All screens are installed level and as per approved shop drawing and engineer's certificate
checkpoint | All blades have fully welded end caps with weep holes
checkpoint | Any existing scratches have been touched up
checkpoint | Screens are clean and free of any dust and dirt
checkpoint | All bolt fixings were M12 SS316 CONCRETE SCREWS MONUMENT, all scew fixings are G12 GAL MONUMENT, screens were installed as per shop drawing
checkpoint | Chemset used for bolt fixing was VFpro22 + as per shop drawings, bolt min EMBD 100mm
checkpoint | Color of RHS blades is Interpon D2525 Flat Matt Monument as per shops- All touch up paints match the actual powdercoat color
checkpoint | ABL-SHP-0500 REV07 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REQULARLY ( FORTHNIGHTLY ) TO SIGN OFF ON THE CHEKLIST
checklist | BAL01A ALUM, ALUMINIUM HANDRAIL
section | Details
checkpoint | All handrails are installed level and as per approved shop drawing and engineer's certificate
checkpoint | All vertical fb posts have fully welded to bottom flat bar
checkpoint | Any existing scratches have been touched up
checkpoint | Handrails are clean and free of any dust and dirt
checkpoint | All bolt fixings were M10 GAL ROD AND DOME NUT MONUMENT, handrails were installed as per shop drawing
checkpoint | Chemset used for bolt fixing was VFpro22 + as per shop drawings, bolt min EMBD 80mm
checkpoint | Mid Horizontal 25x3 CHS is welded to 2 vertical FB at both ends and rest of posts, CHS only run through a round hole with no welding
checkpoint | Color of handrail is Interpon D2525 Flat Matt Monument as per shops- All touch up paints match the actual powdercoat color
checkpoint | ABL-SHP-3000 REV03 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REQULARLY ( FORTHNIGHTLY ) TO SIGN OFF ON THE CHEKLIST
checklist | BAL01B GLASS, BALUSTRADE
section | Details
checkpoint | Glass balustrades are installed level
checkpoint | Glass balustrades are installed as per approved shop drawing.
checkpoint | All gaps are following approved set out drawing and comply with BCA being less than 125mm
checkpoint | SS accessories and handrail to be Brushed #4 Linish finish
checkpoint | Top channels are connected properly and welded properly as per engineer's certificate
checkpoint | All rubbers are installed properly
checkpoint | VFPRO22+ chemset was used for fixing glass spigots
checkpoint | 4M12 SS316 Chemical anchors 100mm EMBD was used
checkpoint | ABL-SHP-4000 REV04 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REQULARLY ( FORTHNIGHTLY ) TO SIGN OFF ON THE CHEKLIST
checklist | BAL02 GLASS, BALUSTRADE
section | Details
checkpoint | Glass balustrades are installed level
checkpoint | Glass balustrades are installed as per approved shop drawing.
checkpoint | All gaps are following approved set out drawing and comply with BCA being less than 125mm
checkpoint | Aluminium handrail to be installed level and to vertical posts
checkpoint | Cover plates to be installed for each posts
checkpoint | All rubbers are installed properly
checkpoint | VFPRO22+ chemset was used for fixing glass anchors
checkpoint | 4M12 SS316 Chemical anchors 100mm EMBD was used
checkpoint | ABL-SHP-4100 REV03 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REQULARLY ( FORTHNIGHTLY ) TO SIGN OFF ON THE CHEKLIST
checklist | BAL03A ALUM, ALUMINIUM BALUSTRADE
section | Details
checkpoint | All balustrades are installed level and as per approved shop drawing and engineer's certificate
checkpoint | All vertical blades have fully welded to bottom backing flat bar for North and South balustrades, and welded to backing RHS for West balustrades
checkpoint | Any existing scratches have been touched up
checkpoint | Balustrades are clean and free of any dust and dirt
checkpoint | All bolt fixings were M12 GAL ROD AND DOME NUT MONUMENT, handrails were installed as per shop drawing
checkpoint | Chemset used for bolt fixing was VFpro22 + as per shop drawings, bolt min EMBD 100mm
checkpoint | Top folded sheet to be welded front and back with laser weld to all RHS blades neatly
checkpoint | Color of balustrade is Interpon D2525 Flat Matt Monument as per shops- All touch up paints match the actual powdercoat color
checkpoint | ABL-SHP-3100 REV05 ( North & South) and ABL-SHP-0500 REV07 ( West) were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REQULARLY ( FORTHNIGHTLY ) TO SIGN OFF ON THE CHEKLIST
checklist | BAL04 GLASS, BALUSTRADE
section | Details
checkpoint | Glass balustrades are installed level
checkpoint | Glass balustrades are installed as per approved shop drawing.
checkpoint | All gaps are following approved set out drawing and comply with BCA being less than 8mm
checkpoint | SS accessories and handrail to be Brushed #4 Linish finish
checkpoint | Top channels are connected properly and welded properly as per engineer's certificate
checkpoint | All rubbers are installed properly
checkpoint | VFPRO22+ chemset was used for fixing glass spigots
checkpoint | 4M12 SS316 Chemical anchors 100mm EMBD was used
checkpoint | ABL-SHP-3250 REV02 were used for installation on site
label | INSPECTION WAS DONE MOSTLY VISUALLY ON SITE BY SITE TEAM AND PHOTOS WERE PROVIDED TO PROJECT MANAGER - ON SITE INSPECTION ALSO WAS DONE BY THE PROJECT MANAGER ( MARJAN SOLTANI ) - ANJIE IS RESPONSIBLE TO CHECK ALL THE ABOVE ITEMS REQULARLY ( FORTHNIGHTLY ) TO SIGN OFF ON THE CHEKLIST