## PVC
type | name | values
checklist-flat | SikaPlan unbonded PVC with grout control
checkpoint | Scope Description with slab/wall area identification
text | SOW description
button | Attach TDS for application
checkpoint | Substrate Acceptance
button | Substrate washed / cleaned & assessed for surface uniformity (photos attached below) | Yes,No
button | Substrate temperature is not less than 10*C and no greater then 35*C as per TDS Service Temperature | Yes,No
button | Substrate free from pooling or ponding water, and adequate fall in substrate | Yes,No
label | If any of these checkpoints fail information and required action by builder provided in comments below
checkpoint | Geotextile Cushion Layer
button | Geotextile laid with 50mm overlap? | Yes,No
button | Laps taped? | Yes,No
checkpoint | Membrane Installation
button | Substrate free from pooling or ponding water? | Yes,No
button | Membrane installed with minimum 40mm overlap? | Yes,No
button | Sika Dilatec Tape installed to any terminations where required? | Yes,No
button | All Dilatec Tape terminations welded as per manufacturer's specification? | Yes,No
checkpoint | PVC Waterstop (Construction Joins and Compartments)
button | Waterbar installed along construction joint to match grout control compartment where possible? | Yes,No,N/A
button | Waterbar installed to create 150m2 compartments? | Yes,No,N/A
button | Waterbar installed along blinded wall where required? | Yes,No,N/A
button | Waterbar installed along formwork where insitu wall will be installed where required? | Yes,No,N/A
button | All jig weld joins fully fused? | Yes,No,N/A
checkpoint | Grout Control To Compartments
button | Grout hose installed as per manufacturer's layout and specification? | Yes,No,N/A
button | Grout flanges installed to hose ends? | Yes,No,N/A
button | Sufficient hose included to reach proposed/agreed injection box location? | Yes,No,N/A
checkpoint | Construction Joins - Hydrophilic Waterstop and Grout Hose
button | Grout hose installed as per manufacturer's layout and specification? | Yes,No,N/A
button | Sufficient hose included to reach proposed injection box location? | Yes,No,N/A
button | Hydrophilic Waterstop installed to manufacturer's specification? | Yes,No,N/A
checkpoint | Post Steel Installation
button | Injection box for grout control system installed to manufacturer's specification? | Yes,No,N/A
button | Hose for grout control system connected with 300mm excess beyond injection box? | Yes,No,N/A
button | Injection box for SikaFuko CJ installed to manufacturer's specification? | Yes,No,N/A
button | Hose for for SikaFuko CJ connected with 300mm excess beyond injection box | Yes,No,N/A
checkpoint | Manufacturer Inspection
label | Manufacturer's Warranty Certificate attached below