## Master List Templates
Id | Type | Name | Values | Prompting Name
b7f460f6-67c6-57bd-aed7-612cc3cb240a | checklist | Add Daily Cassette Log |  | Daily Cassette Log -
299c3fee-b807-53b1-a7ee-3ce91cfec21f | checkpoint-no-value | Date:
e5ab19af-90b5-4328-9a8b-ee0707087643 | textbox
0d491264-86a4-5b6c-a7dc-196361e9f477 | checkpoint-no-value | Cassette Number:
8e11a44b-51f7-4a8f-9494-ec9e467452ec | textbox
5dacc027-cdc7-5b10-956b-92513c661cee | checkpoint-no-value | Record any delays:
22cd20b8-86af-49a9-97d4-39d5b860ca1a | textbox
f0e40656-5365-51e6-8fb7-a4d5e9ff5656 | checkpoint-no-value | Wind/Weather Conditions:
5114a122-dcf7-44a7-be38-8623182196af | textbox
0edbd7b2-6f3d-5b01-b219-c40aa5f7b2d9 | checkpoint-no-value | Comments/Issues/Observations:
a6aebd36-6433-4aca-b8f4-ef6216c059cf | textbox
04dcdab0-54dd-53d3-94fd-691c487ec5c4 | checklist | Add Dayworks Checklist |  | Dayworks -
ee0383ca-3fd8-5b25-952e-ae0e4101f788 | checkpoint | Day Work Details
d27d8079-cce6-47f2-bc8f-5447bd0b63c3 | textbox | NTSC / SI #:
d63889f7-ee5a-4b1a-8284-614d5f938189 | textbox | Labours (HR)
926bb36c-59db-4b70-828c-6bc1bf2ce049 | textbox | Work Description:
693bbb1a-ade5-4140-a549-223cae16f4cb | textbox | Materials:
6d1abe7d-16c2-45ff-b354-7f74775359b8 | textbox | SWP Representative. Prepared By:
7e548609-67fa-4b3f-91fa-027d546e556f | textbox | Client Representative. Confirmed By:
30467075-d5d2-5d5d-a049-21ffde42c097 | signoff | Request Signature Signoff
14820da1-b35a-5766-9286-d0ab4ea86d40 | checklist | Add Defect Checklist |  | Defect -
9925937c-68cd-5073-88f2-e8d459d1aa53 | checkpoint | Defect details recorded
9b18e909-7530-4d08-ad54-acb417409980 | textbox | Explanation of defect:
3af60290-922d-4e09-aeb9-b795186cbbd5 | textbox | Area:
da7b5fcc-182d-4ccf-ade5-02dfaae6dedb | textbox | Party responsible for damages:
f37cdc9e-47d2-43c7-b8ce-36034d624bbc | textbox | Efforts required for repair:
16d78d9b-0a7d-4e07-bb38-68e664e6d30e | textbox | Man hours required for repair:
7900e5b5-e926-5e1e-925a-123dad3334d3 | signoff | Request Approval from Main Contractor
2114e461-656d-5d42-a97e-9420a90df687 | checkpoint | Defect Fixed
e49cdba4-cacd-5ac7-a72a-31b7bc0a6817 | signoff | Request Defect signoff
85c80cd8-cbdc-53a5-9efe-afaeb4c1494d | checklist | Add Delay Checklist |  | Delay Checklist
a5b58d36-b437-5cab-b363-87181133464a | checkpoint-no-value | Delay details.
ae5b692f-ee75-4a3d-90e7-43a6b2bca49e | textbox | Date:
8e11a44b-51f7-4a8f-9494-ec9e467452ec | textbox | Description:
22cd20b8-86af-49a9-97d4-39d5b860ca1a | textbox | Area/Grids:
e5ab19af-90b5-4328-9a8b-ee0707087643 | textbox | Wind/Weather Conditions:
8a6c51f4-eee9-5345-926b-2cfbe8d0c647 | checklist | Add Final Inspection Checklist |  | Final inspection
f0ffd1e2-3dab-50f3-be12-aeb1ec69baa9 | checkpoint | Final inspection
5c48b2f9-7155-5010-a625-9c61273b1f4a | textbox | Date
cd590b2d-dfd9-5926-aa7f-cbbffee96ba3 | textbox | Area/elevation/grids
f185db39-ef5a-566f-a627-b84ed061402b | textbox | Description
bc73c8d4-7e08-5fa4-a4f2-97028cc937d1 | note | Attach Photos
6fd84f98-7125-519a-b6bb-f8f9a6dfaaf3 | signoff | Request Signature Signoff
28a9a391-11e7-5c0d-8371-9e7e8c6a8785 | checklist | Add Flood Testing Checklist |  | Flood Test Area:
8a4eaf28-9371-58c4-85f6-db197a9447a0 | checkpoint | Is area fully finished, QA’d and ready to be tested
24935fb7-5fb8-5299-a92e-a2004d25e833 | checkpoint-no-value | Flood test details
dc968f8f-9cf1-485a-a65f-e4087427ee32 | textbox | Date:
b0fb2bc4-3c3c-47bb-93fe-add4a651804d | textbox | Area tested:
befd486d-6456-4e39-ba95-1395566ebfda | textbox | Duration:
3fff6840-5866-4f4c-96c8-494f7e9efd79 | button | Have you checked regularly for leaks | Yes, No, N/A
050fef10-15f2-4590-ba62-2a0b1b1b0a29 | button | Is there rain in the forecast | Yes, No, N/A
b9de0cd4-9c7a-42cb-89ee-535d7ebdcd00 | button | Have all leaks been repaired | Yes, No, N/A
b3a66885-67d4-50d9-b9b0-ee0c6d8d5e64 | checkpoint | Flood test complete
5d04628a-e7a1-4bd7-b9ee-92a88ef12e94 | button | Have the plugs been removed from the drains | Yes, No, N/A
b74c91b9-0371-4641-ad5b-1c9d76ee0c77 | button | Debris and materials removed from the gutter/membrane/roof | Yes, No, N/A
38444c32-3df0-5eb8-b810-e1ffee34aa4d | signoff | Sign Off
31f884dc-4dfa-5171-9626-9f8a1060529d | checklist | Add Variation Checklist |  | Variation Details -
af43077e-903d-5d88-8da8-e50a24463098 | checkpoint | Variation Details Approved
28d26279-c304-4689-8317-1deb797dc8fe | textbox | Reference/Drawing/Instruction Number
2247155b-6de8-434c-a1e1-058d724a6a62 | textbox | Variation Area
ae7fc046-dca9-4fab-98f8-374caeb044ec | textbox | Materials & labour breakdown
822653e1-1a8d-5c1e-9229-bee00e9e7e9a | signoff | Request Variation Acknowledgement
8d20db40-ceeb-512f-b832-5bd4676ee2c5 | checkpoint | Variation Completed
d302c95c-762e-5e5c-a32b-f0e8b483eb06 | signoff | Request Variation Signoff
6dc7d3da-43aa-5117-a699-3ded3248a90c | checklist | FiberTite to concrete checklist |  | FiberTite to concrete checklist
e1a8eb4f-234a-5b06-b9f7-d276be4ee242 | section | Pre start
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
7103836d-412f-5715-800f-6afbac969feb | checkpoint | Visual inspection of substrate ready for SWP
d219dab5-650f-5137-bfa3-7713ce0a690e | checkpoint | QA document received from previous trade from main contractor
064c8193-ffc3-51bb-8d83-844ae5209881 | checkpoint | Large holes filled with grout by others
c4e85f06-29ad-5f78-90f3-7a93a366da3b | checkpoint | All lumps and sharp concrete bits ground/hammered down
036543a6-b42f-5009-ac49-2c848d2eb466 | section | Concrete substrate
aca2494a-3a3f-551a-8a5c-101bb3252566 | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
99886534-bea6-5689-9ca7-6716555c119c | section | FiberTite
6c20861f-37eb-5d15-bf66-3cf3639622e7 | checkpoint | Prime substrate where required
19869c98-c957-5a4d-b97f-adff0bbc1b28 | checkpoint | Adhesive installed to substrate
d134af65-9a47-56fc-8f50-c057ef806c16 | checkpoint | Laying of membrane into adhesive
c901c743-ed3d-5c30-bf83-f4efe837a5d2 | checkpoint | Broom/rolling of membrane
1ec6b720-94a8-5859-b4f9-b62e6db04951 | checkpoint | Wipe and clean laps prior to welding
e1be64d7-af99-524b-bc48-c26bc7d10686 | checkpoint | Test weld with welding machine
ab80f606-30f7-5863-b382-d6227f85742a | checkpoint | Probe of seam with QA hook
f6195677-c44c-5db8-ade0-55d3e47922ab | section | Sumps
6cf2a9b4-c57b-505a-82b6-687c954968c5 | checkpoint | Sealant installed to dropper flange under membrane
bc1f549d-9e79-5e5a-8194-17fed3c84b29 | checkpoint | Membrane dressed in to outlets
9b9d9376-0a03-5822-9feb-457d57eb270d | checkpoint | Clamp/rings/basket installed
e6db231c-49f8-5f3e-8809-f640909388e8 | checkpoint | Flood test
f0705160-d24c-5423-b145-d8327c13dd59 | section | ILD report
0e6c9afb-4fa3-47e9-886b-7e96dc78676b | checkpoint | ILD report
8e83a7db-cbc0-55c0-ba24-bb68d3cf267e | section | Fiberclad flashing
b0fca163-ac91-56b1-a7c2-9dd3b1b4ae62 | checkpoint | Installed correctly according to specifications ( right way around )
29250ace-2f06-5e8f-a594-6009a152747b | checkpoint | Fixing and welding done according to specifications and details
4276b962-a179-4df0-b844-27cc58383ea7 | checkpoint | Probe of seam with QA hook
bd08d8ef-758c-50d4-bd13-c5e4a2658fb2 | section | Pressure bar installed
f2871290-74ee-4103-be20-0bb9abff8453 | checkpoint | Installed correctly according to specifications ( right way around )
7e4f1f68-4dd7-5cfb-977f-ccfab6e3365c | checkpoint | Fixings done according to specifications and details
2ab39d91-f95b-5f9e-8cfe-2cb752424161 | checkpoint | Prime of Substrate where required
75a630e1-9e71-5e13-a75b-6ac118742939 | checkpoint | Sealant installed
93e97369-7f72-54d2-9a4c-c98f13f64345 | section | Over flashings
974a2163-9e72-5cbe-8edf-75321b9da9cb | checkpoint | Over flashings has a separation barrier
378c7421-d227-420f-a98d-a8cf9c4ab232 | checkpoint | Fixings done according to specifications and details
52aa4514-1c56-5a33-a041-81270e0b7bbb | checkpoint | Primer of Substrate
e9896931-740d-4705-8018-c9f642bd381a | checkpoint | Sealant installed
f46dcb38-e25c-5d04-b7dc-f03aeb2c40c2 | section | Review and sign off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
fc303b23-3010-523e-b47d-84901362e177 | checkpoint | All installation work completed, checked and reviewed as per specifications
2e691dee-b203-5515-9b2b-c309ddadd52e | signoff | Client/main contractor sign off
9579d0b3-48b0-57bc-883b-ee76fac98d42 | checklist | FiberTite to plywood checklist |  | FiberTite to plywood checklist
e1a8eb4f-234a-5b06-b9f7-d276be4ee242 | section | Pre start
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
7103836d-412f-5715-800f-6afbac969feb | checkpoint | Visual inspection of substrate ready for SWP
d219dab5-650f-5137-bfa3-7713ce0a690e | checkpoint | QA document received from previous trade from main contractor
eb41fc88-e015-590a-94bf-0e5a3f031f4e | checkpoint | Visual check no screws/nails/fixings popping up
9196c211-3b23-5927-89ad-38c09ac34bb5 | checkpoint | Visual check that joints are flush and even
c2faf38a-48cf-52bc-b03b-b0ef3cd187ea | section | Plywood Substrate
aca2494a-3a3f-551a-8a5c-101bb3252566 | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
850507ea-7454-5465-b03b-d2958de3fe80 | section | ILD Mesh System installed
3df9c246-9247-58f9-8a4a-84441ce2930e | checkpoint | ILD System installed as per specification
0336b682-e5eb-5c7f-886a-3df72cf6d5f0 | checkpoint | ILD test plate installed
99886534-bea6-5689-9ca7-6716555c119c | section | FiberTite
6c20861f-37eb-5d15-bf66-3cf3639622e7 | checkpoint | Prime substrate where required
19869c98-c957-5a4d-b97f-adff0bbc1b28 | checkpoint | Adhesive installed to substrate
d134af65-9a47-56fc-8f50-c057ef806c16 | checkpoint | Laying of membrane into adhesive
c901c743-ed3d-5c30-bf83-f4efe837a5d2 | checkpoint | Broom/rolling of membrane
1ec6b720-94a8-5859-b4f9-b62e6db04951 | checkpoint | Wipe and clean laps prior to welding
e1be64d7-af99-524b-bc48-c26bc7d10686 | checkpoint | Test weld with welding machine
ab80f606-30f7-5863-b382-d6227f85742a | checkpoint | Probe of seam with QA hook
f6195677-c44c-5db8-ade0-55d3e47922ab | section | Sumps
6cf2a9b4-c57b-505a-82b6-687c954968c5 | checkpoint | Sealant installed to dropper flange under membrane
55ddb11e-2110-571b-a1fd-63684e7a3701 | checkpoint | Membrane dressed into outlets
9b9d9376-0a03-5822-9feb-457d57eb270d | checkpoint | Clamp/rings/basket installed
e6db231c-49f8-5f3e-8809-f640909388e8 | checkpoint | Flood test
f0705160-d24c-5423-b145-d8327c13dd59 | section | ILD report
23fbc3b6-1d00-44b1-941f-1dd477488f1b | checkpoint | ILD report
1d33ba91-381d-5d50-82cc-ea7ee43ae967 | section | Fibre clad flashing
b0fca163-ac91-56b1-a7c2-9dd3b1b4ae62 | checkpoint | Installed correctly according to specifications ( right way around )
29250ace-2f06-5e8f-a594-6009a152747b | checkpoint | Fixing and welding done according to specifications and details
5c37d5fd-e879-4671-b971-71fb91ad857b | checkpoint | Probe of seam with QA hook
bd08d8ef-758c-50d4-bd13-c5e4a2658fb2 | section | Pressure bar installed
0a55e0aa-d342-4e82-9ac4-58ab5b17ec79 | checkpoint | Installed correctly according to specifications ( right way around )
7e4f1f68-4dd7-5cfb-977f-ccfab6e3365c | checkpoint | Fixings done according to specifications and details
2ab39d91-f95b-5f9e-8cfe-2cb752424161 | checkpoint | Prime of Substrate where required
75a630e1-9e71-5e13-a75b-6ac118742939 | checkpoint | Sealant installed
93e97369-7f72-54d2-9a4c-c98f13f64345 | section | Over flashings
974a2163-9e72-5cbe-8edf-75321b9da9cb | checkpoint | Over flashings has a separation barrier
f2e1d317-e1c4-4cbe-8758-341618d113bf | checkpoint | Fixings done according to specifications and details
e39d9f29-a2a2-4115-b7e5-cd4773e290c4 | checkpoint | Prime of Substrate where required
6712a71f-be10-4cb9-a337-c9905244bc5c | checkpoint | Sealant installed
f46dcb38-e25c-5d04-b7dc-f03aeb2c40c2 | section | Review and sign off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
fc303b23-3010-523e-b47d-84901362e177 | checkpoint | All installation work completed, checked and reviewed as per specifications
2e691dee-b203-5515-9b2b-c309ddadd52e | signoff | Client/main contractor sign off
f01e1269-08ad-59e2-b007-6b4b5ed7770a | checklist | FiberTite to plywood warm roof checklist |  | FiberTite to plywood warm roof checklist
e1a8eb4f-234a-5b06-b9f7-d276be4ee242 | section | Pre start
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
7103836d-412f-5715-800f-6afbac969feb | checkpoint | Visual inspection of substrate ready for SWP
d219dab5-650f-5137-bfa3-7713ce0a690e | checkpoint | QA document received from previous trade from main contractor
eb41fc88-e015-590a-94bf-0e5a3f031f4e | checkpoint | Visual check no screws/nails/fixings popping up
9196c211-3b23-5927-89ad-38c09ac34bb5 | checkpoint | Visual check that joints are flush and even
c2faf38a-48cf-52bc-b03b-b0ef3cd187ea | section | Plywood Substrate
b56fe38e-ceb1-5f3c-a743-e04ba20c9eb5 | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for VCL
5fd7e401-7ecf-5005-bb0c-029d0ecc6349 | section | Vapor control layer
73de4c79-3f90-5044-87ff-266cae56ce98 | checkpoint | Substrate clean, dry, free of debris
79d39a41-da40-5f5d-ac0b-69b606bd4b3a | checkpoint | Z flashing installed
02f934ed-fe57-5ee8-a748-0a249675588a | checkpoint | VCL installed and covered all surface
31aa2278-65c8-5b81-9b4c-ca7297065bb6 | checkpoint | VCL lapped with a minimum of 100mm side and end laps
081f4c6d-dc68-5faa-a9d5-6135f30b3647 | section | Insulation
aa298f9d-2cd4-5697-a0c1-e27f7c34c45d | checkpoint | VCL clean, dry, free of debris prior to install
bc5fed37-1379-5a67-9729-2094a663832b | checkpoint | VCL has been checked for damages and repaired
32002d9e-9966-58a4-82a4-5d5e60483fc6 | checkpoint | Closure flashings installed correctly
98d6e376-aedb-54ea-aa16-067904339d5e | checkpoint | Specified insulation board installed
d233c62e-d7fc-5559-a846-b8b60d11e882 | checkpoint | Boards tightly butted
3985d604-14e7-5a82-943a-648a3293f0d9 | checkpoint | Fixing plan attached
95c85948-319a-5e48-84a0-fc0e3f56f7e7 | checkpoint | Installed as per fixing plan if no HDP board
65885843-748f-5b00-8218-0f2a691a3d0c | section | ILD system installed
96c8423b-958e-59ed-a2e4-f7edcdb4add4 | checkpoint | ILD System installed as per specs
0336b682-e5eb-5c7f-886a-3df72cf6d5f0 | checkpoint | ILD test plate installed
94ee1aa1-1f17-55d1-8e4a-e0d46100e85e | section | HDP board
251388a7-0a7c-5e2a-a302-678daf7cd2a8 | checkpoint | PIR clean, dry, free of debris prior to install
8745aaad-72d4-4c12-b5fc-002ef7714723 | checkpoint | Fixing plan attached
be02a6be-4fb6-5df5-93ed-3c9370a3eb9a | checkpoint | HDP installed tightly butted in brick pattern
73b7991f-acd8-504b-b879-f8ae3faf40a6 | checkpoint | Installed as per fixing plan
99886534-bea6-5689-9ca7-6716555c119c | section | FiberTite
6c20861f-37eb-5d15-bf66-3cf3639622e7 | checkpoint | Prime substrate where required
19869c98-c957-5a4d-b97f-adff0bbc1b28 | checkpoint | Adhesive installed to substrate
d134af65-9a47-56fc-8f50-c057ef806c16 | checkpoint | Laying of membrane into adhesive
c901c743-ed3d-5c30-bf83-f4efe837a5d2 | checkpoint | Broom/rolling of membrane
1ec6b720-94a8-5859-b4f9-b62e6db04951 | checkpoint | Wipe and clean laps prior to welding
e1be64d7-af99-524b-bc48-c26bc7d10686 | checkpoint | Test weld with welding machine
ab80f606-30f7-5863-b382-d6227f85742a | checkpoint | Probe of seam with QA hook
f6195677-c44c-5db8-ade0-55d3e47922ab | section | Sumps
6cf2a9b4-c57b-505a-82b6-687c954968c5 | checkpoint | Sealant installed to dropper flange under membrane
bc1f549d-9e79-5e5a-8194-17fed3c84b29 | checkpoint | Membrane dressed in to outlets
9b9d9376-0a03-5822-9feb-457d57eb270d | checkpoint | Clamp/rings/basket installed
e6db231c-49f8-5f3e-8809-f640909388e8 | checkpoint | Flood test
f0705160-d24c-5423-b145-d8327c13dd59 | section | ILD report
32e47e90-856b-4d03-a607-0ab5a2e0103d | checkpoint | ILD report
1d33ba91-381d-5d50-82cc-ea7ee43ae967 | section | Fibre clad flashing
b0fca163-ac91-56b1-a7c2-9dd3b1b4ae62 | checkpoint | Installed correctly according to specifications ( right way around )
29250ace-2f06-5e8f-a594-6009a152747b | checkpoint | Fixing and welding done according to specifications and details
57ef8a65-759b-4c37-a8d1-f290f32a06b8 | checkpoint | Probe of seam with QA hook
bd08d8ef-758c-50d4-bd13-c5e4a2658fb2 | section | Pressure bar installed
1e379b80-d3ab-45b2-b6ac-08fbcd7304f8 | checkpoint | Installed correctly according to specifications ( right way around )
7e4f1f68-4dd7-5cfb-977f-ccfab6e3365c | checkpoint | Fixings done according to specifications and details
2ab39d91-f95b-5f9e-8cfe-2cb752424161 | checkpoint | Prime of Substrate where required
75a630e1-9e71-5e13-a75b-6ac118742939 | checkpoint | Sealant installed
93e97369-7f72-54d2-9a4c-c98f13f64345 | section | Over flashings
974a2163-9e72-5cbe-8edf-75321b9da9cb | checkpoint | Over flashings has a separation barrier
3f90316d-a3dc-4fb7-bcd3-c8e18a30563c | checkpoint | Fixings done according to specifications and details
eaf931cd-5353-491d-bf7a-15fadda529e5 | checkpoint | Prime of Substrate where required
3ca71e08-0a90-4870-a384-d082e4eb01a3 | checkpoint | Sealant installed
f46dcb38-e25c-5d04-b7dc-f03aeb2c40c2 | section | Review and sign off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
fc303b23-3010-523e-b47d-84901362e177 | checkpoint | All installation work completed, checked and reviewed as per specifications
2e691dee-b203-5515-9b2b-c309ddadd52e | signoff | Client/main contractor sign off
43efdbb7-dda9-4704-bb1b-c41be860e373 | checklist | FiberTite Warm Roof Fully Adhered over Concrete CIT |  | FiberTite Warm Roof Fully Adhered over Concrete CIT
2c71a3ff-1401-4534-91bc-01ddb5ea9737 | section | Pre start
581a87de-2106-4ab2-8c8f-b7bd6cd26dae | checkpoint | Area Accessible
fe319e40-a078-4007-bc3b-1e60517c8eff | checkpoint | Edge Protection installed
fe36c668-a5e2-4e5f-900d-4d24461ba320 | checkpoint | Substrate completed and handed over by others &/or QA from proceeding trades supplied by Main contractor
7459a3f5-1aec-4336-be25-074e9843bbc5 | section | Concrete Substrate
75689c20-d64b-43a3-b1a5-b67342868bfa | checkpoint | Handed over by Main contractor
2ac78209-3c53-45fe-b9da-ef1cb836b2e4 | section | Vapor Control Layer
5015e3c8-99e0-4e28-9fd2-837d37dd267c | checkpoint | Substrate clean, dry, and free of debris
d796efb6-8d90-4f31-bdc8-951df70d9a7e | checkpoint | All areas covered and sheets lapped 100mm
13ed4bf3-e657-4f48-ac54-52d39515e911 | checkpoint | All holes/penetrations patched and water tight
7608c8f9-beca-4924-aae9-fed6dc4051c0 | section | 40mm PIR board Mechanically fixed into concrete
00190dc2-f8de-46c9-8607-8b8c3b8d0b8f | checkpoint | Concrete Surface is dry prior to install
ac1242cd-9cc9-47e0-8a5a-12b67233e751 | checkpoint | Installed in brick pattern
caaafceb-89a9-42fa-94f1-047b5e719259 | checkpoint | Tightly installed, no gaps
aea9a037-93e0-48fa-b79e-fbe4d3f0ecac | checkpoint | PIR Board fixed into concrete
17163299-1d09-43c9-9314-d4da3d88ca86 | section | Tapered PIR Installed
8c1bc489-2a7f-40b6-93f1-4fde3fb1db54 | checkpoint | Surface is dry prior to install
cf3d1914-fdce-4ea9-9fbb-81e17f9f7c3f | checkpoint | 600U Board bond adhesive installed as per suppliers recommendations
ee815fda-10fe-463e-a9e4-140683763eca | checkpoint | Tapered PIR boards installed into 600U Adhesive
f25fc23d-aec3-4708-b799-f56fa8632db6 | section | HDP Board
9b22af73-5ffb-47a5-a000-2fd109494c20 | checkpoint | Tapered PIR Board dry prior to install
57556701-eae3-450a-8659-0487d5eda28a | checkpoint | 600U Board bond adhesive installed as per suppliers recommendations
392d3ea4-59ec-46a3-ba21-874141bdb17f | checkpoint | HDP Board installed into 600U Adhesive
7ab3c8ee-10de-4fc5-ad25-6d06f95aad71 | section | Fibretite Installation
d991966e-4309-4c0d-a488-35a870ee1b42 | checkpoint | HDP board clean and dry prior to install
2554ca8a-f258-4a5f-a22b-5419ed146db6 | checkpoint | Adhesive installed to substrate
1d9ebfeb-2cf9-4378-bbc2-d787b702c542 | checkpoint | Laying of membrane into adhesive
b3d33afb-3e31-41f9-8bab-e7b2342b4be8 | checkpoint | Broom/rolling of membrane
78f19460-24e8-4687-96aa-baa2bbc3a805 | checkpoint | Wipe and clean laps prior to welding
3cf1d10b-c3ea-401c-b4a3-714e67337d7c | checkpoint | Test weld with the welding machines
a5660a59-f38e-4dfe-a789-ece2520cbc43 | checkpoint | Probe of seam with QA hook
62233c75-da73-4572-a182-de4d813e9713 | section | Outlets
6650cb32-d0c3-49a1-832f-cbf35789a789 | checkpoint | Membrane dressed into drains/outlets
7908e09a-9739-40ec-ae14-2692acea90b1 | checkpoint | Clamps/Rings/Baskets installed
045dafb3-2b50-4bd8-b2ad-2a33c9178f7a | checkpoint | Outlets flood tested
050bcf48-eb33-42b4-9180-2c422bd69aa4 | checklist | Fibertite Warm Roof over DD400 checklist |  | Fibertite Warm Roof over DD400 checklist
6279699a-4eb3-4890-8ece-5a0ec511f009 | section | Pre start
128550e4-145e-47ec-b8cc-eccca7e1d9be | checkpoint | Area accesable
db7236a5-6bae-49dc-a9e6-692256a4394c | checkpoint | Edge protection and safety installed
01c052a4-d209-4b2a-b3e2-077b66cad587 | checkpoint | visual inspection of substrate ready for SWP
12e5beb7-d397-45bd-b0b9-d287ba883502 | checkpoint | Qa document recevied from main contractor
80770d37-367c-4df4-a751-4ae788a07ee2 | section | Substrate
dd3c3218-ec29-4f06-accd-92cd23d4e699 | checkpoint | Substrate screwed down in every purlin line
b5fb306d-3e84-400b-9c0f-f7f18c7b48df | checkpoint | Substrate has been cleaned and washed down
ecf89b2b-1177-48ed-a573-afe3bc1d0976 | checkpoint | Roof Pan Infills
05ae41e6-2cbc-40cb-a8ad-4566dba867ba | checkpoint | Surface is dry before installing Fillets
7839f26e-c08e-4bb9-8f08-5fa71e41ad6b | checkpoint | Every pan has been filled
32dd768f-fe5b-440a-908d-78092acc6dce | section | Vapor control layer
4aecfe93-006b-4337-a9e6-9405d65c37b2 | checkpoint | Substrate clean, dry, free of debris
f587d3f0-bdb6-4d8a-997c-d2037314bac6 | checkpoint | VCL installed and covered all surface
0dc2df43-c160-4406-907e-e3fefb53a894 | checkpoint | VCL lapped with a minimum of 100mm laps
d0a43e24-d0e3-48fa-ba90-e0fc8fa55b9e | section | Insulation
dc15b881-e94b-4aa4-afc1-35d59c0e7774 | checkpoint | VCL clean, dry, free of derbris prior to install
38e88007-e163-46ca-b853-efcd286965e2 | checkpoint | All holes/penetrations patched and watertight
514b3a8a-d8ca-4db6-8ec0-96b2dd90f726 | checkpoint | Insulation board installed in a brick pattern
1cf51d72-1e66-4482-aaae-5f586e8abaaa | checkpoint | Boards tightly butted, and no gaps
0f681ae5-511c-46f2-8b1b-1ae304606e89 | checkpoint | Fixing plan attached
1d229bbc-97c8-4d52-ae74-8858bc2593e3 | checkpoint | Fixings as per fixing plan if no HDP board
cd925417-e5a2-4c00-9221-5d2803ced66c | section | HDP board
4a2e6c22-1567-4fbf-ad45-652827ea01e8 | checkpoint | Substrate dry & free of derbris prior to install
ce073e6c-99e0-45d2-aa03-c489e0e8a480 | checkpoint | Fixing plan attached
4729533e-6bb9-49d7-930e-0bed2c9f4c96 | checkpoint | HDP board installed
d084efb4-2b8e-41e8-ac6a-4755d4b790df | checkpoint | HDP installed as per fixing plan
3ccd8931-8d65-4727-96cb-0c6529031807 | section | FiberTite
288bf597-f92a-40c2-b584-29a42cebee1e | checkpoint | Correct glue as per specification
e8b17f0d-d56d-42f8-b191-17088cdfdb45 | checkpoint | Adhesive installed to substrate
afd81323-c0f5-4c08-a5a7-8bf010e662d7 | checkpoint | Laying of mebrane into adhesive
b6cd0585-62df-40cb-879f-6ca51d0f85ab | checkpoint | Broom/rolling of membrane
7f508ba6-39b5-4851-8fe2-573b53bed7b2 | checkpoint | Wipe and clean laps prior to welding
b39f7b4a-d796-4129-8fa5-cb6d454b4323 | checkpoint | Test weld with welding machine
19c07502-e4dd-4b14-98d1-d544af82927d | checkpoint | Probe of seam with QA hook
926f5c18-0a88-4b0f-9e10-31229734aad8 | section | Fibreclad flashing
b6335414-77c7-4ce6-867f-fb83c8b8142a | checkpoint | Fibreclad installed correctly
0ba0dd42-7bc4-46bb-83bf-3c81f82d7914 | checkpoint | Fixing and welding done
bceb163f-6592-4959-990a-a928a8e4282b | checkpoint | Probe of seam with QA hook
230ed0b2-c251-40cd-be1d-3b364f502498 | section | Pressurebar installed
33a1f134-aeca-4c62-bf58-6a11394d62c3 | checkpoint | Pressure bar installed correctly
b1f73b4b-03bd-4646-9eb9-e409756e778c | checkpoint | Fixings done according to specifications and details
ea20fe56-666a-4403-b928-ab06beb74e4b | checkpoint | Silicone installed
9c3f85bd-dc27-4d4e-95a8-0043a05ac3fe | section | Over flashings
f2000205-3d57-4878-8732-9e8e6dc4a3f7 | checkpoint | Over flashings has a separation barrier
589af2ca-3038-4fc1-9930-f16ed56662ec | checkpoint | Fixings done according to specifications and details
d5a5fffd-d1cc-452d-81cb-e9e13f9bfe57 | checkpoint | Primer of Substrate
5410fed7-3d52-430a-aa61-d84a2a9ab8f4 | checkpoint | Silicone installed
54800c19-9682-4bfa-8ffa-e091b50c48f6 | signoff | Review and sign off
b4a5ff1a-0860-4394-88c9-a23269e8eb05 | checkpoint | Area left clean and tidy
3e290551-4db3-44a3-ac3a-6c76be6c44a8 | checkpoint | All installation work completed, checked and reviewed as per specfications
db998f56-ad82-495f-8e5c-a58249b515cf | signoff | Client/main contractor sign off
3d8b0c41-4a1c-5df3-8908-9af17b21e585 | checklist | FiberTite warm roof to Base deck checklist |  | FiberTite warm roof to Base deck checklist
e1a8eb4f-234a-5b06-b9f7-d276be4ee242 | section | Pre start
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
7103836d-412f-5715-800f-6afbac969feb | checkpoint | Visual inspection of substrate ready for SWP
d219dab5-650f-5137-bfa3-7713ce0a690e | checkpoint | QA document received from previous trade from main contractor
8b918af5-3ed8-51c6-9bcc-55d3b9e9b617 | section | Metal deck
93f36608-9c64-5013-92eb-0efd2b6584c8 | checkpoint | Base deck screwed down in every pan and every purlin
294f700a-300a-5db5-a152-caae5f911ae3 | checkpoint | Base deck laps stitched together at 300mm centres
637992d3-c244-5950-a328-57d24a10f062 | checkpoint | Correct fixing
5fd7e401-7ecf-5005-bb0c-029d0ecc6349 | section | Vapor control layer
73de4c79-3f90-5044-87ff-266cae56ce98 | checkpoint | Substrate clean, dry, free of debris
79d39a41-da40-5f5d-ac0b-69b606bd4b3a | checkpoint | Z flashing installed
02f934ed-fe57-5ee8-a748-0a249675588a | checkpoint | VCL installed and covered all surface
31aa2278-65c8-5b81-9b4c-ca7297065bb6 | checkpoint | VCL lapped with a minimum of 100mm side and end laps
081f4c6d-dc68-5faa-a9d5-6135f30b3647 | section | Insulation
aa298f9d-2cd4-5697-a0c1-e27f7c34c45d | checkpoint | VCL clean, dry, free of debris prior to install
9c8f8b3c-d3c2-560d-aa77-af55aed0a276 | checkpoint | VCL has been cheeked for damages and repaired
32002d9e-9966-58a4-82a4-5d5e60483fc6 | checkpoint | Closure flashings installed correctly
98d6e376-aedb-54ea-aa16-067904339d5e | checkpoint | Specified insulation board installed
d233c62e-d7fc-5559-a846-b8b60d11e882 | checkpoint | Boards tightly butted
3985d604-14e7-5a82-943a-648a3293f0d9 | checkpoint | Fixing plan attached
95c85948-319a-5e48-84a0-fc0e3f56f7e7 | checkpoint | Installed as per fixing plan if no HDP board
65885843-748f-5b00-8218-0f2a691a3d0c | section | ILD system installed
96c8423b-958e-59ed-a2e4-f7edcdb4add4 | checkpoint | ILD System installed as per specs
0336b682-e5eb-5c7f-886a-3df72cf6d5f0 | checkpoint | ILD test plate installed
94ee1aa1-1f17-55d1-8e4a-e0d46100e85e | section | HDP board
251388a7-0a7c-5e2a-a302-678daf7cd2a8 | checkpoint | PIR clean, dry, free of debris prior to install
e3edb2b4-ca78-444e-882f-935640b6dcf7 | checkpoint | Fixing plan attached
be02a6be-4fb6-5df5-93ed-3c9370a3eb9a | checkpoint | HDP installed tightly butted in brick pattern
73b7991f-acd8-504b-b879-f8ae3faf40a6 | checkpoint | Installed as per fixing plan
99886534-bea6-5689-9ca7-6716555c119c | section | FiberTite
6c20861f-37eb-5d15-bf66-3cf3639622e7 | checkpoint | Prime substrate where required
19869c98-c957-5a4d-b97f-adff0bbc1b28 | checkpoint | Adhesive installed to substrate
d134af65-9a47-56fc-8f50-c057ef806c16 | checkpoint | Laying of membrane into adhesive
c901c743-ed3d-5c30-bf83-f4efe837a5d2 | checkpoint | Broom/rolling of membrane
1ec6b720-94a8-5859-b4f9-b62e6db04951 | checkpoint | Wipe and clean laps prior to welding
e1be64d7-af99-524b-bc48-c26bc7d10686 | checkpoint | Test weld with welding machine
ab80f606-30f7-5863-b382-d6227f85742a | checkpoint | Probe of seam with QA hook
f6195677-c44c-5db8-ade0-55d3e47922ab | section | Sumps
6cf2a9b4-c57b-505a-82b6-687c954968c5 | checkpoint | Sealant installed to dropper flange under membrane
bc1f549d-9e79-5e5a-8194-17fed3c84b29 | checkpoint | Membrane dressed in to outlets
9b9d9376-0a03-5822-9feb-457d57eb270d | checkpoint | Clamp/rings/basket installed
e6db231c-49f8-5f3e-8809-f640909388e8 | checkpoint | Flood test
f0705160-d24c-5423-b145-d8327c13dd59 | section | ILD report
7789ded1-da20-43fb-8c13-4e064efdbefb | checkpoint | ILD report
1d33ba91-381d-5d50-82cc-ea7ee43ae967 | section | Fibre clad flashing
b0fca163-ac91-56b1-a7c2-9dd3b1b4ae62 | checkpoint | Installed correctly according to specifications ( right way around )
29250ace-2f06-5e8f-a594-6009a152747b | checkpoint | Fixing and welding done according to specifications and details
b96fe374-06c1-486e-ba6e-f93e7d107b8c | checkpoint | Probe of seam with QA hook
bd08d8ef-758c-50d4-bd13-c5e4a2658fb2 | section | Pressure bar installed
f301144c-ed2c-4166-b347-cd618473030b | checkpoint | Installed correctly according to specifications ( right way around )
7e4f1f68-4dd7-5cfb-977f-ccfab6e3365c | checkpoint | Fixings done according to specifications and details
2ab39d91-f95b-5f9e-8cfe-2cb752424161 | checkpoint | Prime of Substrate where required
75a630e1-9e71-5e13-a75b-6ac118742939 | checkpoint | Sealant installed
93e97369-7f72-54d2-9a4c-c98f13f64345 | section | Over flashings
974a2163-9e72-5cbe-8edf-75321b9da9cb | checkpoint | Over flashings has a separation barrier
7f6c2660-8b50-464d-8020-fbca9fbc0cb7 | checkpoint | Fixings done according to specifications and details
fe2edd67-0395-4690-8e64-66e843792726 | checkpoint | Prime of Substrate where required
885964b7-842a-4511-831f-91204b0f657d | checkpoint | Sealant installed
f46dcb38-e25c-5d04-b7dc-f03aeb2c40c2 | section | Review and sign off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
fc303b23-3010-523e-b47d-84901362e177 | checkpoint | All installation work completed, checked and reviewed as per specifications
7585220a-22c1-54b7-ae2b-27990ca383c8 | checkpoint | Client/main contractor sign off
dff6ec3e-2a75-434e-b1d7-e01ed0294e11 | checkpoint | All installation work completed, checked and reviewed as per specifications
efd1414e-0d7e-5caf-99d9-3857ed59dcb2 | signoff | Client/main contractor sign off
3e458c95-5e08-5380-9683-74ec2480677c | checklist | FiberTite warm roof to CLT mechanically fixed and adhered checklist |  | FiberTite warm roof to CLT mechanically fixed and adhered checklist
e1a8eb4f-234a-5b06-b9f7-d276be4ee242 | section | Pre start
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
7103836d-412f-5715-800f-6afbac969feb | checkpoint | Visual inspection of substrate ready for SWP
d219dab5-650f-5137-bfa3-7713ce0a690e | checkpoint | QA document received from previous trade from main contractor
21507718-73e2-5cc5-b35e-3ed7fc10b39c | section | CLT Substrate
0bf40428-aadb-58df-92b1-80bf038974ab | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for primer
1f492d36-f948-53c8-a184-7a6e6da11797 | checkpoint | Installation of SA primer
5fd7e401-7ecf-5005-bb0c-029d0ecc6349 | section | Vapor control layer
73de4c79-3f90-5044-87ff-266cae56ce98 | checkpoint | Substrate clean, dry, free of debris
79d39a41-da40-5f5d-ac0b-69b606bd4b3a | checkpoint | Z flashing installed
789cfc41-4062-56f9-8876-70403094ff94 | checkpoint | Install VCL over primer
31aa2278-65c8-5b81-9b4c-ca7297065bb6 | checkpoint | VCL lapped with a minimum of 100mm side and end laps
b6fbf408-f0f7-4683-bf6d-4f8967f166f8 | checkpoint | Installation of SA primer
081f4c6d-dc68-5faa-a9d5-6135f30b3647 | section | Insulation
aa298f9d-2cd4-5697-a0c1-e27f7c34c45d | checkpoint | VCL clean, dry, free of debris prior to install
bc5fed37-1379-5a67-9729-2094a663832b | checkpoint | VCL has been checked for damages and repaired
32002d9e-9966-58a4-82a4-5d5e60483fc6 | checkpoint | Closure flashings installed correctly
d97eea37-974c-586b-baee-b4daab33805f | checkpoint | Install board adhesive in specified pattern
d233c62e-d7fc-5559-a846-b8b60d11e882 | checkpoint | Boards tightly butted
7b742e5f-bf37-51bc-b14c-8122052377e2 | section | Tapered EPS
afa97f46-988e-566c-b6a0-bf8d37e765dc | checkpoint | Insulation boards clean and dry. Free from dirt/debris ready for adhesive
2ad77196-9bd4-4bb9-9059-096fd76e161c | checkpoint | Install board adhesive in specified pattern
a0fd9e5b-7675-5c49-8878-319847029bda | checkpoint | EPS board installed into adhesive
65885843-748f-5b00-8218-0f2a691a3d0c | section | ILD system installed
96c8423b-958e-59ed-a2e4-f7edcdb4add4 | checkpoint | ILD System installed as per specs
0336b682-e5eb-5c7f-886a-3df72cf6d5f0 | checkpoint | ILD test plate installed
94ee1aa1-1f17-55d1-8e4a-e0d46100e85e | section | HDP board
251388a7-0a7c-5e2a-a302-678daf7cd2a8 | checkpoint | PIR clean, dry, free of debris prior to install
d1a42f56-cb0b-41f6-bc82-7bd697b7bf4b | checkpoint | Install board adhesive in specified pattern
722b8dc9-9ef8-5e1c-8bb4-87d887bfb9e0 | checkpoint | HDP board installed in brick pattern where possible
99886534-bea6-5689-9ca7-6716555c119c | section | FiberTite
6c20861f-37eb-5d15-bf66-3cf3639622e7 | checkpoint | Prime substrate where required
19869c98-c957-5a4d-b97f-adff0bbc1b28 | checkpoint | Adhesive installed to substrate
d134af65-9a47-56fc-8f50-c057ef806c16 | checkpoint | Laying of membrane into adhesive
c901c743-ed3d-5c30-bf83-f4efe837a5d2 | checkpoint | Broom/rolling of membrane
1ec6b720-94a8-5859-b4f9-b62e6db04951 | checkpoint | Wipe and clean laps prior to welding
e1be64d7-af99-524b-bc48-c26bc7d10686 | checkpoint | Test weld with welding machine
ab80f606-30f7-5863-b382-d6227f85742a | checkpoint | Probe of seam with QA hook
f6195677-c44c-5db8-ade0-55d3e47922ab | section | Sumps
6cf2a9b4-c57b-505a-82b6-687c954968c5 | checkpoint | Sealant installed to dropper flange under membrane
bc1f549d-9e79-5e5a-8194-17fed3c84b29 | checkpoint | Membrane dressed in to outlets
9b9d9376-0a03-5822-9feb-457d57eb270d | checkpoint | Clamp/rings/basket installed
e6db231c-49f8-5f3e-8809-f640909388e8 | checkpoint | Flood test
f0705160-d24c-5423-b145-d8327c13dd59 | section | ILD report
3264dc95-3b83-4c16-b551-a04a7005550c | checkpoint | ILD report
8e83a7db-cbc0-55c0-ba24-bb68d3cf267e | section | Fiberclad flashing
b0fca163-ac91-56b1-a7c2-9dd3b1b4ae62 | checkpoint | Installed correctly according to specifications ( right way around )
29250ace-2f06-5e8f-a594-6009a152747b | checkpoint | Fixing and welding done according to specifications and details
08f2aa89-8f09-4707-9fc9-36b9dd3e1083 | checkpoint | Probe of seam with QA hook
bd08d8ef-758c-50d4-bd13-c5e4a2658fb2 | section | Pressure bar installed
e4716001-d6af-4e4f-9da0-efa44c859d9a | checkpoint | Installed correctly according to specifications ( right way around )
7e4f1f68-4dd7-5cfb-977f-ccfab6e3365c | checkpoint | Fixings done according to specifications and details
2ab39d91-f95b-5f9e-8cfe-2cb752424161 | checkpoint | Prime of Substrate where required
75a630e1-9e71-5e13-a75b-6ac118742939 | checkpoint | Sealant installed
93e97369-7f72-54d2-9a4c-c98f13f64345 | section | Over flashings
974a2163-9e72-5cbe-8edf-75321b9da9cb | checkpoint | Over flashings has a separation barrier
2d8ff388-567d-4994-83ba-69641b279578 | checkpoint | Fixings done according to specifications and details
52aa4514-1c56-5a33-a041-81270e0b7bbb | checkpoint | Primer of Substrate
58d8a82a-fda0-4eaf-9e7d-bd72e79ab775 | checkpoint | Sealant installed
f46dcb38-e25c-5d04-b7dc-f03aeb2c40c2 | section | Review and sign off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
fc303b23-3010-523e-b47d-84901362e177 | checkpoint | All installation work completed, checked and reviewed as per specifications
7585220a-22c1-54b7-ae2b-27990ca383c8 | checkpoint | Client/main contractor sign off
3f6f1be0-434c-550b-a83c-918e0f8dfa65 | checklist | FiberTite warm roof to concrete fully adhered checklist |  | FiberTite warm roof to concrete fully adhered checklist
e1a8eb4f-234a-5b06-b9f7-d276be4ee242 | section | Pre start
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
7103836d-412f-5715-800f-6afbac969feb | checkpoint | Visual inspection of substrate ready for SWP
d219dab5-650f-5137-bfa3-7713ce0a690e | checkpoint | QA document received from previous trade from main contractor
064c8193-ffc3-51bb-8d83-844ae5209881 | checkpoint | Large holes filled with grout by others
c4e85f06-29ad-5f78-90f3-7a93a366da3b | checkpoint | All lumps and sharp concrete bits ground/hammered down
228a0b8d-e14e-5eb9-9fb6-ad4aba16f80a | section | Concrete Substrate
0bf40428-aadb-58df-92b1-80bf038974ab | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for primer
459830c0-a5e5-559e-9610-3c9d5ddf4ae1 | checkpoint | installation of SA primer
5fd7e401-7ecf-5005-bb0c-029d0ecc6349 | section | Vapor control layer
73de4c79-3f90-5044-87ff-266cae56ce98 | checkpoint | Substrate clean, dry, free of debris
79d39a41-da40-5f5d-ac0b-69b606bd4b3a | checkpoint | Z flashing installed
789cfc41-4062-56f9-8876-70403094ff94 | checkpoint | Install VCL over primer
31aa2278-65c8-5b81-9b4c-ca7297065bb6 | checkpoint | VCL lapped with a minimum of 100mm side and end laps
1f492d36-f948-53c8-a184-7a6e6da11797 | checkpoint | Installation of SA primer
081f4c6d-dc68-5faa-a9d5-6135f30b3647 | section | Insulation
aa298f9d-2cd4-5697-a0c1-e27f7c34c45d | checkpoint | VCL clean, dry, free of debris prior to install
bc5fed37-1379-5a67-9729-2094a663832b | checkpoint | VCL has been checked for damages and repaired
32002d9e-9966-58a4-82a4-5d5e60483fc6 | checkpoint | Closure flashings installed correctly
d97eea37-974c-586b-baee-b4daab33805f | checkpoint | Install board adhesive in specified pattern
98d6e376-aedb-54ea-aa16-067904339d5e | checkpoint | Specified insulation board installed
d233c62e-d7fc-5559-a846-b8b60d11e882 | checkpoint | Boards tightly butted
65885843-748f-5b00-8218-0f2a691a3d0c | section | ILD system installed
96c8423b-958e-59ed-a2e4-f7edcdb4add4 | checkpoint | ILD System installed as per specs
0336b682-e5eb-5c7f-886a-3df72cf6d5f0 | checkpoint | ILD test plate installed
94ee1aa1-1f17-55d1-8e4a-e0d46100e85e | section | HDP board
251388a7-0a7c-5e2a-a302-678daf7cd2a8 | checkpoint | PIR clean, dry, free of debris prior to install
93baa27a-23fe-5409-af5e-268e9ebd35ed | checkpoint | install board adhesive in specified pattern
722b8dc9-9ef8-5e1c-8bb4-87d887bfb9e0 | checkpoint | HDP board installed in brick pattern where possible
99886534-bea6-5689-9ca7-6716555c119c | section | FiberTite
6c20861f-37eb-5d15-bf66-3cf3639622e7 | checkpoint | Prime substrate where required
19869c98-c957-5a4d-b97f-adff0bbc1b28 | checkpoint | Adhesive installed to substrate
d134af65-9a47-56fc-8f50-c057ef806c16 | checkpoint | Laying of membrane into adhesive
c901c743-ed3d-5c30-bf83-f4efe837a5d2 | checkpoint | Broom/rolling of membrane
1ec6b720-94a8-5859-b4f9-b62e6db04951 | checkpoint | Wipe and clean laps prior to welding
e1be64d7-af99-524b-bc48-c26bc7d10686 | checkpoint | Test weld with welding machine
ab80f606-30f7-5863-b382-d6227f85742a | checkpoint | Probe of seam with QA hook
f6195677-c44c-5db8-ade0-55d3e47922ab | section | Sumps
6cf2a9b4-c57b-505a-82b6-687c954968c5 | checkpoint | Sealant installed to dropper flange under membrane
bc1f549d-9e79-5e5a-8194-17fed3c84b29 | checkpoint | Membrane dressed in to outlets
9b9d9376-0a03-5822-9feb-457d57eb270d | checkpoint | Clamp/rings/basket installed
e6db231c-49f8-5f3e-8809-f640909388e8 | checkpoint | Flood test
f0705160-d24c-5423-b145-d8327c13dd59 | section | ILD report
71c18c4d-aac3-4513-b5a5-df35af43b61f | checkpoint | ILD report
8e83a7db-cbc0-55c0-ba24-bb68d3cf267e | section | Fiberclad flashing
b0fca163-ac91-56b1-a7c2-9dd3b1b4ae62 | checkpoint | Installed correctly according to specifications ( right way around )
29250ace-2f06-5e8f-a594-6009a152747b | checkpoint | Fixing and welding done according to specifications and details
2583c1f0-6f88-4b98-b0a5-161538930eaa | checkpoint | Probe of seam with QA hook
bd08d8ef-758c-50d4-bd13-c5e4a2658fb2 | section | Pressure bar installed
515df10d-3e36-4684-943c-923950ec5678 | checkpoint | Installed correctly according to specifications ( right way around )
7e4f1f68-4dd7-5cfb-977f-ccfab6e3365c | checkpoint | Fixings done according to specifications and details
2ab39d91-f95b-5f9e-8cfe-2cb752424161 | checkpoint | Prime of Substrate where required
75a630e1-9e71-5e13-a75b-6ac118742939 | checkpoint | Sealant installed
93e97369-7f72-54d2-9a4c-c98f13f64345 | section | Over flashings
974a2163-9e72-5cbe-8edf-75321b9da9cb | checkpoint | Over flashings has a separation barrier
6ad8fbe7-0f95-4888-9d7f-28ab3ce55a40 | checkpoint | Fixings done according to specifications and details
52aa4514-1c56-5a33-a041-81270e0b7bbb | checkpoint | Primer of Substrate
1266b566-11d3-482a-be06-a2a9e444b7f1 | checkpoint | Sealant installed
f46dcb38-e25c-5d04-b7dc-f03aeb2c40c2 | section | Review and sign off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
fc303b23-3010-523e-b47d-84901362e177 | checkpoint | All installation work completed, checked and reviewed as per specifications
2e691dee-b203-5515-9b2b-c309ddadd52e | signoff | Client/main contractor sign off
874b715b-c2e8-57b7-814d-b9c5c3cbbfd4 | checklist | Metal cladding checklist |  | Metal cladding checklist
e1a8eb4f-234a-5b06-b9f7-d276be4ee242 | section | Pre start
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
8f9e43f7-1f24-50c4-b672-75b26450fc24 | checkpoint | Building wrap installed check plans and specifications and QA / handover received from main contactor
ebbb3896-f69c-57c7-a142-17f9e6009257 | checkpoint | Battens installed with the correct spacings check plans and specifications QA / handover received from previous trade from main contactor
cbae3f9d-a65b-5ab9-abcc-1d76a3a0b924 | checkpoint | visual inspection by SWP
174c99dd-ea3f-565c-8c7e-b3d74282486d | section | Rohm rails Install
cf352b48-a928-52de-86a8-2455234ad6a1 | checkpoint | flashing tape installed check plans and specifications
0054e2e3-1947-5ef9-be9a-6bbdebfd5b73 | checkpoint | Rohm rails installed with the correct spacings check plans and specifications
58645187-8c12-590c-be05-0490293dbbe0 | checkpoint | Rohm rails installed to fixing plan
a9a52574-30e1-582c-9a44-5b560c7a6c4b | section | Cladding install
a379382d-3a72-57e9-847b-cf859f2c446f | checkpoint | Cladding installed plump and straight
77497bed-77e5-5b45-a811-64749ebb686e | checkpoint | Screw pattern according to plan/specs/best practice
89c47462-a1a0-5864-999f-515fad74210b | checkpoint | Closure foam installed
47be2aa2-db15-50cd-a391-6f1c4d75281d | checkpoint | Top end turned up
35d70514-e37d-596e-a1e3-d8abb887b7a6 | section | Flashing install
682b8957-db1e-58e3-9dd0-3b342604b5e3 | checkpoint | Sealant installed with 2 continues beads
9098ae0f-9ed5-5b57-862f-967682e49383 | checkpoint | Clean excess sealant
30a5c81c-7df6-51e9-ae82-fd8677c46608 | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
c55262aa-843e-5f3e-b598-3f0421aa2dcf | checkpoint | Flashings installed as per drawings and specifications
5295a8b9-9e83-50ed-950b-3fd22b53cd44 | checkpoint | Fixings installed as per drawings and specifications
f46dcb38-e25c-5d04-b7dc-f03aeb2c40c2 | section | Review and sign off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
fc303b23-3010-523e-b47d-84901362e177 | checkpoint | All installation work completed, checked and reviewed as per specifications
2e691dee-b203-5515-9b2b-c309ddadd52e | signoff | Client/main contractor sign off
a9ed196d-c420-5331-96dc-d5a8aba8e375 | checklist | Metal gutter and downpipe checklist |  | Metal gutter and downpipe checklist
e1a8eb4f-234a-5b06-b9f7-d276be4ee242 | section | Pre start
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
7103836d-412f-5715-800f-6afbac969feb | checkpoint | Visual inspection of substrate ready for SWP
d219dab5-650f-5137-bfa3-7713ce0a690e | checkpoint | QA document received from previous trade from main contractor
cd0e9e91-6b88-51e6-a776-1b92ebf25275 | section | Gutter install
523910c9-9d10-5159-8f36-aaf76288def0 | checkpoint | Brackets installed according to drawings and specifications
7936ea84-5748-5250-9011-36b64e4023c5 | checkpoint | Gutter lapped and sealed correctly according drawings and specifications
6612c418-1657-5aee-b463-03ead9c3cd46 | checkpoint | All terminations and ends folded and sealed
c24a8949-7bec-511e-a240-172abfcaad35 | checkpoint | Expansion joints installed
79eb02fe-2355-527d-89eb-21f11c3df826 | checkpoint | Expansion joints roof flashings installed
17f7d447-2ac5-534c-8432-433a7c9b4253 | section | Downpipe install
20dfa99f-a134-5a24-a6b6-c382b6d1ee42 | checkpoint | Correct size dropper installed, riveted and sealed
0c086f81-92f0-5faf-be84-c0c4467d4610 | checkpoint | Correct downpipe brackets installed with the correct spacings
2173b63b-7731-556a-8f8d-a637d3bf6c3e | checkpoint | Down pipe installed plumb and straight
f46dcb38-e25c-5d04-b7dc-f03aeb2c40c2 | section | Review and sign off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
fc303b23-3010-523e-b47d-84901362e177 | checkpoint | All installation work completed, checked and reviewed as per specifications
2e691dee-b203-5515-9b2b-c309ddadd52e | signoff | Client/main contractor sign off
73f445e7-bfbc-5383-9f38-3ec60b4daee7 | checklist | Metal Roof checklist |  | Metal Roof checklist
e1a8eb4f-234a-5b06-b9f7-d276be4ee242 | section | Pre start
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
c9785af7-e1d8-5692-8522-446429a44ecd | checkpoint | Purlins installed and QA / handover received from previous trade from main contractor
cbae3f9d-a65b-5ab9-abcc-1d76a3a0b924 | checkpoint | visual inspection by SWP
5a0ce871-10ca-54c0-ac2d-9271dd53901e | section | Safety Mesh install
509e047a-4f33-56b5-8539-1198a90f6d6b | checkpoint | Laid and secured perpendicular to the purlins
0202d392-4a70-5c9c-bf2e-5c6f44f903c7 | checkpoint | Lap side joins by min 1 grid section
b5f05e39-199a-599b-b8df-b7a5dcce17d7 | section | Underlay installed
816f6fb7-6239-5285-8819-f8a03676cea4 | checkpoint | Correct underlay installed as per specifications
7ca5c1a6-9342-59bc-96d7-bee4aad550d6 | checkpoint | Overlapped a minimum 150mm side laps and 200mm end laps
9294f5b2-14c0-5cd6-8f96-5bda39ec417d | checkpoint | All areas covered
ffd4b62b-e896-5a38-9905-af51657dff72 | checkpoint | Underlay installed as per specifications
beeaf8f8-6df8-5ece-949f-2a62ff7d9e3b | checkpoint | Joints taped together as per drawings and specifications
94d37750-c693-5de7-b9b3-c073bc483e4e | section | Metal roof installation
4569237a-f97d-5348-b09d-e84e519c09ac | checkpoint | Drip edge installed as per drawings and specifications
30946d3c-62f8-5ffe-8aa6-76e8105f793a | checkpoint | Laid straight and perpendicular to gutter/purlins
dd623da8-cae0-56be-bf2d-71d3a6e60e95 | checkpoint | Gutter overhang as per drawings and specifications
47be2aa2-db15-50cd-a391-6f1c4d75281d | checkpoint | Top end turned up
a3391d76-f8f2-5efa-a9c0-17587568de2e | checkpoint | Bottom ends turned down
89c47462-a1a0-5864-999f-515fad74210b | checkpoint | Closure foam installed
8698bf1f-8ea3-5ccd-9992-10f00abafb81 | checkpoint | Sheets fixed in to the purlins
77497bed-77e5-5b45-a811-64749ebb686e | checkpoint | Screw pattern according to plan/specs/best practice
35d70514-e37d-596e-a1e3-d8abb887b7a6 | section | Flashing install
682b8957-db1e-58e3-9dd0-3b342604b5e3 | checkpoint | Sealant installed with 2 continues beads
9098ae0f-9ed5-5b57-862f-967682e49383 | checkpoint | Clean excess sealant
30a5c81c-7df6-51e9-ae82-fd8677c46608 | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
c55262aa-843e-5f3e-b598-3f0421aa2dcf | checkpoint | Flashings installed as per drawings and specifications
5295a8b9-9e83-50ed-950b-3fd22b53cd44 | checkpoint | Fixings installed as per drawings and specifications
f46dcb38-e25c-5d04-b7dc-f03aeb2c40c2 | section | Review and sign off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
fc303b23-3010-523e-b47d-84901362e177 | checkpoint | All installation work completed, checked and reviewed as per specifications
2e691dee-b203-5515-9b2b-c309ddadd52e | signoff | Client/main contractor sign off
3dca2560-7880-5525-83c6-2ca62471acb5 | checklist | MSR checklist |  | MSR checklist
e1a8eb4f-234a-5b06-b9f7-d276be4ee242 | section | Pre start
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
3f57a587-530a-5d44-ba1d-66f34b53d32f | checkpoint | Purlins installed and QA / handover received from main contractor
cbae3f9d-a65b-5ab9-abcc-1d76a3a0b924 | checkpoint | visual inspection by SWP
94906bf6-a130-52d7-af4e-aff651c4c264 | section | Liner deck
4e497465-918c-5a36-b03c-234ec25d9cc0 | checkpoint | Liner deck fixed down in every purlin and every pan
e3ef8791-61e1-582c-8321-c4b091b5f78a | checkpoint | Correct fixing installed
5fd7e401-7ecf-5005-bb0c-029d0ecc6349 | section | Vapor control layer
73de4c79-3f90-5044-87ff-266cae56ce98 | checkpoint | Substrate clean, dry, free of debris
79d39a41-da40-5f5d-ac0b-69b606bd4b3a | checkpoint | Z flashing installed
02f934ed-fe57-5ee8-a748-0a249675588a | checkpoint | VCL installed and covered all surface
31aa2278-65c8-5b81-9b4c-ca7297065bb6 | checkpoint | VCL lapped with a minimum of 100mm side and end laps
227a7a80-df8b-5261-8051-51cc38cd5446 | section | Acoustic board install
27e4a18b-dfeb-553b-96d5-ca92645fa53d | checkpoint | VCL clean, no ponding water, free of debris prior to install
31aaf7db-dc5b-53d0-b548-66f1d7edf8d3 | checkpoint | VCL has been cheeked for damages
b8585718-e1c8-5c8e-b7ef-9f27fcde946a | checkpoint | All holes/penetrations patched
f6fae2fd-c8fb-58ff-aac9-83c2e1afbae5 | checkpoint | Acoustic board installed
081f4c6d-dc68-5faa-a9d5-6135f30b3647 | section | Insulation
f62af3a5-4157-5cac-b068-47fd1d47e061 | checkpoint | Boards tightly butted all areas covered
6e2cfb95-c79c-5508-90f2-309d20edb3e8 | checkpoint | Correct insulation installed as per spec
b5f05e39-199a-599b-b8df-b7a5dcce17d7 | section | Underlay installed
816f6fb7-6239-5285-8819-f8a03676cea4 | checkpoint | Correct underlay installed as per specifications
7ca5c1a6-9342-59bc-96d7-bee4aad550d6 | checkpoint | Overlapped a minimum 150mm side laps and 200mm end laps
9294f5b2-14c0-5cd6-8f96-5bda39ec417d | checkpoint | All areas covered
ffd4b62b-e896-5a38-9905-af51657dff72 | checkpoint | Underlay installed as per specifications
beeaf8f8-6df8-5ece-949f-2a62ff7d9e3b | checkpoint | Joints taped together as per drawings and specifications
94d37750-c693-5de7-b9b3-c073bc483e4e | section | Metal roof installation
4569237a-f97d-5348-b09d-e84e519c09ac | checkpoint | Drip edge installed as per drawings and specifications
30946d3c-62f8-5ffe-8aa6-76e8105f793a | checkpoint | Laid straight and perpendicular to gutter/purlins
dd623da8-cae0-56be-bf2d-71d3a6e60e95 | checkpoint | Gutter overhang as per drawings and specifications
47be2aa2-db15-50cd-a391-6f1c4d75281d | checkpoint | Top end turned up
a3391d76-f8f2-5efa-a9c0-17587568de2e | checkpoint | Bottom ends turned down
89c47462-a1a0-5864-999f-515fad74210b | checkpoint | Closure foam installed
88883583-a7cc-556f-9ac2-186aee62ad0a | checkpoint | Screw pattern according to plan/specs/fixing plan
35d70514-e37d-596e-a1e3-d8abb887b7a6 | section | Flashing install
682b8957-db1e-58e3-9dd0-3b342604b5e3 | checkpoint | Sealant installed with 2 continues beads
9098ae0f-9ed5-5b57-862f-967682e49383 | checkpoint | Clean excess sealant
30a5c81c-7df6-51e9-ae82-fd8677c46608 | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
9a3f78f2-dc1c-5df8-9c5a-c69f9641878a | checkpoint | Flashings installed as per drawings and specifications and facing away from waterflow
5295a8b9-9e83-50ed-950b-3fd22b53cd44 | checkpoint | Fixings installed as per drawings and specifications
f46dcb38-e25c-5d04-b7dc-f03aeb2c40c2 | section | Review and sign off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
fc303b23-3010-523e-b47d-84901362e177 | checkpoint | All installation work completed, checked and reviewed as per specifications
2e691dee-b203-5515-9b2b-c309ddadd52e | signoff | Client/main contractor sign off
52b8a2b2-2b5b-5e0b-bd0c-37635898a790 | checklist | MSR cladding checklist |  | MSR cladding checklist
e1a8eb4f-234a-5b06-b9f7-d276be4ee242 | section | Pre start
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
c9785af7-e1d8-5692-8522-446429a44ecd | checkpoint | Purlins installed and QA / handover received from previous trade from main contractor
cbae3f9d-a65b-5ab9-abcc-1d76a3a0b924 | checkpoint | visual inspection by SWP
5fd7e401-7ecf-5005-bb0c-029d0ecc6349 | section | Vapor control layer
73de4c79-3f90-5044-87ff-266cae56ce98 | checkpoint | Substrate clean, dry, free of debris
02f934ed-fe57-5ee8-a748-0a249675588a | checkpoint | VCL installed and covered all surface
31aa2278-65c8-5b81-9b4c-ca7297065bb6 | checkpoint | VCL lapped with a minimum of 100mm side and end laps
174c99dd-ea3f-565c-8c7e-b3d74282486d | section | Rohm rails Install
c5140925-038e-5176-bd11-ec7471cfc022 | checkpoint | C channel flashings installed
cf352b48-a928-52de-86a8-2455234ad6a1 | checkpoint | flashing tape installed check plans and specifications
0054e2e3-1947-5ef9-be9a-6bbdebfd5b73 | checkpoint | Rohm rails installed with the correct spacings check plans and specifications
58645187-8c12-590c-be05-0490293dbbe0 | checkpoint | Rohm rails installed to fixing plan
081f4c6d-dc68-5faa-a9d5-6135f30b3647 | section | Insulation
f62af3a5-4157-5cac-b068-47fd1d47e061 | checkpoint | Boards tightly butted all areas covered
de003f7b-a15a-5664-a2cd-ff8a40cab34c | checkpoint | Correct PIR installed as per spec
b5f05e39-199a-599b-b8df-b7a5dcce17d7 | section | Underlay installed
816f6fb7-6239-5285-8819-f8a03676cea4 | checkpoint | Correct underlay installed as per specifications
7ca5c1a6-9342-59bc-96d7-bee4aad550d6 | checkpoint | Overlapped a minimum 150mm side laps and 200mm end laps
9294f5b2-14c0-5cd6-8f96-5bda39ec417d | checkpoint | All areas covered
ffd4b62b-e896-5a38-9905-af51657dff72 | checkpoint | Underlay installed as per specifications
beeaf8f8-6df8-5ece-949f-2a62ff7d9e3b | checkpoint | Joints taped together as per drawings and specifications
eb7cda8e-0691-55a3-b061-04bd15b9205b | section | Cladding installation
902d195a-3d0d-59e5-8aee-369dcd5b1c09 | checkpoint | Starter flashings installed
30946d3c-62f8-5ffe-8aa6-76e8105f793a | checkpoint | Laid straight and perpendicular to gutter/purlins
47be2aa2-db15-50cd-a391-6f1c4d75281d | checkpoint | Top end turned up
89c47462-a1a0-5864-999f-515fad74210b | checkpoint | Closure foam installed
88883583-a7cc-556f-9ac2-186aee62ad0a | checkpoint | Screw pattern according to plan/specs/fixing plan
35d70514-e37d-596e-a1e3-d8abb887b7a6 | section | Flashing install
682b8957-db1e-58e3-9dd0-3b342604b5e3 | checkpoint | Sealant installed with 2 continues beads
9098ae0f-9ed5-5b57-862f-967682e49383 | checkpoint | Clean excess sealant
30a5c81c-7df6-51e9-ae82-fd8677c46608 | checkpoint | Expansion joints /slip joints installed with runs longer than 12m colour steel or 8m Ali
c55262aa-843e-5f3e-b598-3f0421aa2dcf | checkpoint | Flashings installed as per drawings and specifications
5295a8b9-9e83-50ed-950b-3fd22b53cd44 | checkpoint | Fixings installed as per drawings and specifications
f46dcb38-e25c-5d04-b7dc-f03aeb2c40c2 | section | Review and sign off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
fc303b23-3010-523e-b47d-84901362e177 | checkpoint | All installation work completed, checked and reviewed as per specifications
2e691dee-b203-5515-9b2b-c309ddadd52e | signoff | Client/main contractor sign off
728f0399-a87f-51b3-a8eb-99569343357c | checklist | New Files |  | New Files
8111ace1-1386-5c1f-8290-3df28e3c8d3f | section | Details
bf27e821-390a-5a54-a126-b3a0987340c0 | checkpoint | Upload Files
81d7fa0a-af65-5e3c-9b22-51e0be54f04f | checklist | QA - Carpark MMA Checklist |  | Carpark MMA Checklist
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
fd165085-6310-55ca-872c-b70bcbb38962 | checkpoint | SSSP onsite
533bc378-7e7d-5e77-8b60-2412e7d1457a | checkpoint | Fencing demarcation installed
7ab7d63a-e684-52de-a9e5-bdcaea01bf25 | checkpoint | Site signage installed
c0e9bd74-e7d8-5ee9-bae7-2272d9eaa5db | checkpoint | Area Accessible
c79d3f4e-779d-5b99-86ed-a64d3c0b52a2 | checkpoint | Substrate complete and ready for SWP
19427c17-055d-56b0-bc35-272f71ae6351 | section | Surface Prep
7a68cce8-fa4b-5515-98e2-4b199c515fbe | checkpoint | Removal of coatings
b4e95087-beeb-585b-93ed-3533effe23d7 | checkpoint | Grind of substrate
c3e7be63-7a0d-57b6-bbe4-826e377c601a | checkpoint | Shotblast of substrate to achieve suitable profile
31dae5c9-56fd-5437-a6c8-ffc0abc5dbbe | section | Pre-start of membrane install
8ecffc91-e53d-54b1-bc2f-4a3b1a4df21a | checkpoint | Substrate dry
d2a72c8a-e2d1-5147-84e2-c53c3b0dc665 | section | Membrane install
7ed096ed-57b4-5d14-8b0b-a2f6e31be681 | checkpoint | Prime of substrate
7b3f661a-2350-5667-828a-fe221157bfae | checkpoint | Stripe out cracks
fae87579-f343-550e-af6e-717a0dd77a0c | checkpoint | Map out areas based on coverage rates for install
25f9f452-c747-5a9e-8195-d57ce07084d4 | checkpoint | Membrane layer installed
5da26dbe-4873-5ce3-a11e-4f61f428b1b1 | checkpoint | Wear layer installed and broadcast
9df19f0c-c161-5b15-993e-0b6bbfc6118b | checkpoint | Excess broadcast swept and removed
6a0250eb-606f-50c3-9c5e-dd45d1826686 | checkpoint | 1st Top coat
8b2a3e63-ed37-59ec-b44d-cf391324bf32 | checkpoint | 2nd top coat
840d5017-bec3-5286-8679-f3e06e1e0d86 | checkpoint | Site cleared and broken down
58d45799-b961-4f5d-87c3-c157cd1bac5f | checkpoint | Site cleared and broken down
82c4d50f-8d74-5251-b09e-3813fa35f160 | checklist | QA - Fiberglass System Checklist |  | Fiberglass System Checklist
a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
c79d3f4e-779d-5b99-86ed-a64d3c0b52a2 | checkpoint | Substrate complete and ready for SWP
19427c17-055d-56b0-bc35-272f71ae6351 | section | Surface Prep
235d3743-68af-5201-acd3-528cc7d2a23b | checkpoint | Concrete free of contaminants
cbe3b648-f69d-5966-96ed-24676486c18f | checkpoint | Concrete flat and smooth
736d89c1-1ce6-5946-a1ce-e48b869e1782 | checkpoint | Bug holes in plinths filled and smooth
d2a72c8a-e2d1-5147-84e2-c53c3b0dc665 | section | Membrane install
55ecb7f9-2a72-52b5-8b03-62220dd4ed47 | checkpoint | Install sealant angle fillets to all wall floor junctions
ff73973d-c48a-57fd-8626-c7fc953ec6d2 | checkpoint | Prime surfaces with Epistixx
a5c41064-971a-5a20-b07e-89d3a29555a8 | checkpoint | 2nd body coat
3d42f470-3e27-50d3-a12d-9c367682304c | checkpoint | 3rd body coat
b1c00d9a-283a-5d0e-bd53-be499eb97729 | checkpoint | Traxx 2000 wear coat.
28fadde4-654a-579a-8e7b-dfd99c1f9260 | section | Review and Sign Off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
8bc9e78a-347e-5cb7-bbe4-631942b3466e | checkpoint | All installation work complete, checked and reviewed as per specification
03feb2e0-5dfb-5205-b56a-a8f27373d438 | checkpoint | Client / Main Contractor sign off
ade1d7ff-ccd3-5452-af37-2b8232a96ebb | checklist | QA - Fibertherm Checklist |  | Fibertherm Checklist
a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
c79d3f4e-779d-5b99-86ed-a64d3c0b52a2 | checkpoint | Substrate complete and ready for SWP
89b312d0-78d6-5b21-ade5-65622d56dc5b | section | Metal Deck
7e9bd4a1-17ea-53f1-b057-832040acc3f4 | checkpoint | Timber to have separation
fb1e4fa0-b240-58aa-b2ab-56b80f6c14b9 | checkpoint | End openings to have closure foam installed
d2455f48-ac51-5575-809d-ccef4e45ea00 | checkpoint | Base deck screwed down in every pan
2e656403-411a-5c09-b647-e0d308ad20ca | checkpoint | VCL tape to be installed to all sheet laps
84935dc8-17ee-56cf-8233-f78cc3313a0e | checkpoint | VCL tape to all upstands
a7506eb6-f479-54c1-bc02-b35206a9bec8 | section | Post and Rail install
f13d6b62-13ab-5d8d-86b4-8379644d7415 | checkpoint | Post installed at correct fixing centers
1c299338-89e8-5aca-8ea1-9e34c82522e8 | checkpoint | Thermal break pad under post foot
55651d6d-4026-59dd-863b-6ea294e52e58 | checkpoint | Rail installed to posts
3be7bd06-4b10-55ea-ae1b-79d88e9e4b0f | section | Insulation install
5928eb0f-4a60-5d14-af30-563f9e991674 | checkpoint | Specified Insulation installed
3bad6875-d408-53bb-943c-05d63b6fd448 | checkpoint | No Gaps
e6d7eeb4-78a5-52fd-91be-d15b8594fe96 | section | Top Deck install
09610b0c-c460-5ae2-8d4b-bd80a1717100 | checkpoint | Lay sheets straight
675907f2-2d2e-5001-8b52-cb2c0499fb68 | checkpoint | Hang over into gutter min 75mm
23568b5e-315d-52c1-ad88-97747fbc4f19 | checkpoint | Top end of sheets turned up
9ff372cb-b7cc-50cd-b05f-35857590a974 | checkpoint | Bottom end of sheets turned down
dea68afd-daa6-53d9-8b44-0c28265a6dff | checkpoint | Fixing back to rail
1033c5f8-94c5-51b2-bfea-2f5c71b2d9ac | checkpoint | Profile washers
e6b46ac2-2dd3-5a31-8dde-8ac3e172a0c7 | checkpoint | Screwed off as per fixing plan
35d70514-e37d-596e-a1e3-d8abb887b7a6 | section | Flashing install
ae82a4f1-f726-577e-9155-e21b139891d2 | checkpoint | Fixings according to specs & details
28fadde4-654a-579a-8e7b-dfd99c1f9260 | section | Review and Sign Off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
8bc9e78a-347e-5cb7-bbe4-631942b3466e | checkpoint | All installation work complete, checked and reviewed as per specification
03feb2e0-5dfb-5205-b56a-a8f27373d438 | checkpoint | Client / Main Contractor sign off
e912c1a2-633b-57dd-a618-ec0dc4d12cd3 | checklist | QA - Fibertite Overlay Install Checklist |  | Fibertite Overlay Install Checklist
a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
c79d3f4e-779d-5b99-86ed-a64d3c0b52a2 | checkpoint | Substrate complete and ready for SWP
691ae12f-acc2-5904-80b8-90c3607eed06 | section | Substrate
ffe5d951-9ab9-5a42-aeda-8de062f74eba | checkpoint | Mechanically Fix existing roof pans to Purlins after checking underneath from inside that we're not going to puncture pipes or wires
8a7353e1-6b65-5c14-9661-47d716c772bd | checkpoint | Cut back existing roof edge at gutter
0df6c4d7-6e9d-5ff8-857c-5c00cc33c922 | checkpoint | Remove ridge as we go
d933b228-2971-5c14-95e1-eba339d91099 | section | VCL-Vapour Control Layer
d2008c2a-5250-5c1b-85de-1d87843f79d3 | checkpoint | Surface/Substrate is dry, clean and free from sharp edges
91e87471-ee3c-5f86-aedb-5cf70005070f | checkpoint | All areas covered and lapped a minimum of 50mm
c76f2066-dce6-5a14-95e0-1f0480ff3e3e | checkpoint | All holes/penetrations patched and made watertight
aa678121-9cd7-579e-b426-a671777bc2fc | section | Roof Pan Infills
6f62e612-5f43-578b-a82f-d9e88d4b4712 | checkpoint | Surface is dry before installing Poly
59762aef-ada8-5539-adb3-1b890b6d49de | checkpoint | Infills to be a minimum 5mm above ridges on roof
aebb5033-8d29-5b0d-9ae5-24b0d539262a | checkpoint | Every pan has been infilled
204ab11c-6538-5237-a7ae-b6c9f641ca64 | section | Roofboard
2477f1f4-2b6d-52de-a113-bf8fefbfbd00 | checkpoint | Substrate/surface dry & clean prior to being installed
b171b558-e3aa-5c61-a4ce-d47cc47627e0 | checkpoint | Installed in brick pattern
79e9c002-1307-5726-ba82-60f23bc2a142 | checkpoint | Correct screws with load washer
01d8a1da-0f1b-5d52-9816-77051de620b4 | checkpoint | Installed as per wind uplift fixing plan
9a1fae80-f8a4-5bdc-9ec4-711150687c96 | checkpoint | Install 70mm X 100mm zincalume flashing at gutter edge for strength
b3098a4e-2d2d-5531-8d33-62cd3a06eec9 | section | Fibertite
e99b5e05-4de6-5af2-a300-6a04de12f2b4 | checkpoint | Correct Glue being used for substrate
94ce6395-2f43-5b96-8730-714f5b04df9b | checkpoint | Fibertite fully glued to substrate
04493f9b-c891-54d5-9f4c-ef094ac5b624 | checkpoint | Broom/rolling of fibertite
cca6ba74-d669-5290-b383-3559ec5abb5b | checkpoint | Wipe/clean laps with acetone prior to welding
5462aa24-e979-50b4-9d1e-6e82648b15ee | checkpoint | All laps, details, penetrations fully welded/closed and QA'd with hook
3dd8790a-fc1a-5fd4-b101-b2e26dba5385 | checkpoint | Clamps / rings / baskets installed
e7ee8757-7511-5b9a-ac42-04f4156c0a65 | checkpoint | Flooded / ILD checked
6096719d-32c8-566a-b182-0f3c3a3accfb | section | Fiberclad Flashings
d28888df-f527-5879-a21e-8f8c497bcab4 | checkpoint | Installed correctly
fde8ad75-347c-5478-98dd-eff6c938f669 | checkpoint | Fixed down according to specification
e178af69-6fdc-5a0b-961f-a0dcf79062fc | checkpoint | Cleaned down with acetone prior to welding
cf00d4b8-d6e0-5472-b077-9c34e4b68450 | checkpoint | Fibertite fully welded to flashing and QA'd with hook
28fadde4-654a-579a-8e7b-dfd99c1f9260 | section | Review and Sign Off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
8bc9e78a-347e-5cb7-bbe4-631942b3466e | checkpoint | All installation work complete, checked and reviewed as per specification
03feb2e0-5dfb-5205-b56a-a8f27373d438 | checkpoint | Client / Main Contractor sign off
8642b61a-eb3d-53bc-9558-2c233d40476a | checklist | QA - Torch On to Concrete Checklist |  | Torch On to Concrete Checklist
a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
c79d3f4e-779d-5b99-86ed-a64d3c0b52a2 | checkpoint | Substrate complete and ready for SWP
228a0b8d-e14e-5eb9-9fb6-ad4aba16f80a | section | Concrete Substrate
aca2494a-3a3f-551a-8a5c-101bb3252566 | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
c4e85f06-29ad-5f78-90f3-7a93a366da3b | checkpoint | All lumps and sharp concrete bits ground/hammered down
333e9f51-0f68-512e-82fd-793690441512 | checkpoint | Large holes filled with grout
0e44c938-753b-5d4d-a7ba-d033f7b85ebd | section | Prime of Substrate
79f1de1f-65be-53af-92c9-1185e9a28ac7 | checkpoint | Substrate clean and free from debris
121030bf-0ba0-5d7c-adca-b861e3cb45fb | checkpoint | Primer installed
c3974f43-3a60-5bbf-ad82-1704e6b6a918 | section | Base Sheet
5abf28fd-57ed-50f6-a44b-762ee6302edb | checkpoint | Install from low to high
59d8826f-3695-5fa2-b7d9-49381a63cc0a | checkpoint | Side laps a minimum of 80mm and end laps 150mm
295460e8-a2c2-5063-ac06-4d67ccbb3ff7 | checkpoint | Check all welds at the end of the day
b73cf941-50a5-502e-9e29-5626b41cce49 | section | Cap Sheet
3d8ce91f-eb21-549a-929e-704bd4138aa7 | checkpoint | Install low to high
66a7c629-c2e4-4b55-8df6-ee1af54827e5 | checkpoint | Side laps a minimum of 80mm and end laps 150mm
784e6c43-eb6a-5c28-89b4-b3396b054e45 | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
1ee09d6d-7799-5dae-9725-ab47757145bc | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
f079103e-608b-53cf-a738-d9c990415510 | checkpoint | Membrane dressed into drains/outlets
a71e3d68-81d0-5fc2-9746-96f57d564297 | checkpoint | Install clamps/rings/baskets
44c452de-7385-58d7-b990-1047f8c5f756 | checkpoint | Flood/ILD test
28fadde4-654a-579a-8e7b-dfd99c1f9260 | section | Review and Sign Off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
8bc9e78a-347e-5cb7-bbe4-631942b3466e | checkpoint | All installation work complete, checked and reviewed as per specification
03feb2e0-5dfb-5205-b56a-a8f27373d438 | checkpoint | Client / Main Contractor sign off
db433549-cbfa-54db-a680-262a56a05efd | checklist | QA - Torch On to Plywood Checklist |  | Torch On to Plywood Checklist
a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
c79d3f4e-779d-5b99-86ed-a64d3c0b52a2 | checkpoint | Substrate complete and ready for SWP
c2faf38a-48cf-52bc-b03b-b0ef3cd187ea | section | Plywood Substrate
aca2494a-3a3f-551a-8a5c-101bb3252566 | checkpoint | Substrate clean and dry. Free from dirt/debris contamination and ready for membrane
f6fb9b8e-29fa-55e6-8d5d-c6939005ae0e | checkpoint | No Screws/nails/fixings popping up
3d108166-5fb7-56eb-aaa9-9ca02e8c1169 | checkpoint | Joints flush and even
0e44c938-753b-5d4d-a7ba-d033f7b85ebd | section | Prime of Substrate
79f1de1f-65be-53af-92c9-1185e9a28ac7 | checkpoint | Substrate clean and free from debris
121030bf-0ba0-5d7c-adca-b861e3cb45fb | checkpoint | Primer installed
c3974f43-3a60-5bbf-ad82-1704e6b6a918 | section | Base Sheet
5abf28fd-57ed-50f6-a44b-762ee6302edb | checkpoint | Install from low to high
59d8826f-3695-5fa2-b7d9-49381a63cc0a | checkpoint | Side laps a minimum of 80mm and end laps 150mm
295460e8-a2c2-5063-ac06-4d67ccbb3ff7 | checkpoint | Check all welds at the end of the day
b73cf941-50a5-502e-9e29-5626b41cce49 | section | Cap Sheet
3d8ce91f-eb21-549a-929e-704bd4138aa7 | checkpoint | Install low to high
6ba0f4eb-a712-434e-af27-ae252aa84a2c | checkpoint | Side laps a minimum of 80mm and end laps 150mm
784e6c43-eb6a-5c28-89b4-b3396b054e45 | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
1ee09d6d-7799-5dae-9725-ab47757145bc | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
f079103e-608b-53cf-a738-d9c990415510 | checkpoint | Membrane dressed into drains/outlets
a71e3d68-81d0-5fc2-9746-96f57d564297 | checkpoint | Install clamps/rings/baskets
44c452de-7385-58d7-b990-1047f8c5f756 | checkpoint | Flood/ILD test
28fadde4-654a-579a-8e7b-dfd99c1f9260 | section | Review and Sign Off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
8bc9e78a-347e-5cb7-bbe4-631942b3466e | checkpoint | All installation work complete, checked and reviewed as per specification
03feb2e0-5dfb-5205-b56a-a8f27373d438 | checkpoint | Client / Main Contractor sign off
9ece929c-50fc-59a8-8e2c-725456426719 | checklist | QA - Torch on Warmroof Over Metal Deck Checklist |  | Torch on Warmroof Over Metal Deck Checklist
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
c79d3f4e-779d-5b99-86ed-a64d3c0b52a2 | checkpoint | Substrate complete and ready for SWP
89b312d0-78d6-5b21-ade5-65622d56dc5b | section | Metal Deck
25ce1e5e-ae55-5cd8-b6ff-eae1f7016eff | checkpoint | Timber to have separation barrier
d2455f48-ac51-5575-809d-ccef4e45ea00 | checkpoint | Base deck screwed down in every pan
04785d0f-42bc-5ee4-9115-a64dbd84bd3d | checkpoint | Sheet edges stitched together at 300mm centres
5f218991-af8a-5460-9dd1-474a131416b4 | checkpoint | No sharp edges protruding
c2d85594-faca-5d84-a86f-151a54cf252e | section | Vapour Control Layer
1d472034-bbf1-5d8d-aeda-4bbb3a1cbe24 | checkpoint | Is the substrate clean, dry and clear of swarf
c5b12c4f-7c14-5857-acc2-b36baddd6c4b | checkpoint | All areas covered and sheets lapped 50mm
03aa6d7c-5e3e-5fd9-ba7b-52b4118c07aa | checkpoint | All holes/penetrations patched and water tight
081f4c6d-dc68-5faa-a9d5-6135f30b3647 | section | Insulation
d5a65516-d3e8-50a3-9e9e-15e3da9741b5 | checkpoint | Surface is dry prior to install
64e0ff13-c86f-56d5-8071-6e084d6e19da | checkpoint | Vapour control layer has been checked for no damage
0bf6a039-0521-5985-a2fc-9b3c1d087e16 | checkpoint | Insulation board installed
b605ce5e-30ce-53da-86b3-ca16a46be124 | checkpoint | Joints flush (no gaps between boards on ends)
59df802c-a3f5-5036-97d4-0974dbf4ab80 | section | Securock
262f519e-c215-5a0c-8d3a-5b025456c69a | checkpoint | Is the surface dry
b171b558-e3aa-5c61-a4ce-d47cc47627e0 | checkpoint | Installed in brick pattern
e5332bc1-ccbb-5ac1-a1de-77e3de8fa154 | checkpoint | Correct length screw with recessed flat plates
01d8a1da-0f1b-5d52-9816-77051de620b4 | checkpoint | Installed as per wind uplift fixing plan
24c6b3fc-0fc8-5211-81d2-020412202e64 | checkpoint | Prime of Securrock
c3974f43-3a60-5bbf-ad82-1704e6b6a918 | section | Base Sheet
5abf28fd-57ed-50f6-a44b-762ee6302edb | checkpoint | Install from low to high
6fe52ba7-bf31-5bbb-ad07-410ec31522c9 | checkpoint | Bleed of bitumen on overlap should be up to 10mm
59d8826f-3695-5fa2-b7d9-49381a63cc0a | checkpoint | Side laps a minimum of 80mm and end laps 150mm
8a64996e-e5f4-528a-9b13-20fa96a809b2 | checkpoint | Check of all welds at the end of the day
b73cf941-50a5-502e-9e29-5626b41cce49 | section | Cap Sheet
0288084c-01b3-4e14-bee0-6e6b45c47841 | checkpoint | Install from low to high
84493199-029c-4b11-be93-4570f23d4dba | checkpoint | Side laps a minimum of 80mm and end laps 150mm
784e6c43-eb6a-5c28-89b4-b3396b054e45 | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
1ee09d6d-7799-5dae-9725-ab47757145bc | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
d4f065e7-3be0-5bc4-8b82-c06ca5ad177a | checkpoint | Clamps / rings / baskets installed and press into overflows and outlets
f96430f9-634f-5749-93c6-19981bd6cd8e | checkpoint | Flood test / ILD tested
28fadde4-654a-579a-8e7b-dfd99c1f9260 | section | Review and Sign Off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
8bc9e78a-347e-5cb7-bbe4-631942b3466e | checkpoint | All installation work complete, checked and reviewed as per specification
03feb2e0-5dfb-5205-b56a-a8f27373d438 | checkpoint | Client / Main Contractor sign off
c1488257-0237-5b65-9c2e-8f744d1f428f | checklist | QA - Torch on Warmroof Over Plywood Checklist |  | Torch on Warmroof Over Plywood Checklist
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
c79d3f4e-779d-5b99-86ed-a64d3c0b52a2 | checkpoint | Substrate complete and ready for SWP
ecbf054b-e524-5121-98cf-196c200162e5 | section | Plywood
a6322119-d812-5d57-8c94-ad514027026a | checkpoint | Plywood clean and dry. Free from dirt/debris and and ready for priming
499f834e-b096-526e-9ca0-d7bd79441f59 | checkpoint | No screws/nails/fixings popping up
036099d0-8af4-5e60-b32f-b8112725bb5a | checkpoint | Plywood joints flush and even
c2d85594-faca-5d84-a86f-151a54cf252e | section | Vapour Control Layer
1d472034-bbf1-5d8d-aeda-4bbb3a1cbe24 | checkpoint | Is the substrate clean, dry and clear of swarf
c5b12c4f-7c14-5857-acc2-b36baddd6c4b | checkpoint | All areas covered and sheets lapped 50mm
03aa6d7c-5e3e-5fd9-ba7b-52b4118c07aa | checkpoint | All holes/penetrations patched and water tight
081f4c6d-dc68-5faa-a9d5-6135f30b3647 | section | Insulation
d5a65516-d3e8-50a3-9e9e-15e3da9741b5 | checkpoint | Surface is dry prior to install
64e0ff13-c86f-56d5-8071-6e084d6e19da | checkpoint | Vapour control layer has been checked for no damage
0bf6a039-0521-5985-a2fc-9b3c1d087e16 | checkpoint | Insulation board installed
b605ce5e-30ce-53da-86b3-ca16a46be124 | checkpoint | Joints flush (no gaps between boards on ends)
59df802c-a3f5-5036-97d4-0974dbf4ab80 | section | Securock
262f519e-c215-5a0c-8d3a-5b025456c69a | checkpoint | Is the surface dry
b171b558-e3aa-5c61-a4ce-d47cc47627e0 | checkpoint | Installed in brick pattern
e5332bc1-ccbb-5ac1-a1de-77e3de8fa154 | checkpoint | Correct length screw with recessed flat plates
24c6b3fc-0fc8-5211-81d2-020412202e64 | checkpoint | Prime of Securrock
01d8a1da-0f1b-5d52-9816-77051de620b4 | checkpoint | Installed as per wind uplift fixing plan
c3974f43-3a60-5bbf-ad82-1704e6b6a918 | section | Base Sheet
5abf28fd-57ed-50f6-a44b-762ee6302edb | checkpoint | Install from low to high
59d8826f-3695-5fa2-b7d9-49381a63cc0a | checkpoint | Side laps a minimum of 80mm and end laps 150mm
8a64996e-e5f4-528a-9b13-20fa96a809b2 | checkpoint | Check of all welds at the end of the day
b73cf941-50a5-502e-9e29-5626b41cce49 | section | Cap Sheet
e0bdf590-ec3f-48af-aecb-8cd4282b99b5 | checkpoint | Install from low to high
52a31b7c-074d-4674-8690-7b64db5695c3 | checkpoint | Side laps a minimum of 80mm and end laps 150mm
784e6c43-eb6a-5c28-89b4-b3396b054e45 | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
1ee09d6d-7799-5dae-9725-ab47757145bc | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
d4f065e7-3be0-5bc4-8b82-c06ca5ad177a | checkpoint | Clamps / rings / baskets installed and press into overflows and outlets
83b9ff1b-4f6a-5898-b9be-de3aea864fb0 | checkpoint | Flood test / ILD checked
28fadde4-654a-579a-8e7b-dfd99c1f9260 | section | Review and Sign Off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
8bc9e78a-347e-5cb7-bbe4-631942b3466e | checkpoint | All installation work complete, checked and reviewed as per specification
03feb2e0-5dfb-5205-b56a-a8f27373d438 | checkpoint | Client / Main Contractor sign off
c0512164-bdda-53e5-aca0-a057f634cb6c | checklist | QA - Torch On Warmroof to Concrete Checklist |  | Torch On Warmroof to Concrete Checklist
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
431de1d9-fdd4-5bde-bd01-79ab526467b9 | checkpoint | Area accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
c79d3f4e-779d-5b99-86ed-a64d3c0b52a2 | checkpoint | Substrate complete and ready for SWP
5c66b280-0e24-5bf6-a8f9-047d28ee4c5a | section | Concrete
2bcd3e0c-6e2c-5c30-b288-e6a17cf00e19 | checkpoint | Concrete clean and dry. Free from dirt/debris and ready for priming
e7aa5575-f2a8-54cd-8b91-8a15df086acc | checkpoint | All lumps and sharp concrete bits ground down/hammered down
333e9f51-0f68-512e-82fd-793690441512 | checkpoint | Large holes filled with grout
c2d85594-faca-5d84-a86f-151a54cf252e | section | Vapour Control Layer
1d472034-bbf1-5d8d-aeda-4bbb3a1cbe24 | checkpoint | Is the substrate clean, dry and clear of swarf
c5b12c4f-7c14-5857-acc2-b36baddd6c4b | checkpoint | All areas covered and sheets lapped 50mm
03aa6d7c-5e3e-5fd9-ba7b-52b4118c07aa | checkpoint | All holes/penetrations patched and water tight
081f4c6d-dc68-5faa-a9d5-6135f30b3647 | section | Insulation
d5a65516-d3e8-50a3-9e9e-15e3da9741b5 | checkpoint | Surface is dry prior to install
64e0ff13-c86f-56d5-8071-6e084d6e19da | checkpoint | Vapour control layer has been checked for no damage
0bf6a039-0521-5985-a2fc-9b3c1d087e16 | checkpoint | Insulation board installed
b605ce5e-30ce-53da-86b3-ca16a46be124 | checkpoint | Joints flush (no gaps between boards on ends)
59df802c-a3f5-5036-97d4-0974dbf4ab80 | section | Securock
262f519e-c215-5a0c-8d3a-5b025456c69a | checkpoint | Is the surface dry
b171b558-e3aa-5c61-a4ce-d47cc47627e0 | checkpoint | Installed in brick pattern
6cc5503f-136d-5f54-81e1-b9eb9221a532 | checkpoint | Correct length screw with load washer
24c6b3fc-0fc8-5211-81d2-020412202e64 | checkpoint | Prime of Securrock
01d8a1da-0f1b-5d52-9816-77051de620b4 | checkpoint | Installed as per wind uplift fixing plan
c3974f43-3a60-5bbf-ad82-1704e6b6a918 | section | Base Sheet
5abf28fd-57ed-50f6-a44b-762ee6302edb | checkpoint | Install from low to high
59d8826f-3695-5fa2-b7d9-49381a63cc0a | checkpoint | Side laps a minimum of 80mm and end laps 150mm
8a64996e-e5f4-528a-9b13-20fa96a809b2 | checkpoint | Check of all welds at the end of the day
b73cf941-50a5-502e-9e29-5626b41cce49 | section | Cap Sheet
1b4d555c-edf4-4134-8d74-f9b52d653732 | checkpoint | Install from low to high
2e24444c-4098-4d7d-b389-5631831dc78a | checkpoint | Side laps a minimum of 80mm and end laps 150mm
784e6c43-eb6a-5c28-89b4-b3396b054e45 | checkpoint | Exposed vertical upstands terminated no less than 150mm above the roof and approved termination bar or cap flashing
1ee09d6d-7799-5dae-9725-ab47757145bc | checkpoint | Base flange of membrane shall extend onto the horizontal section of the roof a minimum of 100mm
da23f941-9944-5abc-b469-f8f8358fc989 | checkpoint | Clamps / rings / baskets press into overflows and outlets
30390f4a-dd56-5304-91bd-6b6af571c3ea | checkpoint | Flood test / ELD tested
28fadde4-654a-579a-8e7b-dfd99c1f9260 | section | Review and Sign Off
d21b14a7-739f-588d-8c47-71bb08be490c | checkpoint | Area left clean and tidy
8bc9e78a-347e-5cb7-bbe4-631942b3466e | checkpoint | All installation work complete, checked and reviewed as per specification
03feb2e0-5dfb-5205-b56a-a8f27373d438 | checkpoint | Client / Main Contractor sign off
6e9ff196-9b95-53a6-a7fe-714c53bd329c | checklist | Supplier Site Visit |  | Site Visit date:
cd6a7ee9-c00d-594d-96fb-b5f5ad13ba34 | checkpoint-no-value | Site Details
6d41fa6a-4e1a-577e-a624-6bd736f97876 | textbox | Job Name
22044acf-ec81-5b86-a826-c71cabe41273 | textbox | Who is in attendance
1235194d-88da-53a0-854a-ce85145c2b1e | textbox | Area/Gridlines/Detail
2b861131-7b9e-51e9-95bf-a57d2d62e13a | checkpoint | Photos
e4f72de6-232e-5c0f-a8f5-0b30ac9ea698 | textbox | Inspection Notes
3b1bfa02-2288-51be-9aaf-840ef1a2ab1d | signoff | Signoff Required
2ad3b4b9-8095-52af-bfbe-37050dc3ce3c | checklist | SYS - PT - Job Details |  | Job Details
ed730432-54a4-509a-8253-b46459261773 | checkpoint | Site Info
4e739149-fe6d-425d-b45e-4a4ff63e7c1e | textbox | Site Address
e326d577-6e3a-40b7-870a-8e178eda7195 | textbox | Main Contractor Details
6c1ef37c-4d31-4405-b668-f398c4ad1275 | textbox | Project Managers Details
351c3436-2ae9-42ae-9ee9-1146e81bffa2 | textbox | Site Manager Details
e0578cae-2efd-59dc-b758-b292350b189e | checkpoint | Latest Drawings
f1c62679-43b3-540b-9dae-ba7748dea703 | checkpoint | Scope of Works Attached
7bbc4832-be77-571c-8cd0-9c7f262291dc | checkpoint | Additional Pre Start Docs
b7fd5091-2ebb-5ece-992d-a0af1cfac90b | checkpoint | Fixing Plan Attached
625547e3-3754-513a-8f5e-30d5d4c1ff09 | checklist | Weather Monitoring |  | Weather Monitoring
a11d4216-3dbf-5fb5-91e6-7e8efa2480a0 | section | Current Weather
ba339880-e613-55e6-bc7e-c4ddacd1ff38 | checkpoint | Wind / weather conditions
5a8ec816-5f52-5730-adb3-71a6dd3ba503 | checkpoint | Record any delays
1a169b5b-31dd-5fc9-8bf3-c595d8cd112c | checkpoint | area / gridlines
2999b979-f461-5b2f-9c10-09d35dfc5cbd | checkpoint | Comments / issues / observations
00ffebb5-f6f8-53c5-961d-a8394872fe4f | section | Weather Forecast
1667a243-cbf8-5135-b1e3-d0f02777b195 | checkpoint | What is the weather forecast this week
88d05f79-691e-4c08-a86f-d23daec4a4b8 | checkpoint | Record any delays
cffd34d4-0013-4fde-92c7-8fda168f13a8 | checkpoint | area / gridlines
5ea6eabe-437a-41d1-8ca9-d65dbcd79f38 | checkpoint | Comments / issues / observations
93b2dbb7-ffb2-5b1f-a343-12328a51c125 | checklist | Wellington Library Eurostyle Spanlok |  | Wellington Library Eurostyle Spanlok
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
65667475-4273-5460-a627-2cb20cb92ab4 | checkpoint | Coil ordered, colour sorted
635777e8-814b-577a-9f92-d03c35602def | checkpoint | Clips, screwed ordered as per spec
c66a6dd8-9e76-53d6-ad9c-e8d07695802c | checkpoint | Pan width, Set out of pans agreed with main contractor/architect
6be27934-a9a5-56e1-b0f6-0d7d41f0149e | checkpoint | Roof Logic 'Rhom Rail' centre fixings /wind design agreed with main contractor/architect
3c96a18d-68d5-590f-8252-9fd1b48e89b6 | checkpoint | Substrate ready
4917beb7-f0f8-5f58-a9a2-1512a2a3386b | section | Install
042fbae9-885a-548c-ba5e-30f0313830e3 | checkpoint | Roof Logic 'Rhom Rail' including RL VTB) straight/plumb sit out in fixing according to specification
dccc9420-4cfa-566b-afa8-726aea8ec084 | checkpoint | Vaproshims (100 x 25 x 6mm) installed behind Roof Logic 'Rhom Rail'
5a9b6fc5-3c81-564a-b476-f569c743f781 | checkpoint | perforated/drained closure flashing
ea68b512-ae01-51d9-bea9-003c8c665374 | checkpoint | Bottom starter flashing installed
b4289c7f-e461-56b9-bbd5-cccdc8a4962b | checkpoint | Clip spacing correct for of sheet 365mm wide tray profile ( 2 screws per clip.wafer 10-16x30B8)
134c9681-93cc-5b58-b1a3-ad5b01d0e7de | checkpoint | Cladding running straight/plumb
bae2e426-4943-57e1-8f28-c62a4a061dde | checkpoint | Window/door/louvre flashings installed according to plans/best practice
d6664c90-8b14-5b22-893a-8971a27d29dc | checkpoint | Finish flashings completed and sealed properly
11f8e152-1ca6-58c0-bc6a-dbc91af1dcdb | checkpoint | Any damage
1676bf02-28c2-5906-9ef0-9b4804b57927 | checkpoint | Main contractor sign off
88635cfe-e3fc-5588-a2eb-a51f7ef9a547 | checkpoint | Cladding Install Complete
ca526da9-e86f-5727-adf2-f7edd6bedc9b | checkpoint | Main contractor to protect
2d8c2db0-1584-5efb-95d2-6ba228c5359d | signoff | Request Sign Off
bc64a16f-e11b-5423-b596-1d5812f834ab | checklist | Xtreme FibreTite Checklist |  | FiberTite Checklist - Area:
a3dc4eb6-3451-54ec-b8d1-6ad687083d71 | section | Pre Start
c0e9bd74-e7d8-5ee9-bae7-2272d9eaa5db | checkpoint | Area Accessible
999603b7-39b7-5c4a-bee7-b4fd529e0655 | checkpoint | Edge protection and safety installed
d529fe9e-3662-5c04-bc15-c4acb4349941 | checkpoint | Substrate complete and ready for SWP (metal/concrete/ply)
54009437-fb9e-53b2-a70a-b3f4408edbc0 | checkpoint | Perimeter support installed installed if metal deck substrate
89b312d0-78d6-5b21-ade5-65622d56dc5b | section | Metal Deck
25ce1e5e-ae55-5cd8-b6ff-eae1f7016eff | checkpoint | Timber to have separation barrier
d2455f48-ac51-5575-809d-ccef4e45ea00 | checkpoint | Base deck screwed down in every pan
c2d85594-faca-5d84-a86f-151a54cf252e | section | Vapour Control Layer
1d472034-bbf1-5d8d-aeda-4bbb3a1cbe24 | checkpoint | Is the substrate clean, dry and clear of swarf
c5b12c4f-7c14-5857-acc2-b36baddd6c4b | checkpoint | All areas covered and sheets lapped 50mm
03aa6d7c-5e3e-5fd9-ba7b-52b4118c07aa | checkpoint | All holes/penetrations patched and water tight
39337afd-c802-553a-bb15-38fc8943af56 | section | Acoustic Board
262f519e-c215-5a0c-8d3a-5b025456c69a | checkpoint | Is the surface dry
b171b558-e3aa-5c61-a4ce-d47cc47627e0 | checkpoint | Installed in brick pattern
30b97b8d-0650-5c6e-87c4-f03c01ab2008 | checkpoint | correct length screw with recessed flat plates
23d3c0d5-0d22-5644-a75c-21013355b2d4 | checkpoint | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
081f4c6d-dc68-5faa-a9d5-6135f30b3647 | section | Insulation
d5a65516-d3e8-50a3-9e9e-15e3da9741b5 | checkpoint | Surface is dry prior to install
64e0ff13-c86f-56d5-8071-6e084d6e19da | checkpoint | Vapour control layer has been checked for no damage
bbad2df7-5dc7-5412-8e7c-db86b22a0f5d | checkpoint | Insulation board installed in a brick pattern
b605ce5e-30ce-53da-86b3-ca16a46be124 | checkpoint | Joints flush (no gaps between boards on ends)
e5c154b6-c42a-5cdb-acd8-a88894de0f38 | checkpoint | Fixings at correct spacing according to spec if no Securock in system.
4382520b-63a8-5718-a2b4-b7469c2127d5 | section | HDP Roofboard
2f39f522-68e0-443e-a414-02039e2626ef | checkpoint | Is the surface dry
d2ef3ce9-0947-40b1-8336-1ff15724dac5 | checkpoint | Installed in brick pattern
781cbcd6-d4a2-477e-b107-88ad2bf61d8b | checkpoint | correct length screw with recessed flat plates
2e1e2f77-2f2d-488e-b91c-2397ff1be844 | checkpoint | Installed as per wind uplift fixing plan for both edges and perimeters and main field of roof
99886534-bea6-5689-9ca7-6716555c119c | section | FiberTite
e1be64d7-af99-524b-bc48-c26bc7d10686 | checkpoint | Test weld with welding machine
19869c98-c957-5a4d-b97f-adff0bbc1b28 | checkpoint | Adhesive installed to substrate
adac1280-a8d3-58b1-bc17-ce98fe4e3231 | checkpoint | Laying of membrane into the adhesive
c901c743-ed3d-5c30-bf83-f4efe837a5d2 | checkpoint | Broom/rolling of membrane
9c05655c-ad40-59d1-a398-837bbf4e42bf | checkpoint | Wipe and clean of laps prior to welding
2441ef0b-c131-5745-b87f-29a7db192fbf | checkpoint | Probe of seams with QA hook
2abbac23-d0c9-5f10-ae75-cdb5f1be70a8 | checkpoint | Clamp and weld of outlets and overflows
8e2e7674-e516-5663-a559-2e2a8cb7262b | checkpoint | Flood test of outlets
84be7c7b-9071-5f49-a348-59fa7d8ed780 | section | Fiberclad flashings
ffed9106-b352-5fcb-a562-8d02e8954597 | checkpoint | Installed correctly according to specifications (Right way around)
828decae-a0ff-5a76-9f66-38f06c93cc0c | checkpoint | Fixings and welding done according to specifications and details
a839d4d0-16b3-5bad-bbeb-7e8328c7282d | checkpoint | Probe of weld with QA hook
7fe71b6e-bbf6-52fe-a8cd-dba21c68074e | checkpoint | Area Complete (Request MC Signoff)

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
61e89bb9-db48-41c4-a954-7f3ddd2f303f | checklist | Basedeck install checklist |  | Basedeck install checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
34383c6f-e0df-49b4-82af-afc9fa3bcb3c | checkpoint | Pre Start
d82240ff-6e02-5669-a27d-28c34827fe90 | tickbox | Area accessible
a8560549-1958-59b9-90e3-816a09c2545b | tickbox | Edge protection in place
ecf58ada-394c-5320-91f3-8687af6235ba | tickbox | Structure and substrate has been handed over by main contractor
69ce669b-259e-5e36-8f3c-b0efbd8cc549 | tickbox | Visual inspection by SWP
97b5340f-cb6b-4d64-b2c7-37082c49f241 | checkpoint | Basedeck
862952ee-2f25-5971-a26c-e020163b5de9 | tickbox | Basedeck installed as per agreed scope
feb05036-784f-5bc7-a283-ae9b3ed89e0b | tickbox | Approved fixings used
7ae4253c-2256-548a-aaf9-ee7bd45750eb | tickbox | Base deck fixed off at every purlin and every pan
75876079-3794-56df-b207-38ff7518568f | tickbox | Base deck stitched along side/laps at 300mm centres
e83cd796-d4a0-451d-9e79-e3eb9980cf62 | checkpoint | VCL
f01cc56e-6668-5b68-9edf-aae8295747fa | tickbox | Substrate is clean, dry and clear of swarf
285dc2bd-b82f-518b-9238-1d96be9b88bc | tickbox | All areas covered and lapped 100 mm min
0076043b-879f-546c-b2ec-474c59cb1a1d | tickbox | All holes/penetrations patched and watertight
f4013b6d-e8b9-5cb5-99e6-67316f4d4bcd | tickbox | Area left clean and tidy
6292d321-d145-5af2-a265-aa3d50214471 | tickbox | All installation work completed, checked and reviewed as per specifications
8b468166-9b7a-44e8-8350-75a77262dd1e | signoff | Review and sign off