## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
050bcf48-eb33-42b4-9180-2c422bd69aa4 | checklist | Fibertite Warm Roof over DD400 checklist |  | Fibertite Warm Roof over DD400 checklist
| section | Pre start
| checkpoint | Area accesable
| checkpoint | Edge protection and safety installed
| checkpoint | visual inspection of substrate ready for SWP
| checkpoint | Qa document recevied from main contractor
| section | Substrate
| checkpoint | Substrate screwed down in every purlin line
| checkpoint | Substrate has been cleaned and washed down
| checkpoint | Roof Pan Infills
| checkpoint | Surface is dry before installing Fillets
| checkpoint | Every pan has been filled
| section | Vapor control layer
| checkpoint | Substrate clean, dry, free of debris
| checkpoint | VCL installed and covered all surface
| checkpoint | VCL lapped with a minimum of 100mm laps
| section | Insulation
| checkpoint | VCL clean, dry, free of derbris prior to install
| checkpoint | All holes/penetrations patched and watertight
| checkpoint | Insulation board installed in a brick pattern
| checkpoint | Boards tightly butted, and no gaps
| checkpoint | Fixing plan attached
| checkpoint | Fixings as per fixing plan if no HDP board
| section | HDP board
| checkpoint | Substrate dry & free of derbris prior to install
| checkpoint | Fixing plan attached
| checkpoint | HDP board installed
| checkpoint | HDP installed as per fixing plan
| section | FiberTite
| checkpoint | Correct glue as per specification
| checkpoint | Adhesive installed to substrate
| checkpoint | Laying of mebrane into adhesive
| checkpoint | Broom/rolling of membrane
| checkpoint | Wipe and clean laps prior to welding
| checkpoint | Test weld with welding machine
| checkpoint | Probe of seam with QA hook
| section | Fibreclad flashing
| checkpoint | Fibreclad installed correctly
| checkpoint | Fixing and welding done
| checkpoint | Probe of seam with QA hook
| section | Pressurebar installed
| checkpoint | Pressure bar installed correctly
| checkpoint | Fixings done according to specifications and details
| checkpoint | Silicone installed
| section | Over flashings
| checkpoint | Over flashings has a separation barrier
| checkpoint | Fixings done according to specifications and details
| checkpoint | Primer of Substrate
| checkpoint | Silicone installed
| signoff | Review and sign off
| checkpoint | Area left clean and tidy
| checkpoint | All installation work completed, checked and reviewed as per specfications
| signoff | Client/main contractor sign off