## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
61e89bb9-db48-41c4-a954-7f3ddd2f303f | checklist | Basedeck install checklist |  | Basedeck install checklist |  | b9580664-258a-49db-b2ed-bb8ab43522db
| section | Pre Start
| checkpoint | Area accessible
| checkpoint | Edge protection in place
| checkpoint | Structure and substrate has been handed over by main contractor
| checkpoint | Visual inspection by SWP
| section | Basedeck
| checkpoint | Basedeck installed as per agreed scope
| checkpoint | Approved fixings used
| checkpoint | Base deck fixed off at every purlin and every pan
| checkpoint | Base deck stitched along side/laps at 300mm centres
| section | VCL
| checkpoint | Substrate is clean, dry and clear of swarf
| checkpoint | All areas covered and lapped 100 mm min
| checkpoint | All holes/penetrations patched and watertight
| checkpoint | Area left clean and tidy
| checkpoint | All installation work completed, checked and reviewed as per specifications
| signoff | Review and sign off