## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | SWMS Monitoring |  |  |  |  | Yes | SWMS Monitoring | 0d830396-da47-4837-8eb2-1071b88d2d01
checkpoint-no-status |  |  | checkpoint | Outline of Activity Being Monitored
checkpoint-no-status |  |  | checkpoint | Documents referenced during monitoring
label | d0a3b4ab-cfe6-5b19-8a5e-a2e88d5d807b |  | note | (SWMS, Permit, Traffic Management Plan, Methodology, Engineering Advice, SOP/ JSA)
checkpoint-no-status |  |  | checkpoint | Summary of Monitoring
label | 9c4b8242-a76a-50d1-a64f-081c7016e7c6 |  | note | (Provide an outline of any positive observations or conversations, work practices being performed well, compliance with the documents reference or a brief outline)
select | b34462bf-c29d-5586-9d80-f7734bc6e94d |  | dropdown | Was work required to be stopped? | Yes,No
checklist-flat |  |  | checklist | Pre-start / Toolbox |  |  |  |  | Yes | Pre-start / Toolbox | 3acf4afb-40d6-4052-91d5-9508cff7ab84
checkpoint-no-status |  |  | checkpoint | Title of Activity, Process or Section of Work Being Reviewed
text | 1caee8a4-5d45-5f9a-945f-0ef8a65cfbaf |  | textbox | Built Attendance
checkpoint-status |  |  | checkpoint | Subcontractors Signed onto Prestarts
label | 0750612c-f168-5497-a47a-8146d4e844b0 |  | note | Include photograph of all subcontractor's prestart documentation (including Built)
checklist-sectioned |  |  | checklist | Wall Closure Checklist |  |  |  |  | Yes | Wall Closure Checklist | 4967ca1f-3be2-4a7a-b115-40841327bb8c
checkpoint-group |  |  | section | Electrical Services
checkpoint-status |  |  | checkpoint | Electrical cabling completed
label | 71f90cfa-8510-5ba4-87b0-7d41b7fd055f |  | note | Subcontractor Responsible - Ion Electrical
checkpoint-status |  |  | checkpoint | Communications cabling completed
label | 0e9881dd-fcdc-5863-87bd-68d1980c9daf |  | note | Subcontractor Responsible - Ion Electrical
checkpoint-status |  |  | checkpoint | Lighting cabling completed
label | 76459666-69b1-533b-9fc6-3939d9865bc3 |  | note | Subcontractor Responsible - Ion Electrical
checkpoint-status |  |  | checkpoint | Security cabling completed
label | 85aa2bce-8498-56c1-ab0f-b6e48dc2f0d1 |  | note | Subcontractor Responsible - Ion Electrical
checkpoint-status |  |  | checkpoint | Mechanical protection installed (where required)
label | b433d6c6-3c85-5fd4-b86d-0dfe5a1a0404 |  | note | Subcontractor Responsible - Ion Electrical
checkpoint-status |  |  | checkpoint | Firewall penetrations inspected and tagged
label | b343556a-f347-566b-91ed-e2ff01a1281b |  | note | Subcontractor Responsible - Ion Electrical
checkpoint-group |  |  | section | Hydraulic Services
checkpoint-status |  |  | checkpoint | Drainage pipework completed
label | 869a071a-0e0b-5010-859a-a06465830dfb |  | note | Subcontractor Responsible - Jordan Plumbing
checkpoint-status |  |  | checkpoint | Water reticulation pipework completed
label | bcd03fac-abf3-54ef-8cca-b4c1379de0a3 |  | note | Subcontractor Responsible - Jordan Plumbing
checkpoint-status |  |  | checkpoint | Mechanical protection installed (where required)
label | d0233df0-a5e1-5181-9980-8db04bf98212 |  | note | Subcontractor Responsible - Jordan Plumbing
checkpoint-status |  |  | checkpoint | Firewall penetrations inspected and tagged
label | cb4363c8-9f2e-5ae3-8f14-f14b5749a9b1 |  | note | Subcontractor Responsible - Jordan Plumbing
checkpoint-group |  |  | section | Fire Services
checkpoint-status |  |  | checkpoint | Dry fire cabling completed
label | 964fda36-c432-5c85-b7c3-6440894667e7 |  | note | Subcontractor Responsible - Trojan Fire
checkpoint-status |  |  | checkpoint | Wet fire pipework completed
label | ed436c0f-64fd-5a54-8912-da78693fd8e1 |  | note | Subcontractor Responsible - Trojan Fire
checkpoint-status |  |  | checkpoint | Mechanical protection installed (where required)
label | 46061737-20a3-5820-9d25-a692c3689a6d |  | note | Subcontractor Responsible - Trojan Fire
checkpoint-status |  |  | checkpoint | Firewall penetrations inspected and tagged
label | 996cda9c-e3bd-55be-96df-416b3246185c |  | note | Subcontractor Responsible - Trojan Fire
checkpoint-group |  |  | section | Mechanical Services
checkpoint-status |  |  | checkpoint | Ductwork completed (for risers)
label | 6b0f0886-eb51-5cca-8d27-5ac5a1c9cb6a |  | note | Subcontractor Responsible - O.P. Industries
checkpoint-status |  |  | checkpoint | Electrical cabling completed
label | c44841bd-a292-552c-9839-5e6447f9d0ce |  | note | Subcontractor Responsible - O.P. Industries
checkpoint-status |  |  | checkpoint | Pipework completed
label | f60ef437-6e45-5903-8470-e15bb31a900c |  | note | Subcontractor Responsible - O.P. Industries
checkpoint-status |  |  | checkpoint | Mechanical protection installed (where required)
label | 08ebcc52-516e-550c-93b4-c5d7dd9efa74 |  | note | Subcontractor Responsible - O.P. Industries
checkpoint-status |  |  | checkpoint | Firewall penetrations inspected and tagged
label | a7d226dd-1504-5cac-a03a-177019e419d6 |  | note | Subcontractor Responsible - O.P. Industries
checkpoint-group |  |  | section | Ceilings & Partitions
checkpoint-status |  |  | checkpoint | Void clean
label | b12712d6-a19c-5b6c-a73c-049c7e2619cd |  | note | Subcontractor Responsible - Wake Concepts
checkpoint-status |  |  | checkpoint | Noggings installed
label | 8e0d38d1-1c01-5f52-aa0a-efed75fdef6d |  | note | Subcontractor Responsible - Wake Concepts
checkpoint-status |  |  | checkpoint | Trimmers installed
label | 219f002d-6c0d-52ce-90c4-be02ea9608e4 |  | note | Subcontractor Responsible - Wake Concepts
checkpoint-status |  |  | checkpoint | Insulation installed
label | 8ed40313-3de8-5311-b748-c817cb668d41 |  | note | Subcontractor Responsible - Wake Concepts
checkpoint-status |  |  | checkpoint | Partition types checked
label | cc20c746-d8d4-5d35-a230-dd84b0246d70 |  | note | Subcontractor Responsible - Wake Concepts
checkpoint-group |  |  | section | Lift
checkpoint-status |  |  | checkpoint | Rebate's, call buttons and landing indicators installed
label | 87e6cc9c-0248-54df-808b-7f5a722a379e |  | note | Subcontractor Responsible - Kone
checkpoint-status |  |  | checkpoint | Electrical conduit installed
label | 570382c1-1f31-533c-99f6-b504345e80bf |  | note | Subcontractor Responsible - Kone
checkpoint-status |  |  | checkpoint | Lift reveal installed
label | 981f0a57-a0cd-5ddd-83e6-4068606ea77a |  | note | Subcontractor Responsible - Kone
checkpoint-group |  |  | section | Final Sign Off
checkpoint-status |  |  | checkpoint | Works completed
text | dfb53390-977e-5c78-9f04-8264b2644c06 |  | textbox | Minor non-conformance details
text | b7a39132-41e9-56ac-82b2-85ed0a2f4a24 |  | textbox | Rectified Date
checkpoint-status |  |  | checkpoint | Reviewed, photographs taken & ready to close - signature attached below
checklist-sectioned |  |  | checklist | Ceiling Closure Checklist |  |  |  |  | Yes | Ceiling Closure Checklist | 4dc8e76a-8ec7-4f6e-9fa3-b44f67706137
checkpoint-group |  |  | section | ELECTRICAL SERVICES
checkpoint-status |  |  | checkpoint | Electrical cabling completed
label | 85a3c501-80b5-55aa-82c6-c1960fb5e4e5 |  | note | Subcontractor Responsible - Ion Electrical
checkpoint-status |  |  | checkpoint | Communications cabling completed
label | 4b2538e5-355f-5e99-8fd0-e3dfc65eea96 |  | note | Subcontractor Responsible - Ion Electrical
checkpoint-status |  |  | checkpoint | Lighting cabling completed
label | ee5325d7-c237-5c10-b45d-918403b084a8 |  | note | Subcontractor Responsible - Ion Electrical
checkpoint-status |  |  | checkpoint | Security cabling completed
label | cc716c00-a12a-5504-b9dd-c054ba838cd8 |  | note | Subcontractor Responsible - Ion Electrical
checkpoint-status |  |  | checkpoint | Seismic restraints installed (where required)
label | e9d1e570-e51f-547f-b501-5bcd6f9dec4b |  | note | Subcontractor Responsible - Ion Electrical
checkpoint-status |  |  | checkpoint | Firewall penetrations inspected and tagged
label | 685fffd6-4f2a-5de0-94da-46be66724e73 |  | note | Subcontractor Responsible - Ion Electrical
checkpoint-group |  |  | section | HYDRAULIC SERVICES
checkpoint-status |  |  | checkpoint | Drainage pipework completed
label | 78235baf-6b75-5710-812b-482f051db062 |  | note | Subcontractor Responsible - Jordan Plumbing
checkpoint-status |  |  | checkpoint | Water reticulation pipework completed
label | b6468fd3-1533-543a-b8fa-551ddfb402a4 |  | note | Subcontractor Responsible - Jordan Plumbing
checkpoint-status |  |  | checkpoint | Seismic restraints installed (where required)
label | 497496d3-3cff-5ae6-80a0-69874da7200a |  | note | Subcontractor Responsible - Jordan Plumbing
checkpoint-status |  |  | checkpoint | Firewall penetrations inspected and tagged
label | 791f3d7c-8ae7-58c2-80ee-0a62a2a264e8 |  | note | Subcontractor Responsible - Jordan Plumbing
checkpoint-group |  |  | section | FIRE SERVICES
checkpoint-status |  |  | checkpoint | Dry fire cabling completed
label | 441ff436-2754-5b9f-8c79-c37a90859ec3 |  | note | Subcontractor Responsible - Trojan Fire
checkpoint-status |  |  | checkpoint | Wet fire pipework completed
label | 4b85db80-d354-5c6a-b30f-40e8a402d17a |  | note | Subcontractor Responsible - Trojan Fire
checkpoint-status |  |  | checkpoint | Seismic restraints installed (where required)
label | a45ddfa1-f6a8-5b82-a496-36052b41e1d5 |  | note | Subcontractor Responsible - Trojan Fire
checkpoint-status |  |  | checkpoint | Firewall penetrations inspected and tagged
label | 58f1ba79-82e7-5720-8819-6eea1c47cc8b |  | note | Subcontractor Responsible - Trojan Fire
checkpoint-group |  |  | section | MECHANICAL SERVICES
checkpoint-status |  |  | checkpoint | Ductwork completed
label | d1527288-cf84-5dc9-87aa-4eb5c7fb298d |  | note | Subcontractor Responsible - O.P. Industries
checkpoint-status |  |  | checkpoint | Electrical cabling completed
label | 61561b62-7d87-58c8-91a3-1b33e9d32026 |  | note | Subcontractor Responsible - O.P. Industries
checkpoint-status |  |  | checkpoint | Pipework completed
label | 159dc858-f2d7-518b-83cf-d3a90f825f83 |  | note | Subcontractor Responsible - O.P. Industries
checkpoint-status |  |  | checkpoint | Seismic restraints installed (where required)
label | 1569ff59-402e-549f-840f-b2d9993f4e8c |  | note | Subcontractor Responsible - O.P. Industries
checkpoint-status |  |  | checkpoint | Firewall penetrations inspected and tagged
label | de05cb53-9775-5fd5-a8dd-02a6f8bcc9d0 |  | note | Subcontractor Responsible - O.P. Industries
checkpoint-group |  |  | section | CEILINGS & PARTITIONS
checkpoint-status |  |  | checkpoint | Void clean
label | f32a01eb-6088-5a83-8de6-238c7528f885 |  | note | Subcontractor Responsible - Wake Concepts
checkpoint-status |  |  | checkpoint | Acoustic baffles installed
label | 3ab8ed6d-573f-573d-b065-c4c7970eaa75 |  | note | Subcontractor Responsible - Wake Concepts
checkpoint-status |  |  | checkpoint | Access panels coordinated and framed
label | 8b10132d-e54c-5ec8-9094-cee13171bc2d |  | note | Subcontractor Responsible - Wake Concepts
checkpoint-status |  |  | checkpoint | Insulation installed
label | 622a9526-67d0-5cb4-bd20-6e9da3e61e03 |  | note | Subcontractor Responsible - Wake Concepts
checkpoint-status |  |  | checkpoint | Ceiling types checked
label | 261eff1c-5f6a-5247-b8b5-1615e1f9af7d |  | note | Subcontractor Responsible - Wake Concepts
checkpoint-group |  |  | section | Final Sign Off
checkpoint-status |  |  | checkpoint | Works completed
text | 6533ec46-3f1f-5dc9-bc05-f2df33587a06 |  | textbox | Minor non-conformance details
text | 8c05562c-9af3-5499-a107-fa810d5287e1 |  | textbox | Rectified Date
checkpoint-status |  |  | checkpoint | Reviewed, photographs taken & ready to close - signature attached below
checklist-flat |  |  | checklist | Built Concrete Placement |  |  |  |  | Yes | Built Concrete Placement Checklist | 5cf852bd-c3c2-45e4-97a3-a18cd36f0123
checkpoint-status |  |  | checkpoint | Concrete Mix Design on Dockets
text | 0711baea-26f7-5388-99d9-b7caf7bcf7c6 |  | textbox | Insert Concrete Mix Design
checkpoint-status |  |  | checkpoint | Concrete Mpa
text | 935d19a9-ad58-5abc-8736-d47a0e10c210 |  | textbox | Insert Concrete Strength
checkpoint-status |  |  | checkpoint | Concrete Strength Correct on Delivery Dockets
checkpoint-status |  |  | checkpoint | Curing Applied
checkpoint-status |  |  | checkpoint | Concrete Tester on site
checkpoint-status |  |  | checkpoint | Water Addition
button | 19a870f6-d9e0-5741-a594-b76ea5f98bb7 |  | button | Water Added (and recorded on docket) | Added & Recorded,Added & Not Recorded
checklist-flat |  |  | checklist | Loading Bay Installation Sign-off Checklist |  |  |  |  | Yes | Loading Bay Installation Sign-off Checklist | 65da0faf-c61d-472a-bb09-2ba3d22b44e3
checkpoint-status |  |  | checkpoint | Loading Bay Installed As Per Propping Design
checkpoint-status |  |  | checkpoint | Loading Bay Installed By Competent Persons (Rigger)
checkpoint-status |  |  | checkpoint | Gates Closed
checkpoint-status |  |  | checkpoint | Padlock On Doors
checkpoint-status |  |  | checkpoint | Props Secured
checkpoint-status |  |  | checkpoint | Safe Working Load Signage On Loading Bay
checkpoint-status |  |  | checkpoint | Chain In Place At Front Of Loading Bay
checkpoint-status |  |  | checkpoint | Kickers In Place
checkpoint-status |  |  | checkpoint | Handrails In Place
checkpoint-status |  |  | checkpoint | Barricade Area
checkpoint-status |  |  | checkpoint | Backpropped As Per Design
checkpoint-status |  |  | checkpoint | Bracket Dynabolted Into Ceiling For Harness
checkpoint-status |  |  | checkpoint | Signage Displayed During Installation Process
checklist-flat |  |  | checklist | Concrete Prepour Checklist - Stairs |  |  |  |  | Yes | Concrete Prepour Checklist - Stairs | 716a9d96-ff51-4713-8426-0730710aa4cb
checkpoint-status |  |  | checkpoint | Stair Pan & Formwork Installation
label | efd199a3-ab0b-57cd-9745-8fbe486dd8dc |  | note | Subcontractor Responsible - Form 700 **Signature Required
checkpoint-status |  |  | checkpoint | Electrical Conduits
label | f7d3ef26-cae4-53d7-9a92-1c9663005875 |  | note | Subcontractor Responsible - ION **Signature Required
checkpoint-status |  |  | checkpoint | Fire Services Installation
label | 9079394b-1b24-5d9b-afd5-fc7041cd2380 |  | note | Subcontractor Responsible - Trojan **Signature Required
checkpoint-status |  |  | checkpoint | Hydraulic Services
label | 9dceb5c7-44d1-58fe-8469-bc566d046b1f |  | note | Subcontractor Responsible - Jordans **Signature Required
checkpoint-status |  |  | checkpoint | Reinforcement - Complete
label | e57b2d70-ae4a-5234-8e2a-69f9e5431db2 |  | note | Subcontractor Responsible - Titans **Signature Required
checkpoint-status |  |  | checkpoint | Engineer's Comments Received
select | c89120a8-74ac-5bfa-a133-986eb9935c00 |  | dropdown | Actions Required | No Defects,Defects Rectified
checkpoint-status |  |  | checkpoint | General Observations
boolean | 21b02e61-1527-585d-85e6-2bf4e8ee514a |  | tickbox | Cleanout Pre-pour
boolean | 60e40f24-05cf-52e7-84f7-7530f9633aa6 |  | tickbox | Cover Achieved
checklist-flat |  |  | checklist | Quality On-site Inspection - Concrete Structure |  |  |  |  | Yes | Quality On-site Inspection - Concrete Structure | 73b6f548-7c73-4fda-9e91-28b08a5ffbaa
checkpoint-no-status |  |  | checkpoint | Areas or Locations Inspected
checkpoint-status |  |  | checkpoint | Wall Starters
label | e4c19ca3-a4ad-532e-8ac5-21062f9a56b5 |  | note | Wall/ starters set out e.g centre line pinned in accordance with drawings.
checkpoint-status |  |  | checkpoint | Electrical Installation
label | 3cce0da3-9f46-58c1-b116-df77c96f342e |  | note | Electrical cast-ins/conduit installed e.g. Correct sizing runs parallel/vertical adequately saddled, galvanised conduit deburred, lids fitted and screwed, sets/bends to trade standard, exposed external conduit threads sealed, all PVC joints glued, expansion joints installed where require.
checkpoint-status |  |  | checkpoint | Hydraulic Installation
label | e8f0b1b7-9ccc-5352-b69d-a57c808044ab |  | note | Hydraulic installed e.g. in-ground sewer, storm water, pits installed e.g. Authority approval received, excavation as per design, dimensions and levels as per design, sleeving protected, backfill compaction adequate, penetrations capped and tape. Static test passed. Authorities inspection completed with defects rectified.
checkpoint-status |  |  | checkpoint | Mechanical Installation
label | b2cddac1-e029-586e-a929-49527c052227 |  | note | Mechanical provisions e.g. Set-out as per design, conduit, penetrations etc.
checkpoint-status |  |  | checkpoint | Formwork Installation
label | 6d5cf72b-c040-5d80-91e4-94d22eff09db |  | note | Formwork installed e.g. formwork line and level correct. Frames, braces and supporting members in place, all cast-in items installed in slab area such as dowel bars, block outs, penetrations, set downs, H/D bolts. Joints installed correctly. Area clean of debris and ready for concrete.
checkpoint-status |  |  | checkpoint | Jumpform and Proprietary Installation
label | df100571-98d4-5ed2-b362-982305852eb5 |  | note | Formwork - jumpform and proprietary system installed e.g. formwork element built to formwork design, access and egress to and from working area in place for other trades, working platforms in place, edge protection, kickboards and handrails in place, penetrations and blockouts completed and covered.
checkpoint-status |  |  | checkpoint | Reinforcement Installation
label | c2ee3972-74e4-5371-858d-eef128cc9860 |  | note | Reinforcement installed e.g. beams, bottom, reo, top reo, starters, walls, columns installed as per design with correct size, type, spacings, position, adequate coverage, splicing lap, adequate chairing.
checkpoint-status |  |  | checkpoint | Concrete Pour
label | e9bdf061-a190-5226-b263-e36c8ff13e78 |  | note | Concrete poured e.g. correct mix design, concrete dockets received, NATA tester onsite, levels marked in place, finished level within tolerance, surface finish acceptable, curing provisions in place.
checkpoint-status |  |  | checkpoint | Other
label | e26f60ac-9eb2-5109-90cf-938fbfac44c2 |  | note | Compliance for other checks performed.
checklist-flat |  |  | checklist | Critical Risk Control Monitoring |  |  |  |  | Yes | Critical Risk Control Monitoring | 8173a8bd-a0a5-4f86-9499-18bf5b7571dc
checkpoint-no-status |  |  | checkpoint | Areas or Locations Inspected
text | aeb5f501-6a5e-5ad9-b6f2-aa11ad2664c9 |  | textbox | Subcontractor
select | 503ef7c4-aa09-51d8-87a2-8419f766edc4 |  | dropdown | Critical Risk Control Type | Object Fall From Height,Other (Specify below)
text | 3c7f5b3e-d116-5d4f-97c3-a31aeb4637c9 |  | textbox | If 'Other' - specify
boolean | 68045f9a-dd76-5f9a-933a-01261b3ccd82 |  | tickbox | Clearway
boolean | 5d6b5537-27e5-58e0-92f6-bbe6e9ad0f3b |  | tickbox | Secure Zone
boolean | c5063ea2-4fe0-5ee5-a8f8-93338d3a07e2 |  | tickbox | Exclusion Zone
boolean | c7c8f5bf-7786-57b3-9906-91945d5d0988 |  | tickbox | Secondary Edge Protection Deployed
text | 7014fb2a-cd85-57ad-862b-0b6439f11822 |  | textbox | General Comments
checklist-sectioned |  |  | checklist | Concrete Prepour Checklist - Core |  |  |  |  | Yes | Concrete Prepour Checklist - Core | 9c5f8154-35c0-49ab-a76e-578dc31a340c
checkpoint-group |  |  | section | Pre-Pour Checks
checkpoint-status |  |  | checkpoint | Jumpform Handover
label | d20012de-d1ad-5c52-8adb-7bdb7d4ae283 |  | note | Subcontractor Responsible - Form 700 **Signature Required
checkpoint-status |  |  | checkpoint | Electrical Inserts & Penetrations Complete
label | 407d2012-a668-51fe-8342-b9495cfa7ffe |  | note | Subcontractor Responsible - ION **Signature Required
checkpoint-status |  |  | checkpoint | Hydraulic Inserts & Penetrations Complete
label | e2cd0ded-f3f3-5808-aa42-f483eafcbba4 |  | note | Subcontractor Responsible - Jordans **Signature Required
checkpoint-status |  |  | checkpoint | Mechanical Inserts & Penetrations Complete
label | a0e9bcf9-69c2-55f4-82fc-05f3aed5a680 |  | note | Subcontractor Responsible - OP Industries **Signature Required
checkpoint-status |  |  | checkpoint | Fire Inserts & Penetrations Complete
label | b95da85c-6dc2-50a0-81fe-45bb22c1feb9 |  | note | Subcontractor Responsible - Trojan Fire **Signature Required
checkpoint-status |  |  | checkpoint | Reinforcement Complete
label | 5d75806b-3b3e-5f6f-8df8-a6bc0daafdc3 |  | note | Subcontractor Responsible Titan Steelfixing **Signature Required
checkpoint-status |  |  | checkpoint | HD Bolts / Castins (Line and Level)
label | 1277c1b1-437a-5c96-ac7a-c1424fb2e24c |  | note | ** Comment on Cast-ins Installed
checkpoint-status |  |  | checkpoint | Wall Closure
label | 72c67ccc-1da5-5f1d-9670-ac2d8fd110e6 |  | note | Subcontractor Responsible - Form 700
checkpoint-status |  |  | checkpoint | Survey - Line and Level
label | 8af1bc7c-ba88-5093-8ef3-fcacc8c36076 |  | note | Subcontractor Responsible - Form 700
checkpoint-status |  |  | checkpoint | General Observations
boolean | 09586ea2-5127-5d3a-8d16-9dee7491b267 |  | tickbox | Cleanout Pre-Pour
boolean | 0d79b0a6-96f1-570b-b717-3304a372c953 |  | tickbox | No Reinforcement Protruding from Penetrations
boolean | 3d81876a-cbd9-51c2-83e3-bef9491e496a |  | tickbox | Cover Achieved
checkpoint-group |  |  | section | Engineers Site Inspection
checkpoint-status |  |  | checkpoint | Reinforcement Inspection
select | 0fa4596c-7ff2-5455-bb99-0782c9961fbd |  | dropdown | Actions Required | No Defects,Defects Rectified on-site,Defects Outstanding - Close out Required
checklist-flat |  |  | checklist | Built Sign-off |  |  |  |  | Yes | Built Column ITP | 9e75d457-ea62-4f36-858e-0ff3010304a3
checkpoint-status |  |  | checkpoint | Reinforcement Placement
label | f2ca3aa8-a6fb-5d9c-be09-c34574286a19 |  | note | Subcontractor Responsible - Titans **Signature Required
checkpoint-status |  |  | checkpoint | Engineer's Comments Received
select | 446bb5e2-8d84-50c4-84de-181240f00982 |  | dropdown | Actions Required | No Defects,Defects Rectified
checkpoint-status |  |  | checkpoint | Electrical Installation Complete
label | de7cc821-dd92-5f49-a92b-d40cdbc5db68 |  | note | Subcontractor Responsible - ION **Signature Required
checkpoint-status |  |  | checkpoint | Hydraulic Installation Complete
label | 8cbdffc2-37ba-5f8f-98e4-5f1617d2379a |  | note | Subcontractor Responsible - Jordans **Signature Required
checkpoint-status |  |  | checkpoint | Mechanical Sensor Conduit Installation Complete
label | 12f9c09c-7fe8-4b64-a531-5a2a7a17e5e1 |  | note | Subcontractor Responsible - O.P. Industries **Signature Required
checkpoint-status |  |  | checkpoint | Formwork Sleeve Installed
label | 0db7a4af-9b73-5760-a082-9f4d09739a2e |  | note | Subcontractor Responsible - Form 700 **Signature Required
checkpoint-status |  |  | checkpoint | Column Reinforcement Verticality Check
label | c79b6fcb-26ec-5913-9a0e-ec5913428583 |  | note | Visual/ Column Prepour Survey
checkpoint-status |  |  | checkpoint | General Observations
boolean | 119860f7-7c49-55f3-b556-21947eacce33 |  | tickbox | Cleanout Pre-pour
boolean | 96b48794-72ca-5d3e-bd41-3135bbad80c4 |  | tickbox | Cover Achieved
checklist-flat |  |  | checklist | Formwork Stripping Completion Checklist |  |  |  |  | Yes | Formwork Stripping Completion Checklist | ad0e172c-ea6f-4f94-a042-1cd87dfed6e2
checkpoint-status |  |  | checkpoint | Columns stripped and Slurry Removed
checkpoint-status |  |  | checkpoint | Formwork removed from area
checkpoint-status |  |  | checkpoint | Penetrations stripped and covered
checkpoint-status |  |  | checkpoint | Patching complete to soffit / walls / columns / jump pockets
checkpoint-status |  |  | checkpoint | Edge protection in place
checkpoint-status |  |  | checkpoint | All stripped formwork cleaned, de-nailed, strapped, and removed
checkpoint-status |  |  | checkpoint | Slab area cleaned thoroughly & trade waste placed in bins provided
checkpoint-status |  |  | checkpoint | Outstanding Items
select | 1da0803e-878a-5071-8ea6-4fab434963a7 |  | dropdown | Select: | Outstanding Items,No Items Outstanding
label | 9a5011eb-b180-5c80-afea-9d7d336f3632 |  | note | List all outstanding items below, close out required prior to passing this checkpoint
checkpoint-status |  |  | checkpoint | Handover Accepted
checklist-flat |  |  | checklist | Offsite Inspection - Subcontractor ITP / Checklist |  |  |  |  | Yes | Offsite Inspection - Subcontractor ITP / Checklist | b0450662-a3a4-4d73-8ba1-c02f8c8d455f
checkpoint-status |  |  | checkpoint | Areas or Locations Inspected
label | b82188e5-9e4e-55d7-a0f6-1bc92bbb2504 |  | note | Identify the area/s reviewed during the inspection. They may include whole of project, certain levels or certain locations.
checkpoint-status |  |  | checkpoint | Drawings/ Documents
label | 03f14f92-933c-5d44-8c8d-c16c9d767b82 |  | note | Drawings and documents receipt, issue for approval, superseded, issue for manufacture can be demonstrated at subcontractor site.
checkpoint-status |  |  | checkpoint | Sample Approval
label | e8d9d0bf-e9e1-5c13-a741-a77281c17a59 |  | note | Sample approval can be demonstrated at subcontractor site.
checkpoint-status |  |  | checkpoint | Material Inspections
label | 7b908e50-3f45-5eee-b6f7-274cd65dda5c |  | note | Material incoming inspections of quantity and damage can be demonstrated at subcontractor site.
checkpoint-status |  |  | checkpoint | Purchasing
label | 8092ec6e-2189-53cd-9474-2560ba9a941c |  | note | Purchasing and supplier process can be demonstrated at subcontractor site.
label | ec74a0df-0856-5ce6-a853-f53efe9ebacd |  | note | Compliant/ Non- compliant/ Not Applicable
checkpoint-status |  |  | checkpoint | Delivery Control
label | 65ee06c5-91f2-5191-9ea7-3fb22d5e9476 |  | note | Control of delivery dockets and test certificates can be demonstrated at subcontractor site.
checkpoint-status |  |  | checkpoint | Consumables Control
label | 4de78bb6-9ec0-563a-8671-a6f205c73b5c |  | note | Consumables control can be demonstrated at subcontractor site.
checkpoint-status |  |  | checkpoint | Installers Qualifications
label | c1edbb70-6649-543a-a725-777e051dd429 |  | note | Installers qualifications can be demonstrated at subcontractor site.
checkpoint-status |  |  | checkpoint | Transport Handling
label | 38436cc6-3f62-5cf3-8682-b1423e05202e |  | note | Transport and handling can be demonstrated at subcontractor site
checkpoint-status |  |  | checkpoint | Other
label | 9b833de7-2352-50ff-b6d2-d894efc8a625 |  | note | Compliance for other checks performed.
checklist-flat |  |  | checklist | Material Traceability Inspection |  |  |  |  | Yes | Material Traceability Inspection | b091b6f1-adf9-45e1-914b-fdc472d6fa47
checkpoint-no-status |  |  | checkpoint | Material Traceability Option
select | 81ea1745-badb-5584-b3fc-ee47789cdabe |  | dropdown | Inspection type | Specification,Sample Register
text | dfe12799-85a5-59e0-856e-ea57880d21b8 |  | textbox | Areas or Locations Inspected
label | b2481f94-1ea4-5270-a67e-0c1b0a93c9a0 |  | note | Identify the area/s reviewed during the inspection. They may include whole of project, certain levels or certain locations.
checklist-flat |  |  | checklist | Subcontractor Drawing Inspection |  |  |  |  | Yes | Subcontractor Drawing Inspection | b20d86cf-a07b-4b57-ae0f-aea5b37daab5
checkpoint-no-status |  |  | checkpoint | Areas or Locations Inspected
label | 17b3302e-e2f5-546a-837c-4b2cfdce58f1 |  | note | Identify the area/s reviewed during the inspection. They may include whole of project, certain levels or certain locations.
checkpoint-status |  |  | checkpoint | Revisions
label | 5955c83e-c1f7-558e-97db-3279633d92f6 |  | note | Check Aconex/Fieldwire/Drawing register to see if drawing revisions match and the status of the drawing is IFC.
checkpoint-status |  |  | checkpoint | Other
label | 2d77659f-d70c-5651-8828-cdedf3c0ba39 |  | note | Compliance for other checks performed.
checklist-flat |  |  | checklist | Built Spinewall Precast ITP |  |  |  |  | Yes | Built Spinewall Precast ITP | e63293fe-3fa5-49ce-9f0a-640c37d3e0f6
checkpoint-status |  |  | checkpoint | Panel Delivery Inspection
checkpoint-status |  |  | checkpoint | Horizontal Joint (Dry Pack)
label | 3d59bac7-138b-50eb-8655-3f3fbe9570bd |  | note | Material Traceability Check
checkpoint-status |  |  | checkpoint | Dowel Duct Grout
label | 6b2d125e-b12d-59ad-8aeb-da421a8837a7 |  | note | Material Traceability Check
checkpoint-status |  |  | checkpoint | Ties into landing
checkpoint-status |  |  | checkpoint | Wet-stitch Reinforcement
checkpoint-status |  |  | checkpoint | Wet-stitch Pour
checkpoint-status |  |  | checkpoint | Stripping Props
boolean | 7668c747-4987-51a2-999e-909e6b192e08 |  | tickbox | Panels ready for Props to be stripped
checklist-flat |  |  | checklist | Offsite Inspection - Subcontractor Quality Plan |  |  |  |  | Yes | Offsite Inspection - Subcontractor Quality Plan | e9dac972-d57e-4655-98a2-1b9c2f167b18
checkpoint-no-status |  |  | checkpoint | Areas or Locations Inspected
label | 3c26677f-789c-509c-99df-b3380d6aab3f |  | note | Identify the area/s reviewed during the inspection. They may include whole of project, certain levels or certain locations.
checkpoint-status |  |  | checkpoint | Organisation Chart
label | 8a89fdf8-5ddf-560b-ae05-f433d8e53fee |  | note | Organisation chart, responsibilities of staff demonstrated at subcontractor site.
checkpoint-status |  |  | checkpoint | Design Sample
label | be004318-2824-573c-b47f-85ca45a1088d |  | note | Design/Sample control process can be demonstrated at subcontractor site.
checkpoint-status |  |  | checkpoint | Document Data
label | b64fe952-b6ef-5e83-90b3-b1e40267cf0f |  | note | Document and data control process can be demonstrated at subcontractor site.
checkpoint-status |  |  | checkpoint | Purchasing
label | b9dac909-0ef3-5e69-ae73-ce4c3f50a9ac |  | note | Purchasing and supplier process can be demonstrated at subcontractor site.
checkpoint-status |  |  | checkpoint | Product Identification
label | 6afccf43-711e-53f3-9abd-270cc0e7a7e1 |  | note | Product identification and traceability can be demonstrated at subcontractor site.
checkpoint-status |  |  | checkpoint | Process Control
label | 34403db3-c7c8-5368-9a71-3aa73628aee1 |  | note | Process control can be demonstrated at subcontractor site.
checkpoint-status |  |  | checkpoint | Inspection Testing
label | c7d91469-7e6e-598b-a1c8-398fe5603e59 |  | note | Inspection and testing can be demonstrated at subcontractor site.
checkpoint-status |  |  | checkpoint | Inspection Control
label | c1bad5b6-9b29-5cf7-beee-db56ed54fd01 |  | note | Control of inspection, measuring and test equipment can be demonstrated at subcontractor site.
checkpoint-status |  |  | checkpoint | Non-conformance Control
label | 3d13b4fe-87b6-5a1e-856e-607afcbf8106 |  | note | Control of non-conformance can be demonstrated at subcontractor site.
checkpoint-status |  |  | checkpoint | Handling Control
label | 486d6618-659b-551d-af8f-14d4dd2686d4 |  | note | Control of handling, storage, packaging and delivery can be demonstrated at subcontractor site.
checkpoint-status |  |  | checkpoint | Other
label | 9fb53091-f1ba-5c5b-9917-9679c7c65c3a |  | note | Compliance for other checks performed.
checklist-flat |  |  | checklist | Supervisor Site Inspection |  |  |  |  | Yes | Supervisor Site Inspection | fc6656f4-be14-404c-95a6-84a21d574076
checkpoint-no-status |  |  | checkpoint | Areas or Locations Inspected
select | d0bb3ba5-5f01-54d5-9e90-4946ccedbb11 |  | dropdown | Type of Site Inspection | Supervisor Inspection,Consultative Process Inspection,Environmental Inspection,Other (Specify Below)
text | d79e6409-a50e-5923-98cc-eed48364abc8 |  | textbox | If 'Other' - specify
label | e1bb70eb-2096-53e0-8729-fe1c9ebdf1f2 |  | note | (Identify the area(s) reviewed during the inspection)
checkpoint-no-status |  |  | checkpoint | Summary of Inspection
label | f3b645a9-dbc7-56c8-89aa-f0b420519a40 |  | note | (Provide an outline of any positive observations or conversations, work practices being performed well, compliance with the documents reference or a brief outline)
checklist-sectioned |  |  | checklist | Concrete Pre-Pour Checklist - Slab |  |  |  |  | Yes | Concrete Pre-Pour Checklist - Slab | fd442cb5-b228-4cb4-864c-1ff9b0d0d96b
checkpoint-group |  |  | section | Pre-Pour Checks
checkpoint-status |  |  | checkpoint | Formwork Completed
label | 06fa4554-44d4-5f34-a6ed-daa8d8809784 |  | note | Subcontractor Responsible - Form 700 **Signature Required
checkpoint-status |  |  | checkpoint | Formwork Certificate Received
label | a2f7aec4-d735-5dd6-9223-39b95cd1b303 |  | note | Subcontractor Responsible - Form 700 **Signature Required
checkpoint-status |  |  | checkpoint | Electrical Inserts & Penetrations Complete
label | 5362aac9-bd96-543c-a8d3-77dc7d373cea |  | note | Subcontractor Responsible - ION **Signature Required
checkpoint-status |  |  | checkpoint | Hydraulic Inserts & Penetrations Complete
label | ff4bfc84-4ef7-5639-ba51-3f3a7bbcfea2 |  | note | Subcontractor Responsible - Jordans **Signature Required
checkpoint-status |  |  | checkpoint | Mechanical Inserts & Penetrations Complete
label | 834a63fa-2be9-5ae8-a016-519dee1fe69e |  | note | Subcontractor Responsible - OP Industries **Signature Required
checkpoint-status |  |  | checkpoint | Fire Inserts & Penetrations Complete
label | a616e864-c12a-5482-aa09-e6b49cc99689 |  | note | Subcontractor Responsible - Trojan Fire **Signature Required
checkpoint-status |  |  | checkpoint | Post Tensioning Complete
label | 7d1dc4a5-c903-5ad9-b5d5-8372dc0eb878 |  | note | Subcontractor Responsible AusPT **Signature Required
checkpoint-status |  |  | checkpoint | Reinforcement Complete
label | b5670851-9d82-5774-8c93-a77fda614030 |  | note | Subcontractor Responsible Titan Steelfixing **Signature Required
checkpoint-status |  |  | checkpoint | HD Bolts / Castins (Line and Level)
label | 9936cecc-af9e-5ed9-ba4a-c911a47d9b94 |  | note | ** Comment on Cast-ins Installed
checkpoint-status |  |  | checkpoint | Joint Locations Confirmed by Formwork - External Joints
label | 22d983ae-d23d-53ed-8b21-9133489efd92 |  | note | Subcontractor Responsible - Form 700
checkpoint-status |  |  | checkpoint | Survey - Line and Level
label | b0f5c6ae-4d24-5803-ab34-31feb05dc20d |  | note | Subcontractor Responsible - Form 700
checkpoint-status |  |  | checkpoint | Electrical Conduits
label | 43ecec3a-f6e4-5bf1-890e-a09d3faa9bd4 |  | note | Subcontractor Responsible - ION **Signature Required
checkpoint-status |  |  | checkpoint | Hydraulic Services
label | ead12f05-5170-536d-8e70-4c24c027fdaf |  | note | Subcontractor Responsible - Jordans **Signature Required
checkpoint-status |  |  | checkpoint | General Observations
boolean | 1f83d385-0e70-56ac-8f1d-8be876abad31 |  | tickbox | Cleanout Pre-Pour
boolean | a59e4edb-db35-5ab9-a1d0-08811bb8c36a |  | tickbox | No Reinforcement Protruding from Penetrations
boolean | a925a160-e573-5a54-8a61-18af64d0073a |  | tickbox | Cover Achieved
checkpoint-group |  |  | section | Engineers Site Inspection
checkpoint-status |  |  | checkpoint | Reinforcement Inspection
select | 3bb9396d-35cc-5d98-ae8c-edb52b273913 |  | dropdown | Actions Required | No Defects,Defects Rectified on-site, Defects Outstanding - Close out Required
checkpoint-status |  |  | checkpoint | Post Tensioning Inspection
select | 1fc3d339-7eea-5e1c-b25f-3658318ce3c5 |  | dropdown | Actions Required | No Defects,Defects Rectified on-site, Defects Outstanding - Close out Required