## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Detailed Excavation |  |  |  |  | Yes | C - S - Detailed Excavation | 1b1fcc40-597c-4383-bd2d-4fea75109c3f
checkpoint-status |  |  | checkpoint | Grids/profiles/set out completed, clearly marked and accurate
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Services (overhead / below ground) considered and isolated where required before excavation commences
checkpoint-status |  |  | checkpoint | Approval given to commence detailed excavation
checkpoint-status |  |  | checkpoint | Excavation checked, correct and approved
boolean | 04d28910-e9c9-5bd2-9a95-613f7d90c8ab |  | tickbox | Location accurate
boolean | 4d9129b0-c09c-5561-8e88-5d96918cca7f |  | tickbox | Depth correct (allow for site concrete if required)
boolean | 0f6af734-6ba9-581f-832b-b3878555f989 |  | tickbox | Width correct (allow for boxing if required)
checkpoint-status |  |  | checkpoint | Placement of Geotextile (2 photos required)
checkpoint-status |  |  | checkpoint | Placement of hardfill
checkpoint-status |  |  | checkpoint | Placement of Geogrid (2 photos)
checkpoint-status |  |  | checkpoint | NDM test and report (supporting documents incl. photos)
checkpoint-status |  |  | checkpoint | Completed level of hardfill (completion NDM test with report and supporting documents (incl. photos) and uploaded into QA system)
checkpoint-status |  |  | checkpoint | Any additional layer of hardfill (300mm) requires an NDM test (report and supporting documents (incl. photos) sent uploaded into QA system
holdpoint |  |  | signoff | Sand blinding and check final RL. (completion required to handover to the next stage-townhouses only)
checkpoint-status |  |  | checkpoint | Excavation for services is completed and accurate
checkpoint-status |  |  | checkpoint | Excess material cleaned up and removed as required
checkpoint-status |  |  | checkpoint | Detailed excavation completed, reviewed and approved
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Earthworks Checks |  |  |  |  | Yes | QA - Earthworks Checklist (V1) | 3de082c8-8866-4b3e-a6ee-874187738c7f
checkpoint-status |  |  | checkpoint | Inspection of subgrade, after topsoil stripped
checkpoint-status |  |  | checkpoint | NDM tests on imported material in 300mm layers
checkpoint-status |  |  | checkpoint | General photos / comments / observations
checkpoint-status |  |  | checkpoint | Earthworks completed, checked and acceptable
boolean | 24b633f0-1e59-4c87-bba1-eefcd3a0c25a |  | tickbox | Report & Signoff request sent to Ryman & T+T
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | H&S - Upload - |  |  |  |  | Yes | H&S - Upload of Daily H&S Paperwork (V2) | 4126ec19-ae66-44fe-8ed7-ab8e5f911742
checkpoint-status |  |  | checkpoint | H&S Paperwork filled out & attached
label | ed994d10-d5b2-4784-8ce7-1eda50c5e211 |  | note | Select "PASS" once the paperwork is completed and uploaded here
holdpoint |  |  | signoff | Request Review
checklist-sectioned |  |  | checklist | QA - Stormwater / Gravity Sewer (Main Line) - Installation Checklist (V2) |  |  |  |  | Yes | QA - Stormwater / Gravity Sewer (Main Line) - Installation Checklist (V2) | 4c87dbcc-2222-41a3-ae3d-f5f98b083b70
checkpoint-group |  |  | section | Pipe Laying / Manhole Install
checkpoint-status |  |  | checkpoint | Latest construction drawings referenced and followed
text | 6b075eee-f7c0-4f5c-8474-1f77ee482a97 |  | textbox | Drawing & Revision Number
checkpoint-status |  |  | checkpoint | Correct safety procedures (i.e. trench supports or benching)
checkpoint-status |  |  | checkpoint | Setout & Excavation completed checked and accurate.
checkpoint-status |  |  | checkpoint | Ground conditions checked & acceptable (min 50kpa)
boolean | d10d335d-ef31-43b7-bead-4d4fad6a47fc |  | tickbox | If ground is soft or uncertain - Notify Ryman & Woods
checkpoint-status |  |  | checkpoint | Trench width, Bedding depth and material correct (photo required)
checkpoint-status |  |  | checkpoint | Correct materials (size, material & class of pipe & MH) laid to specified level, grade and jointed as specified
checkpoint-status |  |  | checkpoint | Relevant building line junctions installed
text | de91b245-67ee-4336-add1-b8e14a419d0b |  | textbox | Invert Level (upstream manhole)
text | 7f873965-82ac-46c8-81d0-0e66992a0e64 |  | textbox | Invert Level (downstream manhole)
text | a1bae0c5-0c4f-4ce1-a60b-70a31c674e6d |  | textbox | Design length of pipe (m)
text | 2a1bac9a-11b0-489e-b61f-a37aa8c80431 |  | textbox | Length of pipe installed (m)
text | f676110b-a253-47e6-a1bd-25d9f2bfa9a6 |  | textbox | Grade of Pipe-Line %
checkpoint-status |  |  | checkpoint | Connections to manholes complete and approved (photo required)
checkpoint-status |  |  | checkpoint | Manhole benching completed and acceptable (photo required)
checkpoint-status |  |  | checkpoint | As-built junctions before backfill
boolean | feae76b4-6180-473a-90e8-8d072acb6193 |  | tickbox | Woods has viewed and approved for backfilling
checkpoint-group |  |  | section | Backfill & Testing
checkpoint-status |  |  | checkpoint | Approval to backfill
checkpoint-status |  |  | checkpoint | General photos during backfill
checkpoint-status |  |  | checkpoint | Backfill completed & compacted as specified (draft testing) (Photos during backfill required)
boolean | eee933d3-5e07-41e8-a4ef-d3c668845986 |  | tickbox | Specified compaction achieved
checkpoint-status |  |  | checkpoint | Pressure test (timestamp photos of gauge before & after)
checkpoint-status |  |  | checkpoint | CCTV
checkpoint-status |  |  | checkpoint | Testing Results (Inc. final compaction results),Photos & as-built information provided to Woods
checkpoint-status |  |  | checkpoint | Cast Iron Lid installed and fixed at correct height (photo required)
holdpoint |  |  | signoff | FINAL SIGN OFF
checklist-flat |  |  | checklist | Pressure Sewer |  |  |  |  | Yes | QA - Pressure Sewer - V1 | 6d307792-d0b1-4e88-a3ba-9e11cdb8ff32
checkpoint-status |  |  | checkpoint | General photos / comments / observations
checkpoint-status |  |  | checkpoint | Welds tested and documents attached & completed
checkpoint-status |  |  | checkpoint | Pressure test attached & completed
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | Service Trench |  |  |  |  | Yes | QA - Service Trench - V1 | 6e733ec1-819d-4cb9-9f79-5f98762a8d04
checkpoint-status |  |  | checkpoint | Survey the area and record data
checkpoint-status |  |  | checkpoint | General photos / comments / observations
checkpoint-status |  |  | checkpoint | Accurate backfill and compact - NDM results / photos attached
holdpoint |  |  | signoff | Request Sign Off
checklist-sectioned |  |  | checklist | Pre-Commencement Checks |  |  |  |  | Yes | Pre-Commencement Checklist (V3) | 746a0d16-b46c-43be-b769-d1c0c548c282
checkpoint-group |  |  | section | Health & Safety Pre-Commencement Checks
checkpoint-status |  |  | checkpoint | Trade Contractor H&S Policy - Completed & Attached
checkpoint-status |  |  | checkpoint | Trade Contractor Site Specific Safety Plan (SSSP) - Completed & Attached
checkpoint-status |  |  | checkpoint | Trade Contractor Worksafe NZ Notification - Completed & Attached (if applicable)
label | 37eb00ad-3fe8-4fbf-91a7-8f80cabd3ba2 |  | note | If not required select N/A
checkpoint-status |  |  | checkpoint | Trade Contractor Environmental Policy - Completed & Attached (if applicable)
label | 1b4b5b5e-bc9a-48de-bf72-b069b9ab5092 |  | note | If not required select N/A
checkpoint-status |  |  | checkpoint | Any Additional Prestart H&S Documentation uploaded
label | 5506d5cf-c484-4998-9f4f-03fb857274a4 |  | note | "Pass" once uploaded or select "N/A" if there are no additional requirements to those listed above
checkpoint-status |  |  | checkpoint | All Health & Safety Pre-Commencement Checks Completed
label | a4d1c141-d20b-41d9-ab07-cc9f3b64dbec |  | note | Do not select "Pass" HERE until all above requirements have been marked as "PASS" or you have selected "N/A"
boolean | 1def316e-f51c-422e-a2f6-2e1dec90b1b1 |  | tickbox | Report with all Health & Safety Pre-Commencement checks sent to Main Contractor
label | 28f3c2df-0d9a-4aa1-acf2-bb2688854343 |  | note | Click the three dots in the top right of the Conqa app to send this completed documentation to the respective Main Contractor
holdpoint |  |  | signoff | Request Review
checkpoint-group |  |  | section | Quality Pre-Commencement Checks
checkpoint-status |  |  | checkpoint | Trade Contractor Quality Management Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Trade Contractor Inspection & Test Plan Completed, Agreed & Attached
checkpoint-status |  |  | checkpoint | Trade Contractor Lisences/Tickets attached and current
label | adfd83d4-adb6-4f03-be54-d7c94ce3fb15 |  | note | If required (plumbing, waterproofing, electrical etc), if not select NA
checkpoint-status |  |  | checkpoint | Trade Insurances attached and current
label | 0775ce78-b956-4910-b30d-c1fa4f0f4a6e |  | note | If required, if not select NA
checkpoint-status |  |  | checkpoint | Relevant Breakdown & Checklists Setup on Conqa & Reviewed by Main Contractor
boolean | ed41be9f-6a34-4c45-91c7-04c115b8cb8b |  | tickbox | Conqa EXCEL breakdown & checklists attached
button | 46db26b7-ddea-441c-9db3-7831d8372195 |  | button | Does your breakdown & checklists meet the Main Contractor requirements & have they been reviewed | YES, NO, N/A
checkpoint-status |  |  | checkpoint | Conqa Setup & Trade Contractor Project Team Trained & Given Access
label | 76134d43-2765-49bf-9513-00e5c0bea770 |  | note | Conqa Support Contact Details - support@conqa.nz, 09 886 4647 or use the live chat in app
checkpoint-status |  |  | checkpoint | Review Access Granted to Main Contractor & Any Relevant Third Parties
label | f4d62f93-8628-4e5c-92ac-c5e3b4d453d5 |  | note | Contact the Conqa Support team to assist in providing access to relevant parties
checkpoint-status |  |  | checkpoint | Matrix/Insights Setup (if required)
label | e295ab29-d9b2-4cdd-bd08-7ed873bda5af |  | note | login to account.con.qa & click on "insights" to see a summary of your work - if incomplete please contact the Conqa support team to assist
checkpoint-status |  |  | checkpoint | Any Additional Prestart Quality Documentation uploaded
label | 91e366c2-ece1-4ae8-9a66-a928cb1b35e8 |  | note | "Pass" once uploaded or select "N/A" if there are no additional requirements to those listed above
checkpoint-status |  |  | checkpoint | All Quality Pre-Commencement Checks Completed
label | 5ea7ad90-9249-4f46-805a-61d187e4bdc1 |  | note | Do not select "Pass" HERE until all above requirements have been marked as "PASS" or you have selected "N/A"
boolean | d3b5fb1b-ee1f-4fa5-ba9d-bd6236dd3d6e |  | tickbox | Report with all Quality Pre-Commencement checks sent to Main Contractor
label | 039f05d4-d02a-4e98-9b7e-323307bb2783 |  | note | Click the three dots in the top right of the Conqa app to send this completed documentation to the respective Main Contractor
holdpoint |  |  | signoff | Request Review
checklist-flat |  |  | checklist | QA - Water Main (180mm Watermain/ Fire main) |  |  |  |  | Yes | QA - Water Main (180mm Watermain/ Fire main) - V1 | 778ec991-cd40-40ef-a7ed-b4650c150260
checkpoint-status |  |  | checkpoint | Survey the area and record data
checkpoint-status |  |  | checkpoint | General photos (test welds & pre-construction welds) / comments / observations attached
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | C - S - Pipe Laying - Water |  |  |  |  | Yes | C - S - Pipe Laying - Water | 80b0af7c-8f21-4ced-8c4d-60cd80e59c2a
checkpoint-status |  |  | checkpoint | Set-out completed, checked and accurate
checkpoint-status |  |  | checkpoint | Excavation location and depth accurate
checkpoint-status |  |  | checkpoint | Ground conditions checked and acceptable
checkpoint-status |  |  | checkpoint | Bedding depth and material correct
checkpoint-status |  |  | checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
checkpoint-status |  |  | checkpoint | Pipe laying completed as per the specifications
checkpoint-status |  |  | checkpoint | Backfill completed & compacted as per the specifications
checklist-flat |  |  | checklist | Compliance / Completion Documentation |  |  |  |  | Yes | Compliance / Completion Documentation Checklist (V1) | 9646ea20-cedd-4e2f-b4fa-820bc5e48f9c
checkpoint-status |  |  | checkpoint | All Compliance / Completion Documentation - Completed & Attached
button | 48b5ad2a-1a97-4337-82a9-99e92e634fc4 |  | button | PS3 - Completed and Attached | Yes, N/A
button | add2d002-a17e-42cc-98ed-cb6cc1035a29 |  | button | Any Additional Compliance Documentation - Completed and Attached | Yes, N/A
label | 0e8a6f7d-bff9-469e-bf68-0d859e35fd1d |  | note | Do not select "Pass" HERE until all above requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Job Details |  |  |  |  | Yes | Job Details Checklist (V1) | 995241d4-7257-424d-a7db-be36728984af
checkpoint-status |  |  | checkpoint | Site Information Recorded
label | f6920e92-1693-473f-99cc-ff63c9ab29c2 |  | note | Site Address - Riccarton Park - 25 Steadman Rd, Riccarton
label | 30ac5b4e-a380-4b4f-bbb5-ba8a2d85d20f |  | note | Main Contractor Details - Ryman Healthcare
label | 9ef3b3a8-cde8-4838-9318-7747a4d653c7 |  | note | Project Managers Details - Andrew Inch - andrew.inch@rymanhealthcare.com
label | 56db5f32-b599-414d-baec-4b305447ed82 |  | note | Site Manager Details - Martin Collins - martin.collins@rymanhealthcare.com
label | 5fcec986-d710-4e30-b877-e77242afbc79 |  | note | QA Admin Details - Leshani Gunawardana - Leshani.Gunawardana@rymanhealthcare.com
checkpoint-status |  |  | checkpoint | Scope of Works Attached
checkpoint-status |  |  | checkpoint | Additional Pre Start Docs
checkpoint-status |  |  | checkpoint | All relevant job details entered above
label | b238500e-1211-4e90-add8-30f6fac9d04d |  | note | Do not select "Pass" HERE until all above requirements have been marked as "PASS" or "N/A"
checklist-flat |  |  | checklist | C - S - Pipe Laying - Wastewater |  |  |  |  | Yes | C - S - Pipe Laying - Wastewater | 9df3f9ff-f6d9-4165-b585-1c223705b3cb
checkpoint-status |  |  | checkpoint | Set-out completed, checked and accurate
checkpoint-status |  |  | checkpoint | Excavation location and depth accurate
checkpoint-status |  |  | checkpoint | Ground conditions checked and acceptable
checkpoint-status |  |  | checkpoint | Bedding depth and material correct
checkpoint-status |  |  | checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
checkpoint-status |  |  | checkpoint | Upstream & downstream manhole invert levels and gradient of the pipe line checked and acceptable
checkpoint-status |  |  | checkpoint | Connections to manholes completed and approved
checkpoint-status |  |  | checkpoint | Air/water test completed & acceptable
checkpoint-status |  |  | checkpoint | Pipe laying completed as per the specifications
checkpoint-status |  |  | checkpoint | Backfill completed & compacted as per the specifications
checklist-flat |  |  | checklist | Crane Pad |  |  |  |  | Yes | QA - Crane pad preparation (V1) | a0ede7bd-275d-49e1-ac85-89744aa76054
checkpoint-status |  |  | checkpoint | Survey the area and record data
checkpoint-status |  |  | checkpoint | General photos / comments / observations
checkpoint-status |  |  | checkpoint | Crane pad completed, checked and acceptable
boolean | 94b2ec7b-24db-4d5e-a730-8baea0e93041 |  | tickbox | Report & Signoff request sent to Ryman & T+T
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Bulk Excavation |  |  |  |  | Yes | C - S - Bulk Excavation | a48816a5-03a7-4e85-934b-61ac84a9cbda
checkpoint-status |  |  | checkpoint | Excavation depth determined using appropriate RL's (Check relevant drawings and revisions)
checkpoint-status |  |  | checkpoint | Confirm location and isolation of relevant services
checkpoint-status |  |  | checkpoint | Batters formed correctly
checkpoint-status |  |  | checkpoint | Trenches/ pits / hazardous areas appropriately isolated
checkpoint-status |  |  | checkpoint | Soft spots identified and appropriate remedial completed
checkpoint-status |  |  | checkpoint | Hardfill/ blinding installed correctly to required specification
checkpoint-status |  |  | checkpoint | Static Rolled (2 photos required)
checkpoint-status |  |  | checkpoint | Scala Test and results upload (including supporting documents)
checkpoint-status |  |  | checkpoint | Excavation completed - Correct locations and RL's achieved
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | F - S - Backfilling |  |  |  |  | Yes | F - S - Backfilling | b1dbf854-8c2b-48a0-b0b3-30a796a37e58
checkpoint-status |  |  | checkpoint | Area clean of debris
checkpoint-status |  |  | checkpoint | Backfill completed correctly and heights checked/ correct
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | bf885c55-ad3a-4a6f-a7ea-7a278a586a85
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | c25961df-ebb5-5236-98eb-00d390d53f5f |  | button | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached | Yes,N/A
label | 7af7d4d9-fbe9-55ba-a3e7-a42b67d8c960 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | QA - Water Install - V1 |  |  |  |  | Yes | QA - Water Install - V2 | daf98fa5-4f01-43ba-8f7e-9d51f5a9165e
checkpoint-no-status |  |  | checkpoint | Water Install
button | 13918f11-8988-43ab-97ec-25d788b600ee |  | button | Subgrade is acceptable | Yes, No
button | e71d2dc3-de24-4556-87cd-43e454fef8db |  | button | Approval obtained to commence work | Yes, No
checkpoint-status |  |  | checkpoint | THB01 - Pipe installed and accurate (Photos required) - Correct drawing revision checked and attached
holdpoint |  |  | signoff | Raise Remedial/ Request Sign Off
checkpoint-status |  |  | checkpoint | THB02 - Pipe installed and accurate (Photos required) - Correct drawing revision checked and attached
holdpoint |  |  | signoff | Raise Remedial/ Request Sign Off
checkpoint-status |  |  | checkpoint | THB03 - Pipe installed and accurate (Photos required) - Correct drawing revision checked and attached
holdpoint |  |  | signoff | Raise Remedial/ Request Sign Off
checkpoint-status |  |  | checkpoint | THB04 - Pipe installed and accurate (Photos required) - Correct drawing revision checked and attached
holdpoint |  |  | signoff | Raise Remedial/ Request Sign Off
checkpoint-status |  |  | checkpoint | THB05 - Pipe installed and accurate (Photos required) - Correct drawing revision checked and attached
holdpoint |  |  | signoff | Raise Remedial/ Request Sign Off
checkpoint-status |  |  | checkpoint | THB10 - Pipe installed and accurate (Photos required) - Correct drawing revision checked and attached
holdpoint |  |  | signoff | Raise Remedial/ Request Sign Off
checkpoint-status |  |  | checkpoint | THB 12- Pipe installed and accurate (Photos required) - Correct drawing revision checked and attached
holdpoint |  |  | signoff | Raise Remedial/ Request Sign Off
checkpoint-status |  |  | checkpoint | Pressure check and chlorination check attached
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | Townhouse Pads Checks |  |  |  |  | Yes | QA - Townhouse Pads Checklist (V1) | dd6ddefc-f454-4f80-9493-f99d334a63b2
checkpoint-status |  |  | checkpoint | Survey the area and record data
checkpoint-status |  |  | checkpoint | Accurate backfill and compact - NDM results / photos attached
checkpoint-status |  |  | checkpoint | NDM tests on final AP65 building raft
checkpoint-status |  |  | checkpoint | General photos / comments / observations
checkpoint-status |  |  | checkpoint | Townhouse Pads completed, checked and acceptable
boolean | 45be13d8-df71-4af1-8fb8-137cd61e92d7 |  | tickbox | Report & Signoff request sent to Ryman & T+T
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | QA - ACM Pit backfill- V1 |  |  |  |  | Yes | QA - ACM Pit backfill- V1 | df1ad84d-eb77-427a-b8f6-08ad3dca11ba
checkpoint-status |  |  | checkpoint | Survey the area and record data
checkpoint-status |  |  | checkpoint | General photos / comments / observations
checkpoint-status |  |  | checkpoint | Accurate backfill and compact - NDM results / photos attached
holdpoint |  |  | signoff | Raise Remedial/ Request Signoff