## Project Structure
Folder Structure |  |  | Checklists
Site QA
Job Name: | St Pauls Apartment Café
Job Number: | 3465
| Elevation / Zone | Window # | Suite
|  | D1 | Commercial/Domestic
|  | D2 | Commercial/Domestic
|  | D3 | Commercial/Domestic
|  | D4 | Commercial/Domestic
|  | W1 | Seismic Suite (non curtain wall)
|  | W2 | Seismic Suite (non curtain wall)
|  | W3 | Seismic Suite (non curtain wall)
|  | W4 | Seismic Suite (non curtain wall)
|  | W5 | Seismic Suite (non curtain wall)
|  | W6 | Seismic Suite (non curtain wall)
|  | W7 | Seismic Suite (non curtain wall)
|  | W8 | Seismic Suite (non curtain wall)
|  | W9 | Seismic Suite (non curtain wall)
|  | W10 | Seismic Suite (non curtain wall)
|  | W11 | Seismic Suite (non curtain wall)
|  | W12 | Seismic Suite (non curtain wall)
|  | W13 | Seismic Suite (non curtain wall)
|  | W14 | Seismic Suite (non curtain wall)

## Resources (2)
type | name | values
checklist-flat | Seismic Suite (non curtain wall)
checkpoint | Opening Prepared, Wrapped & Datums
checkpoint | Seismic Installed As Per Shop Drawings
checkpoint | Panel Fitted & Locked Off
checkpoint | Airseal and Internal Flashings (Photo)
checkpoint | External Flashings / Weather Seals / Drainage
checkpoint | Site Glazing Completed
checkpoint | Trade Clean
checkpoint | Wights - Sign Off
checklist-flat | Seismic Suite (Curtain Wall)
checkpoint | Opening Prepared By Main Contractor
checkpoint | Setout/Grids/Datum Lines
checkpoint | Seismic Installed As Per Shop Drawings
checkpoint | DL Brackets Fitted & Welded correct location
checkpoint | Panel Fitted & Locked Off
checkpoint | Splicers & Soakers Sealed (provide photo reference)
checkpoint | Airseal and Internal Flashings (photo)
checkpoint | Smoke Seal Complete (photo)
checkpoint | External Flashings / Weather Seals/Drainage
checkpoint | Trade Clean & Sign Off
checklist-flat | Commercial/Domestic
checkpoint | Opening Wraped & Prepared Correctly
checkpoint | External Flashings / Weather Seals As Per Shop Drawing
checkpoint | Installed / Fixed As Per Shop Drawings
checkpoint | Airseals Completed (photo)
checkpoint | Site Glazing Completed
checkpoint | Trade Clean & Sign off