## Sheet1
Inspection and Test Plan
Project: |  | Bay Road Foul Sewer Renewal CC1810 |  |  |  | R0: 04/08/25 | Role | Person(s) Responsible
Job nr |  | 25069 |  |  |  |  | Project Engineer | Norbert Jacsek
Location: |  | Bay Road, Grasmere, Invercargill (ch 350 - 730) |  |  |  |  | Operations Manager | Bryan Duggan
Action |  | Witness | W | WCL | Wilson Contractors (2003) Ltd | Activity by | Contract Manager | Hamish Lindsay
|  | Hold Point | H | ICC | Invercargill City Council |  | ICC Engineers Representative | Tom Andersen
|  | Monitor | M | Lab / Sur | Independent testing agent / Registered surveyor |  | ICC Engineer | Rob Hayes
Print, sign and date
No | Contract Spec # | Inspection / Test Point | ACTION (W, M, H) | Activity by | Conformance Criteria (What's Required) | Quantity | Frequency / When? | Inspection / Test Method | Records / evidence, WCL form | Standard | Wilson | ICC
Contract
1 | D1.3 | Site Management Plan (QEHS, SSST, KSA) | H | WCL | Ensure Quality, Environment, Health & Safety Management Systems Plan Site Specific Safety Plan and Key Step Analysis are approved. Living document to be adjusted and updated as required. A copy of QEHS plan, SSSP and KSA to be on site at all times. |  | Prior to commencement | Submission (NTE) | Sign This ITP LN-01, FM-83, FM-69 | ICC STANDARD SPECIFICATIONS | YES | YES
2 | D1.18 | TMP | H | WCL | traffic management plan to be submitted and approved by Road Controlling Authority |  | Prior to commencement | Sumission (NTE) | Sign This ITP TMP | Code of practice for temporary traffic management (CoPTTM) | YES | YES
3 | D1.4 | Works Access Permit | H | WCL | TMP and Corridor Access Request to be sumbitted on myWorksites |  | Prior to commencement | Document | Sign This ITP WAP |  | YES | YES
4 |  | Permit to Enter | H | WCL | KiwiRail |  | Prior to any work near the railway area | Document | Permit to Enter |  | YES | YES
5 | D1.14 | Client start-up meeting | H | ICC, WCL |  |  | Prior to commencement | Document | Sign This ITP MoM | ICC STANDARD SPECIFICATIONS | YES | YES
Material
6 | D2.4.2 | Bedding material | W | Lab | Material to comply with contract specification | 650 m3 | Prior to commencement | Lab report | Grading Results | ICC STANDARD SPECIFICATIONS G3 of AS/NZS 2566.2 | YES | YES
7 | D2.4.3 D1.29.3 | Sub Base Aggregate AP65 | W | Lab | Materials to comply with contract specification | 2500 m3 | Prior to commencement | Lab report | MDD and Grading Results | ICC STANDARD SPECIFICATIONS | YES | YES
8 | D1.29.4 | Crushed Basecource Aggregate M/4 AP40 | W | Lab | Materials to comply with contract specification | 250 m3 | Prior to commencement | Lab report | MDD and Grading Results | ICC STANDARD SPECIFICATIONS NZTA M/4 | YES | YES
9 | C1.4 D2.4.1 | Pipe material (F25402 - F25403) | M | WCL, ICC | DN300 uPVC SN16 RESTRAIN | 30 m | 1 / delivery WCL is to inspect all deliveries ICC to inspect deliveries as required | Visual inspection | Sign This ITP | ICC STANDARD SPECIFICATIONS AS/NZS 1260:2017 | YES | YES
10 |  | Pipe material (F25403 - F25406) |  |  | DN300 uPVC SN8 | 328 m |  |  |  |  | YES | YES
11 |  | Pipe material (F25406 - F25410) |  |  | DN225 uPVC SN8 | 378 m |  |  |  |  | YES | YES
12 | D4.3 | Pipe material lateral |  |  | DN100 uPVC SN6 | 780 m |  |  |  |  | YES | YES
13 | D18.2 | Precast manhole elements | M | WCL, ICC | min. 25 Mpa 1050 mm nominal diameter 150 mm lid (HO loading) | 8 MH | 1 / delivery WCL is to inspect all deliveries ICC to inspect deliveries as required | Visual inspection | Sign This ITP | ICC STANDARD SPECIFICATIONS NZS 4058 NZS 3107 | YES | YES
14 | D15.2 | Manhole covers | M | WCL, ICC | Heavy Duty Ductile iron, HN-HO-72 hinged, 600 mm clear opening, gas seal | 8 | 1 / delivery WCL is to inspect all deliveries ICC to inspect deliveries as required | Visual inspection | Sign This ITP | ICC STANDARD SPECIFICATIONS | YES | YES
15 | D15.2 Fig. D9 | Cleaning eye cover | M | WCL, ICC | Warrior Surface box clear opening of 380mm x 224mm | 1 | 1 / delivery WCL is to inspect all deliveries ICC to inspect deliveries as required | Visual inspection | Sign This ITP | ICC STANDARD SPECIFICATIONS | YES | YES
16 | D2.8.3 D12.3.1 | Asphalt (carriageways) | W | WCL, ICC | DG10 | 730 m (main) 700 m (lateral) | 1 / delivery WCL is to inspect all deliveries | Document | Sign This ITP Delivery docket | ICC STANDARD SPECIFICATIONS | YES | YES
17 | D13.3.4 | Asphalt (footpath) | W | WCL, ICC | mix DG7, 180/200 penetration grade bitumen | 58 x 1 m | 1 / delivery WCL is to inspect all deliveries | Document | Sign This ITP Delivery docket | ICC STANDARD SPECIFICATIONS | YES | YES
No | Contract Spec # | Inspection / Test Point | ACTION (W, M, H) | Activity by | Conformance Criteria (What's Required) | Quantity | Frequency / When? | Inspection / Test Method | Records / evidence, WCL form | Standard | Wilson | ICC
Pre Construction
18 | D1.5 | Pre-work site inspection | H | WCL | Video or photos near the construction zone to determine their pre construction condition. (landowners property) |  | Prior to commencement | Inspection Document | Sign This ITP Video Photo | ICC STANDARD SPECIFICATIONS | YES | YES
19 | D1.18 | Temporary traffic management | H | WCL | Signs set up as per TMP, with a copy on site with STMS. TMP monitored for practicality. If changes are required these are to be agreed upon with the engineer. |  | Prior to commencement | Visual inspection Document | Sign This ITP On-site record | ICC STANDARD SPECIFICATIONS CoPTTM | YES | YES
20 | D2.7.1 | Set out | W | ICC, WCL | Mark out of alignment for mains and laterals |  | Prior to commencement | Surface marking | Sign This ITP | ICC STANDARD SPECIFICATIONS | YES | YES
21 | D1.8 | Protection and identification of other Services | H | WCL, asset owners | Mark out on site of all services. Services to be potholed for as per Wilsons company policy |  | Prior to commencement | Surface marking Visual inspection | Sign This ITP | ICC STANDARD SPECIFICATIONS Wilson's prior to excavate policy | YES | YES
22 | D1.11 D9.5 | Notification to residents and businesses | M | WCL | Letter drop / business visits |  | Prior to commencement (min. two working days prior to access restriction) | Document delivered | Sign This ITP Notification letter | ICC STANDARD SPECIFICATIONS | YES | YES
23 | D1.32.7 | Railway survey | M | WCL, SUR | survey monitoring for track settlement: 1 m increments along the track, 20 m either side of the work centreline, / 3 m of progress of the pipe’s installation under the track. |  | Before and after the works | Surveying | Survey record | KiwiRail Civil Specification Installation of Utility Structures on Railway Land (C-SP-AE-64322) | YES | YES
24 | C1.8 D1.6 | NZ Heritage induction | H | WCL, ICC | Contractor briefing is to be completed by all personnel working on the project |  | 48 hours prior to any work | Induction | induction record | ICC STANDARD SPECIFICATIONS | YES | YES
No | Contract Spec # | Inspection / Test Point | ACTION (W, M, H) | Activity by | Conformance Criteria (What's Required) | Quantity | Frequency / When? | Inspection / Test Method | Records / evidence, WCL form | Standard | Wilson | ICC
Foul Sewer renewal
25 | D2.7.2 | Excavation | M | WCL | The finished excavation surface shall be a smooth consistent surface at the appropriate grade. No tolerance on the excavation base level that reduces the depth of the bedding will be allowed. | 706 m - main 780 m- lateral | continuous | Visual inspection Levelling | Sign This ITP | ICC STANDARD SPECIFICATIONS | YES | YES
26 |  | Removal of existing pipelines and manholes | W | WCL | Excavation will include the removal of existing redundant mains, manholes and property connections | 273 m D300 378 m D225 780 m D100 8 manholes | during excavation | Visual inspection | Sign this ITP | ICC STANDARD SPECIFICATIONS | YES | YES
27 | C1.11 | Disposal of Surplus Materials | M | WCL | The Contractor shall dispose of any surplus materials in a safe and sustainable manner | 3500 m3 | Continuous | Document | Sign this ITP Disposal register | ICC STANDARD SPECIFICATIONS | YES | YES
28 | D2.7.2 | Subgrade inspection | M | WCL, ICC | To determine if improvements are required | 706 m | Prior to placement of bedding | Visual inspection | Sign This ITP | ICC STANDARD SPECIFICATIONS | YES | YES
29 | D2.4.2 | Free draining material | M | WCL | pea gravel wrapped in a suitable geotextile up to 100 mm over the trench bed | max 706 m | Continous, in accordance with observed groundwater conditions | Secific approval should be given by the Engineer | NTE, NTC | ICC STANDARD SPECIFICATIONS | YES | YES
30 | D2.7.3 D2.5.1 | Pipe installation open trench (main: F25402 - F25410) | M | WCL | +/- 30mm (horizontal) +/- 5mm (vertical) joints as per manufacturers specifications (lubrication, chamfering, whiteness marking, etc) | 651 m | Continous (pipe laser) 1/20 m (independent optical level) | Using calibrated pipe laser Optical levelling | Sign this ITP Leveling record | ICC STANDARD SPECIFICATIONS manufacturers specifications. | YES | YES
31 | D4.4 Fig. D3 Fig. D4 Fig. D5 | Pipe installation (lateral) | M | WCL | grade: min 1:100 (with laser) min 1:60 (with dumpy level) Connection to the main: 45° reducing wye Concrete haunching: 25 MPa Connection at boundary: slip coupler/plumbqwik | 58 lateral 780 m | Continous | Measurement Document | Sign this ITP Detailed Drainage Connection Sheet | ICC STANDARD SPECIFICATIONS | YES | YES
32 | D2.7.6 | Bedding - DN300 main (F25402 - F25406) | M | WCL | lb (depth below): min 100 mm lc (width beside): min 200 mm lo (depth above): min 150 mm compacted layers not exceeding ⅓ of the pipe OD | 328 m | continuous | Measurement Levelling | Sign this ITP | AS/NZS 2566 table 4.2. | YES | YES | During compaction of bedding / pipe laying and prior to placement of subbase material
33 | D2.7.6 | Bedding - DN225 main (F25406 - F25410) | M | WCL | lb (depth below): min 100 mm lc (width beside): min 150 mm lo (depth above): min 150 mm compacted layers not exceeding ⅓ of the pipe OD | 378 m | continuous | Measurement Levelling | Sign this ITP | AS/NZS 2566 table 4.2. | YES | YES | During compaction of bedding / pipe laying and prior to placement of subbase material
34 | D2.7.6 | Bedding (lateral) | M | WCL | lb (depth below): min 75 mm lc (width beside): min 100 mm lo (depth above): min 100 mm compacted layers not exceeding ⅓ of the pipe OD | 780 | continuous | Measurement Levelling | Sign this ITP | AS/NZS 2566 table 4.2. | YES | YES
35 | D18 Fig. D12 | Manhole (D1050) | M | WCL | neck depth ≤ 315 mm in-situ concrete packing flexible joint located within 1 metre | 8 | 1 / manhole | Measurement Levelling Document | Sign this ITP Manhole Inspection Sheet | NZS 3109:1997 | YES | YES
36 | D18 Fig. D7 | Cleaning eye | M | WCL | as per Fig D7 | 1 | 1 / installation | Visual inspection Measurement | Sign this ITP | ICC STANDARD SPECIFICATIONS | YES | YES
37 | Fig. D13 - D16 | Service cover (manhole) | W | WCL, ICC | Cover levels to be adjusted to existing surface levels (+10mm, -0 mm) 25 Mpa concrete packing | 8 | before surface reinstatement | Visual inspection Measurement | Sign this ITP | ICC STANDARD SPECIFICATIONS | YES | YES
38 | D15 Fig. D7 | Service cover (cleaning eye) | W | WCL, ICC | Cover levels to be adjusted to existing surface levels (+10mm, -0 mm) perpendicular / parallel the road alignment. | 1 | before surface reinstatement | Visual inspection Measurement | Sign this ITP | ICC STANDARD SPECIFICATIONS | YES | YES
39 | D2.9.2 | Pressure test | H | WCL, ICC | (Main + N side laterals) + (S side laterals) Test length: as per table 6.1 AS/NZS 2566.2 pressure: 25kPa pressure loss < 7Kpa | 8 section 35 S side lat | 1 / section (manhole to manhole) 1 / S side lateral) | Low pressure air test | Sign This ITP Pressure test report FM-119 | AS/NZS 2566:2:2002 6.4.2 | YES | YES
40 | D2.9.3 | CCTV Inspection and Cleaning | H | WCL | to confirm that the lines are free from debris and have no defects | 736 m (main) | prior to the final surface reinstatement | CCTV inspection | Sign this ITP CCTV survey | New Zealand Pipe Inspection Manual AS/NZS 2566:2 | YES | YES
No | Contract Spec # | Inspection / Test Point | ACTION (W, M, H) | Activity by | Conformance Criteria (What's Required) | Quantity | Frequency / When? | Inspection / Test Method | Records / evidence, WCL form | Standard | Wilson | ICC
Surface reinstatement
41 | D13 | Landscaping | W | WCL | The final surface in the berm area should match the existing levels | 58 laterals | following lateral installation | Visual inspection Levelling | Sign this ITP | ICC STANDARD SPECIFICATIONS | YES | YES
42 | D13.7 | Grass seeding | W | WCL | approved seed mixture, 35 g/m2 | 58 laterals | following landscaping | Visual inspection | Sign this ITP Blending docket | ICC STANDARD SPECIFICATIONS | YES | YES
43 | D2.7.7 | Subbase (AP65) compaction | H | WCL | Carriageway: 0.3 - 1.5 m deep: min 35 CIV > 1.5 m deep : min 25 CIV | 706 m (main) 700 m (lateral) | During installation, every 200 mm layers at 6 m intervals for all trenches in carriageway above main and connections | Clegg test | Sign This ITP Clegg Test Result Sheet | ICC STANDARD SPECIFICATIONS | YES | YES
44 | D2.11.5 | Subbase (AP65) compaction | H | WCL / Lab ICC | 95% compaction rate It is not required to complete NDM testing on connections | 706 m (main) | At pipe laying commencement and reconfirmed at 120 m intervals for open trench every 200 mm layers | NDM test (direct transmission) | Sign This ITP NDM Test Result Sheet | ICC STANDARD SPECIFICATIONS | YES | YES
45 | D2.7 | Basecourse (AP40) compaction | H | WCL / Lab ICC | minimum depth of 150 mm 98% compaction rate It is not required to complete NDM testing on connections | 706 m (main) | 1 / 20 m of trench including one test at the start and end of the trench | NDM test | Sign This ITP NDM Test Result Sheet | ICC STANDARD SPECIFICATIONS | YES | YES
46 | D2.8.3 | Trench reinstatement - marking out saw cutting | H | ICC | Engineers rep to mark out saw cutting required 150 mm overcuts 1 m rule | 706 m (main) 700 m (lateral) 58x1 m (footp) | Prior to sealing | Visual inspection, measurements (1 m rule) | Sign This ITP Pre seal inspection record (FM-114) | ICC STANDARD SPECIFICATIONS National Code of Practise for Utility Operators' Access to Transport Corridors | YES | YES
47 | D2.7.7.2 | Basecourse (AP40) geometry | H | WCL, ICC | -5 mm +15 mm h = 45-65 mm (carriageways) h = 25-45 mm (footpath) | 730 m (main) 700 m (lateral) 58x1 m (footp) | Prior to sealing | Visual inspection String line / straight edge inspection | Sign This ITP Pre seal inspection record (FM-114) | ICC STANDARD SPECIFICATIONS NZTA B/2 | YES | YES
48 | D11.4.3 | Membrane Seal | H | WCL, ICC | Residual bitumen application rate: 2.0 l/m2 +/- 10%. (spray truck) ≥ 1.5 l/m2 (hand operated sprayer bar) | 706 m (main) 700 m (lateral) | Prior to asphalting | Visual inspection | Sign This ITP, Delivery docket | ICC STANDARD SPECIFICATIONS | YES | YES
49 | D12.5 | Asphalt paving (carriageway) | H | WCL, ICC | trenches wider than 1.5 m shall be paver-laid 5 mm from a 3 m straight edge laid longitudinally 5 mm from a 1 m straight edge laid transversely lips ≤ 5 mm (where it joins existing seal) | 730 m (main) 700 m (lateral) | 1 / finished surface | Post seal surface inspection | Sign This ITP | ICC STANDARD SPECIFICATIONS | YES | YES
50 | D13.6 | Asphalt paving (footpath) | H | WCL, ICC | 30 mm Footpaths and Surfaced Frontages 30 mm Residential Crossing 50 mm Heavy Duty Crossing 5mm above kerb edges, and flush with property vehicle accessways The gap under a 3m straight-edge placed longitudinally shall not exceed 5mm lips ≤ 3mm | 58x1 m | 1 / finished surface | Visual inspection straight edge inspection | Sign This ITP, Delivery docket | ICC STANDARD SPECIFICATIONS | YES | YES
51 |  | Road markings | W | WCL, ICC | Reinstatement of the existing markings |  | 1 / finished surface | Post seal surface inspection | Sign This ITP | ICC STANDARD SPECIFICATIONS | YES | YES
Completion
52 | D17 | As-built information | H | WCL | Encountered Services Record Sheet Detailed Water Connection Sheet As-built drawings as per D17 |  | Following/during completion of works | Document | Sign This ITP DWCS, ESRS, As-built | ICC STANDARD SPECIFICATIONS KiwiRail specifications | YES | YES
53 |  | Works Completion Notice | H | WCL | KiwiRail + myWorksites | [5 empty] | YES | YES
54 |  | Site walkover | H | WCL, ICC | Snag list to be compiled, and completed |  | At Completion | Review | Sign This ITP SNAG List | ICC STANDARD SPECIFICATIONS | YES | YES
Wilsons Engineer |  |  |  |  | Wilsons Contract Manager |  |  | ICC Engineers Representative
Signed By : Norbert Jacsek |  |  |  |  | Accepted By : Hamish Lindsay |  |  | Accepted By : Tom Andersen
Signature: |  |  |  |  | Signature: |  |  | Signature: