## Master List Templates
Id | Type | Name | Values | Prompting Name
8a4bfb74-04d2-47d1-9d9c-4e0e45c8e71f | checklist | Documents |  | Documents
d27e664b-b8db-4dae-8ce3-cc3995597fdf | section | Details
9483f8e0-de31-4f34-b59b-8778c5e33994 | checkpoint | Document attached
71311430-12af-4de5-b2e1-320343a3d7c5 | checklist | Test ITP | itp | Test ITP
20380797-825e-43d5-b636-1e28953acadd | section | Preliminary Works
107e3d9c-f945-48ad-a893-382139576ad3 | checkpoint | 3.1 Pre-construction Photos
955645e1-125c-52ac-a36d-9f7aaf64fd68 | note | Inspection Point: Quality Control Activity - Photos of worksite including vehicle access points.
de815be8-ff5b-5bbf-8fcf-b6a74f875d15 | note | ○ Photos of any existing defects/damage.
f629ba35-c6c9-5e84-afb6-f12afe19ba50 | note | Acceptance Criteria - Coverage of whole site
b343e756-6236-534e-a04c-adde741f9cf9 | note | Verifying Document - Photos saved
487d2c77-26c6-574d-9f8c-69197b900e60 | note | Reference: Contract Specs/Standards - D1.4
aa7dcc23-975c-5d3e-90f1-e46ecef13a8e | note | Inspection Point/Signature & Date - PM
441f8f47-9e59-4e93-af48-52ea9db74b4f | checkpoint | 3.2 Verify Construction Drawings
5979cb19-48d2-5a0f-8a4a-18a2495e019b | note | Inspection Point: Quality Control Activity - Verify Construction Drawings that are in the site folder are the latest revision.
77adfc3c-637c-5532-a2de-de99b4eb0801 | note | Acceptance Criteria - Latest drawings approved
2e7272cf-1b67-5992-8aea-1c720473b1e1 | note | Verifying Document - Drawings Register
91384230-7de8-55b8-b9f0-cf3094b4e632 | note | Reference: Contract Specs/Standards -
53f92b21-b0f6-50b0-9a66-65c339b74caa | note | Inspection Point/Signature & Date - PM
92a4d361-6a90-4261-aacc-b17a70c5ba02 | checkpoint | 3.3 Road Authority Notifications
a5905a4b-3c67-5ea9-9f5c-3f49ad93a559 | note | Inspection Point: Quality Control Activity - Corridor access Permit.
0158a33e-7ce3-58a8-babd-2c00a85ada9b | note | ○ Block by block Temporary Traffic Management Plans.
c980e384-1324-5a31-ad80-c5f42c7f2909 | note | Acceptance Criteria - Permit & Traffic Plan approved
670802ca-5daf-518d-ba40-b11f61b8bba8 | note | Verifying Document - Work Access Permit & TMP
ae04fd1d-8285-5e71-9dc0-6c451b22a24a | note | Reference: Contract Specs/Standards - C1.09, D1.4
afbe1801-0461-5ff9-9968-d71d709c4667 | note | Inspection Point/Signature & Date - PM
d39f31d1-9f41-49b3-8e2e-f1d32ae48a60 | checkpoint | 3.4 Management Plan
dacc70c9-2410-5db2-bd45-66d975547e52 | note | Inspection Point: Quality Control Activity - H&S Plan
c98cf114-7fba-5cd7-9f75-05f14d1dc0c4 | note | ○ Environmental Plan
ff8ca60d-7b07-570e-837e-2ea6f5924d22 | note | ○ Quality Assurances
6ad36c2d-187f-596a-87f1-b024ccfeeffd | note | Acceptance Criteria - Plans & Safety Measures in place
d5f70aa4-3aed-5da0-b07e-f5410907778d | note | Verifying Document - H&S Plan, Method Statement
79d6f9d4-a271-5202-907c-58e7835bcb83 | note | Reference: Contract Specs/Standards - D1.3
7f636cf1-81e6-5b8d-8b3a-e415c151f5d7 | note | Inspection Point/Signature & Date - PM, CR
5d595464-2779-423b-add8-0d8127f9cada | checkpoint | 3.5 Public Notification
3a84e0b1-0335-5dc4-bb53-a8236469f1e8 | note | Inspection Point: Quality Control Activity - Notice of works to properties in the construction zone in each block
111ac031-f06c-52e2-8d36-657040eef63d | note | ○ Notification to Rubbish collection contractor.
6425c7b3-a4a7-5fc9-b4d2-348fb03ae6aa | note | ○ Project Signage
1fb132d3-92db-5038-aa91-124209dd7f89 | note | Acceptance Criteria - 48 hours prior notification
6a28c857-a4f5-59ec-8a55-c083caf0c3a7 | note | Verifying Document - Letter to residents
c926fb82-add6-5d96-9893-e1996f955a14 | note | Reference: Contract Specs/Standards - D1.10
bdbcb526-3a1e-5e5d-86ef-0a808ab8369e | note | Inspection Point/Signature & Date - PM
83d17dff-2396-439e-955c-8f1f727f65ed | checkpoint | 3.6 Shutdown/Isolation
6ea865c2-ca78-5854-8fa3-2264bf699993 | note | Inspection Point: Quality Control Activity - Shutdown/Isolation process verified in each block closure
1555c1d5-29de-5a42-a7d4-8b3739287984 | note | Acceptance Criteria - Shutdown process verified
cd7f89f3-8fdf-5085-8c83-7bb9094c8b0a | note | Verifying Document - Notification letters
ef26b893-83e8-5557-854d-c80eb7263938 | note | Reference: Contract Specs/Standards - C1.16, D2.7.8
28d7be85-39af-58e3-9302-9376a974da67 | note | Inspection Point/Signature & Date - PS
d167c212-b415-420c-a15c-45c677294de6 | checkpoint | 3.7 Construction Set Out
742868c8-23f0-5452-9b92-ba186649d8d7 | note | Inspection Point: Quality Control Activity - Correctly mark out the position of the new pipelines for construction.
9e97b2cc-ba1a-5815-b8f9-fbfc1eb1d305 | note | Acceptance Criteria - Construction Plans checked
5b2e22e1-e5ff-5dc0-99bf-61f23b16df05 | note | Verifying Document - Construction Plans
62386f7d-45bf-5fb2-8ee5-5645b5fb6848 | note | Reference: Contract Specs/Standards - D2.7.1
d58502cb-242d-55dc-b860-3551207f6eba | note | Inspection Point/Signature & Date - PS, CR
a5600e25-383f-46d4-8512-0c264c1e449f | checkpoint | 3.8 Pre-Excavation Permits
dae1eccc-c23e-53c5-a82d-0efd94bccfeb | note | Inspection Point: Quality Control Activity - Permit to excavate for the location has been endorsed by an authorised person.
4086823b-a3b0-5514-bed4-f7f9e3b60915 | note | ○ Existing service plans & locates
c1e5fd2a-aef6-51bf-8cd0-bb993a96c4c9 | note | ○ Close approach permits
e9ebe2eb-6bb3-5920-af4f-3e5f51dc6ced | note | ○ Notifiable works
c0184131-3963-58e5-89ee-4c85ee5a746b | note | Acceptance Criteria - Permit to excavate endorsed
ef5bff12-f195-5b6f-aa81-cb8850c90580 | note | Verifying Document - Ground Disturbance Permit
64acb508-1d91-553b-8bd2-2bec3032ca97 | note | Reference: Contract Specs/Standards - D1.7
7835cccc-5334-5c60-a2d5-886aa9e0b519 | note | Inspection Point/Signature & Date - PS
02c8290d-79fe-4b01-a4f8-43e9d4c6e881 | signoff | HOLD POINT
abbb431d-e004-44ec-b738-fab1868140b8 | section | Incoming Goods Inspections
2aa07f2e-4aed-4158-88a0-e6abf1872ee1 | checkpoint | 4.1 Pipe & Fitting Inspections
335e2b85-3765-5d7c-823f-1a30f4f4c2cd | note | Inspection Point: Quality Control Activity - Visual check of materials delivered:
3c2f6b16-25d4-518b-a78c-50cd0381e2b9 | note | ○ Correct Material & dimensions
38ce9bbf-d35b-56d0-9094-6888dbbe0772 | note | ○ Condition & Quantity
e0aca729-1137-5fa6-a9c4-e65d8d4be14e | note | ○ Free of defects – surface abrasion, ovality, not kinked or crushed
c7813b84-576f-505d-b003-53fb30070daf | note | ○ Batch/serial numbers present
e60eb730-8b8d-5bbe-9001-2c575dd38607 | note | Acceptance Criteria - Correct material & no defects
775a2f60-1a0d-5a61-a840-33859f5f5380 | note | Verifying Document - Packing Slips
5523d66d-7eb8-57b7-8130-17f63b83eb86 | note | Reference: Contract Specs/Standards - D2.4,D3.3, D4.3, D5.3, D8.3
4815886f-d85b-584d-a8bf-54bb43596b4d | note | Inspection Point/Signature & Date - PS
18a89c7a-07fc-4278-9ab2-46bbdeed02f3 | checkpoint | 4.2 Pipe & Fitting Storage
736fc6ca-0587-58a7-aa66-1e6006900b05 | note | Inspection Point: Quality Control Activity - Stored as per manufacturers specifications including maximum height limits and safely chocked in place.
88679b02-09b0-5f6d-85d2-86abe8c910f1 | note | ○ All pipes are end capped.
ace5e548-9b68-55f8-acb6-13682245a6d3 | note | ○ No scoring of pipe more than 10% of thickness.
0f1df64d-4495-5578-a941-f201cb9bd702 | note | ○ No damage to epoxy coating on Ductile fittings.
1dbf0fff-4157-5283-af1b-f1fa245cb0fd | note | Acceptance Criteria - Stored as per manufacturer
c2c2afc7-5301-5e5c-ba67-ba552d116bc1 | note | Verifying Document - Manufacturer’s Storage Instructions
99bbba7a-beec-5223-939d-15034191d36d | note | Reference: Contract Specs/Standards -
1dbd7e86-bf3c-5e32-8b08-073e38069992 | note | Inspection Point/Signature & Date - PS, CR
6b2618a5-8d30-4b91-a333-0dfd3ca9cf5f | signoff | HOLD POINT
1f6a3545-531a-431b-8950-db0056c6a96e | section | Construction Inspections
5b9fc0f7-1004-4407-be8c-24b464b7f09e | checkpoint | 5.1 Trench Excavation
02e391fc-3a18-522d-9c19-e2a03e270cfb | note | Inspection Point: Quality Control Activity - Trench width to be sufficient to safely lay the pipe (including shoring if required) and compact the side support of the new pipe. Bedding details below;
a6f490ee-48df-5ce7-ad7c-e1ea3aa3e379 | note | ○ Sufficient room to enable the pipe, joint, bed, haunch or surround shown in the drawings to be accommodated.
eec54b15-5ecd-5436-96af-7f3f1ec2feb7 | note | ○ Trench depth to enable pipe to be laid with the designed cover as shown on construction plans.
8fd021a9-e8d2-5b4c-8b4b-5843892fc6d1 | note | ○ If trench bottom to be suitable to compact pipe bedding as support pipe.
fc3f41ae-94b6-572c-ac89-2a9ef6fb22bf | note | Acceptance Criteria - Trench dimensions correct
e3b19d68-be79-52b1-b552-b4069f08f057 | note | Verifying Document - Daily Site Diary
84a404dc-63b4-5583-b4db-f3add2e91694 | note | Reference: Contract Specs/Standards - D2.6, D2.7
5aa888e2-14d6-582f-9a52-d9c849c2397e | note | Inspection Point/Signature & Date - PS
27edf7a6-5c6f-40e4-b0c0-9ab61a806878 | checkpoint | 5.2 Encountered Services
da1255de-facf-5b78-9de0-40b88d5693d6 | note | Inspection Point: Quality Control Activity - Block by block ensure existing live services are not unnecessarily damaged by works.
5fc0b366-4852-5bfe-a581-cba57122ba03 | note | ○ Repair any services that are temporarily removed during construction.
c6c5167f-c5f2-5998-b8d3-01f5f3e9341c | note | ○ Record any services found.
0631e0d3-22a9-5d7c-8b37-c6cbd46c7c91 | note | Acceptance Criteria - Existing services not damaged
81f412b2-a38d-50f2-a598-84775c34f384 | note | Verifying Document - Encountered Services Record
90c9acea-6aa9-5d0a-b22b-e74a722eebd8 | note | Reference: Contract Specs/Standards - D1.7, D2.7.7
7d0df532-6775-5e02-87ef-5933b5113c19 | note | Inspection Point/Signature & Date - PS
0bb6eb81-7e4a-451f-830e-1b4ed2ca3ea2 | checkpoint | 5.3 Pipe Installation
e9a5264d-e34d-57c2-b251-70577ea28002 | note | Inspection Point: Quality Control Activity - Interior of each pipe visually inspected to ensure free of debris.
4de7eba6-7a52-508a-8f6f-3da7ba17c6ad | note | ○ Re-cap end of pipe after installation.
9fcd0740-534d-500d-8189-e0970be0fe0f | note | ○ Check pipe installed at correct depth.
97372ff6-7a61-5b54-b317-dc368cef403b | note | ○ Ensure all collars are free from contamination in McDougall St berm
d141a6e9-ce08-571e-8cfd-8a4080f2f31b | note | Acceptance Criteria - Pipes free of debris & correctly installed
6c48859f-43ee-519f-b185-e2757b35f5ef | note | Verifying Document - Daily Site Diary
d6e34e20-3287-5bb8-accf-914843f1e5ed | note | Reference: Contract Specs/Standards - D2.5, D2.7, D8.4.2
c344ad27-9a7c-5088-8578-ce9de1f06115 | note | Inspection Point/Signature & Date - PS
315ca360-db4e-4b0f-b047-bcd13a88803d | checkpoint | 5.4 Concrete Pre-Pour Inspection
a0c3ca9d-7c53-5f00-a910-1efc9d53070f | note | Inspection Point: Quality Control Activity - Check dimensions of formwork match details in the Construction Drawings.
63a3685f-631f-50f2-b45b-5b550dd42985 | note | ○ Check pipe fitting joints are clear of concrete pour.
23788df5-5f26-5f32-a93c-2b6f87bf050f | note | ○ Thrust blocks to be poured against good solid natural ground.
2e389bbc-ca69-56cc-991e-0c7ae5298cfb | note | Acceptance Criteria - Thrust blocks against solid ground
4630ea02-6452-5ef8-9df0-b7baf484a9ae | note | Verifying Document - Daily Site Diary & Photos
2a52135d-b44a-5d64-8c2f-594fcb8d9444 | note | Reference: Contract Specs/Standards - D5.1, D5.3.2, D5.7
270f8374-94d2-5ff4-afe3-a9f4d98bb457 | note | Inspection Point/Signature & Date - PS, CR
02e5fe15-a3d0-4117-9c59-df286de87b71 | checkpoint | 5.5 Hydrant Depth
c166f8ac-68a4-56d5-a714-45a77c232876 | note | Inspection Point: Quality Control Activity - Confirm depth requirements have been met;
2f2ace55-1dbf-557c-880b-7b6a3dd25264 | note | ○ Hydrant outlet: 200mm min. to 400mm max.
285e10aa-95d7-51d9-ab64-3b2072cdb2d5 | note | Acceptance Criteria - Hydrant depth verified
9803aeb2-9d90-54ba-9e49-df36b5629658 | note | Verifying Document - Daily Site Diary
f8c94654-15c9-51e9-8452-342e59ecae6e | note | Reference: Contract Specs/Standards - D5.5
cc256614-c42e-5f6e-a39f-f68a89b87155 | note | Inspection Point/Signature & Date - PS
a0e3fce6-d131-4d47-b2fa-1afd64dedf22 | checkpoint | 5.6 Compaction Testing
ba0f25db-c515-54bf-af10-241ef05a2184 | note | Inspection Point: Quality Control Activity - Confirm trenches in paved areas are compacted to standard block by block.
49e7f8fd-7c6b-5d23-b61b-854926d2d227 | note | Acceptance Criteria - Compaction confirmed
22f4308c-0c3d-5079-b554-738af731d09f | note | Verifying Document - Clegg Record Sheet
ea3ff20d-d289-5332-88c3-7d7ac37a937a | note | Reference: Contract Specs/Standards - D2.7.10
bb591b35-fe0b-530a-8cb7-36e77516390e | note | Inspection Point/Signature & Date - PS
cdecfdb6-ad87-453e-b692-8fb65eb5cbe7 | checkpoint | 5.7 Watermain Pressure Testing
1da5f833-284a-5b18-99a9-331354fad608 | note | Inspection Point: Quality Control Activity - Hydrostatic pressure test on new pipeline and fittings block by block.
2f9a2668-68c2-5f33-8c5e-ec33a157d16e | note | Acceptance Criteria - Pressure test passed
36849462-809a-58b1-a71f-40568e648c95 | note | Verifying Document - Pressure Test Record Sheet
a57df2e3-9168-58b3-8e23-04a24658c806 | note | Reference: Contract Specs/Standards - D2.9.1, AS/NSZ 2566.2:2002 Section 6
2d130f10-37f0-55a1-8d72-a460b1f28c32 | note | Inspection Point/Signature & Date - PS, CR
a1e1175c-838a-44d4-97e2-105d86a88295 | checkpoint | 5.8 Watermain Sterilization
ce10429c-a3e0-5c3c-b478-43bc65ee371b | note | Inspection Point: Quality Control Activity - Flushing and sterilizing full length of new pipeline and fittings block by block.
14828d25-390c-5376-8cc6-48d3ee750694 | note | Acceptance Criteria - Sterilization completed
72845af4-3a77-57b0-bfd3-8c8b00ad194a | note | Verifying Document - Sterilization Record Sheet
c67f69b9-5827-576d-aa4b-e05ef53cf735 | note | Reference: Contract Specs/Standards - D2.9.1, AS/NSZ 2566.2:2002 Section 6
99631707-3d31-5b31-aff4-efb8e8c21979 | note | Inspection Point/Signature & Date - PS, CR
ddf7462a-b76e-41eb-a36d-0de8b8dd2a87 | checkpoint | 5.9 As-built Information
517e67db-4033-58c1-a6ca-d3362f98ca30 | note | Inspection Point: Quality Control Activity - Capture data for all new construction work.
ba450391-5c8a-5c55-b1c4-c22f0833b96c | note | Acceptance Criteria - Redline mark-up plan submitted
3eb797e2-7275-5590-8fac-676aa04c793f | note | Verifying Document - Redline Mark-up Plan
b2cc15a1-1e88-5f06-9c50-d2d2827d97a5 | note | Reference: Contract Specs/Standards - C1.22
3c06f156-3b4e-51b2-91ab-48d5a7624304 | note | Inspection Point/Signature & Date - PM
6fda002d-0146-4403-8542-79c60a61f794 | signoff | HOLD POINT
8b2fb51e-3dea-4864-85cf-ea6c1f2099ae | section | Final Inspection and Handover
e1185f06-97ee-41c3-ba68-9fa87ec8f197 | checkpoint | 6.1 Final Inspection of Works
937e6486-743d-5157-8e7e-d97207a69798 | note | Inspection Point: Quality Control Activity - Work is inspected by the authorised person and complies with the nominated specification/standards
17149ea4-e39d-5a08-9b34-a5a55b8544b8 | note | Acceptance Criteria - Work inspected & complies with standards
69020570-efe6-5843-a2ad-9a102698555a | note | Verifying Document - Practical Completion Certificate
b28f2ad8-0f63-5340-9f55-310a0e29c35a | note | Reference: Contract Specs/Standards -
5422ff6f-c5f8-5de4-8a22-f168bf4f557c | note | Inspection Point/Signature & Date - PM
aca660fb-dc8b-43a6-b666-e84980ea511b | signoff | HOLD POINT

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
7a3f3c1f-0276-48af-a823-86ba993c4e97 | checklist | ITP - Korimako SW | itp | ITP - Korimako SW
735e2b54-0cbf-4797-a265-ff9cba903335 | section | Contract
b6a712ab-9548-480c-9f30-3893ac4380e7 | checkpoint | 1 - D1.3
7c5acbc3-4ce4-5e94-80fd-930c8e9d47cf | note | Inspection / Test Point - Site Management Plan (QEHS, SSST, KSA)
659ef7a0-a350-5d43-93d8-510b8b559618 | note | ACTION (W, M, H) - H
681c6e69-be79-5ea7-9f11-21a3edd85a2b | note | Activity by - WCL
57e561c9-4e86-5fba-b619-493d4232f560 | note | Conformance Criteria (What's Required) - Ensure Quality, Environment, Health & Safety Management Systems Plan Site Specific Safety Plan and Key Step Analysis are approved.
d5ebf7bf-2a39-53e6-b4dc-78a6e2aa462b | note | ○ Living document to be adjusted and updated as required. A copy of QEHS plan, SSSP and KSA to be on site at all times.
1315cbaf-d636-54c7-bde1-de84dbe1b3dc | note | Frequency / When? - Prior to commencement
dead3dae-1e26-50af-a06d-ae395f1b319e | note | Inspection / Test Method - Submission (NTE)
678e584d-97f3-5866-86e6-94f23cc08c1a | note | Records / evidence, WCL form - Sign This ITP, LN-01, FM-83, FM-69
12ce31c4-c103-54ef-a8d9-323098c05ef6 | note | Standard - ICC STANDARD SPECIFICATIONS
6e7c872f-ca89-54d1-807d-2ace7cb1a927 | note | Print, sign and date: Wilson - YES
3c017a0a-4393-5023-9034-6f590e00f801 | note | Print, sign and date: ICC - YES
a77506d5-afc3-4108-9757-099ca23f76d0 | signoff | HOLD POINT
15d27ff0-200b-451e-97b8-b3450e99babf | checkpoint | 2 - D1.18
f9b97371-4576-5a1d-9ddd-18f4d01d9bbf | note | Inspection / Test Point - TMP
f23d1404-5f98-5e67-a8bc-efd14575b597 | note | ACTION (W, M, H) - H
670300fd-e575-5314-b012-77b1307d8d24 | note | Activity by - WCL
e5b566b9-e434-5400-accf-a8b766e3ccd2 | note | Conformance Criteria (What's Required) - traffic management plan to be submitted and approved by Road Controlling Authority
cdb947c8-12c9-5b90-8780-35ac3672d636 | note | Frequency / When? - Prior to commencement
c476d30d-5fc7-59a2-8206-c78625fba342 | note | Inspection / Test Method - Sumission (NTE)
bf764329-64bb-5d13-b7b5-9fa1fb78613a | note | Records / evidence, WCL form - Sign This ITP, TMP
6ff3847b-b6c0-5d35-84e8-19005c42cb82 | note | Standard - Code of practice for temporary traffic management (CoPTTM)
36516d47-7d36-5602-b2c1-afae266272ae | note | Print, sign and date: Wilson - YES
d1f739f2-77e4-587a-9e56-9325728e67f9 | note | Print, sign and date: ICC - YES
52590838-fb03-4549-8174-919f4ee05f67 | signoff | HOLD POINT
1d35ec61-299a-451a-ab43-325f63c35192 | checkpoint | 3 - D1.4
0a0ec68e-2dd8-531e-a0b6-c61902886e83 | note | Inspection / Test Point - Works Access Permit
44cf580b-3da2-55c4-aa2f-d7564e6a0274 | note | ACTION (W, M, H) - H
c8569884-69b9-5156-8a0e-6d6ab1ca3b60 | note | Activity by - WCL
4b80c992-157b-5be1-98e2-6bf44ec51f81 | note | Conformance Criteria (What's Required) - TMP and Corridor Access Request to be sumbitted on myWorksites
239e9811-711f-503e-bdd7-34052d1d81db | note | Frequency / When? - Prior to commencement
940d41e7-2e5f-5454-8aa8-98ce154be877 | note | Inspection / Test Method - Document
7fd1a68f-70b1-56ec-8fe9-5a6bc4200c4e | note | Records / evidence, WCL form - Sign This ITP, WAP
e0ac1f7f-1fc2-52a1-afc8-1f9629af9b9a | note | Print, sign and date: Wilson - YES
99521bc0-b0f2-5367-a2c7-3b672565a0ac | note | Print, sign and date: ICC - YES
95b52079-74ce-47ad-8b88-818ef9db97b0 | signoff | HOLD POINT
9647913f-c5b2-4b67-b098-99412b2e84cb | checkpoint | 4 - D1.14
94965139-2461-57a2-976b-548db726952e | note | Inspection / Test Point - Client start-up meeting
4587127e-6eb8-5ffd-806b-4c7c9b6f9344 | note | ACTION (W, M, H) - H
960480c1-ab35-566d-b41b-4789e967569f | note | Activity by - ICC, WCL
5f810ad3-c5dc-5d0c-a88a-5bbad08f98b8 | note | Frequency / When? - Prior to commencement
5ca42778-76e0-5a48-b9db-4c379c1d3747 | note | Inspection / Test Method - Document
f2e5527f-27f1-5e44-98c5-a56496afde1d | note | Records / evidence, WCL form - Sign This ITP, MoM
5f526e83-9576-500e-ab6f-5dc1d09bd6b6 | note | Standard - ICC STANDARD SPECIFICATIONS
64ddeb6e-297f-5915-a340-f4c938e2a8dd | note | Print, sign and date: Wilson - YES
fa32e63c-77df-5899-8ff1-a52819a97718 | note | Print, sign and date: ICC - YES
775d13a7-94c4-4464-b854-f1e73b41e103 | signoff | HOLD POINT
55e65dc0-b4be-41b9-a3b1-d3f42a4bcf18 | section | Production
c568d2f9-78db-425d-b701-58de82633835 | checkpoint | 5 - D2.4.2
d2026a05-d885-5771-95e4-1f0469aea68f | note | Inspection / Test Point - Bedding material
3c97ca92-4f92-5d14-9da0-d4eacb4bc058 | note | ACTION (W, M, H) - W
f86c9e6b-b2b2-50d9-b85f-06711f9fce68 | note | Activity by - Lab
50b2350b-5725-56f8-bd0c-02c49a15ef1f | note | Conformance Criteria (What's Required) - Material to comply with contract specification
380f8f67-0ec2-5372-b4ce-e35fc3f574e1 | note | Quantity - 280 m3
6b96a0c9-c781-5bce-98f4-6593963c797e | note | Frequency / When? - Prior to commencement
35f6aaa4-e651-5330-9f5a-f0c868a186ff | note | Inspection / Test Method - Lab report
ce691fca-1890-51fa-833b-740b4f9e8cc9 | note | Records / evidence, WCL form - Grading Results
8b411003-cad0-5a82-b8dc-97a5c3c95913 | note | Standard - ICC STANDARD SPECIFICATIONS G3 of AS/NZS 2566.2
05670777-a3ae-50e2-862e-f5626d256c44 | note | Print, sign and date: Wilson - YES
4c22c739-4063-5d87-a903-3cba059f3e46 | note | Print, sign and date: ICC - YES
8692ea2b-3e16-49e7-9265-05121123f164 | checkpoint | 6 - D1.29.3
6a9f319f-d515-55e9-a8a2-2400e1a22f72 | note | Inspection / Test Point - Sub Base Aggregate AP65
f277c94e-c5b5-5c00-bbea-c9c543808cb2 | note | ACTION (W, M, H) - W
4b00c892-fb67-5176-ac9a-aaa46a260473 | note | Activity by - Lab
4d03ed92-a777-5f6e-bbcc-35256d17be1f | note | Conformance Criteria (What's Required) - Materials to comply with contract specification
f09fa2e6-9d5b-534c-96f4-912d949f04f2 | note | Quantity - 90 m3
d0677eb3-239c-5091-a91f-2ae1a0abff6d | note | Frequency / When? - Prior to commencement
c5a849d9-6129-5679-8efe-bd577f1faefc | note | Inspection / Test Method - Lab report
ef7f2d59-cf44-5800-8e29-00f5993c5ffc | note | Records / evidence, WCL form - MDD and Grading Results
73879201-8d36-5512-85d1-29327a166337 | note | Standard - ICC STANDARD SPECIFICATIONS
db6c6114-726e-5d9f-9102-226418c47afd | note | Print, sign and date: Wilson - YES
58a6ff5d-3de5-57e0-83f8-e7e3a45c1f9d | note | Print, sign and date: ICC - YES
1dd65330-bb15-40fc-ae98-309f09ec1bc1 | checkpoint | 7 - D1.29.4
c4bbff50-2dbc-5e9f-9136-169d924125a9 | note | Inspection / Test Point - Crushed Basecourse Aggregate M/4 AP40
89679f96-75c8-52ef-8b84-16d9e27d9f88 | note | ACTION (W, M, H) - W
ab206ed1-4de8-5fab-8110-cc5473b92a6c | note | Activity by - Lab
13192121-5d5f-5647-abbc-389cf809cce8 | note | Conformance Criteria (What's Required) - Materials to comply with contract specification
84672626-b4f5-567e-a07a-687ffc2c9454 | note | Quantity - 22 m3
6e876c96-a7c4-5328-94f7-07c2c215888f | note | Frequency / When? - Prior to commencement
05db40c0-746e-5bab-b4ee-3ff5c729f058 | note | Inspection / Test Method - Lab report
5452af47-b390-54bc-a001-3ee03e37718c | note | Records / evidence, WCL form - MDD and Grading Results
a6778c85-4b09-5e97-8928-6bca095a1c81 | note | Standard - ICC STANDARD SPECIFICATIONS NZTA M/4
824a3695-c520-50f9-a9c9-1ddeb67b5ac1 | note | Print, sign and date: Wilson - YES
9753e80e-01b4-52d9-b997-349aaaf39f99 | note | Print, sign and date: ICC - YES
63f2fa8b-eb89-4a8e-80c1-dc8f9b107825 | section | Pre Construction
4b3e8fd8-9a9a-4f7a-a386-e93694097cf6 | checkpoint | 8 - D1.5
b76d8130-8389-52b7-acbf-441d96518d76 | note | Inspection / Test Point - Pre-work site inspection
19616bee-260a-54d8-85be-84f669fa5060 | note | ACTION (W, M, H) - H
cea6ab68-cdb5-5819-84c3-9c5284c7b8bf | note | Activity by - WCL
228904c6-347d-563e-82ab-0ae8259094b3 | note | Conformance Criteria (What's Required) - Video or photos near the construction zone to determine their pre construction condition (landowners property).
81127b55-782c-505d-bf67-ae6feff33032 | note | Frequency / When? - Prior to commencement
a144bce8-2b69-5bea-9f1f-7da0dbcb3378 | note | Inspection / Test Method - Inspection Document
7c659e3c-8264-5b95-88ca-55da74efefa4 | note | Records / evidence, WCL form - Sign This ITP Video, Photo
daa4f8b8-e328-516e-a44d-c8783deb0a91 | note | Standard - ICC STANDARD SPECIFICATIONS
32455598-90e7-5760-a2c8-8e46405f65ca | note | Print, sign and date: Wilson - YES
25fe2586-2c06-5883-ac5e-afbe6a629c33 | note | Print, sign and date: ICC - YES
8c566e12-602e-4cfa-a8be-6fa3cfb176c9 | signoff | HOLD POINT
bb6c69c8-d346-4564-9f2b-8584e9c25448 | checkpoint | 9 - D1.18
9eae7902-f715-55c3-8a2c-35612ad68b3a | note | Inspection / Test Point - Temporary traffic management
f6c2c32b-7c7e-50e2-b783-3e4ca0367097 | note | ACTION (W, M, H) - H
a2067ca4-bcac-5921-996f-902ab6d4fd51 | note | Activity by - WCL
bd0a217a-46ef-5708-8283-867c4003009d | note | Conformance Criteria (What's Required) - Signs set up as per TMP, with a copy on site with STMS. TMP monitored for practicality. If changes are required these are to be agreed upon with the engineer.
0e73753a-c6b1-5537-8ab7-c87f6ec94615 | note | Frequency / When? - Prior to commencement
ba352293-ada9-55f3-b0aa-af32d635e9ad | note | Inspection / Test Method - Visual inspection Document
099c5f1d-7b76-59be-96b3-ae3a6583490b | note | Records / evidence, WCL form - Sign This ITP On-site record
3c425a19-02d2-58c0-8285-00de9d69797b | note | Standard - ICC STANDARD SPECIFICATIONS CoPTTM
cf9abe90-ceea-5511-8928-fd20b900cde4 | note | Print, sign and date: Wilson - YES
a15864b1-781d-527a-bc2b-98337479fc63 | note | Print, sign and date: ICC - YES
03396473-8d52-4678-b592-3160b60ce177 | signoff | HOLD POINT
8b8e3838-a0de-4172-8940-dc0769ed3a8d | checkpoint | 10 - D2.7.1
2eef4ea5-378a-504e-8a14-cc15e90311e6 | note | Inspection / Test Point - Set out
0d578a1d-1075-534b-96ad-3aadfd7d37d6 | note | ACTION (W, M, H) - W
22658013-45b4-534b-869f-6204f0a542b6 | note | Activity by - ICC, WCL
3a999fbc-0e2b-5797-b084-64b2154d61b1 | note | Conformance Criteria (What's Required) - Mark out of alignment for mains and laterals
37871598-85f3-55a3-81f4-80cdea930f51 | note | Frequency / When? - Prior to commencement
cd6e4254-9a99-50cd-affe-1f2d25827340 | note | Inspection / Test Method - Surface marking
750dbc2b-7441-53c0-be36-a15b83ce3a52 | note | Records / evidence, WCL form - Sign This ITP
d6d78be5-026e-5262-ae60-6191f7770f87 | note | Standard - ICC STANDARD SPECIFICATIONS
1e83a1cf-cd80-533b-ae09-5d604fad887b | note | Print, sign and date: Wilson - YES
f7e41fac-7b40-5533-8449-fed2aad4405d | note | Print, sign and date: ICC - YES
801cffd3-7be7-4320-ba78-ed4966aecfcd | checkpoint | 11 - D1.8
8922b650-ecdd-5fd4-a98c-3710eb707d0b | note | Inspection / Test Point - Protection and identification of other Services
25a7af2b-4fed-55cd-99ad-2cdec7c219cc | note | ACTION (W, M, H) - H
c88dd100-8c51-53b2-b7e5-3e60cef027ba | note | Activity by - WCL, asset owners
eb9ec4bc-6e4d-5ccf-b5fc-6f36fe01df18 | note | Conformance Criteria (What's Required) - Mark out on site of all services. Services to be potholed for as per Wilsons company policy
a8c4eb9d-944d-533c-ab11-f5487182c1a8 | note | Frequency / When? - Prior to commencement
892e0948-3acd-5f5d-8b65-287ab1d15f55 | note | Inspection / Test Method - Surface marking Visual inspection
2671c13b-bb70-5a7a-b5d6-82018591e298 | note | Records / evidence, WCL form - Sign This ITP
096f1a7b-71e4-5919-92fd-bd2dbdd83785 | note | Standard - ICC STANDARD SPECIFICATIONS Wilson's prior to excavate policy
0beaaee6-7769-5974-8b26-8e2b5ad57782 | note | Print, sign and date: Wilson - YES
388a8dce-7381-526c-b842-7bb51f14ef74 | note | Print, sign and date: ICC - YES
8defe1fd-c505-40bc-b997-86c49b18de65 | signoff | HOLD POINT
60161888-1d7f-4b00-ac74-a80885289c56 | checkpoint | 12 - D1.11, D9.5
bbf38de6-01c5-586f-9e27-3b2494bc8f8b | note | Inspection / Test Point - Notification to residents and businesses
5078480a-6752-5cc3-a3df-30e8a5b8c90c | note | ACTION (W, M, H) - M
72cf0f12-ae76-5b1c-822b-fc33f8fee8de | note | Activity by - WCL
007c172b-16ba-5db5-831b-cb7468db06b1 | note | Conformance Criteria (What's Required) - Letter drop / business visits
f89517a7-835f-5706-a267-3fe2d51a2612 | note | Frequency / When? - Prior to commencement (min. two working days prior to water shutoff or access restriction)
0fffae80-0f12-56d4-88fa-1918e28a11c1 | note | Inspection / Test Method - Document delivered
8ee4f00d-a099-5e76-93c2-5575a279e047 | note | Records / evidence, WCL form - Sign This ITP Notification letter
ce8921f0-add4-5923-94a6-98a389586416 | note | Standard - ICC STANDARD SPECIFICATIONS
8df5c54c-8f93-5071-a2b4-0498c347ed63 | note | Print, sign and date: Wilson - YES
1aa262e5-216e-50e8-b71d-e847a1639de6 | note | Print, sign and date: ICC - YES
15a7e45e-5e87-4be3-9bdb-dfb73133c648 | section | Stormwater Main
7b452a7e-150a-4e27-8c14-d0a7587968c9 | checkpoint | 13 - C1.4, D2.4.1
94135f68-281f-5287-b801-3e184ad95f85 | note | Inspection / Test Point - Pipe material (main)
d5d4ff71-b9f5-5586-b157-f31c0b284f83 | note | ACTION (W, M, H) - M
6e723946-208d-5b9c-9be3-529eb86c615c | note | Activity by - WCL, ICC
ac6f5fc7-e3f8-5507-96c9-45c1514a0fcb | note | Conformance Criteria (What's Required) - DN450 RC JR Class 4, ICC to inspect pipe deliveries as required
09dcb804-9c82-53b6-9e06-509983290ea8 | note | Quantity - 360 m
7e0c8af7-d9d1-51a1-80e1-6d8db077146e | note | Frequency / When? - 1 / delivery
d5b49021-3d1b-563a-b723-7f9c34701263 | note | Inspection / Test Method - Visual inspection
f16bfaca-fca2-58c2-b913-097daea1ea59 | note | Records / evidence, WCL form - Sign This ITP
6dae2c78-0b07-59fc-98bd-efdf6f65fef3 | note | Standard - ICC STANDARD SPECIFICATIONS AS/NZS 4058:2007
1cd75dad-aeec-568a-9962-c58b2d1bdf80 | note | Print, sign and date: Wilson - YES
6dfe8044-1995-543c-bf00-daa95120bdad | note | Print, sign and date: ICC - YES
7c85c7b4-d78d-48b3-8055-1bf4147bab5e | checkpoint | 14 - D4.3.1
654b2c28-2589-5482-beab-d9ba06f93fa2 | note | Inspection / Test Point - Pipe material (lateral)
5d1882e9-ebf8-5d06-9810-7954cec9cae8 | note | ACTION (W, M, H) - M
9e879cef-f651-5784-9703-074768b61b6d | note | Activity by - WCL, ICC
806250c7-d60d-53a9-9757-38a21850a9d2 | note | Conformance Criteria (What's Required) - DN100 uPVC SN6 RRJ
e74b4886-86f1-5835-85d7-dc52e77e97a3 | note | Quantity - 32 m
9e90bc0c-e767-551a-95a9-fc280d3fe5ff | note | Frequency / When? - 1 / delivery
56f3df5b-290c-53db-b626-3141422c2cb7 | note | Inspection / Test Method - Visual inspection
2f62b212-9cde-52c6-99b4-38b95b5eeadc | note | Records / evidence, WCL form - Sign This ITP
b9747a74-44f0-5882-9c8a-6e7542ceaebb | note | Standard - AS/NZS 1260:2017
fc42d732-95fe-5203-9051-bcdb8c6fd7b1 | note | Print, sign and date: Wilson - YES
f93619d1-5568-5614-8611-19a430feab13 | note | Print, sign and date: ICC - YES
513df1fa-78dd-4ca7-ab28-bbbb01efd22c | checkpoint | 15 - D4.3.1
f3e1f240-9694-5948-84d0-9a52d2ba56c0 | note | Inspection / Test Point - Pipe material (sump lead)
f5bfc363-37a9-5700-989a-60f78f7f2844 | note | ACTION (W, M, H) - M
ffccb7c9-106c-5ec4-b7ca-c0259b49704b | note | Activity by - WCL, ICC
f93e27ad-b5ad-56f7-9594-2115a33fc674 | note | Conformance Criteria (What's Required) - DN150 uPVC SN8 RRJ DN225 uPVC SN8 RRJ
84e0e508-c028-5e5a-8aea-edf5dc27bb74 | note | Quantity - 45 m
945c74a8-f042-5ac4-bced-584bdeb92913 | note | ○ 35 m
78f2e5e7-b4a8-5519-bff8-865e72970692 | note | Frequency / When? - 1 / delivery
b1076b65-5e63-5696-8b34-d5b34450e0a9 | note | Inspection / Test Method - Visual inspection
e567bf3d-03bb-503a-b118-151e3a543fd5 | note | Records / evidence, WCL form - Sign This ITP
de832e51-9f8b-5e50-a350-ed1715512c28 | note | Standard - AS/NZS 1260:2017
1de9f081-b63a-5a58-a5ca-c1c5ff2084df | note | Print, sign and date: Wilson - YES
dfefec0e-f31b-59ce-b105-68a15840762a | note | Print, sign and date: ICC - YES
b0b2620c-3e36-4399-95f5-e47c273743ba | checkpoint | 16 - D2.7.2
6f86975f-6db5-5cb4-af73-ac9bd0baef36 | note | Inspection / Test Point - Excavation
979eb822-42dc-5199-963b-935d90ed1995 | note | ACTION (W, M, H) - M
703a4735-771b-5ee6-9b2e-8dc7121ab67f | note | Activity by - WCL
f940dddf-391b-578e-92c6-0d8975a1b9de | note | Conformance Criteria (What's Required) - The finished excavation surface shall be a smooth consistent surface at the appropriate grade. No tolerance on the excavation base level that reduces the depth of the bedding will be allowed.
a7c843af-f346-58e4-b465-9549084b061e | note | Quantity - 472 m
b57a7ccf-97f2-5059-8c49-36605d7c97a9 | note | Frequency / When? - continuous
dd73e3ea-096a-507e-ade1-55c91bedd17d | note | Inspection / Test Method - Visual inspection Levelling
bd63777a-ecc0-546c-9d93-0adeab645719 | note | Records / evidence, WCL form - Sign This ITP
320e4fb2-efeb-51fc-ae7e-22460783d33d | note | Standard - ICC STANDARD SPECIFICATIONS
ccc672ad-0557-5b1e-b511-ddb24256b002 | note | Print, sign and date: Wilson - YES
5486fcb0-dd21-537f-a53c-ee841e24aaf0 | note | Print, sign and date: ICC - YES
4473db22-1cea-47c9-9d70-05dc687d8ae3 | checkpoint | 17 - D13.4.3
6e9a0f19-d3fd-5724-aa18-1c3cb44f11da | note | Inspection / Test Point - Subgrade inspection
d0096092-14b1-57f6-96cb-5f93ad008ab6 | note | ACTION (W, M, H) - M
805e7522-b325-5e8b-b9c2-ebd44fa375e9 | note | Activity by - WCL, ICC
a429dcc6-f48e-5572-8b73-58c5dd6ece3e | note | Conformance Criteria (What's Required) - To determine if improvements are required
fdd63264-7591-5e55-aae2-ca25ab853a04 | note | Quantity - 472 m
92f80012-5b8b-549e-9854-2cab11f6e2f4 | note | Frequency / When? - Prior to placement of bedding
e0bc0151-8368-535f-bf6c-21675b4c5610 | note | Inspection / Test Method - Visual inspection
838bd536-b580-5c22-9c2c-12ca8c5b300e | note | Records / evidence, WCL form - Sign This ITP
648aa574-5515-5e91-8b00-5405a7949f7b | note | Standard - ICC STANDARD SPECIFICATIONS
22e7ac9e-1f4c-5838-9b6b-967d29c394e0 | note | Print, sign and date: Wilson - YES
426714a9-dc23-52ac-8348-7e0afca38a9a | note | Print, sign and date: ICC - YES
916d1e59-2578-4f98-b3ef-1911e47efe27 | checkpoint | 18 - D2.4.2
3358bfd9-8b85-5500-aab6-29aa2e0a6281 | note | Inspection / Test Point - Free draining material
af1ff7fa-8693-58fd-9397-847bf9e78fd6 | note | ACTION (W, M, H) - M
d49f0f7c-02a8-531c-8730-0a6ffe24c49a | note | Activity by - WCL
03e75420-bd49-5177-a949-dfa932ec5a8b | note | Conformance Criteria (What's Required) - pea gravel wrapped in a suitable geotextile up to 100 mm over the trench bed
e579a149-c3e7-5f3c-9392-ccd023e354b8 | note | Quantity - 0 - 360 m
5423d839-447b-516a-91c4-a9d7e346d379 | note | Frequency / When? - Continous, in accordance with observed groundwater conditions
f053dc27-5584-558a-a24e-25de372bf619 | note | Inspection / Test Method - Secific approval should be given by the Engineer
a2b41474-8288-58f1-84b7-04e6e199b0c5 | note | Records / evidence, WCL form - NTE, NTC
1070c633-7d32-5835-b54a-853cc867a76b | note | Standard - ICC STANDARD SPECIFICATIONS
39ab7702-eaf1-5c42-91df-d272fea64415 | note | Print, sign and date: Wilson - YES
91656ac1-dd81-5732-984c-089d83f5c108 | note | Print, sign and date: ICC - YES
e52eb042-6512-4265-b35e-ed66b5494178 | checkpoint | 19 - D2.7.3
a7e2aa01-a5ed-56e9-8f7a-6f856cf6366f | note | Inspection / Test Point - Pipe installation (main)
0bece6c0-cb91-5c0a-a323-5a7b081a6354 | note | ACTION (W, M, H) - M
f5441256-b1b9-535b-9263-b9e18b8b6500 | note | Activity by - WCL
0cd18171-cd03-5dd7-ba09-54d769055b5d | note | Conformance Criteria (What's Required) - +/- 30mm (horizontal)
bfa0cadc-8e2f-5620-ae9e-7c6ed488b5b1 | note | ○ +/- 5mm (vertical)
d10ae28c-2562-5ca6-9d11-79a3585affc6 | note | Quantity - 360 m
11b5a4ac-5d0c-5c4e-9938-8afe05bcf61d | note | Frequency / When? - Continous (pipe laser), 1/20 m (independent optical level)
9ca94d05-57e9-5b66-9e75-67e7434490ec | note | Inspection / Test Method - Using calibrated pipe laser, Optical levelling
ecfd4a26-13b9-5a41-8636-fbc304c1e8bb | note | Records / evidence, WCL form - Sign this ITP leveling record
85ed7d38-9b90-5238-b02e-6bd13e5fbf6b | note | Standard - ICC STANDARD SPECIFICATIONS
0e988915-7295-5649-b52d-c505d32bbc9d | note | Print, sign and date: Wilson - YES
c3287a21-d231-5d94-b799-792bf8ec55ba | note | Print, sign and date: ICC - YES
a8e2711d-9a27-41b3-a56b-f9a34e9c6fd6 | checkpoint | 20 - D4.4
614ed155-6323-5b0d-b704-56813a163462 | note | Inspection / Test Point - Pipe installation (lateral)
9bc7dc76-9690-5b1e-b6b1-795b269137b3 | note | ACTION (W, M, H) - M
ec9e8e9a-59f0-53a8-9de0-5c67626efd1c | note | Activity by - WCL
db39f5f9-215f-50e5-87f1-98ff3583f927 | note | Conformance Criteria (What's Required) - grade: min 1.00 %
ca76fcfe-212c-589e-9b71-ffebb8d5b935 | note | ○ Connection to the main: 90° saddle Connection to D600 manhole: gritted manhole finisher
e9f0e43d-131b-5a93-8e51-c96f7ff497aa | note | ○ Connection at boundary: slip coupler/plumbqwik
c2250526-4887-5b5b-8d20-ba9e45269470 | note | Quantity - 3 (to 600 mh)
ad12d76a-4d64-5854-9f88-d54ff456421e | note | ○ 7 (to main)
f9a44c38-c573-50af-a01e-f10fec492219 | note | ○ 1 (to 1050 mh)
2a79f115-1788-5e33-9193-481183176248 | note | Frequency / When? - Continous
950190e0-f530-5999-97b1-698841b02ef1 | note | Inspection / Test Method - Measurement Document
35162346-1e2d-56b5-8d71-f7e5d4de9331 | note | Records / evidence, WCL form - Sign this ITP Detailed Drainage Connection Sheet
43e9aad9-9c17-5de7-92fd-e7d0f7a7cfba | note | Standard - ICC STANDARD SPECIFICATIONS
7012964e-8818-5d10-b8fa-ad91eb9784bf | note | Print, sign and date: Wilson - YES
c9ff12ba-b092-589b-a530-ab4ce33433a2 | note | Print, sign and date: ICC - YES
5a38e2ad-ef1d-46e0-989d-e42e18b63dc4 | checkpoint | 21 - D4.4
e93bea08-d8a9-5c89-96f5-b3d31eda507b | note | Inspection / Test Point - Pipe installation (sump lead)
8ee81265-c26f-557b-9c03-2751efe05e02 | note | ACTION (W, M, H) - M
360a55b3-2349-5d5e-b62a-1c21c69b0f86 | note | Activity by - WCL
fcbefb4b-ff44-5c55-86f0-599fd1674a61 | note | Conformance Criteria (What's Required) - grade: min 1.00 %
7558d750-11ea-54b6-b329-3b26ae12bb0c | note | ○ Connection to the main: 90° saddle
412e2f3b-1d25-5a57-a5b9-677f46aa13b3 | note | ○ Connection to D600 mh / yard sump: gritted manhole starter / finisher
ff00ae03-59c1-56a1-ac5d-5cf39578fcd1 | note | Quantity - 3 (to 600 MH)
6aa85beb-d20e-50ab-ae92-df11dfd8d976 | note | ○ 3 (to main)
2f0de6f9-e1d1-5cbf-a680-1b4a9b884f20 | note | Frequency / When? - continous
28fedeae-08bb-5c0d-9e19-dec128049b30 | note | Inspection / Test Method - Measurement Visual inspection
13af9081-dfa7-5629-a647-e05519789ee0 | note | Records / evidence, WCL form - Sign This ITP
cad948d5-62b4-578f-badd-b63a1f687d7a | note | Print, sign and date: Wilson - YES
2e8f07ef-64d6-5736-b2e6-42f32592e297 | note | Print, sign and date: ICC - YES
a39eeb74-79a5-412b-9df7-85e6bf5ba082 | checkpoint | 22 - D2.7.6
1d131939-4bd9-5518-a060-f984ed07720c | note | Inspection / Test Point - Bedding (main)
ee7473af-0dc2-5a31-a4a3-52aee660c11c | note | ACTION (W, M, H) - M
3da6068f-8c02-5ae8-931c-3b25d065916f | note | Activity by - WCL
900116a1-e112-5066-883d-d44f849a0d26 | note | Conformance Criteria (What's Required) - lb (depth below): min 150 mm lc (width beside): min 300 mm lo (depth above): min 150 mm compacted layers not exceeding ⅓ of the pipe OD
8f5cd678-b2c1-5bed-a2a5-edacb543bc3a | note | Quantity - 360 m
4a4e09c2-a3c7-5f35-ac9c-e15afa7a2884 | note | Frequency / When? - continuous
51237c5d-7ca0-5b48-9e01-4f1d7c4bbecd | note | Inspection / Test Method - Measurement Levelling
d4f50a58-6c1e-51d7-b9e5-be24fecbdd8d | note | Records / evidence, WCL form - Sign this ITP
60e05604-8c3f-5d5a-a589-52ae91ac6860 | note | Standard - AS/NZS 2566 table 4.2.
c02b750b-480a-5ad9-b989-02b15ce90553 | note | Print, sign and date: Wilson - YES
ac26db46-4098-51ac-b474-6608466c5c43 | note | Print, sign and date: ICC - YES
60830c05-2379-4e3a-a308-9054e393a03f | checkpoint | 23 - D2.7.6
a6e91d62-27fb-5be0-a536-3e8011bc19a1 | note | Inspection / Test Point - Bedding (lateral)
47fc898f-652c-50a3-9fda-b7c18d81dec3 | note | ACTION (W, M, H) - M
b6cbd504-c129-58ab-906c-b4529d869df2 | note | Activity by - WCL
6270afcc-36c0-5418-8dec-b7e02c1034e3 | note | Conformance Criteria (What's Required) - lb (depth below): min 75 mm lc (width beside): min 100 mm lo (depth above): min 100 mm compacted layers not exceeding ⅓ of the pipe OD
fb40b0f1-a8c3-55e7-b01b-5538cad14f12 | note | Quantity - 32 m
572fda2f-b32c-5e08-a9e5-259effbbd3aa | note | Frequency / When? - continuous
5c1f1e4e-387a-5a5c-8a48-d2828bd7c3f4 | note | Inspection / Test Method - Measurement Levelling
bb955fc7-3edf-5d24-8bf5-33f280699133 | note | Records / evidence, WCL form - Sign this ITP
2f7f1a98-e236-5320-a343-a398df445d4f | note | Standard - AS/NZS 2566 table 4.2.
62f9d576-a720-5cdd-8590-adf7c1ca700f | note | Print, sign and date: Wilson - YES
24289366-b00f-5160-a891-be22edd58c08 | note | Print, sign and date: ICC - YES
94e92f16-0887-44f9-b4de-1d9850260211 | checkpoint | 24 - D2.7.6
2f216ddd-067d-5bc8-ae3e-e4d977b8234f | note | Inspection / Test Point - Bedding (sump lead)
74953f36-58c4-5bbe-95b7-fe32ed54c75d | note | ACTION (W, M, H) - M
164b655a-1384-5176-93ed-6d7d5a297464 | note | Activity by - WCL
21d00f60-c5ec-5c32-ba13-be413446ca9f | note | Conformance Criteria (What's Required) - lb (depth below): min 100 mm lc (width beside): min 150 mm lo (depth above): min 150 mm compacted layers not exceeding ⅓ of the pipe OD
44e6e99b-3b7e-544d-a7a2-347d0a87c916 | note | Quantity - 80 m
0ce63e93-d99e-579f-9bd1-4d5213242113 | note | Frequency / When? - continuous
6ad4a79f-1eae-5fcd-a9d9-8d82456b770a | note | Inspection / Test Method - Measurements Levelling
0c89558b-5bcc-5d9a-92b9-86855fb5b1fe | note | Records / evidence, WCL form - Sign this ITP
a4116579-2f14-51c9-ba03-a7d8073c9687 | note | Standard - AS/NZS 2566 table 4.2.
5b996814-67d4-581d-a708-a660430e1382 | note | Print, sign and date: Wilson - YES
4a72d320-62a9-556f-9e12-2a3eb9a744b8 | note | Print, sign and date: ICC - YES
4def9328-1fc7-4b75-bf70-9edfb93a6cb6 | checkpoint | 25 - D18 Fig. D12
79698e5d-8b80-5398-9c08-b0a1dc5540a4 | note | Inspection / Test Point - Manhole (D1050)
9e956a27-97d9-5199-ba1a-440eb53a5b5e | note | ACTION (W, M, H) - M
09785ce9-5947-5166-a1eb-8f5467f8d626 | note | Activity by - WCL
a6f8f097-d3ad-5284-946b-9f8fe77e24d3 | note | Conformance Criteria (What's Required) - 1050mm
3b0f49dc-54c0-59dc-9d16-75ed1d10d74e | note | ○ The sump shall be at least 300 mm from the underside of the lowest invert level.
c65ca283-795a-5870-99a6-577eaa794cd2 | note | ○ Neck depth ≤ 315 mm
9168a17b-0f70-5269-93a4-fa527cd55a2c | note | ○ In-situ concrete packing
35b401a7-9d3a-5972-9713-207063bc96c7 | note | Quantity - 7
d20d42d2-0691-50d8-9a80-acbd81e55905 | note | Frequency / When? - 1 / manhole
a974d557-c35e-57af-bc96-4bf64cc6e030 | note | Inspection / Test Method - Measurement Levelling Document
596c7e87-9acd-5134-890b-2b91ce376b96 | note | Records / evidence, WCL form - Sign this ITP Manhole Inspection Sheet
67b4d5b4-858c-5184-8e85-2c1343caada7 | note | Standard - NZS 3109:1997
fbe6a7c4-52e5-5780-823d-0734eb6913d4 | note | Print, sign and date: Wilson - YES
9faac0d4-8479-5465-9f09-5b914a2e22c6 | note | Print, sign and date: ICC - YES
c458785d-8b55-4e3b-b939-32eccd3e2603 | checkpoint | 26 - D18
8ddfce61-88ac-57b3-82ff-3fe05f0b6f5d | note | Inspection / Test Point - Manhole (D600)
f91b57a9-fe56-51ce-b01e-18188f2afc1b | note | ACTION (W, M, H) - M
dee42a76-2e06-5158-882a-a7b587bca62c | note | Activity by - WCL
c5aa6bf7-286a-5e3f-b1ea-a651a2da2435 | note | Conformance Criteria (What's Required) - CIRCULAR SUMP+INTERNAL BASE 600.900.100MM
8a8da777-9167-59b1-9d9a-0fdaa8ded2f2 | note | ○ 600 mm cover Class D
45d7bd08-c3f6-553a-a8d5-0a05fea22ad6 | note | ○ Connection to the main: D225 uPVC
b6725ee2-94ba-5d7e-b754-4d4f751e4940 | note | Quantity - 3
d8fc10a5-834d-5ede-80ab-f67c46ccd0ce | note | Frequency / When? - 1 / manhole
074803af-6aca-5369-a8a4-a023614c76b0 | note | Inspection / Test Method - Measurement Levelling Document
46002239-ea21-504f-8fde-815294855083 | note | Records / evidence, WCL form - Sign this ITP, Manhole Inspection Sheet
99de449e-8a4a-528e-9d04-79fa586defad | note | Standard - ICC STANDARD SPECIFICATIONS
62f4c35e-7817-5af3-a246-b95ad227eeb8 | note | Print, sign and date: Wilson - YES
d29c108c-5d48-53ff-aa57-90914303ae41 | note | Print, sign and date: ICC - YES
06c55ad6-0f5e-4f82-be39-9eb0a876ff7e | checkpoint | 27 - D18
c695b3ff-dba9-5e55-bc16-c1d7c3400a0c | note | Inspection / Test Point - Yard sumps
1c5adb2d-5a33-5f23-a7ba-53bca31569a0 | note | ACTION (W, M, H) - M
6fd53cb1-fd40-52d5-8e49-080f1054fa78 | note | Activity by - WCL
0ce51b32-ca47-5c91-9140-a177d5cd9d96 | note | Conformance Criteria (What's Required) - Flat top concrete sump box 450x450x1200
0e038f74-aba3-5995-8c1a-4146164b7e20 | note | ○ Cast Iron sump grate + frame 450x450 D150 sump lead
59fb03b8-111b-5b8a-bded-464491e60f6d | note | Quantity - 5 (1 existing is to be reconnected)
2c606a32-8374-52a0-8cd1-8315af0ec39a | note | Frequency / When? - 1 / yard sump
7f01e648-bcc3-50c7-998e-48be6f2c038e | note | Inspection / Test Method - Measurement Levelling Document
386fe96c-6e35-50aa-a0f3-f872e3e0520a | note | Records / evidence, WCL form - Sign this ITP, Manhole Inspection Sheet
7b87c624-de15-5ffc-a65d-c823c9434136 | note | Standard - ICC STANDARD SPECIFICATIONS
40583caf-d975-5b95-b3fe-ec723bb5e77f | note | Print, sign and date: Wilson - YES
08249f8f-41c2-5db8-90d5-a3a24f44cb40 | note | Print, sign and date: ICC - YES
f7453156-868c-40f6-8e55-33188bff5a61 | checkpoint | 28 - D15
d2a995e5-7626-5ea1-a091-77c77edf92e7 | note | Inspection / Test Point - Service covers
0cbe7a6e-08e7-5f69-85c2-d7f596570a50 | note | ACTION (W, M, H) - W
be107823-1977-53da-8f01-219f7069d0e1 | note | Activity by - WCL, ICC
1a7173db-09ad-509e-9ca0-603a979120a6 | note | Conformance Criteria (What's Required) - HN-HO-72
80ffcc37-8c1e-56e9-896c-8ffccbeca768 | note | ○ d600 mm, 450x450 mm
1f17dd16-bfa0-569f-b028-a8c899a5f602 | note | ○ Cover levels to be adjusted to existing ground levels
adb247ad-913c-5337-a3e2-3585b7b06e72 | note | Quantity - 7 grated 600
3774a073-440f-5325-b398-992ea3ef237f | note | ○ 3 solid 600
8fdd4dd7-10ee-5350-88b2-d242266cba18 | note | ○ 5 grated 450x450
578711f2-1bd0-5f75-b462-42fe0626732c | note | Frequency / When? - before surface reinstatement, landscaping
89305dc3-b438-51fd-9fb1-2967b2d9e68b | note | Inspection / Test Method - Visual inspection Measurement
46247632-1225-5b26-8b12-59788315b0d3 | note | Records / evidence, WCL form - Sign this ITP
c2304735-f682-5c17-bb0d-cd4d1e1ec38f | note | Standard - ICC STANDARD SPECIFICATIONS
2f9ea7ff-f26c-5511-bd3e-b2b9d958633d | note | Print, sign and date: Wilson - YES
07ffba0d-09f5-5761-822d-3a7f964bbf24 | note | Print, sign and date: ICC - YES
70e692d7-753b-4b4b-a3e5-d79869239b01 | checkpoint | 29 - D2.9.3
1c878dc5-ee48-59a1-be34-421a1ac9ff44 | note | Inspection / Test Point - CCTV Inspection and Cleaning
0a273d2d-c65b-5b5f-a5ea-7db705b558df | note | ACTION (W, M, H) - H
909d96c3-f145-5193-9288-0b86820c19ea | note | Activity by - WCL
9bb4af2a-f4a2-52ee-9c07-accbd4fd9205 | note | Conformance Criteria (What's Required) - to confirm that the lines are free from debris and have no defects
234a26d5-9a3a-5cbd-b362-0fcc7da5cb08 | note | Quantity - 360 m (main)
9c4b1451-e5d7-506f-a255-6c9c33fe954e | note | Frequency / When? - prior to the final surface reinstatement
7f136d13-ed50-5e81-a650-c88d2e4b5155 | note | Inspection / Test Method - CCTV inspection
bcded117-8fe2-5a7e-86b2-d257d0bcd978 | note | Records / evidence, WCL form - Sign this ITP CCTV survey
b4cf04c9-f692-501b-b7f1-c8187010e6c4 | note | Standard - New Zealand Pipe Inspection Manual AS/NZS 2566:2
6036e4ff-b698-5ee3-8ab3-b1cf5764a022 | note | Print, sign and date: Wilson - YES
db65c08f-640b-53dd-9132-e98b49514516 | note | Print, sign and date: ICC - YES
b8d6265d-7a54-49da-90e8-a3e25f092275 | signoff | HOLD POINT
db76051e-8b08-4e5e-b6e7-258df5243c56 | checkpoint | 30
2af750f7-35b9-546f-86c2-30566ff49396 | note | Inspection / Test Point - Removal of existing pipelines and manholes
4cdd8737-5ed2-502a-8b4e-62ab2b301c45 | note | ACTION (W, M, H) - W
99ed989a-b3f4-52e3-8a51-400368c6fc62 | note | Activity by - WCL
4bb0afcd-a24f-5561-8f42-97459df7b109 | note | Conformance Criteria (What's Required) - DN150 EW
edc2f671-5c01-5789-b001-b73ea0596e4f | note | ○ Excavation may include the removal of existing redundant mains located within the trench extents.
60cb2421-804d-5ae4-a4be-c9bb9675ed0f | note | Quantity - max 360 m + 10 manholes
3ca67605-7a40-5391-943f-75206bde1874 | note | Frequency / When? - during main installation (parts of Southern Korimako alignment)
1f7ff79e-8df9-5c3b-9154-579a418ce1c5 | note | Inspection / Test Method - Visual inspection
f016e4a8-aaf0-5131-b63b-2507bfb76b6a | note | Records / evidence, WCL form - Sign this ITP
bdc315da-82eb-5e16-b3eb-5648ff30f3c8 | note | Standard - ICC STANDARD SPECIFICATIONS
cb4e2428-f9f1-51f9-82ce-a287f024a881 | note | Print, sign and date: Wilson - YES
35b79392-dcb1-5e90-965b-6b8d2117254b | note | Print, sign and date: ICC - YES
2717ffdc-9efd-4a9d-847e-e8f9b9cb452d | checkpoint | 31 - D2.10
4d599a5d-11e3-5bb5-9ba0-ea2c38103c0a | note | Inspection / Test Point - Abandonement of existing pipelines by filling
accaa636-578c-5d3f-a9e4-849e444afd0b | note | Activity by - WCL
2dc35785-bd3d-5713-aa79-40781f0f68c7 | note | Conformance Criteria (What's Required) - DN150 EW
b1eca681-d17f-535f-bf39-90069cc99de5 | note | ○ Filling material and methodology for execution shall be approved by the Engineer.
995e8e56-00cc-5074-b0f1-d4c9c48a5ae4 | note | ○ Ensure there are no active connections to the main
23147676-57cd-54da-b256-4f8e31875929 | note | Quantity - 15 m3
1e4a4941-41c1-5186-af1d-f5b83dd4b742 | note | Frequency / When? - following new main installation (Northern Korimako alignment)
f8125056-35f7-50a3-9c39-c4413a55eaf4 | note | Inspection / Test Method - Visual inspection Document
fe3a15df-c8e1-5731-ab0e-b87a7d747999 | note | Records / evidence, WCL form - Sign this ITP Delivery docket
07d50146-d8cd-5f3e-8fb1-07c0db5c1311 | note | Standard - ICC STANDARD SPECIFICATIONS
f27831dc-6395-5f36-abdb-427c279dc2d7 | note | Print, sign and date: Wilson - YES
11d8b2c6-2229-5704-9ed9-deaf322c5923 | note | Print, sign and date: ICC - YES
6ddf774e-ee5e-4ca7-9e6a-cdb11c876b41 | checkpoint | 32 - D2.7.7
b4dc3230-994b-5d7e-b9ef-333af360dcce | note | Inspection / Test Point - Backfilling and compaction (existing, excavated material in berm)
5dad1994-058d-51cc-842b-8e2bd93b2b00 | note | ACTION (W, M, H) - M
ea7a63c4-7dbd-57c1-af1b-c33db966a091 | note | Activity by - WCL
4d679981-02b6-5a7c-bd57-c7beeb65ebf2 | note | Conformance Criteria (What's Required) - All backfill material layers shall be placed and compacted in layers with appropriately sized mechanical compaction equipment to achieve uniform compaction for the full depth. This shall be in compacted layers not exceeding 200mm depth
9de1eae5-bfcb-510a-96bf-da4fad9861ed | note | Quantity - 240 m
bcfc9d24-01a7-5183-ab87-98fad551f080 | note | Frequency / When? - continuous
e4cdd428-26d6-5323-acd4-be5505e5933c | note | Inspection / Test Method - NDM testing: not required
5cf8df45-66fb-5349-abcb-803b78e6eae4 | note | ○ Clegg testing: not required
a6779478-784d-5b66-b132-4a2c4120b05d | note | Records / evidence, WCL form - Sign this ITP
9b644b2c-8aed-54c7-8b1d-6b37f3ed5e85 | note | Standard - ICC STANDARD SPECIFICATIONS
a1794dd4-d4c7-584a-8efd-464f5ae5b447 | note | Print, sign and date: Wilson - YES
234e5535-35f1-5f6e-b1a5-37879dcdb518 | note | Print, sign and date: ICC - YES
40509417-549d-483e-bb92-df9bdc752b07 | section | Surface Reinstatement
6a782ac8-4cb7-4005-8447-989976a6f272 | checkpoint | 33 - D13
b026c092-5998-5402-8fdf-1898fda77675 | note | Inspection / Test Point - Landscaping
f46661d3-b24d-57e2-88a8-0f8cb06aec06 | note | ACTION (W, M, H) - W
b2077d49-8840-5ac1-bb9a-ec8c0d56e84b | note | Activity by - WCL
a9d74b33-11dd-5747-a27d-744f06668ba7 | note | Conformance Criteria (What's Required) - The final surface in the berm area is to be re-graded, with new sump manholes and yard sumps established as the low points.
10de8f77-ccba-5310-b0fe-5a79e595368d | note | Quantity - 240 m
22bd6d74-191e-50c2-9cfc-7165a9c28977 | note | Frequency / When? - following new main and lateral installation
4e1fc4ce-6737-5502-8fd6-0f43ae098abd | note | Inspection / Test Method - Visual inspection Levelling
cc229498-b78d-50af-81ce-0aa59c043f40 | note | Records / evidence, WCL form - Sign this ITP
d81e0b6f-3359-564e-92e1-6067a909c0eb | note | Standard - ICC STANDARD SPECIFICATIONS
2986a164-517c-5bca-83a1-f4a489410144 | note | Print, sign and date: Wilson - YES
fc86b085-8908-5d83-b1f6-5427890033e9 | note | Print, sign and date: ICC - YES
fd9b47e0-17a4-47bd-aadf-e4822f397d68 | checkpoint | 34 - D13.7
bf1d1af0-7a59-56c2-8c14-47351efa0f23 | note | Inspection / Test Point - Grass seeding
94518652-6674-5bb3-97e9-c103c21e8822 | note | ACTION (W, M, H) - W
d4bfba46-782a-5cb6-8188-9f83ab543c87 | note | Activity by - WCL
00fb2c97-2fa5-51ca-9b5f-5a7f5c0daa98 | note | Conformance Criteria (What's Required) - approved seed mixture, 35 g/m2
2cfcbf40-ebf9-567a-a2cc-630084198963 | note | Quantity - 240 m
efa73eed-4fd1-52c7-84f1-bb33b6076caf | note | Frequency / When? - following landscaping between the months of September - April
9a6c18b2-d016-5bdf-ab6a-99df6bd3c892 | note | Inspection / Test Method - Visual inspection
21f189c3-91a2-52d8-a874-df706c5cd844 | note | Records / evidence, WCL form - Sign this ITP, Blending docket
211ab9c0-a73e-574c-a527-9132e7d24f6b | note | Standard - ICC STANDARD SPECIFICATIONS
c126b06c-4860-509a-b701-3b243bc530da | note | Print, sign and date: Wilson - YES
73c75144-2ba3-5966-815a-4a580cbc89c1 | note | Print, sign and date: ICC - YES
d2d63e92-4cc1-45ec-9fd2-92e96a9b4eab | checkpoint | 35 - D2.7.7
c0c15429-dd7a-5288-a2bd-644d4c919708 | note | Inspection / Test Point - Subbase (AP65) compaction
030be206-a408-5c78-a838-327f2d430299 | note | ACTION (W, M, H) - H
685b5b40-14c3-53db-b18e-4049be3a5eb3 | note | Activity by - WCL
b44cf56e-2206-5813-ba78-4e0a62812126 | note | Conformance Criteria (What's Required) - Carriageway:
b5b47316-3bee-582b-bfb0-b398b688c945 | note | ○ 0.3 - 1.5 m deep: min 35 CIV
6fc821e4-5486-5b5e-ab04-0b9ee31f7883 | note | ○ > 1.5 m deep : min 25 CIV
6138c811-94cf-512b-98ee-3fa08edd34af | note | Quantity - Culvert + ch 240 - 329 ch 87, 139, 220, 224, 253, 295
7e30cf19-703c-5ee5-97e4-461618a42d06 | note | Frequency / When? - During installation, every 200 mm layers at 5 m intervals for all trenches in carriageway above main and connections
286015b9-b11d-523a-9679-f9aa0d0c20c1 | note | Inspection / Test Method - Clegg test
7e68e563-4d3c-5c16-a411-b4f547d72a3c | note | Records / evidence, WCL form - Sign This ITP, Clegg Test Result Sheet
8ad1713b-c2ed-5115-8876-5a4bd50f05a9 | note | Standard - ICC STANDARD SPECIFICATIONS
1fb23858-3ec3-5526-9cd4-16ae17d4f2bc | note | Print, sign and date: Wilson - YES
0983be0a-742d-586d-8eb5-a924e1e7fd12 | note | Print, sign and date: ICC - YES
2b526035-ab37-4f67-844c-d8ebd3544ee5 | signoff | HOLD POINT
99362bac-821c-4638-be52-1d39e8b3ec40 | checkpoint | 36 - D2.11.5
15d5c8ad-4f4e-5063-a397-ef387f18dc67 | note | Inspection / Test Point - Subbase (AP65) compaction
ff57555d-74c3-53e0-829d-5615c4430299 | note | ACTION (W, M, H) - H
76dee525-cd40-53a0-a5f9-7f6cc5de4733 | note | Activity by - WCL / Lab ICC
d0ac3989-fe23-501b-a0df-6c2e70dc65df | note | Conformance Criteria (What's Required) - 95% compaction rate
4782f9fd-53fe-5117-a95c-93f324032bc6 | note | ○ It is not required to complete NDM testing on connections.
1c4d0038-e0dd-5ab1-8850-451c8365f258 | note | Quantity - Culvert + ch 240 - 329 = 95 m
ab0a8b41-7cd8-598f-b689-16b008408807 | note | Frequency / When? - At pipe laying commencement and reconfirmed at 120m intervals for open trench every 200 mm layers
cafd17e2-85dd-584c-8d8d-064d6ed07579 | note | Inspection / Test Method - NDM test (direct transmission)
a3bac81f-d8a5-5c56-ba0c-6cdaaee95673 | note | Records / evidence, WCL form - Sign This ITP, NDM Test Result Sheet
4865f7da-7bc9-5587-9145-556e7acf7660 | note | Standard - ICC STANDARD SPECIFICATIONS
a77f2205-be1f-5b66-95b9-be1c4e451e1e | note | Print, sign and date: Wilson - YES
59509228-6c3d-5415-9bfe-f2483783d172 | note | Print, sign and date: ICC - YES
712ec10c-1df8-4111-89fb-3d852512bbf6 | signoff | HOLD POINT
bd43dfa5-4f53-4f78-83e3-c31634cfcfaf | checkpoint | 37 - D2.7
8d47a946-2eed-51b9-b9a6-9b95886ebe2c | note | Inspection / Test Point - Basecourse (AP40) compaction
77a3900f-027c-59f2-9be3-1082a176ffe8 | note | ACTION (W, M, H) - H
383b1ef1-6eb3-52ae-bd27-90c7a076df28 | note | Activity by - WCL / Lab ICC
63e208e8-4cc1-56b6-9dc2-40198c326c14 | note | Conformance Criteria (What's Required) - 98% compaction rate
0c257df3-4bd4-54a7-8c0a-b46ecddcb582 | note | ○ It is not required to complete NDM testing on connections
ef9b1c43-657d-50ef-942f-69ad25e7bff9 | note | Quantity - Culvert + ch 240 - 329 = 95 m
2eb3f66f-cace-5615-ab54-997df222640d | note | Frequency / When? - 1 / 20 m of trench including one test at the start and end of the trench
d6b92e65-9160-5ef2-bd96-e61b58593ae7 | note | Inspection / Test Method - NDM test
d7ffe1aa-ea0c-537a-b407-30ea74bc1895 | note | Records / evidence, WCL form - Sign This ITP, NDM Test Result Sheet
00e11f53-14c2-5f87-85bb-e9c3e4a1e1f9 | note | Standard - ICC STANDARD SPECIFICATIONS
850db269-8894-5eef-98ea-2d572d056a3f | note | Print, sign and date: Wilson - YES
434ae73f-625f-5280-959b-0ecd170001b5 | note | Print, sign and date: ICC - YES
4e03c168-cf71-48e2-aabb-f766354a4091 | signoff | HOLD POINT
e56f31b2-78b9-4ed7-a44f-056ac4b4ddae | checkpoint | 38 - D2.8.3
9560d720-8fe3-5248-8274-3f20c991a244 | note | Inspection / Test Point - Trench reinstatement - marking out saw cutting
bce64201-d627-56f4-a72d-9f6d695bb4ae | note | ACTION (W, M, H) - H
a02ee454-b654-5bb3-9f90-95dd27ee464e | note | Activity by - ICC
25cef921-b2ec-514e-b694-634f5ba0aed0 | note | Conformance Criteria (What's Required) - Engineers rep to mark out saw cutting required (overcuts)
3156f03c-f3c5-56e4-bd80-7b9e3603f1cf | note | Quantity - 6 m: Marama
d3e14116-8776-535d-b0f2-1f80ce9970e6 | note | ○ 79 m: Kori
01bebcee-4475-594e-b354-f6c9d7c69650 | note | Frequency / When? - Prior to sealing
37441cd7-b4c2-50fa-adf3-c29a8b2ad02e | note | Inspection / Test Method - Visual inspection, measurements (1 m rule)
ea71c88a-b588-5937-9807-633d4fcd9657 | note | Records / evidence, WCL form - Sign This ITP
a15d74f7-949c-597c-b3a9-ab6dd64935f3 | note | Standard - ICC STANDARD SPECIFICATIONS National Code of Practise for Utility Operators' Access to Transport Corridors
001fbefa-e31e-5fe2-896a-6b8ae588905b | note | Print, sign and date: Wilson - YES
3f5f2494-7006-529b-aefc-862eb2633a3f | note | Print, sign and date: ICC - YES
ec9efe86-7739-4755-8940-e2568e0b8eb6 | signoff | HOLD POINT
6d6d559a-cf2a-47c6-b644-6f8999a38dd5 | checkpoint | 39 - D2.7.7.2
58092f74-3136-5649-b11e-65f7e9130a64 | note | Inspection / Test Point - Basecourse (AP40) geometry
8b1c5829-0149-5582-8702-12dfed6ebc5a | note | ACTION (W, M, H) - H
8ea82875-e7dd-59c6-a614-f5a6c7817d7d | note | Activity by - WCL, ICC
b0a0214f-e6f2-53ec-a663-58a477924d15 | note | Conformance Criteria (What's Required) - -5 mm +15 mm
bcdf426f-cb4a-553f-a3fe-666d9ead836c | note | ○ h = 45-65 mm (carriageways) h = 25-45 mm (footpath)
49761595-0a45-545f-a5a3-cd0652f24d23 | note | Quantity - Culvert + ch 240 - 319 = 85 m +5 cross
c146b1b7-55cc-5d78-ae16-e9cf839fb81a | note | Frequency / When? - Prior to sealing
3984826f-4e4b-5ccb-9730-74b417a39fe6 | note | Inspection / Test Method - Visual inspection String line / straight edge inspection
a2f6b27a-cc49-5c28-84e8-2b09e735c78d | note | Records / evidence, WCL form - Sign This ITP, Pre seal inspection record (FM-114)
4afbb11c-c49f-58e2-b05f-0ace4756a85d | note | Standard - ICC STANDARD SPECIFICATIONS NZTA B/2
f41731cd-ed5f-5d7f-875e-c7109f008a97 | note | Print, sign and date: Wilson - YES
677e62ec-5db2-5c60-b64a-a797e6fa5d98 | note | Print, sign and date: ICC - YES
843df76c-3739-446d-bbcc-6b029fe986e3 | signoff | HOLD POINT
e0729ccd-2adf-41d3-aa27-57d8f218d235 | checkpoint | 40 - D11.4.3
d78caaf9-8162-5702-bbec-c059780b8723 | note | Inspection / Test Point - Membrane Seal
d4e548da-00b0-59a3-bd78-64fa5ce29b03 | note | ACTION (W, M, H) - H
07c14745-d0cd-5afb-8045-241f53a29f8a | note | Activity by - WCL, ICC
06a877ff-d013-5a4d-a84a-f9b9df58e829 | note | Conformance Criteria (What's Required) - Residual bitumen application rate ≥ 1.5 l/m2
c3e3134a-9928-54ce-b08c-28a5345825f8 | note | Quantity - Culvert + ch 240 - 319 = 85 m
173f9b14-4990-5669-97ed-bc59ab7803fc | note | Frequency / When? - Prior to asphalting
6b0aef45-710a-5bf0-a07c-f8991023d580 | note | Inspection / Test Method - Visual inspection
ab4a5288-5217-518b-9185-3abe775f77ce | note | Records / evidence, WCL form - Sign This ITP, Delivery docket
b6a1b461-e542-5b87-8355-35ca36b536f0 | note | Standard - ICC STANDARD SPECIFICATIONS
92eefb19-88b3-5037-bb31-9648920a464b | note | Print, sign and date: Wilson - YES
bdb4ce38-53e3-5d84-b98d-9de9f9dad4be | note | Print, sign and date: ICC - YES
8225b0b8-07e0-4122-b129-a0765387bb51 | signoff | HOLD POINT
c6a86e58-c725-4e6e-89a9-8eea53eb0118 | checkpoint | 41 - D12.5
02d2b1c9-1bf7-5974-9be5-bf6132ada8f7 | note | Inspection / Test Point - Asphalt paving geometry
85ed1db4-6ab9-50a6-b5c2-deec24af1781 | note | ACTION (W, M, H) - H
5f2f9f52-46d3-5ce6-8de4-072fa4223454 | note | Activity by - WCL, ICC
c5e2eec3-e5b7-57b6-bebc-402a3afc47fe | note | Conformance Criteria (What's Required) - 5 mm from a 3 m straight edge laid longitudinally
5b22b3af-ccb0-5bc7-8f7d-41be708202b8 | note | ○ 5 mm from a 1 m straight edge laid transversely
6e2b1f63-03be-5837-a63e-ce7fc0151378 | note | Quantity - 85 m
7a56318f-d962-5d44-8266-092321f5b8d4 | note | Frequency / When? - 1 / finished surface
ca9b8b07-afff-5d77-9352-fb37b19ef4c8 | note | Inspection / Test Method - Post seal surface inspection
0c4409dd-e817-5057-a8e3-95043a8fbdd8 | note | Records / evidence, WCL form - Sign This ITP
07a58daf-934d-5c80-ab47-0ddec36c9ac6 | note | Standard - ICC STANDARD SPECIFICATIONS
811aebd5-e972-5ae9-bfd4-41ab5aac20cc | note | Print, sign and date: Wilson - YES
361fa848-6c78-5f64-a641-8f8bf915c02d | note | Print, sign and date: ICC - YES
0f3c6800-452f-4e2d-a22c-4a2ce608e252 | signoff | HOLD POINT
8a4d73b7-580b-4b8e-88b5-7147a151fc8d | checkpoint | 42 - D2.8.3, D12.3.1
4dc2c181-4f2c-5a16-9fdd-0eae54b97584 | note | Inspection / Test Point - Asphalt paving material
afe5abf6-bbbb-5921-a449-f18c7262d14d | note | ACTION (W, M, H) - W
ce95b76e-27e4-5d02-9fe1-9204b5d2231a | note | Activity by - WCL, ICC
fef5099a-a727-5051-ad39-57d385ad713e | note | Conformance Criteria (What's Required) - DG10 (carriageways)
33a0bdd7-b732-5f98-8c21-a8f62eb11b8b | note | Quantity - 13 t
3b6540e0-7bd6-5578-800f-cfdd51a8798e | note | Inspection / Test Method - Document
2e42117f-bd86-503b-92ac-c1a24b92b146 | note | Records / evidence, WCL form - Sign This ITP, Delivery docket
951063ae-ec27-51ca-aa37-284661335375 | note | Standard - ICC STANDARD SPECIFICATIONS
b69c7262-401b-5390-a2f8-6a5409f18c41 | note | Print, sign and date: Wilson - YES
61ab6511-28eb-5573-adf9-54e374c3dc1c | note | Print, sign and date: ICC - YES
40907c77-7aca-4398-905d-ba44fa41a749 | checkpoint | 43
4daf013f-a2b3-5990-9189-f0b7bb131af5 | note | Inspection / Test Point - Road markings
508c95cb-2c9c-5115-bb2f-f04bf103f28b | note | ACTION (W, M, H) - W
07941cf3-9da4-59e1-990b-c6eb722de1ef | note | Activity by - WCL, ICC
ea906077-2c9a-5448-b2c8-6a0b504f753b | note | Conformance Criteria (What's Required) - Reinstatement of the existing markings
4ff8a323-36d2-5865-a7e9-fb9f5d986222 | note | Frequency / When? - 1 / finished surface
9b099661-257e-5013-b89f-b8ba9051b22e | note | Inspection / Test Method - Post seal surface inspection
4dd3e46d-dc85-5811-b76f-768a1fcede47 | note | Records / evidence, WCL form - Sign This ITP
388f270a-eb0b-5c55-b246-9739d747ea63 | note | Standard - ICC STANDARD SPECIFICATIONS
2d46107d-6601-5197-8a49-0b7b2d04e315 | note | Print, sign and date: Wilson - N/A
b571edf8-6f8f-5260-85bf-a479b78e361c | note | Print, sign and date: ICC - N/A
7937b3a8-6c93-474a-b235-1f48ae50843f | section | Completion
d8887458-0e98-4045-af16-304667f0bb33 | checkpoint | 44 - D17
5f3a3f77-19ef-556c-ae26-0bb616aa7ab6 | note | Inspection / Test Point - As-built information
845649ca-e99d-5610-bd60-e33518c7826d | note | ACTION (W, M, H) - H
67b5193f-1369-5613-afe3-5b92c2cbee5c | note | Activity by - WCL
07743bea-1b47-5d58-b45e-fc190f86a42b | note | Conformance Criteria (What's Required) - Encountered Services Record Sheet Detailed Water Connection Sheet
ff2bccdc-e68b-505d-8f3d-4a23c049ea24 | note | ○ As-built drawings as per D17
c6a4efcd-a4ba-59c7-b9d7-82fa2d48f4f9 | note | Frequency / When? - Following/during completion of works
41694192-ae83-54e0-a535-68428f8ef52f | note | Inspection / Test Method - Document
4fd0e133-cb53-5cd9-aa91-14e14f26b6f9 | note | Records / evidence, WCL form - Sign This ITP DWCS, ESRS, As-built
f078e198-c5f2-56fb-951b-34db47839233 | note | Standard - ICC STANDARD SPECIFICATIONS
0276c185-5fb0-581f-bf75-a08fef437c7e | note | Print, sign and date: Wilson - YES
7468b8a1-5d01-5c23-8750-d528b4b25e7e | note | Print, sign and date: ICC - YES
da7cf2f2-c99a-439a-be3c-42616b28a496 | signoff | HOLD POINT
d452a859-b677-4d32-b80e-e4a7cd7fdd8c | checkpoint | 45
8f1b912a-4114-584d-a967-58360a6dce3c | note | Inspection / Test Point - Site walkover
8f038e97-ae8f-51be-9b45-54ac92fd841a | note | ACTION (W, M, H) - H
30de1a66-b11f-51e7-ae41-819cb7cbc863 | note | Activity by - WCL, ICC
14f8037d-57f3-52c0-b7cc-62821dfbc15c | note | Conformance Criteria (What's Required) - Snag list to be compiled, and completed
479681d5-d43c-5a1f-bb1e-ce78ad2a057d | note | Frequency / When? - At Completion
204f93b5-1f62-514b-b0eb-2e1bbc3c12fc | note | Inspection / Test Method - Review
ace9152a-9e68-5ef8-b2ef-6be4b00694cb | note | Records / evidence, WCL form - Sign This ITP SNAG List
61b6d5de-9f55-53dd-aa22-1b3e2e16601a | note | Print, sign and date: Wilson - YES
9357d877-563b-5182-831c-bca8e5a333a7 | note | Print, sign and date: ICC - YES
cdc02150-4876-4255-b790-06a7b9474ba9 | signoff | HOLD POINT
892ee077-5d5a-4c2f-b0c9-451ee4e6f41e | checkpoint | Signoff
23c9a425-4398-5e76-8e03-1d875d9acfad | note | Wilsons Engineer
e2b91b30-d7ad-5599-ac77-7f2809c7a73c | note | Signed By : Norbert Jacsek
533f52c5-843c-5213-9e52-d4c926fce5e2 | note | Wilsons Contract Manager
bb0f01af-1425-5ba3-a144-e6dfc73b5083 | note | Accepted By : Hamish Lindsay
923bc2f2-c7ca-5dfc-9dc8-d3e20e1310be | note | ICC Engineers Representative
3315ca70-3c40-582f-9ca0-01fdd566d75d | note | Accepted By : Tom Andersen
c54865e7-6be3-4c12-b7da-0a1056968157 | signoff | Signature: