## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Bay Road FS | itp
section | Contract
checkpoint | 1 - D1.3
label | Inspection / Test Point - Site Management Plan (QEHS, SSST, KSA)
label | ACTION (W, M, H) - H
label | Activity by - WCL
label | Conformance Criteria (What's Required) - Ensure Quality, Environment, Health & Safety Management Systems Plan
label | ○ Site Specific Safety Plan and Key Step Analysis are approved.
label | ○ Living document to be adjusted and updated as required. A copy of QEHS plan, SSSP and KSA to be on site at all times.
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Submission (NTE)
label | Records / evidence, WCL form - Sign This ITP, LN-01, FM-83, FM-69
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 2 - D1.18
label | Inspection / Test Point - TMP
label | ACTION (W, M, H) - H
label | Activity by - WCL
label | Conformance Criteria (What's Required) - traffic management plan to be submitted and approved by Road Controlling Authority
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Sumission (NTE)
label | Records / evidence, WCL form - Sign This ITP, TMP
label | Standard - Code of practice for temporary traffic management (CoPTTM)
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 3 - D1.4
label | Inspection / Test Point - Works Access Permit
label | ACTION (W, M, H) - H
label | Activity by - WCL
label | Conformance Criteria (What's Required) - TMP and Corridor Access Request to be sumbitted on myWorksites
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Document
label | Records / evidence, WCL form - Sign This ITP, WAP
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 4 -
label | Inspection / Test Point - Permit to Enter
label | ACTION (W, M, H) - H
label | Activity by - WCL
label | Conformance Criteria (What's Required) - KiwiRail
label | Frequency / When? - Prior to any work near the railway area
label | Inspection / Test Method - Document
label | Records / evidence, WCL form - Permit to Enter
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
section | Material
checkpoint | 5 - D1.14
label | Inspection / Test Point - Client start-up meeting
label | ACTION (W, M, H) - H
label | Activity by - ICC, WCL
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Document
label | Records / evidence, WCL form - Sign This ITP, MoM
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 6 - D2.4.2
label | Inspection / Test Point - Bedding material
label | ACTION (W, M, H) - W
label | Activity by - Lab
label | Conformance Criteria (What's Required) - Material to comply with contract specification
label | Quantity - 650 m3
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Lab report
label | Records / evidence, WCL form - Grading Results
label | Standard - ICC STANDARD SPECIFICATIONS G3 of AS/NZS 2566.2
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 7 - D2.4.3, D1.29.3
label | Inspection / Test Point - Sub Base Aggregate AP65
label | ACTION (W, M, H) - W
label | Activity by - Lab
label | Conformance Criteria (What's Required) - Materials to comply with contract specification
label | Quantity - 2500 m3
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Lab report
label | Records / evidence, WCL form - MDD and Grading Results
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 8 - D1.29.4
label | Inspection / Test Point - Crushed Basecource Aggregate M/4 AP40
label | ACTION (W, M, H) - W
label | Activity by - Lab
label | Conformance Criteria (What's Required) - Materials to comply with contract specification
label | Quantity - 250 m3
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Lab report
label | Records / evidence, WCL form - MDD and Grading Results
label | Standard - ICC STANDARD SPECIFICATIONS NZTA M/4
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 9 - C1.4, D2.4.1
label | Inspection / Test Point - Pipe material (F25402 - F25403)
label | ACTION (W, M, H) - M
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - DN300 uPVC SN16 RESTRAIN
label | Quantity - 30 m
label | Frequency / When? - 1 / delivery
label | ○ WCL is to inspect all deliveries
label | ○ ICC to inspect deliveries as required
label | Inspection / Test Method - Visual inspection
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS AS/NZS 1260:2017
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 10 - C1.4, D2.4.1
label | Inspection / Test Point - Pipe material (F25403 - F25406)
label | ACTION (W, M, H) - M
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - DN300 uPVC SN8
label | Quantity - 328 m
label | Frequency / When? - 1 / delivery
label | ○ WCL is to inspect all deliveries
label | ○ ICC to inspect deliveries as required
label | Inspection / Test Method - Visual inspection
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS AS/NZS 1260:2017
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 11 - C1.4, D2.4.1
label | Inspection / Test Point - Pipe material (F25406 - F25410)
label | ACTION (W, M, H) - M
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - DN225 uPVC SN8
label | Quantity - 378 m
label | Frequency / When? - 1 / delivery
label | ○ WCL is to inspect all deliveries
label | ○ ICC to inspect deliveries as required
label | Inspection / Test Method - Visual inspection
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS AS/NZS 1260:2017
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 12 - D4.3
label | Inspection / Test Point - Pipe material lateral
label | ACTION (W, M, H) - M
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - DN100 uPVC SN6
label | Quantity - 780 m
label | Frequency / When? - 1 / delivery
label | ○ WCL is to inspect all deliveries
label | ○ ICC to inspect deliveries as required
label | Inspection / Test Method - Visual inspection
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS AS/NZS 1260:2017
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 13 - D18.2
label | Inspection / Test Point - Precast manhole elements
label | ACTION (W, M, H) - M
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - min. 25 Mpa
label | ○ 1050 mm nominal diameter
label | ○ 150 mm lid (HO loading)
label | Quantity - 8 MH
label | Frequency / When? - 1 / delivery
label | ○ WCL is to inspect all deliveries
label | ○ ICC to inspect deliveries as required
label | Inspection / Test Method - Visual inspection
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS NZS 4058, NZS 3107
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 14 - D15.2
label | Inspection / Test Point - Manhole covers
label | ACTION (W, M, H) - M
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - Heavy Duty Ductile iron, HN-HO-72 hinged, 600 mm clear opening, gas seal
label | Quantity - 8
label | Frequency / When? - 1 / delivery
label | ○ WCL is to inspect all deliveries
label | ○ ICC to inspect deliveries as required
label | Inspection / Test Method - Visual inspection
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 15 - D15.2, Fig. D9
label | Inspection / Test Point - Cleaning eye cover
label | ACTION (W, M, H) - M
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - Warrior Surface box clear opening of 380mm x 224mm
label | Quantity - 1
label | Frequency / When? - 1 / delivery
label | ○ WCL is to inspect all deliveries
label | ○ ICC to inspect deliveries as required
label | Inspection / Test Method - Visual inspection
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 16 - D2.8.3, D12.3.1
label | Inspection / Test Point - Asphalt (carriageways)
label | ACTION (W, M, H) - W
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - DG10
label | Quantity - 730 m (main), 700 m (lateral)
label | Frequency / When? - 1 / delivery
label | ○ WCL is to inspect all deliveries
label | Inspection / Test Method - Document
label | Records / evidence, WCL form - Sign This ITP, Delivery docket
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 17 - D13.3.4
label | Inspection / Test Point - Asphalt (footpath)
label | ACTION (W, M, H) - W
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - mix DG7, 180/200 penetration grade bitumen
label | Quantity - 58 x 1 m
label | Frequency / When? - 1 / delivery
label | ○ WCL is to inspect all deliveries
label | Inspection / Test Method - Document
label | Records / evidence, WCL form - Sign This ITP, Delivery docket
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
section | Pre Construction
checkpoint | 18 - D1.5
label | Inspection / Test Point - Pre-work site inspection
label | ACTION (W, M, H) - H
label | Activity by - WCL
label | Conformance Criteria (What's Required) - Video or photos near the construction zone to determine their pre construction condition. (landowners property)
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Inspection Document
label | Records / evidence, WCL form - Sign This ITP, Video, Photo
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 19 - D1.18
label | Inspection / Test Point - Temporary traffic management
label | ACTION (W, M, H) - H
label | Activity by - WCL
label | Conformance Criteria (What's Required) - Signs set up as per TMP, with a copy on site with STMS. TMP monitored for practicality. If changes are required these are to be agreed upon with the engineer.
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Visual inspection Document
label | Records / evidence, WCL form - Sign This ITP, On-site record
label | Standard - ICC STANDARD SPECIFICATIONS CoPTTM
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 20 - D2.7.1
label | Inspection / Test Point - Set out
label | ACTION (W, M, H) - W
label | Activity by - ICC, WCL
label | Conformance Criteria (What's Required) - Mark out of alignment for mains and laterals
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Surface marking
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 21 - D1.8
label | Inspection / Test Point - Protection and identification of other Services
label | ACTION (W, M, H) - H
label | Activity by - WCL, asset owners
label | Conformance Criteria (What's Required) - Mark out on site of all services. Services to be potholed for as per Wilsons company policy
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Surface marking, Visual inspection
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS, Wilson's prior to excavate policy
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 22 - D1.11, D9.5
label | Inspection / Test Point - Notification to residents and businesses
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - Letter drop / business visits
label | Frequency / When? - Prior to commencement (min. two working days prior to access restriction)
label | Inspection / Test Method - Document delivered
label | Records / evidence, WCL form - Sign This ITP Notification letter
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 23 - D1.32.7
label | Inspection / Test Point - Railway survey
label | ACTION (W, M, H) - M
label | Activity by - WCL, SUR
label | Conformance Criteria (What's Required) - survey monitoring for track settlement: 1 m increments along the track, 20 m either side of the work centreline, / 3 m of progress of the pipe’s installation under the track.
label | Frequency / When? - Before and after the works
label | Inspection / Test Method - Surveying
label | Records / evidence, WCL form - Survey record
label | Standard - KiwiRail Civil Specification, Installation of Utility Structures on Railway Land (C-SP-AE-64322)
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 24 - C1.8, D1.6
label | Inspection / Test Point - NZ Heritage induction
label | ACTION (W, M, H) - H
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - Contractor briefing is to be completed by all personnel working on the project
label | Frequency / When? - 48 hours prior to any work
label | Inspection / Test Method - Induction
label | Records / evidence, WCL form - induction record
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
section | Foul Sewer renewal
checkpoint | 25 - D2.7.2
label | Inspection / Test Point - Excavation
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - The finished excavation surface shall be a smooth consistent surface at the appropriate grade. No tolerance on the excavation base level that reduces the depth of the bedding will be allowed.
label | Quantity - 706 m - main, 780 m- lateral
label | Frequency / When? - continuous
label | Inspection / Test Method - Visual inspection, Levelling
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 26 -
label | Inspection / Test Point - Removal of existing pipelines and manholes
label | ACTION (W, M, H) - W
label | Activity by - WCL
label | Conformance Criteria (What's Required) - Excavation will include the removal of existing redundant mains, manholes and property connections
label | Quantity - 273 m D300
label | ○ 378 m D225
label | ○ 780 m D100
label | ○ 8 manholes
label | Frequency / When? - during excavation
label | Inspection / Test Method - Visual inspection
label | Records / evidence, WCL form - Sign this ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 27 - C1.11
label | Inspection / Test Point - Disposal of Surplus Materials
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - The Contractor shall dispose of any surplus materials in a safe and sustainable manner
label | Quantity - 3500 m3
label | Frequency / When? - Continuous
label | Inspection / Test Method - Document
label | Records / evidence, WCL form - Sign this ITP, Disposal register
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 28 - D2.7.2
label | Inspection / Test Point - Subgrade inspection
label | ACTION (W, M, H) - M
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - To determine if improvements are required
label | Quantity - 706 m
label | Frequency / When? - Prior to placement of bedding
label | Inspection / Test Method - Visual inspection
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 29 - D2.4.2
label | Inspection / Test Point - Free draining material
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - pea gravel wrapped in a suitable geotextile up to 100 mm over the trench bed
label | Quantity - max 706 m
label | Frequency / When? - Continous, in accordance with observed groundwater conditions
label | Inspection / Test Method - Secific approval should be given by the Engineer
label | Records / evidence, WCL form - NTE, NTC
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 30 - D2.7.3, D2.5.1
label | Inspection / Test Point - Pipe installation open trench (main: F25402 - F25410)
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - +/- 30mm (horizontal)
label | ○ +/- 5mm (vertical)
label | ○ joints as per manufacturers specifications (lubrication, chamfering, whiteness marking, etc)
label | Quantity - 651 m
label | Frequency / When? - Continous (pipe laser)
label | ○ 1/20 m (independent optical level)
label | Inspection / Test Method - Using calibrated pipe laser, Optical levelling
label | Records / evidence, WCL form - Sign this ITP, Leveling record
label | Standard - ICC STANDARD SPECIFICATIONS manufacturers specifications.
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 31 - D4.4, Fig. D3, Fig. D4, Fig. D5
label | Inspection / Test Point - Pipe installation (lateral)
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - grade: min 1:100 (with laser)
label | ○ min 1:60 (with dumpy level)
label | ○ Connection to the main: 45° reducing wye
label | ○ Concrete haunching: 25 MPa
label | ○ Connection at boundary: slip coupler/plumbqwik
label | Quantity - 58 lateral, 780 m
label | Frequency / When? - Continous
label | Inspection / Test Method - Measurement Document
label | Records / evidence, WCL form - Sign this ITP, Detailed Drainage Connection Sheet
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 32 - D2.7.6
label | Inspection / Test Point - Bedding - DN300 main (F25402 - F25406)
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - lb (depth below): min 100 mm
label | ○ lc (width beside): min 200 mm
label | ○ lo (depth above): min 150 mm
label | ○ compacted layers not exceeding 1/3 of the pipe OD
label | Quantity - 328 m
label | Frequency / When? - continuous
label | Inspection / Test Method - Measurement Levelling
label | Records / evidence, WCL form - Sign this ITP
label | Standard - AS/NZS 2566 table 4.2.
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 33 - D2.7.6
label | Inspection / Test Point - Bedding - DN225 main (F25406 - F25410)
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - lb (depth below): min 100 mm
label | ○ lc (width beside): min 150 mm
label | ○ lo (depth above): min 150 mm
label | ○ compacted layers not exceeding 1/3 of the pipe OD
label | Quantity - 378 m
label | Frequency / When? - continuous
label | Inspection / Test Method - Measurement Levelling
label | Records / evidence, WCL form - Sign this ITP
label | Standard - AS/NZS 2566 table 4.2.
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 34 - D2.7.6
label | Inspection / Test Point - Bedding (lateral)
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - lb (depth below): min 75 mm
label | ○ lc (width beside): min 100 mm
label | ○ lo (depth above): min 100 mm
label | ○ compacted layers not exceeding ⅓ of the pipe OD
label | Quantity - 780
label | Frequency / When? - continuous
label | Inspection / Test Method - Measurement Levelling
label | Records / evidence, WCL form - Sign this ITP
label | Standard - AS/NZS 2566 table 4.2.
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 35 - D18, Fig. D12
label | Inspection / Test Point - Manhole (D1050)
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - neck depth ≤ 315 mm
label | ○ in-situ concrete packing
label | ○ flexible joint located within 1 metre
label | Quantity - 8
label | Frequency / When? - 1 / manhole
label | Inspection / Test Method - Measurement Levelling Document
label | Records / evidence, WCL form - Sign this ITP, Manhole Inspection Sheet
label | Standard - NZS 3109:1997
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 36 - D18, Fig. D7
label | Inspection / Test Point - Cleaning eye
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - as per Fig D7
label | Quantity - 1
label | Frequency / When? - 1 / installation
label | Inspection / Test Method - Visual inspection Measurement
label | Records / evidence, WCL form - Sign this ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 37 - Fig. D13 - D16
label | Inspection / Test Point - Service cover (manhole)
label | ACTION (W, M, H) - W
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - Cover levels to be adjusted to existing surface levels (+10mm, -0 mm)
label | ○ 25 Mpa concrete packing
label | Quantity - 8
label | Frequency / When? - before surface reinstatement
label | Inspection / Test Method - Visual inspection Measurement
label | Records / evidence, WCL form - Sign this ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 38 - D15, Fig. D7
label | Inspection / Test Point - Service cover (cleaning eye)
label | ACTION (W, M, H) - W
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - Cover levels to be adjusted to existing surface levels (+10mm, -0 mm) perpendicular / parallel the road alignment.
label | Quantity - 1
label | Frequency / When? - before surface reinstatement
label | Inspection / Test Method - Visual inspection Measurement
label | Records / evidence, WCL form - Sign this ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 39 - D2.9.2
label | Inspection / Test Point - Pressure test
label | ACTION (W, M, H) - H
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - (Main + N side laterals) + (S side laterals)
label | ○ Test length: as per table 6.1 AS/NZS 2566.2
label | ○ Pressure: 25kPa
label | ○ Pressure loss < 7Kpa
label | Quantity - 8 section
label | ○ 35 S side lat
label | Frequency / When? - 1 / section (manhole to manhole)
label | ○ 1 / S side lateral)
label | Inspection / Test Method - Low pressure air test
label | Records / evidence, WCL form - Sign This ITP, Pressure test report, FM-119
label | Standard - AS/NZS 2566:2:2002 6.4.2
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 40 - D2.9.3
label | Inspection / Test Point - CCTV Inspection and Cleaning
label | ACTION (W, M, H) - H
label | Activity by - WCL
label | Conformance Criteria (What's Required) - to confirm that the lines are free from debris and have no defects
label | Quantity - 736 m (main)
label | Frequency / When? - prior to the final surface reinstatement
label | Inspection / Test Method - CCTV inspection
label | Records / evidence, WCL form - Sign this ITP, CCTV survey
label | Standard - New Zealand Pipe Inspection Manual AS/NZS 2566:2
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
section | Surface reinstatement
checkpoint | 41 - D13
label | Inspection / Test Point - Landscaping
label | ACTION (W, M, H) - W
label | Activity by - WCL
label | Conformance Criteria (What's Required) - The final surface in the berm area should match the existing levels
label | Quantity - 58 laterals
label | Frequency / When? - following lateral installation
label | Inspection / Test Method - Visual inspection Levelling
label | Records / evidence, WCL form - Sign this ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 42 - D13.7
label | Inspection / Test Point - Grass seeding
label | ACTION (W, M, H) - W
label | Activity by - WCL
label | Conformance Criteria (What's Required) - approved seed mixture, 35 g/m2
label | Quantity - 58 laterals
label | Frequency / When? - following landscaping
label | Inspection / Test Method - Visual inspection
label | Records / evidence, WCL form - Sign this ITP, Blending docket
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 43 - D2.7.7
label | Inspection / Test Point - Subbase (AP65) compaction
label | ACTION (W, M, H) - H
label | Activity by - WCL
label | Conformance Criteria (What's Required) - Carriageway:
label | ○ 0.3 - 1.5 m deep: min 35 CIV
label | ○ > 1.5 m deep : min 25 CIV
label | Quantity - 706 m (main), 700 m (lateral)
label | Frequency / When? - During installation, every 200 mm layers at 6 m intervals for all trenches in carriageway above main and connections
label | Inspection / Test Method - Clegg test
label | Records / evidence, WCL form - Sign This ITP, Clegg Test Result Sheet
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 44 - D2.11.5
label | Inspection / Test Point - Subbase (AP65) compaction
label | ACTION (W, M, H) - H
label | Activity by - WCL / Lab ICC
label | Conformance Criteria (What's Required) - 95% compaction rate
label | ○ It is not required to complete NDM testing on connections
label | Quantity - 706 m (main)
label | Frequency / When? - At pipe laying commencement and reconfirmed at 120 m intervals for open trench every 200 mm layers
label | Inspection / Test Method - NDM test (direct transmission)
label | Records / evidence, WCL form - Sign This ITP, NDM Test Result Sheet
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 45 - D2.7
label | Inspection / Test Point - Basecourse (AP40) compaction
label | ACTION (W, M, H) - H
label | Activity by - WCL / Lab ICC
label | Conformance Criteria (What's Required) - minimum depth of 150 mm
label | ○ 98% compaction rate
label | ○ It is not required to complete NDM testing on connections
label | Quantity - 706 m (main)
label | Frequency / When? - 1 / 20 m of trench including one test at the start and end of the trench
label | Inspection / Test Method - NDM test
label | Records / evidence, WCL form - Sign This ITP, NDM Test Result Sheet
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 46 - D2.8.3
label | Inspection / Test Point - Trench reinstatement - marking out saw cutting
label | ACTION (W, M, H) - H
label | Activity by - ICC
label | Conformance Criteria (What's Required) - Engineers rep to mark out saw cutting required
label | ○ 150 mm overcuts
label | ○ 1 m rule
label | Quantity - 706 m (main)
label | ○ 700 m (lateral)
label | ○ 58x1 m (footp)
label | Frequency / When? - Prior to sealing
label | Inspection / Test Method - Visual inspection, measurements (1 m rule)
label | Records / evidence, WCL form - Sign This ITP, Pre seal inspection record (FM-114)
label | Standard - ICC STANDARD SPECIFICATIONS National Code of Practise for Utility Operators' Access to Transport Corridors
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 47 - D2.7.7.2
label | Inspection / Test Point - Basecourse (AP40) geometry
label | ACTION (W, M, H) - H
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - -5 mm +15 mm
label | ○ h = 45-65 mm (carriageways)
label | ○ h = 25-45 mm (footpath)
label | Quantity - 730 m (main)
label | ○ 700 m (lateral)
label | ○ 58x1 m (footp)
label | Frequency / When? - Prior to sealing
label | Inspection / Test Method - Visual inspection String line / straight edge inspection
label | Records / evidence, WCL form - Sign This ITP, Pre seal inspection record (FM-114)
label | Standard - ICC STANDARD SPECIFICATIONS NZTA B/2
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 48 - D11.4.3
label | Inspection / Test Point - Membrane Seal
label | ACTION (W, M, H) - H
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - Residual bitumen application rate:
label | ○ 2.0 l/m2 +/- 10%. (spray truck)
label | ○ ≥ 1.5 l/m2 (hand operated sprayer bar)
label | Quantity - 706 m (main), 700 m (lateral)
label | Frequency / When? - Prior to asphalting
label | Inspection / Test Method - Visual inspection
label | Records / evidence, WCL form - Sign This ITP, Delivery docket
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 49 - D12.5
label | Inspection / Test Point - Asphalt paving (carriageway)
label | ACTION (W, M, H) - H
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - trenches wider than 1.5 m shall be paver-laid
label | ○ 5 mm from a 3 m straight edge laid longitudinally
label | ○ 5 mm from a 1 m straight edge laid transversely
label | ○ lips ≤ 5 mm (where it joins existing seal)
label | Quantity - 730 m (main), 700 m (lateral)
label | Frequency / When? - 1 / finished surface
label | Inspection / Test Method - Post seal surface inspection
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 50 - D13.6
label | Inspection / Test Point - Asphalt paving (footpath)
label | ACTION (W, M, H) - H
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - 30 mm Footpaths and Surfaced Frontages
label | ○ 30 mm Residential Crossing
label | ○ 50 mm Heavy Duty Crossing
label | ○ 5mm above kerb edges, and flush with property vehicle accessways
label | ○ The gap under a 3m straight-edge placed longitudinally shall not exceed 5mm
label | ○ lips ≤ 3mm
label | Quantity - 58x1 m
label | Frequency / When? - 1 / finished surface
label | Inspection / Test Method - Visual inspection, straight edge inspection
label | Records / evidence, WCL form - Sign This ITP, Delivery docket
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 51 -
label | Inspection / Test Point - Road markings
label | ACTION (W, M, H) - W
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - Reinstatement of the existing markings
label | Frequency / When? - 1 / finished surface
label | Inspection / Test Method - Post seal surface inspection
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
section | Completion
checkpoint | 52 - D17
label | Inspection / Test Point - As-built information
label | ACTION (W, M, H) - H
label | Activity by - WCL
label | Conformance Criteria (What's Required) - Encountered Services Record Sheet
label | ○ Detailed Water Connection Sheet
label | ○ As-built drawings as per D17
label | Frequency / When? - Following/during completion of works
label | Inspection / Test Method - Document
label | Records / evidence, WCL form - Sign This ITP, DWCS, ESRS, As-built
label | Standard - ICC STANDARD SPECIFICATIONS KiwiRail specifications
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 53 -
label | Inspection / Test Point - Works Completion Notice
label | ACTION (W, M, H) - H
label | Activity by - WCL
label | Conformance Criteria (What's Required) - KiwiRail + myWorksites
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 54 -
label | Inspection / Test Point - Site walkover
label | ACTION (W, M, H) - H
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - Snag list to be compiled, and completed
label | Frequency / When? - At Completion
label | Inspection / Test Method - Review
label | Records / evidence, WCL form - Sign This ITP, SNAG List
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | Signoff
note | Wilsons Engineer
note | Signed By : Norbert Jacsek
note | Wilsons Contract Manager
note | Accepted By : Hamish Lindsay
note | ICC Engineers Representative
note | Accepted By : Tom Andersen
signoff | Signature: