## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Korimako SW | itp
section | Contract
checkpoint | 1 - D1.3
label | Inspection / Test Point - Site Management Plan (QEHS, SSST, KSA)
label | ACTION (W, M, H) - H
label | Activity by - WCL
label | Conformance Criteria (What's Required) - Ensure Quality, Environment, Health & Safety Management Systems Plan
label | ○ Site Specific Safety Plan and Key Step Analysis are approved.
label | ○ Living document to be adjusted and updated as required. A copy of QEHS plan, SSSP and KSA to be on site at all times.
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Submission (NTE)
label | Records / evidence, WCL form - Sign This ITP, LN-01, FM-83, FM-69
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 2 - D1.18
label | Inspection / Test Point - TMP
label | ACTION (W, M, H) - H
label | Activity by - WCL
label | Conformance Criteria (What's Required) - traffic management plan to be submitted and approved by Road Controlling Authority
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Sumission (NTE)
label | Records / evidence, WCL form - Sign This ITP, TMP
label | Standard - Code of practice for temporary traffic management (CoPTTM)
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 3 - D1.4
label | Inspection / Test Point - Works Access Permit
label | ACTION (W, M, H) - H
label | Activity by - WCL
label | Conformance Criteria (What's Required) - TMP and Corridor Access Request to be sumbitted on myWorksites
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Document
label | Records / evidence, WCL form - Sign This ITP, WAP
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 4 - D1.14
label | Inspection / Test Point - Client start-up meeting
label | ACTION (W, M, H) - H
label | Activity by - ICC, WCL
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Document
label | Records / evidence, WCL form - Sign This ITP, MoM
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
section | Production
checkpoint | 5 - D2.4.2
label | Inspection / Test Point - Bedding material
label | ACTION (W, M, H) - W
label | Activity by - Lab
label | Conformance Criteria (What's Required) - Material to comply with contract specification
label | Quantity - 280 m3
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Lab report
label | Records / evidence, WCL form - Grading Results
label | Standard - ICC STANDARD SPECIFICATIONS G3 of AS/NZS 2566.2
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 6 - D1.29.3
label | Inspection / Test Point - Sub Base Aggregate AP65
label | ACTION (W, M, H) - W
label | Activity by - Lab
label | Conformance Criteria (What's Required) - Materials to comply with contract specification
label | Quantity - 90 m3
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Lab report
label | Records / evidence, WCL form - MDD and Grading Results
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 7 - D1.29.4
label | Inspection / Test Point - Crushed Basecource Aggregate M/4 AP40
label | ACTION (W, M, H) - W
label | Activity by - Lab
label | Conformance Criteria (What's Required) - Materials to comply with contract specification
label | Quantity - 22 m3
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Lab report
label | Records / evidence, WCL form - MDD and Grading Results
label | Standard - ICC STANDARD SPECIFICATIONS NZTA M/4
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
section | Pre Construction
checkpoint | 8 - D1.5
label | Inspection / Test Point - Pre-work site inspection
label | ACTION (W, M, H) - H
label | Activity by - WCL
label | Conformance Criteria (What's Required) - Video or photos near the construction zone to determine their pre construction condition. (landowners property)
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Inspection Document
label | Records / evidence, WCL form - Sign This ITP, Video, Photo
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 9 - D1.18
label | Inspection / Test Point - Temporary traffic management
label | ACTION (W, M, H) - H
label | Activity by - WCL
label | Conformance Criteria (What's Required) - Signs set up as per TMP, with a copy on site with STMS. TMP monitored for practicality. If changes are required these are to be agreed upon with the engineer.
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Visual inspection Document
label | Records / evidence, WCL form - Sign This ITP, On-site record
label | Standard - ICC STANDARD SPECIFICATIONS CoPTTM
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 10 - D2.7.1
label | Inspection / Test Point - Set out
label | ACTION (W, M, H) - W
label | Activity by - ICC, WCL
label | Conformance Criteria (What's Required) - Mark out of alignment for mains and laterals
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Surface marking
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 11 - D1.8
label | Inspection / Test Point - Protection and identification of other Services
label | ACTION (W, M, H) - H
label | Activity by - WCL, asset owners
label | Conformance Criteria (What's Required) - Mark out on site of all services. Services to be potholed for as per Wilsons company policy
label | Frequency / When? - Prior to commencement
label | Inspection / Test Method - Surface marking, Visual inspection
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS Wilson's prior to excavate policy
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 12 - D1.11, D9.5
label | Inspection / Test Point - Notification to residents and businesses
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - Letter drop / business visits
label | Frequency / When? - Prior to commencement (min. two working days prior to water shutoff or access restriction)
label | Inspection / Test Method - Document delivered
label | Records / evidence, WCL form - Sign This ITP Notification letter
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
section | Stormwater main
checkpoint | 13 - C1.4, D2.4.1
label | Inspection / Test Point - Pipe material (main)
label | ACTION (W, M, H) - M
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - DN450 RC JR Class 4
label | ○ ICC to inspect pipe deliveries as required
label | Quantity - 360 m
label | Frequency / When? - 1 / delivery
label | Inspection / Test Method - Visual inspection
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS AS/NZS 4058:2007
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 14 - D4.3.1
label | Inspection / Test Point - Pipe material (lateral)
label | ACTION (W, M, H) - M
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - DN100 uPVC SN6 RRJ
label | Quantity - 32 m
label | Frequency / When? - 1 / delivery
label | Inspection / Test Method - Visual inspection
label | Records / evidence, WCL form - Sign This ITP
label | Standard - AS/NZS 1260:2017
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 15 - D4.3.1
label | Inspection / Test Point - Pipe material (sump lead)
label | ACTION (W, M, H) - M
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - DN150 uPVC SN8 RRJ, DN225 uPVC SN8 RRJ
label | Quantity - 45 m, 35 m
label | Frequency / When? - 1 / delivery
label | Inspection / Test Method - Visual inspection
label | Records / evidence, WCL form - Sign This ITP
label | Standard - AS/NZS 1260:2017
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 16 - D2.7.2
label | Inspection / Test Point - Excavation
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - The finished excavation surface shall be a smooth consistent surface at the appropriate grade. No tolerance on the excavation base level that reduces the depth of the bedding will be allowed.
label | Quantity - 472 m
label | Frequency / When? - continuous
label | Inspection / Test Method - Visual inspection Levelling
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 17 - D13.4.3
label | Inspection / Test Point - Subgrade inspection
label | ACTION (W, M, H) - M
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - To determine if improvements are required
label | Quantity - 472 m
label | Frequency / When? - Prior to placement of bedding
label | Inspection / Test Method - Visual inspection
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 18 - D2.4.2
label | Inspection / Test Point - Free draining material
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - pea gravel wrapped in a suitable geotextile up to 100 mm over the trench bed
label | Quantity - 0 - 360 m
label | Frequency / When? - Continous, in accordance with observed groundwater conditions
label | Inspection / Test Method - Secific approval should be given by the Engineer
label | Records / evidence, WCL form - NTE, NTC
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 19 - D2.7.3
label | Inspection / Test Point - Pipe installation (main)
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - +/- 30mm (horizontal)
label | ○ +/- 5mm (vertical)
label | Quantity - 360 m
label | Frequency / When? - Continous (pipe laser)
label | ○ 1/20 m (independent optical level)
label | Inspection / Test Method - Using calibrated pipe laser, Optical levelling
label | Records / evidence, WCL form - Sign this ITP, leveling record
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 20 - D4.4
label | Inspection / Test Point - Pipe installation (lateral)
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - grade: min 1.00 %
label | ○ Connection to the main: 90° saddle
label | ○ Connection to D600 manhole: gritted manhole finisher
label | ○ Connection at boundary: slip coupler/plumbqwik
label | Quantity - 3 (to 600 mh)
label | ○ 7 (to main)
label | ○ 1 (to 1050 mh)
label | Frequency / When? - Continous
label | Inspection / Test Method - Measurement Document
label | Records / evidence, WCL form - Sign this ITP, Detailed Drainage Connection Sheet
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 21 - D4.4
label | Inspection / Test Point - Pipe installation (sump lead)
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - grade: min 1.00 %
label | ○ Connection to the main: 90° saddle
label | ○ Connection to D600 mh / yard sump: gritted manhole starter / finisher
label | Quantity - 3 (to 600 MH), 3 (to main)
label | Frequency / When? - continous
label | Inspection / Test Method - Measurement, Visual inspection
label | Records / evidence, WCL form - Sign This ITP
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 22 - D2.7.6
label | Inspection / Test Point - Bedding (main)
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - lb (depth below): min 150 mm
label | ○ lc (width beside): min 300 mm
label | ○ lo (depth above): min 150 mm
label | ○ compacted layers not exceeding ⅓ of the pipe OD
label | Quantity - 360 m
label | Frequency / When? - continuous
label | Inspection / Test Method - Measurement Levelling
label | Records / evidence, WCL form - Sign this ITP
label | Standard - AS/NZS 2566 table 4.2.
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 23 - D2.7.6
label | Inspection / Test Point - Bedding (lateral)
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - lb (depth below): min 75 mm
label | ○ lc (width beside): min 100 mm
label | ○ lo (depth above): min 100 mm
label | ○ compacted layers not exceeding ⅓ of the pipe OD
label | Quantity - 32 m
label | Frequency / When? - continuous
label | Inspection / Test Method - Measurement Levelling
label | Records / evidence, WCL form - Sign this ITP
label | Standard - AS/NZS 2566 table 4.2.
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 24 - D2.7.6
label | Inspection / Test Point - Bedding (sump lead)
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - lb (depth below): min 100 mm
label | ○ lc (width beside): min 150 mm
label | ○ lo (depth above): min 150 mm
label | ○ compacted layers not exceeding ⅓ of the pipe OD
label | Quantity - 80 m
label | Frequency / When? - continuous
label | Inspection / Test Method - Measurements Levelling
label | Records / evidence, WCL form - Sign this ITP
label | Standard - AS/NZS 2566 table 4.2.
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 25 - D18 Fig. D12
label | Inspection / Test Point - Manhole (D1050)
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - 1050mm
label | ○ The sump shall be at least 300 mm from the underside of the lowest invert level.
label | ○ Neck depth ≤ 315 mm
label | ○ In-situ concrete packing
label | Quantity - 7
label | Frequency / When? - 1 / manhole
label | Inspection / Test Method - Measurement Levelling Document
label | Records / evidence, WCL form - Sign this ITP, Manhole Inspection Sheet
label | Standard - NZS 3109:1997
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 26 - D18
label | Inspection / Test Point - Manhole (D600)
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - CIRCULAR SUMP+INTERNAL BASE 600.900.100MM
label | ○ 600 mm cover Class D
label | ○ Connection to the main: D225 uPVC
label | Quantity - 3
label | Frequency / When? - 1 / manhole
label | Inspection / Test Method - Measurement Levelling Document
label | Records / evidence, WCL form - Sign this ITP, Manhole Inspection Sheet
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 27 - D18
label | Inspection / Test Point - Yard sumps
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - Flat top concrete sump box 450x450x1200
label | ○ Cast Iron sump grate + frame 450x450
label | ○ D150 sump lead
label | Quantity - 5 (1 existing is to be reconnected)
label | Frequency / When? - 1 / yard sump
label | Inspection / Test Method - Measurement Levelling Document
label | Records / evidence, WCL form - Sign this ITP, Manhole Inspection Sheet
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 28 - D15
label | Inspection / Test Point - Service covers
label | ACTION (W, M, H) - W
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - HN-HO-72 d600 mm, 450x450 mm
label | ○ Cover levels to be adjusted to existing ground levels
label | Quantity - 7 grated 600
label | ○ 3 solid 600
label | ○ 5 grated 450x450
label | Frequency / When? - before surface reinstatement, landscaping
label | Inspection / Test Method - Visual inspection Measurement
label | Records / evidence, WCL form - Sign this ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 29 - D2.9.3
label | Inspection / Test Point - CCTV Inspection and Cleaning
label | ACTION (W, M, H) - H
label | Activity by - WCL
label | Conformance Criteria (What's Required) - to confirm that the lines are free from debris and have no defects
label | Quantity - 360 m (main)
label | Frequency / When? - prior to the final surface reinstatement
label | Inspection / Test Method - CCTV inspection
label | Records / evidence, WCL form - Sign this ITP, CCTV survey
label | Standard - New Zealand Pipe Inspection Manual AS/NZS 2566:2
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 30 -
label | Inspection / Test Point - Removal of existing pipelines and manholes
label | ACTION (W, M, H) - W
label | Activity by - WCL
label | Conformance Criteria (What's Required) - DN150 EW
label | ○ Excavation may include the removal of existing redundant mains located within the trench extents.
label | Quantity - max 360 m + 10 manholes
label | Frequency / When? - during main installation (parts of Southern Korimako alignment)
label | Inspection / Test Method - Visual inspection
label | Records / evidence, WCL form - Sign this ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 31 - D2.10
label | Inspection / Test Point - Abandonement of existing pipelines by filling
label | Activity by - WCL
label | Conformance Criteria (What's Required) - DN150 EW
label | ○ Filling material and methodology for execution shall be approved by the Engineer.
label | ○ Ensure there are no active connections to the main
label | Quantity - 15 m3
label | Frequency / When? - following new main installation (Northern Korimako alignment)
label | Inspection / Test Method - Visual inspection Document
label | Records / evidence, WCL form - Sign this ITP, Delivery docket
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 32 - D2.7.7
label | Inspection / Test Point - Backfilling and compaction (existing, excavated material in berm)
label | ACTION (W, M, H) - M
label | Activity by - WCL
label | Conformance Criteria (What's Required) - All backfill material layers shall be placed and compacted in layers with appropriately sized mechanical compaction equipment to achieve uniform compaction for the full depth. This shall be in compacted layers not exceeding 200mm depth
label | Quantity - 240 m
label | Frequency / When? - continuous
label | Inspection / Test Method - NDM testing: not required
label | ○ Clegg testing: not required
label | Records / evidence, WCL form - Sign this ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
section | Surface reinstatement
checkpoint | 33 - D13
label | Inspection / Test Point - Landscaping
label | ACTION (W, M, H) - W
label | Activity by - WCL
label | Conformance Criteria (What's Required) - The final surface in the berm area is to be re-graded, with new sump manholes and yard sumps established as the low points.
label | Quantity - 240 m
label | Frequency / When? - following new main and lateral installation
label | Inspection / Test Method - Visual inspection Levelling
label | Records / evidence, WCL form - Sign this ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 34 - D13.7
label | Inspection / Test Point - Grass seeding
label | ACTION (W, M, H) - W
label | Activity by - WCL
label | Conformance Criteria (What's Required) - approved seed mixture, 35 g/m2
label | Quantity - 240 m
label | Frequency / When? - following landscaping between the months of September - April
label | Inspection / Test Method - Visual inspection
label | Records / evidence, WCL form - Sign this ITP, Blending docket
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 35 - D2.7.7
label | Inspection / Test Point - Subbase (AP65) compaction
label | ACTION (W, M, H) - H
label | Activity by - WCL
label | Conformance Criteria (What's Required) - Carriageway:
label | ○ 0.3 - 1.5 m deep: min 35 CIV
label | ○ > 1.5 m deep : min 25 CIV
label | Quantity - Culvert + ch 240 - 329, ch 87, 139, 220, 224, 253, 295
label | Frequency / When? - During installation, every 200 mm layers at 5 m intervals for all trenches in carriageway above main and connections
label | Inspection / Test Method - Clegg test
label | Records / evidence, WCL form - Sign This ITP, Clegg Test Result Sheet
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 36 - D2.11.5
label | Inspection / Test Point - Subbase (AP65) compaction
label | ACTION (W, M, H) - H
label | Activity by - WCL / Lab ICC
label | Conformance Criteria (What's Required) - 95% compaction rate
label | ○ It is not required to complete NDM testing on connections.
label | Quantity - Culvert + ch 240 - 329 = 95 m
label | Frequency / When? - At pipe laying commencement and reconfirmed at 120m intervals for open trench every 200 mm layers
label | Inspection / Test Method - NDM test (direct transmission)
label | Records / evidence, WCL form - Sign This ITP, NDM Test Result Sheet
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 37 - D2.7
label | Inspection / Test Point - Basecourse (AP40) compaction
label | ACTION (W, M, H) - H
label | Activity by - WCL / Lab ICC
label | Conformance Criteria (What's Required) - 98% compaction rate
label | ○ It is not required to complete NDM testing on connections
label | Quantity - Culvert + ch 240 - 329 = 95 m
label | Frequency / When? - 1 / 20 m of trench including one test at the start and end of the trench
label | Inspection / Test Method - NDM test
label | Records / evidence, WCL form - Sign This ITP, NDM Test Result Sheet
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 38 - D2.8.3
label | Inspection / Test Point - Trench reinstatement - marking out saw cutting
label | ACTION (W, M, H) - H
label | Activity by - ICC
label | Conformance Criteria (What's Required) - Engineers rep to mark out saw cutting required (overcuts)
label | Quantity - 6 m: Marama, 79 m: Kori
label | Frequency / When? - Prior to sealing
label | Inspection / Test Method - Visual inspection, measurements (1 m rule)
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS National Code of Practise for Utility Operators' Access to Transport Corridors
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 39 - D2.7.7.2
label | Inspection / Test Point - Basecourse (AP40) geometry
label | ACTION (W, M, H) - H
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - -5 mm +15 mm
label | ○ h = 45-65 mm (carriageways)
label | ○ h = 25-45 mm (footpath)
label | Quantity - Culvert + ch 240 - 319 = 85 m +5 cross
label | Frequency / When? - Prior to sealing
label | Inspection / Test Method - Visual inspection String line / straight edge inspection
label | Records / evidence, WCL form - Sign This ITP, Pre seal inspection record (FM-114)
label | Standard - ICC STANDARD SPECIFICATIONS NZTA B/2
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 40 - D11.4.3
label | Inspection / Test Point - Membrane Seal
label | ACTION (W, M, H) - H
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - Residual bitumen application rate ≥ 1.5 l/m2
label | Quantity - Culvert + ch 240 - 319 = 85 m
label | Frequency / When? - Prior to asphalting
label | Inspection / Test Method - Visual inspection
label | Records / evidence, WCL form - Sign This ITP, Delivery docket
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 41 - D12.5
label | Inspection / Test Point - Asphalt paving geometry
label | ACTION (W, M, H) - H
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - 5 mm from a 3 m straight edge laid longitudinally
label | ○ 5 mm from a 1 m straight edge laid transversely
label | Quantity - 85 m
label | Frequency / When? - 1 / finished surface
label | Inspection / Test Method - Post seal surface inspection
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 42 - D2.8.3, D12.3.1
label | Inspection / Test Point - Asphalt paving material
label | ACTION (W, M, H) - W
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - DG10 (carriageways)
label | Quantity - 13 t
label | Inspection / Test Method - Document
label | Records / evidence, WCL form - Sign This ITP, Delivery docket
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
checkpoint | 43 -
label | Inspection / Test Point - Road markings
label | ACTION (W, M, H) - W
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - Reinstatement of the existing markings
label | Frequency / When? - 1 / finished surface
label | Inspection / Test Method - Post seal surface inspection
label | Records / evidence, WCL form - Sign This ITP
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - N/A
label | Print, sign and date: ICC - N/A
section | Completion
checkpoint | 44 - D17
label | Inspection / Test Point - As-built information
label | ACTION (W, M, H) - H
label | Activity by - WCL
label | Conformance Criteria (What's Required) - Encountered Services Record Sheet
label | ○ Detailed Water Connection Sheet
label | ○ As-built drawings as per D17
label | Frequency / When? - Following/during completion of works
label | Inspection / Test Method - Document
label | Records / evidence, WCL form - Sign This ITP, DWCS, ESRS, As-built
label | Standard - ICC STANDARD SPECIFICATIONS
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT
checkpoint | 45 -
label | Inspection / Test Point - Site walkover
label | ACTION (W, M, H) - H
label | Activity by - WCL, ICC
label | Conformance Criteria (What's Required) - Snag list to be compiled, and completed
label | Frequency / When? - At Completion
label | Inspection / Test Method - Review
label | Records / evidence, WCL form - Sign This ITP, SNAG List
label | Print, sign and date: Wilson - YES
label | Print, sign and date: ICC - YES
holdpoint | HOLD POINT