## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
0bdc19fa-1296-474d-ac25-6d749bbda7d3 | checklist | HOP-CIV-Material delivery inspection-Precast Pits and pipe Rev 0 | itp | HOP-CIV-Material delivery inspection-Precast Pits and pipe | e3a8dacb-2cfd-4112-87b1-1f89cc7d93cd
24d70341-675c-4802-ac9a-0c3548b9ce63 | section | Details
83cc4258-8dae-426c-997c-22addd1d8f34 | checkpoint-no-value | Referenced Documentation
35f331d1-6e1c-5a3f-a0f3-4a98493aa958 | note | Document Title: HOP-Chk-Civil-Material delivery inspection-Precast Pits and pipe Rev 0
f5c98846-0fbe-5269-8d5a-123a945112f1 | note | ITP Description: Material delivery inspection-Precast Pits and pipe Rev 0
7caaaf82-85bd-5ed7-a691-54c67b9a2653 | note | Discipline (e.g. CIV/STR/RAIL): Chk-Civil
1ad14ac2-14ee-58e2-abb9-f639289acf94 | note | Revision Number: 1
e88a8531-0ed5-5683-8943-ae9b2aaddb29 | note | Revision Date: 21/01/2025
ffe19023-8bed-5ac1-8274-46c64cdeb123 | note | ITP created by: Cedric Guico
1865a1b3-186c-5ec0-ad1c-56c8fc829a43 | note | ITP approved for use by: Pradeep Talasila
928e8d32-b808-59a5-9cb1-a6496dfa387f | note | 1.01 - Non Dependent
a1d69f0a-521e-5bdb-b0ca-291d0fc0ec31 | note | Reference - VR 701
d839454d-8b18-4a19-a7df-5efc8065b774 | checkpoint | 1 - Delivery Details
3f8f166a-9db5-5da5-8e0a-7cf2b5c5a2d7 | note | Acceptance Criteria -
70c769fd-b2cc-5a5d-a60d-ce0e1560112e | textbox | Enter: Delivery Docket Number:
9ef2123f-9c3e-5c69-9e39-296c23532dc2 | textbox | Enter: Delivery Date:
8b3ece18-81ec-5988-8ae1-fc75bf61ac8a | textbox | Enter: Element ID (s):
d0ba77ea-be42-5086-905d-1607f489366c | note | ○ Attach: Delivery Docket and packaging Slip
4be98648-d8ad-56dc-9cd6-1c5ca1bf2fd8 | note | Method - Document Review, Visual
cd6b20b6-ad9c-5423-a0bb-6bf0f4ad946e | note | Frequency - Each Delivery
60ea403f-43ff-575f-aabe-7928b238d337 | note | Category - IP
b0d8cc2b-48c3-5d0e-bea0-24b54ce687f8 | note | Responsibility - PE/SE
44506d5d-60a4-54cf-8cc4-a495b3a57eff | note | Verifying Documents - This Checklist
8afc8693-89b0-5766-bd25-33e448f41cc1 | date | Date Completed:
1d297ce6-b39a-49bf-8dbb-2b4f16db0132 | checkpoint | 2 - Packaging Inspection-Quantity
c997ee43-c090-5cd6-9f6b-0a6ba8a49e4a | note | Acceptance Criteria - Does the number of packages in the delivery match that listed on the freight list/packaging slip?
7fd083bf-fb51-5f3f-b69b-7ae577d3afba | note | Method - Visual
10862c7f-23a3-59b0-87fe-444bba83cd7e | note | Frequency - Each Delivery
6c5d3e78-5486-5d9d-80bc-eba96d8bec4d | note | Category - IP
420fc208-8f1d-5f31-9de4-8b8e699b287a | note | Responsibility - PE/SE
78324c5b-00b3-5fc3-9a7a-c18e0704c28b | note | Verifying Documents - This Checklist
98e8e5d1-a577-516b-aeac-1c46d52099ad | date | Date Completed:
abbd30db-811b-49c8-9ab8-49d25bd6592c | checkpoint | 3 - Packaging Inspection-Delivery Contents
5b63d063-754e-5122-a4df-00d22ff55d67 | note | Acceptance Criteria - Do the contents of the delivery match the freight list/packaging slip?
ba90d115-32f4-5a11-8e92-254c1e172d8c | note | Method - Document Review, Visual
3243695f-ae1c-51cf-9c0d-ad61658d38f8 | note | Frequency - Each Delivery
38b38779-7295-5ede-856e-d68d11831e68 | note | Category - IP
4a566d18-5cf1-53bb-b74b-12129cfc5138 | note | Responsibility - PE/SE
87d6777a-a6bc-529d-bd62-8680671cf074 | note | Verifying Documents - This Checklist
e30038ae-f455-5bba-88fb-ec616eb2bf01 | date | Date Completed:
5e117473-72f4-4b82-b128-708982c1a478 | checkpoint | 4 - Packaging Inspection-Birth Certificate
00fa5612-e739-5697-abcc-d25f14be9f71 | note | Acceptance Criteria - Is the delivery accompanied by Precast items Birth Certificates?
b4b530f9-1ca2-50b8-ae94-2854a3f59e5a | note | ○ Precast components are to be marked on the birth certificate.
47a4240f-e3fc-54f1-a347-e0ef586ef274 | note | ○ Cast date and lot are to be marked on the birth certificate.
35010815-8d1e-5e22-be5b-7f3ff0d71105 | note | Method - Document Review
f736d948-7a2e-52fe-a211-cc4cf19be012 | note | Frequency - Each Delivery
0870c512-9118-5bdb-9f7d-9555733fa0a5 | note | Category - IP
11ccc0ea-a7f0-55c0-b9b2-a3fbdf2e8550 | note | Responsibility - PE/SE
49cda089-28bc-573c-ae92-561c0207b839 | note | Verifying Documents - This Checklist
553c6f84-2127-596c-9bff-b0e2e2fd6d97 | date | Date Completed:
c85d93fb-5cb7-4d51-acad-ec3187075f5d | checkpoint | 5 - Packaging Inspection-Transport
d20aa368-1b69-5f15-93b0-c1fb38db77e6 | note | Acceptance Criteria - Is the condition of packaging acceptable.
cd75eebe-9003-564b-af44-8e3564e877b8 | note | ○ Precast items are protected from damage during the transport
e8d5f259-836d-5e9f-8240-86c7a49b3c3b | note | Method - Visual
f57a1e6e-e53c-5d11-b8f3-494985f58b97 | note | Frequency - Each Delivery
b3c1aaa2-e908-5032-ae56-500a09e36832 | note | Category - IP
8634d380-8ddd-5cf9-afef-b933ba58664b | note | Responsibility - PE/SE
0721e9bb-8225-517d-b725-049b165c4c12 | note | Verifying Documents - This Checklist
02763241-e69e-5a62-a0ec-411667bbb454 | date | Date Completed:
db4f3788-e460-44eb-87f4-101fefb7bf4f | checkpoint | 6 - Fault IDs:
81189551-a490-5140-b344-06e189aa4d66 | note | Acceptance Criteria - For each precast type delivered, check for the following:
60b4060f-611e-5f63-a49f-ca413d5cff76 | note | 1 - Identification markings match the Precast type
25fecf9b-140b-5741-8687-3a53ec284aa8 | note | 2 - Precast Pit fabricated as per drawings - inverts size.
a237311d-8137-5d67-a761-f4a1111d398b | note | 3 - Precast Pit Fabricated as per drawings - Inverts position (Distance from the bottom and edges).
052bdf69-74d4-5bc0-a676-4a75eeb4dcd2 | note | 4 - Precast Pit Fabricated as per Drawings - Invers Position - Correct Wall (orientation).
f7594e1e-706b-5390-9f23-aa0c2962600c | note | 5 - Precast Pits- Inverts coliding.
79f8746d-efa8-58cc-b0ea-c457dc994037 | note | 6 - Precast Pits a - Inspect for Cracks.
6668862c-2da7-5e5c-9b11-d76978ede803 | note | 7 - Precast Pits - Inspect for Spalling/Damage to concrete surface
41233777-ecde-5c56-999b-a26361aaab7d | note | 8 - Precast Pits - Inspect for Exposed Reinforcement.
0bf1ad67-ce4f-579e-bd16-1f9c850e2f81 | note | 9 - Precast Pits - Inspect for correct Lifting mechanism.
6f3eb9b8-6c00-5824-a90b-517ba0d57095 | note | 10 - Pipes-Inspect rubber rings
3bea0570-0e19-5bd1-a60e-c5464b62a19a | note | 11 - Precast Pits and RCPs - Inspect for other fabrication defects (specify on the following lines)
a513ba25-7cda-59b7-ace2-01da6d7828dd | note | 12 - Pipes - Inspect for any defaults/deformation in the pipe
04d79ead-0461-5948-a9d7-e5a0d48493a0 | note | Method - Visual, Measure
57f61bda-da5c-5614-9942-6b8fab447c76 | note | Frequency - Each Delivery
facdae43-48f8-57ef-b09f-2558d516bec9 | note | Category - IP
c798c022-8405-556c-ac3c-3b0265917c9a | note | Responsibility - PE/SE
22c19dca-59cc-5700-994b-d15e338ad259 | note | Verifying Documents - This Checklist
d02351fe-68f3-5b80-890c-9088268bd265 | date | Date Completed:
a3c15620-a9d6-4ed3-a370-09b89a614dc0 | checkpoint | 7 - Check for Faults - 1
8d4a53eb-ecd1-5670-8d1b-13b258f4be97 | note | Reference - Item 6 on this Checklist
f651eeaa-70a3-5466-9db5-f6de6ac668d7 | note | Acceptance Criteria - For Each Precast type delivered:
bda929a7-7fa0-5df6-b0e0-abd45f9b0e7f | textbox | Enter: Pit Identification:
8607002c-bf8c-5c81-929b-d7938f866f96 | textbox | Enter: Quantity:
7ad3866e-3e8a-505f-b6a8-fcabff560201 | textbox | Enter: Fault ID if any:
b321d4b9-4032-5705-b349-369cfccca117 | note | Method - Visual, Measure
79f94937-d897-58a1-b712-b4b7e398d65a | note | Frequency - Each precast type delivered
f909879e-1e8e-5b00-a730-46b4ea5081f0 | note | Category - IP
1422e49b-481a-556e-8b2a-68af584f47e9 | note | Responsibility - PE/SE
3623f033-cd0d-55bc-aaa2-8f790bb3a35d | note | Verifying Documents - This Checklist
4e9cda59-7cf2-58b8-b404-989c58b8bf4e | date | Date Completed:
9c0dc801-6bf4-4573-8278-4c0a21f8fa04 | checkpoint | 7 - Check for Faults - 2
dca1119c-357d-5688-b725-724d34d10302 | note | Reference - Item 6 on this Checklist
7835d228-2c54-596a-9fc8-8914194d8657 | note | Acceptance Criteria - For Each Precast type delivered:
ec4904c0-d946-556e-8b34-d1d20bc56b4c | textbox | Enter: Pit Identification:
51996110-15ae-5cf4-b2b6-e85ff34c4bfc | textbox | Enter: Quantity:
0e196c56-f262-5174-82c0-8f254869e6d3 | textbox | Enter: Fault ID if any:
581b2407-8e0e-5b57-9877-ce78437b1075 | note | Method - Visual, Measure
408f7d9e-a587-5bbc-a560-6039cdc10da3 | note | Frequency - Each precast type delivered
1ac13b7e-1482-5d62-bb2f-8cab2513aad3 | note | Category - IP
e3f15314-7fad-535c-9d5b-368f1dcc8697 | note | Responsibility - PE/SE
ce956ffd-78de-5489-9d06-da882a1fd6b7 | note | Verifying Documents - This Checklist
408f598d-497f-505a-aeb0-52ea6e9d7449 | date | Date Completed:
fde0c8d0-ed87-4ffd-bb04-850b04a51a09 | checkpoint | 7 - Check for Faults - 3
fb969b21-9137-5d0b-8336-947e5e8b7c00 | note | Reference - Item 6 on this Checklist
6066d05b-78d2-54c5-b02a-d2895662a6a8 | note | Acceptance Criteria - For Each HDPE pipe type delivered:
9f7bf03f-625a-537c-80b9-a0328f8e3724 | textbox | Enter: Pipe Identification:
ddd133c5-bb49-5524-a571-0f0f845e02fc | textbox | Enter: Quantity:
b1363489-dcf7-55fb-8933-1741e03022bf | textbox | Enter: Fault ID if any
83186c8f-97ee-53dd-949e-0a4ddc65a70a | note | Method - Visual, Measure
56a6a9b7-494a-5359-b81e-9d666012368b | note | Frequency - Each precast type delivered
6f5665ee-a9da-5fe7-8acb-215354027a3d | note | Category - IP
6f371f4c-5394-5882-af6c-1bcb44ae6561 | note | Responsibility - PE/SE
1d8ce237-090c-5694-8f90-dd29e762dde8 | note | Verifying Documents - This Checklist
a36c96e2-35e6-5292-93a4-fe327a8bada8 | date | Date Completed:
3807fe77-f4f4-4022-bb37-3eed1505067d | checkpoint | 7 - Check for Faults - 4
c7ca82e7-3393-5445-b4ac-75ef9bb033e5 | note | Reference - Item 6 on this Checklist
23b97830-bfe6-5a6e-b098-b6b9bdbcd1b2 | note | Acceptance Criteria - For Each HDPE pipe type delivered:
ce2d49e9-e4e5-595e-9b8a-4cd43deb46f6 | textbox | Enter: Pipe Identification:
048eab69-aa73-5df4-9a48-3cd5757304fd | textbox | Enter: Quantity:
1ca09a44-13f8-5523-9c46-947f918c21fd | textbox | Enter: Fault ID if any:
fb08aed5-101c-559f-9887-a1925a65a1aa | note | Method - Visual, Measure
895749a7-ef67-59de-a7a7-6eb79dbdc9de | note | Frequency - Each precast type delivered
bc9d79c8-3f91-5c15-98a1-88fec60e77fd | note | Category - IP
8da37648-35c3-531d-a50f-67b270163772 | note | Responsibility - PE/SE
26cb86b0-7c5d-5542-bccb-1a7c216e71de | note | Verifying Documents - This Checklist
9012004e-b0c3-5e31-bb40-e54bd65445aa | date | Date Completed:
a9860f4f-9d1e-4b2a-9f8b-d14d9e3e1f46 | checkpoint | Final Inspection
a577edb2-0afc-5bbc-b600-b20d159d89fe | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
13ec3a35-8743-58b7-af78-8728de33bfb1 | textbox | Name:
27ba1362-19b2-55b0-bee8-02d4eb2112ba | textbox | Position:
259a70ba-2d15-5df0-99b4-7f7a96a18d08 | textbox | Date Completed:
02a48a96-4171-4659-9211-2153e3e0df5f | signoff | Sign ITP
| checklist | ITP-214-CIV-Hop-Piling Pad (Supply and Install) Rev 0 (FH01) | itp | ITP-214-CIV-Hop-Piling Pad (Supply and Install) | 7cecba3e-2029-4d43-8578-416bab79e186
| section | 1. Referenced Documentation
| checkpoint-no-value | Referenced Documentation
84263cdc-ec53-5e9d-b0f7-257e2c6f8b3b | note | Document Title: ITP-214-CIV-HOP-Piling Pad (Supply and Install)
1c7f2a55-240c-5ffd-9271-e52d0de18abc | note | ITP Description: Piling Pad (Supply and Install)
96c5efda-a7e6-5ba6-bae8-685f91d12c2a | note | Discipline (e.g. CIV/STR/RAIL): CIV
e6ed8d1f-cc7e-550d-9f82-0081ca1d07b5 | note | Revision Number: 0
e65c6d85-7c98-570d-bb37-48780b24a8de | note | Revision Date: 18/10/2024
51db878c-36aa-59d4-894a-b0b473f32d4b | note | ITP created by: Cedric Guico
fd25f724-295b-5ed1-b66e-4a9cd0d75716 | note | ITP approved for use by: Pradeep TALASILA
7b24354f-252d-5ddd-86d9-12e1d6c2cc08 | note | 1.1 - Non Dependent
1ebf6581-7004-5817-abaf-6a0c1509f9d7 | note | Reference - VicRoads Standard Section 204 (Dec 2015)
5f47d667-849d-5b10-be79-87cd0e5f3583 | note | 1.2 - Non Dependent
290854e3-830c-54bc-937f-f83bd5b746d8 | note | Reference - VicRoads Standard Section 173 (Oct 2008)
6bf20715-79ff-5459-a3c8-ee42f294c7f8 | note | 1.3 - Non Dependent
dbef7e4a-a0f0-5184-913c-79f3fc0f15a5 | note | Reference - Temporary Works Design - Crane Piling Pad Design
8309c337-3778-5868-81ff-eca88a75d37c | note | 1.4 - Non Dependent
6f94a464-ddf9-54fe-9197-190118d7b23f | note | Reference - IFC Drawings
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Class 3 Crushed Rock
9d16927b-5d75-58fd-be6d-486e4acb1a72 | note | Reference - IFC Drawings
0bc4f5dd-1e06-557e-938b-e915396a7354 | note | VicRoads:
1d2f5e8f-b9bb-5a81-8197-0cafa1357170 | note | ○ Section 204
d871d6e6-529e-587e-a144-c7ea75175e9a | note | ○ Section 173
e82104e7-6092-5d3e-b63a-f2f7f0603371 | note | Acceptance Criteria - Material shall meet the requirements as per Temporary work design requirements
6712f7ed-11d7-54f8-bce7-0582c89cbaf9 | textbox | Enter: TeamBinder Material approval No.
52b1871e-2952-5997-ad26-07ab1452e841 | note | Method - Document Review
037b0994-fe6f-55c8-83cc-079ed59cbf8a | note | Frequency - Each Lot
f9bb95f1-aae7-56b0-9397-8be0201f97bf | note | Category - HP
cd1a2f52-6950-5f7a-91b4-8161c9706adb | note | Responsibility - SE/Site Supervisor
84a38f0b-b434-5c3a-9812-bd1216e73f53 | note | Verifying Documents - NATA Test –Material Test Report PSD,LL,PI,PL ,MMD & OMC
8cacd062-10da-58e3-be36-0027b58870eb | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Pre-construction / Pre-installation Activities
| checkpoint | 3.1 - Survey Set-out
c2790153-51e4-5b86-b7d7-798e7944fc8e | note | Reference - Temporary work design Drawing
39017be6-dfdb-53b7-9959-423dbfac732b | note | VicRoads:
5acde777-bf4a-5727-badb-2381f8b25e7a | note | ○ Section 204
8ea57f26-3607-5f0b-9762-db0d1d9cf97e | note | ○ Section 173
6b440383-bcb7-5c7b-b5af-8f1ec2154d12 | note | Acceptance Criteria - Survey to set out extent of crane piling pad requirements.
3892128d-8dac-51ad-92d8-a062bd4211e5 | note | ○ Survey pegs in place and clearly marks out the limits of works.
cae1d930-440c-57e7-8b7c-9878edf35e61 | note | Method - Visual and Measure
271a4788-ae8b-5c7f-8140-55fa2a7a977a | note | Frequency - Each element
1c6f2035-77e5-5be2-99c4-e6e65c5a2f72 | note | Category - IP
ba85f3bb-aaaa-59bc-9583-f378a3ad01aa | note | Responsibility - Surveyor, SE/PE
8ac3ec9c-1361-540e-83a3-c754a459fc2f | note | Verifying Documents - This ITP
095edcfc-fbc9-57d7-a883-229898f549f0 | date | Date Completed:
| checkpoint | 3.2 - Check location of underground and above ground utilities
a1cfec09-7bf1-5254-94e0-fb15ed3aa038 | note | Reference - DBYD, QMP
080c659a-792e-5027-af92-c44778ce1200 | note | Acceptance Criteria - Ensure that:
5880425a-d1fc-5bad-9cc9-d1532e0a6fe8 | note | ○ Dial Before You Dig
2c1865fa-e8e4-5006-8672-e02badc5dfa8 | note | ○ Services isolated
b08c248d-680d-578a-94a1-918e5a27413a | note | ○ Permits obtained from internal and external authorities
5e9b4202-7a99-5830-90c5-d8b66d11ae04 | note | Method - Visual and Measure
74766376-e125-54b0-9cd7-8cc9fc7d0a4c | note | Frequency - Each Lot
c433e26f-9805-5ef2-8aaf-60b614d5eb23 | note | Category - IP
fd022310-8bd1-541c-afda-030aba47757a | note | Responsibility - SE/PE
5d5c2c88-0931-5c75-979c-40572bec9506 | note | Verifying Documents - This ITP
946369c8-64df-5132-b9f1-b330b0cc8c6e | date | Date Completed:
| section | 4. Construction / Installation Activities
| checkpoint | 4.1 - Ground Conditions
8293edd8-6ef1-5f13-9a1a-337ebfc868cc | note | Reference - IFC Drawings
0ac14ec6-d634-5d33-93f5-2a3e60db2b7e | note | Acceptance Criteria - All foundations are to be free of water and loose material.
a25f6301-cf68-5826-b8f8-c349de941902 | note | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
2dd0a7a5-7baf-59b3-9451-fe393046d040 | note | Method - Visual
ef74959f-ad7a-53b6-bf17-15fa4e62c3d3 | note | Frequency - Each post
908b032f-a963-5e9e-ae6a-b6361d1910e7 | note | Category - IP
899d84a7-f5bc-573b-8f78-359a4db0fa59 | note | Responsibility - SE/Site Supervisor
1485c49c-1517-59a9-9c96-6d171542a5d1 | note | Verifying Documents - This ITP
f159ed16-e1fc-5532-a509-4544f98ff6b1 | date | Date Completed:
| checkpoint | 4.2 - Preparation of piling platform foundation (proof Roll)
b737b16f-cafc-5535-9fd1-c6d1ed5e9bc8 | note | Reference - Temporary Works Design Drawing
d7daf6b6-585c-51f8-95b2-58eb61a32005 | note | VicRoads:
ccd92b10-ef54-558e-91d8-a379471a1c1d | note | ○ Cl 204.12
f29cc87b-7de3-5f56-b182-9a68a94713e0 | note | Acceptance Criteria - Areas upon which fills are to be constructed, all layers of fill, shall be test rolled in accordance with Section 173. Any unstable areas detected by test rolling shall be rectified. Nominated Authority to be present during all test rolling.
6b5714d0-10ca-5726-abfa-6da48e6a61e0 | note | ○ Temporary work Design Drawing and equipment design requirements. No waving indication.
57625fe3-fbb3-51f0-9679-ed05eedde980 | note | Method - Visual
6083612d-2ee3-53d3-bd24-94489ce3859e | note | Frequency - Each fence footing
f81fb49f-7928-527c-b4db-c3d96ab17541 | note | Category - HP
0463a8f8-617f-5e85-b306-3959701d7f13 | note | Responsibility - SE/Site Supervisor, Nominated Authority
bbb9f5d7-4a6d-5d18-ae96-f4be675eb651 | note | Verifying Documents - This ITP
f7b9c291-24f0-51eb-b92d-657f33d302ed | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Fill, Compaction and testing
f64a1db6-a0d9-5c5b-8b0c-705393b4c1b8 | note | Reference - Temporary Works Design Drawing
26420633-e6f1-55ad-8ce0-74b761390ed4 | note | VicRoads:
e9c602ca-45dc-557b-9445-538f5aabfb2f | note | ○ Cl 204.10
237a135f-becb-5b05-8f4f-9346ab47363e | note | ○ Cl 204.13
45440e3b-ea85-5b9e-bda4-9d6e6ff3c372 | note | Acceptance Criteria - Bearing Test to support piling rig (as indicated in temporary works design). Target 100kPa.
68a0614e-a4f0-5c37-8896-d0e026f976ca | note | ○ Testing and acceptance of compaction and moisture content as per VicRoads Cl 204.13
5e8aad32-3f6a-547a-a1d1-dd69fc6f2c31 | note | ○ Attach: compaction test results
eaf444ca-9ada-5a7c-bde6-07ebf4a1e1d6 | note | Method - Test
b06db687-37e0-554f-89a2-8b6be13dba98 | note | Frequency - Each Pad
0be89de4-8b07-5dfd-82b3-7cb67566871f | note | Category - HP
aa6acedb-3f3b-5528-bd35-281aaaf07f2b | note | Responsibility - SE/PE
bd532a4f-3423-53b0-b6cb-c92c3927185b | note | Verifying Documents - NATA Bearing Test Report, Compaction Test Results
568d43bd-8506-5df8-a74f-8ca18158a924 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 - Verify survey conformance
096afb79-02c3-57f0-a520-623e6623d446 | note | Reference - Temporary Works Design Drawing
51ac5295-9dc3-5c0d-be8e-3063cc34b082 | note | VicRoads:
9c98b054-3b5c-56ce-9d17-5a8afee0f4a5 | note | ○ Cl 204.03
62cc40c3-9e9f-5a20-bb37-c529d1a2354a | note | Acceptance Criteria - Construction Tolerances finished ground level ± 40mm or equipment requirements
523a7d6d-fa1f-5d8f-b5ec-fba29d1972d2 | note | ○ Attach: Survey report
5733fff4-4dbf-5a5b-bdf1-9d02f4d8b690 | note | Method - Visual
cb593ef0-9a1a-5fc5-aef1-fa54f958bc82 | note | Frequency - Each Pad
68eb4f7d-a0b2-5a5e-8a3a-7dff5bb0b513 | note | Category - IP
45a6e5b4-3e0f-5384-aed7-893f9a858c14 | note | Responsibility - SE/Site Supervisor
7701d51c-2d71-5800-aaac-72d22f784c7e | note | Verifying Documents - This ITP
24727e7c-71f0-5fc3-9245-a2fcf0686282 | date | Date Completed:
| checkpoint | Final Inspection
ceb52eaa-806c-54e1-b88b-f8b875d6fef5 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
3a806a1c-1487-554a-a2d4-b4d7503b1696 | textbox | Name:
9758f3d5-bd53-5198-a596-c5a8c2e72af0 | textbox | Position:
05938094-f9bf-5f7f-a4a0-c08a084a3104 | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-215-CIV-HOP Rail Delineation Fence Rev 0 (FH01) | itp | ITP-215-CIV-HOP Rail Delineation Fence | 79d178a0-3844-4f84-a537-d72335ff4de2
| section | 1. Referenced Documentation
| checkpoint-no-value | Referenced Documentation
d191f820-c417-54e5-a572-4046c73ba5de | note | Document Title: ITP-215-CIV-HOP- Rail Delineation Fencing
d693921b-ec1d-55d1-af48-20fb69702e79 | note | ITP Description: Rail Delineation Fencing
475e5ca0-a03e-546d-b5a5-3012a35f6723 | note | Discipline (e.g. CIV/STR/RAIL): CIV
1c969dcd-467c-5596-b5b3-a39533719556 | note | Revision Number: 0
edafeae0-7777-5818-bb8a-7ae7dc784e6d | note | Revision Date: 18/10/2024
d337c6f1-7a91-57a2-8abf-f4515c04c909 | note | ITP created by: Cedric Guico
5992a250-ebd3-5810-a26c-6866ed9d8ada | note | ITP approved for use by: Pradeep TALASILA
331170d8-5c77-51e9-b3f6-29d686b828c9 | note | 1.1 - FH01 Hopkins Barrier Alignment
9a49fc7a-bdce-570a-abc3-be567d32b21f | note | Reference - Mark Up
8cec1281-29f1-5ea2-a24c-69053bdd0f6e | note | 1.2 - Hopkins FH01 Occupation Works Mark Up
9a3f7a3c-6bfc-56cb-a754-9ca83b35d449 | note | Reference - Mark Up
49814096-f71d-558d-9f8f-87d7c70c8634 | note | 1.3 - MRP-DPK-102-00-CPW-0061
0d81cb01-d944-5a9b-ae7e-85f89f060213 | note | Reference - IFC Drawing
6b718562-acb4-5c9b-9835-a5a10d4f466f | note | 1.4 - Rev 1, SAST-3281 Rev 1, and AS 1725 Chain link Fabric Fencing Security Fences and Gates
83b894d6-e166-57a6-b758-9f005833ef76 | note | Reference - Standard
| section | 2. Materials
| checkpoint | 2.1 - DB80 Concrete Barrier & Gawk Screens
5c2d17f9-d957-5dbb-ae19-52b14b80042b | note | Reference - IFC Drawings
ab339fac-4ebb-58a5-9750-813e4d0534ed | note | Acceptance Criteria - Delineation fence to be DB80 Concrete Barrier & Gawk Screens
f7f40ac6-a61b-5328-9ab4-652d9900c1a9 | note | Method - Document Review
000a0c71-527e-59ef-a60b-cc50523d1316 | note | Frequency - Each Fence
e1c05713-d40a-5099-92d2-577d757bb0cc | note | Category - IP
ed0e8e94-e91a-5e9f-995c-0f8bfb810e38 | note | Responsibility - SE/Site Supervisor
3a5a6559-7bd8-5eee-89b1-1b5aed50824f | note | Verifying Documents - Supplier Certificate of Compliance
a59ceffa-55fb-5212-9675-cb2cc4a7ccf5 | date | Date Completed:
| checkpoint | 2.2 - Class 3 Crushed Rock
117bcd93-d19d-5c82-841d-6b2a41065459 | note | Reference - IFC Drawings
d3aef1f5-7c3a-5cda-b837-f8e920f692dc | note | Acceptance Criteria - Class 3 Crushed Rock to be installed for barrier foundation and crane piling pad
cb1225c6-9545-5e8f-aa60-aefe892465c6 | note | Method - Document Review
9379d7dc-fd0b-522f-a5af-01e73f5076ff | note | Frequency - Each lot
67869a83-be9e-5da9-a3fa-e511a5a3d9c1 | note | Category - IP
925f8d6c-c8dd-5788-a05b-79d46c187e6b | note | Responsibility - SE/Site Supervisor
e8beda6f-3890-53fe-a04b-e981c14123f8 | note | Verifying Documents - Supplier Certificate of Compliance
cf653c9e-8b07-5559-aba9-255dc9fe617c | date | Date Completed:
| section | 3. Pre-construction / Pre-installation Activities
| checkpoint | 3.1 - Removal of vegetation
e1cbbb2d-5c65-5b62-93e1-2c061757e048 | note | Reference - Environmental control plan
b51a5d87-7730-5482-b1c2-62a5051d09d3 | note | Acceptance Criteria - As per environmental controls
a3520868-733f-54e5-a1b4-63da18b9d36f | note | Method - Visual
6c828dd4-4f66-58a8-bdfc-3356e232d6ec | note | Frequency - Each Lot
0b6579cc-8e32-5c6a-991b-065b688ddef0 | note | Category - IP
d8e973c5-c3c8-56cc-81e8-99f7ebdf8103 | note | Responsibility - SE/PE
47229729-6d42-51bc-8903-b0a411cac757 | note | Verifying Documents - This ITP
c0115b27-4fe2-56d4-b521-0556199b0eac | date | Date Completed:
| checkpoint | 3.2 - Survey Set-out
29120912-87d9-526d-8ea5-22efe0c1e023 | note | Reference - IFC Drawings
447c8ae7-8097-58ac-9aaa-65f7d3812dec | note | Acceptance Criteria - Survey to set out the following but not limited to: existing services, refuge bays and fence start and end points.
4ef0f97c-b75a-5301-8dfc-e10f9b4e8998 | note | ○ Offset checked against the running edge prior to installation of barriers.
3c073e81-ebe8-595a-a948-178edb9ba2d9 | note | Method - Visual and Measure
68e7f464-62f2-5341-813e-6c724adb663f | note | Frequency - Each element
c159e597-d369-5cdb-8707-033335ead6dc | note | Category - IP
25b2e5d7-9461-5006-87cb-a82a2170edb4 | note | Responsibility - Surveyor, SE/PE
4f792443-f02c-51d7-bef1-5adff5187995 | note | Verifying Documents - This ITP
490565b6-a1d1-500e-8cca-9b0598993896 | date | Date Completed:
| section | 4. Construction / Installation Activities
| checkpoint | 4.1 - Excavation works
836b0f13-fc68-555a-ad1e-a762dac4204c | note | Reference - IFC Drawings
b50cc577-77d0-5c0d-b4ff-3f8a169ffc24 | note | Acceptance Criteria - Excavation completed by mechanical plant and hand tools.
764a4a56-e414-5e9e-ada2-04957127c3bc | note | ○ Follow asset owners guidelines for work around their service.
6b90bbc0-b9ed-580e-89ae-882c539fd644 | note | Method - Visual
01f8c23d-b4a7-5af7-b679-e4e5186823e9 | note | Frequency - Each fence footing
5ecd1ff0-6d9e-5ba3-9601-7421d99b84b4 | note | Category - IP
d2e7386a-d3b3-5eac-b02e-fde83bf970f1 | note | Responsibility - SE/Site Supervisor
52a1d07e-7676-5c98-a28b-8735209ba8e2 | note | Verifying Documents - This ITP
2bf99fcc-bf73-5c4d-a10a-a4fb833f4b5d | date | Date Completed:
| checkpoint | 4.2 - Ground Conditions
5e81b261-fb0a-5df1-b1f6-1c6da0b7bc20 | note | Reference - IFC Drawings
e42978e0-85d5-5b26-8d40-829da6c365c9 | note | Acceptance Criteria - All foundations are to be free of water and loose material.
8b55b79d-765d-56e0-92c8-8bbbed607799 | note | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
2165e043-8b9a-5cd6-af71-37ae4d1ed38d | note | Method - Visual
b36db615-30b2-5395-b67b-67c5637bfb74 | note | Frequency - Each post
57319001-0a01-52c0-a99c-902d310439ed | note | Category - IP
d5914840-cd19-5dfc-a954-6ab7e0830bd2 | note | Responsibility - SE/Site Supervisor
7af9d2b9-8d49-54c8-b5bb-3d398305b8a9 | note | Verifying Documents - This ITP
7a22d926-b5a7-5080-804e-fd043972cd81 | date | Date Completed:
| checkpoint | 4.3 - Install fence foundation
5122b421-3da1-5212-996c-002d94c80c3f | note | Reference - IFC Drawings
5bcc2d87-4c8f-57ed-a3d9-a7e2050eeb94 | note | Acceptance Criteria - Excavation of 300mm from ESL. Install Class 3 Crushed Rock as per set out requirements
961fec83-689f-5d79-bd55-c33e3c004fa6 | note | ○ The foundation shall have a minimum bearing capacity of 100kPa
4ffd0827-b9e9-5cf8-bb0d-3f640f3fbca9 | note | Method - Visual
f9909901-15ea-5272-96f4-0962a80503a0 | note | Frequency - Each post
57aad923-d581-5890-b781-bcf19dcfb715 | note | Category - HP
9d1509d5-0adf-58c9-961e-8a02ed9ea196 | note | Responsibility - SE/Site Supervisor
50c4e41f-9d43-54e0-96e9-a6a58a56eabf | note | Verifying Documents - Geotechnical test report
2fabf47e-a7c8-5223-b20d-036b42141452 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Fence Installation
5261bfcc-bcff-52fb-9e0b-1b41ae1516ef | note | Reference - IFC Drawings
1134ec2b-ed9e-57a7-bdbc-e9c3151a3128 | note | Acceptance Criteria - Concrete barriers (DB80 F Shape) to be installed as per survey set out. - Installation to of fence to be 2.588m offset from outside edge of rail to the inside of the barrier. Barriers to be installed with 3x interconnected barriers between refuge bays (18m)
d6fd7eda-f200-5c5f-9022-677259f7d7c3 | note | ○ Install gawk screens compatible with concrete barriers.
cea1ed9b-4c4f-5508-92c7-16174354b14e | note | Method - Measure
2a0048a5-3448-5163-8e6c-6dd8bf91aaf4 | note | Frequency - Each Fence
8c349b59-b48d-5c07-86f7-d4e03c452aa7 | note | Category - IP
87a889b6-31d2-53f8-82b0-a90405fd896e | note | Responsibility - SE/Site Supervisor
4753dd8c-52cc-5292-9b04-1414a8be68e5 | note | Verifying Documents - This ITP
a4c712db-55ef-57ed-903a-f0c39130375b | date | Date Completed:
| checkpoint | 4.4 - Refuge Installation
2b118917-b10e-5df5-98d9-04218fd252b7 | note | Reference - IFC Drawings
98a04ef7-b552-5f43-b111-6a39c40401f9 | note | Acceptance Criteria - No concrete barriers to be installed at locations of refuge bays.
f8bef07c-3c48-5910-91d7-bfdefc84c986 | note | ○ Refuge bays to be 1200mm wide at intervals of 18m.
3f5fa22a-9d5b-57ab-9a04-66eacf2fd2b5 | note | ○ Install additional refuge bays or reduced spacing to allow access to rail assets
1a0fe004-b602-501e-a292-b2f9f5111037 | note | ○ 50mm dia PVC pipe push out bars to be installed. PVC tubes to be pushed off from track side only.
51a6e0bd-a68f-5864-ae23-7a297a79ffca | note | ○ Refuge access to be 1200mm wide
402c31f2-82b4-5358-8456-de2ab70e1812 | note | ○ Refuge bay signage installation halfway between each refuge bay
ef273b43-fa48-59ff-922a-b3dc63c4dec8 | note | Method - Visual/Measure
c97da713-4659-580e-b36f-c76ff3450cfe | note | Frequency - Every 18m MAX.
1e5477d4-37c0-550f-ab47-d7a35435b974 | note | Category - IP
5f7b3dab-7153-5fb5-b70c-b017aa8130e3 | note | Responsibility - SE/Site Supervisor
26fe2768-d15d-5e8d-887b-534c9451427e | note | Verifying Documents - This ITP
4c8eea41-bf93-5540-a2e3-db8bd3415604 | date | Date Completed:
| checkpoint | 4.5 - Limited Clearance Sign
53fec01e-33a0-5514-99ea-0007436e1b34 | note | Reference - IFC Drawings
62baa09e-c58e-5d12-ae36-d0d1c7af1c80 | note | Acceptance Criteria - Limited clearance signs to be erected at all refuge locations and at each end of Delineation Fence
a3c0ffbb-05e9-5fca-a6f8-67609f435776 | note | ○ Sign to read "DANGER LIMITED CLEARANCE DO NOT OCCUPY DURING PASSAGE OF TRAINS"
cc5cda43-230a-5050-8e7c-bda36d8e2661 | note | Method - Visual
f13d470f-2d35-5a34-9de5-e1b8e064e862 | note | Frequency - As required
a7560630-6f4f-5cba-8ce7-8d5d2de65f62 | note | Category - IP
ddb46dc7-1069-525f-9ccc-292cde1f2700 | note | Responsibility - SE/Site Supervisor
50cac5c0-e370-52ba-b496-42f8a08b30d8 | note | Verifying Documents - This ITP
17d5ee21-0c00-5b26-a9ba-0696378e15ee | date | Date Completed:
| section | 5. Post-construction / Post-installation Activities
| checkpoint | 5.1 - Fence Height and Track Clearance
e63e5b20-5173-5139-ae65-1aa93dfbadc7 | note | Reference - IFC Drawings
a47ecfe3-003f-539f-a344-8b71ff09214d | note | Acceptance Criteria - Inside face of concrete barriers clearance from rail to be physically checked with tape measure.
c7b726e7-3f33-5c04-a6b8-4e237b84edf0 | note | ○ All corners to be checked with Engineer and Foreman
beb86dae-2740-583b-893f-9303280e4988 | note | Method - Measure
fcb2af75-e342-5a4d-ad0b-f22843e1f633 | note | Frequency - Each lot
d15b4a40-c885-594e-ac0b-93223d7047d9 | note | Category - IP
bb53a209-6627-57dc-bbed-0b880de3be04 | note | Responsibility - SE/Site Supervisor
257054ee-8120-5cd5-a8a2-e50245e191bf | note | Verifying Documents - This ITP
74a17379-b133-5478-9c93-c23ab28cad94 | date | Date Completed:
| checkpoint | Final Inspection
be1140aa-847e-593e-be93-1a560b5cd4e4 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
874b3e0c-fa53-5864-91bf-abde275c72eb | textbox | Name:
bfe28735-7fa6-51ad-8342-7a26ae39ce3a | textbox | Position:
bedfa33f-ea5e-50ae-8715-c8e0ba24a77c | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-217-CIV-HOP-Subgrade Preparation - Road Rev 0 | itp | ITP-217-CIV-HOP-Subgrade Preparation - Road | 93ed4a07-b86f-4140-a36b-cb628cdfc27c
| section | 1. Referenced Documentation
| checkpoint-no-value | Referenced Documentation
ae3a06ab-b600-59be-98fd-0c7885b7eac0 | note | Document Title: ITP-217-CIV-HOP-Subgrade Preparation - Road
d900c4f8-28ba-5ed7-9a76-40c5c456d5e9 | note | ITP Description: Subgrade Preparation - Road
9752d344-e3e0-501e-a7ff-733210a20f73 | note | Discipline (e.g. CIV/STR/RAIL): 217-CIV-HOP
2a151781-2bfa-5ac6-98f3-2c901c4f92bc | note | Revision Number: 0
2fcfe915-5b30-5a6e-8d92-9c39f2c50cf1 | note | Revision Date: 27/11/2024
2c8e51c8-405d-5a6f-8171-43cb4f7e26db | note | ITP created by: Cedric Guico
28e83cfd-1865-5500-9296-a881a4befe46 | note | ITP approved for use by: Pradeep Tisala
13dd9261-cb97-5624-abf1-821d284b45b0 | note | 1.1 - Non Dependent
ac7470dd-e4d5-5119-87af-3eabb58a8d41 | note | Reference - VicRoads Section 204
0765fd29-e2e4-5ab9-9f71-366b2ed3237e | note | 1.2 - Non Dependent
72862a21-2a2c-55c3-ae8c-2fa9f37f6d2b | note | Reference - VicRoads Section 173
| section | 2. Preliminaries-Materials
| checkpoint-no-value | 2.1 - Non Dependent
a00ff88d-8c33-5f5a-aa0a-fff1fb9fcab4 | note | Reference - N/A
| section | 3. Preliminaries-Documentations
| checkpoint-no-value | 3.1 - Non Dependent
804fa473-fc52-5530-a72a-49d66572b468 | note | Reference - N/A
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set-Out
049f4249-18b8-53be-b44b-8d12d0e325f8 | note | Reference - IFC Drawings
13fab9c5-f68f-508e-8780-32dc1f54fe11 | note | Acceptance Criteria - Area has been set out in accordance with the drawings
dbdf0549-c3ad-5a81-beae-ae0ccee741c6 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC Drawing/Propellel/GIS Mapping (LOT MAP):
35256112-3058-5eaf-88c5-e3e88e4f2a2f | note | Method - Verify
b2c9e087-aaa5-5bae-802b-346f581d967d | note | Frequency - Prior to commencement of excavation
9242b4bf-d23e-5f8d-ba2f-ed74c61a1e9d | note | Category - IP
1524ebd4-c9fd-5fea-85de-52477b7c817d | note | Responsibility - SE/Surveyor
f0e8c05c-7f96-59f7-af26-e0ae766e6bef | note | Verifying Documents - This ITP
2b123b04-4101-50bb-96f2-9ae39d5beaba | date | Date Completed:
| section | 5. Construction / Installation Activities
| checkpoint | 5.1 - Inspection of Subgrade Material-Subgrade Material Properties
006c6311-25e5-56fe-9743-01c59330ca31 | note | Reference - Section 204.06 (c), Section 204.06 (e) IFC Drawings
6921f7d9-d4fa-534c-b8ff-5735ff252cf6 | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
5315c69e-e328-51e7-9786-fbdbf21d9733 | note | ○ In situ material within 400mm of cut floor level to be consistent with IFC Drawings
01b53d4f-aed6-5b3d-9ef6-3a06ee547606 | note | ○ Assigned CBR ≥ 2.5%
32804467-5cf9-541a-94c2-a1c5b05847ee | note | ○ If parameters are met, rip and re compact to a depth of 150mm.
6a6ca43a-4597-5490-950b-f87dfe50a370 | note | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming Type B fill.
21ee5111-bf78-5624-a843-1684b4f47f7f | note | ○ If existing material needs to be removed and replaced with Type B Fill, ITP-CIV Type B Fill - Road is to be utilised.
80626748-842d-5586-8efe-e217f47a054d | note | ○ Attach: Laboratory testing Verification:
96e5fd3c-3b96-5375-8ae7-9c1c61034ac3 | textbox | Enter: Type B fill Lot Number:
a34e1180-e372-50f3-93f1-497cf053702c | note | Method - Verify-Document Review
98e03ce4-f732-5ff5-a5a0-063a8ef2d510 | note | Frequency - Each lot
5ef4424f-b189-55eb-a9db-021a4277dbb8 | note | Category - HP
5e6347f5-4f57-5485-8f64-aba85d4fda0e | note | Responsibility - PE/Nominated Authority
c2b74c59-4918-50e5-bb03-29274c1aa7ac | note | Verifying Documents - This ITP/Test Report/Referenced Lot number
3e2f93bf-80ee-5b93-8b65-92d812720c8f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.2 - Material classified as silt
95d25f0e-5f5f-552a-95db-8c2a27c99d1d | note | Reference - Section 204.04 b)
3e11dd5a-12ec-564b-ad7d-6f152bccd413 | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type B material without stablisation to the satisfaction of the Nominated Authority
014fd130-25a6-52d7-ae43-fe8078a5fe48 | note | Method - Document Review
e272ddd9-561b-58a9-92d6-24ede00b1855 | note | Frequency - Prior to commencing
21931fc5-8384-5851-9809-951db02db72e | note | Category - HP
8d1f4557-5148-5616-b416-468f18954c38 | note | Responsibility - SE/Nominated Authority
b32827b0-f6d6-5c43-b860-df1549f74d23 | note | Verifying Documents - Superintendent satisfied with Stabilisation, Signed ITP/records
7adc24b6-66c5-5ac3-9b8d-cd6ebc976078 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable)
1a492527-de4e-504e-a1af-6d7efdf969bf | note | Reference - Section 204.06 f)
c0fc51c1-7851-506f-ab59-5ccc4828f2f4 | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
2e5ea80e-ce9a-5cb9-8d94-6f65d5d82f1d | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
c64a46d5-5501-5dc2-9fbd-e456c43a3bf4 | note | Method - Site Inspection/ Document Review
0d8123bc-ac6a-5d75-bea7-f59f5b94bb8e | note | Frequency - Prior construction of the regulating layer
3cc50fb0-8001-57c8-a7d1-7c1aded33033 | note | Category - HP
ce6c2dae-a0d8-5ad1-b6ed-09e219bf2b27 | note | Responsibility - SE/Nominated Authority
cfa7a87d-01a1-5b36-93fa-132dac3c29ca | note | Verifying Documents - This ITP
769ac3a2-8d57-5376-91bc-f967d874aee4 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Unsuitable Material
24db2e64-8200-5f53-8a7c-77e280063f96 | note | Reference - Section 204.07 d)
d7c8904d-5c37-56c7-8ecf-2a36c05e3d72 | note | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
7502f09e-ded4-5de9-bb16-98d4de94d1ee | note | Method - Visual inspection
0e283f63-7bb9-55b4-a9bb-f2a236c7ee97 | note | Frequency - Each lot
5c6bd240-959e-54cc-9810-7cf26c6159ae | note | Category - HP
912a0e43-1227-523b-94e5-81bada77bfaf | note | Responsibility - SE/Nominated Authority
84da6777-fe10-5f39-bdf3-21f60386ed96 | note | Verifying Documents - This ITP
84ba9126-30cc-5f4d-8a9c-6ebfcf2cc3cf | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.5 - Groundwater
483c51e7-3fd6-5158-99a5-02c7c99b93eb | note | Reference - Section 204.06 h)
6433c17f-fa3d-50ea-b637-e34b49366096 | note | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
04e1eceb-c992-5a14-92f3-fefcfdd97508 | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
8801ff4a-a1ca-5323-a8a7-919686a0e83a | note | Method - Visual inspection
cf91217d-b127-533d-a96a-29b2ed635eee | note | Frequency - Each lot
87711c2b-b45e-5f96-979c-ecc865c9a9a8 | note | Category - HP
c3f2ae08-f5cb-55a9-9a74-2cfc0483658a | note | Responsibility - SE/Nominated Authority
d9f2ef00-abb7-5d2f-bf87-3687a87835fe | note | Verifying Documents - This ITP
0d23cd14-8601-571e-acaa-d87e2705c2ea | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.6 - Cut to Fill Zones
60066be2-c548-5a45-bdb3-e09b745c0bd2 | note | Reference - Section 204.06 g)
22ba1f0d-5c62-5efc-9b25-b3c57f459970 | note | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type B material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type B material.
1dc009e0-efad-5a72-a9f8-8b207bd5a2b8 | note | Method - Site Inspection
eddb1fd4-2b80-5bd9-9fcf-d1c80e7e7a57 | note | Frequency - Each lot
f9e9b6a3-0b8a-5051-ab38-b98bdfc09934 | note | Category - IP
270a1eb8-178f-53ca-b302-63e1d4729770 | note | Responsibility - SE/Site Supervisor
ade2c0dd-acd1-5747-b31a-89568bba3b1e | note | Verifying Documents - Sign ITP
8dd1b3b7-4015-5ee5-8dbf-3aababe86005 | date | Date Completed:
| checkpoint | 5.7 - Proof Roll
c84bb3d8-40e0-529f-864e-3cbefba1ecf6 | note | Reference - Section 173
fa3e5b36-a395-5d49-9b97-4f84c91e573b | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
a27be75b-c235-518a-8fea-b595e4030d6e | note | Method - Visual inspection
2edcca5f-be18-54f1-bd33-7cf0d38149cd | note | Frequency - Each lot
c9b49745-9fde-5e72-842e-20eac11dcb9c | note | Category - HP
65b990cd-a1d5-58b9-8e1c-320c5c6e8f35 | note | Responsibility - Site Engineer/Superintendent
8da28191-f1c6-59a0-a512-ca5d654375b4 | note | Verifying Documents - This ITP
3068fbc2-f904-513f-9cc8-8b1c1efd17ac | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.8 - Compaction Testing
861b76fd-ba95-5dd5-a98d-78bcf0a92c58 | note | Reference - Table 204.131
dc6ea0a4-b787-5fb1-9684-576b341726ee | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
77c02592-33f7-5965-8963-6087531d7cf2 | note | ○ Ripped and re-compacted material below Cut Floor Level
61d584f9-95f8-5a79-800c-a755f23373a0 | note | ○ Scale B: Standard Compaction 98%.
cba39fac-42fb-56ba-be6f-8be9f838c6b6 | note | ○ Attach: Compaction Test Result:
27e2a015-2818-5e25-926a-68032d771448 | note | Method - Document Review
0782a018-a391-52ca-bbfc-393e36bc2ed4 | note | Frequency - Each lot
b9b10f5e-97bf-5937-83e2-8a3fde15c9e8 | note | Category - IP
6e2d6a86-650f-5e31-b79d-b215e1c0191c | note | Responsibility - PE/SE
20982af9-e370-5004-aa78-99e8580a8441 | note | Verifying Documents - Test Records, Lot Register
40f6be5a-70bc-54f9-9053-2c18bada8267 | date | Date Completed:
| checkpoint | 5.9 - Post Compaction Material Property Testing
1187bb8d-edd9-5716-a039-36a0c3483d38 | note | Reference - Vic Roada 204.04 Table 204.141, Section 204.14 a) or b)
22ac1d0e-316e-5b70-ab12-63f1b6003709 | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
7d0a3c86-019a-53b3-85ec-11cf7eb2887b | note | • CBR ≥ 3% and Swell ≤ 1.5%
f231b31f-5de5-5f4d-b87c-40f5ca4a1b18 | note | • Max Permeability = 5X10-9 m/s
6b30647a-26e6-53bf-8a27-11fd7ab215f7 | note | ○ Grading:
bce54021-6fab-50a7-8db7-3cf1e740cca1 | note | • 75.0mm 100%
eeec9e59-0aad-5613-9870-cae0a6d19cf5 | note | • 4.75mm 40-80%
d2f407ea-1f04-58bb-a11e-3d1e559cd932 | note | • 0.075mm 10-40%
f20e7992-27af-5fe7-92ea-ef2391949c60 | note | • Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
676c7a8b-8216-5cc5-855e-010d6952fa87 | note | ○ Scale B:
35e1b51b-28fe-5df8-8d69-46e530b7d20c | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
b2483daf-9566-5732-8045-563d448ddeaf | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
10bed505-68da-5ad3-9c86-c1c0465fd622 | note | ○ Attach: Post compaction test results:
3dedfc47-5ad4-5532-8560-21d45408e347 | note | Method - Review Document
0f898efa-f4ac-5fbd-8fdd-166701397c5b | note | Frequency - Refer to Section 204
253176d4-ce50-5ad3-a2aa-0b352ac8f7cc | note | Category - IP
234c85c5-ebd8-561d-9bf2-16dcd2215298 | note | Responsibility - PE/SE
8d30198b-a413-5c28-8d8e-332ba293d8cb | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
248c16fc-ba04-538d-8751-6fb7604c52b4 | date | Date Completed:
| section | 6. Post Construction Activities
| checkpoint | 6.1 - Survey Conformance
e48a7927-a1c0-5105-ad4a-ef9741145781 | note | Reference - VicRoads 204.03f,g and h
122ace27-64a2-5b43-895e-08c3d062181d | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
24d2a366-6c00-51a9-a536-22f9b6048afc | note | ○ Level tolerances (Scale A):
56aa437c-ade9-5afc-932c-550ad5a72588 | note | • Range x = +5, -15mm
85ae3850-b36a-5f4f-a972-c9200bbebf2b | note | • Max S = 12 mm
c3829083-081f-59a7-81fa-7d00c22cf7a6 | note | • 80 measurements per lot
df872d3d-c1fa-54cf-851b-aef2d4bfd0de | note | ○ Level tolerances (Scale B):
4df18165-d8b4-5431-8d36-ad7abb7edfc6 | note | • Range x = +5, -25mm
cd30031e-e8c7-5f3e-a6c8-40f02ae5bed9 | note | • Max S = 15 mm
bbb9a867-5c2a-542c-8fb3-ee19f6820119 | note | • 40 measurements per lot
5f187ec1-33f3-5336-86c4-0b7bd08b1868 | note | ○ Level tolerances (Scale C):
9b1d2d8b-3dfb-5e4d-a68d-84edb4fea3fc | note | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
3e52f572-5c51-55e6-ba60-a042e3b96048 | note | Method - Review Document
e43c399c-65e9-5283-bdbe-e21efb145933 | note | Frequency - Each lot
6ec17fd9-e027-56b3-9176-9d113c3ad436 | note | Category - SCP
be668823-88b2-5145-ac1b-30cf0019b159 | note | Responsibility - SE/Surveyor
0493af51-d82c-5e94-a290-a664f2e5a6f8 | note | Verifying Documents - Sign ITP, Attach Survey Report
5bb6d329-7f9d-56c1-a75f-2f1fb912d4d8 | date | Date Completed:
| checkpoint | Final Inspection
4944243c-c2ed-5c25-88bc-1373299fb3d2 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
e0646d04-1ae7-5740-a992-904d9ebc9ca5 | textbox | Name:
53bb8171-1db4-58af-907e-57046a4059ab | textbox | Position:
d854d8ca-0958-5d06-b7a5-577d00eeb911 | textbox | Date Completed:
| signoff | Sign ITP
5765976a-9835-4fa5-b214-ad38ba94f9c0 | checklist | ITP-218-CIV-HOP-Type A Fill - Road Rev 0 | itp | ITP-218-CIV-HOP-Type A Fill - Road | 95ca80eb-6742-4732-be0f-14ef2be1da06
e2ee1c46-4da8-4750-8997-8fafad3cd0b0 | section | 1. Referenced Documentation
a1d51c55-8eeb-4e86-9f05-b44880799d07 | checkpoint-no-value | Referenced Documentation
19ddd7c6-d115-5078-bbfa-2bb725553b10 | note | Document Title: ITP-218-CIV-HOP- Type A Fill - Road (Supply and Install)
b1688898-af57-5a77-b796-be05817a05af | note | ITP Description: Type A Fill - Road (Supply and Install)
db066cac-7e2c-5d19-b91a-f877289f6ec8 | note | Discipline (e.g. CIV/STR/RAIL): 218-CIV-HOP-
aa07528d-c2cf-5845-a820-98924efb0a11 | note | Revision Number: 0
0ec61fc5-4ab9-5a33-974d-2c3a97579163 | note | Revision Date: 28/10/2024
42c6c8bc-a728-529d-bdef-fc6d9a3acc70 | note | ITP created by: Cedric Guico
04ad805a-eff2-5531-9e82-cc0055cf958c | note | ITP approved for use by: Pradeep Tisala
281098cd-0d92-5d3d-a48c-817a97cbe6d8 | note | 1.1 - Non Dependent
0d370d08-5c61-5283-bda0-053a995f43b1 | note | Reference - IFC Drawings
a175d07e-8fa3-58a7-804b-2f046966f1fe | note | VicRoads Standard Section 176 (Sept 2008)
89f57077-9de4-5911-a3e1-1a1d91bcb083 | note | VicRoads Section
edf8ac37-d178-5d13-8755-adec757a13ad | note | 204 (Dec 2015)
2c2d41dc-feda-59d7-b60f-704c2c9a0003 | note | Code of Practice RC500.20
662bbf3d-951b-50b5-b8bd-a70bca4fca17 | note | Code of Practice RC500.5
7b122f7a-3f94-4597-a01e-729178b54da1 | section | 2. Preliminaries-Materials
765e4387-27fa-44d3-aa1b-6bd348f618ca | checkpoint | 2.1 - Material Conformance
98ea6876-c08b-583d-8ece-2f3a26d7f0f4 | note | Reference - Section 204.04 b) Table 204.041 IFC Drawings
83e29795-c43f-50fc-8fa2-543f0d35518e | note | Acceptance Criteria - Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
167ab4eb-6f88-581a-9620-bc5b281df4a4 | note | ○ Assigned CBR≥8%
33a5a072-9fa8-5fe9-a56e-5267cc9e3d29 | note | ○ Swell ≤ 1.5%
11eff2b1-91c3-5168-82ed-dead1c7189d9 | note | ○ Permeability ≤ 5X10-9 m/s
36306193-dca1-5c67-8fc4-1d99ff482761 | note | ○ Grading:
f55471f2-e841-5a00-83d0-23e001f388d9 | note | • 75.0mm 100%
887823ec-9b7b-582a-af22-8457a6ebb6b2 | note | • 4.75mm 40-80%
dc54b8b5-b459-5f62-a21d-08d80d24615a | note | • 0.075mm 10-40%
b7ae7f43-83a6-5d51-84bc-31cae86c85ee | textbox | Reference: Material approval in Teambinder:
c8a617a6-88fb-51f7-a264-6db870f23887 | note | Method - Document Review
bde6dbec-3059-5cf3-a637-a43460fe1ee2 | note | Frequency - Once, for each material type
39605636-0715-590b-bb5a-380592c78d51 | note | Category - HP
eeaa1b45-2897-5e95-85ba-dfc5f7aeace6 | note | Responsibility - SE/Nominated Authority
ced1e042-174c-5234-b604-94bfc7759ea5 | note | Verifying Documents - Supplier Material Conformance Certificate
c7aaa1c3-096e-5da9-915c-1ecd5398dd63 | date | Date Completed:
2bc4eabc-0ca5-45ae-b5ce-e35a3452f3a8 | signoff | AUTHORITY HOLDPOINT
15434780-887b-4152-bfcc-4deb1dea4753 | section | 3. Preliminaries-Documentations
2a574c11-2dff-4fe4-8584-da3ca4ef603c | checkpoint | 3.1 - Pre-Commencement of Fill Works
b0759753-5457-5bed-87e9-09c67cbedc64 | note | Reference - Section 204.10 (b)
dde01fa7-0e77-55d8-b99e-8a008e2f6db0 | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
a936a6e6-0367-51e5-998a-7370418933a9 | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
8c128ebf-74b9-5107-82ef-6b8a406ca0f6 | note | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
eaacfaaf-7b7d-5747-b321-ac7f7436a2f1 | textbox | Reference: Subgrade Preparation Lot Number:
d928f46a-4eb9-5dd7-84e8-72d8922f21ad | note | Method - Visual Inspection
52450297-61b5-529c-b685-228fd6d838cb | note | Frequency - Prior to commencement of fill works
448b9ac8-2128-5cac-9abb-4c080d4a9c13 | note | Category - HP
59978814-c441-5c3f-82a4-80f5f9427e2e | date | Date Completed:
96d52a2f-da91-4fa2-9401-d34b4c3eaedc | signoff | AUTHORITY HOLDPOINT
d55866d3-0f28-4692-a7fd-d2ac093390e8 | section | 4. Pre-construction / Pre-installation Activities
33ebc3a5-d00d-4292-bfaa-1fefe9be795b | checkpoint | 4.1 - Survey Set Out
beee4df8-2fa2-5010-8c94-0a858442a29c | note | Reference - Design Drawings
3f3355ec-ca67-548b-a1e8-66251e43ddc4 | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
71810a6e-d50a-5bb6-9b5c-21e263917e78 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
c440cb81-3bad-545f-ac27-4216d29c41be | note | Method - Visual Inspection
0792c1e2-ecb0-59c1-9325-b11041ecc5c0 | note | Frequency - Each lot prior to commencement
effeed58-588f-5223-b52c-155cf0068824 | note | Category - HP*
c70536f9-703c-5dfe-ab44-97bb640b2487 | note | Responsibility - PE
526e0366-b7cc-524d-88d4-e29ab8c6f4d0 | note | Verifying Documents - Signed ITP, Lot Map
4223832a-5a5c-5059-a8a4-8b25bb2111ff | date | Date Completed:
c87dc116-160d-494d-9710-53d76f1573b2 | section | 5. Type A Fill/Verge Activities
adba1e7f-bc7b-42d5-b0e6-5b2cb8614116 | checkpoint | 5.1 - Placing of Fill
176d48f9-ea88-5285-ac41-9b2fb0aaf312 | note | Reference - Section 204.10
6d509333-16cb-5988-be1a-5b8ea5ac6958 | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
686a520a-ef35-5fa2-b9e2-6890a42bca8a | note | Method - Visual
1bc64947-7032-5632-9cf3-f9da9ace315c | note | Frequency - Each Lot
8536581c-4ebb-5f4b-976f-552301b31cfd | note | Category - WP
532cb39f-5f6c-5394-a1fe-05f08181fd15 | note | Responsibility - SE/Site Supervisor
028f99ef-7438-5c17-812d-cc0d453d025c | note | Verifying Documents - Sign ITP
9632e991-8707-5fe5-a89b-41174f8c2691 | date | Date Completed:
3e8025c5-951f-438b-894c-28613bc564db | checkpoint | 5.2 - Test Roll
bc1053f6-426d-5c8d-8290-4b50bbd6dece | note | Reference - Section 173.03, Section 204.12
af5ec64c-49a9-545b-85ea-f0cdfff173e3 | note | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
61ec8b8c-24c1-53c2-976e-b1fd6879cf3c | note | Method - Test Roll as per 173.03
977373dc-abd1-55ef-b7d9-e1f6473f1220 | note | Frequency - Each Lot/Layer
b92f1bce-fc32-532f-a6d8-7835527a3a15 | note | Category - HP
8c489676-8ad4-5de8-a797-2ea97a52c6a6 | note | Responsibility - SE/Nominated Authority
1445eed7-8625-5c59-8a47-247e3ce88c05 | note | Verifying Documents - Sign ITP
279893bf-0b4c-56e3-a04b-0678c6f920ce | date | Date Completed:
d3aab339-8ee2-4136-88a4-59e5fa25b059 | signoff | AUTHORITY HOLDPOINT
9b813820-3aa1-4fff-8324-c7f9494dc8bf | checkpoint | 5.3 - Compaction Testing
f55954ee-9b68-51e5-ab34-9b1458a8bdb1 | note | Reference - Table 204.131 Section 204.14 c) Table 204.142
fff29af4-01d7-5c21-b947-5ca4a2198cd4 | note | Acceptance Criteria - Testing as per 204. Ensure testing is tracked and reports available.
568bb44c-b921-5c72-b677-3a2ccad7116a | note | ○ Standard Compactive Effort
b0d965cf-1d77-55f3-bf1a-4ba369586d48 | note | • For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
61d17ef5-997a-583d-a3fb-15ea772fd1a7 | note | • For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
9092cde4-7c61-5273-b092-02aaa3a0ccae | note | ○ Compaction and Moisture content
1338cb97-fcf0-559c-a9ae-9774e3d47ba4 | note | • Scale B: Standard Compaction 98%.
3885d04c-2320-5e01-847e-f68c4e166c74 | note | ○ Lot size - the leser of one day's production or 5,000sqm
d19af8c8-4be0-55ba-bc81-856387b325af | note | ○ ATTACH: COMPACTION TEST RESULTS
9ee842e8-205d-51a0-8bd3-f9ba2164bf8a | note | Method - Review Document
93d24f45-1a3c-5321-bd94-70d63d6b3c5b | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
85cb33c8-e079-5bde-9719-608a3171e1c2 | note | Category - IP
2ecc3657-1ed7-5673-a21a-80f8e44b9091 | note | Responsibility - SE/Site Supervisor
f47ad164-f945-521f-aab7-f41d5d05b127 | note | Verifying Documents - Sign ITP, Attach Compaction Test Report
0c9a7bca-5f38-5805-ba55-1549ea615ad1 | date | Date Completed:
5e90cdda-f777-47c9-b075-dda95d43deed | checkpoint | 5.4 - Preparation of final surface
f9b82bb1-f074-5643-b29b-7fb2364aa437 | note | Reference - Section 204.15, 204.03 (g)
b358599d-4516-5ad7-be80-ad9b0ed7cf11 | note | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
2e81b214-320d-5be2-a437-beb9fa9dab79 | note | Method - Measure
464b1be7-6790-5494-983f-8b67a2153d73 | note | Frequency - Top layer
77d58644-c6d2-57ce-9ba8-5c0aff6d65d4 | note | Category - IP
e95038ba-0d25-52c6-aaa2-888de819955a | note | Verifying Documents - Signed ITP
567e4447-2db0-5553-a73e-6191bb507418 | date | Date Completed:
93f04eda-9108-4f83-84cd-51a4362556a1 | section | 6. Post-construction Activities
c5f615ae-738b-4b73-af7d-537e8dc93db0 | checkpoint | 6.1 - Post Compaction Material Property Testing
1fe498ea-36f3-5781-b199-a4ec421dac81 | note | Reference - Table 204,041, Table 204.141 Section 204.14 a) or b)
a2acf588-c08e-5abc-9f7e-faaf2e9d273a | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
09c6a4b4-4893-5c3e-9285-b68ecc83e637 | note | ○ CBR ≥ 3% and Swell ≤ 1.5%
b673a2fd-b306-51b1-889b-d317eacc20b0 | note | ○ Max Permeability = 5X10-9 m/s
0f21ac78-1ae1-5a5f-b7cf-c9d35723c602 | note | ○ Grading:
d5700551-9cab-5fa9-9eea-8813469c1113 | note | • 75.0mm 100%
235390b3-1f01-5fb6-88e5-24acf53f29fc | note | • 4.75mm 40-80%
7d9fb7eb-366d-58aa-9e38-fec02b06fd30 | note | • 0.075mm 10-40%
5f964964-92bb-5dab-843c-b5f6840189af | note | ○ Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
6ae0dfed-7d5a-57c4-8cd2-e37a0762035f | note | ○ Scale B:
552fa734-8c62-533a-9364-22cf8497eef2 | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
35e5575f-278a-5c7f-8976-73c3fb9f4bdd | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
e502188e-5278-5a56-b0fa-cd05a911f591 | note | ○ Attach: Post compaction test results:
09f67c26-7277-58c2-b274-fa8b9337e463 | note | Method - Review Document
16554a5c-22a3-53e1-96b4-571e03643ee8 | note | Frequency - Refer to Section 204
aa60cf95-d546-5a8f-b229-9f9fd932ca31 | note | Category - IP
ae5efe1c-099d-5e42-9148-447d879d7d68 | note | Responsibility - SE/Site Supervisor
d8f877a5-256e-5d3f-9d98-022220ecbf8b | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
fc6ff704-9b66-56f9-8c72-5bb8d40251b3 | date | Date Completed:
53548024-edfe-43d0-855e-fcce68a07899 | checkpoint | 6.2 - Survey Conformance
1afcdb11-46a7-53b4-b422-7367c8f6676b | note | Reference - VicRoads 204.03f,g and h
14aea2ec-99ed-5b5c-b2ee-d0338c4af5bc | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
c5fd2474-9e35-5ece-8c11-277ce44f413b | note | ○ Level tolerances Scale A:
1a1c5c16-422a-541a-9d8b-a668067c87e0 | note | • Range x = +5, -15mm
84a967bd-1223-54b3-848f-9d2f7ec67ac9 | note | • Max S = 12 mm
fc067ab8-d4da-5e6f-a362-90aef524a87d | note | • 80 measurements per lot
7d689e41-5a7f-531d-ad56-5bf646d16ada | note | ○ Level tolerances Scale B:
d70e7c38-a5ef-5d46-b9a3-a55c1b1d62f2 | note | • Range x = +5, -25mm
84cb3bd8-2fca-541e-b01c-09a998eee8dd | note | • Max S = 15 mm
443bc57e-8c3f-57d1-a503-67a77f062c40 | note | • 40 measurements per lot
a122079a-1cae-5d01-986f-53718a5bf5a6 | note | ○ Level tolerances Scale C:
cb9ff527-2887-54eb-ba39-f37ce1c56b07 | note | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
e219ff12-c3e5-5183-bcb5-a094614ef984 | note | Method - Document Review
daf26ab1-bd00-5d1e-bb2b-6c943e8a8913 | note | Frequency - Top of Type A/Verge
2d951b43-d7b6-5ec9-9cae-abc6b6be2aee | note | Category - IP
32b59760-b09d-5e74-97a8-91a15fa8f7be | note | Responsibility - Surveyor, SE/PE/SPE
75a278e1-d5c0-509d-8ce1-69c21e3b13d6 | note | Verifying Documents - This ITP, Survey Conformance Report
278aa528-603e-5796-87d8-b74eb4ef3155 | date | Date Completed:
d0560e37-fbda-4eed-ae39-eb757c2c8114 | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
15493a6b-73f9-512d-a35b-2c8d62deb02b | note | Reference - MRPA Quality Management Plan
9541c672-cf84-5fd6-ba07-db86c9d298af | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
df5935e4-ce18-585e-9831-c777996fdb8f | note | Method - Document Review
16188793-d0a0-599d-b7c0-154e95eeb30a | note | Frequency - Once, prior to closure of this lot / element / Work area
587af470-9522-580e-8fdb-a5e539957ecb | note | Category - HP*
f49b2e9c-74a9-5695-8f7f-fc148e296239 | note | Responsibility - SE/PE/SPE
eaeea5fd-6608-5729-876c-515e586021ae | note | Verifying Documents - This ITP
d8991b21-f937-5cfb-92a9-797dd756490a | date | Date Completed:
00a0c1ef-c86a-4b13-9550-1bfeac6eac61 | checkpoint | Final Inspection
4057bd54-ea3e-523f-8a1b-047ec468001b | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
5587b9cd-3c63-50d1-baa2-e771eb2eda22 | textbox | Name:
5d3709b2-3e36-5745-8dbc-21af2a1747e0 | textbox | Position:
2baf4aef-881a-5dce-b570-f9446c531171 | textbox | Date Completed:
03f39c84-855d-448d-9493-4700d83b7d62 | signoff | Sign ITP
| checklist | ITP-219-CIV-HOP-Type B Fill - Road Rev 0 | itp | ITP-219-CIV-HOP-Type B Fill - Road | 2565bb16-7d5f-45be-b165-c73d7899023d
| section | 1. Referenced Documentation
| checkpoint-no-value | Referenced Documentation
acb0a8f7-e813-55c8-9efc-3a81b5c527b6 | note | Document Title: ITP-219-CIV-HOP-Type B Fill - Road (Supply and Install)
66094893-57da-542e-ab84-36b1106c9cd6 | note | ITP Description: Type B Fill - Road (Supply and Install)
3fb9dd41-a5fc-5ac7-b10b-e2bcfec0ec0d | note | Discipline (e.g. CIV/STR/RAIL): 219-CIV-HOP
d27dbd9d-b67a-591c-9f38-5c98372d45ea | note | Revision Number: 0
2b701284-f79b-5838-b8f2-6bef253db65e | note | Revision Date: 28/10/2024
75bfac59-de84-5f83-8030-b1b936d17c27 | note | ITP created by: Cedric Guico
daa923be-2f1e-5235-af42-ac1c16fd9982 | note | ITP approved for use by: Pradeep Talasila
8f0901c2-996f-5a78-be97-6e024c24e061 | note | 1.1 - Non Dependent
44bbfa86-d30e-56cd-9d24-62d661046764 | note | Reference - Reference Documents:
45ea5528-f2d1-5eef-8106-92796fc22afd | note | IFC Drawings
8c9fe042-083e-5f6a-b91b-30eaa6036271 | note | VicRoads Standard Section 176 (10/9/2008)
191b3e30-4b4f-56b5-a6e0-c2cd90843b29 | note | VicRoads Standard Section 204 (29/12/2015)
| section | 2. Preliminaries
| checkpoint | 2.1 - Material Supply
7c0d5cbd-b6a5-5850-9434-0c856eea7971 | note | Reference - General Notes on IFC Section 204.4 c), 204.06 e)
d8410b39-f91b-5866-aa12-1146503ed5b9 | note | Acceptance Criteria - Free of topsoil, deleterious &/or perishable matter and maximum particle size ≤ 150mm. Swell < 2.5%. CBR >2%. Material classified as expansive or silt, either before or after compaction, shall not be used as Type B.
77afc90a-9802-5b3f-8f69-7b8697fbde73 | note | Method - Doc. Review
8a77c0d8-d768-55b5-bfb8-10d2f50770fa | note | Frequency - Prior to Commencement
9d9dc511-62a0-53be-ba93-dadf357000d5 | note | Category - HP
10f732e8-5532-5e6a-8e4f-6e2e14be615b | note | Verifying Documents - NATA Test Certificate
ce6f80da-f311-58ed-baf7-f8dc92e1f791 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Pre-construction / Pre-installation Activities
| checkpoint | 3.1 - Survey Set Out
5f67bd80-fe48-58ff-a391-08676d3c2b37 | note | Reference - Design Drawings
23fca6d6-63df-5263-a753-8f7b7b967046 | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
8c373e32-c7e9-59bf-84be-679d3ef86e2f | note | Method - Visual Inspection
5ac98b46-32d4-50cd-bb21-4ad129ca17be | note | Frequency - Each lot prior to commencement
14034f55-1442-5b29-b835-c63e4a7bb2bd | note | Verifying Documents - Signed ITP
37acdafd-83df-5e63-ac70-54ea68f8ef03 | date | Date Completed:
| checkpoint | 3.2 - Pre-Commencement of Fill Works
bd99e62e-42e2-5296-a2ea-034d711116eb | note | Reference - Section 204.10 (b)
b8c91b57-fd72-594b-bd19-cb3b85ca37f2 | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
9e146468-3d4a-5572-923c-af23ff8cf874 | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
e94d7045-6c6f-59b2-9274-3f70fb5d64be | note | Method - Visual Inspection
fd27578c-7337-5836-983a-7f059e64c6a7 | note | Frequency - Prior to commencement of fill works
831ddce7-c6b5-5e6f-bee3-f90be613075c | note | Category - HP
11bf6365-15a4-5881-82ae-9ea09f085908 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4. Construction / Installation Activities
| checkpoint | 4.1 - Placing of Fill
5cb68a68-da10-5c01-a943-ed6d82136faa | note | Reference - Section 204.10 (d) (iii)
7d2a4be8-f0e2-5386-8fd0-61409756a0dc | note | Acceptance Criteria - Type B material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm unless dispensation granted by superintendent.
ab5b33b0-2bf9-597d-a5d2-9fee160c1786 | note | Method - Monitor
cf0e2d35-cb37-5db8-9a26-3d8d49b6780b | note | Frequency - Each layer
da6791ef-8064-5fa5-b305-5a4eeea23c2a | note | Verifying Documents - Signed ITP
8c24a632-0362-5767-8bd5-117ffa9d8e7f | date | Date Completed:
| checkpoint | 4.2 - Keying of Layers
f901051d-2aa4-53e6-b3e3-e2aa990a2a43 | note | Reference - Section 204.10(d)(i)
5713f8e5-92ae-56fd-9ef7-4c533b5be59b | note | Acceptance Criteria - Each layer of fill shall be keyed into the layer above by creation of a textured surface.
821e80ef-0c07-51f5-a032-0d4f95911b60 | note | Method - Monitor
cc1e1765-7268-5b27-8d37-d59ac84c6af9 | note | Frequency - Each layer
a13b735b-aad0-532a-9fc4-3c94f4a2e724 | note | Verifying Documents - Signed ITP
d70f54a0-90d2-54d7-814d-bbc7eb7cb8c6 | date | Date Completed:
| checkpoint | 4.3 - Test Rolling
56d79405-b2ce-5109-b39a-153a4b653b88 | note | Reference - Section 204.12, 173.03
1eab19ee-7000-55ab-b045-e55d3ea1e1bf | note | Acceptance Criteria - All layers of fill and cut floor level to be test rolled in accordance with section 173.
21c761e3-6867-5f7c-929e-8def23df36df | note | Method - Measure
4f1c9c99-f93b-53eb-b45c-9ab65f14d2aa | note | Frequency - Each layer
a6861437-0889-5a37-ac43-36474f30343d | note | Category - HP
42e6014d-d3d1-57b7-8f08-83e3d0ded7c9 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 - Post Compaction Testing
d5549135-26d9-5bf7-9941-35c7c6ce5f8a | note | Reference - Section Table 204.131, 204.13, 204.14
35b77117-3aa9-53a4-9af7-f66a346b3f5a | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level
1e1e2bae-bacd-51de-9a22-ce340949c20c | note | ○ Scale B: Standard Compaction 98%.
d6bdf326-177e-538d-96d6-76d1d0524596 | note | ○ Attach: Compaction Test Result:
4d735e21-b06d-537c-8a17-5a9c802b021d | note | Method - Doc. Review
e8573c2f-d8c7-5be1-a479-a6ebf11ecd4b | note | Frequency - Initially test every lot until three consecutive achieve passing results. If achieved, minimum frequency of testing from Table 204.142:
1d4462fe-56cb-5d33-94a4-356e2c452acd | note | ○ Placed within 400 mm of top of Type B: Test every second lot of like material and work
b801eb5e-ed65-5d93-ba1e-a0da915a1a5f | note | ○ Placed more than 400 mm below top of Type B material: Test every third lot of like material and work
d48fee27-be37-57d8-bf4d-1578fd6f0603 | note | Verifying Documents - NATA Test Certificate
0987aed6-c9fd-5ae1-b4dd-e6cafdfd376d | date | Date Completed:
| checkpoint | 4.5 - Preparation of final surface
56882728-8a81-532d-88ac-b879a1ea6078 | note | Reference - Section 204.15, 204.03 (g)
8d3ecb9e-a28e-5968-bda6-fdb204367b66 | note | Acceptance Criteria - The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
b6e2eadd-c991-59a8-911d-b00bb6d66350 | note | Method - Measure
c2e56a2f-8351-5ff1-a138-fba1c532dc45 | note | Frequency - Top layer
868d90c0-c801-5153-b0f5-1e892a72275c | note | Verifying Documents - Signed ITP
60da8d07-fe46-5fb2-b2ab-20f4160a9df5 | date | Date Completed:
| section | 5. Post-construction / Post-installation Activities
| checkpoint | 5.1 - Survey Conformance As Built
ca5b1e5e-065a-527f-ba09-f5bf72c83e04 | note | Reference - Section 204.03 (e, g & h), 206.16
73d24cb8-6a21-5eb4-8c06-db723e06dd1f | note | Acceptance Criteria - Surface is not to be more than 15mm or less than 30mm from what is specified in IFC drawings
e984124e-0bd3-5b97-b7c0-5925e114f97f | note | ○ The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
184ce952-1530-58ed-8e8b-b64a75ecff9a | note | ○ Scale B:
4cf234a0-e407-5658-8e9c-1a425f5fcc2e | note | • Min. No. of Measurements Per Lot: 40
99133f43-4bd1-5b70-8ad5-d1833306eddd | note | • Tolerance: mean value of readings +5mm to -25mm and Maximum Standard Deviation to be 15mm
d8253628-bba2-5b12-a996-e65c246ba94d | note | Method - Review
7278af70-b0a7-59fe-9ef3-bdf6608e6d5e | note | Frequency - Each lot (Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2)
29d92c92-0c71-5d95-b804-12aa6bd26950 | note | Verifying Documents - Survey Conformance As Built
f1bbbfc1-d0ad-5037-be88-db1c14dbe9e4 | date | Date Completed:
| checkpoint | Final Inspection
d5adbf39-13f3-5556-9d44-be77cc582dd1 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
124c84dc-b26c-5658-ba56-9bc3c4060c01 | textbox | Name:
5db359ba-7f49-5209-bcbf-552e7d6b7ae4 | textbox | Position:
abdd0675-0ff5-5379-8bb7-ffef170109ed | textbox | Date Completed:
| signoff | Sign ITP
| checklist | ITP-220-STR-HOP-Bored Piling Rev 0 | itp | ITP-220-STR-HOP-Bored Piling | 36e2df45-99df-407e-860c-9b2e8fe89a2b
| section | 1. Referenced Documentation
| checkpoint-no-value | Referenced Documentation
1e67540f-8c5f-56be-95c9-fd2e1a691b42 | note | Document Title: ITP-220-STR-HOP-Bored Piling
39922a44-0b6d-5e83-b01c-7ef8f8a40e74 | note | ITP Description: Bored Piling
b61b7ea4-c47c-598f-819b-1cb18c0b68f8 | note | Discipline (e.g. CIV/STR/RAIL): 220-STR-HOP
51e9bd01-e907-5653-afbe-c3e9546da598 | note | Revision Number: 0
a908fbfc-f310-50a4-a685-7d409e39c314 | note | Revision Date: 6/11/2024
9d040f65-1f3c-5cf9-a3fd-5a360d553f30 | note | ITP created by: Cedric Guico
3eb9cf9f-7453-5fb2-af59-9104299e017d | note | ITP approved for use by: Pradeep Talasila
eb1516f5-6427-5004-9d4b-e11fdd1b733b | note | 1.1 - Non Dependent
c523516c-50ab-5b0f-9a74-f0e048c1dddb | note | Reference - VicRoads Section 606 - July 2017
75b7b5f3-e00f-5d0c-9638-87e9989f675e | note | VicRoads Section 610 - Feb 2020
1106f812-4e99-53ad-8f67-38e1593f57a1 | note | VicRoads Section 611 - November 2018
f5f24545-e031-51f5-bdcf-3935dabfe2f3 | note | AS2159-2009
add50412-2cea-52f0-96f2-606bcbf12552 | note | AS3810.1 2018
acdcc83a-5dee-5c0b-8e7a-8e135fb727df | note | AS5100.3-2017
| section | 2. Preliminaries - Materials
| checkpoint | 2.1 - Concrete Mix
5f121ea1-531d-5424-bb4b-06774bd33a7e | note | Reference - 610.07, Table 610.071
30c02ec1-b950-5d60-9d23-afd0bffeb0fc | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
217892aa-1dbf-5411-8ef9-c5b949935cc3 | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
06787c65-1541-5c61-909d-d8deebbcada5 | textbox | Enter: Teambinder Material Approval number
81c6df64-566f-507d-a44f-1eb2bb317c01 | note | Method - Document Review
7c585404-9102-5a0d-bb40-20d57c8cdeb1 | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
ee697bb7-6c83-5993-b2cb-9f57c0e316ed | note | Category - HP
9cd81a5d-b6b4-5dbc-a746-ddebac4b2990 | note | Responsibility - Nominated Authority
9428cfc1-b994-5047-a9d9-ecdf5c337c5c | note | Verifying Documents - ConQA Hold Point Release
62fe3aef-33ce-53c7-8da6-d62b936833fa | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - ACRS Certification (for Reinforcement)
856803db-faf5-5d3a-8577-64d61d63a50e | note | Reference - 611.05 (a)
4e141d18-6bde-5ba0-8ea0-e3130354692d | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
ea4ec80e-93c0-5df0-9da1-b009866c9940 | note | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
0dbdaced-7b78-5063-af38-9ccfbca98177 | textbox | Enter: Teambinder Material Approval number
a5b30f77-c2d7-56d3-b636-87e86db217ef | note | Method - Document Review
c5cbd37a-c5b5-579e-b9cc-01b30b77b995 | note | Frequency - Once for each supplier, 14 days of award of contract
0d9adbb0-0a24-59bb-abd4-70b76110b454 | note | Category - HP
25971cab-a8e3-57bf-99de-80878d6f58c9 | note | Responsibility - Nominated Authority
e06529fd-a40a-525e-9034-ac9e9f2dcfe1 | note | Verifying Documents - This ITP
a82b306d-77ca-5692-a4b5-5fc954161c73 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Bar Chairs/Aspros/wheels Certification
db02f381-2ac9-52b7-8ef6-3c91ea70421d | note | Reference - 610.26 (a)
ef483d3e-39f6-5a0f-b1b4-3cffc10b090b | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demostrate suitablity to prevent excessive deformation under loads.
813ad428-9b94-5559-8277-12eca2b7a86a | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
3027b0d0-62f2-5dfe-ac04-76674023a427 | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
4b74ab51-4878-56ef-a731-ea6654627ca4 | textbox | Enter: Teambinder Material Approval number
2a4cfbee-4884-55eb-b435-e9f49afa1443 | note | Method - Document Review
8f0fc3ac-5c28-57ca-9d21-6266e9d2e8d1 | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
19e427d7-8207-53ce-87a0-a0568283bb3c | note | Category - HP
607fb6ee-fc3f-5ff5-9dc8-c9b4137cf2e2 | note | Responsibility - Nominated Authority
05a91867-f692-50f1-a195-4f30546419b1 | note | Verifying Documents - This ITP
2df8c190-e105-53ae-a802-f7dee73d19b3 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries - Procedures & Documentation
| checkpoint | 3.1 - Working Platform certification
0bcab087-8903-55e7-a389-113b66ca5768 | note | Reference -
b896779d-77d7-5c5f-a18b-63261c664759 | note | Acceptance Criteria - Satisfies minimum plant bearing pressures requirement. As per seperate ITP.
413f5098-655e-5d59-ab1c-fbc29ff4eade | note | Method - Document Review
b01aab19-cc98-5fb6-8e4e-72d703d58b42 | note | Frequency - Prior to works commencing & after rain event which there is >10mm in a 24hr period.
02f478c1-618c-5e1a-a37b-fa09bacfab9d | note | Category - HP
b7b71ca3-0b0c-55b3-b0be-9d27c4fcf0ea | note | Responsibility - Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
25ba6366-c229-5a29-ab08-89bbcc70a376 | note | Verifying Documents - This ITP
e4f73645-7d1c-5ae9-a998-ba56e0a0a7b3 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Piling Operations Work Procedure
c026145f-8fab-5086-ab86-df85f684bb89 | note | Reference - 606.03 (a)
cafbb4fc-50d0-5801-9d03-6d69c707b948 | note | Acceptance Criteria - Piling operations work procedure to be submitted for review to the Nominated Authority.
e75af755-fe47-56bf-8f37-0bb37bab9596 | textbox | Enter: Teambinder Approval number
4683f993-30d8-5fe5-bcb0-31f8ae339d76 | note | Method - Document Review
484d61aa-ff1b-5450-88d6-89db8f84243a | note | Frequency - Once, 4 weeks prior to the commencement of piling
7fe3e125-f47d-54f5-9d00-5f27baa5075d | note | Category - HP
cb42a035-8960-5cf9-973b-c678f9cba7ce | note | Responsibility - Nominated Authority
56029e36-6113-5fba-92c7-62a3659c54fe | note | Verifying Documents - ConQA Hold Point Release
6004f01a-f993-5245-87a4-80b5a7d0496c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Temporary Steel Casings
b4045bee-353c-5692-baa7-55e0c025352a | note | Reference - 606.03 (b)
83d5b929-7fed-5307-80e0-9f4573251605 | note | Acceptance Criteria - Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
37d66acc-13ea-57c0-ac40-5f2701f07aec | note | ○ Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
a7e6b751-1dbb-5d69-b900-640c444a289e | note | ○ The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
6d34c552-3fe4-5d9f-a630-b02d2b43827b | textbox | Enter: Teambinder Approval number
e24b7e23-99d3-5682-a53b-cfc8c474bab3 | note | Method - Document Review
60a1e7ed-3398-5d08-ae2d-38e800d8d043 | note | Frequency - Where applicable, once, prior to use
6e7ccc9e-65d0-5e1d-b629-2abe3c36013b | note | Category - HP
551253d2-194e-5167-9408-c23b51d501dc | note | Responsibility - Nominated Authority
af93dcd6-f8bf-5a96-b3d9-63ff65516f26 | note | Verifying Documents - This ITP
66977686-4205-5153-a3d5-f908b51d99c2 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Casting Under Water Procedure
112a9b0b-5815-5bfa-8062-ba1ec671538d | note | Reference - 606.06 (a)
378ee5e3-051e-53b7-aa9d-ac103f729d7b | note | Acceptance Criteria - Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
874a3c69-b26a-501d-b6f7-3eac0deb1ddb | textbox | Enter: Teambinder Approval number
80c2ac92-0df2-5405-8729-cdaa899937d1 | note | ○ Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
82284ddf-acc3-5d9a-8d9d-72c2fbf73cc2 | note | Method - Document Review
266c1977-0d8c-5a53-ab80-b6f0fd45f06c | note | Frequency - Where applicable, once, prior to placement of concrete
eb4ba3d4-cbcc-5f10-804d-13ab47d1d77d | note | Category - HP
dd7b8263-d66b-5170-84e2-6c65e6894523 | note | Responsibility - Nominated Authority
866f306c-6061-5905-b4f6-3488b91c2829 | note | Verifying Documents - This ITP
0a296f14-d915-5176-8b8a-54a423dd2abc | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.5 - Boring With Bentonite or Polymer Fluids
61f36ffc-29d9-5822-80e8-17f4cf2ff179 | note | Reference - 606.03 ( c)
1ac7c772-45d5-5a33-9560-a7993837f5ff | note | Acceptance Criteria - Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
1fda2a33-fd17-5cb3-971b-af279145c2db | textbox | Enter: Teambinder Approval number
c6195ce2-d988-5c5d-9d88-1e68e65d960d | note | ○ Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
ab55b0c7-016f-5a68-a7c3-b3a0f186bb0c | note | Method - Document Review
02324c7f-8fc4-5e6e-86d4-70ff8e194500 | note | Frequency - Where applicable, once, prior to commencement of boring
0f770639-b944-541a-aa55-812c0118bdba | note | Category - HP
b2f2b196-777c-5c2c-b67d-da08ec51c9b6 | note | Responsibility - Nominated Authority
89af91bc-482b-571a-a881-43f7ae1687fe | note | Verifying Documents - This ITP
f0d9ed66-2ac1-509c-b760-005d483c2c9b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Dynamic Pile Testing Procedure
864a5e0c-595b-56bf-80f6-714f151a8f4f | note | Reference - 606.07 (c)
216a2053-fd9f-554f-a4ac-86710a576782 | note | Acceptance Criteria - Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
3968d1ea-9a1c-531a-b5e4-1fe8a60f7ac4 | textbox | Enter: Teambinder Approval number
a14a13cd-0cbe-5130-a8fa-503b5c53c355 | note | Method - Document Review
5ef8bb78-6205-5043-b380-0f237f8db9c1 | note | Frequency - Once, prior to testing
c2908864-aeb5-528e-b231-f73cc2153bd7 | note | Category - HP
f329af81-f464-51ed-bae3-320885724fc0 | note | Responsibility - Nominated Authority
af3b6238-7d7c-57ad-856b-6a6fa3a6bdd7 | note | Verifying Documents - This ITP
c4cfee76-bfe1-564a-b847-d71f6d3eac50 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Pre-qualified Pile Testing Consultant
41cec84a-4506-5b2f-a8fc-5cfb24ea1bf8 | note | Reference - 606.07
9781caf8-4374-56bf-8f6e-86a4754e9de0 | note | Acceptance Criteria - All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
02c59eaf-7db7-511a-819f-a771bb763048 | note | ○ Details of the consultant to be submitted for review to the Nominated Authority.
3cf1c3de-33be-566b-990c-73ff6af8038b | textbox | Enter: Teambinder Approval number
34b1beff-7e6c-5a55-9501-47fd4ea969a9 | note | Method - Document Review
cf8ef076-f5d1-54dc-a679-70f3c0175e9f | note | Frequency - Once, two weeks prior to testing
7cbbd17b-0c6f-54a2-bb80-c367f35a583b | note | Category - HP
45dbdc3f-69b6-5c58-9ae0-90a24d4d0a1d | note | Responsibility - Nominated Authority
ece8c989-c517-563e-8072-a06710d9da93 | note | Verifying Documents - ConQA Hold Point Release
c0959a90-92b3-5e47-8e8f-9c5c8c4345e9 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
896c0740-1c02-5b66-9898-f48a549ae78d | note | Reference - 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b)
562abe99-6179-5c6f-a87c-f77ab9a2d16a | note | Acceptance Criteria - Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding specification & qualifications (including macro inspection) have been approved by Nominated Authority.
7091915c-86d6-566f-892a-4ef9f04a4598 | textbox | Enter: Teambinder Approval number
0ddb386a-1620-505b-87ee-674ac41adda3 | note | Method - Document Review
b161add2-bb61-58a9-87e2-0534d335649e | note | Frequency - Where applicable, once, prior to welding
cc7165a9-68ab-58b9-be74-d1bd3033d272 | note | Category - HP
9c0a82eb-4536-5c64-b4f3-eac8b017083c | note | Responsibility - Nominated Authority
11a4635d-ef82-554a-b0c9-fa14662ab09c | note | Verifying Documents - ConQA Hold Point Release
368ffeed-d7ee-5889-a11a-3b37178f931c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction Activities
| checkpoint | 4.1 - IFC Drawings
3a62cc6c-0d19-57d4-ac2d-4fee874c3144 | note | Reference - MRPA Quality Management Plan
505d2e0c-7683-565f-8723-09461f6f7742 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
707bdb3a-49c2-5cd8-b168-ea3df1446665 | note | Method - Document Review
b53c7279-6088-5d71-a769-fabfbb9a6a75 | note | Frequency - Prior to starting Works and at regular intervals
9c64ba41-7ed9-51e5-8cdd-47e17a809e9a | note | Category - HP*
dffc00d0-8cab-514b-a8e1-8547d958f457 | note | Responsibility - All
61477ebf-7a1d-59d0-8a95-da113cc9058b | note | Verifying Documents - This ITP
26ee0af8-88bd-5eaf-83f2-037126513278 | date | Date Completed:
| checkpoint | 4.2 - Survey Set-out
73f2d780-eff1-5fc5-a64a-1b5c33b5da91 | note | Reference - IFC Drawings 606.08 (a - c)
a2ac46e4-ee82-5c2f-ae87-430effcd0d6e | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
4ec668ce-1af1-5751-9eb2-c25bd1724602 | note | ○ Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
396d25be-a85b-50d5-ae28-8a8332bb383f | note | Method - Measure, Visual
e1adcd06-c745-5cd0-b9ee-b4169a7885d8 | note | Frequency - Each pile
ef8ee8a3-7915-5e0a-ab8b-a3a5037c61ec | note | Category - IP
7007b1c2-4666-5a6d-a7bc-bc6460daf5ec | note | Responsibility - Surveyor, SE
5a304930-c049-569c-a1de-44acc67349c0 | note | Verifying Documents - This ITP
603644df-a170-5a51-8fa0-bfff0842b9cb | date | Date Completed:
| checkpoint | 4.3 - Protection of Adjacent Piles
424f01b7-5f13-552d-a60e-02916f0e071f | note | Reference - 606.04
d99dcbaa-628a-5367-9024-73e372496752 | note | Acceptance Criteria - Pile construction shall not:
f47b50c7-717d-56bf-a9db-ffe587270fa6 | note | i. result in damage to adjacent newly cast piles due to ground vibration.
c26fc452-adce-5534-b2a6-e2553afd45b6 | note | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
4ec656bb-1246-5800-a5e3-8def437dea05 | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
2cc49f15-769d-5ac8-bf6e-34f5030a91bf | note | Method - Measure, Visual
1df57ca3-282f-5d59-ab5a-fe799606a809 | note | Frequency - Each pile
7c77d63e-2857-58af-a98b-9a9431c457ce | note | Category - HP*
3ab517e6-eaf3-5fa7-b593-b473b2937b4e | note | Responsibility - SPE/PE
c94ef725-369d-544d-862b-68056e35eaed | note | Verifying Documents - This ITP
63db98ad-2bf3-57b5-acf4-8edb49d19ec4 | date | Date Completed:
| section | 5. Construction Activities
| checkpoint | 5.1 - Boring Operations
9cd5604d-f38c-58b9-80ea-b5b8ff998f50 | note | Reference - IFC Drawings 606.03 (a)
7cbb19a1-2040-56b7-8e92-b7fda6e45979 | note | Acceptance Criteria - Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
0b99a011-e349-519f-a467-28ab2b28eb7b | note | ○ Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
391163b7-7c22-5ffa-8515-4dfda081053f | note | ○ Excavation clean and de-watered (where applicable) for inspection.
0c57ea43-81bb-5b58-be4e-e892c061db20 | note | ○ Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
1018d2c1-1760-5c84-a793-149403617781 | note | ○ Excavated material to be disposed of as appropriate to maintain a clean site.
534e80fd-ba98-5a45-9071-b262d0538a22 | note | Method - Measure, Visual
85e630b7-ac7e-5790-bcc3-47f5b10c1e53 | note | Frequency - Each pile
a15b4a9c-2b52-5c74-bff9-e608c12ca392 | note | Category - IP
4e656ca5-be26-5c0d-9580-981b555f4593 | note | Responsibility - Surveyor, SE/PE/SPE
3a987ef6-459b-5d18-8a85-31619506a0e7 | note | Verifying Documents - This ITP
2a5d2e36-b688-5e85-827e-30bf097d2403 | date | Date Completed:
| checkpoint | 5.2 - Formwork Extension
81959329-e75d-5a7c-a8b9-68a84a6cad63 | note | Reference - IFC Drawings
01853a55-0654-584f-8c5e-4fa4cfb271a1 | note | Acceptance Criteria - Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
3d5cf1d3-88a8-5cf1-8c30-c95cc26aa024 | note | Method - Measure, Visual
86f90031-fafe-5961-9354-b859c7512f10 | note | Frequency - Where applicable, each pile
8f48c271-6c7f-5670-a89b-f6c55bf9a28f | note | Category - IP
32ce6a6a-edb7-59ae-89d3-275a153d348b | note | Responsibility - Surveyor, SE/PE/SPE
67bd932c-7dde-5437-a054-3737d4cbffc2 | note | Verifying Documents - This ITP
1bd73ab3-cfb6-56b0-b65e-c34026eadf66 | date | Date Completed:
| checkpoint | 5.3 - Inspection of Pile Excavation
de912b39-8729-5761-8fc1-b724e0169963 | note | Reference - 606.05
8282fd32-f169-5374-b722-d1863c88e496 | note | Acceptance Criteria - Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
87bd67f9-8185-551e-a8fd-15f41d483978 | note | ○ Attach: Geotechnical Field Sheet or Report
413b1566-21e4-52ec-b01b-903ab5de2dfb | note | Method - Measure, Visual
f7e2688e-e724-5c0d-92a1-0d16724678b2 | note | Frequency - Each pile
4ed8dcfb-d5b2-592d-a1cb-6a7a2d4f5a39 | note | Category - HP
ec54701c-394e-5b70-a920-4f1dc96ac13f | note | Responsibility - Geotechnical Engineer
61057f66-86ba-5931-8626-836e8f3a2631 | note | Verifying Documents - ConQA Hold Point Release
816be101-b16e-5a37-994b-52f4ce665fa5 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.4 - Reinforcement - Placement
1ea7fb68-bf54-5bf8-85a9-c5ddccf1095e | note | Reference - IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12, 606.06 (a)
42cb15f3-70e2-598b-b33c-fc933591954d | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
250f800f-9c1b-5677-960d-d68bb513ac77 | note | ○ Projecting reinforcement is the correct length and location.
19ee350b-3e85-5a38-b483-c666fbd2ff8c | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
f22c3dab-917c-5f0e-833a-230c865f13ad | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
06e1b68d-8030-5332-8e96-25c77f1a6a8c | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
5f9a33cb-511b-5fef-bd52-63d562e19c91 | note | ○ Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
65eedbe4-7708-55f6-968f-46572ba8d581 | note | Method - Measure, Visual
bda3a61e-ea6c-5817-bfea-6424f94661fa | note | Frequency - Each pile
067bbbbc-7a48-5066-aa29-6fa5ce4ac38c | note | Category - IP
c27298d7-3f0d-592a-99cb-b5fc3f3d8ec5 | note | Responsibility - Foreman, SE/PE/SPE
ae697c5c-8ad1-5f86-959d-0a7a654cc362 | note | Verifying Documents - This ITP
f3ff5ac1-f1ac-5718-bc9a-1fb0fec397c7 | date | Date Completed:
| checkpoint | 5.5 - Reinforcement - Electrical Continuity
ca8e9c17-440e-5393-a36d-1b1f2c968079 | note | Reference - IFC Drawings 610.29 (d), 610.43
4a211db4-0b1e-59f0-940d-54854efad86f | note | Acceptance Criteria - Pile reinforcement cage to be made electrically continuous by:
56ac2bf6-e664-5e38-98a6-78c4b189f544 | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
fc951c31-0275-5441-be97-8274d9f5113c | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
e7e121f1-e78f-5721-bbd9-a5a3aaaaf8a9 | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
6f36fad5-a408-5179-b954-9f2d69ea0799 | note | ○ Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
2e4f1a37-41a8-514b-89ef-7637fad98ce2 | note | ○ Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
1689c382-7974-598e-8990-21bf76923b16 | note | Method - Measure, Visual
6b5711ed-0397-58eb-9736-e8bf32fa11b5 | note | Frequency - Where applicable, each pile
94fade81-ee48-59ff-adac-9ce084cd1692 | note | Category - IP
757e19e0-c70a-5e70-9149-dff443c2f006 | note | Responsibility - Earthing Engineer, SE/PE/SPE
d7788875-0c52-573d-924b-8b038a06416d | note | Verifying Documents - This ITP
4d8f030c-55d0-5473-9b56-8d2ba591d549 | date | Date Completed:
| checkpoint | 5.6 - Cast-in Items
95781763-34aa-5d42-ad19-462282943ba9 | note | Reference - IFC Drawings 610.46 (a) Table 610.462, 610.47 (a) Table 610.472, AS3810.1 Table 3.3.6.2
267d97ec-2d31-54a0-a6cb-a3c3131a5365 | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
3f1124a1-87fd-5b91-8daf-abde90fc8650 | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
b6bf8b79-82e3-5935-a697-2a8fc2be621d | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
97f7ebd1-5977-5e4a-9c18-3d4072c22b62 | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
8ef14404-c22c-5599-b06e-58251f0afd40 | note | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
4df08e95-04d1-5ccf-9691-90eaa901da9f | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
6be88504-15f1-5f67-b8af-4cdcf8ee8c2e | note | ii. Running dimensions of a group of the above = ±6mm
58846332-bb23-525c-b3ac-17228e12e15b | note | iii. Ducts and conduit location = ±12mm
570b41bb-4ec9-517d-89cf-c0f85cd3fb96 | note | iv. Diameter of ducts and conduits = ±3mm
eaad132b-c060-5654-b892-d25479eb91b9 | note | Method - Measure, Visual
89431967-c1df-5877-b7b4-6d3e64048c93 | note | Frequency - Where applicable, each pile
6dd135d6-c1a0-5b3d-9f3c-20fd7739c5b1 | note | Category - IP
f6fd7210-71a6-5145-ad62-2290df690db1 | note | Responsibility - Foreman, SE/PE/SPE
6e683ce6-a17e-5ddc-9e70-875df7f70875 | note | Verifying Documents - This ITP
a22e8b24-4827-5db9-aae2-ecee16dcfb94 | date | Date Completed:
| checkpoint | 5.7 - Pre-pour Inspection
c59df4d8-2964-52bf-aabf-34e6cbbd16a0 | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
417cfc2f-1e2e-5bf1-8fea-0f20e2065899 | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
105b611a-3571-5e7c-a523-9f7ef53267d6 | note | ○ All foreign material has been completely removed from the excavation.
40814792-98b6-5c67-9326-027e9c6d3aaa | note | Method - Measure, Visual
fd7d64f7-a1db-5dac-8f8b-54e324992f10 | note | Frequency - Each pile
70c5858f-c4b5-5b94-9652-06fc6257862f | note | Category - HP
4ada0db9-be0e-5964-b6be-d48837d5cce4 | note | Responsibility - Nominated Authority
89c52215-953d-59ba-b172-e2650da01778 | note | Verifying Documents - ConQA Hold Point Release
61d13245-7639-5ba0-b8c2-9027b1f88786 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.8 - Weather Conditions & Evaporation Limits
8cc654a2-ba2a-57e9-9155-b9b1aa2cc403 | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
49880277-58fb-53bd-b1af-3539f318f6b3 | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
595e9e05-ac1f-5fe5-a298-6533b2f9f20a | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
3958c2a1-8377-5b2c-b1cb-bf29a30549a9 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
1d0c6c39-e3ac-54c0-81cc-d54588167bd5 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
f0603e22-aca1-57b0-9c0f-5902f5f7163f | note | ○ Record: Required information on the Concrete Pour Record.
53f63f70-9f02-570d-9082-a2908425c685 | note | Method - Measure, Visual
0a0c2c0c-aa81-5eb8-a477-9223ddb10c2f | note | Frequency - Each pile
9effa244-caad-5fcf-84d1-a635c3d7e290 | note | Category - IP
8366e2cf-0011-5cfd-baee-6c8c7cb325e3 | note | Responsibility - Foreman, SE/PE/SPE
336d9f2d-4ac7-5984-b6f0-7d1df6c677fa | note | Verifying Documents - This ITP
27753efc-d151-5177-9ce6-d991e1ca7eb3 | date | Date Completed:
| checkpoint | 5.9 - Concrete Testing - Sampling Frequency
302c47be-16c8-56ed-8d5f-c72487089d5a | note | Reference - Site Sampling & Testing Procedure 610.16 (b) Table 610.161
e4502b2d-6881-53b6-b477-87dba94e1d1d | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
0679210d-8ea9-5288-95ad-13836e9a1038 | note | • 0m³ to 10m³ = 1 sample
15f9cb24-f4f1-5864-85f8-2314241d8d00 | note | • 10m³ to 25m³ = 2 samples
8a4f8845-aee9-54da-9c84-bcb7bb6fdb92 | note | • 25m³ to 50m³ = 3 samples
52153e66-e717-5f02-a5c3-f6590405436a | note | • 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
fdce4880-9cfe-5ab0-987e-07948b8dcf47 | note | ○ For each additional 50m³ and additional sample shall be taken.
16824b54-8a7b-5d34-a117-e3374c96e544 | note | ○ Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
410e5516-7d37-5c23-9394-deb4037923a6 | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
f582b48c-0e31-50e2-b292-25337270205b | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
29ce393b-fe8b-52ff-a5ca-5930044a224b | note | ○ Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
2e83be43-99e7-52a3-9416-d97ea708ce24 | note | ○ Record: Required information on the Concrete Pour Record.
e7528a02-1b67-5f12-ad99-65374026a1e1 | note | Method - Test
8ff222b9-e93b-5fcb-ae9a-c0bd3b6a06a9 | note | Frequency - Each pile
868e4b72-4ee2-5df2-acb0-3b353881dcf5 | note | Category - IP
3f41e154-c780-5298-b48e-338b0eb40681 | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
fa1a4250-01b3-51e7-b178-1921ba1e3f7a | note | Verifying Documents - This ITP
8fe89e58-c118-5a70-8f5a-97c1fbdbeb2b | date | Date Completed:
| checkpoint | 5.10 - Concrete Testing - Spread, Passability & Viscosity
c68c5786-08c6-55cc-8ed1-b18934b55065 | note | Reference - 610.13 (b)
ba3bb36f-dfe3-52cc-8394-106cf64999c2 | note | Acceptance Criteria - Spread range = 550mm to 750mm
da302508-778c-55ce-a606-d7e8cb609901 | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
aaffdbc1-9cd7-5c8a-b7c5-8ae8606115ca | note | ○ Passability = ≤10mm (aggregate height differential)
a7395690-bb64-54d6-aca4-c726f41a396a | note | ○ Record: Required information on the Concrete Pour Record.
9e54fbec-aba1-5fe7-a827-7cade79d29fe | note | Method - Test
4191bf5e-bf4a-5aea-8de0-ffda6390bdc2 | note | Frequency - Each sample of Self-compacting Concrete
1fa7e24d-b5d0-5215-bb4d-3d005a88992b | note | Category - IP
c56e1683-8378-50ce-88b1-ea1b6a2afcd7 | note | Responsibility - Concrete Tester
9bdf8877-98ee-5f7d-9e2d-3324c81c3669 | note | Verifying Documents - This ITP
ee35de0e-f754-5bab-8b28-17345b1c50ea | date | Date Completed:
| checkpoint | 5.11 - Concrete Testing - Compressive Strength Cylinders
3781c095-cbd2-5681-a210-e88cada19381 | note | Reference - Site Sampling & Testing Procedure 610.16
4f8524cb-9789-5520-b413-e3819d21eef4 | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
a67c1e8e-e429-5f77-92d1-996ae26369a7 | note | ○ Record: Required information on the Concrete Pour Record.
849b751f-4cc3-59b8-96f8-c7f650ea2f4d | note | Method - Test
a94a1ab3-8681-55d0-88af-4220bfaf8b2d | note | Frequency - Each sample
158141d1-f4de-5812-a8d8-1524a65c785e | note | Category - IP
4a76f95b-ed08-5332-8389-db76463d30e5 | note | Responsibility - Concrete Tester
eaf0e5a8-a73c-5fc1-a717-c9963b362ad6 | note | Verifying Documents - This ITP
baf23bad-cfde-54cd-9712-e84822853fa4 | date | Date Completed:
| checkpoint | 5.12 - Placement & Compaction (Dry or Wet Excavation Conditions)
0ba67935-ad15-5764-8d02-ca987db877fd | note | Reference - Piling Quality Procedure 610.18 (a) & (b), 610.18 (d) (i), 606.06 (a & b)
a7375776-22ea-513b-8fbc-3f1298bdc74e | note | Acceptance Criteria - Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
8f6fa32e-bccc-50dd-b4f5-37a786001322 | note | ○ All concrete batches are traceable.
3f8735bc-081e-5830-9cf5-e0c126fff449 | note | ○ Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
17a52a12-48dd-5de5-8a4c-f9eca8d6618d | note | ○ The initial discharge is pumped to waste until a consistent workable mix is discharged.
f5465f5b-cb43-5478-9849-d18d524d12ab | note | ○ The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
850d0f78-cbc6-588b-8af1-0342597de171 | note | ○ Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
57e9312b-9d70-597f-9645-0d27f3f8a480 | note | ○ Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
ffc6dff9-2a27-5b90-b005-c66850626759 | note | ○ Record: Required information on the Concrete Pour Record.
17bf09f1-741c-5ff3-812d-a3bef22759ef | note | ○ Attach: Concrete Pour Record
3b70869c-c079-5c14-823b-fb7c2a2ae9cc | note | ○ Attach: Concrete Dockets
7692b3e3-2abf-5e25-8f2f-49a0b7f82e38 | note | Method - Visual
47e21a9a-a05b-5931-a3a4-0ac722f58079 | note | Frequency - Each load
81146944-63ab-5b4c-9129-e6ebb44e87c1 | note | Category - SP
cf67469c-c127-5a8b-ad15-14e87718e307 | note | Responsibility - Foreman, SE/PE/SPE
da2f3bd6-aeab-5ae5-b524-8c053a0b020b | note | Verifying Documents -
d134f090-995c-53ec-b198-5804ceb13a51 | date | Date Completed:
| checkpoint | 5.13 - Surface Finishes
9a9e3fa6-1337-58e5-8f56-4a9747699b94 | note | Reference - IFC Drawings 610.31, 610.20
d3e2856c-5595-5cca-b73d-6003546ed5be | note | Acceptance Criteria - Surface finish as per IFC drawings.
8d9ccf44-2172-5273-8dd1-4028af3f4ab0 | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
bf3e0985-b1b9-5e56-b823-ad92d4eab73e | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
af42b48f-cd33-543a-a892-68e9a57cc374 | note | Method - Visual
5d7b3e83-9317-5363-a98f-86e931ce19a3 | note | Frequency - Each pile
e8fe25f8-cf78-5992-b5d5-af1f39848b3b | note | Category - IP
2192f2f3-3156-58bf-aaf2-6914bcbc4e64 | note | Responsibility - Foreman, SE/PE/SPE
e4385112-fd7c-567c-ad4a-38007db4a13e | note | Verifying Documents - This ITP
468459e5-6581-5d7f-a54a-db37493df55d | date | Date Completed:
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Pile Trimming
8b45ed8b-3c85-527a-9ef6-3edb32cd2577 | note | Reference - IFC Drawings AS2159 Clause 7.2.2 - 3, 606.06 (a & b)
a2ebeee1-eab0-5fad-bef0-0850c131cf50 | note | Acceptance Criteria - Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
09d3abcb-f59e-5f27-8117-96bad8c402f0 | note | ○ Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
6e7b99e8-4980-53d6-8bba-6ff9afa55ec9 | note | ○ Any weak or damaged concrete shall be removed back to sound concrete.
e1b9ba58-f277-5e1f-a5c7-92ded451c7cc | note | Method - Measure, Visual
4bd4bef5-6216-5ec1-a239-8b9b51b5f9c3 | note | Frequency - Where applicable, each pile
52a062d9-08f1-57ef-a06c-49fccec42e22 | note | Category - IP
a3a9db79-95db-5259-9fde-2c502060777d | note | Responsibility - SE/PE/SPE
ae752483-f119-5ac4-8edb-1656905a74ba | note | Verifying Documents - This ITP
490adb58-d819-5a84-886d-a86202ef3a12 | date | Date Completed:
| checkpoint | 6.2 - Compressive Strength Test Results
bd9e4d1c-72a4-5476-b756-61816b328acb | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
c534816e-b4cf-5741-bb3f-25ebb57b298d | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
fc0acd5f-9a2d-5114-abb8-e5c2413a292b | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
6fb73d58-ee8d-5ba3-bc3e-b2e13170f3f2 | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
9ccc87db-7a14-50f1-9fd2-10d597663051 | note | ○ Attach: Compressive Strength Test Results
9b0a9ec6-6326-5736-a4d6-b379d9bc1578 | note | Method - Document Review
6ec7b982-e3ca-53e9-9818-69540bf24079 | note | Frequency - Each cylinder
6e8b7f9a-c385-5ded-8f69-bb4603567576 | note | Category - IP
659d485c-a126-5165-a98f-2d6d379d13ef | note | Responsibility - SE/PE/SPE
930ff70c-3d2a-5ad0-b31d-7a25cbf522f6 | note | Verifying Documents - This ITP
d27e321d-7b1a-5c24-a16a-ad65aae13909 | date | Date Completed:
| checkpoint | 6.3 - Pile Integrity Testing
ddef8926-5570-5450-a7f5-17a50ac89855 | note | Reference - 606.07 (a, d & e), AS2159 Clause 8.8
7aa12adb-4e7f-5f97-b4d0-f6dbbb84c79e | note | Acceptance Criteria - Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
e85fe644-e0cb-5352-989b-5d30914d9ca9 | note | ○ Cross-sectional area = ≥95%
8f9f3ce3-29e4-5702-a2a0-c128f7e6a7d3 | note | ○ If any test fails, all piles shall be tested.
fba3ba68-c1d0-51f7-9fd6-5919427a355e | note | ○ Attach: Pile Integrity Test Report
84b3cc6b-42a2-54f6-8527-c8670a9ddd38 | note | Method - Document Review
80ed7e76-b28c-5e1b-9c83-5a34ab5b8a72 | note | Frequency - Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass.
4ece9a61-e922-5629-afca-d67957ae7302 | note | Category - IP
379c1963-7da8-5359-a7e8-1714021cddbc | note | Responsibility - Testing Consultant, SE/PE/SPE
7354f4c2-ee16-5eee-a9ba-ef9fc78ce653 | note | Verifying Documents - This ITP
d96c1cfc-14ad-5e9c-ad66-3318371fc293 | date | Date Completed:
| checkpoint | 6.4 - Static Load Testing
da9cef20-50da-5650-835c-92b47515bd98 | note | Reference - IFC Drawings 606.07 (b, d & e), AS2159 Clause 8.4
77267956-ffbd-5198-83b8-3ec2a911ed9d | note | Acceptance Criteria - Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
af43bdb8-c402-503f-bdd6-87cf5a8cc663 | note | i. Displacement vs Time Graph = linear or decreasing rate of creep
ca7a2f9d-17e6-5e27-880e-fd2d9f08743e | note | ii. Creep rate = <2mm / log cycle of time at the test load
0c3861ba-1ab2-5651-8ce6-7538c77458a9 | note | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
893f3f9a-b31a-59c8-8982-9f6dc9e30d9b | note | ○ Attach: Static Load Test Report
9662a363-d4ec-589b-820e-1a30514b1e41 | note | Method - Document Review
710c9613-d53b-5852-acc1-c1d3ef458664 | note | Frequency - Where applicable, as shown on the IFC Drawings
295a77d5-2825-5003-8e72-51eb8360d443 | note | Category - IP
def32cdc-a131-50e8-b8b6-a696064c1ef7 | note | Responsibility - Testing Consultant, SE/PE/SPE
1fc9d086-cc4f-5276-8b3d-f53c37caf5fe | note | Verifying Documents - This ITP
a87f22a7-0a43-53fa-9de6-474c977e83a8 | date | Date Completed:
| checkpoint | 6.5 - Dynamic Pile Testing
6f351174-8044-5ab6-a74e-1f3f45dc8af3 | note | Reference - 606.07 (c, d & e), AS2159 Clause 8.7
8bba8697-243f-5a30-aa76-57f851ab92fe | note | Acceptance Criteria - Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
d713de89-4415-5dc1-9f4a-9e34a2fdd581 | note | ○ Measured Ultimate capacity = ≥ values on IFC drawings
f93d0c0b-92ec-5cbe-9924-a825bd744360 | note | ○ Attach: Dynamic Pile Test Report
c65fe53c-9c7e-5ef3-8b96-96f01789692a | note | Method - Document Review
95af3984-1434-5e21-a029-c37563f757a7 | note | Frequency - Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile. At least 1 test per 10 piles.
4708b502-f331-595d-86a1-16678af782c3 | note | Category - IP
2c3090d4-97fe-54df-86e2-f3edfe9db271 | note | Responsibility - Testing Consultant, SE/PE/SPE
4df64c00-6db9-5703-a0c3-f2db73b7f277 | note | Verifying Documents - This ITP
1495b441-6c03-58c9-a0dd-d95abd48efaf | date | Date Completed:
| checkpoint | 6.6 - As-built Survey
02f2d743-732c-5cd2-9c63-81cac05369ac | note | Reference - IFC Drawings 606.08 (a - c), AS2159 Clause 7.2.2
a2ee014c-8355-5bcd-9a2f-c6929ed34993 | note | Acceptance Criteria - The following tolerances apply to piles:
b428205c-152d-5057-a5a4-6213b305de34 | note | i. Pile head plan location = ±75mm
c6253853-1872-5deb-9bb7-a3339a078e1c | note | ii. Variance from vertical or rake = 1:100
fe5e1c4a-bcca-5f5c-bbb2-a60e749a754d | note | iii. Irregularities in straightness = 1:100
4603c2ca-0af6-55d5-b46b-d892f2391a98 | note | iv. RL = ±25mm
a7fc3d5a-6a08-5c85-b8e3-c3c3b4106f82 | note | ○ Attach: Survey As-builts / Survey Report
a5276113-348c-54ad-bf3c-2575405ca130 | note | Method - Document Review
20d64742-a8f8-5d2f-a771-2677fa1ac5c0 | note | Frequency - Each pile
c9e4f1ff-58fe-540b-9a11-168ce0120d71 | note | Category - IP
434c5c54-6f77-582c-94c8-d9885134c268 | note | Responsibility - Surveyor, SE/PE/SPE
43f402ce-afbc-515e-94d2-6dea0abbd8ac | note | Verifying Documents - This ITP
9104a83e-3a57-56bc-87a4-7992fff98a77 | date | Date Completed:
| checkpoint | 6.7 - Non-conformance Report (NCR) Closure
9a3e85f2-5ab9-5941-9a79-7cbcf61af748 | note | Reference - MRPA Quality Management Plan
3b7c2ea6-49a2-5260-a690-09ba60785c09 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
159e9041-7c89-591a-bc9c-a1b2b7f593b3 | note | Method - Document Review
2dd4a481-aebe-5ed2-8c20-7936128d622c | note | Frequency - Once, prior to closure of this lot / element / Work area
d8681b2b-1884-529e-8544-3e81cee328aa | note | Category - HP*
a6469f9c-c530-5f9a-bc8b-bbac04460b4a | note | Responsibility - SE/PE/SPE
b7929814-73e2-5cdc-ac05-3e7050f04008 | note | Verifying Documents - This ITP
a2e36a20-bb7b-55c9-83df-563a6961b7ab | date | Date Completed:
| checkpoint | Final Inspection
fac9be9f-d655-511e-a47a-df39ea48788a | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
d1dacf71-2881-526f-8050-ab6e06bb72cb | textbox | Name:
b74503c0-7496-57be-b6e2-2155cfd21b39 | textbox | Position:
11d5030e-d61c-525e-89ae-96d55f0603aa | textbox | Date Completed:
| signoff | Sign ITP
b5bda619-d417-4fd5-8d71-a2615e2e5364 | checklist | ITP-233-RAIL-HOP-Track Removal & Construction Rev 1 | itp | ITP-233-RAIL-HOP-Track Removal & Construction | 13c3a3e1-b161-459e-89a2-ff0ef703975f
1cec713c-9dce-4a58-a6ea-e32b4f2f6228 | section | 1. Referenced Documentation
53661e1c-7ba6-49a3-847b-0affa8e1779a | checkpoint-no-value | Referenced Documentation
ac1b6f1e-167f-5410-b72a-7739f10c50ec | note | Document Title: ITP-233-Rail-Track Removal & Construction
86168ce5-ea27-582b-89fb-23d8adc397f2 | note | ITP Description: Track Removal & Construction
970bee59-6885-5303-b56e-35650d082748 | note | Discipline (e.g. CIV/STR/RAIL): 233-Rail
34e00916-4ccd-5855-955c-a984875929e7 | note | Revision Number: 1
a0052e1c-fd8f-5ee9-8876-b7a5e26fef89 | note | Revision Date: 22/10/2024
9250a8e6-3aa0-5944-aa79-67ef792357df | note | ITP created by: Jake Argentaro
7f5f5bc1-98db-51ef-b437-e6b33b32e8d2 | note | 1.01 - Non Dependent
761c5602-0815-5ba2-96b7-3d7e66550ede | note | Reference - Hopkins Road Track & Civil IFC Drawing Set MRP-DPK-102-00-CPW-0061, MRP-DPK-102-00-CPW-0060
03bfa7be-b738-50b0-96a2-2d652fcfcaec | note | 1.02 - Non Dependent
59d50b29-8e74-5b51-8835-7831a5fb8702 | note | Reference - NIST-2654 Ballast
d8968243-33f7-5672-8ce3-caa0ae8e2c03 | note | 1.03 - Non Dependent
0dd8cc18-0ad8-5d86-925a-e95f387de75c | note | Reference - NIST-2651 Sleepers and Fastenings
ff4d9290-da2a-5377-97c9-9b2b4d114689 | note | 1.04 - Non Dependent
7bbc6832-991c-5e64-a663-3e56daee8e83 | note | Reference - NIST-2650 Rail Use Laying and Adjustment
811a2763-06eb-5cae-8697-8c3aa509c975 | note | 1.05 - Non Dependent
9b5d37c9-5b95-5585-a1ec-92249f2d0063 | note | Reference - NIST-2630 Track Construction
a0a47374-4814-519e-88fe-ebd15814d135 | note | 1.06 - Non Dependent
9d912078-4580-5fe9-861f-c34052d0f261 | note | Reference - NIST-2706 Track Geometry
c1999a49-4059-5210-87ce-3f1f3d5d4dff | note | 1.07 - Non Dependent
6e92bc19-5092-5191-ac18-a205083affcf | note | Reference - NIST-2659 Earthworks and Drainage
c6cfa177-440b-5bc6-96c7-7b35977218f7 | note | 1.08 - Non Dependent
25e196f7-faf3-5ac8-94af-9d97a57ee956 | note | Reference - NIST-2618 Track Design
02afe01b-2dad-55d4-be3d-d1f6302e1cc2 | note | 1.09 - Non Dependent
5839b34a-210a-559b-8e65-2edc357f851a | note | Reference - NIFO-2650.5 Aluminothermic Weld Record
d091cdfe-21a3-50d2-968d-9f1ad27c8b1e | note | 1.10 - Non Dependent
26dc38ae-1453-5fb6-8bf2-5eecc1c94548 | note | Reference - NIFO-2690.3 Certificate of Track for Operation
c3755ff5-f885-419f-9b4f-eeaf6597330b | section | 2. Preliminaries
052d7ad5-fceb-4ac9-b7ab-7e614b48abed | checkpoint | 2.01 - Obtain and submit Material Certificate of Compliance for Track Materials;
47c7fbe6-dbfc-5dfc-946e-e42bb18267b9 | note | – Track Rail
f17e2c83-4117-5655-be8e-f13d16912ff1 | note | – Track Sleepers
01d8dcfe-005c-5f67-b4dc-32b17df72408 | note | – Track Jewellery
50b7959b-c86d-5a5a-983f-61c64913747f | note | – Geofabric
5c562704-f1d8-57b1-863d-f4b6ceaebd37 | note | – Ballast Matting
1ceb4ed9-3b24-53d1-a98e-82e5483361fe | note | – Ballast 60mm Aggregate
82906f90-273e-5459-9aec-6736fa675b54 | note | – Welding Kits
b9e75cd0-4d12-50c6-a123-46f5472d528c | note | – Welding Crucibles
68a0e5d5-37e4-5815-af5e-b85ea67c6ae8 | note | Reference - IFC Drawing(s), Track Constrction Site Mudmap, Bill of Materials
39981a4b-e4dc-545e-a400-9b7538c1f558 | note | Acceptance Criteria - Units to be free from damage, total and types of units for full set validated No signs of discoloration
4e53a86b-9cbc-5e65-b872-2e3cd1acdc7f | note | ○ Attach: Manufacturer Cetificates of Compliance
9ec2b53f-b38a-5a20-ba6f-413429515878 | note | Method - Review Document
8a57c43c-6ba5-56b9-999b-2f528c8cae75 | note | Frequency - Once
6fe46f25-6ee3-5521-8fd2-c5a43e036ec7 | note | Category - HP
e3e6ac7c-9299-521f-b005-e7fe4136f92c | note | Responsibility - Site/Project Engineer
08dd5a45-0ae2-5a5f-b985-c1dc55dc3a94 | note | Verifying Documents - ConQA Hold Point Release
9034d884-670f-5733-a93b-9eb388f47dbc | date | Date Completed:
13007d98-7895-42e8-944e-009ab8f1e9a0 | signoff | AUTHORITY HOLDPOINT
e668b736-7243-451b-adf1-b2864292c542 | checkpoint | 2.02 - Submit Welding Procedure/welding qualification welders Record
ab8dfc4d-f29c-5308-9cbf-0a02be736623 | note | Reference - NIST-2650 Rail, AS 1085.20 Welding Rail Steels
fc4a3129-1fb6-5678-a727-1ff5f6528248 | note | Acceptance Criteria - Qualified personnel & welding accordance with manufacturers specs.
1f00d4db-4638-5e4f-85ac-7636f97f3f96 | note | Method - Review Document
32063660-6716-5bd9-91c3-877da7388bb0 | note | Frequency - Once
60b27ed7-64e0-5682-968b-3390e143962d | note | Category - HP
4cf3c44f-7e4e-54b9-a2e8-5077ad600e5e | note | Responsibility - Site/Project Engineer
7f6eb449-5ba8-5bed-bcb5-9a40d97b1577 | note | Verifying Documents - ConQA Hold Point Release
d764daf0-9257-57a6-b9ac-5ec9c0ed879b | date | Date Completed:
672121a0-b2c2-4e5c-9d3b-f0f63c6e45a9 | signoff | AUTHORITY HOLDPOINT
f1db7d35-0bc0-4858-bf99-e8ea9a41e131 | checkpoint | 2.03 - Inspect supplied items upon delivery
f3f1eff6-4305-5424-b8cf-b9eb40117b88 | note | Reference - Bill of Materials
5b3f1206-ccf1-53da-887d-705bd4d2940b | note | Acceptance Criteria - No damage or debris on components
a2325d7d-f1c1-5d8c-97b4-54c4134c5122 | note | ○ Validate total number and type of components matches drawing
24af8a92-5a84-537a-a8ca-54bce3f4d6ad | note | ○ Attach: Photos on site;
79406030-f5eb-526d-af72-1494f78dc455 | note | – Track Rail
e8a181b2-262d-5a6d-aded-9a91c4e729e4 | note | – Track Sleepers
3e936192-0eca-5e5e-8af4-ff5cba09dd70 | note | – Track Jewellery
a11d69d1-d5f8-5313-b292-fe5bcac1befa | note | – Geofabric
f11b3a2b-4085-5ec8-9103-0b4dd895c908 | note | – Ballast 53mm Aggregate
135d7b66-5eaa-5294-88f3-c63e81e4767b | note | – Welding Kits
2a558eb8-a85a-5d5a-9c6d-a3ac2e3b3cc9 | note | – Welding Crucibles
a3a34ffa-e31a-5f8e-9df6-0cdead8cfc2a | note | Method - Visual, Measure
b00ba67c-18a1-590f-8101-a2f3bb1f4a50 | note | Frequency - Per delivery
25d3327a-b9f7-5c5f-93f1-92bec9fa2624 | note | Category - IP
780cc19e-c76d-5fb2-890a-438c3bbe1224 | note | Responsibility - Site/Project Engineer
7fb0dd3f-afa5-59a5-9dbd-e7f30fadec0b | note | Verifying Documents - Material Inspection Report
9eee3f21-a75d-5ff7-9221-fbd19ff031fb | date | Date Completed:
e3b88708-a9a1-4e7a-a154-a418845ecf74 | checkpoint | 2.04 - Confirm extent of track removal required for civil works
1733709c-c360-55ef-832c-ab350b4eee41 | note | Reference - IFC Drawing(s), Track Constrction Site Mudmap
31ce294e-89b8-5b73-92de-f6b21cd3fa80 | note | Acceptance Criteria - Extent of civil works and subsequent track removal to be confirmed in conjunction with MRPA civil team, limits of removal to be marked up on site
880bfad8-a091-5773-9cb5-6e41f93cf5c6 | note | ○ Pre-removal survey of existing track alignment
3c804d75-2521-5869-96ee-b13bf81fde85 | note | Method - Visual, Measure
5f39c344-85d8-5111-8a49-1f5de9f9780f | note | Frequency - Once
78de452a-87ab-50c7-b0e9-f562315aeebb | note | Category - IP
b52811f9-e501-5b41-a811-3a3c79bb69a0 | note | Responsibility - Site/Project Engineer
9d53ee4a-9e85-54a5-89b0-7c164231dd2c | note | Verifying Documents - This ITP
7b86346e-e093-54f8-a014-a8a42af8133f | date | Date Completed:
227a18b5-9d93-48a3-8b8f-ca004a2b0423 | section | 3. Construction / Installation Activities
6fa1715c-e545-4263-a0ea-d7311587f0ae | checkpoint | 3.01 - Deconstruct and remove track componends, including rail, sleepers, jewellery & ballast. Stockpile materials as required for reuse during construction
b217daf0-7edd-5fbb-b09e-38e96e499ea0 | note | Reference - IFC Drawing(s), Track Constrction Site Mudmap
e9764ea6-cded-5173-ad6b-67b3dab7eaba | note | Acceptance Criteria - Track structure to be removed to the designated limits as identified.
872511f7-e69f-5aa9-8dbf-f9cd3bdf878e | note | ○ Visual confirmation of removal on site
23b36569-18f8-5ccf-b8c5-d9d06d6f95b9 | note | Method - Visual, Measure
ce09bfdf-171c-53bf-9579-811ab77e47a2 | note | Frequency - Once
dcc4007c-51e9-582f-aa8d-197cf332d5cc | note | Category - IP
576e07f2-ef02-568d-9a13-2951def29529 | note | Responsibility - Track Supervisor, Site/Project Engineer
0d581278-6b30-5f8f-a267-6828ffa97b1a | note | Verifying Documents - This ITP
292ce303-0af4-5b5c-9669-e4820eddc422 | date | Date Completed:
5df56c74-4f8c-4557-b831-5e5e37ac6665 | checkpoint | 3.02 - Earthworks completed and site handed over from Civil Contractor
eddea061-d4db-5a18-a6b2-7f783119f409 | note | Reference - NIST-2659 Earthworks and Drainage
8e222d68-1e73-5a23-a9a6-2763e9f73580 | note | Acceptance Criteria - Confirmation of completion of underlying ITP(s)
17b552ee-3ac3-5146-ad5e-4d6e49cbf35f | textbox | Underlying ITP reference:
634b5e1a-18cb-51f6-ad28-dcf2e23c244a | note | ○ Applicable: Stage 2 Track Construction
1ad817b8-a257-5b54-b6d0-283627b5a22d | note | Method - Visual, Measure
93280113-3d19-5e7d-907a-a816160d0c3e | note | Frequency - Once
a146fb56-bbff-591f-84b0-ff47d189bec2 | note | Category - IP
dd2c39fa-8f41-589d-8fd0-effe72831c52 | note | Responsibility - Track Supervisor, Site/Project Engineer
2786f316-0203-57f5-841d-2f47b9c4e7f4 | note | Verifying Documents - This ITP
71c564bd-1c30-50dc-b780-614f2f97a40c | date | Date Completed:
a4b5ae1f-bf61-4a6f-b776-395216ada4af | checkpoint | 3.03 - Installlation of Bottom Ballast
4e7a93bd-30d5-5da0-9a68-8eebb096f0e9 | note | Reference - NIST-2654 Ballast
c731c0d7-97a1-554a-af65-76d8f990bafb | note | Acceptance Criteria - Overal Minimum 300mm bottom ballast depth
e06b7f70-f44b-52d5-a078-b7f0da67ed46 | note | ○ Ballast to be placed in 150mm max layers. Layers to be compacted with 10 tonne smooth drum vibrating roller with minimum 3 passes, in areas where wheeled roller cannot access, ballast to be compated using a vibratory compaction plate
e98f373c-6a98-501a-9d7e-d6bd679a2e1b | note | ○ Bottom Ballast to be left 20mm below final design level
092feb36-1056-595f-a50c-44dae8775385 | note | ○ Tolerance: Under sleeper -0mm/+25mm.
a8ac6350-0179-5e92-a9df-1951f1684971 | note | ○ Attach Site Photo: Installed Bottom Ballast Layer
ce3b0191-3717-5353-9326-53517b67d72f | note | ○ Applicable: Stage 2 Track Construction
92225965-b19b-50ab-be59-f78c5c7ea2f2 | note | Method - Visual, Measure
e0faad71-bbf4-5a4c-80be-b51a33504daa | note | Frequency - Once
c1749d08-6f6c-524e-bc31-0504c88ba765 | note | Category - IP
54fcc853-04e5-5474-a412-1070f81f46bc | note | Responsibility - Track Surveyor, Track Supervisor, Site/Project Engineer
10f01765-9821-5b73-98d0-7b31ce2c1956 | note | Verifying Documents - This ITP
67be03eb-5db3-5e16-a0e8-e0a941509557 | date | Date Completed:
7179affb-d428-4375-bb72-a8669fec673e | checkpoint | 3.04 - Laying of Sleepers
05f2a84f-6947-51b3-8176-6ce433ee00ff | note | Reference - NIST-2651 Sleepers and Fastenings
c19fe499-4d0f-5ffb-893a-7590570fb23a | note | Acceptance Criteria - Sleepers square at nominal 685mm +/-25mm for open track
9befc90f-c8fb-5e5b-b9df-1fe48b7713a0 | note | ○ Attach Site Photo:
749dd491-5b65-5cfe-bf99-ef89c1983b9d | note | – Laid Sleepers
c7784575-2379-5ddd-92d1-e535ddaec7a4 | note | – Sleeper Spacing Measurement
9f827df1-c32b-5502-abcf-26cc6dfc2f0f | note | Method - Visual, Measure
4d3d4aab-374d-5331-9187-7d6fc97f33f3 | note | Frequency - Once
da01ba39-7527-5788-ae78-a58a1c1669ba | note | Category - IP
0ddd529d-e9a0-5495-9ea1-72ac81ce0a34 | note | Responsibility - Track Supervisor, Site/Project Engineer
365fc5ce-59a6-527b-b5fc-68a98297ad94 | note | Verifying Documents - This ITP
3bbb0d25-b425-596f-9371-96f66f27a164 | date | Date Completed:
72fdb395-5ea7-4729-b863-ecd7406a11f3 | checkpoint | 3.05 - Rail & Fastening Installation
a4cd9d1e-75ff-5277-a0c8-ae49b028dfd8 | note | Reference - NIST-2650 Rail, NIST-2651 Sleepers and Fastenings
b769c300-84b3-5304-8011-98fc669958b5 | note | Acceptance Criteria - All rail sitting within Sleeper footing with correct sleeper insulators, rail ends positioned the midpoint of sleeper bays +/-50mm, no rail ends to be located within 3m of existing track welds, rail fastenings installed
6f4d24b7-e86c-5aa0-b6a0-7d480f58eaeb | note | ○ New Rail lengths installed to be as per approved Hopkins Road Rail Weld Plan
bfa8eaa1-b24a-5b99-9c92-37a57913c75c | note | ○ Gauge of track to be checked upon installation of fastenings
98979b30-c044-5933-9472-4eede6d5f1a0 | note | ○ Gauge +4mm/-3mm
7606b60a-7071-5105-a136-a8022f396af1 | note | ○ Gauge Variation over 2m 4mm
5341958c-9a14-5512-877b-5e24c38458c6 | note | ○ Attach Site Photo:
09de8a1e-4d46-5d2e-889a-9528507e23b0 | note | – Laid rail
8df2e9bd-96fb-5182-9127-1e85bcd5ae00 | note | – Rail joint to exisiting weld measurement
1baf9142-ff9b-5e5b-847f-dd60de36619a | note | – Rail joint between sleeper bay measurements
b5cd0a77-9b64-5ba6-b694-42f92c8fb05c | note | Method - Visual, Measure
21ef7d67-e71f-5baa-a178-577fdad3c6b9 | note | Frequency - Once
6705c5ec-d87e-55db-a165-4716f15a176e | note | Category - IP
66d0afbf-e28c-528e-87e9-8ee23c74d05c | note | Responsibility - Track Supervisor, Site/Project Engineer
45ae877a-cc77-538e-a5a3-c26d058a7496 | note | Verifying Documents - This ITP
233c0f46-2346-5548-a3f1-44db6105d03e | date | Date Completed:
2ae3268d-a2cc-4e18-9d3b-cfd5c0032384 | checkpoint | 3.06 - Track Tamping
e7ae554b-75aa-52b7-944b-82ef3b8f729f | note | Reference - NIST-2630 Track Construction, NIST-2706 Track Geometry
e1bf238e-915b-562e-9c84-7a86d198bbe6 | note | Acceptance Criteria - Tamping Ensures Track Geometry Tolerances are not breached (dimentions are in mm);
3b887af8-043b-5a77-a699-ea8349a182ba | note | ○ Line (10m Chord) +/-5mm
ae5c413a-3ecb-5bff-af7f-0018fbd87651 | note | ○ Twist (3.5m Chord) +/-5mm
28c80973-0731-5d78-bc49-0fb8b11b2472 | note | ○ Twist 10m (Chord) +/-10mm
510b5b84-6201-5883-af5d-cc719b7badb9 | note | ○ Cant +/-5mm
efb3c238-ef90-5921-9a76-18ea808bc221 | note | ○ Top (10m Chord) +/-5mm
7f36889a-f809-5faf-90e6-c702a3617aaf | note | ○ Alignment +/-20mm
b86a8656-ab43-5ebf-956b-ac9185c3db39 | note | ○ Survey measurment of RL of top of rail head
0d80dd1d-bddc-5704-be74-a6dc6c5c59d3 | note | ○ A minimum horizontal clearance of 3.0m from track centreline to structure.
dff478ed-3a7f-5fb2-ae22-890c6cbcd5b9 | note | ○ Attach;
fca8d769-8e1d-5bcf-9c97-a0452eef6eed | note | – Tamping Geometry Recording
4aa24e02-53f1-50c5-bae0-af47ee4a3951 | note | – Survey RL measuring sheet
35861c5f-45e7-57ae-860e-82a315219256 | note | ○ Attach Site Photos:
59a4fe04-d8b5-5a00-b756-88c57fd71c09 | note | – Tamping Activity
3d8eda09-8c64-5168-90cc-16bc47bc9d37 | note | – Structual Offset Measurement
d52b31f8-cfcb-5bfe-aa8f-b832df3d8d5c | note | Method - Visual, Measure
da580e28-8c35-588c-b4c5-b41622955209 | note | Frequency - Once
aa1b088e-f1ac-5e67-9240-fb98f31c21b0 | note | Category - HP
bf3ee2a5-4a75-5bef-8fab-1e65b8bff36f | note | Responsibility - Track Surveyor, Track Supervisor, Site/Project Engineer
0aa2d481-d9f0-5aa7-8e14-070789349142 | note | Verifying Documents - This ITP
d7f49704-9dbd-59e1-819b-25b85ebc8543 | date | Date Completed:
352dc2ea-76b7-41d6-84b3-42e9c325496c | signoff | AUTHORITY HOLDPOINT
2cb6335e-7fc1-46af-b8b5-b69b920f6bb0 | checkpoint | 3.07 - Regualting and Ballast Profile
d67ef0bd-4b1a-5e0e-9ded-83003f53a594 | note | Reference - NIST-2630 Track Construction, NIST-2706 Track Geometry
53f5eb1b-f912-5b31-ab57-f0cc1cc18ce0 | note | Acceptance Criteria - Ballast shoulder of 400mm width from outer edge of sleeper and with 1:1.5 angle of repose thereafter
3abb7be1-1bd3-53ba-8bc7-083590a75dd5 | note | ○ No Ballast to be on top surface of sleepers or aorund rail Fastenings
37a8bf24-22e0-5841-8c3f-14ad48774e43 | note | ○ Attach Site Photos:
73f063d2-5440-5a28-bf58-3de25091610d | note | – Ballast Shoulder Measurement
08c07cc2-d859-5708-b31a-247260e0ebbe | note | – Rubber Panels free of ballast materials
a114bc9a-9b68-56cc-b688-6253a5dfb89f | note | Method - Visual, Measure
eda95bf2-5341-5663-a958-51e0e130b262 | note | Frequency - Once
32d66cb6-4008-554b-aa51-8b8c8432c2c2 | note | Category - IP
2cf22177-d8c3-5ed3-b5f9-02caa60b15ee | note | Responsibility - Track Supervisor, Site/Project Engineer
6b9986ba-b6c7-5486-9851-bd820c9f81f5 | note | Verifying Documents - This ITP
8dc870e5-d1f3-5532-ac69-76ff98bf15f0 | date | Date Completed:
5038e2aa-bdc5-477a-928b-58b797337713 | checkpoint | 3.08 - Aluminothermic Welding
985e765d-980e-562f-833b-707d366217fa | note | Reference - NIST-2650 Rail, NIFO-2650.5 Aluminothermic Weld Record
df0f638b-9f23-53e9-8975-6637f65359ca | note | Acceptance Criteria - Welds to be lined and finished to alignment standard
f1d28cf9-06c3-5e1e-b24c-a2ece5f31374 | note | ○ Tolerance:
c4b34533-a4c1-5a18-b004-a07997816e64 | note | – Gauge Face +1.0/-0.5mm
55dc01c1-ab3b-5513-a7fb-2c41303f047d | note | – Running Face +0.6/-0.0mm
0f5769d2-1172-51ff-8bf5-76d82b5b240a | note | ○ Verify Aluminothermic welding carried out in accordance with AS1085.20
707c8b63-e943-5c00-9a17-d09cc998fc8b | note | ○ Aluminothermic Weld Return Form to be completed
de03c30b-9b7e-550a-8d73-6610729a8e9e | note | ○ Attach
6631d9df-66fc-58b9-bbf6-01a795ce6289 | note | – Aluminothermic Weld Return Form
f1f50110-3018-5395-a536-cc0db376bcfb | note | ○ Attach Site Photos:
c5626c4f-c80c-5398-8921-9eebf6fa1778 | note | – Welding Aligning
e37e8a00-2c17-567b-9d4a-cae9b6453613 | note | – Welding Process
6342aa7e-22e5-566f-ae9d-d3ded2c1bb3c | note | Method - Visual, Measure
37ecc29e-6ddc-52a8-93e5-cc966c5f353c | note | Frequency - Each Weld
1d981443-8b3c-5665-af17-dcbe251d37f9 | note | Category - IP
0dce6a2a-6773-5bab-99d0-cb35cf118cb2 | note | Responsibility - Track Welder, Track Supervisor, Site/Project Engineer
cce4576b-df79-5b36-8ab6-f087b9bc076d | note | Verifying Documents - This ITP
0475f5f3-b4a6-5e52-9fb9-73d010bebe8a | date | Date Completed:
66ded4bb-0353-40fd-a4f1-3bf05ac687fa | checkpoint | 3.09 - Track Stressing
e6d0452e-bd86-5b46-b8d5-17336c4505a1 | note | Reference - NIST-2650 Rail, NIFO-2650.5 Aluminothermic Weld Record
a4746ab7-ab32-5aa4-93d5-bff73afc5318 | note | Acceptance Criteria - Stressing Rail in line with V/Line Rail Welding Process
f93ffec8-fc63-544d-a7a3-63b7396cef5e | note | ○ Ensure Stressing only performed between rail temperatures; >10 and <38 degrees
9d0b5e71-f65c-5d49-886f-0d2621ebea81 | note | ○ Complete track stressing in 330m module or otherwise as noted on approved track stressing plan
91c22311-dba5-5300-bf08-18b0f57a0b97 | note | ○ Reference Marks recorded pre and post tensing of rail
878041b0-ed9d-5f64-be86-8e09f57479f8 | note | ○ Aluminothermic Weld Return Form to be completed
f368a18e-ddc5-5958-b7e7-5256542af874 | note | ○ Attach
94bc590f-f190-57f4-bd45-658f3c75f9f1 | note | – Aluminothermic Weld Return Form
0b4f52b7-3e6a-5fee-abbc-5c74dcef5de4 | note | ○ Attach Site Photos:
530591a6-cb1c-5044-9948-1cfd9787db0a | note | – Stressing Activity
81840bb0-85d0-525e-87d2-2b137fae8f6c | note | – Under Rail Roller Spacing
f56b7fdd-92c5-5401-afdc-d13b718a2267 | note | – Before/After Reference Mark Measurments
d020044b-b5fb-5523-858d-ff6baab994b0 | note | Method - Visual, Measure
d8569e2f-ed84-5023-bc6a-797e931cfaa9 | note | Frequency - Each Restress module
e823eead-0c31-51dd-ba42-1cda4cdc7354 | note | Category - IP
f33a8af4-017f-582d-82b6-5ec2cc51f8eb | note | Responsibility - Track Welder, Track Supervisor, Site/Project Engineer
694557b4-4007-5ba5-b50a-30f67e87a5a4 | note | Verifying Documents - This ITP
00059a1d-7ed2-5de5-a69c-6a01d0c3d1af | date | Date Completed:
c82588b1-d403-485f-a6f3-59d4e615e671 | checkpoint | 3.10 - Weld Ultrasonic Testing
05e3d4b0-251e-59bc-923d-99a5aac3d146 | note | Reference - NIST-2650 Rail, NIFO-2650.5 Aluminothermic Weld Record
c511328b-f158-58a9-9c54-358305c7ecbc | note | Acceptance Criteria - Ultrasonic testing to be carried out in accordance with NIST-2650 Rail
83500920-05ef-56fa-b203-b9f144e4036b | note | ○ The cross section of the area of the head and web shall be completely scanned;
18ff08e8-ded8-5e59-898d-6e24a35335aa | note | – The foot area shall be scanned in accordance with AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2.
d080f53e-5d5d-5a9a-8f24-d1d2d8912e83 | note | – Welds shall be scanned to both directions.
65d5174e-5c24-5712-a31d-455c6177cca4 | note | ○ No classified internal defects found
d5a779b4-f160-5078-94f1-6f363735be5b | note | ○ Final weld geometry to be assessed
14997246-58f0-5a61-a12e-dfd5d06f47ef | note | ○ Tolerance:
16e8c830-f628-573a-bf8c-66bec6e140ad | note | – Gauge Face +1.0/-0.5mm
3c737f66-a702-532f-83cd-0368a7cedf60 | note | – Running Face +0.6/-0.0mm
78621ad1-37d5-5d1f-bccd-d070e8fdbfad | note | ○ Aluminothermic Weld Return Form to be completed
45489189-8167-5334-80f1-2380f79ae058 | note | ○ Attach
f60ae436-2f66-5a8b-8e85-65795bad779d | note | – Aluminothermic Weld Return Form
ef6ec2f5-5aee-5c01-b9cb-53f0077bc5bc | note | – Aluminothermic Weld Test Report
9024cb2d-a521-51b4-8b77-a78fb347c49e | note | ○ Attach Site Photos:
3579bd1c-fffe-5c9a-9a2c-d73751af379c | note | – Welding Aligning
866c0052-d6ab-5869-a224-ad1b7a70fa7f | note | – Welding Process
b1993a63-a1f3-558b-8b6f-ff98e7f03479 | note | Method - Visual, Measure, Test
97cd65a7-18dd-53a9-9220-35d503688e8f | note | Frequency - Each Weld
ef1044da-c144-5db8-aafe-4ca82a2adacf | note | Category - HP
b73a9f78-8ca9-541f-9b6c-5482de630f57 | note | Responsibility - Weld Tester, Track Supervisor, Site/Project Engineer
33a6e796-153c-5c91-bed7-ca12e551c8d6 | note | Verifying Documents - This ITP
2ef71d70-b3e5-5176-aecb-43e9a52d377c | date | Date Completed:
6e3a4ee1-8aed-41ac-92a7-504056b3bfc7 | signoff | AUTHORITY HOLDPOINT
e8394f8b-4b06-408d-ab4d-7fa04ff0ee59 | checkpoint | 3.11 - Installation of Guard Rail & Guard Rail Nose
e17e1afd-0a15-54d8-820c-16ce8192ae20 | note | Reference - IFC Drawing(s), NIST-2650 Rail
a8ec6f8b-6912-5871-b6ff-e6a3186a715e | note | Acceptance Criteria - Install guard rail and guard rail nose as per IFC design
e2b3c1d6-8162-59b2-ba31-ee5107acb7f2 | note | ○ Guardrail to be installed with alternating fastening pattern
c251e3ef-52e3-59c7-b5f4-6a4576a00e6d | note | ○ Guardrail to be isntalled at lengths of either 13.7m, 19.9m or 27.5m, joints to be gap adjusted and plate & bolted upon completion
5c254598-2966-5518-82df-b085dede77ed | note | ○ Attach Site Photo:
cb41755c-e3e9-5fdd-acaa-75a2db15b5f5 | note | – Guard rail isntalled
c3edf3c6-bed2-524b-9f21-818b34c1c12e | note | – Guard rail nose installed
18063b94-fbc3-55bf-a45b-5d5c87d2306b | note | Method - Visual, Measure, Test
d228adc6-85e8-5d60-839d-816be850596a | note | Frequency - Once
6ba6266a-d830-5a33-8a9d-a1f99973ca71 | note | Category - HP
3622b183-49d7-521c-b2a6-5838afd5938a | note | Responsibility - Track Supervisor, Site/Project Engineer
3dc37cd8-3609-55fe-8f92-6fbe6920de2d | note | Verifying Documents - This ITP
67e35ef7-b0b8-5c4b-8fda-5bd5a4a2cd3c | date | Date Completed:
965fe67b-9305-4957-887c-dbd3aabc48b9 | signoff | AUTHORITY HOLDPOINT
a68a06c9-3544-4517-a2e9-dcc49d2b40f7 | section | 4. Post-construction / Post-installation Activities
ff733a3c-dc89-4624-8df0-b9865a788cbe | checkpoint | 4.01 - As-built Survey
6a0b44c3-0631-5589-9e28-0ecce1496c2e | note | Reference - IFC Drawing(s)
3a14d1b1-de08-54c1-b8e2-1e98bf14cd64 | note | Acceptance Criteria - Survey activities undertaken to validate correct construction
6b216909-02e0-5349-a708-c07ef707336b | note | ○ Attach:
f6e72255-3b84-52bf-b2e5-e1afbe9963f6 | note | – Survey Report
3317be74-c9c4-5378-9be5-cd83da81b2d5 | note | – Engineering Asset From
b555e47a-b4ee-523a-aaf2-7ce963b5024a | note | Method - Survey, Document Review
b73ebbf0-f5d2-5ade-8efb-845e6c0cbca6 | note | Frequency - Once
f22e5842-2d66-51d7-9288-cbf361f65dc5 | note | Category - IP
fe71680d-ca29-5960-ac82-e2caac4a08d1 | note | Responsibility - Track Surveyor, Site/Project Engineer
14c83884-3795-5a1b-b95e-6780472732e5 | note | Verifying Documents - This ITP
4ea49d85-34af-5eeb-aa1a-427d531ec24d | date | Date Completed:
b5ff65a1-9365-4dc0-9d8f-5360086a0c95 | checkpoint | 4.02 - Track Certification
e26bfb07-af7a-5a17-8edb-745f609cc869 | note | Reference - NIFO-2690.3 Certificate of Track for Operation
9da44514-c148-5f91-9a7b-9e1299190053 | note | Acceptance Criteria - Attach:
380d2f75-cadd-5a82-b0aa-9b53d78f6500 | note | – Track Geometry Conformance Certificate
997192b4-421a-546f-801d-a813bacf0a61 | note | – Track System and Component
80969fb7-1906-5374-b471-2c299a685212 | note | ○ Attach Site Photos:
8284408a-678e-5f8e-bd39-7928b209ef61 | note | – Before/After Photo of worksite
aa406d03-a19b-504c-9f44-60a2ea114e37 | note | Method - Visual, Measure, Doument Reivew
f0bfff49-fc53-5924-b733-030f4d367756 | note | Frequency - Once when all occupation works complete
251dfeed-9fab-59d5-9d32-0c945d910894 | note | Category - HP
4d1c877c-d66e-55af-ba4b-4ada199a76ee | note | Responsibility - Track Certifier, Site/Project Engineer
69c8d125-097e-5938-931f-a71faffcb95d | note | Verifying Documents - ConQA Hold Point Release
f29136ff-459c-5010-82ed-10f3d02bde42 | date | Date Completed:
077e7b5a-c193-44bd-af80-205c50e54911 | signoff | AUTHORITY HOLDPOINT
104def8f-1036-4382-8172-6d7d276bb312 | checkpoint | Final Inspection
b1a76b38-34f1-5d24-900e-858dcfddef70 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
46f22774-d7f5-5d8c-9c91-2eecfec6e58a | textbox | Name:
9c3f2f58-ccdc-5ed9-bb9a-0853a9e207a3 | textbox | Position:
e56e1733-2ee5-553b-99eb-a1d525f39d7c | textbox | Date Completed:
baaf26ce-30a1-4b05-a563-036c2485f959 | signoff | Sign ITP
5fc8aa10-4dab-4128-8a19-1a527f1fde3c | checklist | ITP-238-CIV-HOP-Stormwater Drainage Pipes supply and Installation Rev1 | itp | ITP-238-CIV-HOP-Stormwater Drainage Pipes supply and Installation | 40711e59-1df5-4a4f-8260-e4c3dbdcb74f
3d83087c-8474-43f1-84d4-e0a50701bc11 | section | 1. Referenced Documentation
8a6cc1dd-d3ec-4689-895f-7e4f04ae6868 | checkpoint-no-value | Referenced Documentation
c5b0f62d-49df-59c9-ab9c-a5e30fe83dc6 | note | Document Title: ITP-238-CIV-HOP-Stormwater Drainage Pipes supply and Installation
b2cdad0c-2a55-532d-8a8f-ec5c01645968 | note | ITP Description: HOP-Stormwater Drainage Pipes supply and Installation
5241a44a-095e-5533-ad49-658031975183 | note | Discipline (e.g. CIV/STR/RAIL): 238-CIV
7ad72ecb-1aa8-557b-be67-8f6bff064ae5 | note | Revision Number: 1
a5fd9f5c-9e4a-5683-91ee-a935e73c1664 | note | Revision Date: 8/01/2025
f2ffb986-01d4-57e3-8de4-718e73105fd7 | note | ITP created by: Cedric Guico
ca9a301c-076a-5422-bd6e-ff32eb7f0461 | note | ITP approved for use by: Pradeep Talasila
04220660-831a-5940-b75a-35be1fc8a3c0 | note | 1.01 - Non Dependent
617fa5f4-8224-545f-876d-2a2678279c49 | note | Reference - VR 701
03ec9686-df8a-429e-a29d-0839b1f24234 | section | 2. Preliminaries - Materials
50090e9a-26ec-4932-81f9-8ed1b542be9b | checkpoint | 2.1 - Drainage Reinforced Concrete Pipes (RCP)
78e9e347-7125-5b6f-82a7-c839008075d9 | note | Reference - Section 701.04, Section 701.05, Section 701.09
524eb115-03e9-548e-98a1-0f59bc3efe42 | note | Acceptance Criteria - Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with AS/NZS 4058 and Sections 701.05 & 701.09
c3c4089a-d3d4-5d40-809e-04280162100e | note | ○ Precast reinforced concrete box culverts shall comply with the requirements of Section 701.04
377acad9-12a3-5daf-9356-fe34a53a90d9 | note | ○ Rubber ring joints shall comply with the requirements of AS 1646
a11e274b-ea58-5820-a03c-3ddd5b0d1746 | textbox | Enter: Teambinder Material Approval number
04598692-0e06-58a9-b8c7-34453af9b62f | note | Method - Document Review
29d49dd8-ec90-5f88-8e49-03558fbade0c | note | Frequency - Each lot
734672d1-40cf-593e-bb25-4d932051f336 | note | Category - HP
3853a593-8084-5c38-8b4b-76ddcb4ef24e | note | Responsibility - Nominated Authority
a024ae16-b095-5361-b775-82d0b9753149 | note | Verifying Documents - Teambinder Material Approval
b960f4cd-df6f-53d9-b6c8-d45dfab4c4dd | date | Date Completed:
1a78fd3b-8d3a-48f3-9af8-730e2bcaefd0 | signoff | AUTHORITY HOLDPOINT
3e7d9d90-4a12-431e-a689-a48bd856b3c8 | checkpoint | 2.2 - Drainage Flexible Pipes
8078e131-4e10-59e2-8315-31ab2de2bf5f | note | Reference - Section 701.08
2cb218ba-eec2-568f-a1bf-c7b76b3fb413 | note | Acceptance Criteria - Flexible pipes shall be supplied in accordance with 701.08
d1c93c78-2769-5edf-b71e-e8f52cdea5a8 | textbox | Enter: Teambinder Material Approval number
02803dcf-18ab-5b3b-ae3f-e67371183dd7 | note | Method - Document Review
bcfe9fa3-972a-5bfa-915e-b9db6c3b0b88 | note | Frequency - Each lot
116971fb-e6fc-5cbd-b1ac-9e94cd06791a | note | Category - HP
4108b198-8457-5629-b48b-22d063e60d9f | note | Responsibility - Nominated Authority
42bfe68e-fc4e-5d2f-bf03-a447da317080 | note | Verifying Documents - Teambinder Material Approval
feb3d539-ce3a-55e5-a118-a4f761493050 | date | Date Completed:
4a9a1462-6abb-4187-86e9-a5b86e39c1f5 | signoff | AUTHORITY HOLDPOINT
ba175b0b-3768-4b40-98dd-cfc9af4d769b | checkpoint | 2.3 - Drainage Bedding Material
3773b383-af6a-5002-8cdb-1c2426039776 | note | Reference - Section 701.09
40f13e7b-1420-5e52-ab83-7dd44bcc46e0 | note | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
192cca10-3dd7-52a8-9a28-f5a555d2c56b | textbox | Enter: Teambinder Material Approval number
40a4bed1-a44e-5173-aec7-cdfc55a110a5 | note | Method - Document Review
63b1effd-3472-5468-a764-47c007076a72 | note | Frequency - Each lot
be3cdda9-a186-5b44-bd49-4a8c3cd0e78c | note | Category - HP
43053bf5-c767-5726-a13b-1c5a4c9d1a38 | note | Responsibility - Nominated Authority
547ff253-b6e1-590c-a998-cbb61bd07eb9 | note | Verifying Documents - Teambinder Material Approval
4a1a97e8-5f34-55dc-b782-535bd57183e0 | date | Date Completed:
86776051-a1c8-4991-a048-e44da87b362e | signoff | AUTHORITY HOLDPOINT
15e9544e-7433-4b8d-8d64-9d4769cb4126 | checkpoint | 2.4 - Drainage Backfill Material
761a25ee-a3a1-5e90-80a9-0a582cf0c13c | note | Reference - Section 701.09, Section 701.19
49fc3a10-eb8b-511f-b3cb-cc6332e13627 | note | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
7a6c34b6-f2e8-5695-b50f-a8b2973a52e6 | note | ○ Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with Section 701.19
7a9a5480-e162-5b37-a6fb-eb7422c348d5 | textbox | Enter: Teambinder Material Approval number
72cea4d2-c195-511d-8f0a-6008d4233c8c | note | Method - Document Review
3f7d980a-10ca-55f2-bb86-f2f5cc40b244 | note | Frequency - Each lot
09d92b33-4c56-5099-a313-37afab2187d0 | note | Category - HP
87fa18b5-7f05-5586-984a-080f8a31b763 | note | Responsibility - Nominated Authority
aafd2f17-24a9-5fb9-9d03-ce28976906d3 | note | Verifying Documents - Teambinder Material Approval
4138ca46-f27d-553d-a6d4-dc413b5fc867 | date | Date Completed:
9535231f-9191-46b0-8b42-137727cf9dce | signoff | AUTHORITY HOLDPOINT
c697db84-7a71-4a16-804e-0bd91036cabc | section | 3. Preliminaries - Procedures & Documentation
494ad958-781f-40ea-8323-adba2bd23a66 | checkpoint | 3.1 - Subcontractor QA Submissions and ITP
81d13622-94cf-5ab7-90d7-136bf7494793 | note | Reference - VR 701
c15ed15a-184b-5ead-a136-f69d6c755f25 | note | Acceptance Criteria - Subcontractor Signed ITP Shall conform with the Hold Point Release in the Main ITP.
62cf022b-4401-5234-90ba-2eaedf0c20dc | note | ○ ATTACH: Subcontractor Signed ITP
d72f1dda-2483-58ad-b2d8-c0e827c0ce30 | note | Method - Document Review
ca364706-e856-56c3-a0a1-ac3fff5b6143 | note | Frequency - Each Lot (in case undertaken by subcontractor)
526b58b3-94d7-577e-982e-5df56d616c82 | note | Category - HP*
e691facb-7050-5573-96c4-d80907efdefb | note | Responsibility - SE
87f73afd-8c3f-5cba-9f96-a5bbe7e9514e | note | Verifying Documents - ConQA Hold Point Release
48fa5cbf-f79d-5eb4-a3e7-fda9bbe8bff9 | date | Date Completed:
42651151-7139-443d-8cba-33e1ffb6e60d | section | 4. Pre-construction Activities
683f66b2-6ad9-4c8d-b4ba-634ca7978a06 | checkpoint | 4.1 - Survey Set-Out-
a3448ff1-4404-5bfe-8126-3505d847808d | note | Reference - 710.1
39717e97-1ecb-53a3-a8c6-9c55503f0f9a | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
ea570ac3-4d15-53bf-9688-cddee88ca048 | note | ○ The culverts constructed shall be constructed true to line and level.
0cf8c593-5927-5b51-9a3d-470480ab31b7 | note | ○ MARK UP LOCATION OF THIS LOT ON THE MAIN LOT MAP
306fbd2e-561c-5b9c-aca7-cdd0985bd3d8 | note | Method - Survey, Measure
60b681d8-2124-57ed-8c75-e20c7d75af13 | note | Frequency - Each Lot
807ef1f4-15fd-560c-b188-d5784d3287cd | note | Category - HP*
46f23337-1188-5ea2-bedf-b797e147a48a | note | Responsibility - SE
a0c228b9-e251-573d-9ecd-1cb2a6452937 | note | Verifying Documents - This ITP, Main Lot Map
84748ea7-7c40-5bd3-bcd4-821995e9f0c3 | date | Date Completed:
00014228-c92d-488d-9c24-c7006d9955e2 | section | 5. Construction Activities
97a2eb20-9a8b-4c1e-9081-42c87787405e | checkpoint | 5.1 - Trench Excavation
6ab1fe37-4447-54dc-a063-3be0b4725bc4 | note | Reference - VR 701.15
9cc0e160-7b44-5bc2-8b72-5c01be72fda6 | note | Acceptance Criteria - For box culverts, the width of the trench shall be such that the clearance from the outside of the culvert to the wall of the trench is in the range 0.5 to 1.0 times the overall height of the culvert.
5f72acef-8a6c-5559-80e9-c09cf68b77b0 | note | ○ Horizontal Clearance to wall of trench
7facd0e6-f9d8-578a-bb87-dcd8b79c71e4 | note | ○ Pipe Culverts:
ba471026-c6db-5888-abca-9f8d41b66229 | note | — 300mm < Horizontal clearance for corrugated metal culverts < 1000mm
6df95756-6e5a-572e-afdb-c2b076694963 | note | — 300mm < Horizontal clearance for other Pipe culverts < 600mm
2745dab9-3311-565d-9349-56ff4a10b254 | note | ○ Box Culverts:
09ee2527-8b4a-57ba-be11-487667919fdf | note | — 0.5 times the height of the culvert < Horizontal clearance < overall height of the culvert
021ddf8e-d224-581f-a906-4db856f11aab | note | Method - Measure
23f33fbd-f60d-58ac-b31b-b33e60bf4cdb | note | Frequency - Each Lot
b37c24ae-2ea0-5f2a-bcce-5d5f4fc620a5 | note | Category - IP
8af9fd50-d6a5-56e0-b115-a3cf481a4c01 | note | Responsibility - SE
128c6285-0992-570c-b21d-f9855b09e710 | note | Verifying Documents - This ITP
f88d6a4b-f49e-5881-8444-6c3474bd8c16 | date | Date Completed:
8bb3fdc4-59ea-4e2b-9acf-7aefa27f2ff0 | checkpoint | 5.2 - Trench Base
6cbd186e-abda-5966-a3b4-444cf9d82567 | note | Reference - VR 701.15
292e68d8-f012-5714-8d2a-1d78736ec769 | note | Acceptance Criteria - The base of the trench shall be compacted to refusal using mechanical plant
2838563a-fa13-5a19-98a2-0afe5fe01771 | note | Method - Visual
e103f43f-6fab-51f3-8eab-3808838591cc | note | Frequency - Each Lot
fb12cf38-0218-5bbf-9126-075b21c1184d | note | Category - SP
b9767d74-a52d-57cd-8a94-098b8fbf5b05 | note | Responsibility - SE
3025635a-23b1-5fc5-86b5-86de5b160518 | note | Verifying Documents - This ITP
219c9139-7a43-54af-ad10-6d02346c64df | date | Date Completed:
57a4e193-5cf5-4db2-87cf-c667edf14e86 | checkpoint | 5.3 - Bedding-Placement and compaction
46490040-c4d6-5577-861b-980de52f43ad | note | Reference - VR 701.16, VR 701.20 (a)
ed42a657-9e1f-5ffa-b68c-08a1b05edfce | note | Acceptance Criteria - Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be not less than:
396c9157-6c2f-5197-903f-f61057e4ae2a | note | — 100 mm where D < 1500 mm
4b08d255-a08a-5485-8765-70f8a351bb81 | note | — 200 mm where D ≥ 1500 mm
228bfb67-4122-5252-8f4b-7d2f8a75a942 | note | ○ Bedding materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer
8b07663c-5918-5817-9275-bfdf1bafe9fe | note | Method - Visual, Measure
d0197297-db2b-540a-9ec2-3de65eababff | note | Frequency - Each Lot
4950ae7f-3850-56c7-8733-7110e6c858d2 | note | Category - SP
0a7c1a71-ec8e-5401-ad37-b6d5f8f4f605 | note | Responsibility - SE
b016a6c6-c8d6-5edd-951e-aa4646f5cba1 | note | Verifying Documents - This ITP
9f14aedd-7bc3-5919-acad-32862f1f3ea7 | date | Date Completed:
5860936c-fafb-4327-ba41-e24a3202a14f | checkpoint | 5.4 - Laying pipes-Bedding conformity
eff3c81e-78e3-5aaf-a60d-2f4001c1ec6c | note | Reference - VR 701.17
386d19e6-d62b-5ca9-9213-09f5e537828a | note | Acceptance Criteria - Laying of pipes or box culverts shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and that box culverts and pipes are not damaged.
4b301231-c691-58b7-aac3-42f04e4fcdf9 | note | ○ Laying of pipes or box culverts shall commence from the downstream end.
9c8315c6-1e27-541e-81d4-c879150d49ab | note | Method - Visual
c8269f40-0a89-5d10-af61-d4e5c014bdf6 | note | Frequency - Each Lot
bca16fdd-e0fc-5b09-9b28-f47e1841f319 | note | Category - HP*
8db2d29d-cc8b-5a87-ba8c-96099239042a | note | Responsibility - SE
e9db97cb-886e-5041-92e6-af6e3cc14a48 | note | Verifying Documents - This ITP
87499353-0333-5d6c-ba45-0b2237133f4c | date | Date Completed:
7084be11-2f6e-440a-8ace-bfc49e6f096b | checkpoint | 5.5 - Pipe Laying
d203e75f-b988-51c4-a1f3-54cf779003b8 | note | Reference - VR 701.16, VR 701.17
08829fc6-3fec-580d-9375-c72bbba1452e | note | Acceptance Criteria - Laying of pipes or box culverts shall commence from the downstream end.
5b0e6c9f-c4f7-5de5-b6b3-60b38a0a14c9 | note | ○ Rebate and socket ends of pipe sections shall be placed facing upstream and be fully entered.
ceee8849-5a36-5575-9e82-637e9d28957a | note | ○ The lower portion of the pipe shall be in contact with the bedding for the full length of each section.
bc43d5e5-e3df-5ae1-9b98-33fd268cc81b | note | ○ The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length.
637c45e1-f057-55d2-bb95-b437ea37ff58 | note | ○ When the sections are in position, an additional layer of bedding material shall be placed to a height equal to 30% of the nominal pipe diameter or culvert height
0718c15e-208c-5ef8-9db8-ad0f47d69777 | note | Method - Visual
7be10e26-b702-5b39-b74f-30f2829ad957 | note | Frequency - Each Pipe
aac1bce1-fc26-5a10-b97b-08f569fdf85e | note | Category - SP
cc5b5faa-6595-5556-a1b6-102b9bb560b2 | note | Responsibility - SE
55706f8f-8896-5b3d-9075-cb902a2e18df | note | Verifying Documents - This ITP
0b8cb377-001d-5cbf-b282-eb24bef11c20 | date | Date Completed:
ba02fe4c-b313-4a96-b3dd-4641039c6912 | checkpoint | 5.6 - Pipe Joints and rotation
3d0ba90e-10af-53bc-8fb5-e55bfeeef52d | note | Reference - VR 701.18
d4a7c5a5-14ea-5129-9b19-949c08c6573f | note | Acceptance Criteria - All interlocking RCP shall be mortar jointed, or wrapped with a 200 mm wide external joint rubber band.
3409171f-71ec-5249-a592-c0244c303de7 | note | ○ Pipes shall be laid with lifting holes uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed. .
60dbe54a-3628-5ac9-ab47-85cf55f00146 | note | Method - Visual
940ee461-ebe6-54d3-b845-768413a233f2 | note | Frequency - Each Pipe
91a27032-2334-5b48-899c-e11ca0b3bd81 | note | Category - SP
ebbf0619-068f-57c5-a2a4-36d955245d1e | note | Responsibility - SE
553c9fe7-5837-5dab-8c90-d341860f2051 | note | Verifying Documents - This ITP
9e50f5b9-7553-5586-9165-7643393d62b9 | date | Date Completed:
87cbfcad-b345-42b3-8a3d-a4eb87e2ef00 | checkpoint | 5.7 - Conformity with drawings
47031b9a-01ea-58a0-89d0-33f70e4c0eb1 | note | Reference - VR 701.10
b3009fbf-ccf3-57a7-901d-a79979e66895 | note | Acceptance Criteria - The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
1779afbe-eda3-5e9d-9717-a699e10aa4f2 | note | ○ Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
0ebafd6a-65d5-5256-9fb4-2fbb603f7340 | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
0987ef50-91d5-5494-96ff-8258b4ebdbea | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
87f5070a-07b4-5adc-9979-477755eb0c58 | note | (c) invert level of pipes at pits ±50 mm
a67fa551-bf17-52a3-ad52-d0c936523e41 | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
a06157d6-ae32-5e4b-9ee5-99485c582a93 | note | ○ ATTACH: Survey Report
8ed21852-52a1-5341-9dc3-8d6fac04401d | note | Method - Measure
3d3531b6-b283-5b85-b737-3318a3be9869 | note | Frequency - Each Lot
75844952-71a1-53bf-9826-65eed70e2bc9 | note | Category - HP*
8efe7fd6-b1ba-5312-b9a2-97e3d70b7776 | note | Responsibility - SE
e36c2cf2-e296-5d88-92ad-a9ae9348b668 | note | Verifying Documents - Survey Report
2493f336-eb63-567e-9952-da299dc2eb00 | date | Date Completed:
96422d68-42bc-4621-b6c3-c4edfbe7f648 | checkpoint | 5.8 - Backfill-Under area to be paved
bd1c84d0-2d5c-571d-b940-0d7894c0dfc6 | note | Reference - VR 701.19 (a) i
72bd7a52-ec74-543b-bb81-57424569acd3 | note | Acceptance Criteria - Culvert under area to be paved
a130f539-8a19-5b2c-bb23-c0f766d2e9d4 | note | ○ Where the trench has been excavated from design subgrade level or above, the trench shall be backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material.
51e5bdd2-37b0-56d1-abd6-45105cb69b23 | note | ○ Where the trench is excavated from below design subgrade level the trench shall be filled with selected backfill material.
a4c69002-1e21-54c6-9221-4936d1778188 | note | Method - Visual
124ca301-a003-5eb2-9d47-aa86d591b5a9 | note | Frequency - Each Lot
c095bdfa-ab9c-5b79-8777-0b09c5464f1d | note | Category - SP
d474fc00-76c0-5b50-bc0b-77e87fa10620 | note | Responsibility - SE
c83e879a-c5b5-5e0c-ba41-6467837f7878 | note | Verifying Documents - This ITP
88dd39f0-de70-5630-8f98-9da19249b6ad | date | Date Completed:
e0e65b45-1d11-4bee-8b79-da4ae4898d38 | checkpoint | 5.9 - Backfill-Under area not to be paved
907ee0a7-b252-5e5e-b543-04b8be767272 | note | Reference - VR 701.19 (a) ii
60b676c0-5ea6-5551-b1ae-849682dfde2b | note | Acceptance Criteria - The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level
1c6629ee-2ba6-5324-aaa0-c9d02bf71e32 | note | Method - Visual
f6991abe-6ce3-555d-8332-7facf41ee368 | note | Frequency - Each Lot
6fdea9aa-1deb-586d-acd4-810c47334980 | note | Category - SP
3157574f-6976-58f3-baa1-741f2ed0e4b7 | note | Responsibility - SE
3676a40b-bede-529d-ad5a-6419a4d0feb7 | note | Verifying Documents - This ITP
3e138ce1-82e1-54ad-ab4a-973136ada50b | date | Date Completed:
7250bd50-ff3c-4bc4-b148-e1c293f8c42c | checkpoint | 5.10 - Backfilling with cement stabilised sand
dec7629c-5bf8-5d75-8d37-6765ff9649b5 | note | Reference - VR 701.19 ( c)
3a714e0d-3584-5d9c-89fc-b378215f63dc | note | Acceptance Criteria - Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height
d74202c6-67fa-517d-ae7a-9d31618fcef1 | note | Method - Visual
ce48f20e-b58a-5e91-babc-bae64484de8b | note | Frequency - Each Lot
2bc1abef-31d8-5609-8ac1-8f8e19baa091 | note | Category - SP
6b61bd03-a870-5b70-9095-42404afcc4e7 | note | Responsibility - SE
5ed50200-2dd9-5fc0-921e-5a943eeebe36 | note | Verifying Documents - This ITP
329c3cd9-77f9-5135-b44d-4d87c74f5cd6 | date | Date Completed:
bc1bd617-ffcc-4c0f-8f2d-6792d0f3738a | checkpoint | 5.11 - Backfill Placement
9170d461-7fd4-59d1-a6da-36f1429a059e | note | Reference - VR 701.20
1ebfce14-8f58-5d10-9bf7-e008aa32daec | note | Acceptance Criteria - backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
b1626f32-b2f3-5dd4-91f0-d04776d13f81 | note | Method - Visual
c472c82b-912f-575a-b344-2e9bfe7ca192 | note | Frequency - Each Lot
130dd6e6-6a73-5d30-9338-61e664634476 | note | Category - SP
1529228b-ec9f-51fa-86d2-564561969f8a | note | Responsibility - SE
fa2dc0d6-875d-5aba-a6ba-c810f35a8f08 | note | Verifying Documents - This ITP
8064a6b4-04a2-534e-9528-50485b4c72eb | date | Date Completed:
d2c1a55f-12ad-4201-b971-b0caf036818d | checkpoint | 5.12 - Backfill Compaction
0e7c26fe-f2c2-5459-9258-7d43400ecc69 | note | Reference - VR 701 (b)
7883c1ee-472c-58de-921e-4ec719734692 | note | Acceptance Criteria - 20% of all bedding/Backfill layers for each culvert shall be tested.
d2818229-cb6b-5101-ae03-37ad61149917 | note | ○ Backfill material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%.
53131a29-0182-5fd0-877a-eb9f544ca5d2 | note | ○ Backfill material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
4cfd464c-f187-540d-b919-35f642a648f3 | note | Method - Test
450db28a-6769-57fa-a049-8a47b13af5d8 | note | Frequency - Each Lot
ab8cff5c-9d5c-5018-937e-a4d97a6e5ab8 | note | Category - HP*
f8e5bfff-ef14-59ba-b9b3-0841b27478a3 | note | Responsibility - PE
37d2f600-c7bd-5785-b35d-dc40b68dc200 | note | Verifying Documents - This ITP
a1da2fa5-0088-51fc-bc5b-0599cd31a8fa | date | Date Completed:
023347ee-1ecb-4029-9072-0e7ecfa57022 | section | 6. Post-construction Activities
b13a6cde-bc21-459f-af0e-658fda48ea70 | checkpoint | 6.1 - Compaction and Moisture content tests
1421c97c-fe12-57ba-931b-2837df93d5ed | note | Reference - VR 701.20
ff940d5d-2d3f-5d2c-a843-2398cce3b335 | note | Acceptance Criteria - Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
be00742e-f910-5639-87bf-c2d6afb7c191 | note | ○ ATTACH: Compaction and Moisture content test results:
7578f4aa-3aee-514a-aec2-c15a686ba94d | note | Method - Document Review
09363cf1-8282-56c5-a0d0-26345f8daeef | note | Frequency - Each Lot
103c2eaf-ba48-5df4-9db6-a3edf6ce86e7 | note | Category - IP
a3f4a6bd-cebd-57c3-a530-e25e3a953b02 | note | Responsibility - SE/PE
a029adfc-d4d0-5af0-a792-a52decd4ec64 | note | Verifying Documents - Test Results
8e582fdd-cada-5c03-9ac1-045d6b3c1292 | date | Date Completed:
c4dd4a03-4301-4cf2-85f0-cde587ddad74 | checkpoint | Final Inspection
892e34bd-b18f-564d-9174-92fbdd43c938 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
20c6922a-7be9-58dd-b5b5-7f9bcdfd9f8d | textbox | Name:
2b117e3a-691d-5669-babf-0117ea2d3134 | textbox | Position:
8ba35996-c000-5d26-a1a1-f3d1005220a8 | textbox | Date Completed:
1fb47246-4b81-41bc-aeff-d3f29fc993f1 | signoff | Sign ITP
bf855fe1-bf32-4f80-9b59-4e58400b17f6 | checklist | ITP-239-CIV-HOP-Stormwater Drainage Pits Supply and Installation Rev1 | itp | ITP-239-CIV-HOP-Stormwater Drainage Pits Supply and Installation | 54174cbb-3d45-41f7-9b4d-935518ea9d4a
6fcbcb67-b7ef-4898-9677-67cfbcefcda4 | section | 1. Referenced Documentation
bb52b62f-b2a0-4f38-b9c0-0998c202b24c | checkpoint-no-value | Referenced Documentation
aa67d2e6-5dfa-5eff-aa0b-a63649668f96 | note | Document Title: ITP-239-CIV-HOP-Stormwater Drainage Pits Supply and Installation
66463ba3-f255-5442-81b9-58e6bba5f651 | note | ITP Description: HOP-Stormwater Drainage Pits Supply and Installation
7e2b2878-5327-5866-b911-a537be5f392c | note | Discipline (e.g. CIV/STR/RAIL): 239-CIV
86c29202-ce47-59b0-8714-3dc66a4cfb2b | note | Revision Number: 1
22388ce3-201a-5a7f-8c4e-243322c53b57 | note | Revision Date: 8/01/2025
9c4a0cc8-cc2b-5e3f-96fd-cebc40ad72fd | note | ITP created by: Cedric Guico
e676d0e4-7aa0-5cee-8c2b-0c39c055727c | note | ITP approved for use by: Pradeep Talasila
605f8b74-99b4-506c-9668-89e1615f34a5 | note | 1.01 - Non Dependent
d5763527-8add-5f41-b4d1-8355291e8f80 | note | Reference - VR 701
25e7f8cb-d1fd-41aa-8a00-28576974d747 | section | 2. Preliminaries - Materials
2a6a4eb5-6a8b-4129-8582-957df8dc1e84 | checkpoint | 2.3 - Precast Drainage Pit
53b3a19c-4e8f-5ef2-a133-9987b8531dc3 | note | Reference - Section 705.07, Section 705.04, Section 705.09
879ba425-39b8-53c8-9f61-ca8b1e49f70e | note | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
1f0c1aba-54e2-5b1d-a81d-0f43412d5639 | note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
0d1ed05a-5951-56b0-94b6-488296e4b535 | textbox | Enter: Teambinder Material Approval number
0469352b-5d7f-5a4b-8155-e9a23444d951 | note | Method - Document Review
0051805f-cb8c-53d0-9c17-5076d3b80e3d | note | Frequency - Each lot
c4447409-f744-5f00-b9a4-b3a5a4f54a5b | note | Category - HP
dd5bb9a4-9a9f-5f48-90a0-552e7be36ce9 | note | Responsibility - Nominated Authority
0e0f6e8b-e4f1-5fe1-888c-c75fb765c15b | note | Verifying Documents - Teambinder Material Approval
547e45e6-9573-5735-a749-a08b5cbc0abb | date | Date Completed:
3ea9c658-5ccf-43b5-a23c-dde25143fd63 | signoff | AUTHORITY HOLDPOINT
9e55d292-f3ba-47d0-a76d-114a89f47e55 | checkpoint | 2.4 - Cast in Place Drainage Pit
0ca49446-45e6-5130-ba24-fe5e7880fb4c | note | Reference - Section 705.06 IFC Drawings
8f8fe98f-5e18-58d7-9934-9ec5a44a5686 | note | Acceptance Criteria - Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
8ee2b3c4-9098-56a9-8c88-e08d894baceb | note | Method - Document Review
cbb77c8f-d0b1-505e-93ea-da5686feef35 | note | Frequency - Each lot
658373a4-6037-5cf3-b1e2-47adca6268f3 | note | Category - HP
cd7604b9-1ede-5b51-85db-e1e7c49da860 | note | Responsibility - Nominated Authority
f03dee27-03a2-5144-ba4c-da45c2824aff | note | Verifying Documents - Teambinder Material Approval
acb8f31e-5183-5367-a3dc-861e2828d27a | date | Date Completed:
3493d709-6876-4c1a-b8f6-8321884eb257 | signoff | AUTHORITY HOLDPOINT
26bf49ef-7549-4e44-9eae-bddd333f4e04 | checkpoint | 2.5 - Drainage Pit - Step Irons
5badb552-fbff-5151-a6ad-2cef630a64ea | note | Reference - Section 705.04, Section 705.12
5c53c55f-95a8-5054-8171-53c08555785b | note | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
e27405fb-1d35-53e7-87ce-dab9cfda54bb | note | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
59c1fc62-41bd-5b34-a07e-637197a716d1 | textbox | Enter: Teambinder Material Approval number
7dd002bf-1e39-5f59-8a76-862045230572 | note | Method - Document Review
a4edc6bd-bfb2-5aee-b310-62f397857af8 | note | Frequency - Each lot
32076261-7b14-51ce-9b47-45110e22a8ec | note | Category - HP
29c6991a-b53a-50d9-96d8-5e6968345e32 | note | Responsibility - Nominated Authority
e4b79122-ad92-55f1-b8bb-bda7fe021d5c | note | Verifying Documents - Teambinder Material Approval
225517eb-1f27-504f-bc87-1c3d021b1672 | date | Date Completed:
7e4257a2-5eb1-4ce0-aa6a-d69ab6f2386d | signoff | AUTHORITY HOLDPOINT
a9b58867-09ef-4081-b775-1a532a0c03f7 | section | 3. Preliminaries - Procedures & Documentation
b6a68536-5f93-4ff0-8c0b-b51f0b64d0f9 | checkpoint | 3.1 - Subcontractor QA Submissions and ITP
bee1cb47-c6a1-5191-9307-908981b1a207 | note | Reference - VR 701
bef77dae-78ec-52e6-95f4-aa90954edbdf | note | Acceptance Criteria - Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
edb51d2a-c485-5fd1-96a9-a323b686020c | note | ○ ATTACH: Subcontractor Signed ITP
2cc8c7c8-a012-5442-b900-13d330c29ad6 | note | Method - Document Review
19200deb-7f97-54de-8a91-cc6a8bdba2ce | note | Frequency - Each Lot (in case undertaken by subcontractor)
abd20c05-e23f-5f0c-9472-2701b04f4e0b | note | Category - HP*
6310310e-1585-5090-b25e-0234fa05e03e | note | Responsibility - SE
78635f93-fa22-541a-9cf3-edf122830e55 | note | Verifying Documents - ConQA Hold Point Release
e22c442a-b8c2-5498-836c-91886c064b4e | date | Date Completed:
e3fa674a-2e7f-42b7-9ad0-ff69e1aeb115 | section | 5. Construction Activities
61760f9c-87bc-4467-9d77-f8ca45483a78 | checkpoint | 3.1 - Survey Set Out
65e66aff-8733-5a02-bc76-f13f6091c6ae | note | Reference - VR 701.10
9be6e42a-ceab-5bf6-a2aa-ff62c56e212e | note | Acceptance Criteria - Survey activities undertaken to ensure and validate the plan location, height and line of pits in accordance with design documentation and 701.10
dc08edba-6fac-5d53-9ae7-6ad0c3081982 | note | Method - Visual inspection
545c998d-ecd4-52bb-97ee-53cfcc64f00c | note | Frequency - Each Lot
ab99f76c-b404-58c4-8d6c-60ef0ed967ac | note | Category - HP*
c0d7ea31-ff08-53a7-bb24-737b7a0a97e0 | note | Responsibility - SE
66eb16f6-b2b4-5cdd-a21e-41dc24e692bc | note | Verifying Documents - This ITP
6b9fe3d1-f23c-5932-a3d9-280c23b4ef02 | date | Date Completed:
b1bf8023-4c35-436c-85ce-171e960e3dab | checkpoint | 3.2 - Pit Excavation
d797a3f7-038e-56f9-a03c-fdb821b548e9 | note | Reference - VR 705.05
35b0e0b0-df67-5191-9043-865296a05f03 | note | Acceptance Criteria - Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
8a9235ff-8a7b-57b1-bc8c-2dccc4a278dc | note | Method - Visual inspection
f64c5768-3190-5ee4-bf82-0bcb1e4b136f | note | Frequency - Each Lot
f76f6950-3ad2-54d0-a468-19c984f6b246 | note | Category - IP
0abbdc9b-c0ad-5cf7-8b75-087c9d0333cf | note | Responsibility - SE
4eee9d09-4ed7-5bfa-8402-526de3e0a116 | note | Verifying Documents - This ITP
13a03b8b-ac76-564c-bde9-4496212d7c7d | date | Date Completed:
5eca2d19-8981-4995-8a12-7779a8407ce8 | checkpoint | 3.3 - Excavation Foundation
2dcc600d-bdc2-5cb7-9ea2-038080ebc2af | note | Reference - VR 705.05
1a64c33b-1895-5631-980c-327fcd8b7ddd | note | Acceptance Criteria - Bedding conforming to to 710.09 shallbe supplied, placed and compacted to a thickness:
d640a8e6-897d-5299-9fde-d878eecdb2af | note | ○ > 80mm for clay foundations
ddc8488c-8e2d-54ff-82cd-01f79628f037 | note | ○ > 150mm for rock foundations
6196ec2b-9ab9-53b8-b887-00f0fb742535 | note | Method - Visual inspection
f98b3ffc-433c-5eb8-bbbc-ac8a36cbd94c | note | Frequency - Each Lot
6e2ca064-bc6e-5cc5-a3d2-40deb9c1f422 | note | Category - IP
2bf2b825-9df2-5942-9b82-307e511d09af | note | Responsibility - SE
7e8872c8-f9d1-5f74-b3dd-4db5e277995f | note | Verifying Documents - This ITP
b082d68e-3329-575e-b04a-f7f31b4e8e86 | date | Date Completed:
45c96417-7b0d-4e4a-8f72-d2770c21b76c | checkpoint | 3.4 - Jointing
96828e10-e550-5962-b1bc-caa8237003f7 | note | Reference - VR 705.11
96b4eec0-48de-598e-82ec-a0f306c47972 | note | Acceptance Criteria - All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
192782c7-fbaa-584f-b94d-0a76c2c620c7 | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment
93df69d9-2124-5326-9a8a-eb470cd38bb5 | note | Method - Visual inspection
531b5fc4-1312-5a7d-acaf-b8e91e72ea1e | note | Frequency - Each Lot
8e7085d7-5156-571d-8aca-8f0c36e71394 | note | Category - IP
2aaf69a7-81d0-52af-8092-4b79e168b7ba | note | Responsibility - SE
b11ce707-b26b-58fb-9dbf-f273b880e99e | note | Verifying Documents - This ITP
d1ac3b7f-44dc-58dc-84ae-01f30d695bd9 | date | Date Completed:
60d1a8bb-151d-493e-8597-59b5ac5aa935 | checkpoint | 3.5 - Shaping of Floor
c3c217d3-3de3-5210-8333-685dfbb59748 | note | Reference - VR 705.13
d70987bc-fd5f-5777-83e0-83907674b455 | note | Acceptance Criteria - Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
da91d253-e9fd-5320-96b7-0db2aeb0eb4b | note | Method - Visual inspection
59bddce2-90f0-53c5-8f90-bc94e859a220 | note | Frequency - Each Lot
02edaa0f-cdbb-56cb-8c73-52709902fd02 | note | Category - IP
92e4ad2e-80d4-5574-895f-798397e38af3 | note | Responsibility - SE
e30ec31c-2186-52b6-bec4-283c6fd6e51d | note | Verifying Documents - This ITP
16946530-1aca-57c7-85bf-6b6e9525773d | date | Date Completed:
01a2cf2d-2da2-41c9-bd54-48ecfc53eabe | checkpoint | 3.6 - Step Irons
202b3674-cffa-5fab-bfae-cb7922f2ce1b | note | Reference - VR 705.12
bbfee364-3bed-574e-80f8-cfd56b47e193 | note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with AS 1657. Ladder rungs shall not obstruct openings and that water does not discharge on them.
7877a0d3-a795-59c7-8d8c-aed8d16ad79f | note | Method - Visual inspection
1e4fde2d-446d-5cba-b740-d5e6bb82431a | note | Frequency - Each Lot
ac265a85-ed3c-5bc5-8fba-f37ee7cd1f97 | note | Category - IP
c5da32cb-9bb4-5852-958b-28ab7067a175 | note | Responsibility - SE
a6e0aeaa-32c0-5e6f-af6e-e8293433d24d | note | Verifying Documents - This ITP
96fb6310-b34d-5389-bfa1-d33682b9d794 | date | Date Completed:
2d9b5dd5-cc3e-488f-88fa-9e42aed6a266 | checkpoint | 3.7 - Fitting of Covers
a62010e1-88b1-59a2-8e1c-473861af8509 | note | Reference - VR 705.17
982407f7-f240-5af9-9e7f-25f5095419f2 | note | Acceptance Criteria - Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
3c813d90-f608-5e11-953d-4d2d61b14a96 | note | ○ Height shall be within 10mm of the design level
8ff972ed-db21-5928-beba-8ffcbb36662f | note | Method - Visual inspection
99a0a625-8f95-53c2-81f6-6b6f8ee76c58 | note | Frequency - Each Lot
fabc037e-9741-5f9b-a65a-b8723ab5f6c4 | note | Category - IP
08c13c3c-7c21-5ddd-9f93-43d9accd2ec4 | note | Responsibility - SE
e20b5b13-abd5-50fb-a46e-38d04d6135e0 | note | Verifying Documents - This ITP
aa21cb47-54c0-5617-8fd8-9dbc942a5db2 | date | Date Completed:
0140a7b8-c722-4cff-a187-90ea0218316e | checkpoint | 3.8 - Backfilling Around Drainage Pits
ae2d14c6-5f3e-5706-aa0f-5b28e747d81b | note | Reference - VR 705.18
17d0cb03-e5f2-54f8-97a9-b9b728bc6f46 | note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal
10ea603c-cadd-5fcd-99c0-4ae274bc973f | note | Method - Visual inspection
5aaf4e97-3d33-596a-8a99-f19c50a132c0 | note | Frequency - Each Lot
3a6e158b-ca46-5f6a-b79c-633ee1a9d583 | note | Category - IP
735dfda3-d10a-5427-8459-f5f421d2022a | note | Responsibility - SE
906cca5f-b1e8-5b94-aade-99f30c34ccab | note | Verifying Documents - This ITP
8d0a986f-fc09-5dae-aac5-5febad09fef0 | date | Date Completed:
b517ec68-6909-4aaf-bfbd-cbc615f3e78b | section | 6. Post-construction Activities
455949ca-e1c7-4d71-aaf4-258d51c1929e | checkpoint | 6.1 - Placement of Pit-Conformity with drawings
5e7f1874-c2e9-5966-b3e6-c4d17690c672 | note | Reference - VR 701.10
9c2d814b-114a-5cca-a2d8-20fa3996d6f7 | note | Acceptance Criteria - The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
a042e894-9a8a-5c4f-9488-eb0440121bba | note | ○ Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
dde612f0-1818-58f8-a046-e1d4d9073170 | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
fa446548-0b9f-5249-aa9e-761d33ee2a6c | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
0db6270c-f5fb-5fc2-b858-a4227085df1e | note | (c) invert level of pipes at pits ±50 mm
4334e931-2b3b-5e37-a53c-fa5e949ab50d | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
392417a8-32d0-5d09-9601-02f89f97c96d | note | ○ ATTACH: Survey Report
f4c9ed41-a7d8-5133-9ab7-5d98e9296a8f | note | Method - Measure
09c86717-6f79-5ebf-88f9-659f33627632 | note | Frequency - Each Lot
d333f620-5f2b-5554-a33a-011cfcb4e509 | note | Category - HP*
6809e522-7bf0-5c3a-bcd6-207f8639658d | note | Responsibility - SE
5be5469f-3511-5133-b93a-53973e6e69fe | note | Verifying Documents - Survey Report
7f03f872-75ed-5c93-bbb5-e58b7f4ae522 | date | Date Completed:
34defb91-1494-4ed1-962d-af4bf1513ddd | checkpoint | 6.2 - CCTV Inspection
9854ca03-e2a7-5f5c-88e7-28869e7f1845 | note | Reference - VR 701.30
338bf069-78b3-504e-a202-4646d561aef6 | note | Acceptance Criteria - All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
64c92349-110e-593e-8713-e43f7e957359 | note | ○ ATTACH: CCTV Report (PDF):
41a1318f-64d6-5aca-9e1b-d2e7257914b1 | note | Method - Document Review
f2b50307-bb66-55dc-a97a-a1e0c1e91680 | note | Frequency - Each Lot
866ff064-6448-5e8c-8d87-1c38c8848cf0 | note | Category - HP
b0c812d3-7bfb-5fd2-afe5-cede9d1d4781 | note | Responsibility - Nominated Authority
289ad981-f6f7-599a-9c44-a58509a46764 | note | Verifying Documents - CCTV Reports
6352c312-3947-54d5-95c6-350b00c46d34 | date | Date Completed:
ede8cb41-4a29-4664-bd16-eeadf33f0361 | signoff | AUTHORITY HOLDPOINT
f6559e2b-f1b3-4973-932b-c052d938e743 | checkpoint | Final Inspection
7e945759-7eb7-5b3b-b209-9e13882b2937 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
8d9a6986-6290-5569-8100-e35670cbd139 | textbox | Name:
70c57463-981d-510d-ae79-09221f4ef6fb | textbox | Position:
c9c31fab-1dda-54d0-9c34-f0673217fc08 | textbox | Date Completed:
3f9f1aee-3129-4517-9d85-7862a18c4401 | signoff | Sign ITP
b6e180a5-9266-4c55-8022-6b5f39691430 | checklist | ITP-241-STR-HOP-Structural Concrete Rev 0 | itp | ITP-241-STR-HOP-Structural Concrete | 9f8d924c-92e4-4110-9c96-9f18d64b3876
d6dc801e-1111-4ed3-8339-7d19d467f78c | section | 1. Referenced Documentation
080ca0b2-757e-4959-aa7a-209abd0a9ce2 | checkpoint-no-value | Referenced Documentation
9384eafc-5b6f-5792-a07d-3481a3c09f76 | note | Document Title: ITP-241-STR-HOP-Structural Concrete
fb68559c-69d9-547c-aaa2-439b07402fd1 | note | ITP Description: HOP-Structural Concrete
6268d1b8-6528-5ca4-a505-be356608ba21 | note | Discipline (e.g. CIV/STR/RAIL): 241-STR
9218c51d-0c5f-52e3-8e13-ee52f85a4bbe | note | Revision Number: 0
aa64b55f-0dff-5064-bb3d-13a3930235cb | note | Revision Date: 19/02/2025
e4c06645-a3df-5aec-870a-b4dc6d10c846 | note | ITP created by: RM
63006118-b727-564f-8ce9-ab3f63d2d8ff | note | ITP approved for use by: RM
9a611d2c-2c77-55fa-bc5d-538d0a23bb8c | note | 1.1 - Non Dependent
db99dba5-336f-5319-b5a6-4af91490b34b | note | Reference - VicRoads Section 602 October 2007
f984b851-3cd6-5eb1-ae0b-beb116ced78c | note | 1.2 - Non Dependent
cef92b00-43d2-54c6-a41b-bab313311c85 | note | Reference - VicRoads Section 610 February 2020
6a4b4586-9361-5c55-b53e-d13d68fccb1c | note | 1.3 - Non Dependent
cab740d6-b000-56a1-a6da-7178a2f39d7b | note | Reference - VicRoads Section 611 November 2018
76adc801-b860-50d9-8e1e-d40466e73770 | note | 1.4 - Non Dependent
ae03a025-fa90-54c5-a1d0-e83d61a8bf83 | note | Reference - VicRoads Section 614 June 2017
8d0cce23-5c0e-5718-867b-e922efe76a19 | note | 1.5 - Non Dependent
f17b81d0-0040-5d43-bc9c-31895f3269db | note | Reference - AS3810.1 2018
48d8f177-67c3-47fd-b13b-ece035fd4481 | section | 2. Preliminaries - Materials
51db0fc7-df80-4398-a056-f9e8cfc25e9e | checkpoint | 2.1 - Concrete Mix
b84e390e-9c06-5aa6-8b19-e11dbbce5815 | note | Reference - 610.07, Table 610.071 IFC Drawings
0b314a37-76d8-5b13-bf7f-b7967773486d | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
0938845d-213e-5345-89e1-90917d2ecde5 | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
e591d0f3-fc08-591d-b940-feed46af0420 | textbox | Enter: Teambinder Material Approval number
cd699eb6-1f32-5ff2-a9ce-6e11ac9423d8 | note | Method - Document Review
6b4e7e12-f0d2-5a5d-8d96-0b6d1970a583 | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
45a34f10-1777-5137-93de-0f537b3d22ff | note | Category - HP
4d10cd05-3c41-5b95-b9e6-b01533993e26 | note | Responsibility - Nominated Authority
dcb03e18-f543-5d5f-bb39-48cdc2d17c7c | note | Verifying Documents - ConQA Hold Point Release
a687ff9d-8d11-59e4-a741-3609a7fcc4e7 | date | Date Completed:
8b86b78e-db71-49eb-8b94-80b61b21e5b4 | signoff | AUTHORITY HOLDPOINT
472e34c6-c194-4b43-8650-09186712f7be | checkpoint | 2.2 - ACRS Certification (for Reinforcement)
3f763e68-4502-58ab-86a4-fd0fba0a9277 | note | Reference - 611.05 (a)
4d759f1d-e669-59f9-8983-dc60134c9e16 | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
4fdc0c5d-4d18-5750-84a7-b73904185119 | note | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
ffcc8cfb-c99d-5965-84b5-86f84edb80e8 | textbox | Enter: Teambinder Material Approval number
6a542af4-47f0-5841-b890-cd9f725a5107 | note | Method - Document Review
4f5727ad-ad0a-588e-9ec2-3c591efeb5f7 | note | Frequency - Once for each supplier, 14 days of award of contract
c680f6da-084c-5080-9c07-a831114a3ab6 | note | Category - HP
39705e66-14f4-5890-9fd3-4f9c781b1e95 | note | Responsibility - Nominated Authority
4691c93d-dc58-501d-a0dd-5d9675131c57 | note | Verifying Documents - This ITP
e87c53a2-9000-5412-a600-32478add8175 | date | Date Completed:
3b09cc7f-6571-44b5-b3b8-d3dc8a97eee4 | signoff | AUTHORITY HOLDPOINT
b0232f79-cef1-4368-b6ca-2a65403d3a89 | checkpoint | 2.3 - Bar Chairs/Aspros Certification
a453b7d8-7111-5fd7-a9e6-252c148ab0c6 | note | Reference - 610.26 (a)
f465adc2-8917-5ef0-a10f-abdfe8d16f6a | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
9edba838-19a2-52ee-a84a-b07989a6bc85 | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
d877253f-f2c7-5fda-9c19-9a902d4d4f99 | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
fee7138e-87d6-5b5b-a4e9-61f5a1d8eebf | textbox | Enter: Teambinder Material Approval number
c774220f-47ee-5efd-ba0c-76b9cb997b9c | note | Method - Document Review
791cb6e0-6f23-5b9e-befa-7e5307ee1e70 | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
d7940c2e-e697-5ded-970f-493efbff11a6 | note | Category - HP
6264005b-21ac-5e94-928b-80399cebffec | note | Responsibility - Nominated Authority
0f8fa035-a5e6-5981-9310-aa50f5a19230 | note | Verifying Documents - This ITP
b14a3989-307f-57a2-846b-87e0cc1e0b86 | date | Date Completed:
7b49abc3-7645-44b7-a53a-db5cf320f9b7 | signoff | AUTHORITY HOLDPOINT
ab6d32e9-73e5-4ddf-bd77-1c37913c00d5 | checkpoint | 2.4 - Evaporative Retardant
ccf9351a-c6ef-5788-a3f5-db997ed86778 | note | Reference - 610.17 (f)
b80459ea-3487-5d96-9e0e-f5fb62a55d86 | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
f3120eef-df71-5e96-bc79-6e05128a025f | textbox | Enter: Teambinder Material Approval number
626b4b27-ce68-585d-acce-0d4c5aedc1bf | note | Method - Document Review
0189c806-a435-58d4-847d-75a353293098 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
0befe346-c173-55a6-ab87-be4586d472ea | note | Category - HP
9d3f5204-487a-50f7-ad62-b37954f226ec | note | Responsibility - Nominated Authority
96ce78fa-079f-566b-92b0-3ea635a245f2 | note | Verifying Documents - This ITP
230bf723-c0ca-597b-ba14-65d8bc9acc6b | date | Date Completed:
88901a8e-e258-4c30-a890-9053a136eee6 | signoff | AUTHORITY HOLDPOINT
7c70a188-731c-41dc-9ed0-8560c2f0c9e3 | checkpoint | 2.5 - Curing Compound
ecb05866-39fb-5cf9-91c3-a4ab47c24607 | note | Reference - 610.23 (d)
5d1b6870-14a1-593f-bd70-7b800040a5b3 | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
eacafac8-4960-526e-a606-5ba076749d1a | textbox | Enter: Teambinder Material Approval number
8a74b1e5-39a3-5cc1-9b2a-798b456ef90e | note | Method - Document Review
1d3b2cc0-692d-51b5-b65d-4e8d3b8e8a1a | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
64b7fd31-57df-5d73-8adb-92c747e6a877 | note | Category - HP
b219e88a-6ab8-56d8-849e-f835530fdd67 | note | Responsibility - Nominated Authority
2a011e1f-3312-50f0-bd62-7b36ceb78dd5 | note | Verifying Documents - This ITP
62651c54-33bf-5fb5-948b-db4360d45e28 | date | Date Completed:
84da6356-220c-4be2-9c7d-0c4ec993598c | signoff | AUTHORITY HOLDPOINT
3a9c82c4-b877-4095-9531-d9991a988943 | section | 3. Preliminaries - Procedures & Documentation
36bfdbeb-8826-40f1-9258-878218ba5738 | checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
1f6f8214-b8bd-5ed2-8836-bf6bf5b905eb | note | Reference - 610.18 (a) (i)
986174a1-49d7-50fc-ba6e-683ae1a9cbb3 | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
45ad12ab-6575-592b-a4fc-aa9a28625dbb | textbox | Enter: Teambinder Approval number
6aee0b83-e2b0-5c9c-97f6-ab18a6034161 | note | Method - Document Review
6d4546a0-1c8b-5742-ae36-0bfbbe845d93 | note | Frequency - Once, 4 weeks prior to placement of concrete
f248ff85-52a1-5d98-a9e0-c8ce35086bdb | note | Category - HP
5d0ec1f2-7f40-5db4-b045-be643cb545df | note | Responsibility - Nominated Authority
539d5578-fc13-5310-8aaf-0ad48dcd2ed4 | note | Verifying Documents - ConQA Hold Point Release
105e77e1-496a-59cd-bb3c-da07a3eef028 | date | Date Completed:
cd1ec2a7-6944-4773-99bc-0cf052640e21 | signoff | AUTHORITY HOLDPOINT
e4a285c2-5025-4938-a9df-98cf36df8a3e | checkpoint | 3.2 - Concrete Sampling and Testing Procedure
95f24b99-7ae2-5626-9fe3-c9b088bc8db1 | note | Reference - 610.18 (a) (v)
d9a2e1be-358c-5961-bb1c-e5d3959feae7 | note | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
9ffe652d-caed-537d-9828-de7842aa87e7 | textbox | Enter: Teambinder Approval number
686cc549-16cb-5140-8f0a-d1b3aefb1481 | note | Method - Document Review
51b2dcd3-0238-5208-8c26-e4488a5c2501 | note | Frequency - Once, 4 weeks prior to placement of concrete
44819d8a-2d5a-55b4-85ef-aba8038f743f | note | Category - HP
d19860e3-9d5c-545c-b23b-26f95ce8bf29 | note | Responsibility - Nominated Authority
d32e96b6-6654-5a58-a3f0-e9400030a9a9 | note | Verifying Documents - ConQA Hold Point Release
23235737-6e49-5ba5-8519-ee89df4a1070 | date | Date Completed:
22587d95-a677-4503-8ed8-2af0824afc16 | signoff | AUTHORITY HOLDPOINT
889c0ae4-eaed-4f52-bc07-ed27acb068c9 | checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
a4472035-6665-529d-b26d-d2274f393ea9 | note | Reference - 610.18 (a) (iv)
01fa4419-13de-5476-a37e-4098b6240a0e | note | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
31bb2508-293f-5bb7-b5d5-45b78e652003 | note | Minutes of this meeting to be submitted to the Nominated Authority.
c1072fee-502f-5f37-945b-4c0560b70862 | textbox | Enter: Teambinder Approval number
e98a5263-4139-5994-9036-36dcb85fe559 | note | Method - Document Review
85ae6272-899b-564b-bd7c-94e8c5e3e64a | note | Frequency - Once, 4 weeks prior to placement of concrete
cea3299b-46d1-568d-8e56-9ec39eaf4cc0 | note | Category - HP
d320f1b2-d9c6-53f8-877c-03d7db831760 | note | Responsibility - Nominated Authority
8c1c9f7f-f9a7-5a8f-8990-a935fa2aa549 | note | Verifying Documents - ConQA Hold Point Release
26025dca-cdfe-5b48-90dc-8cad6954e4c8 | date | Date Completed:
f651b274-4802-474b-a3a1-ef5d1ead3cd7 | signoff | AUTHORITY HOLDPOINT
0d8ea7ef-8271-4463-a1b5-45b50086a65c | checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
e7b4faf4-a7c0-51b7-9d0c-67140528daf9 | note | Reference - 610.17 (a)
366dd33c-513b-5529-8f5b-ba341b257c36 | note | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
ff85aef1-7af5-5cfe-aec7-80ef9967498c | textbox | Enter: Teambinder Approval number
eb7fb31d-268f-5057-92d5-49ae0735740d | note | Method - Document Review
b5bf2a9b-8af6-5a6c-b7a9-1350313c5e3f | note | Frequency - Once, 2 weeks prior to placement of concrete
049b97cd-72c6-570e-81ef-7346e35e5276 | note | Category - HP
e78ac9b8-28e1-5193-bd02-5797d5eeb67a | note | Responsibility - Nominated Authority
4f1807a6-0ea1-5d16-a2cc-c126bbd548fa | note | Verifying Documents - This ITP
a84a1a6f-ae04-59b9-ab29-e36783af3995 | date | Date Completed:
c944da93-4d80-4347-b677-e89a8b4ff74b | signoff | AUTHORITY HOLDPOINT
f4d375a0-68dc-4bdd-81dd-b3016929b0fd | checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
9218c1d4-24f7-5eaa-b068-ee4127a38686 | note | Reference - 610.23 (a)
075c3a17-2699-5941-bb43-c14984f9abe2 | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority.
249e45dd-cf7a-5c4e-99fe-3cf49cd0bda9 | textbox | Enter: Teambinder Approval number
01e0c0c9-d613-5a9d-95ce-856743eed16c | note | Method - Document Review
53e2f6e9-f865-5d70-8d9d-4d5f60efa7d7 | note | Frequency - Once, 4 weeks prior to placement of concrete
70cf7b0b-75f4-5f85-a509-1ed98dd6304e | note | Category - HP
9e549a99-9a23-5341-b8c4-e4567b72a068 | note | Responsibility - Nominated Authority
9d659524-18f4-53c7-aa06-3d3922f878e4 | note | Verifying Documents - ConQA Hold Point Release
77ed285a-e3f8-5df0-8b37-0fd31807c961 | date | Date Completed:
0604923a-f65f-4b46-b4ca-3ea07f6bfe6e | signoff | AUTHORITY HOLDPOINT
f572c0da-e469-4f84-87a1-7b906523b10c | checkpoint | 3.6 - Concrete Drilling Procedure
97f2c7be-42d5-58ea-a505-99b74e3e5aa8 | note | Reference - 610.46
65508083-6eee-538f-a22d-ca50e915c354 | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
8805be0c-401c-50a3-8fc9-7d7d452cd0a7 | note | The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
e9771487-635c-5e1b-8871-62568c65be1f | textbox | Enter: Teambinder Approval number
4b278353-ee6c-5077-8bcd-3a4816560dc2 | note | Method - Document Review
d5e0619a-0cec-5535-80e1-79423c49551c | note | Frequency - Where applicable, once, 2 days prior to drilling
d1ca66c2-99eb-58b3-a177-1dcfd6ef6942 | note | Category - HP
461a4d0a-cc7a-5a60-8023-edb5646012c6 | note | Responsibility - Nominated Authority
9258d0f0-380b-5e5b-ba79-c417006e427d | note | Verifying Documents - ConQA Hold Point Release
9e325cba-46b3-582a-ae6d-b927011f3e08 | date | Date Completed:
4e2ea18b-8cd7-4341-8ae4-88415d699ddb | signoff | AUTHORITY HOLDPOINT
e496c407-c3bc-41f9-8340-e0b45cfc70d7 | checkpoint | 3.7 - Temprature difference measuring-Calibration
b256d7f4-85a2-5ad3-9002-a887a5ec2923 | note | Reference - MRPA Quality Management Plan
564cc5a9-5c21-5dac-be56-f9ee4998b5b2 | note | Acceptance Criteria - Calibration records are valid and up to date.
cde8348b-7343-56ab-8371-2b2ecb34b991 | note | ○ Attach: Calibration certificate
a651425b-4eeb-551e-855f-f371bb3a154b | note | Method - Document review
2b072c73-82d5-5777-b8cc-77d1ba0cb0cf | note | Frequency - Where applicable
f28f9106-df31-5831-b58e-b383a7a270a1 | note | Category - HP*
bfc2121f-303d-5b6f-99b7-fd9acc0619c3 | note | Responsibility - PE
8eaf1171-7399-5a78-b5a5-f7c4e212fb54 | note | Verifying Documents - This ITP, Attached calibration certificate
b2d9fe12-b2b2-5052-8b73-5d4a968ef964 | date | Date Completed:
7c8f4ec1-ad53-42b3-a4a0-94133c825d69 | section | 4. Pre-construction Activities
ed055741-dfb9-457b-8108-bb081b1ca396 | checkpoint | 4.1 - IFC Drawings
a8b6e8e8-c0b2-5aaa-ac1b-2232ab164948 | note | Reference - MRPA Quality Management Plan
a50b8890-e7b3-5f20-8025-0554d98d3bf0 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
6c07767d-c257-5594-848f-01611f935bbf | note | Method - Document Review
4fb81e16-775f-5491-90b7-b2e0304e1402 | note | Frequency - Prior to starting Works and at regular intervals
b2ca6ee3-145a-5a4d-b025-bf70d20fbdc8 | note | Category - HP*
ccb6ea57-ea64-53ff-b256-227c1a0ec802 | note | Responsibility - All
d4c3ed02-dc8b-5e59-813c-809b7ea00992 | note | Verifying Documents - This ITP
1d84241c-858a-5408-9c51-3e87f2d1dcda | date | Date Completed:
8d321297-e9fa-4958-960a-20f5ca395be7 | checkpoint | 4.2 - Survey Set-out
2c1eb853-bb3c-5f92-93bf-6bb70296e9ad | note | Reference - IFC Drawings 610.47 (a), Table 610.472
3c79bba9-ef0e-5330-9cdd-6e81aaf57816 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
0aa43f16-f152-565c-b06f-ac1922fdd298 | note | ○ Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
8492155d-4116-588e-b82b-178bf3f6b23b | note | Method - Measure, Visual
6de9a34b-1e0f-52e2-acb8-c544b42e3e24 | note | Frequency - Each element
6c6cd2ab-059f-5eaf-8fdc-8035497bb0a4 | note | Category - IP
c20fb8b8-dac7-5f3d-a0a7-1cf87d73eca0 | note | Responsibility - Surveyor, SE/PE
c402044d-183a-5a59-a84d-dccdc9932fb9 | note | Verifying Documents - This ITP
2aa044a8-bae8-5253-986f-fcfae68dec65 | date | Date Completed:
8facca0e-dd93-4b4b-bae4-e52c26fa6890 | checkpoint | 4.3 - Excavation support
6b31b15e-e704-57c0-82aa-dd4ac951e995 | note | Reference - 602.02
e28f44aa-c181-5bd0-b7b9-a283ea654205 | note | Acceptance Criteria - For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
09b61344-a5df-5912-bb77-b4c0f780a23c | textbox | Enter: Teambinder Approval number
fb7ff226-2caf-5919-802f-84658f4c8ab2 | note | Method - Document Review
50f45b61-c345-5ac8-bc4b-a45a22124c48 | note | Frequency - Where applicable, not less than 10 business days prior to excavation
a95dabfa-a127-5f41-b3b8-48c7deee57e7 | note | Category - WP
06b2eb19-1d02-542e-a36f-d82dd355bf1e | note | Responsibility - SE/PE/SPE
3adec1b2-0419-5940-a11a-f7e3e51515e1 | note | Verifying Documents - ConQA Hold Point Release
2ed628cf-1cc0-5f08-8df8-6ba0c0cac7a8 | date | Date Completed:
59162592-9a67-4487-a134-c31696a95528 | checkpoint | 4.4 - Excavation Inspection
b1eb3fe4-e6bb-5b04-bf1a-1e9e3ef441b6 | note | Reference - 602.03
1a6b4302-4736-5b3e-8e8f-e563d00596e7 | note | Acceptance Criteria - Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
33289e22-8d82-527b-aa39-59f0f60400b6 | note | Method - Visual
d2eaaa4a-93c0-56eb-9d6f-b6ab5727e1e2 | note | Frequency - Where applicable, prior to placing blinding concrete
c9fc0e13-0d24-5380-879c-56a0a6c59a08 | note | Category - HP
637bb5c0-cc1e-5a70-bdee-3bfbc8117d92 | note | Responsibility - Nominated Authority
08c66cd4-8dfd-5370-83f4-98bc57daa43c | note | Verifying Documents - ConQA Hold Point Release
f4cc8db6-9d48-56af-af93-c4cdbb553012 | date | Date Completed:
f0e74fb8-4a6c-45c2-ac33-e94417ada085 | signoff | AUTHORITY HOLDPOINT
31328df6-14a7-455a-b6e9-821617f3aa63 | section | 5. Construction Activities
3347295b-248b-4e5c-b0f7-c04563149ddd | checkpoint | 5.1 - Formwork Design and Construction
0396415d-7923-5f5b-b42d-0c1ff105c04c | note | Reference - IFC Drawings
2b9da914-11da-5da0-9326-693f7c9b1143 | note | ○ 614.04
4e72fa21-cb1f-53d2-8201-dfc57eacb94e | note | ○ 614.05
777f0f9b-4d85-5356-9570-3e814229e220 | note | ○ 614.06
2daabb67-00b9-5d33-8e55-bbf8437a1ef3 | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
acc05b83-68f2-5e42-845a-768289129f39 | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
9569411d-fc41-57b3-b4d2-981d70b4a310 | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
30425007-7b62-5276-83d9-02d863d6b9c7 | note | Method - Document Review, Visual, Measure
718b39a3-5dbd-5dc8-85dc-2cd719893910 | note | Frequency - Each type of element
72771706-0133-5d4e-b879-169becbbefc7 | note | Category - IP
fc94a954-d774-5128-8832-35dc8b4cfeda | note | Responsibility - Temporary Works Designer, Proof Engineer, SE/PE/SPE
8d1be01a-8207-57ae-9d72-3ce7b9dfd441 | note | Verifying Documents - This ITP
e5de4b5c-209a-5374-bcd3-bbe09803c1ba | date | Date Completed:
161d2533-dd6e-45e5-9fad-eedcd6dfe87b | checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
52f0a9d8-f988-5f03-b25e-ca5119abbecd | note | Reference - 614.08
e7053771-51bc-5823-9385-f90b159726f3 | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
c303c618-1086-5d49-b0b2-ded3b9e17f1a | note | ○ Walls with heights greater than 2.0 metres
cfbe1cab-d140-58d6-ad8e-f9346d06c2db | note | ○ Any member for which self-compacting concrete is proposed.
3aa85b14-3682-51cd-b1ab-ddc1901b49c1 | note | ○ Attach: Attachment A
559311f0-45d3-55f0-8c13-058d972bf1e5 | note | ○ Attach: Attachment B
408eddb0-03bc-51d1-b0e9-8dd83278cc09 | note | Method - Document Review, Visual, Measure
59c77ea9-62a7-5d11-9b0e-9e24f4a34da1 | note | Frequency - Each element (where greater than 2m)
199a05e5-e22c-56cc-a0ef-b7913e41d396 | note | Category - HP
4db45c0b-e3f8-5a0d-9cec-c35ebdb4e7d8 | note | Responsibility - Temporary Works Designer, Proof Engineer
52bd3b72-5058-575f-be49-0fe9d30c6370 | note | Verifying Documents - ConQA Hold Point Release
9e4602b9-ca57-5992-88a3-b9d61a3cde04 | date | Date Completed:
03e35b50-0353-4058-9a10-5ab3b250cf11 | signoff | AUTHORITY HOLDPOINT
26963b8e-6271-4a4d-883c-24129da78d99 | checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
07951dbf-a129-5b01-b85d-f003ddcf234e | note | Reference - 614.08
ba1558be-a122-55a3-9eac-1c1836bf965e | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
68535d75-e7c4-5c1a-9643-50d228e63070 | note | ○ Walls with heights less than 2.0 metres
0f8189d9-0c41-5da7-839c-ca85624f52bf | note | ○ Attach: Attachment C
1169cd33-17e4-5dfb-aeed-74354bc7ebcb | note | Method - Document Review, Visual, Measure
6fc48f50-e10b-5a40-b5fc-e1ea348c9000 | note | Frequency - Each element (where 2m or less)
104aa1f2-988d-5d12-99c8-d66d429fcf32 | note | Category - HP
05c484e9-7d5b-52c5-bbc0-ef08b5abc467 | note | Responsibility - Temporary Works Designer, Proof Engineer
5512d2d5-49aa-584c-b19a-280f0025c866 | note | Verifying Documents - ConQA Hold Point Release
6eb8cbca-32e5-5271-8e87-15cfb767b70f | date | Date Completed:
688c2d12-6c5a-49f5-9157-4e562c3545d3 | signoff | AUTHORITY HOLDPOINT
b4e9bfca-0cf9-4446-928f-9e722e319e5c | checkpoint | 5.4 - Pre-pour Survey
52bf80f9-cbb9-57c1-950b-bb2438a736b7 | note | Reference - 610.47 (a), Table 610.472
d69dea2e-efb6-57b2-8496-8fa1008e5a84 | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
983f4413-2a2e-5879-baa1-04ce67b86cb6 | note | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
bbc2eaac-a772-54ad-b857-eb863a3025bd | note | Method - Measure, Visual
e54e988d-bf43-5935-aae1-2999b2e34d71 | note | Frequency - Each element
f0a29438-1170-5164-a27f-a5949d254d74 | note | Category - HP*
e19c16d4-d88a-5c8e-ab15-e00f119d0edc | note | Responsibility - Surveyor, SE/PE/SPE
e5173da7-c13b-5968-b8ef-5cead6f79366 | note | Verifying Documents - This ITP
a20aadcb-ee94-5697-94d9-90b9ce3cf892 | date | Date Completed:
f83f4158-1819-402f-b447-e9953bc005ca | checkpoint | 5.5 - Reinforcement Placement
8ad4af78-6eb5-5b60-99ae-e89ea0550b13 | note | Reference - IFC Drawings
95c39037-5088-5432-bdd1-401979d487d5 | note | ○ 611.06
dffea7c0-35d0-5873-ac02-7806c54e34bf | note | ○ 611.09
1181d0a2-0106-5b57-a851-aea1de0b0ec0 | note | ○ 611.10
62104525-c8d1-5dd6-85e5-2a00fc5d904a | note | ○ 611.11
8d9d9d83-3683-5028-8b23-d98ee9396b99 | note | ○ 611.12
6e74cd2c-5fa2-50c2-b20c-6d20aa4ce247 | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
d13e5b0f-5afd-5eb2-abee-4348e2c1c8ba | note | ○ Projecting reinforcement is the correct length and location.
2e6a8bc8-90cf-52ea-bb35-8bc7f60a7eb8 | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
367d15b2-ef5e-54fb-aee7-d1f6536d99e2 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
6afa8d19-c1a4-537f-9459-b14e2eeeae52 | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
0db953df-a6a7-5257-a841-a8e811aa1384 | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
76eb878b-30cc-51aa-b80e-1e3032b368ed | note | Method - Measure, Visual
dc09fead-58a6-5851-b75a-08596fc33ef8 | note | Frequency - Each element
6ca15591-6374-5e7a-a490-a227bb49f811 | note | Category - IP
ac7319e1-05ce-5c9d-947f-421542a65cf8 | note | Responsibility - Foreman, SE/PE/SPE
8c0340b0-1740-55ce-b737-67cb03479103 | note | Verifying Documents - This ITP
b59e2732-e3f3-5e84-823e-f00575d4556a | date | Date Completed:
c9ca6697-475a-47f5-ac0f-d35a83047f11 | checkpoint | 5.6 - Cast-in Items
398006d8-de45-5b43-a5b6-7f73cc95328a | note | Reference - IFC Drawings 610.47 (a), Table 610.472, AS3810.1 Table 3.3.6.2
75dde24b-1617-536c-ace7-90ea333a07c8 | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
178d20ab-e8ec-5690-940a-1fcc06baee5a | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
3f695cb8-6a28-5659-98df-2f822312be3f | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
5be1e627-de10-5756-a665-4a297ae2c6bf | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
d7d86f2d-bff6-5493-a3ab-019b424cbb11 | note | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
9d6e90ab-c923-563c-81df-59439d6501f6 | note | — i. Bolts, ferrules, projecting bars & couplers = ±3mm
7b8af07f-075c-5c58-b183-1a1ce488a7ac | note | — ii. Running dimensions of a group of the above = ±6mm
bd176f43-c94e-5752-8aaa-f6a57ad1bec0 | note | — iii. Ducts and conduit location = ±12mm
0450a659-e252-50d7-b9bf-0688609ae334 | note | — iv. Diameter of ducts and conduits = ±3mm
ea7358cc-266f-5892-b09b-404f57457ef0 | note | Method - Measure, Visual
902d2db3-50b5-520a-8f5b-4f0ea19555b5 | note | Frequency - Where applicable, each element
f3198b69-1453-5197-a6cd-b2828df298d7 | note | Category - IP
61803269-9026-51b0-91e3-46e9b633cbef | note | Responsibility - Foreman, SE/PE/SPE
8a00c83c-fb96-56d9-a26d-40e5a1fa5fba | note | Verifying Documents - This ITP
5a6d4903-e2bd-54c6-aec9-d5d9ea44ca58 | date | Date Completed:
dc5f578b-c07b-4bce-80d1-cae80e48c146 | checkpoint | 5.7 - Thermal Differential Monitoring
e66b5253-4172-505a-b03b-2a4f99d99ef9 | note | Reference - 610.22
6c1bb7e5-96e6-506f-9f59-21d886c07379 | note | Acceptance Criteria - Thermal differential monitoring thermocouples installed.
a6ab8000-ca3e-5ee1-bf51-fdf8d8c54561 | note | ○ Only applicable if the element has:
314dbaf5-7529-53a7-92d4-e1ff12c22745 | note | — i. The least dimension of a member exceeds 500 mm or
51647561-a55f-5bb4-90d7-8808b37a99df | note | — ii. One or more faces being restrained by previously hardened concrete or other external constraints.
cade44d9-fb06-58c7-8de9-f965153a373a | note | ○ Temperature differential monitoring shall be undertaken on at least one representative member from each type of large and restrained members, provided that any required control measures to reduce the differential temperature within the specified limits is adopted for the subsequent construction of members of the same type.
c33ec9d4-1e6f-5058-92d4-b9662ac13ff3 | note | Method - Measure
7127d61a-0041-5bbe-b458-939715f8b25e | note | Frequency - Where applicable, each element
015ceab9-4bb9-505c-b2b2-8cb3139a3db6 | note | Category - IP
daebc54f-1dec-5dcc-9c9d-5595f54a3356 | note | Responsibility - Foreman, SE/PE/SPE
6b92cb7b-c824-5d11-aca3-f7ed67834dbf | note | Verifying Documents - This ITP
96cf6494-8f33-5c4c-9d04-9d511b713104 | date | Date Completed:
877f8285-6ef6-4227-9434-0a91935068f9 | checkpoint | 5.8 - Pre-pour Inspection
40a8d530-af35-5a15-afca-cfba8a3c2d23 | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
f624aad7-7d20-539e-b9bf-f9f2519c2b40 | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
b08b072e-5f77-52a7-b8b1-89c5b2583702 | note | ○ All foreign material has been completely removed from the forms.
5e0814fa-c616-5446-9638-bdf8e9ab7d45 | note | ○ ATTACH: Pre-Pour Checklist
1c9a5b2e-43b3-58d5-ba49-233cdf8e513c | note | Method - Measure, Visual
8bf3473a-0615-53e8-b9aa-c0137803071f | note | Frequency - Each element
3354d1be-c92e-5deb-baf0-4dff45d428e8 | note | Category - HP
a87cef4c-500f-5f7c-a41f-fca449e8a27f | note | Responsibility - Nominated Authority
7e495bae-a1b9-5bd4-aa62-f72fa9f52595 | note | Verifying Documents - ConQA Hold Point Release, Pre-pour checklist
f0a370a2-ac86-5bd8-bc2c-006396c1eb10 | date | Date Completed:
80d7654e-7904-41e8-b288-4d14d47256f4 | signoff | AUTHORITY HOLDPOINT
1cc7f55e-56fa-4656-95f7-8b52c7ddfb3b | checkpoint | 5.9 - Weather Conditions & Evaporation Limits
273df8fa-60bd-59c2-a24d-0e4e721c966b | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e), Table 610.171
85267b12-65b1-568b-ac9a-f427a0e6ad08 | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
6faa9baf-0d70-5a44-8636-291214655b81 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
267f0eb0-8a98-5428-be5a-556c3559310b | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
ddf393ca-a8a1-595f-887c-14e1c9c6c84f | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
abcbfd5d-a6c2-57f4-8b39-6c4204bb707e | note | ○ Record: Required information on the Concrete Pour Record.
c2556bba-782f-5d89-9815-dcadffa0e7df | note | Method - Measure, Visual
1ae40ec3-8d3d-5286-b23e-3c48c54f030b | note | Frequency - Each element
fc845633-dce7-5bf1-b2e7-a34bab64e685 | note | Category - IP
314d9334-426f-51df-bd6c-3742a22cf72e | note | Responsibility - Foreman, SE/PE/SPE
2f855532-e8fd-553f-a5b1-2d19ee7562af | note | Verifying Documents - This ITP, Concrete Pour Record
5eb7e4a2-d1eb-55cd-9bf5-6b1cdeac02e6 | date | Date Completed:
9207f34d-0b5e-4ee1-b44a-9a5392b2f934 | checkpoint | 5.10 - Concrete Testing - Sampling Frequency
557910c5-9f7a-5e00-87ad-daa8fbd06fdb | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
a54a1a08-485d-5bbb-86fe-d4c1233ab984 | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
51aa4eef-bdf3-5ba9-92ba-a507ec981c5f | note | — 0m³ to 10m³ = 1 sample
271e226a-c45e-543b-a6d3-90f9dfb7ecff | note | — 10m³ to 25m³ = 2 samples
7668ed80-47b6-5237-bfed-64ff5229e06d | note | — 25m³ to 50m³ = 3 samples
976de922-1221-5c8e-8ea9-1029a901fe6c | note | — 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
d1a123bf-c86e-5042-9297-00f22cca8cc4 | note | ○ For each additional 50m³ and additional sample shall be taken.
3c71b28b-839b-5658-ae76-efb96cfab72d | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
4f229d14-1200-53ec-9420-9219b440c719 | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
d7dbd905-667d-5810-98be-230a0b0d0cb1 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
ad4b40e2-df8c-506d-8f7c-10c4c85e5df3 | note | ○ Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
d3f0cf39-529e-5ae5-9977-882b87e3fe7c | note | ○ Record: Required information on the Concrete Pour Record.
4e26cceb-732e-5534-b796-5de8f8f319fb | note | Method - Test
52e5c54a-36b3-5ad3-8e8e-dedc32f79aa7 | note | Frequency - Each element
e8752ee6-b8cb-58b0-990e-96b71386be72 | note | Category - IP
d7bd337f-6762-56c7-ae07-dfade03b79ac | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
a62072c6-2603-53d0-bc4a-2636f50cd414 | note | Verifying Documents - This ITP, Concrete Pour Record
0d1d4be6-54fe-5608-b8d1-a0c4a94475b8 | date | Date Completed:
01faf5ad-755b-4458-ab16-9f63f8489404 | checkpoint | 5.11 - Concrete Testing - Slump
2e25e44a-98aa-544d-b47c-88dcdbb61158 | note | Reference - 610.16 (c)
6991f216-0964-5aad-b390-891ef8b0fb57 | note | Acceptance Criteria - Slump testing tolerances =
859ac6a7-e656-5d3c-a7da-aa77ea35a856 | note | <60mm = ±10mm
7b062a25-dc8a-54ce-8f74-51a2e2100f79 | note | ≥60mm to ≤80mm = ±15mm
d6871920-3684-5714-934c-aa123316c3f8 | note | >80mm to ≤110mm = ±20mm
7796ed39-5797-575a-9f31-5871ebce03bb | note | >110mm to ≤150mm = ±30mm
8bf80568-2527-56c7-80b1-9c49da482433 | note | >150mm = ±40mm
67086a79-6142-54be-86cc-1eb5dcba309a | note | ○ Record: Required information on the Concrete Pour Record.
a7f205f3-43df-5edf-ad9e-291d61a211af | note | Method - Test
6ea61488-4896-514b-8537-c8efd76280b4 | note | Frequency - Each sample of Standard or Superplasticised Concrete
620e06b4-e6b5-5dce-91b2-be1427acbc24 | note | Category - IP
45b23470-95c5-56d0-9467-be7a3c09d820 | note | Responsibility - Concrete Tester
9d8dc7db-218c-5857-b321-1bdcab6671e4 | note | Verifying Documents - This ITP, Concrete Pour Record
48997e85-3296-5f3f-9377-6fc777f136c0 | date | Date Completed:
c922d7b5-3051-4dba-9c0f-0eb064c3e58b | checkpoint | 5.12 - Concrete Testing - Spread, Passability & Viscosity
4293a69e-9461-5248-badc-2674e0186f4e | note | Reference - 610.13 (b)
3df2e0be-062d-5ee7-9263-39c193144889 | note | Acceptance Criteria - Spread range = 550mm to 750mm
5299a325-a803-5b04-9919-fa4d6ebe441d | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
609abcba-5eb5-54fb-b2f5-0e64277db630 | note | ○ Passability = ≤10mm (aggregate height differential)
b5fac7c2-2a6e-5b5d-b15d-a3ca744978c3 | note | ○ Record: Required information on the Concrete Pour Record.
1c1a202c-0686-5c2d-a5c3-5cbd89577574 | note | Method - Test
7440eb64-88df-5802-8fbd-548b12fa1f9e | note | Frequency - Each sample of Self-compacting Concrete
85cd97d4-86d6-5c33-a621-5ecf7dd9c75b | note | Category - IP
77a620a9-abb2-5a8a-81bf-335a86b99437 | note | Responsibility - Concrete Tester
a4f6a4b7-1570-5248-927a-a48dbcb066fb | note | Verifying Documents - This ITP Concrete Pour Record
c8d4212e-955b-5d63-a174-d0868040e79a | date | Date Completed:
ef1a89ee-8a5b-458a-ba1a-2d29d7f518b7 | checkpoint | 5.13 - Concrete Testing - Compressive Strength Cylinders
96b8f66b-b7e0-5cd7-b0ef-47d1664b41a0 | note | Reference - Site Sampling & Testing Procedure
6d418b76-ed59-5249-b056-bc2c7433cff9 | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
5e2af4d8-970d-583b-b6c2-913d4705fcd6 | note | ○ Record: Required information on the Concrete Pour Record.
726dc14f-4582-5e75-b047-5913d4bcf921 | note | Method - Test
aadf1fd5-4de8-514d-9126-6f3cec80c591 | note | Frequency - Each sample
cf15a9cd-fa36-51b8-9e45-dfa1a4112879 | note | Category - IP
ad179d76-4ead-5e76-ac62-4338f917ba96 | note | Responsibility - Concrete Tester
b5015ddc-a88f-54ea-b594-099a8447483e | note | Verifying Documents - This ITP
4cd21b37-7564-5797-afb0-85068de2a5e1 | date | Date Completed:
45ca8447-a34d-46f1-98a6-862e27dab1f4 | checkpoint | 5.14 - Supply & Discharge Rates
f3f8bcc6-ecb4-5997-995f-820cc96e1b8b | note | Reference - 610.13 (a) & (f)
91b11a31-ac83-5907-97ef-65c29e8d7c22 | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
5a4eaeda-dd8f-5228-afff-dfcd3d5fff1e | note | ○ No water is to be added once discharge commences.
252af84e-9097-58f3-b4e5-6e5371cef1fd | note | ○ Maximum time between batching trucks is 25 minutes.
3c13a927-e8ee-5831-9d34-768c23990c6a | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
66c8cadc-85f6-5ed6-b9ba-d5570913ed8c | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
c240e265-1591-510c-8636-677a6bd96548 | note | ○ Record: Required information on the Concrete Pour Record.
9a975bf0-12dd-5ae4-acd1-e99d10044eff | note | Method - Measure, Visual
39124dd3-e0f2-5cfc-839a-b5edf5327970 | note | Frequency - Each load
2b9ff441-a850-5bd2-821e-83d0ed29bee0 | note | Category - IP
1320db36-8f52-54f1-980a-4abe41225cfd | note | Responsibility - Foreman, SE/PE/SPE
46d4ca3e-3b56-537f-88cf-820ac41609da | note | Verifying Documents - This ITP, Concrete Pour Record
bdc2095f-212d-5c8a-9810-94d9072da2fc | date | Date Completed:
761f80e7-4013-4a4d-88b4-b797c39b2108 | checkpoint | 5.15 - Placement & Compaction
018331d7-f395-5cab-8d69-01c51ff4fb89 | note | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b), 610.18 (d) (i)
52d446e0-7cb9-56fa-b0a6-c012f903f970 | note | Acceptance Criteria - All concrete batches are traceable.
52515516-98c9-5fad-9191-faea46e54a5b | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
a91ec6c5-fb74-5593-b24f-dd38e563a36d | note | ○ Concrete is not dropped freely from a height exceeding 2m.
d6b6272a-81af-5585-8338-6d637634d3fe | note | ○ Concrete is not moved horizontally by use of vibrators.
3e698c9c-54b3-55e5-a62f-cdcb82e691d4 | note | ○ Adequate compaction is ensured
8c985369-d075-5d1c-80ee-3d79747a1525 | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
38d4bc98-55ed-59bd-a482-8565ab5b6c24 | note | ○ Concrete layers are not more than 350mm
d5a2acaa-5c5a-572f-b7ba-e6c9b68d39ea | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
60c76fad-26ce-53da-8cb5-137c60f8a4f1 | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
8b8081e5-698a-5a16-b514-3ad64c2cae43 | note | ○ Attach: Concrete Pour Record
505b534b-7a7a-5422-ab3b-837b72b5fc01 | note | ○ Attach: Concrete Dockets
b6e3ac45-b080-5910-8fd6-0e6ec9baace1 | note | Method - Visual
31b51350-74d8-56f5-b769-dc0d219528fa | note | Frequency - Each load
5e21a661-2c6f-5c03-84d0-9e4c09a990d6 | note | Category - SP
c4e1c141-22ee-5d8c-8d5a-8dd3ddadce54 | note | Responsibility - Foreman, SE/PE/SPE
a3a2997a-2185-5683-b82d-ddedbb80c539 | note | Verifying Documents - This ITP, Concrete Pour Record
fef1198a-7b97-5237-8cad-17f57ff2a67c | date | Date Completed:
fc03d63e-2696-47e8-bc65-8e644a1b884f | checkpoint | 5.16 - Surface Finishes
8a9a07a3-77ab-55db-9699-5401acb8d6ba | note | Reference - IFC Drawings 610.31, 610.20
d2a51baf-b3fd-5705-9f9c-1ac299491501 | note | Acceptance Criteria - Surface finish as per IFC drawings.
c2d3cae9-cb7a-5b16-a0c6-0bfd62453e5b | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
be54fc41-7c34-5345-9861-2f390b84343d | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
a034e773-4696-5ae3-b3f7-a8f884f4d52f | note | Method - Visual
d86ae1fe-77d2-5321-8f9d-84eccfd47ec3 | note | Frequency - Each element
92c79b79-9733-5767-8e22-1afdea8c99e6 | note | Category - IP
baef01a9-fd97-5fb4-8afe-fee5903f390d | note | Responsibility - Foreman, SE/PE/SPE
486fe559-800e-5b25-ae10-53f06e17e060 | note | Verifying Documents - This ITP
f1c2ccad-032e-5e2f-a9d7-b51a0adf1830 | date | Date Completed:
4950def2-e778-44b0-ab87-9da0a3e77f55 | checkpoint | 5.17 - Curing-Top Surface
d8243a91-68b3-5835-83a5-fb49bd829ba8 | note | Reference - IFC Drawings
d125ffd2-46a3-58d0-ba21-fceb0c089aee | note | Acceptance Criteria - Top surface of the pier and abutment walls shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pier and abutment walls may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
c6ec8521-6b0a-51a0-b893-705c92df20ba | note | Method - Visual
c6c6ae49-8113-511c-a596-dcd566f92638 | note | Frequency - Each element
a0b4a025-35a7-543e-92dd-eab7ec878922 | note | Category - IP
c3a74ba2-cdd1-5ba3-8a9b-c87c36566927 | note | Responsibility - Foreman, SE/PE/SPE
fdd5018a-3ccc-5d7a-ab5e-89660127153a | note | Verifying Documents - This ITP
84fc44da-2a9f-597a-a85e-869b1ae3ac47 | date | Date Completed:
af8b2045-0178-4ddc-afce-4a334cc75790 | checkpoint | 5.18 - Curing after formwork removal
c471581d-6a5f-5eac-ab00-189829f73bb4 | note | Reference - IFC Drawings
f6a30785-12d0-5b76-9146-f5884897cb43 | note | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
917d1531-e945-5b40-be8c-42edc8817e37 | note | Method - Visual
0054bbc8-8353-51ea-a4bc-fbcaa9b44f44 | note | Frequency - Each element
e8fba6c5-c3a7-5e16-9833-afe216a295dd | note | Category - IP
4b90277b-7fba-57a5-bb49-249235456b53 | note | Responsibility - SE
0cd81279-1570-597b-8a3f-53502156fbcb | note | Verifying Documents - Thip ITP
db3bc633-343d-59e2-a55a-3db660d1efd1 | date | Date Completed:
3197aa82-2355-43a2-be8d-b4dbbac45f9c | section | 6. Post-construction Activities
41e6fb09-5d6c-4164-b798-8f78acb6a376 | checkpoint | 6.1 - Thermal Differential Monitoring
a1b3662e-8a7d-5a01-9aea-110c4c0bb84c | note | Reference - 610.22
e52a98a7-2005-5e7e-b073-9ada2d0a4e8f | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C.
77a56a5f-eeac-5024-9912-19246b80257a | note | ○ Only applicable if the element has:
824aff7e-6bec-5e4d-8c58-5de944b92600 | note | — i. The least dimension of a member exceeds 500 mm
e63798ac-dcfd-58fb-8322-ee082810e5fe | note | — ii. one or more faces being restrained by previously hardened concrete or other external constraints.
97d37a6d-3b3f-5100-9466-adcb730bfacf | note | ○ Attach: Thermal Monitoring Report
a0b099be-f1bf-521a-bf03-2a5f41862c13 | note | Method - Document Review
5ad95328-1bb6-5ecb-b402-e6cecb68c921 | note | Frequency - Where applicable, each element
50f016f4-3e9c-5939-9fd7-0d30cb53ceb7 | note | Category - IP
ea8d7ed7-df6c-580b-b7af-674399e770d3 | note | Responsibility - Foreman, SE/PE/SPE
9deef6ec-5a74-514f-8075-95842c397562 | note | Verifying Documents - This ITP
6eccb763-7ff5-59c0-bf1d-200df5d8d57f | date | Date Completed:
936e5832-028b-4844-af73-10e280c27ab9 | checkpoint | 6.2 - Early Age Compressive Strength Test Results - Removal of Formwork
943ef854-f01e-533a-af29-3653225ec3a5 | note | Reference - IFC Drawings Table 610.251
c61c7f15-5559-5679-9487-dec117597842 | note | Acceptance Criteria - Minimum Period before Removal of Formwork and Formwork Supports is as per 610.251.
594058cd-44b5-5cd0-bae0-04335978a46e | note | Method - Inspection
d9991428-3868-5e73-bd19-1128186c3e26 | note | Frequency - Where applicable, each element
c342cbf6-cab6-5dc2-bca4-09b81433f052 | note | Category - IP
a2087630-5c31-50b3-bc14-51a56ae79593 | note | Responsibility - Foreman, SE/PE/SPE
59f07f45-8470-5d45-9aee-26ae01a193e6 | note | Verifying Documents - This ITP
a79bc81c-e198-5133-b77d-10e211665fa4 | date | Date Completed:
b4840c22-cbf8-4678-b407-563c2900d497 | checkpoint | 6.3 - Surface Inspection - Cracks
f5268e16-f5f5-51a2-9c15-7c702d7b40f0 | note | Reference - 610.24
346acb96-1f4f-50f4-8368-495ecf1ed4ab | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
824afef4-a2c5-59d3-b0d6-fde4ab8edef4 | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
2fbb17d6-0d59-530a-8ea5-52bd2a37f2fe | note | Method - Visual, Measure
031d2b1f-d149-5299-a8a4-0e232dd6b20d | note | Frequency - Each element
f5b171c8-a1bc-50b4-99da-8ecdd530f2f3 | note | Category - IP
6337440d-b7e0-509b-8b34-f4111f6d7db2 | note | Responsibility - SE/PE/SPE
185e0ea8-be90-5b7b-9809-e0c347fd2152 | note | Verifying Documents - This ITP
c2cfc854-3716-52ed-aa1d-e1ba375e9964 | date | Date Completed:
c098a519-f99b-4542-8ddf-8e256ba3a182 | checkpoint | 6.4 - Surface Inspection - Surface Finish
77ae938c-e105-5e14-9cfe-48701aea2863 | note | Reference - IFC Drawings 610.31 (a) - (n), 610.32
2f03e051-54a6-5cf5-a1b6-59ef63c09c08 | note | Acceptance Criteria - Comply with the IFC drawings and specifications.
5fa551b1-65a8-5f32-b9d2-463473ec8ffb | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
50eb9142-1b18-58ec-804b-e11827f315c6 | note | Method - Visual
4202c177-a854-59b6-8794-23bdbfd20543 | note | Frequency - Each element
0d4dc400-76fc-508f-983a-7144695c0361 | note | Category - IP
d5be68c3-5250-5862-bbc1-1173b49d2b89 | note | Responsibility - SE/PE/SPE
0a90505d-e66f-56ef-9e44-49afc4d698d2 | note | Verifying Documents - This ITP
ff3b84cf-20c1-53a9-b9d6-c3f6312eaf71 | date | Date Completed:
fc5b1b5a-9c8e-4f04-82fa-a80286a7f365 | checkpoint | 6.5 - Measurement of Concrete Cover
4ead6ea1-4324-543a-ac57-08bce1731418 | note | Reference - 610.34
ee4287cc-c180-5faa-9963-8fcc2766d316 | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
df61cc5c-3039-57c0-a560-a6a2e9a4f33e | note | ○ Minimum 10 no. measurements recorded in each area.
83fa81e9-43a5-5064-94a9-2b321ed05b9e | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
f1329b98-91c0-5b3e-b2df-015eb3cc96f7 | note | ○ Attach: Covermeter Check Record
49485f7a-cd0e-5743-9ea1-4758f69d12c8 | note | Method - Measure
7d3f905f-433d-5337-847d-e0ef56c8f868 | note | Frequency - Each element
6b945a3c-fca9-52c8-ad4a-05306d75e4ce | note | Category - IP
222a8d3c-8699-530d-b469-00d74bc35a3a | note | Responsibility - SE/PE/SPE
28fb5b66-9bbb-5f9a-8297-579b0dfc1ef3 | note | Verifying Documents - This ITP
cbf5173c-ea6a-5338-a824-bd7f8383b6e6 | date | Date Completed:
eb693e1c-654d-4a7d-8ead-03669592be37 | checkpoint | 6.6 - Early Age Compressive Strength Results - Placement of Fill Against Concrete
0fda29cd-bdaa-5e12-ac68-d904f3aaddb3 | note | Reference - Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
e423776a-bc95-5fc8-8ef2-418df6a55c2f | note | Acceptance Criteria - Fill is not placed against concrete within 14 days of pour.
3229a709-8f47-5c56-8c41-a44dc512a837 | note | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
1a1b5056-2fcb-5ad5-9da7-0a86e0f06047 | note | ○ Attach: Concrete Test Results or Maturity Test Results
2bf2c617-3217-599e-ac85-3e04da3bd962 | note | Method - Document Review
d3e7b1b0-882b-593d-9889-3c7beb63aeb3 | note | Frequency - Where applicable, each substructure element
950a9372-a57c-5364-805d-1fdda7894242 | note | Category - SP
b2e2a92c-2496-521c-8909-8cfdeca12345 | note | Responsibility - Foreman, SE/PE/SPE
4292d02d-b943-5dcb-90c8-571472e7718a | note | Verifying Documents - This ITP
895f5e41-b19b-5ad6-919a-c1efc3d949e1 | date | Date Completed:
fde9a517-6e5b-4407-9e6b-f9a9622f4779 | checkpoint | 6.7 - Compressive Strength Test Results
e7c7f047-f2b2-5f6a-9ab2-d0a80de4e9fe | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
f518ad3e-3352-54b0-8997-8decba389ef5 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
1f2eca38-486c-5d9e-a33e-17d5378c9767 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
50f5dcae-b8bb-52e0-b09d-272e3b5decbc | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
9dda2f71-9e0a-57d9-ac13-aaf207650a28 | note | ○ Attach: Compressive Strength Test Results
986eb9bc-5da7-51bc-9039-5e06b0b8830e | note | Method - Document Review
d102a6d2-a769-5fb0-823d-c5dcfd44f3c5 | note | Frequency - Each cylinder
f6545e04-6367-56aa-a643-56fb1c133e76 | note | Category - IP
86d64a13-520a-59fd-aa5e-699e638f6960 | note | Responsibility - SE/PE/SPE
8932231b-ecec-5c15-b3d7-562b76b96427 | note | Verifying Documents - This ITP
9a603a28-2792-53ac-8d68-5b645e4e8761 | date | Date Completed:
f4230c00-421f-4e9a-8881-fb45daafc656 | checkpoint | 6.8 - As-built Survey
76e44baa-7f98-5c68-9925-5ab9cf168ad1 | note | Reference - IFC Drawings 610.47 Table 610.472
b3a31894-1b44-533a-8c84-e01ff4aeefcf | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
e879dbbc-eaa9-5e9b-b5e3-e03682304374 | note | ○ Attach: Survey As-builts / Survey Report
6b3c3027-3e6e-5bc6-be37-b3206fb7607b | note | Method - Document Review
22dddcc2-3fac-5405-ae98-a8459f81158d | note | Frequency - Each element
baa86ef6-c807-5b5c-aa80-41e574ec9853 | note | Category - IP
28f0bb75-e66c-56bf-80e4-9a3b87b3843e | note | Responsibility - Surveyor, SE/PE/SPE
b02ed3e0-578f-52d6-83f0-01434b98f370 | note | Verifying Documents - This ITP
be82d4ff-a7bd-5117-82bd-0e62074a3908 | date | Date Completed:
ff718a18-9437-434f-babc-52ce439b383f | checkpoint | 6.9 - Non-conformance Report (NCR) Closure
36fdc92c-5e06-5feb-a35a-58d72af94520 | note | Reference - MRPA Quality Management Plan
5ab0455f-342d-565c-bc84-a548de5f790d | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
d914a042-9bd4-53be-85cf-e6a339a579ef | note | Method - Document Review
c4fa99ba-6711-5a66-926a-985fd9586aa8 | note | Frequency - Once, prior to closure of this lot / element / Work area
12475112-ea4b-5620-bd63-072a3e6511b0 | note | Category - HP*
59971a23-6173-5a9d-92c0-1574c8301fe0 | note | Responsibility - SE/PE/SPE
53b40338-a814-5902-8ad9-545a576609bd | note | Verifying Documents - This ITP
b428994d-ef81-5724-b7cb-b1b60f6a56aa | date | Date Completed:
561f7c57-3466-481d-9fbb-b15a4d361428 | checkpoint | Final Inspection
42ab72e0-cfff-59cf-bb62-45d34d017aca | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
834ff845-13f2-57ec-9bdf-93434011c97a | textbox | Name:
382305ee-ade3-5592-beff-0c635249e407 | textbox | Position:
e0db6b67-903b-5c6e-ae4a-437bc0b3a092 | textbox | Date Completed:
141f52df-4518-4c67-9813-0c7e6892e49c | signoff | Sign ITP
c5b719da-419b-4132-b720-ea0a1d6f0689 | checklist | ITP-244-STR-HOP-Bored Piling sense 600 Rev 0 | itp | ITP-244-STR-HOP-Bored Piling sense 600 | 8f10438d-c504-43cb-8bed-d1221ee08b7e
79528b12-86e8-437f-9f99-dd6cc6f5dc43 | section | 1. Referenced Documentation
26b6388e-1d60-4336-ba48-54f66436c432 | checkpoint-no-value | Referenced Documentation
67ee138a-7faa-508d-8186-3682e437827f | note | Document Title: ITP-244-STR-HOP-Bored Piling Sense 600
075165aa-7e65-54d8-9350-f625d383611a | note | ITP Description: Bored Piling Sense 600
c05103db-d90b-5364-b4f3-dc223bbe292d | note | Discipline (e.g. CIV/STR/RAIL): 244-STR-HOP
e0aca74a-09f3-5ec3-98e9-8916df076077 | note | Revision Number: 0
46583cb9-9742-5aba-9fea-def22fba5d8a | note | Revision Date: 3/03/2025
6c7245e1-5a97-5f5b-8b59-9bd287eba6ca | note | ITP created by: Manwel Kalyana
be0fed23-5c8b-5901-ba0b-64123ba7ff04 | note | ITP approved for use by: Pradeep Talasila
aca1b056-611d-5866-80c9-494d59d1cf16 | note | 1.1 - Non Dependent
9e51563b-0d71-565a-80fc-a2afb837446e | note | Reference - VicRoads Section 606 - July 2017
9c11bf7f-f0de-5ee7-8c04-61488130b9d9 | note | ○ VicRoads Section 610 - Feb 2020
767448cd-44e9-5671-af5b-1284aff522cc | note | ○ VicRoads Section 611 - November 2018
4f4f22a8-85cd-554e-a1cd-4582d70d9805 | note | ○ AS2159-2009
7d050f7e-4983-5eea-ab64-fb0a644a6f99 | note | ○ AS3810.1 2018
488daf26-85a3-539e-8916-a39f68648247 | note | ○ AS5100.3-2017
fc4c95f9-af11-5b1c-a852-470c9603f93a | note | ○ AS/NZS 4671 - 2019
d0974697-6384-5e36-ace5-4ae9c1613fc5 | note | ○ AS/NZS 1554.3 - 2017
ba6251e2-5875-48ad-90cd-ab5aa8f00f5e | section | 2. Preliminaries - Materials
9e5e1cd5-467f-434c-bf48-284310601389 | checkpoint | 2.1 - Concrete Mix
6d73aeb7-1cf3-5c9c-a450-d80af8223f78 | note | Reference - 610.07 Table 610.071
04efae1f-39ed-5321-b2d7-165abec6e76c | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
a3851067-5da3-55b4-981c-b7af07528607 | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
fbd1364b-bee4-5b26-8266-cc535132bb19 | textbox | Enter: Teambinder Material Approval number
ed1565c4-5eb7-5c48-90b0-3b1ce9bbca08 | note | Method - Document Review
281a6b08-0fc0-55e3-a0a1-b61b2ce0a228 | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
73e27a28-7341-529b-a976-a21ca1620b4a | note | Category - HP
8b14243b-585d-550d-96fe-0356489011f8 | note | Responsibility - Nominated Authority
602bf5a9-2eec-5318-bba5-09072bd274ba | note | Verifying Documents - ConQA Hold Point Release
63cb256e-9d97-5efe-a83a-3c4b3e42b339 | date | Date Completed:
9caa235e-e6ca-4171-8ac4-fc62008b10f3 | signoff | AUTHORITY HOLDPOINT
2e7bac17-c28f-470e-84d0-0ff6c7ba37bb | checkpoint | 2.2 - ACRS Certification (for Reinforcement)
bac854c4-a670-587e-861f-a62a399c8445 | note | Reference - 611.05 (a)
a48d6b87-4fc8-53fe-846f-c601ca2623d3 | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
2a8ae1dd-6891-5305-be47-38750aa69f47 | note | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
8913c28e-ea41-518c-b45b-e02d531bdb53 | textbox | Enter: Teambinder Material Approval number
038876f4-228c-5089-8108-3dcc795f0283 | note | Method - Document Review
c0a0b0fc-af55-50fa-8807-de503a007d05 | note | Frequency - Once for each supplier, 14 days of award of contract
fa72e3ee-36d2-5482-988d-551436e454f5 | note | Category - HP
6c19b91c-2558-58b3-b9ae-db08394c29fa | note | Responsibility - Nominated Authority
61469fe7-ba86-5201-b2c2-3357c4b347db | note | Verifying Documents - This ITP
9885bce0-fbd7-50b7-a7e9-2c168ab45e99 | date | Date Completed:
87a4cad9-a4f1-422d-82aa-9a70a1d55f74 | signoff | AUTHORITY HOLDPOINT
6151e8ab-e550-48b1-b13b-1b16f6438bd0 | checkpoint | 2.3 - Bar Chairs/Aspros/wheels Certification
f3125974-7a69-59c8-8020-89358f42363c | note | Reference - 610.26 (a)
4e4c1ebf-11ba-5169-8262-34ddadd12140 | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demostrate suitablity to prevent excessive deformation under loads.
68ffda5b-c6c8-5576-ad76-d48b8dba8fba | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
2ca728f4-0f43-5d8d-bbba-ff146324f85e | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
89309a0f-324d-5828-b134-375ed9dae118 | textbox | Enter: Teambinder Material Approval number
fc79de99-1de6-548d-bf62-b5248cbeb6b6 | note | Method - Document Review
0c20b824-859f-5684-9773-6016bafa945d | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
886d8425-016d-5261-8de5-f476b8191dd5 | note | Category - HP
2af3f538-014e-52d3-939f-53ca37c62cec | note | Responsibility - Nominated Authority
5a4bfd0e-2f42-5fd6-b421-78793c46dfdd | note | Verifying Documents - This ITP
80f01636-7dce-5a14-b6eb-b48706b4f527 | date | Date Completed:
347f7fb1-0571-4b4a-b8a3-fded7c060d38 | signoff | AUTHORITY HOLDPOINT
2cfc1554-b13b-4e08-a240-e8ca05fb7180 | section | 3. Preliminaries - Procedures & Documentation
466edd62-6116-43fa-8c04-49b064e03b6e | checkpoint | 3.1 - Working Platform certification
2f96694c-8f44-5f73-93d4-acf813764400 | note | Acceptance Criteria - Satisfies minimum plant bearing pressures requirement. As per seperate ITP.
6ee0691b-6d0a-5089-98d1-0192d447c639 | note | Method - Document Review
9bbae017-8c17-5512-82f0-229379965520 | note | Frequency - Prior to works commencing & after rain event which there is >10mm in a 24hr period.
772e4a80-7ac2-5564-9626-86032de3e084 | note | Category - HP
daf87691-bd34-540f-8472-cc992cb1afb2 | note | Responsibility - Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
d7275012-6208-58ca-bfbb-dc24c5236ae8 | note | Verifying Documents - This ITP
808d754b-f9c6-57a2-a51b-44465d5a5596 | date | Date Completed:
30196f87-7896-426b-816d-d05bf0a3ad9c | signoff | AUTHORITY HOLDPOINT
3ee3456f-944f-4d4c-81ca-5a3571c9a22d | checkpoint | 3.2 - Piling Operations Work Procedure
d18a4870-e859-56d4-864b-f6b814bcf5cc | note | Reference - 606.03 (a)
ce7c0ccc-09e0-540d-8afc-41d72845f41d | note | Acceptance Criteria - Piling operations work procedure to be submitted for review to the Nominated Authority.
e10978b5-43a9-56ac-b361-8544f1153507 | textbox | Enter: Teambinder Approval number
542a70fa-e2b2-5dc7-be01-0de0321b348b | note | Method - Document Review
b20dc045-649d-5d09-8fbd-b4eed9c45898 | note | Frequency - Once, 4 weeks prior to the commencement of piling
03eb1a56-5725-5456-8a5b-567f0e4019ca | note | Category - HP
507e29cf-858d-5b6f-9727-85d0b84b5cca | note | Responsibility - Nominated Authority
eedc71d0-e991-5236-a3db-bc7da793dc8b | note | Verifying Documents - ConQA Hold Point Release
5161364e-a282-58ca-9f5d-591a76908e9c | date | Date Completed:
8206b6e5-f94f-47ec-bf76-ae65184ec9c1 | signoff | AUTHORITY HOLDPOINT
aa5a60ae-1c28-4249-8fe9-b2b500ae07cc | checkpoint | 3.3 - Temporary Steel Casings
f148b0b1-668a-5cb0-bf14-7d5eb8be76d8 | note | Reference - 606.03 (b)
8564588a-6637-5452-b9d5-87f035d1cdad | note | Acceptance Criteria - Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
aed2d8a1-8a40-5cee-85d8-3840d968b947 | note | ○ Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
a833717f-b507-5a61-825e-9cfa09e224f3 | note | ○ The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
02ad331c-2af2-5e4e-9201-40f947cd8342 | textbox | Enter: Teambinder Approval number
3ff00344-a7bc-5aa3-81e5-81c446477c6c | note | Method - Document Review
add91fad-2bcd-5db9-a4dd-dc2ee2152174 | note | Frequency - Where applicable, once, prior to use
d0d8411e-f8d2-55bc-9e61-83ef32f8af4c | note | Category - HP
387f7b2c-c0bb-5d2a-b91b-2986150c9abe | note | Responsibility - Nominated Authority
68bfd8b3-f3f1-56af-9f9f-972afad6e077 | note | Verifying Documents - This ITP
3351e71d-5d76-58ba-80a7-dcfe1cb74808 | date | Date Completed:
5f594e86-3da0-4841-b072-4cd595726b07 | signoff | AUTHORITY HOLDPOINT
6206e009-a409-4a19-a923-d82b248cf6ce | checkpoint | 3.4 - Casting Under Water Procedure
05a6025f-a9b5-5e14-bbe1-4dd9b44f8f3a | note | Reference - 606.06 (a)
1c247ad7-b765-59d2-99f0-dffe26b1a76b | note | Acceptance Criteria - Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
06968a4a-6c01-5a57-b2f9-7335e01110fb | textbox | Enter: Teambinder Approval number
7bf4a4f1-778e-54b4-aa6e-3e57e4a1bfe4 | note | ○ Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
7cde3292-b272-56e1-9ab3-5c1143a4a789 | note | Method - Document Review
4b296a1a-4e9e-56cc-9dac-c726152f1ffc | note | Frequency - Where applicable, once, prior to placement of concrete
432affb6-ab59-502b-a1c5-d87cb131ce10 | note | Category - HP
7a220726-1e35-5070-b287-9cec8035f1d5 | note | Responsibility - Nominated Authority
939e5c24-1fe1-5129-aeb9-f8c57a9c36fe | note | Verifying Documents - This ITP
808f3baa-501a-53bc-b73d-504354f53fdc | date | Date Completed:
d366c28e-d89f-4cae-985d-6ad815e7a380 | signoff | AUTHORITY HOLDPOINT
fb413da8-d28f-4117-a7e4-391a89c0ed62 | checkpoint | 3.5 - Boring With Bentonite or Polymer Fluids
e33a1201-e720-581d-abaa-9529c77877f0 | note | Reference - 606.03 ( c)
ec555f05-f596-5ead-8426-da4872762ed2 | note | Acceptance Criteria - Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
36a63517-8e7a-591d-91bb-439f2bba7340 | textbox | Enter: Teambinder Approval number
88ea303e-31a4-5ca5-b5de-a2b8d86d8e04 | note | ○ Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
90c8fa09-49dd-577f-a876-24ed07aa25cc | note | Method - Document Review
70732512-e415-59e3-8904-c26699f4c7f9 | note | Frequency - Where applicable, once, prior to commencement of boring
624dfdfd-3f69-5c5a-9a61-4ce93752f9e0 | note | Category - HP
3dbe9a75-4609-58d3-b6e6-d781e37d9f86 | note | Responsibility - Nominated Authority
acec52cc-c0b3-5e31-b21b-606d3cdd4ed2 | note | Verifying Documents - This ITP
ad01f302-b516-508d-ab82-7d155a445490 | date | Date Completed:
11d4db93-8bc6-4d78-86b4-78d59937263b | signoff | AUTHORITY HOLDPOINT
28930036-1817-4092-9ec6-71b9774a6e5d | checkpoint | 3.6 - Dynamic Pile Testing Procedure
66b93091-a399-5acb-b276-967510aa0c72 | note | Reference - 606.07 (c)
e6863808-d777-59d1-bab5-8aa5710062cd | note | Acceptance Criteria - Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
f8942d27-73d0-51b2-98cf-57a3764a1c8a | textbox | Enter: Teambinder Approval number
1d051190-9046-59c3-b678-bde8daae7c79 | note | Method - Document Review
d812e13f-0b2d-571f-a4fd-fca0d21a200f | note | Frequency - Once, prior to testing
ba5d51b0-e9cb-5133-9441-68083f701cf7 | note | Category - HP
ff1c930a-dddb-55e5-848f-f6d39d0337a6 | note | Responsibility - Nominated Authority
a7c3f992-0a24-5592-bb22-07ead6350ca5 | note | Verifying Documents - This ITP
a2af0b20-a773-56a1-ac61-01dfaee975af | date | Date Completed:
7b12569d-f47a-4ace-ae3c-893e4d8c878d | signoff | AUTHORITY HOLDPOINT
49ec6d3b-a9cc-4136-9ff0-e27fc9d5cc8e | checkpoint | 3.7 - Pre-qualified Pile Testing Consultant
289f5942-237a-56fd-bc0a-e9c6c111c1fa | note | Reference - 606.07
82b2043d-c12e-5ad5-ab64-d0f788ec17b8 | note | Acceptance Criteria - All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
56e26c17-e232-5c8f-ba72-600505ca6a02 | note | ○ Details of the consultant to be submitted for review to the Nominated Authority.
d594aed8-94ee-58dc-902e-a3c7e07b96ea | textbox | Enter: Teambinder Approval number
c54ca3e8-2fda-5ddb-aef5-77d0b5274527 | note | Method - Document Review
8ee7c736-19e2-5e16-b551-f48c05654d0c | note | Frequency - Once, two weeks prior to testing
c2a0f2ab-1d7a-560a-a238-5eeda1242711 | note | Category - HP
b2b547a3-c0e3-5117-a2bc-ef75c44e8b2c | note | Responsibility - Nominated Authority
3ea392b6-1134-5668-a359-b61fc4925663 | note | Verifying Documents - ConQA Hold Point Release
7ad8e40f-0cf8-50bf-88c6-6a3155599338 | date | Date Completed:
98a1b66a-e671-49c1-8a57-69740f12fd63 | signoff | AUTHORITY HOLDPOINT
3d5a6d1b-a47d-47e2-8ccd-40d31710df73 | checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
f77e75e3-26b3-5010-b28c-c58d3d03fbb7 | note | Reference - 611.13 (a) AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, AS/NZA4671 - 2019, 611.14 (b)
af8bdc6c-5e10-5c7c-a1bd-e58c7dbee528 | note | Acceptance Criteria - All welding procedures shall be provided to the engineer and proof engineer for review for compliance with the design requirements.
ee61139d-b3a3-513b-9273-14ed305eabd4 | textbox | Enter: Teambinder Approval number
a0552a58-a0f9-50af-9bcd-1e26bc8c4d87 | note | Method - Document Review
a807f55e-fdb1-5304-8d82-225dc833c30c | note | Frequency - Where applicable, once, prior to welding
66184b63-37bc-564f-be0b-bba19d157fb1 | note | Category - HP
9446e6de-66be-5a63-9ac0-9a544d233b4a | note | Responsibility - Nominated Authority
6c595c7d-4ac3-5ff4-8b3d-ec31c83af1eb | note | Verifying Documents - ConQA Hold Point Release
41ba0435-c7ce-52e6-8b36-c1c2b1dfe435 | date | Date Completed:
b7250bda-b246-42b3-8f80-09be98bf4c77 | signoff | AUTHORITY HOLDPOINT
818985bd-e7af-4582-8bce-83c4435b965c | checkpoint | 3.9 - Reinforcement Welding Specifications & Qualifications
29879417-1145-521c-b9d0-0457838af784 | note | Reference - 611.13 (a) & (b), AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b), AS/NZA4671 - 2019
c914d3bf-182f-570e-9696-de977cab47c7 | note | ○ IFC Drawings
fa72bc68-4972-58eb-99bb-f5a84fe8d043 | note | ○ INFRABUILD SENSE 600 WELDING GUIDELINES T05A V0.2
046156f4-72b9-5ca9-9fd2-4c0c0c80d3e0 | note | Acceptance Criteria - All quality documentation and test results to support the prequalification of the welding procedures shall be provided to the engineer and proof engineer to demonstrate compliance with the design requirements.
6660adc1-f04c-557e-a537-f85c0236e24b | note | ○ This documentation, along with the engineer's and proof engineer's endorsement, shall be submitted to dtp for review, prior to commencement of welding reinforcement to be used in the structure.
321931cf-d72e-53df-8ca4-3737d57a21e6 | note | i. all welded splices for sense 600 reinforcement shall be prequalified to as/nzs 1554.3-2017 and the requirements of section 611.14(b). welding procedures and itp shall be developed following the guidance in the document titled: infrabuild sense 600 welding guidelines t05a v0.2.
00a2dad4-94e7-5e10-9660-ddcdaa654b34 | note | ii. engineer and qualified welding personnel shall be engaged to develop welding procedures for the welded joints of 600N reinforcement bars for hopkins road bridge, and to propose testing programs for the welded joints;
85e2dd29-f76d-5495-bf23-bf48a94df998 | note | iii. testing of welds shall be performed;
e98d5c1d-9340-542f-b03a-79291d099af5 | note | iv. the testing results shall be reviewed by engineer and demonstrate the testing results meet the design requirements for the welded joints;
6b4d96e5-780a-5743-9f51-bd16c16ed54c | note | v. the satisfactory weld testing evidence together with the engineer’s assessment shall be submitted to dtp for review (not endorsement)
0c4e4ad7-f5ac-52a8-8837-7ba288abec42 | textbox | Enter: Teambinder Approval number
81c4f894-0ea6-553a-9b22-dbf25846efb1 | note | Method - Document Review
5e1d8bd1-1fff-58f7-b224-d2d0e3aa2abb | note | Frequency - Where applicable, once, prior to welding
796dd0ea-7480-5fd9-bb03-4323788aa4f9 | note | Category - HP
713e8882-ac10-5c7c-8732-fc5e08c6e93f | note | Responsibility - Nominated Authority
acfe9909-8cec-53ad-93d5-ab28bd39d748 | note | Verifying Documents - ConQA Hold Point Release
4485ead9-b956-5cdc-9965-514d27a8bbbd | date | Date Completed:
d731e828-6265-4aca-9578-f31c518e2441 | signoff | AUTHORITY HOLDPOINT
58ffc438-8b4b-4070-bae9-e130776625e4 | section | 4. Pre-construction Activities
008c6625-21b8-4c7a-bdff-5e9f17ff8e2d | checkpoint | 4.1 - IFC Drawings
6ae12a0d-15a8-55ec-9501-6ea7d3ebbb28 | note | Reference - MRPA Quality Management Plan
e31067c5-5c5a-5095-a6c3-69faf3da9142 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
0e758f3d-e290-518e-8123-14d709246ffd | note | Method - Document Review
05dfcf0b-ba1f-5b99-8ba4-071cdc567996 | note | Frequency - Prior to starting Works and at regular intervals
3032127a-cc5b-57f3-bc82-58c03bd065e0 | note | Category - HP*
e501781a-83ef-5456-8660-787aaebcf799 | note | Responsibility - All
666192c3-6bdc-5d91-9bba-14f8970bc5b6 | note | Verifying Documents - This ITP
0f2127c3-8ec4-595f-8f31-1827e55691af | date | Date Completed:
05b08fbf-9ceb-45a3-8485-2536c509fe30 | checkpoint | 4.2 - Survey Set-out
021b3020-45b0-58b8-b129-3d3381e34ed1 | note | Reference - IFC Drawings 606.08 (a - c)
1a1ef5f8-43a8-5b9c-831c-9acff94311f0 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
d83cce23-cf34-537b-9c12-e6cba42e802d | note | ○ Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
5bc9cdc1-d064-530d-870c-10993f495f6e | note | Method - Measure, Visual
44a6bc68-d5ba-5980-842d-ffa123f2f41b | note | Frequency - Each pile
3bf9d458-bd05-5355-9712-7f992ed9d500 | note | Category - IP
f68a316e-524d-5030-b518-56d747a3404c | note | Responsibility - Surveyor, SE
39d45f63-b1fd-5fe7-8f8e-92e1c35d90da | note | Verifying Documents - This ITP
eebf9e49-7ffa-587b-b627-2bfe85bbf87e | date | Date Completed:
359fd9f0-8f3d-4080-be4a-0e5eb079c988 | checkpoint | 4.3 - Protection of Adjacent Piles
9148c03f-0b9e-579a-bcbb-155599fa5170 | note | Reference - 606.04
f9baa542-b25a-56eb-9197-4c3d55298aac | note | Acceptance Criteria - Pile construction shall not:
4024deed-a8b4-5e08-b185-1c7dcd1aa437 | note | i. result in damage to adjacent newly cast piles due to ground vibration.
17061248-fa72-551c-b4f5-0e749a2f6834 | note | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
8b70cb08-7f37-5428-a36e-68a933ea1e74 | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
bbcc462a-48d9-5404-a348-5ed873454022 | note | Method - Measure, Visual
55ba716a-0835-5c65-b97d-0a279111b3b3 | note | Frequency - Each pile
9ee3b00d-8036-5eee-8917-a35328d31e79 | note | Category - HP*
d13d4a08-7b5a-582a-b42e-a53e60173fd9 | note | Responsibility - SPE/PE
3feaf016-0867-5bfb-8b49-1231ecfda718 | note | Verifying Documents - This ITP
89301bcf-f631-5e46-a0c0-699fb3ab191a | date | Date Completed:
682cd337-3ea2-47f1-aed9-24889dacca42 | section | 5. Construction Activities
7f22658f-7d61-4924-9c93-47a00fc4fe53 | checkpoint | 5.1 - Boring Operations
7a44ffb0-17b3-5e19-b8ed-b367f3d8495d | note | Reference - IFC Drawings 606.03 (a)
43644638-5b72-5d29-a0ed-9a2bb654cff5 | note | Acceptance Criteria - Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
e9528081-c83a-5b43-8d33-8d0b5418a268 | note | ○ Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
0f54c267-be2d-542b-9e3f-f43ed2a1de17 | note | ○ Excavation clean and de-watered (where applicable) for inspection.
25573217-35c7-5a00-9b99-5eae9f068213 | note | ○ Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
d5fa6300-f86e-5614-bef7-0968519ae214 | note | ○ Excavated material to be disposed of as appropriate to maintain a clean site.
a7db7699-306b-514c-aee1-90f705ebd5a6 | note | Method - Measure, Visual
c0f9222a-cf44-507e-a362-dc19e3d99400 | note | Frequency - Each pile
c365af4c-b2ac-5666-8a5a-f50c6debc19a | note | Category - IP
bd033ef8-da0d-57d0-a442-6cd77b6bed74 | note | Responsibility - Surveyor, SE/PE/SPE
8f699a52-df83-58f5-b994-b2fc603f94a1 | note | Verifying Documents - This ITP
f067e808-ebc8-581f-afde-bb4334c1a9da | date | Date Completed:
f0396bcd-8b0e-4c9b-b87f-f261a1cbc0d0 | checkpoint | 5.2 - Formwork Extension
96f796e1-5bfb-516a-9ae2-66455584d06c | note | Reference - IFC Drawings
42a8aa4c-9478-5918-b8d1-a3189163ecd2 | note | Acceptance Criteria - Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
0cfa499c-175e-5fd5-9800-b25e2e5dc44d | note | Method - Measure, Visual
df51652f-d394-5acf-a2a0-fe5124f7f758 | note | Frequency - Where applicable, each pile
8fde89af-2aed-56a4-868b-321759316e27 | note | Category - IP
3a31f642-f125-5ff7-899f-c85ff4daabba | note | Responsibility - Surveyor, SE/PE/SPE
1c5dcd22-366f-5900-9cb1-4732e69b7305 | note | Verifying Documents - This ITP
523208d1-21ab-50f5-aa15-102dd6f40d75 | date | Date Completed:
0ca780ff-dfa3-4a51-b7a0-554a534be692 | checkpoint | 5.3 - Inspection of Pile Excavation
2c5ea31d-f518-5546-a34b-47d0207912a7 | note | Reference - 606.05
fd4176d8-fa13-56ea-bb6a-3c81969d26f0 | note | Acceptance Criteria - Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
cfa96dcf-4a79-5841-9b0e-481391f978d7 | note | ○ Attach: Geotechnical Field Sheet or Report
21b87232-291f-5425-955c-b916c42b0200 | note | Method - Measure, Visual
b6e9cf94-5b5d-50d6-82ea-df55f63d001f | note | Frequency - Each pile
0b2518fd-c308-585c-98ad-37db59a71bb5 | note | Category - HP
6d9ce0f6-5d24-566c-9ee8-4015f4880ba1 | note | Responsibility - Geotechnical Engineer
e0bce37f-37e9-55ad-b3c9-cd238b22f54a | note | Verifying Documents - ConQA Hold Point Release
569fcff0-4bdd-5dbd-90ea-bc5ce0c73d4a | date | Date Completed:
0c142048-259c-4456-a764-1a30e5232a4e | signoff | AUTHORITY HOLDPOINT
59a53835-95ad-480f-9533-d3e238c80d39 | checkpoint | 5.4 - Reinforcement - Placement
bc97b580-8780-5694-b955-4cc346eea005 | note | Reference - IFC Drawings
0fd96c10-8f63-5fea-b208-34364ead9040 | note | ○ 611.06
41b7d5a1-e5c5-5cc4-97e3-cd493623ab05 | note | ○ 611.09
aa22ddb8-1a47-5734-97d7-a23fd3f679ea | note | ○ 611.10
4da27a2e-a053-5df7-a3e3-b62a0d9627e8 | note | ○ 611.11
535cd92b-64d0-5fcf-8824-806db5407e20 | note | ○ 611.12
caebc203-172f-5a41-bea9-731a222ab893 | note | ○ 606.06 (a)
f025fda9-4673-5a91-a1e6-4add5b173777 | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
38781b86-38a3-58aa-a167-f3ac8c11e46a | note | ○ Projecting reinforcement is the correct length and location.
0af113fb-6ee3-5580-af97-37a14897bc64 | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
8b7a446d-dec7-58b5-8863-cc4ba1e2cd87 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
938635d6-a173-5a2b-a21d-9d321116cace | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
d1b7ddc1-f0cc-58bf-97c8-2924e38c95a9 | note | ○ Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
447a30b1-b541-574f-b06b-25a9119a84b5 | note | Method - Measure, Visual
1417fd68-8e92-5cb5-a8e8-31b1964aa89b | note | Frequency - Each pile
77af36f6-47de-510e-b8b3-904fe7d2f793 | note | Category - IP
ccc37bb1-4bd6-5de0-8051-642973a4f243 | note | Responsibility - Foreman, SE/PE/SPE
4274090b-76e0-5e73-a233-4451bcf3c793 | note | Verifying Documents - This ITP
463f2991-bdf7-5218-84e9-55c1b48814a4 | date | Date Completed:
1974e147-f5fc-418a-87af-a520ce160262 | checkpoint | 5.5 - Reinforcement - Electrical Continuity
1f9032a1-7073-598a-8ea0-c2a12cec7c98 | note | Reference - IFC Drawings 610.29 (d), 610.43, AS/NZS 1554.3-2017
4f261b5f-950f-5f9a-ab44-8c26bffb00cf | note | ○ INFRABUILD SENSE 600 WELDING GUIDELINES T05A V0.2, 611.13 (a)
b3fe3ead-aafe-575f-90f2-19d7e75a1d9a | note | Acceptance Criteria - Pile reinforcement cage to be made electrically continuous by:
5dac5a8a-0595-585f-a5cd-54b6634eceee | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
2ea03308-768f-57b7-8e19-84bd8fcf8102 | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
ab68f9d6-e207-53a5-ac45-6d6b886e0386 | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
943d93d2-6fc8-577c-8418-701cf5020913 | note | ○ Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
efed0e10-7086-5c8f-add8-168db52cb489 | note | ○ Welding of sense 600 reinforcement shall comply with the requirements of dtp specification 611 and as/nzs 1554.3-2017 with the following modifications:
d127c404-8b3e-5e59-bb30-7ae3374858f3 | note | i. tack welding of sense 600 reinforcement is also permitted, provided welding is not within 50mm of the tangent point of a bend in the steel.
3d51d1bb-edf1-53aa-8ee9-fc6e7ffa9882 | note | ii. all tack welding of sense 600 reinforcement shall be prequalified to as/nzs 1554.3-2017. welding procedures and itp shall be developed following the guidance in the document titled: infrabuild sense 600 welding guidelines t05a v0.2.
624b80b7-4d19-5ca5-9b32-ba09f5345240 | note | ○ Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
2a62a485-4e24-5df6-926b-700f528be1fc | note | Method - Measure, Visual
027fb058-1fed-5da7-9a41-56029faaea3d | note | Frequency - Where applicable, each pile
0a0a0e7b-0f25-5c1f-bbc8-da33b46082d1 | note | Category - IP
62a9abec-b663-5750-ae3f-e78d49a4bf7b | note | Responsibility - Earthing Engineer, SE/PE/SPE
4fed5057-5f94-5305-a0b7-145f52da2d3e | note | Verifying Documents - This ITP
fb77c5d4-c670-5eb1-b167-02ab6cb3aa4b | date | Date Completed:
ce25078f-5ed6-49b7-b668-92cd8c1c4f3a | checkpoint | 5.6 - Cast-in Items
f95d712d-8005-5cd4-82a2-c6505bdd197e | note | Reference - IFC Drawings 610.46 (a) Table 610.462, 610.47 (a) Table 610.472, AS3810.1 Table 3.3.6.2
731dde4c-32d4-54aa-9f22-e0dafb320cdc | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
47749d1a-d647-5547-ba36-58ab325e91c8 | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
d3a09e91-8f28-5ffa-8a45-cf03e93b976e | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
ed50d5f1-bac6-5b12-85e8-438d7d35203f | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
808151f2-97dd-522f-8fed-87862c86460d | note | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
e314008a-98a7-5bdb-afc8-fadb00403d0c | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
63aec4ee-11bc-5633-a994-9e3061d6aa6c | note | ii. Running dimensions of a group of the above = ±6mm
0a17666f-9779-5315-b728-c4bceff0b360 | note | iii. Ducts and conduit location = ±12mm
9d9285b2-7482-5ada-88f9-2f2b4b6e76c6 | note | iv. Diameter of ducts and conduits = ±3mm
ac8098e3-eb06-5f06-a594-9fa62201a2ae | note | Method - Measure, Visual
10fdf347-8134-578c-b9f2-292fa250bdcc | note | Frequency - Where applicable, each pile
9f9d9bc5-9df8-5d68-8887-7b46a32e700b | note | Category - IP
9f59276c-16a7-5506-a4d8-734368b1b949 | note | Responsibility - Foreman, SE/PE/SPE
4bb8e10b-0ccc-5ad1-8fa9-af72c7186de5 | note | Verifying Documents - This ITP
1f4add4c-d90c-55c9-9d6a-0c5ea4f058bc | date | Date Completed:
4ce0f494-e7da-4c48-8774-4b4bc6ab9d05 | checkpoint | 5.7 - Pre-pour Inspection
4162199e-aa3e-512f-bbbc-9f60daed9511 | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
b634e40c-9bb7-5047-bfd0-26d8874566dd | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
38435c47-b04f-5ab1-8088-9d3c160a304d | note | ○ All foreign material has been completely removed from the excavation.
dc0844ff-a6cd-5d7f-9f7d-ca1879df4209 | note | Method - Measure, Visual
6082567c-4a15-5937-882e-e63bcc5af70d | note | Frequency - Each pile
cc06bba1-ebcb-5f7e-bc32-2f75dd1e066d | note | Category - HP
ea2fb340-adc9-53eb-b1f5-cd0a510668e3 | note | Responsibility - Nominated Authority
d259e516-6154-51b0-9620-7ddf7c0b54e6 | note | Verifying Documents - ConQA Hold Point Release
2016fcec-11bd-5c43-a3c5-c90a05bf8d1b | date | Date Completed:
270f3ab8-82fd-426d-bc9a-98e6b6167716 | signoff | AUTHORITY HOLDPOINT
7a3a5012-5e0a-448e-9c63-959f67576e8d | checkpoint | 5.8 - Weather Conditions & Evaporation Limits
d472fab5-083c-5c61-bcf6-5fb602d50465 | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
9d3be867-faed-590b-8cf4-b17e1e9df27f | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
e23fc149-8fc6-5e5f-b798-cecfc54169a5 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
0bf73d9d-2550-5f67-9f1f-5f9c0069b4e8 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
9e2ac2e5-5249-59cc-9c5b-233ac7fa850d | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
f5430eaa-5028-5f62-88c4-9fea182d34f2 | note | ○ Record: Required information on the Concrete Pour Record.
2fb252a5-42b9-51dc-b4e2-cdf550e6bf41 | note | Method - Measure, Visual
9a237e96-6fbc-5de0-8fa2-6dbc5a2de652 | note | Frequency - Each pile
4bd86ca6-ae1a-5283-9ce1-5603180d0c27 | note | Category - IP
17a8cb72-3153-56d0-89be-4953d16d9a22 | note | Responsibility - Foreman, SE/PE/SPE
c68372e3-1686-5743-8a92-906e65f0ad17 | note | Verifying Documents - This ITP
e5ade6f6-e3cd-5297-a565-b108f2329c21 | date | Date Completed:
7cb154d3-9a0e-4238-9b1a-6c8078ff5188 | checkpoint | 5.9 - Concrete Testing - Sampling Frequency
4e3aa563-4e9f-56ad-b3d6-eca990c0761a | note | Reference - Site Sampling & Testing Procedure 610.16 (b) Table 610.161
bee8d70e-e559-5674-a58a-ef16345216ac | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
f37499c2-b822-542a-bff3-644843d57fac | note | — 0m³ to 10m³ = 1 sample
acef3b04-352d-5cb8-a508-92e2c4742019 | note | — 10m³ to 25m³ = 2 samples
cdbbf6b0-e6d9-5dda-b722-98b27c1d7aab | note | — 25m³ to 50m³ = 3 samples
5483c4c0-44ab-5639-9476-ab9b5ba69c6c | note | — 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
7854f0cd-10bf-57bf-84ab-ab4f4421ef1a | note | ○ For each additional 50m³ and additional sample shall be taken. where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
234f9123-2f6b-5660-b450-9ca7508609e7 | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
0486524c-2706-5575-bb8c-7096613f3c7d | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
7b33168a-11c6-54b3-9043-5124dd473f74 | note | ○ Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
3baf7df8-d2a5-585b-8f26-9e022ef8e02f | note | ○ Record: Required information on the Concrete Pour Record.
394c5639-ee99-514b-b8b2-4a81ae4001b2 | note | Method - Test
0585b734-077d-507a-a127-5491eca1f70f | note | Frequency - Each pile
8a33c2f9-1f1f-5258-a57e-3c594c3771ba | note | Category - IP
84a41b28-fbc4-528b-af5c-af912c5c8a5a | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
bf6006cc-0413-5bf6-8919-fb55d5c9b25a | note | Verifying Documents - This ITP
9361deca-cd24-59f5-9832-a5a87624ba34 | date | Date Completed:
9c9da6b0-928f-4c2c-b4a0-1f59c95a8826 | checkpoint | 5.10 - Concrete Testing - Spread, Passability & Viscosity
88a0e311-71d3-51de-9829-7f98a8d957b6 | note | Reference - 610.13 (b)
7f653d78-6477-5c9f-9d07-0ac3b3a72159 | note | Acceptance Criteria - Spread range = 550mm to 750mm
cba3894c-287c-5edb-bfe3-d5949ffd354b | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
e4a906b6-e788-5714-83f1-6348db5f8f40 | note | ○ Passability = ≤10mm (aggregate height differential)
a77dd000-9769-546f-92f0-082f06180d5f | note | ○ Record: Required information on the Concrete Pour Record.
a48f0cd5-69e9-55f8-95f1-a40818010efa | note | Method - Test
76d74886-11e1-51c3-8cb6-17c55cebf933 | note | Frequency - Each sample of Self-compacting Concrete
dfc136aa-893c-5f3c-8e0b-1dc6b35ccf10 | note | Category - IP
3e720429-e40f-5c8c-ab8d-0d5be475691d | note | Responsibility - Concrete Tester
3db4883d-830c-55c8-8811-2d562a25e93a | note | Verifying Documents - This ITP
a99613d2-efff-592f-8a8f-ea75c2c9c4d5 | date | Date Completed:
b7c43e1a-f7fb-4eee-8b90-8784dac9b3b6 | checkpoint | 5.11 - Concrete Testing - Compressive Strength Cylinders
ceaf28c9-e73f-56fe-849b-dd6d8a0d60ec | note | Reference - Site Sampling & Testing Procedure 610.16
94674322-0d7d-5eaf-a9e3-641f3a000a6a | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
5dc66a9a-f2bc-5e11-8e39-da9003804358 | note | ○ Record: Required information on the Concrete Pour Record.
a395c78e-1949-5a1c-93d0-69766d569498 | note | Method - Test
1fb9b52c-9fa4-533e-b761-eb3bda789e2a | note | Frequency - Each sample
4a76cfb4-df0c-58e0-8548-ed45e2ae59c1 | note | Category - IP
11ad10f4-aef3-54b0-81da-1e76f5507917 | note | Responsibility - Concrete Tester
3328d772-430d-53aa-9462-790d6a46ca20 | note | Verifying Documents - This ITP
f666a8a2-ee9c-5097-a353-80fbe05d37e1 | date | Date Completed:
cd058e7c-847d-4d9e-8123-c82cd88f3163 | checkpoint | 5.12 - Placement & Compaction (Dry or Wet Excavation Conditions)
4536232c-609c-57bc-978f-da958046ba27 | note | Reference - Piling Quality Procedure 610.18 (a) & (b), 610.18 (d) (i), 606.06 (a & b)
97d232f2-e135-5183-8ba7-aa2cbc5c4cc9 | note | Acceptance Criteria - Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
efc0ee27-dacf-5bca-9b1b-4c2c771b8214 | note | ○ All concrete batches are traceable.
7e3ee56c-4333-56c9-bfff-0aa276aa3e89 | note | ○ Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
dea5699b-9f6c-5554-a2de-a67dce5217d8 | note | ○ The initial discharge is pumped to waste until a consistent workable mix is discharged. The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
895bd677-20de-59ab-a2b9-423e52220065 | note | ○ Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
8f850b98-ae64-5a0c-a972-688303b987e5 | note | ○ Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
939eaf88-ccf5-529a-a830-dd4e4b159585 | note | ○ Record: Required information on the Concrete Pour Record.
ffc52eb4-7e2d-5869-80fb-fef8ce5c6d0e | note | ○ Attach: Concrete Pour Record
3bd34256-4e85-5863-b7df-612132ba3ccd | note | ○ Attach: Concrete Dockets
37d64927-f933-502d-9afe-bde24c32cd02 | note | Method - Visual
694d4f0c-294a-5ef6-8038-2cb29c1b8367 | note | Frequency - Each load
9965336e-a92d-5a9d-940f-ffc24614c103 | note | Category - SP
a1fba3d5-7595-59af-bc05-23c045bb40f3 | note | Responsibility - Foreman, SE/PE/SPE
97f72796-bcab-5673-8777-165fc52975e0 | note | Verifying Documents -
dd8c321d-47b2-5a78-8209-9e39ba122c13 | date | Date Completed:
204221bc-0373-4871-8deb-bace4c5b9d81 | checkpoint | 5.13 - Surface Finishes
29aa5b23-2743-53bc-86b9-ab678b9e7b18 | note | Reference - IFC Drawings 610.31, 610.20
3cbefb4a-80e4-58de-8b88-83e6e646273a | note | Acceptance Criteria - Surface finish as per IFC drawings.
6c5afa05-b354-56d3-bb81-9034c378021e | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
7fe0096c-3b39-5d02-be55-5c75ea7e72e0 | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
76cb6796-14c7-54eb-acf4-dedeb6d9fad2 | note | Method - Visual
da6c298c-28e3-52f5-8c45-47afccf86af2 | note | Frequency - Each pile
e385e903-f184-5c6c-ae42-ecbb5ed69adb | note | Category - IP
706d61a1-9a3f-5d13-9b52-b9ba96df0948 | note | Responsibility - Foreman, SE/PE/SPE
316e5391-1fd6-5238-9a8b-330de3dd81e1 | note | Verifying Documents - This ITP
91fbd652-4825-581f-a246-55cec79c0d42 | date | Date Completed:
470b2d36-bef5-45e7-9a18-a13b1c1194d4 | section | 6. Post-construction Activities
188a15ed-d03f-4d2f-8cc3-b84e062bc83e | checkpoint | 6.1 - Pile Trimming
36b3b364-b27d-5526-a46d-a7b675f8d787 | note | Reference - IFC Drawings AS2159 Clause 7.2.2 - 3, 606.06 (a & b)
08e3d220-d263-5f64-bb82-475f9a20a317 | note | Acceptance Criteria - Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
940eb522-76fe-5332-9e9a-2ba9ca299303 | note | ○ Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
00055e4b-4afa-53eb-8bb0-5fa623684fcd | note | ○ Any weak or damaged concrete shall be removed back to sound concrete.
319aaad2-84a5-5ee0-8d71-d81ae66576de | note | Method - Measure, Visual
a59e2e55-80f1-51b1-bebf-bde320fa6a9a | note | Frequency - Where applicable, each pile
e6a36595-f4a6-5147-97ad-2e1115d2562d | note | Category - IP
e0d1793e-7a18-59fe-b130-b8fa64a9c1a7 | note | Responsibility - SE/PE/SPE
7f036ebc-c1fd-5aa5-a027-3d97358cdfa2 | note | Verifying Documents - This ITP
8dd442e1-9b29-5243-89ab-1d6b1a405b9e | date | Date Completed:
0f74e2b7-ff1b-4dee-ab31-4482ef4f98bb | checkpoint | 6.2 - Compressive Strength Test Results
274d7072-4c3d-5a89-a790-c411b7aacc6c | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
95a6d0d0-3a64-5886-a60d-944e80d066d6 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
9867a4f3-5ab6-57d0-b497-0ae3fc246fee | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
2fc2d75e-8897-5778-97ee-8d16bd22c8db | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
51d5ff7f-1f7d-5a7b-8f22-486c2d91a94c | note | ○ Attach: Compressive Strength Test Results
30536357-9afc-5e93-b8b5-267d9931b31c | note | Method - Document Review
67e2d6e6-5001-53e0-b95e-b25c7e3af658 | note | Frequency - Each cylinder
2bfb38ca-315d-5645-a9ce-de714e79f18c | note | Category - IP
55a114e2-d7ab-5ec0-9e6d-12f611327684 | note | Responsibility - SE/PE/SPE
f4d2c539-d90e-5dca-9f06-7891ecd72d2f | note | Verifying Documents - This ITP
d7d9a1c1-fcef-5673-b448-11e493e3a53a | date | Date Completed:
a7560c3a-f991-4220-bc13-804ca55745b8 | checkpoint | 6.3 - Pile Integrity Testing
7b3cd08a-6d23-5ec7-95c7-fb94ff253d8a | note | Reference - 606.07 (a, d & e), AS2159 Clause 8.8
8f36db14-6e18-5370-998f-9a162e99c5ff | note | Acceptance Criteria - Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
bd23cd2b-1d10-5943-9e66-9bb460e2bacc | note | ○ Cross-sectional area = ≥95%
2b71cea2-ef88-5327-b0f3-ba51b26b4db6 | note | ○ If any test fails, all piles shall be tested.
0e53e1cc-a819-59d0-b363-471c314feb97 | note | ○ Attach: Pile Integrity Test Report
b9fd144a-9db3-50b5-8582-dcce3650bcda | note | Method - Document Review
28470b63-d472-50a7-babb-1a7f5aab3094 | note | Frequency - Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
f916e548-6fd7-538e-b0de-bbed932b817f | note | Category - IP
5fe1b7f8-7c4a-5e5f-bb9b-cf67e2239877 | note | Responsibility - Testing Consultant, SE/PE/SPE
df0569b2-4537-5493-85c9-7a26546e0bce | note | Verifying Documents - This ITP
d12d943b-7902-5f57-9d4e-6121e591257f | date | Date Completed:
a4f99f2d-e013-481a-a2b8-1b8ce9135a29 | checkpoint | 6.4 - Static Load Testing
8d24b57a-f77e-53d9-9798-f59350a9502c | note | Reference - IFC Drawings 606.07 (b, d & e), AS2159 Clause 8.4
e08d6c97-9897-56a9-9f0d-c2842ccc6b79 | note | Acceptance Criteria - Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
b4e67429-fb59-53b9-ab83-e692cedc9206 | note | i. Displacement vs Time Graph = linear or decreasing rate of creep
fac11596-2f39-551b-9406-6a46698f921b | note | ii. Creep rate = <2mm / log cycle of time at the test load
efe5746c-fd57-5203-abc8-244a4c3e5f92 | note | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
57413ecc-221c-5f16-9a25-247556539cee | note | ○ Attach: Static Load Test Report
3d4450af-a055-520f-8edc-a9a2bcc39e74 | note | Method - Document Review
b4a80dd3-aa9c-5388-87cc-829b2c5780a7 | note | Frequency - Where applicable, as shown on the IFC Drawings
e2d5eb67-0649-5a00-b8fc-72771eb274fc | note | Category - IP
4bb8af98-c829-5ea9-9aed-f78a49d73456 | note | Responsibility - Testing Consultant, SE/PE/SPE
f2f4c06d-b534-5371-90ff-9fac6626b08e | note | Verifying Documents - This ITP
ee3b8723-77d0-59af-b6b0-9c49d6c31fa9 | date | Date Completed:
5d5dfe64-605f-4129-a144-5f8546eb4294 | checkpoint | 6.5 - Dynamic Pile Testing
98d3f218-5c96-5a78-b749-acd61d538b20 | note | Reference - 606.07 (c, d & e), AS2159 Clause 8.7
f6b0dc19-405b-5016-ba88-5ed7d1b99633 | note | Acceptance Criteria - Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
ca04f363-6ffd-5f5d-b832-8f7a37f03b07 | note | ○ Measured Ultimate capacity = ≥ values on IFC drawings
a4f09cd5-e32a-527b-91af-b87aff1ea245 | note | ○ Attach: Dynamic Pile Test Report
e22f7d2d-a618-5ff2-aded-59bf4a8754a1 | note | Method - Document Review
d30a263b-5455-596b-988a-00a93266d9c8 | note | Frequency - Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile.
128a1d13-6303-51ab-86cd-eb727bb7d820 | note | ○ At least 1 test per 10 piles
f8af054a-eadf-5df5-b957-e7bb4baf8fef | note | Category - IP
91c40eae-6170-5c75-bdef-7ec26b2993c8 | note | Responsibility - Testing Consultant, SE/PE/SPE
118437ce-a34c-5c7a-ae1c-bb7607969874 | note | Verifying Documents - This ITP
5506110e-c8ed-56e1-a427-2f5e6a7b2bff | date | Date Completed:
e3c35aba-2bfa-4042-9a5f-8a3cfdbaef03 | checkpoint | 6.6 - As-built Survey
6e318a20-2658-5828-8511-2c51cadfe6b4 | note | Reference - IFC Drawings 606.08 (a - c), AS2159 Clause 7.2.2
9e8ff9d2-e8f6-5c54-8081-73fe8b6d841d | note | Acceptance Criteria - The following tolerances apply to piles:
6856a286-8d26-5715-ba59-8827d7bdcfb0 | note | i. Pile head plan location = ±75mm
9958ac5e-62e0-5ddb-9b35-0d9bcad97016 | note | ii. Variance from vertical or rake = 1:100
079b2226-2ee3-503e-b207-0abd03c947dc | note | iii. Irregularities in straightness = 1:100
002647f4-38db-5696-b784-2dafd86a07dd | note | iv. RL = ±25mm
80e18fdb-5377-5760-8238-8cb774fc9451 | note | ○ Attach: Survey As-builts / Survey Report
1fdfa1c1-6eab-5a72-bb12-826fc0fe2aab | note | Method - Document Review
31ce3b03-2c41-5ad2-bf58-07140f778155 | note | Frequency - Each pile
d6d8f527-bd17-53f6-b70a-c72ae95ecfae | note | Category - IP
ffe582fc-adf4-5f79-b264-2672adddfe52 | note | Responsibility - Surveyor, SE/PE/SPE
3ad1b195-2394-5123-af15-96271e22ab8c | note | Verifying Documents - This ITP
75942f00-fe6d-5b26-9938-d83718374d15 | date | Date Completed:
04fe0240-738f-4915-a462-d6b2878d8254 | checkpoint | 6.7 - Non-conformance Report (NCR) Closure
9368d73e-ae22-5d38-a437-9304be51a982 | note | Reference - MRPA Quality Management Plan
b6299209-7868-5a97-8842-f1b569e58cef | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
5597176b-ec83-519f-a620-41e0fc0da9b1 | note | Method - Document Review
cdcdc959-2ad0-50bb-a04d-275d6a4c75ef | note | Frequency - Once, prior to closure of this lot / element / Work area
cc7321d2-89e2-5eea-aca2-5d2c03d60951 | note | Category - HP*
2a52a3da-1980-5667-96e8-bba3584f211a | note | Responsibility - SE/PE/SPE
15ab6cb9-e8b8-51f5-baa6-fabdc4225cc8 | note | Verifying Documents - This ITP
f103e00a-e798-51fc-8a85-598aad9f221f | date | Date Completed:
b366f4fa-5da3-4836-a16e-fde926c66458 | checkpoint | Final Inspection
37a5dcd3-6fa9-50eb-b8a3-18711fe12e62 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
01f28f57-42ca-5c64-8204-4566ee4c7fc3 | textbox | Name:
34ff540f-6160-58c2-b188-452e50b3176b | textbox | Position:
3d742a78-cb6b-5012-a53c-ab8881fa1b19 | textbox | Date Completed:
8a6eefad-bf9b-4fd1-bd49-a5d99393090c | signoff | Sign ITP
865a66b8-ba8e-4d22-8520-66645098cd72 | checklist | ITP-245-STR-HOP-Structural concrete sense 600 Rev 0 | itp | ITP-245-STR-HOP-Structural concrete sense 600 | 70d351ea-afa7-41d6-bba5-7e8ac5db14d5
18e1a7bf-4676-4663-81ec-faa46be91f08 | section | 1. Referenced Documentation
f1bbedc9-d0e4-490a-b5bc-9496e1a2a2f4 | checkpoint-no-value | Referenced Documentation
fb61d252-00aa-5a1c-963c-691b097bef00 | note | Document Title: ITP-245-STR-HOP-Structural Concrete Sense 600
1dba795a-9c65-5b03-9ae8-0be33dd1bf30 | note | ITP Description: Structural Concrete Sense 600
3f36a04e-0b8f-536b-8f26-0199e59cbbc1 | note | Discipline (e.g. CIV/STR/RAIL): 245-STR-HOP
47ff8544-d79d-5b6c-8df1-84a5e4677af4 | note | Revision Number: 0
bb383ac0-272e-5550-af91-cd354f7b402e | note | Revision Date: 3/03/2025
4fb15dda-092e-54fe-a057-ab0b55a515bb | note | ITP created by: Manwel Kalyana
498849e7-5ef1-5275-b858-296a1ae433f9 | note | ITP approved for use by: Pradeep Talasila
44a18ec7-8659-5a8c-9a73-d502cef9e823 | note | 1.1 - Non Dependent
81da99ff-9a94-5247-87ec-7de5a9cabb6e | note | Reference - VicRoads Section 606 - July 2017
583045b1-e158-5135-9da4-0f2eee60d8aa | note | ○ VicRoads Section 610 - Feb 2020
6adf137f-dfad-5e50-9ecd-220d98aa6169 | note | ○ VicRoads Section 611 - November 2018
d1ce98a3-790f-5ae0-ada4-b88274953922 | note | ○ AS2159-2009
2e18de07-d6d7-5b39-ab20-da2179d383da | note | ○ AS3810.1 2018
0e0a8cad-8bd4-5b1a-aea6-90cbaf5c207c | note | ○ AS5100.3-2017
e154deba-1300-5b8f-b3ad-217564eaa621 | note | ○ AS/NZS 4671 - 2019
90501035-474b-5eee-9632-4ab3703dc523 | note | ○ AS/NZS 1554.3 - 2017
642148ae-24e4-4e92-a2ed-d93aecb6023b | section | 2. Preliminaries - Materials
91ad947d-7a9d-4db9-9952-9022e3ee4f5a | checkpoint | 2.1 - Concrete Mix
3b654dbc-edf6-5021-9843-a7dfffa65377 | note | Reference - 610.07 Table 610.071 IFC Drawings
f15ebc7b-5302-59a3-8e83-837e65794a34 | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
2d2d4cea-d099-53cf-829f-f42a5edbaf0c | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
80372941-1ca2-5793-af9a-8b9f532aef53 | textbox | Enter: Teambinder Material Approval number
54ac01a6-c693-5ddf-95bf-c596116bdcc1 | note | Method - Document Review
1b84207d-2ab4-50f2-9852-e4ed40508049 | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
496bb61d-ba3f-5cb2-980b-3e6c540279bf | note | Category - HP
d84d1f00-1448-5c2f-931c-abddb804335e | note | Responsibility - Nominated Authority
6476f6c9-b92c-522e-9195-fbe4fd82ce3d | note | Verifying Documents - ConQA Hold Point Release
e9f2fa57-202d-5499-b79e-1b1fa210e1e3 | date | Date Completed:
e0bbabe4-c72b-423c-87df-759ffc6f31d1 | signoff | AUTHORITY HOLDPOINT
d38e4946-aca8-459b-99f6-b2281d4a1321 | checkpoint | 2.2 - ACRS Certification (for Reinforcement)
10def297-fcb3-5e8a-ba63-178cc857969c | note | Reference - 611.05 (a)
d3f15d69-4d35-5c27-bf54-fcd8727059b2 | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
81060539-2352-56fc-b2ae-2ec0ad71c426 | note | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
b56b86df-9027-5a45-b965-ff6a0f5a4a77 | textbox | Enter: Teambinder Material Approval number
21d3bdf0-ccf1-5ae2-a1d1-851516df2c03 | note | Method - Document Review
42ccbf09-8093-5d97-a4a6-5e5aa07e3eb7 | note | Frequency - Once for each supplier, 14 days of award of contract
1e8159e6-2332-5979-8ce2-1d40c95561a1 | note | Category - HP
39dafbcd-6d68-523c-96bb-b15025436585 | note | Responsibility - Nominated Authority
e51bbe66-2036-5af6-8275-1db9dee4849e | note | Verifying Documents - This ITP
12954e26-3c7f-54b4-9b38-6ed12a5ea844 | date | Date Completed:
3831aefd-6fc2-4af3-a665-45e3cecc2b88 | signoff | AUTHORITY HOLDPOINT
0d7faa95-4262-49ff-985d-17661b6d449b | checkpoint | 2.3 - Bar Chairs/Aspros Certification
f8e90704-6777-5f02-abea-8b36316bb7c1 | note | Reference - 610.26 (a)
62c2a705-0a97-5c2e-a7d5-c8259fcd4cd9 | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
2da28728-6063-5b7f-865f-cc2b00bd2a1c | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
7e4a0664-e7a8-5685-952c-523a5651c8c5 | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
a5341199-bfa0-5ff5-9d21-6b8c713132eb | textbox | Enter: Teambinder Material Approval number
1e8e4677-3c6f-5c79-9d0f-41f8ea4e1a30 | note | Method - Document Review
f63a0ba9-34f4-5cec-abed-bc1f846ae070 | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
00a99658-9788-562f-99a3-09f824e26f05 | note | Category - HP
c74c5935-9265-5b88-98ad-e9346f7f4b1d | note | Responsibility - Nominated Authority
b3aca1da-e0de-5712-9d00-3ab9a48424e7 | note | Verifying Documents - This ITP
cf70c8c8-21a2-53f3-b273-f5544bda809f | date | Date Completed:
fc2c50a5-593f-483e-b81f-a7b6d9054620 | signoff | AUTHORITY HOLDPOINT
3e6a9e83-e8a9-4789-9dd5-40aa790cc228 | checkpoint | 2.4 - Evaporative Retardant
1821733f-946a-5f9e-ae32-0d3bbd02c844 | note | Reference - 610.17 (f)
cc92498f-4eb0-5b94-a9bc-0bb4b7397dea | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
672057e7-636d-5079-85dd-58a2d25fbc04 | textbox | Enter: Teambinder Material Approval number
f06d31e9-88a9-5ab1-8e01-e6013b002faf | note | Method - Document Review
a451c505-ca36-54f1-8f3f-d40185301ec6 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
f60be708-0d45-5d39-b599-944e6f1be0d7 | note | Category - HP
16308f19-fdef-5afc-aa8f-0067d273b03f | note | Responsibility - Nominated Authority
c34324e8-07ad-59fb-b700-7b4ad4ae710d | note | Verifying Documents - This ITP
a7684ae6-9195-5e5f-82db-2b685849a87d | date | Date Completed:
c9b5e091-daca-43ff-8300-90a0b3fa50b5 | signoff | AUTHORITY HOLDPOINT
d93dcccf-7055-48f4-83ca-e3b718d6ad10 | checkpoint | 2.5 - Curing Compound
a2f185bc-7d36-5f63-a218-01449b633b1d | note | Reference - 610.23 (d)
22f995d5-c742-5037-8ab6-489d429b83e6 | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
b61d60d1-d6ba-5cb8-86d9-e8e8be2f7c95 | textbox | Enter: Teambinder Material Approval number
655dd05d-29cd-53b3-84b5-d397d8dad964 | note | Method - Document Review
31e2f158-2eb6-51b7-970b-b81543b2d961 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
991cf246-9da8-559e-b817-bc2e6c36d6a1 | note | Category - HP
3df513c2-49e5-59ac-8e69-6f09c839c22c | note | Responsibility - Nominated Authority
00005243-e244-541b-9d1f-75e3ad862b42 | note | Verifying Documents - This ITP
fd1bf793-3152-5dd0-a3c1-ef5428faa60e | date | Date Completed:
a52c719a-14d0-4503-9d8e-958a58d3fb2b | signoff | AUTHORITY HOLDPOINT
dd067810-b791-4da9-833a-c5a10bcaf6b2 | section | 3. Preliminaries - Procedures & Documentation
2c71724a-4e82-4bbe-93d6-46a815a01ce6 | checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
d8a2e0df-a1b9-5fbd-89aa-7926d249e5b1 | note | Reference - 610.18 (a) (i)
58aaead7-4524-5d8e-8112-845e8f0b3c2d | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
438cea15-1695-589b-985e-c2bda5eb60d6 | textbox | Enter: Teambinder Approval number
774627e4-53dd-53a2-87d1-fa4e2a8f34d8 | note | Method - Document Review
31ca3ca9-034c-5217-bbb7-aa9807831c71 | note | Frequency - Once, 4 weeks prior to placement of concrete
73eda991-9878-5ef0-bd86-1a60d1b107e4 | note | Category - HP
b49451ab-7820-50fa-a276-cba69b4aa461 | note | Responsibility - Nominated Authority
7756ed3f-a3fb-5bfe-a169-58e5511b4815 | note | Verifying Documents - ConQA Hold Point Release
b1c61a80-f881-576a-a524-082dc1b7be1b | date | Date Completed:
84534d0f-7f91-4e18-883a-179460fe31ba | signoff | AUTHORITY HOLDPOINT
2ec8ca55-cde1-48c5-8c42-34641b76e1d8 | checkpoint | 3.2 - Concrete Sampling and Testing Procedure
745ada13-87b4-5f46-8e25-369be6a7f583 | note | Reference - 610.18 (a) (v)
4eda39eb-68ab-58fa-8e54-8b139a520687 | note | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
5bc19190-db77-5153-887d-c568a67e1848 | textbox | Enter: Teambinder Approval number
5c19357d-68b5-5579-95a5-df2c79b916f0 | note | Method - Document Review
0b003d2c-2d63-5624-808a-49def4a826c2 | note | Frequency - Once, 4 weeks prior to placement of concrete
f0fa62a5-0d5e-5d19-8b3f-911b55e77105 | note | Category - HP
f0e2cd38-fe77-51ef-8ad2-7c6d6800e9ec | note | Responsibility - Nominated Authority
1d5e6914-1472-590a-a419-bc834b408a3e | note | Verifying Documents - ConQA Hold Point Release
691d88e1-9928-5b12-9d20-eb54ff61f9a8 | date | Date Completed:
4125fd22-0aba-4492-a327-6dcfdd3fca41 | signoff | AUTHORITY HOLDPOINT
22b76088-09a6-43ba-a53f-158a2d32d102 | checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
9c03d013-167a-5adc-8c75-62d2bff3617f | note | Reference - 610.18 (a) (iv)
4bcb08c2-ad07-5f00-80e2-621d522f311e | note | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
a387716f-01a7-51d5-80f5-4422752a8401 | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
aecb261d-355e-57ad-b2ed-0bceeddd539c | textbox | Enter: Teambinder Approval number
3f192f12-a5f8-55fa-b30c-4c066a98c1de | note | Method - Document Review
1f8f215c-1820-5a9b-aac6-139f77014cb4 | note | Frequency - Once, 4 weeks prior to placement of concrete
27006e57-9d67-5eb8-8037-19b4938edb59 | note | Category - HP
21e5c3fb-e8f1-5b62-ad0b-179030d761f2 | note | Responsibility - Nominated Authority
50b23a2f-85e8-5d5b-a83c-e8a3b2ffdd81 | note | Verifying Documents - ConQA Hold Point Release
fb310532-f91c-55f5-b257-eca5148c77ad | date | Date Completed:
d0a93c67-180a-400f-86b8-0baaa1cfd934 | signoff | AUTHORITY HOLDPOINT
61d9aef3-0fa1-4b13-9ac2-d0659d2fc4a1 | checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
923ebf8a-b755-5214-ae23-285092b3c49d | note | Reference - 610.17 (a)
a509b296-3143-57b1-ba4c-8f4b2871d473 | note | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
a1c6e7a0-c616-51f5-9f22-dd15407257b5 | textbox | Enter: Teambinder Approval number
79cd9a73-c662-5df1-8ad4-440522c32567 | note | Method - Document Review
0f6195bf-f6c9-5e3c-89cb-8150fdee0a7e | note | Frequency - Once, 2 weeks prior to placement of concrete
5a5fd6fb-c92b-5500-a4ba-05b749f220ac | note | Category - HP
38acb6da-390f-5182-a9e6-853b3023ac33 | note | Responsibility - Nominated Authority
e482b30f-d72e-5bdf-aff7-d3431980e2dc | note | Verifying Documents - This ITP
eb7c9f5e-670d-58e7-a2a9-c8cebe495f52 | date | Date Completed:
7e05de92-d326-46c6-806a-7935a996098e | signoff | AUTHORITY HOLDPOINT
1e64f6cc-4733-4a51-8c05-13e49222d270 | checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
1276a595-fd32-5262-972d-529eba57d6f9 | note | Reference - 610.23 (a)
8bd6ae3a-7dd3-5ad6-b36a-dbc164e7f9ea | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority.
af1a6f71-bc90-56a7-a7b9-b44be8fbd78f | textbox | Enter: Teambinder Approval number
1edd0b11-add5-5ae1-93a4-bfa199b2feb7 | note | Method - Document Review
eb076163-02ec-536a-8cb3-45db398b620c | note | Frequency - Once, 4 weeks prior to placement of concrete
5d0efc4d-d8dd-5c53-a4bc-76ddf071142e | note | Category - HP
16fc02a2-38ca-5409-8cbd-72cf28d2bddc | note | Responsibility - Nominated Authority
6fb8dc7e-857a-5d40-84a9-a1cfb724c35e | note | Verifying Documents - ConQA Hold Point Release
8f78d293-b325-5c9c-9e98-698a13ef389c | date | Date Completed:
46698f82-4483-4f8b-b1a2-4e7e59629e07 | signoff | AUTHORITY HOLDPOINT
d494ee36-5965-4365-8c6d-5433e6546a32 | checkpoint | 3.6 - Concrete Drilling Procedure
15ffead7-9a2a-5fd4-865c-8235407a251c | note | Reference - 610.46
9e1b41ed-5b53-5847-af18-c30d2a15bdcb | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
4a7303e6-d59b-58b4-947e-3b267eaa0d43 | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
951082a5-d060-5e4f-b2eb-c16e32f9f7af | textbox | Enter: Teambinder Approval number
251d5b48-c6ec-5216-ba7b-8f759a072972 | note | Method - Document Review
907cec4c-57b0-55b4-8beb-763c85167e99 | note | Frequency - Where applicable, once, 2 days prior to drilling
63179465-1d87-5cbe-a72f-30887425fcc7 | note | Category - HP
0168c05d-5dab-5122-9278-5e50922e5ca7 | note | Responsibility - Nominated Authority
6386d468-b4ff-5e4c-9596-0004d10889b6 | note | Verifying Documents - ConQA Hold Point Release
932bb161-e154-5553-b2d7-7b63b7004e1a | date | Date Completed:
b064db62-7258-4810-a2a9-a727a71234a9 | signoff | AUTHORITY HOLDPOINT
448bd89a-ff2b-4cb7-aaef-b7eb7654d773 | checkpoint | 3.7 - Temprature difference measuring-Calibration
a514ec01-ec1f-5787-9083-b54bc910cf3d | note | Reference - MRPA Quality Management Plan
a0d486cd-53c4-511e-b5e4-5d032d761d07 | note | Acceptance Criteria - Calibration records are valid and up to date.
7fe054df-46f9-534b-ae5d-d0ac85865516 | note | ○ Attach: Calibration certificate
96814b35-3c69-5902-b3db-006cb8148230 | note | Method - Document review
619c1ffd-6c25-53d0-83f4-22ac2f080915 | note | Frequency - Where applicable
bf1a505c-dd20-56a3-bcb4-204eb06d8ddf | note | Category - HP*
a3cb9933-562a-5f48-a44f-9f3ec6e9de59 | note | Responsibility - PE
f4f2de91-067d-5ab1-8b73-9c04f6845bde | note | Verifying Documents - This ITP, Attached calibration certificate
78b00080-afca-5258-ad43-13ca4f724b30 | date | Date Completed:
93add8e9-bffc-4d08-87ab-5f74489b8ef6 | checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
3706047b-ac50-5252-a1cc-89a8b0309fce | note | Reference - 611.13 (a), AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, AS/NZA4671 - 2019, 611.14 (b)
a04d8244-a1fb-51d7-bf7f-6397942d6779 | note | Acceptance Criteria - All welding procedures shall be provided to the engineer and proof engineer for review for compliance with the design requirements.
2d33c150-10eb-58b4-bd6a-b87eca2ce83b | textbox | Enter: Teambinder Approval number
4bf0c212-caff-510b-b347-4efe7f7be1d0 | note | Method - Document Review
ad621479-54a2-5f6f-954f-db52803ea6a1 | note | Frequency - Where applicable, once, prior to welding
09148381-c304-564f-86d0-7da56e9d3688 | note | Category - HP
596a063e-37e8-5b60-a403-3fca23faa607 | note | Responsibility - Nominated Authority
716d2e88-176f-55cc-a398-724fda22d0f1 | note | Verifying Documents - ConQA Hold Point Release
830a4eff-9195-5dc9-a5c4-e639b64225c1 | date | Date Completed:
50c416d9-9010-470c-b70d-5476f1be95bf | signoff | AUTHORITY HOLDPOINT
8763f081-ffa4-45e1-9caa-7f262d946cb8 | checkpoint | 3.9 - Reinforcement Welding Specifications & Qualifications
e095708e-ee7c-5c11-874d-5bee72b831df | note | Reference - 611.13 (a) & (b), AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b), AS/NZA4671 - 2019
b00c3639-fea3-505b-b677-5bba814cca9c | note | ○ IFC Drawings
a57473d7-d551-54c7-b54f-06fd289ab83c | note | ○ INFRABUILD SENSE 600 WELDING GUIDELINES T05A V0.2
19c375fa-424d-5dd2-97f7-32cbaafbc673 | note | Acceptance Criteria - All quality documentation and test results to support the prequalification of the welding procedures shall be provided to the engineer and proof engineer to demonstrate compliance with the design requirements.
4b73410d-175e-51b1-bb64-71e78042d18e | note | ○ This documentation, along with the engineer's and proof engineer's endorsement, shall be submitted to dtp for review, prior to commencement of welding reinforcement to be used in the structure.
35c1aedd-a567-565d-8615-3277351629a4 | note | i. all welded splices for sense 600 reinforcement shall be prequalified to as/nzs 1554.3-2017 and the requirements of section 611.14(b). welding procedures and itp shall be developed following the guidance in the document titled: infrabuild sense 600 welding guidelines t05a v0.2.
86ada530-98bc-5d6f-a079-bfa2941d66f6 | note | ii. engineer and qualified welding personnel shall be engaged to develop welding procedures for the welded joints of 600N reinforcement bars for hopkins road bridge, and to propose testing programs for the welded joints;
81ae8e03-b373-5074-bf9f-e621a358983e | note | iii. testing of welds shall be performed;
9f5d24ec-82c4-54cc-bc03-ea1c53344e7b | note | iv. the testing results shall be reviewed by engineer and demonstrate the testing results meet the design requirements for the welded joints;
69f323b2-4323-55ae-8a31-dbbe51708197 | note | v. the satisfactory weld testing evidence together with the engineer’s assessment shall be submitted to dtp for review (not endorsement)
5ca539bf-388c-58d4-abe0-911720fdc642 | textbox | Enter: Teambinder Approval number
2e81556f-0e9f-53d2-96e4-6dba7470f741 | note | Method - Document Review
1eeebcb4-0af2-50de-a062-b58057ef6ad2 | note | Frequency - Where applicable, once, prior to welding
f5155b9e-fa1b-55b4-a24c-9658d75e96cf | note | Category - HP
f7fd2aba-f1db-547c-b450-db8b05913845 | note | Responsibility - Nominated Authority
6216f907-7ad5-5d99-997c-238499428113 | note | Verifying Documents - ConQA Hold Point Release
f000d87a-9f2d-5f84-97ad-ba34eb4137df | date | Date Completed:
65b69b09-9b56-479f-8bab-79f9dfb11ff0 | signoff | AUTHORITY HOLDPOINT
40cd66cc-3d6d-4115-a5cc-1b2e6fb77dad | section | 4. Pre-construction Activities
6a210317-21a5-4890-8925-b47d0c7f5385 | checkpoint | 4.1 - IFC Drawings
369f25c5-10e4-5502-917c-5d1e7df438f1 | note | Reference - MRPA Quality Management Plan
9f002c83-24e9-5d08-ad6e-853079f88e77 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
002f55c7-3871-54f7-908b-63327e202390 | note | Method - Document Review
7e17edac-d64a-5661-9492-ae7cdc04d2c0 | note | Frequency - Prior to starting Works and at regular intervals
19fc5da9-ce7b-53d9-ae60-1d9230a404de | note | Category - HP*
436217ae-e8b1-5097-b88b-23b2d49b755c | note | Responsibility - All
72eb8340-e66a-562c-883a-cbdf28fd2370 | note | Verifying Documents - This ITP
8bd2b645-261f-550d-8a09-9c93c0561cf3 | date | Date Completed:
bae4affe-ff89-48ff-9249-9807194ecd14 | checkpoint | 4.2 - Survey Set-out
140d9934-b871-56ab-8c6d-c77908023576 | note | Reference - IFC Drawings 610.47 (a) Table 610.472
5d7c122f-e2ca-5464-aefd-d9f3c40e1660 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
83b2d859-4ae9-5dc9-9df8-d2d1f0b89587 | note | ○ Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
0315b08f-e4de-5cce-b5d9-f1559c3436c3 | note | Method - Measure, Visual
ab9b0eeb-b328-57f6-9c5b-6ae5f2b816e3 | note | Frequency - Each element
ba045e59-9f69-5252-8f24-8b6906662b2c | note | Category - IP
41ea7a53-e1f7-51c8-8a96-d1e04e021a4a | note | Responsibility - Surveyor, SE/PE
b1e1f330-b787-50bb-932d-80949f321653 | note | Verifying Documents - This ITP
c438bfda-3cd4-5aaf-bccb-adc3067d7936 | date | Date Completed:
09312a8b-3005-496b-b76a-f5d37ffa2088 | checkpoint | 4.3 - Excavation support
12955001-e247-54a9-9601-b252cf7cdb97 | note | Reference - 602.02
8c842f42-fbed-56b3-b302-f95bc718da85 | note | Acceptance Criteria - For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
3bf5a679-895f-5355-bc84-6395b2138c11 | textbox | Enter: Teambinder Approval number
f13cbf91-1a39-57b1-8799-d5f3ee760bbd | note | Method - Document Review
cecd342b-a503-54e5-a88e-6721c68019f7 | note | Frequency - Where applicable, not less than 10 business days prior to excavation
6330202c-93ce-5bc3-aa30-c94af5858af7 | note | Category - WP
7162197a-63fb-5455-adaa-a5edf6f6e0cb | note | Responsibility - SE/PE/SPE
0f6b9399-1bf8-5e03-a2f7-7c978e91a394 | note | Verifying Documents - ConQA Hold Point Release
dde701f6-a6ee-58e6-94c8-e0013f4d3c74 | date | Date Completed:
24735f9e-e8de-4d78-a277-8400a011639d | checkpoint | 4.4 - Excavation Inspection
d6126854-647e-5970-b682-1775fb435dc2 | note | Reference - 602.03
0a1d813b-9171-50cf-8bf2-3ded2f5ee980 | note | Acceptance Criteria - Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
f391ddd2-2228-5c74-992e-8d565253d7ff | note | Method - Visual
60a73caf-71cd-567a-a52a-c68c666182eb | note | Frequency - Where applicable, prior to placing blinding concrete
297e0b27-5554-52bc-ac8b-e43948a00cdd | note | Category - HP
8542302e-0099-5e7a-800b-1ff4134ad27b | note | Responsibility - Nominated Authority
0e41b97c-da8f-598c-95db-488dbea140b2 | note | Verifying Documents - ConQA Hold Point Release
5644f884-ae03-58d6-898b-da34e098cc7f | date | Date Completed:
b433a456-554f-4298-af20-5f6ae65dd55c | signoff | AUTHORITY HOLDPOINT
a00e1edf-7760-4cca-abe4-acc1d16e1f17 | section | 5. Construction Activities
f592b750-62d9-43eb-92cc-f00d184a0fdf | checkpoint | 5.1 - Formwork Design and Construction
e32513c3-2434-58fd-9709-3abadebe6444 | note | Reference - IFC Drawings 614.04, 614.05, 614.06
e3a6d0b9-1f12-52f8-88e9-b582fd0545bf | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
a5aed420-be25-5d0f-a843-d2312089c3d2 | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
4afddb33-34d1-586a-8ea3-ae1e9aa33921 | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
90596faa-78ab-5689-8d1d-54660e359c89 | note | Method - Document Review, Visual, Measure
24691777-767b-56f6-bf74-094185b004a9 | note | Frequency - Each type of element
ff3dcd8d-e1eb-5c96-9fa1-ceda51fc16b8 | note | Category - IP
215ade61-a057-53b5-977a-f37e2bbbccae | note | Responsibility - Temporary Works Designer, Proof Engineer, SE/PE/SPE
041fa4fc-e523-5030-9f4a-1c83017a44b2 | note | Verifying Documents - This ITP
ae2ff0cc-587d-5646-a8d8-bc10a0c4d7bc | date | Date Completed:
36da2462-335e-4e50-8399-344c695921cf | checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
b11ba6ac-22fb-5180-ad33-a12d884762c4 | note | Reference - 614.08
eb30bafe-dc9d-5bf2-b264-af48d3f8cf4a | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
7640d0b8-323f-5203-8426-8b84276520eb | note | ○ Walls with heights greater than 2.0 metres
26c3b410-9a48-5098-96fa-0b2ffdaf21ca | note | ○ Any member for which self-compacting concrete is proposed.
f701772c-e7b4-5c8d-b377-aec5abf46378 | note | ○ Attach: Attachment A
719cfe68-8d59-5141-9150-8d70c493b66c | note | ○ Attach: Attachment B
292d1fc4-e156-5cfa-a407-861e686c7a19 | note | Method - Document Review, Visual, Measure
7983eadf-46f1-53d5-9ed9-b75bb108d8e7 | note | Frequency - Each element (where greater than 2m)
192cb453-87b8-51e6-8df9-03d2ea237a06 | note | Category - HP
9f429b54-9531-5be5-bb7b-4feeafeff81e | note | Responsibility - Temporary Works Designer, Proof Engineer
601b1f33-cc3f-5f9f-96da-18d272aef2d4 | note | Verifying Documents - ConQA Hold Point Release
a04abe65-a638-5018-8fda-2417613482be | date | Date Completed:
a052958d-7eb9-4920-ae06-0937588e99fe | signoff | AUTHORITY HOLDPOINT
acaaf3eb-46c3-4692-b3cc-0e49c1ee4d33 | checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
6669468e-731f-550a-8d82-fcf7af828edc | note | Reference - 614.08
96432ca4-39e5-5ddf-bf6a-7c66a8d3e2dd | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
75b3b678-9435-594b-bcad-50c872a9411a | note | ○ Walls with heights less than 2.0 metres
0ac653b4-ab15-5025-a779-ef4507ce571c | note | ○ Attach: Attachment C
dece956a-9a69-5e9c-be54-df52e854e5d3 | note | Method - Document Review, Visual, Measure
80f5d770-cccd-5c4d-8893-391c0cd942f0 | note | Frequency - Each element (where 2m or less)
6bba2704-915f-5453-8aa9-787e54422110 | note | Category - HP
b76841c7-c9b7-5fe6-b0e5-f7ca346ef21f | note | Responsibility - Temporary Works Designer, Proof Engineer
e9659220-f7ca-5706-a963-882043b49e68 | note | Verifying Documents - ConQA Hold Point Release
fdac9901-83d5-583b-8707-cc508602e6d1 | date | Date Completed:
fbbc7427-62b9-4788-81ec-1f4b6e14b46f | signoff | AUTHORITY HOLDPOINT
a9e8946a-a18f-4e8b-bb74-a19a865a3446 | checkpoint | 5.4 - Pre-pour Survey
b269a8c8-0407-5f28-bc19-ce07100cc68e | note | Reference - 610.47 (a) Table 610.472
101ee27c-a35b-5d2c-985f-3d98d05353eb | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
4b277334-0b39-53d2-bfdc-9e2b0a99d056 | note | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
05865c49-4184-53a5-b881-6a0ae9921669 | note | Method - Measure, Visual
385e4a79-0951-5513-a9c7-06b17e0b11c4 | note | Frequency - Each element
696229da-c2dc-5e3c-b271-7b7babcd843a | note | Category - HP*
a8e21b56-d023-51de-99c0-fab0b111967a | note | Responsibility - Surveyor, SE/PE/SPE
5c8de79e-fff8-5f80-aca8-0b9c7de40917 | note | Verifying Documents - This ITP
da7a1718-76cd-5b12-b4b9-ee8d333f7924 | date | Date Completed:
3a5cde69-c1b6-434e-83f1-3858e064b859 | checkpoint | 5.5 - Reinforcement Placement
5e6222f0-2da3-58af-b613-c84f7f66f859 | note | Reference - IFC Drawings
b16560f9-5097-58d3-843e-f5872cd555e3 | note | ○ 611.06
21822c68-8463-520e-81a9-4bd7912ca9bf | note | ○ 611.09
6bae752d-f501-51df-a761-308cc2521e26 | note | ○ 611.10
2b6d43ad-3e1d-5b0f-aaa2-5f9acf5cd8fb | note | ○ 611.11
f0491572-774c-5d87-9b27-5e154d0f9187 | note | ○ 611.12
b86e533e-c5ca-5cdc-a85d-55d1328bfc91 | note | ○ AS5100.5-2017
3c7ae3ed-74f8-5f1b-b1d1-98e2f5a9990a | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
3c2810da-7f6a-5bc5-83e0-deaadfb757dc | note | ○ Projecting reinforcement is the correct length and location.
02b7f0af-36d5-5f90-a120-adf0170a8868 | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
76395041-ffb6-573b-b73d-5c6304af96c4 | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
31dd0f1b-72b3-5f13-91c0-449bb12bc352 | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
de9a12c4-1bd2-544e-a471-dc0cfda54dcf | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
c2de3466-3df8-535f-9b13-d81262a17ee5 | note | Method - Measure, Visual
0c506a48-c502-565a-9d6d-2afc28e6c0e7 | note | Frequency - Each element
3476ca15-dc0b-5766-a484-3d7b148b85e9 | note | Category - IP
69a97586-41e5-5991-a176-9c37b72c4ad4 | note | Responsibility - Foreman, SE/PE/SPE
9a359b9c-c066-5eca-8f51-46922f5d668c | note | Verifying Documents - This ITP
a0b76d2f-1099-524e-ae1f-654311cb5926 | date | Date Completed:
853d6ccb-ad81-4a81-b7f1-1a7558936852 | checkpoint | 5.6 - Cast-in Items
d0ea9f23-6f4a-5224-9c80-3a14b228de7a | note | Reference - IFC Drawings 610.47 (a) Table 610.472, AS3810.1 Table 3.3.6.2
1ea43375-ef40-507d-ae49-e6ed48a61d23 | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
22769a2c-19e7-5b8d-b1e5-c6a98395f19f | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
a5d36a15-7a15-54de-ba1e-99cbbf65d767 | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
39c9e7b9-783d-57a7-a781-1b3766ebe27b | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
5b6708e2-950e-5ea7-9f43-e59670b47ac2 | note | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
30676c86-1a3a-5510-8d25-f6de40364598 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
f36a394e-b2fc-5d8d-9b22-023ae17d7ba7 | note | ii. Running dimensions of a group of the above = ±6mm
947d9c57-792e-5e25-b335-0a9dddc51bd3 | note | iii. Ducts and conduit location = ±12mm
e68bf140-06f6-5277-b8e5-e319e16b1c77 | note | iv. Diameter of ducts and conduits = ±3mm
bc3104a8-58cd-5d2f-9b0b-1c1d51dc67a8 | note | Method - Measure, Visual
c6e18e67-fcf9-5368-ad62-40815a382c17 | note | Frequency - Where applicable, each element
201d4917-7837-5452-83bb-e5eeec851ab8 | note | Category - IP
a512966b-a78e-5e0e-a4de-6cf2e545c8a9 | note | Responsibility - Foreman, SE/PE/SPE
df70ca9c-5a66-510c-a741-528aa247dd03 | note | Verifying Documents - This ITP
9a63a753-bf73-5e21-bab5-18796b1538a6 | date | Date Completed:
81afec07-a13d-4883-abf6-d83f54bd2d6c | checkpoint | 5.7 - Thermal Differential Monitoring
21552a94-9559-5de8-ad97-52ab96bc5e27 | note | Reference - 610.22
7685c87e-de1c-5769-b112-ff4fc7d2ed2e | note | Acceptance Criteria - Thermal differential monitoring thermocouples installed.
1986989e-f7f0-5401-a91e-793b4e5ecef3 | note | ○ Only applicable if the element has:
a05868b8-a282-5dc1-b4a6-e3481cc6973b | note | i. the smallest sectional dimension exceeding 500mm
636bd76a-5f04-5546-b259-586d04a15c53 | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints
3db8aab1-5f5a-56b1-8894-e0dbfa72c3df | note | Method - Measure
1b2d48b7-8a65-58fc-9063-98ca03a82cb2 | note | Frequency - Where applicable, each element
ad989da3-71c2-5414-b4ee-fde98f1e4b8f | note | Category - IP
2397b654-4373-51f4-9272-c080e18e530e | note | Responsibility - Foreman, SE/PE/SPE
c574e600-3437-5ce9-b705-ed10ee7ae7a7 | note | Verifying Documents - This ITP
185fe53a-815a-5adf-b05d-4ee6de177bad | date | Date Completed:
f6f5265a-8075-4397-8dab-db7216419d57 | checkpoint | 5.8 - Pre-pour Inspection
5500c9b9-4d94-5991-8efa-7b4b56d87f53 | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
b6201701-7bcf-58f3-92e6-f9ae4128d96f | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
12f02be0-67fc-5a92-9117-8a8948b539e1 | note | ○ All foreign material has been completely removed from the forms.
3575c19c-e7c0-57c8-844d-a31cb8637285 | note | ○ ATTACH: Pre-Pour Checklist
e09fa8a9-9710-5e44-a0bf-a941ab741610 | note | Method - Measure, Visual
9341d5db-8c76-590f-a129-f973ece95d2a | note | Frequency - Each element
ad663f66-de06-52fc-a877-0994b36245bb | note | Category - HP
d2cdb970-a1f6-5ce0-ae48-14681211207f | note | Responsibility - Nominated Authority
89a9914b-4c07-5aad-928f-98d1a6d84346 | note | Verifying Documents - ConQA Hold Point Release, Pre-pour checklist
665b4830-4c6c-53d2-9907-ee09053c67d2 | date | Date Completed:
3f592714-bca3-4ac3-9348-4839decb9222 | signoff | AUTHORITY HOLDPOINT
aa70183f-55d8-458c-b72f-37e1eaf11f32 | checkpoint | 5.9 - Weather Conditions & Evaporation Limits
82bd03e3-f30f-5e6a-99e0-892ea1839994 | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
f5aabbb7-e305-5562-a48e-5b4a08f02904 | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
08c2fa79-1e32-5ce0-ab09-f9cd48740508 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
b373e6b9-2f9e-5973-a672-b962e1d4d31a | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
8bb29e4e-c7a7-5cab-80e8-125aebc3aa68 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
c7f5ee54-42fa-50e5-a678-25e6e5fd3db6 | note | ○ Record: Required information on the Concrete Pour Record.
a1f0818a-7a89-550f-991f-6348924aee5c | note | Method - Measure, Visual
9a05e18a-ade9-5d5c-855d-243e2eb587cb | note | Frequency - Each element
498944e8-42fb-5f76-9c24-29f04f2434ba | note | Category - IP
5a50be22-4198-5b7d-b859-ec098f3f5e0c | note | Responsibility - Foreman, SE/PE/SPE
44725616-2960-5d90-8a00-8b9cb5f5475a | note | Verifying Documents - This ITP, Concrete Pour Record
c13620d6-4b38-5d5b-885f-f19e726afae0 | date | Date Completed:
fb24dee9-d5e6-4e3a-81b9-805dde8ddbba | checkpoint | 5.10 - Concrete Testing - Sampling Frequency
280ee2b7-4375-5d9f-ad16-eb3d99144d29 | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
eb5b6ec4-a387-5123-b56e-53ff43e0dc28 | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
18e16a6b-fe42-518d-949e-73f92a537221 | note | — 0m³ to 10m³ = 1 sample
d69914c9-24f1-5e93-8598-342681606a84 | note | — 10m³ to 25m³ = 2 samples
6165955b-ecfb-58bf-8819-d38c4e1a3114 | note | — 25m³ to 50m³ = 3 samples
550bbc2d-1255-59ab-8871-e866388d8879 | note | — 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
93282eb7-f7e5-5f91-ace0-0eba6f284b6f | note | ○ For each additional 50m³ and additional sample shall be taken.
b6648ed3-74c2-564b-b2ec-b063c3cd93ca | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
571dd3e2-063c-5aef-84a6-03c3962a4576 | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
996a3591-fa56-52f8-9cfd-1166d1f1bec4 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
5bea78f2-a47a-517c-a58e-a557bd218c74 | note | ○ Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
fcddeef3-31e4-503a-8a05-4570ce6125e3 | note | ○ Record: Required information on the Concrete Pour Record.
c3dac545-ae17-543d-9281-55d3152be1fa | note | Method - Test
2e484546-a307-5d43-b836-d4f86a5781b8 | note | Frequency - Each element
8dc80cf7-6b7f-5e0e-aba7-1fd86fdaf4ec | note | Category - IP
d873a86b-03d2-54cd-9c5a-c06798d58e27 | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
0d5868d6-7e38-59ec-9ca9-94a6e7ebb7f6 | note | Verifying Documents - This ITP, Concrete Pour Record
0b4ee8a3-5cf7-5526-be99-800e04c6f619 | date | Date Completed:
f6693641-aefe-4b38-ba31-66cd0881be9c | checkpoint | 5.11 - Concrete Testing - Slump
9c72026b-aae1-594a-b7b4-1dfc28460897 | note | Reference - 610.16 (c)
710a341c-84fe-5ba4-99d9-b47d66066d30 | note | Acceptance Criteria - Slump testing tolerances =
460d56d9-e9fd-5b89-b122-d1598f5255f5 | note | ○ <60mm = ±10mm
b599c3d7-57d3-5c08-b812-aa3c881d0b7f | note | ○ ≥60mm to ≤80mm = ±15mm
6c5d6e1c-462f-5f97-80b4-78ec8b1c37f7 | note | ○ >80mm to ≤110mm = ±20mm
3ae218a4-da5c-5d1f-ae02-7a4bb00b54d1 | note | ○ >110mm to ≤150mm = ±30mm
58f42306-7874-5050-90b2-2a5301e4daa9 | note | ○ >150mm = ±40mm
34d74e1e-68c2-5b8a-b735-7046d9ecc12d | note | — Record: Required information on the Concrete Pour Record.
d3303e52-2ad3-53d2-8a3b-a1471736f4aa | note | Method - Test
20aa6d24-c32c-5e9e-9913-16563c41673b | note | Frequency - Each sample of Standard or Superplasticised Concrete
78ee7fd2-7db4-5fec-ace7-403fb6060b66 | note | Category - IP
27e52b6b-dd6b-5573-859b-d4a603a93e51 | note | Responsibility - Concrete Tester
1d6f9789-af5f-524b-8b9d-01b4b328509a | note | Verifying Documents - This ITP, Concrete Pour Record
4a9cff5d-1035-5809-9168-a444964b8012 | date | Date Completed:
b0d144cb-804e-4417-865b-fbf60acc5cea | checkpoint | 5.12 - Concrete Testing - Spread, Passability & Viscosity
7c0dd6a3-35b8-53a5-8c97-015c80ee5fe7 | note | Reference - 610.13 (b)
36979c24-8599-5191-8bf1-d3a1edde3fde | note | Acceptance Criteria - Spread range = 550mm to 750mm
446f8689-cfa4-5f80-a793-a46cb231d5d9 | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
774a0a1b-8189-5514-a761-53fe1e8b3e0a | note | ○ Passability = ≤10mm (aggregate height differential)
d4083f69-0d2a-545b-8a8e-9a0c51c0250e | note | ○ Record: Required information on the Concrete Pour Record.
2ae7137f-566e-509b-909f-24b37fcddf68 | note | Method - Test
86e49933-b322-5b52-84d8-5c0f03e4e2a9 | note | Frequency - Each sample of Self-compacting Concrete
8229559e-7749-5551-a22f-b68477d307c4 | note | Category - IP
c50600aa-6af9-5165-8186-f9c3b5b18728 | note | Responsibility - Concrete Tester
26303f43-5ac3-5498-9cb5-efd7125fe7d9 | note | Verifying Documents - This ITP, Concrete Pour Record
1a28bc80-39e4-5f7a-a5bd-2827282e044c | date | Date Completed:
0172a8d6-cf8f-44cd-80e1-df32875f8722 | checkpoint | 5.13 - Concrete Testing - Compressive Strength Cylinders
6b7cf706-3437-5bde-a7d7-09e6e94686ad | note | Reference - Site Sampling & Testing Procedure
4315fe73-828a-5db4-bf90-ba528072dc2a | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
b6389cf4-6ce9-5bf0-aa6d-730a461db4ca | note | ○ Record: Required information on the Concrete Pour Record.
5bc20ecf-1c90-5643-ae14-57e2325ce00c | note | Method - Test
2d80fe6d-c57c-5b6f-bed5-296623e0fdf2 | note | Frequency - Each sample
ee491fe7-7802-53e7-9b42-caa2f328783b | note | Category - IP
475ba821-c015-59d4-bc8a-3e3e7eef2797 | note | Responsibility - Concrete Tester
c044fead-28e5-516a-a159-83247a217682 | note | Verifying Documents - This ITP
d1c9d0b1-de60-57fd-ae93-7a1b49b2effe | date | Date Completed:
3d267285-5d5c-4f2d-b578-a303de1371fb | checkpoint | 5.14 - Supply & Discharge Rates
c890a83b-acff-5cbd-b518-d256d8d7988a | note | Reference - 610.13 (a) & (f)
fa1ecc97-37cc-5699-8bc1-0d5a9f91c1e0 | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
c4159af5-6a66-568e-b87c-6cca3a9a383e | note | ○ No water is to be added once discharge commences.
2155170c-3c20-5f19-80a0-6131ea7c185c | note | ○ Maximum time between batching trucks is 25 minutes.
2cfc6048-d122-5e87-87bf-4942ae9f517a | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
e0516a30-c120-51ad-8481-3e3ca8311734 | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
259a050f-64dd-5b67-aefb-044ff43677d3 | note | ○ Record: Required information on the Concrete Pour Record.
f754598a-5926-53a9-9971-459ff0660396 | note | Method - Measure, Visual
def00269-b5ad-505f-a956-6d729b2c8ff2 | note | Frequency - Each load
8999363d-e6e5-5013-af4c-56eb306d08ec | note | Category - IP
83ba86b2-db56-55b9-9ff3-df6412153c24 | note | Responsibility - Foreman, SE/PE/SPE
d43e0511-9568-52b9-9c1b-220c8cf6fa64 | note | Verifying Documents - This ITP, Concrete Pour Record
8cadb17f-d124-5f87-af83-16bbbf63ca28 | date | Date Completed:
281b2fc8-0e1e-4781-a474-762d3bf77f86 | checkpoint | 5.15 - Placement & Compaction
04955bac-1755-5550-945f-77b80606a799 | note | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b), 610.18 (d) (i)
f34f40ed-46f7-51ef-aa48-b17ca52e55a0 | note | Acceptance Criteria - All concrete batches are traceable.
e464271e-4180-505f-903f-fef78738155c | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
bc85ea7e-2eda-5884-84ce-a10f96779561 | note | ○ Concrete is not dropped freely from a height exceeding 2m.
918e4ecf-3534-53e5-ad93-b5f2dda4448b | note | ○ Concrete is not moved horizontally by use of vibrators.
84ccf364-6b78-5718-ab0c-a759419ef607 | note | ○ Adequate compaction is ensured
01fc081b-7d41-5c23-9ed5-00eb14e067b5 | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
f01ba5c5-c833-542a-a1f1-1a332c350298 | note | ○ Concrete layers are not more than 350mm
b32dbd2a-b41f-5e30-85e4-12e51465d898 | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
2c3e2a50-4637-59c0-b963-cf7ebe26ace0 | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
b451533d-d6df-5ab3-af2f-0702897f6760 | note | ○ Record: Required information on the Concrete Pour Record.
f3c34eee-95ed-54f5-be98-6af82f9116f7 | note | ○ Attach: Concrete Pour Record
4c6eac3b-4fc6-5285-be15-588819042ca5 | note | ○ Attach: Concrete Dockets
bc079426-b46f-51fb-aea0-76d4045bac0c | note | Method - Visual
816c304e-41ab-569d-ab1c-4d283351650a | note | Frequency - Each load
322dd2bb-0292-52ca-a002-bc48c07b755a | note | Category - SP
7ea46984-df68-5a7b-bce5-381941794866 | note | Responsibility - Foreman, SE/PE/SPE
35938629-98e1-5c8e-94e5-6e80770e9fae | note | Verifying Documents - This ITP, Concrete Pour Record
4aedfe1d-40f1-58b0-87d6-15eb71ee8df6 | date | Date Completed:
9b0e7dfc-a6b1-4d54-955b-2310b5714ca0 | checkpoint | 5.16 - Surface Finishes
b68c4ddc-524b-5b55-87bb-3d14e6859b9c | note | Reference - IFC Drawings 610.31, 610.20
0a7109ec-f494-5456-a1cc-509a3ea12ead | note | Acceptance Criteria - Surface finish as per IFC drawings.
6e10467f-27e8-5464-8a39-f84275278fe3 | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
a3380993-f9ba-5f02-b343-e9ef32dda76a | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
c9614cf4-b19f-5195-a493-16e28bc8b6f8 | note | Method - Visual
19ade241-11c3-51b0-855d-3fe6da6349b3 | note | Frequency - Each element
a84ee7fc-0075-59c6-8ec1-3381b45ffd15 | note | Category - IP
9d49c1d7-cbb7-598e-8ff6-157ef1b88efa | note | Responsibility - Foreman, SE/PE/SPE
d53c0e62-e0f5-5bda-813f-deb0116491df | note | Verifying Documents - This ITP
45c56abf-99db-56bc-b6c0-37d151cc54a1 | date | Date Completed:
b873152b-3574-4557-953c-3e88005a77a8 | checkpoint | 5.17 - Curing-Top Surface
38271755-3f6d-5589-9942-49f2f40778bf | note | Reference - IFC Drawings
ebbc87db-e139-5f89-ae2b-4373c4cb9286 | note | Acceptance Criteria - Top surface of the pier and abutment walls shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pier and abutment walls may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
2e48b77c-e6c3-5ab5-b40c-4c58df1b11a6 | note | Method - Visual
20bb1179-f351-5e0c-82fb-6bf6cc7bf0ba | note | Frequency - Each element
8d198c0e-9c1e-5557-a4b7-5ca0bb670c8e | note | Category - IP
fa7cee4a-79b7-5082-9520-d3222cc9309e | note | Responsibility - Foreman, SE/PE/SPE
b8c95195-8fc4-5129-a8ee-fcbd63ebf844 | note | Verifying Documents - This ITP
a135388b-98d9-5b56-bcbf-daaacac1fa84 | date | Date Completed:
7d14619d-fa5e-46c2-8dad-1b7bf431f60d | checkpoint | 5.18 - Curing after formwork removal
678b0625-2b9c-51c2-876c-3da51314f825 | note | Reference - IFC Drawings
43221ac0-d283-5abb-b56e-1ac2a37a1956 | note | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
7b324d85-c569-5956-8ff8-d0974caa5851 | note | Method - Visual
a17d47b6-8d84-52c7-ba08-db7af6be17f6 | note | Frequency - Each element
880eb0d1-6420-50b7-9078-ae828d0f4f4a | note | Category - IP
a2a756e6-4f5d-5d82-a2e2-3e3403676b2f | note | Responsibility - SE
9e3fd357-60a8-50e1-b225-ba23997a99f3 | note | Verifying Documents - This ITP
b7fa85be-f471-516f-9b7a-98c00f2e9f0b | date | Date Completed:
6573b1c1-63a2-4c71-96fd-ce593d3499d6 | section | 6. Post-construction Activities
6710a823-dc9f-464c-81b5-38b299b6b5f6 | checkpoint | 6.1 - Thermal Differential Monitoring
ec2bf10d-86d6-517b-b3bf-dd416cf9e27a | note | Reference - 610.22
cd137c92-a1e5-5535-8d33-c41ddec9dcb2 | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C.
7167a93c-c37c-5ee1-ae43-e3dbe5fbde18 | note | ○ Only applicable if the element has:
d6ec56a6-52df-54e4-acac-db06e0f9a9d0 | note | i. the smallest sectional dimension exceeding 500mm
a6241d11-fa9a-520f-ad5f-111ff506a325 | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
97a6fb97-7ab8-5660-bbf7-be98664e9ab3 | note | ○ Attach: Thermal Monitoring Report
6f979f99-f44f-56d9-9e19-cfbb719225b4 | note | Method - Document Review
9f5bf647-57be-5fd1-b45e-06e340501e59 | note | Frequency - Where applicable, each element
17038707-6868-5d40-9ca1-f8b1a50444e3 | note | Category - IP
73a1839f-144b-5abc-87ad-7751ee1dd35c | note | Responsibility - Foreman, SE/PE/SPE
541ffcf5-55e2-5e35-aeab-f2e493fe7f27 | note | Verifying Documents - This ITP
7904c2b8-cca0-50e8-ae4e-42b33a968fbc | date | Date Completed:
b5247c23-fb53-4f0a-95cf-e1897228fa19 | checkpoint | 6.2 - Early Age Compressive Strength Test Results - Removal of Formwork
b5598587-5527-5a13-8442-039af19ad237 | note | Reference - IFC Drawings Table 610.251
06be9362-d025-5206-b2a2-0d4e4862f596 | note | Acceptance Criteria - Minimum Period before Removal of Formwork and Formwork Supports is 7 days or until such time as the concrete has reached the specified 7 day compressive strength, whichever is the greater.
6a15a9bd-bbfd-501e-9eff-cade68fb6c07 | note | ○ Attach: 7 days Concrete Test Results Result
58ac5747-0a2c-5ea5-a620-77bb53797650 | note | Method - Document Review
259a6d6d-267d-5541-af7a-aa10a46a1a1b | note | Frequency - Where applicable, each element
6e2df9e5-fb17-5336-b6c0-adc1189c17dc | note | Category - IP
432726e1-67e1-5de9-adab-f122efea7f41 | note | Responsibility - Foreman, SE/PE/SPE
36b41366-b9d6-51a6-b2df-7961c87c2a49 | note | Verifying Documents - This ITP
f9a8a745-ca25-570b-8ea7-e61ad8161f45 | date | Date Completed:
0fa76952-04d0-4668-8da2-b3e03d945a26 | checkpoint | 6.3 - Surface Inspection - Cracks
ca3806e2-d0de-564d-9b60-dd0ab2f9e157 | note | Reference - 610.24
f99f06ba-7f65-5afe-9054-0fd6ed779a69 | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
d2e1d430-6758-52e7-83d8-4b3b5cf5b229 | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
73004385-892b-5515-b9ee-62c2b12985ec | note | Method - Visual, Measure
6fed6484-5179-5729-a7ef-77194691a1b7 | note | Frequency - Each element
a86640d0-0bd4-5b39-97e9-1a46c46e8fef | note | Category - IP
a17284f3-8c93-5d22-90b1-c98fba9d25d1 | note | Responsibility - SE/PE/SPE
9731d1e9-c459-5b08-88ef-8a5326a7a396 | note | Verifying Documents - This ITP
7cc62c02-2fd2-5db8-bb4b-8a45963aea1c | date | Date Completed:
2415641b-9158-416b-8919-970b84dc64da | checkpoint | 6.4 - Surface Inspection - Surface Finish
f7b8eb8c-1dd6-574a-ba2b-8e33519e30fe | note | Reference - IFC Drawings 610.31 (a) - (n), 610.32
bee38945-76f1-525c-b3dc-834b57c3f49b | note | Acceptance Criteria - Comply with the IFC drawings and specifications.
cc20f5cb-2016-5fc0-84b0-3ee99c429d63 | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
7178cbc8-045a-5ccf-abc2-8cd90a66afc2 | note | Method - Visual
5ff54156-97a3-54da-a492-c8e313d12b1d | note | Frequency - Each element
4a9c6bb7-6429-5678-a81b-4c88b0277759 | note | Category - IP
bee232d8-4322-5148-85d6-09a3ddc8133d | note | Responsibility - SE/PE/SPE
710d9dd6-d272-5778-8bcc-ea607d9d45f5 | note | Verifying Documents - This ITP
6ba83eed-3396-5167-82f9-5a69d9f36911 | date | Date Completed:
6b3eddf5-1506-40c1-a2a3-199b01f3e3b8 | checkpoint | 6.5 - Measurement of Concrete Cover
456e90fb-0b17-5fd7-ab28-511251e38deb | note | Reference - 610.34
70ce963c-4d15-50b6-9464-062429afbc1e | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
75418b23-9a33-5de2-8b15-cf950c8c41d2 | note | ○ Minimum 10 no. measurements recorded in each area.
b0d8bedf-b748-5496-a696-829a33044df9 | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
c56ffc96-3947-5bb6-8885-dc8caf028f30 | note | ○ Attach: Covermeter Check Record
8ef791dd-6c2d-5fe0-b1bf-17ee579f9db3 | note | Method - Measure
b756837d-afc7-565e-b738-2443bea54507 | note | Frequency - Each element
90bb64db-340c-5ca4-af01-4e2434f34461 | note | Category - IP
25128014-ea6b-5647-bad4-1b710acd553d | note | Responsibility - SE/PE/SPE
4039e719-5c13-5012-93ed-b2d71560a5de | note | Verifying Documents - This ITP
bbccc40f-cf2b-55e5-b3d3-4bb037f0e630 | date | Date Completed:
3edcc274-ce48-4dc0-b251-2022d93872f1 | checkpoint | 6.6 - Early Age Compressive Strength Results - Placement of Fill Against Concrete
3ff299c6-af9b-5b1a-9d4d-fbcb7ed068ec | note | Reference - Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
f0f6c8c5-5c2f-51bd-a3ab-16ea8c3c10dc | note | Acceptance Criteria - Fill is not placed against concrete within 14 days of pour.
75519e50-8ae5-5fe9-ae18-52aff1b5cee4 | note | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
d1c84428-6c71-5ea0-8bf2-1fe03288fc9c | note | ○ Attach: Concrete Test Results or Maturity Test Results
5501ec45-a64d-5be3-a1a4-fe14cac44301 | note | Method - Document Review
c664d1d8-e478-5152-aa55-f716cfc1b8bb | note | Frequency - Where applicable, each substructure element
f1ee234e-b565-5ee1-8f81-54d83cc7e349 | note | Category - SP
c9284fef-6623-5c02-87db-ef3cdf89399a | note | Responsibility - Foreman, SE/PE/SPE
5fde49ae-ca49-5978-9082-c0c9f5ac951f | note | Verifying Documents - This ITP
172ef0dd-1b43-51e5-81d4-e7a1db8b39bb | date | Date Completed:
707e772f-8ea0-456c-8675-4682c9481445 | checkpoint | 6.7 - Compressive Strength Test Results
b81b6242-d13a-5123-abc2-1bb705e34f5d | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
b65d57d3-bf99-5534-86d8-2e87601621c9 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
490d2425-be05-582d-b6ab-0c4ab01bf725 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
9af62238-0dbe-569e-9f4f-af8eb9221dc0 | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
b33d2738-73f0-5f63-b59e-f44e323bd8a2 | note | ○ Attach: Compressive Strength Test Results
f66657a9-3a71-5f06-9eae-0d6327fc915f | note | Method - Document Review
aee84cf5-5f81-5716-9f02-02e2dbe2bb5b | note | Frequency - Each cylinder
157c7e1b-0567-5aad-a7a6-6e74b7483a8a | note | Category - IP
4e837842-329d-501b-95d0-de2c88585bf7 | note | Responsibility - SE/PE/SPE
f8fdde2c-526c-5cbe-a178-df065e467af5 | note | Verifying Documents - This ITP
d1e4ec78-6bf6-5413-9814-872f89bced76 | date | Date Completed:
a29ca2b8-c832-4238-a9b5-9b4b3ed2c823 | checkpoint | 6.8 - As-built Survey
2c85a384-3255-5284-8788-95fcdd40a05b | note | Reference - IFC Drawings 610.47 Table 610.472
c493f9d8-6c04-5461-bd86-74c088ea087b | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
7b335515-640e-58df-8dd2-21d954459b03 | note | ○ Attach: Survey As-builts / Survey Report
1849fb56-0af4-5395-bcc2-9c1d39c0ac2e | note | Method - Document Review
af30062a-3e53-5232-8d15-9f17c4749b2c | note | Frequency - Each element
fddc7ef8-2625-5423-a0fe-0d41d8685a3d | note | Category - IP
3b581e61-bd7c-5b32-aeef-5342e9922641 | note | Responsibility - Surveyor, SE/PE/SPE
dde879c4-4a0b-5488-ab7f-4d6891dadb07 | note | Verifying Documents - This ITP
61163b32-ad36-5f9e-8ad3-00ec73bbb04d | date | Date Completed:
c95a461e-df28-4c28-8804-72760141aef8 | checkpoint | 6.9 - Non-conformance Report (NCR) Closure
b156c13a-ec9d-5954-b1a0-520d7548a7af | note | Reference - MRPA Quality Management Plan
2c575fb1-17b5-5fc6-84d8-0cce8bc5c26b | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
6c878feb-d5e6-5239-a4b0-eb02645561c7 | note | Method - Document Review
8fab7003-4c00-50e9-9dcd-9ec4b8543740 | note | Frequency - Once, prior to closure of this lot / element / Work area
e47f78bc-55b4-5162-86f2-b52828c17669 | note | Category - HP*
809159e9-1651-53f4-ace3-d381efad1779 | note | Responsibility - SE/PE/SPE
b41b03f1-ec80-5f62-a00b-5b4665825ac0 | note | Verifying Documents - This ITP
746d4096-c6e2-5dbf-b885-d9c29824ba83 | date | Date Completed:
73687078-837c-4e74-8192-505f59603bad | checkpoint | Final Inspection
c0e086b5-18d8-5b57-bc1f-75bdcfe26a21 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
f02d904b-d534-544e-b1d4-fbc51f81402a | textbox | Name:
5bd51f85-f665-5985-aa14-374d6a27eca4 | textbox | Position:
3c267c11-7ddc-5ed0-bc5d-0d42049eb89a | textbox | Date Completed:
e1213a9f-192f-4131-aec3-cc308254789e | signoff | Sign ITP
82236d59-a627-42b0-983c-4d8aaf2f180e | checklist | ITP-254-CIV-Hopkins-Unbound Flexible Pavement Rev 0 | itp | ITP-254-CIV-Hopkins-Unbound Flexible Pavement | 0600e09f-948c-4bfc-b5bf-4c4c22323bcf
3a804867-72b4-4518-b785-926c1df50901 | section | 1. Referenced Documentation
bbdac5ab-9463-4e17-a04f-1c4e9a5901a3 | checkpoint-no-value | Referenced Documentation
233c31b8-0127-5585-bbc5-59e40e11bcbe | note | Document Title: ITP-254-CIV-Hopkins-Unbound Flexible Pavement
1b0316be-55b3-5d6d-a27e-0e3e5d2306a8 | note | ITP Description: Hopkins-Unbound Flexible Pavement
c66852d7-8405-5086-a0df-9fb3420eb655 | note | Discipline (e.g. CIV/STR/RAIL): 254-CIV
108d7fec-7411-59d9-b696-9de789bc52f3 | note | Revision Number: 0
6b0df67f-f7ca-55ae-a9fe-c788f69f5ad3 | note | Revision Date: 24/04/2025
e7604572-2254-508a-ac28-64865a997648 | note | ITP created by: Cedric Guico
96837bbf-368c-591b-8ba9-badf4b211d2e | note | ITP approved for use by: Pradeep Talasila
94f0da27-b1da-52cf-bc5e-f7a4dc8bfd8a | note | 1.1 - Non Dependent
18f2c464-2f67-5031-af91-a7fbc150b0c2 | note | Reference - Reference Documents: IFC Drawings
f935154e-570b-5262-8654-c27d30c4876c | note | 1.2 - Non Dependent
6cad3c11-cd42-595f-aea4-3a49ec03da61 | note | Reference - VicRoads Section 173 (10/9/2008)
688ab964-507b-5d83-bf70-cee268248f7f | note | 1.3 - Non Dependent
3f0ba129-65ba-5be0-9448-f7cc8ba6a2bb | note | Reference - VicRoads Section 304 (13/8/13)
636ac39b-006c-5f66-b9cb-ec17491fd329 | note | 1.4 - Non Dependent
837af67a-64c7-5b48-adea-568e8c93e3d1 | note | Reference - VicRoads Section 801 (19/07/18)
3494caac-f417-592b-abce-7636f2366812 | note | 1.5 - Non Dependent
db69fb20-5c04-5a61-b640-1fe92d3cd90e | note | Reference - VicRoads Section 812 (13/07/16)
d98b3dc7-3ad5-4d68-a0f9-7d82cd4d02ec | section | 2. Preliminaries-Materials
3ff11e58-db4d-4f19-a340-ba620ec3cfb8 | checkpoint | 2.1 - Crushed Rock Mix Design
6e56c775-9fb6-5854-868c-8d4552b2c6b9 | note | Reference - Section 304.03, Section 304.05, Section 812.04 Table 812.121 IFC Drawings
e9d0db5b-896f-5d9e-8750-f4f05b5d8428 | note | Acceptance Criteria - All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
775d68d8-1001-5b3c-8cab-772c1242d24e | textbox | Enter: Teambinder Material Approval number
d2263e87-64ab-595d-af5d-c9924a74723c | note | Method - Document Review
5566e806-c0ac-54f1-8e73-c720ff96c536 | note | Frequency - Material conformance as per Table 812.121
50557ad7-bca0-5c90-b79e-9e6fbb20b4fb | note | Category - HP
a609635a-a81f-5284-a7e9-b207ad712ec4 | note | Responsibility - NA
c84615bf-2df5-55ec-8baf-9e79d864cafd | note | Verifying Documents - TeamBinder Material Approval Number
48cbd7e4-02bd-55ad-af1a-81c8f9964d74 | date | Date Completed:
4b85cc11-2ed1-43d4-aee3-b892c2c02042 | signoff | AUTHORITY HOLDPOINT
1d4cb551-87d0-4f43-a4a7-fc5bbc2e10ac | section | 3. Preliminaries-Documentation
0b6b190e-61b6-466d-81a2-deeb5860dac7 | checkpoint | 3.1 - Subgrade Preparation
772d7a98-e747-57e0-927d-c2830ab08a5f | note | Reference - 304.04
63ff730a-7151-5cf4-aa56-1254aae3a7ec | note | Acceptance Criteria - Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
b1a5ae64-7d9a-51ca-96a9-bb9956f1a601 | textbox | Reference: Subgrade Preparation/Type fill Lot Number:
f438323e-e933-5daa-b38b-483b525df20b | note | Method - Document Review
5194e5b7-aaed-58ec-b78d-465d86df2ac1 | note | Frequency - Each Lot
111b1fb9-2f6b-52c8-bd23-a3e891d997dd | note | Category - HP*
4cd564de-a2d2-57d2-a349-5b457181520a | note | Responsibility - PE
ec3e11cf-2c11-5f98-99ad-ebc0b3891a4e | note | Verifying Documents - Underlying layer Lot number
75b2a78b-ef4e-5819-b25f-66863cd588ad | date | Date Completed:
7ae42c56-8525-448e-b647-6f74a3773456 | checkpoint | 3.2 - Select Scale
4e2e1dca-8fef-550e-b77a-b1b6a51cadb8 | note | Reference - Project Requirement Specifications, IFC Drawings
ffb222b1-572c-598a-9da3-273bc24c3a97 | note | Acceptance Criteria - Specify site specific scale:
f0d1af21-40f0-594f-bfef-91ac0d626b24 | textbox | Enter: Site Specific Scale (A, B or C)
84eedc32-b0df-5967-a732-b2d46a1a3a07 | note | Method - Document Review
6721a256-0618-50c4-9303-bc0dea216a9f | note | Frequency - Prior to Commencement, Each lot
6567f203-7585-597e-811c-33c0e9a7802c | note | Category - HP*
5b1df932-6a8a-5cad-8aa8-d4d1c49cdece | note | Responsibility - PE
6224b431-a013-5b2c-ac3b-4613bb563517 | note | Verifying Documents - Sign ITP
205dcea3-d84a-5719-9eb4-f5069fd0aa78 | date | Date Completed:
1195f65e-4b35-4e4e-aa22-1e02324c4618 | section | 4. Pre-construction / Pre-installation Activities
f34e0cfd-4336-412f-9f74-34b0c99ed457 | checkpoint | 4.1 - Survey Set-out and Lot size
66c56a5f-9435-5ae3-b606-02778539b8eb | note | Reference - IFC Drawings Section 304.06
cac5661f-1657-5334-913c-51639680794b | note | Acceptance Criteria - Lot size shall be the lesser of 4000sqm or a days production.
5a9aec11-ca2c-5294-aefd-737b60b49cdb | note | ○ Set out pegs are in place and clearly mark out limits of works as per IFC Drawings and VR 304.06.
c0504264-6095-5db3-ac83-019f21888e3c | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
ea59949d-1998-5bc4-8703-64ddb7c7613e | note | Method - Survey, Document Review, Measure
dded87bb-28f9-544a-9cee-41d7b9054ffd | note | Frequency - Each lot
85b14f94-5232-54cb-a437-32bf453bf40c | note | Category - IP
79d0a316-99d5-5f63-b9de-e753581ebcff | note | Responsibility - Surveyor, SE
4fa84d15-be7d-59dc-be6b-234b28df3c33 | note | Verifying Documents - Sign ITP
76fa3daa-cddf-54d1-9071-675eaa8b2777 | date | Date Completed:
57109eab-deb1-4671-b8d3-9e554133a8a9 | section | 5. Construction / Installation Activities
08002069-d5d7-4772-a379-d888d60c2a22 | checkpoint | 5.1 - Crushed Rock Delivery Dockets
4c6e7cde-1120-5cf4-8c4a-2156a0abcadf | note | Reference - 304.04
c33bc328-ec6f-54cd-9363-4056692d6542 | note | Acceptance Criteria - A delivery docket for each load shall be issued to the Superintendent at the point of delivery. Check Delivery docket for compliance to the referenced Material Approval (Line Item 2.1)
97806e88-b416-57fe-b313-b3d0da8d2447 | note | ○ ATTACH: Delivery Docket(s)
83da39b6-7c49-54d5-ae1b-6276c93117d4 | note | Method - Document Review
7bd21eeb-1d09-5110-84c4-40cb500fa0d1 | note | Frequency - Each Lot
404dda8c-6f88-5e60-a299-437c7d74d8d1 | note | Category - IP
2bbf2c3e-97a1-5127-8d2a-2cff3fec3ec9 | note | Responsibility - SE
10d04a86-194c-5a9b-8d7b-63bc3be62ed3 | note | Verifying Documents - Attached Docket, Sign ITP
3f657920-a90a-50ec-8a36-2e794f1400cc | date | Date Completed:
8148b32c-949e-45c7-8086-d5bcc961ea24 | checkpoint | 5.2 - Placement of Material
49ecf068-10b2-5b16-bae9-d58c34a3093e | note | Reference - Section 304.03, Section 304.06, Section 304.08
46889cd8-b5d3-5ad7-a4b2-871665b2ace5 | note | Acceptance Criteria - Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
1ba8ddf6-44d4-53fa-9765-40e16207c47a | note | ○ Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
bb8f8613-df0d-54b6-9f8f-f7207d474442 | note | ○ Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
64c9bbd2-f384-5eb4-9fd3-866171ae5235 | note | ○ At no location shall water pond on the surface of any pavement layer.
7d46f0ab-cf7e-59ac-821c-ffbf1ba015e1 | note | Method - Visual and Measure
28debb7c-db10-5bf9-bfd4-5d8abf405eea | note | Frequency - Each lot
49af9db9-cbdc-5de1-8551-4c35ef5a8b94 | note | Category - IP
296a69d0-ac53-5a93-8d31-87abd5d0bff8 | note | Responsibility - SE/Site Supervisor
2fe72854-597f-5581-8403-a05136ec6557 | note | Verifying Documents - Sign ITP
bf501573-c174-5f35-ba6a-bdd2ef10efaf | date | Date Completed:
316905bd-7ef5-439c-b77c-b457f3e5e0ed | checkpoint | 5.3 - Construction - Jointing
d649b0e6-80a6-5923-8f52-2c3d6eed73f4 | note | Reference - Section 304.07
040e5f07-ee46-5c22-9713-b9066fd509e5 | note | Acceptance Criteria - The layout of joints shall conform to the following requirements:
fda4fe5a-e6fb-51db-987a-48178981c943 | note | (a) material shall be spread in such a manner as to minimize the number of joints;
1959929a-b859-5916-919c-c184862eade6 | note | (b) for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
fe8da806-2323-55bb-907f-aff9300aba86 | note | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
7e89ecf3-37b4-57cf-a532-4db4d481e5fd | note | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
63d0d6b2-57da-5055-a908-7c65629d722c | note | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
ab044711-b931-5450-8397-71f6ecfab0b6 | note | Method - Visual and Measure
083737e8-79ef-5a3e-a127-80b73b2ed5e3 | note | Frequency - Each lot
b40bf095-e5de-5aea-9695-7463423c91fb | note | Category - IP
dee3493b-d462-59b1-b187-b88474bd01be | note | Responsibility - SE/Site Supervisor
fd688166-a145-572d-aab9-97af5e482066 | note | Verifying Documents - Sign ITP
be741009-4adf-59dd-827a-c3788fed863f | date | Date Completed:
cdade7e8-8b66-4873-a683-034c930ee22c | checkpoint | 5.4 - Compaction test (Frequency)
597d5c17-bdec-56f0-baed-1aa89939e6c6 | note | Reference - 304 .11 (b)
04740a31-e5d6-5e80-850c-aac695e015f0 | note | Acceptance Criteria - The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
93b87f6c-fb25-5d32-9d24-f529bdd92bad | note | ○ The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
3b6d5a4c-f01a-58fd-a788-a79b9fa38bbf | note | — Scales A and B: 6 samples
123ef4a8-5c88-5d39-80f6-51dd1dfaeedb | note | — Scale C: 3 Samples
2e2a98c8-30d6-5b7c-abea-ca2c21144801 | note | — Pass: Tested
af96fd54-c235-5c86-8a81-d0e98307bfe6 | note | — NA: Not Tested
6203527c-78c8-50d1-a12d-b2b7b76a60cd | note | Method - Visual
71567b6b-5a3b-54d4-ab68-5703c2a0b793 | note | Frequency - Each Lot Where applicxable
01cfd90b-0184-5d90-9776-4068033137cc | note | Category - IP
caf2d0be-610a-5f91-8ff2-dc8cba63d9c7 | note | Responsibility - SE
f7b9aeb1-db71-5bf4-a721-62a2c0e5bd85 | note | Verifying Documents - Sign ITP
47de45ea-4a5e-5993-9942-c83c482ea53b | date | Date Completed:
c91a1d39-6066-45c1-872c-95cf8c851bc1 | checkpoint | 5.5 - Post Compaction Materials Testing (Frequency)
cef9d389-35e5-550e-801c-f7c91da88515 | note | Reference - 304.11 (c )
cdb46800-f454-50e7-909e-a7985f972395 | note | Acceptance Criteria - SCALE A:
c270e2aa-8042-5dd1-b7e3-e8ff7350fb82 | note | — The first lot of each pavement layer shall be tested for post-compaction grading and PI. If the lot satisfies the requirements specified in 6.1 as applicable, the Contractor may test at the minimum frequency:
de4cea95-3337-59ab-8d3b-68c9d22dcd31 | note | Compaction:
d481aa58-ea3d-5bba-9397-19e80d5657c1 | note | —Lower Subbase: none
f368c0d9-4766-5e89-9050-f5e9cbb5b16e | note | —Upper Subbase: 1 in 4
bdd65f59-e417-5fe0-8dd4-834d2b3a13db | note | —Base: 1 in 2
e5b3331a-2c7a-5d8b-a151-e0cf025a5f7e | note | PI:
d16150da-dcbe-53ce-9b74-10bcc27ec00d | note | —Upper Subbase and Lower Base: 1 (two samples) in 8
721a083c-edc5-5b87-8e59-96a011f0c3da | note | —Upper Base: 1 (two samples) in 4
25680059-3b93-5787-89f2-6099d48ce203 | note | SCALE B:
f783a24b-e133-5370-98c8-ac2701081af3 | note | —the first lot of each pavement course shall be tested for post-compaction grading and PI.
0b666633-c45e-5294-aee5-8d8ef3baf7fa | note | SCALE C:
74fe1d7e-f787-512b-ac88-920720d1b8a6 | note | —Post compaction grading and PI testing is not required (CHOOSE NA)
3d7cf0bc-63ed-5a7c-a15c-764c5a56fb42 | note | Method - Visual
a4c49137-bbd0-5a2b-a262-da2bc8c4be79 | note | Frequency - Each Lot Where applicxable
a3fa4901-1207-5cc9-a147-768da6a10ef2 | note | Category - IP
7ee94c10-d043-5d53-9647-0099e8075b51 | note | Responsibility - SE
412f0a30-c7d0-5232-b7f9-348868c5d5f2 | note | Verifying Documents - Sign ITP
c73685fa-dcdc-5db1-92a5-a972419a1918 | date | Date Completed:
cb392dfd-71e5-4933-b3ba-74cf4e6eaa43 | checkpoint | 5.6 - Proof Roll
17068f19-4d51-5006-ae8b-51e01fdc0a22 | note | Reference - Section 304.08
eafe7810-9239-54d1-bb9c-827f06a491f3 | note | Acceptance Criteria - All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
8eb29937-fd2c-56d0-8376-ca7af7b73bb6 | note | Method - Visual
1a881073-6159-56b7-9379-645cbac01862 | note | Frequency - Each lot
3b5d50d5-78f2-52e1-af6b-7d4395dd7ab9 | note | Category - HP
6ed30126-803e-5630-b88e-93a55efb9a62 | note | Responsibility - Nominated Authority
9e92aa3c-2bd7-53d9-aefb-f51f23c13121 | note | Verifying Documents - Sign ITP
27194ed2-5755-53fb-bf9c-002f0881719c | date | Date Completed:
7f205155-9351-44ca-b58e-0d681eadee5d | signoff | AUTHORITY HOLDPOINT
80ea20e5-204a-4319-a2e2-9ef7a979824e | checkpoint | 5.7 - Protection of compacted layer
2d58de95-9651-5486-b1de-2dbe256440a9 | note | Reference - Section 304.09
1940c333-c720-5439-bc81-661d34930a1a | note | Acceptance Criteria - The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
2c5a034d-7f39-5ba4-a8c0-2b73b674ccfd | note | Method - Visual
90cdb330-9cc0-5dab-b147-49b9efc0979b | note | Frequency - Each lot
649dd9ce-1d4d-5483-b289-8b2a80eac5fc | note | Category - IP
ac3f42ba-9d7a-55e9-b4b8-4e5e1e15cf21 | note | Responsibility - SE/Site Supervisor
d3c1b4f5-838d-5b76-8c61-db6b274c73e5 | note | Verifying Documents - Sign ITP
b5d94f83-88dd-58c6-b510-d6688df83a7c | date | Date Completed:
00f3a45c-f8bb-46cf-b11f-8eec4d51c148 | section | 6. Post-construction / Post-installation Activities
d660ae2c-8975-4ecb-bebd-5df96dffd1c9 | checkpoint | 6.1 - Compaction Testing (results)
af4c5279-0877-5bf3-af75-e72ccac4e69a | note | Reference - Section 173, Section 304.08 Table 304.081
4a215bda-c738-5780-85f1-0955f8fefed9 | note | Acceptance Criteria - During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
25eab771-6bf8-5252-9d5f-f6fd0697e3ac | note | ○ Density Ratio to be based on tests performed with Modified Comp active Effort.
24505069-9199-5df6-a9aa-2dade7fc30b5 | note | Scale A:
7222e75a-e0f3-570d-b599-c857ceeb773f | note | — Subbase Layer Characteristic Density Ratio (CDR) ≥ 98%
999f0270-b02d-5245-bb1e-66ca7502f2ff | note | — Base Layer CDR ≥ 100%
880cfcd6-e990-57c6-a7af-0fccc07816c4 | note | Scale B:
6ce06f5d-ae81-5130-929e-577371fc7046 | note | — Subbase Layer CDR ≥ 97%
01480b12-3941-5d94-a383-085030f7960c | note | — Base Layer CDR ≥ 98%
5a762377-8d7a-5660-ba63-92b4326342c2 | note | ○ 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot.
854beae8-8027-5283-943c-dfa3ec86d077 | note | Scale C:
fa6a0245-44ff-5c8e-a841-2e9b1d79b2a2 | note | — Mean Value of Density Ratio (3 tests):
3f5a40e0-e4cb-5e8e-80b1-f4e639d7b0c0 | note | — Subbase Layers >98%
d0eeccf4-4079-5fce-9173-537ef6a0fc99 | note | — Base Layers >100%
9bc2da1d-8412-5e1b-9318-52dda0ed20c8 | note | ○ ATTACH: Compaction Test Results
685a5287-b170-58e0-9ff4-c1298c748088 | note | Method - Document Review
b1d665b3-f197-5462-acd5-664dfb676e0e | note | Frequency - Each Lot Where applicxable
2eb77189-5dbe-57d9-bbd8-ca38db553596 | note | Category - IP
da4f79a2-3ddb-5e2a-a121-3f3ca459982f | note | Responsibility - PE
e66ad654-1c33-5647-b20b-650251d5e651 | note | Verifying Documents - Compaction Test Rersults
2641ddb5-3ca4-588c-8b7e-2f2f0faf0d0f | date | Date Completed:
232854a1-2301-4053-9028-39634566d95a | checkpoint | 6.2 - Post Compaction Materials Testing (Results)
d1be6a6b-5081-5a47-9948-c0657bbffb02 | note | Reference - Section 304.10, Section 304.11 RC 500.02
451e37ae-9ed9-5716-8778-e24347d33e17 | note | Acceptance Criteria - Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
9caf2b89-ade4-5a16-ba89-a8ae5ee8ca96 | note | 20mm Class 3:
3573c3f1-a87d-53ba-9ef1-d0ab6e77b958 | note | Grading
28c82f91-812e-520d-b53d-a5eb55328085 | note | ○ 26.5mm 100%
870e2c97-f2c6-5b6b-a18c-a1c6f25ce46c | note | ○ 19.0mm 95-100%
eabc279f-5226-5286-9913-f9b13b90c3f5 | note | ○ 13.2mm 75-95%
2fdccae2-0745-5306-95b8-fcea3fba2625 | note | ○ 9.5mm 60-90%
7fa23ec0-af92-58b3-9df7-c387fbc2eea7 | note | ○ 4.75mm 42-76%
328c85e3-0a1a-51ff-a879-5119ed454b36 | note | ○ 2.36mm 28-61%
429181fa-4f6a-5426-a358-ed946516bae8 | note | ○ 0.425mm 14-29%
e9292df5-5312-5fe9-82c2-7f7230998f90 | note | ○ 0.075mm 6-14%
b9c87fa6-f089-5ded-9391-3a5d787a191e | note | — PI between 0 to 10
e60f9aba-a329-5403-8137-eeb20fbfb659 | note | 20mm Class 4:
5c447d61-3fd4-5827-8eb6-1f51e7949473 | note | Grading
d093e677-c9d3-5abc-8045-dbb08cdba81d | note | ○ 26.5mm 100%
7cf5973e-a24e-5c21-b131-d918d9760c20 | note | ○ 4.75mm 42-76%
91a7cf28-d722-540e-86e8-2764b27e063d | note | ○ 0.425mm 10-28%
63449469-29d8-5c63-9776-9c90bb49868d | note | ○ 0.075mm 2-14%
f04ea02e-8035-58e3-8a86-734230faa7ec | note | — PI between 0 to 20
86a9a355-dbef-5442-8dbf-964f4a1b03ef | note | — PI x % passing 0.425 mm sieve (max) 450
40d34f4c-879d-59b9-b0a3-2ad01acff09a | note | Scale C: Post compaction material testing is not required (Choose NA)
2c08af3e-40ef-5ec8-991d-0aaabf21e7c0 | note | Method - Document Review
daf7f20b-1b56-5fac-97f7-4745a749dabf | note | Frequency - Each Lot Where applicable
c43d0e75-458d-5314-86c2-1e3ee6193d44 | note | Category - IP
8ed07594-b414-5a01-b6e4-08f09ceaa163 | note | Responsibility - PE
6dffaba5-8037-50d7-84ef-e89ab0c2baca | note | Verifying Documents - Compaction Test Rersults
675273d8-0b66-5042-9434-3ff015e14264 | date | Date Completed:
eccd6779-7f05-4225-816f-2d9b6eb1bb82 | checkpoint | 6.3 - Survey As-Built - Surface Level
3bebc63b-174f-58b3-9239-931fd9c15cf3 | note | Reference - IFC Drawings Section 304.06 Table 304.061, Table 304.062
816694e0-142c-575f-bd94-ee1c12f8ea25 | note | Acceptance Criteria - No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
5d6d1897-3c34-5b9c-a5f4-a33d1b28ca38 | note | ○ Subbase course shall be not < the specified thickness by more than 15 mm.
79d4460c-13eb-55d6-bff2-a058ea220974 | note | ○ Base Course shall be not < the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be < specified thickness.
2ad4fd4c-d0ae-52f9-b213-5e6acb2cb880 | note | ○ The combined thickness of subbase and base courses shall be not < the specified thickness by more than 15 mm.
c806533f-1aab-56e0-9824-08517ce0a832 | note | Scale A: A minimum of 80 measurements per lot
69aca920-a4ae-5f88-a9c2-e0a6883c3248 | note | — Subbase: mean range +4mm to -8mm, maximum Standard Deviation of 8mm
295a2112-07c5-546b-9e03-10c1d3190ef0 | note | — Base: mean range ±5mm, maximum Standard Deviation of 8mm
03d77c05-ecd2-53aa-80b3-d1979a482729 | note | Scale B: A minimum of 40 measurements per lot
63aab622-c24f-517f-9f74-92eedf2291ff | note | — Subbase: mean range +6mm to -12mm, maximum Standard Deviation of 13mm
e29917a5-0ed0-5f0d-8019-7a03885b6d8f | note | — Base: mean range ±8mm, maximum Standard Deviation of 10mm
5081d734-a09a-5e69-8489-bcdfdaf03f0b | note | Scale C:
79e07417-c905-546f-ab72-1f6847cbc1c2 | note | — Lower Subbase (mm) +15/ -25
69a08168-2dae-527c-8f67-4997db8b1a5e | note | — Upper Subbase (mm) +10/ -25
9ecacfcb-1e9c-5f50-97c2-2e7f7c2a8cd6 | note | — Base (mm) +/-15
89fe4cb8-6c0a-5a73-b4dd-6d0a22ec83e3 | note | Method - Document Review
2da3c916-4c83-50e5-b1d8-522a3c83e6dd | note | Frequency - Each lot
7cdd3638-1773-5e25-809a-b2cee801f4c9 | note | Category - IP
e69d4ac2-eb87-5701-bea5-2b96edfd4f97 | note | Responsibility - PE/Surveyor
3bafe350-e8da-5d3e-b304-6153e4a723df | note | Verifying Documents - Survey Conformance Report
12e23afa-c694-5a08-928d-a389df6bac40 | date | Date Completed:
093b555d-78fc-4656-9d42-912df6ebe698 | checkpoint | Final Inspection
680988a3-7e04-558b-b470-b9326b751246 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
3ec10e3f-c179-5d93-adb0-65ac62c0ab52 | textbox | Name:
261c295a-dd0c-5959-9023-90bbd6f4b837 | textbox | Position:
f5cf95da-28df-564b-a17a-0d221ce70aed | textbox | Date Completed:
f20f1745-6bc1-4a21-9445-558bab01cd94 | signoff | Sign ITP
02316a12-7afe-41a5-acc4-93fa911854bb | checklist | ITP-287-CIV-HOP-Behind Structure Drainage Megaflow Rev 0 | itp | ITP-287-CIV-HOP-Behind Structure Drainage Megaflow | 3b38cabc-df15-48c7-afcd-a3d1c05cd878
d15e21ff-8a8c-4e03-8779-75f77636a7d6 | section | 1. Referenced Documentation
d180ec7f-48da-4857-ae08-73410d420ee9 | checkpoint-no-value | Referenced Documentation
d65e8170-073c-5e51-881c-26edf641d9b2 | note | Document Title: ITP-258-CIV-HOP-Behind Structure Drainage
60491f18-2520-5e57-96af-ce44c49f80a4 | note | ITP Description: HOP-Behind Structure Drainage
853b57cf-a8c8-508d-8d19-c683c7a4b764 | note | Discipline (e.g. CIV/STR/RAIL): 258-CIV
1aeffdf1-6d15-5f54-8178-fc0ee88aa4b2 | note | Revision Number: 0
0fff231a-4a0d-5440-8ba5-c28d6ee84b4c | note | Revision Date: 24/06/2025
9c729778-33e0-5d62-bbf9-02c26e516288 | note | ITP created by: Cedric Guico
41ded4a5-c4f2-5980-b86f-960ff6e05d4d | note | ITP approved for use by: Pradeep Talasila
1e32f734-52f5-59f3-a2e6-05dc3c06b9ed | note | 1.1 - Non Dependent
4a3fd327-9103-5b72-9f11-843ba9a08a60 | note | Reference - VicRoads Section 702 (May '19)
fd4a66a4-4b3c-4013-a909-09732a4f0876 | section | 2. Preliminaries-Material
8e42a430-f993-43db-878c-f3199dccc601 | checkpoint | 2.1 - Megaflow
0cd2f875-dc7f-51f2-89ac-eac01bb86788 | note | Reference - IFC Drawiings
b64df5a5-2a58-5a3d-8a48-8e7f323d9e98 | note | Acceptance Criteria - Product as required on IFC drawings
9db8dbd9-c7dd-5d06-b0aa-3f4da385b2b3 | textbox | Reference: Material approval in Teambinder:
b49ecbc5-b90d-552f-ac88-f906e31d0e41 | note | Method - Verify, Document Review
f6c119e0-8abe-5749-9292-39a8de7009cf | note | Frequency - When applicable
e4d4d09e-cfab-5d33-a381-b4071d7efed1 | note | Category - HP
704c8cca-a501-51e9-b9fb-a3c1d00fb604 | note | Responsibility - Nominated Authority
faf6610f-7022-5feb-8855-e22d2e063d0a | note | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
8ed3701d-b5ba-53e0-8b60-fab013936b18 | date | Date Completed:
bf4089eb-71d3-4ade-85cf-56e06f7ca26a | signoff | AUTHORITY HOLDPOINT
ccbd16a2-61c6-47ed-90d7-629d4f30280b | checkpoint | 2.2 - Pipes
ee6077eb-a01d-5b14-ae50-c521f99adc5e | note | Reference - IFC Drawiings VR 702.04
87aec08a-5fea-5004-9c4c-891455a09d3a | note | Acceptance Criteria - All subsurface drainage shall be Category 1, 100mm dia. Class 1000 PVC pipe.
48de0862-c6df-5d78-b8cc-9d5cd1ceaf1c | textbox | Reference: Material approval in Teambinder:
eea4ce89-4712-5c62-87d8-44222d32c41c | note | Method - Verify, Document Review
8627c494-fdbf-5930-87e6-b2fe7223c3ee | note | Frequency - When applicable
0d001c2e-c6a3-5bb0-b5b2-c9c6edfcb42b | note | Category - HP
8ae6c5cf-3b11-5336-a44b-5de29d250c43 | note | Responsibility - Nominated Authority
e22a3ae3-1aa4-56ca-a688-3d24352bbda2 | note | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
a77e8159-82a9-5210-a34b-423072674bcb | date | Date Completed:
1dd13e54-5d0e-4823-83c2-26eb540bd675 | signoff | AUTHORITY HOLDPOINT
e27da5a4-4eae-4b29-b541-1dec75e3d183 | checkpoint | 2.3 - Perforated Pipes
99236d84-9220-5810-9595-9ea8778bf025 | note | Reference - IFC Drawiings VR 702.05
7c6abf6d-e68d-5722-ae7a-01f0a52cfa2a | note | Acceptance Criteria - All subsurface drainage shall be Category 1, 100mm dia. Class 1000 PVC pipe . Perforations shall be max 1.5mm and minimum length of 150mm per sqm
12bb141c-6567-5a95-a47a-25d9e4e57fd9 | textbox | Reference: Material approval in Teambinder:
07328a33-207d-5ca8-b845-d077a86b9e62 | note | Method - Verify, Document Review
7d18c858-4631-5ba5-8211-1e562653ac36 | note | Frequency - When applicable
8a1b419c-d681-57d6-bd52-a11a549565ca | note | Category - HP
f745e29e-a457-5b7c-8158-49ceb8b132f9 | note | Responsibility - Nominated Authority
df1f0b75-a14a-5308-92d1-d18d0e776aee | note | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
18862907-9aff-5a89-aa17-7973ffc67452 | date | Date Completed:
f12fb9d5-ae4a-48d4-ac97-47b1e50c2b79 | signoff | AUTHORITY HOLDPOINT
ee5a8453-4682-4fd6-a74b-b161404291e8 | checkpoint | 2.4 - Granular backfill material
651ecf59-6109-59b7-8d9b-12f5284447e3 | note | Reference - IFC Drawings VR 702.05
c9cbe7f0-40cc-5e68-8326-5d262154576f | note | Acceptance Criteria - The granular backfill material passing a 4.75 mm AS sieve shall have a Sand Equivalent value not less than 80.
f5a18c7f-703d-5f7e-81ca-c12ceedc3984 | note | ○ Shall comply with Table 702.051
fc8d2b64-6ff4-51ac-9258-2e5138a02a0e | textbox | Reference: Material approval in Teambinder:
98352bb1-2077-55c2-b132-379ef9517cde | note | Method - Verify, Document Review
e9f5c8c6-5cfe-5478-bef9-ed7d1acc3797 | note | Frequency - When applicable
02906ec6-3c30-59a6-b68f-5e96188032d7 | note | Category - HP
79f44cf1-8c50-5017-ac17-47d7f811fb75 | note | Responsibility - Nominated Authority
735aeecb-9017-5140-a893-b3032dc86668 | note | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
0bdabd11-5bf3-5148-a790-679c9ecb719b | date | Date Completed:
79b87532-e6cd-416a-bfee-e58081eff16c | signoff | AUTHORITY HOLDPOINT
5afedf46-be06-4a2e-bf75-75822a2cf80d | checkpoint | 2.5 - Tamseal
fb311eba-e398-5d32-ab5f-91b89c9beef4 | note | Reference - IFC Drawings
446b390f-f067-5219-b349-363e60620756 | note | Acceptance Criteria - Tamseal 10GM high performance elastometric liquid membrane
b8d0f168-929b-5469-8c4e-086e4f473c98 | textbox | Reference: Material approval in Teambinder:
cc4d84c0-5018-52fa-b1c5-f1a3c2acacc6 | note | Method - Verify, Document Review
7321c990-4b97-5fa6-922c-24fdebf2e607 | note | Frequency - When applicable
d75c537b-5a6b-51af-9784-c5cd57439284 | note | Category - HP
65a336b8-b58b-54f0-9cdb-0e9f0a526b4d | note | Responsibility - Nominated Authority
5bbee386-e550-5e9a-b051-d6c99887a5f9 | note | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
a2f5f509-6d51-5633-a40d-b63e88632fce | date | Date Completed:
f08aa421-23fa-4a15-91b8-b65823dcd5e9 | signoff | AUTHORITY HOLDPOINT
8f83caa1-5861-4fbf-9de3-579572e71f89 | checkpoint | 2.6 - Geo textile
2686483c-8562-5803-857b-13576cfddf47 | note | Reference - IFC Drawings VR 702.06
f93b111c-f5e2-5cf6-98cf-1e8831624812 | note | Acceptance Criteria - Geotextiles:
c277366d-d5fd-5d49-a887-3594ca891c2d | note | ○ Shall comply with table 702.061 and the IFC drawings
9a2d647c-a623-5138-83d6-c2dbff337ba2 | textbox | Reference: Material approval in Teambinder:
3cc3e6f4-4d2a-50c2-bc43-f8cf240ad7d1 | note | Method - Verify, Document Review
16322f19-8e53-54fe-bb2c-5d724397c57c | note | Frequency - When applicable
b7c82bf4-9225-576d-b53e-6b6d2e0bf4c6 | note | Category - HP
1738725c-39f8-50bb-9ba7-fc4cfbc69f75 | note | Responsibility - Nominated Authority
03894bdb-2cb0-5aa6-8f01-ce7176287a41 | note | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
dd2510db-7232-5e4b-9289-0d93de59caa5 | date | Date Completed:
05535dc4-dfda-47b3-a3f2-0fc9410ca3de | signoff | AUTHORITY HOLDPOINT
6b389ea0-fe06-45db-bed5-eb06e33fc441 | checkpoint | 2.7 - Drainmat with geotextile fabric
5cb54b48-1327-5294-93e0-06ba5792adcf | note | Reference - IFC Drawings VR 702.06
b98a001f-ad98-5b77-aae2-20beb532aa8e | note | Acceptance Criteria - The Drainmat with geotextile shall comply with table 702.061 and the IFC drawings
c9d8d433-fcf9-5e2c-9169-f1a1bef7a281 | note | ○ Comply with table 702.061 and the IFC drawings
0996771e-bee5-56a5-afd9-f4f54ddceaaa | textbox | Reference: Material approval in Teambinder:
0cff616d-91f4-5af4-ad15-1f705a4d6113 | note | Method - Verify, Document Review
d885fe75-c743-5fe2-96d8-decb9e0e525d | note | Frequency - When applicable
ec219c6e-8db6-5227-b610-234e40ae55af | note | Category - HP
2c69f885-cf2a-5a17-96b2-34e13bf2a25d | note | Responsibility - Nominated Authority
bbeb532d-4767-57ba-89e3-f4c2bcbfab9f | note | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
7760cc79-a66b-59ba-9f7b-6fb022ab2104 | date | Date Completed:
aad7db9d-9660-4057-820e-153c0d5cf53d | signoff | AUTHORITY HOLDPOINT
742c1e62-9001-4794-ade0-4c4afef216fd | checkpoint | 2.8 - Blinding Concrete
9a6083a0-94f6-541e-8a41-c6d4548d9726 | note | Reference - IFC Drawings
4430f18c-d507-598a-b795-9b19fa1aab21 | note | Acceptance Criteria - Blinding Concrete
623ed9c7-54e9-5390-b025-78df53d72a91 | textbox | Reference: Material approval in Teambinder:
3f6751af-3d36-51ee-83db-93f3940cef21 | note | Method - Verify, Document Review
5087b324-6121-5c69-8e5a-9ab86b2b6336 | note | Frequency - When applicable
9090ec05-8414-57e2-acf1-7db01cff78a3 | note | Category - HP
5191587e-569f-53be-a824-063a5a3d2842 | note | Responsibility - Nominated Authority
5a98fc4a-05a3-5b9b-aa44-6db0cfe214b8 | note | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
e64bd6c6-dd5c-5c75-9efd-f7976fa22d75 | date | Date Completed:
58e3ccd6-872b-421d-9b0d-ef7d7de059eb | signoff | AUTHORITY HOLDPOINT
5fd8a3d2-4608-4f26-ab2a-d553380fb140 | section | 3. Pre-construction / Pre-installation Activities
feb4ead9-8e3b-4392-a342-2b01167ef216 | checkpoint | 3.1 - Survey Set Out
937b3f24-e820-5ece-afc0-feb417732a74 | note | Reference - Section 702.03
4bc96358-fde1-50d5-989c-d979b34eee43 | note | Acceptance Criteria - Survey to set out Subsurface Drainage line.
0253be30-7e94-53bd-84a0-dab7ad0a3058 | note | Method - Visual inspection
780a4381-c56f-5629-854a-d278dcfee555 | note | Frequency - Each Lot
407d2b27-afe0-511e-8103-1c4e8274d6a5 | note | Category - HP*
9a20247a-d1fe-5042-9b3d-e076768c10d0 | note | Responsibility - SE/Site Supervisor
26fdcd51-18f2-5290-8286-e385cebc09af | note | Verifying Documents - This ITP
3537df5e-4985-5d68-8763-e8fcab2bed25 | date | Date Completed:
e29ce36e-b1bb-48a1-b973-ce808448a135 | section | 4. Construction / Installation Activities
57180f4c-5c27-4b25-9782-99e636577bff | checkpoint | 4.1 - Placing Blinding Concrete
8cd9582c-5392-52b3-bac5-40a6e002af17 | note | Reference - IFC Drawings
2908edaf-e935-52b8-9c5d-64a4c7ac2e6b | note | Acceptance Criteria - Minimum 50mm thick blinding concrete
0cc934fa-0c8a-5d6e-aa27-5da8724df894 | note | Method - Visual inspection
e4f2a362-37a1-5067-a543-c10647e8e7f8 | note | Frequency - Each lot
39045dfb-6958-597f-9cc0-d3d8861771ed | note | Category - IP
66491d10-9bec-5488-aee9-6784c275f643 | note | Responsibility - SE
5ebf193c-d7c3-544c-b7df-03819e090c23 | note | Verifying Documents - This ITP
22fdf177-4e7e-56d7-a529-90f84955dd34 | date | Date Completed:
9072ecc2-e8f8-4e62-a791-d9fdc22fca35 | checkpoint | 4.2 - Application of Tamseal
187e7bef-a52b-58ac-bea0-9d4b29fb6461 | note | Reference - IFC Drawings
e834cd8d-7e3b-5096-88e3-b01e74eb2a3e | note | Acceptance Criteria - A 2mm thick target dry film to be sprayed in accordance with manufacturers' specifications.
482a88a0-6d81-5dbe-8c61-250e80efcf31 | note | Method - Visual inspection
333f4d35-a53c-5448-8609-b492b9726fe0 | note | Frequency - Each lot
e0d3faed-79f0-56ef-9a67-c26136fd94f3 | note | Category - IP
f3271d69-aa0f-59b2-950e-9b741fcac73a | note | Responsibility - SE
5d4c790f-3f80-5753-a173-a0887ab18784 | note | Verifying Documents - This ITP
0e00f6ab-0f28-5b9c-b0ac-7aca4963c2e2 | date | Date Completed:
38044564-ca87-4b40-a518-b691f398c7bb | checkpoint | 4.3 - Placing the Geotextile behind the wall
60ad25a2-b77b-5c31-a2fe-3e0be29b8c80 | note | Reference - Section 702.07
8c87b52c-fa27-5555-8ac9-b6ea87de48d8 | note | Acceptance Criteria - Placing the geotextile filter fabric such a system shall be placed over the full height of fill which is in contact with the structure
21449576-137c-5c60-b2b1-c5d8b552f4a2 | note | Method - Visual Inspection
8cb44a5b-d4fa-5968-8d99-af8efb2e818a | note | Frequency - Each lot
f366f967-be96-5eaa-8fc1-19b338e9b3de | note | Category - HP
5247f20c-0b3d-50d0-b2f0-4846be7f755b | note | Responsibility - SE/Nominated Authority
7c089534-11d7-5d19-9bc1-cb9f2dcba94c | note | Verifying Documents - Nominated Authorith sign off ThisLine
7364e9fb-d092-555c-a4c4-1f5171c4fb79 | date | Date Completed:
ee30851c-6b77-4aff-991c-a6c3c02c5ac0 | signoff | AUTHORITY HOLDPOINT
12e463b8-da17-4948-90ce-2b81ef72e476 | checkpoint | 4.4 - Placing the Megaflow with granular backfill
e7adc43a-d29c-558b-9f2a-206c58c07629 | note | Reference - Section 702.09 IFC Drawings
47d79062-c2ca-5b6f-be94-a645fcd66c76 | note | Acceptance Criteria - Megaflow shall be placed centrally in the granular backfill such that the megaflow stands vertical, and held firmly in place. The grade of the megaflow shall be not flatter than 1 in 250.
f9fb259d-d898-573a-9358-19f9193b4297 | note | Method - Visual inspection
991ca2b0-7834-52ae-9837-a6d0410ddd1e | note | Frequency - Each lot
436727be-ab12-5d8a-8a16-6f9cbd0f9920 | note | Category - IP
fbb8eece-b584-50cc-a5d5-fe2c5f6d2334 | note | Responsibility - SE/Site Supervisor
3ebec770-3d4c-58a3-b9e4-2632b0769b2c | note | Verifying Documents - This ITP
c4b41898-68a2-5725-8d78-088beecaf529 | date | Date Completed:
cf26ebe6-ea15-4297-ad52-65f1c126e7dd | checkpoint | 4.5 - Placing the verical pipes
cc68b513-07da-5459-a4ed-c95193f5eeb1 | note | Reference - IFC Drawings
4b822a6a-1e2a-5fd8-96aa-4024cb9fe211 | note | Acceptance Criteria - Vertical pipes to be installed as per IFC drawings
27ec7a4b-b766-5eda-b58b-992dfb9a6410 | note | Method - Visual inspection
0e98d45b-29ea-52b7-9215-16b94d28d41d | note | Frequency - Each lot
4b2fb268-5e5b-5c0e-9eb2-92d38c820b84 | note | Category - IP
e32af4bd-a3bb-5f7b-942a-16dfb151a8c8 | note | Responsibility - SE/Site Supervisor
d07f97e9-ddcb-5c19-9bb5-bd5c47dbb319 | note | Verifying Documents - This ITP
3285ed54-186b-50ab-8f39-cd02e683a89b | date | Date Completed:
cb800e93-0495-4fe9-bf1d-317cf44825a4 | checkpoint | 4.6 - Placing the slotted pipe
bd88d465-ac9e-5613-8a00-3f34cf2d20a8 | note | Reference - Section 702.09 IFC Drawings SD 1601
e0bc2210-9829-559d-b649-d43120479c0d | note | Acceptance Criteria - Slotted pipes shal lbe installed as per IFC drawings
319e0403-8476-5d63-bfa8-a691e7404c33 | note | Method - Visual inspection
0470c7f8-ce22-5bd5-923a-f2a9b5cc588f | note | Frequency - Each lot
8e9fac52-af5a-56d5-8e7c-7a60fbacd32b | note | Category - IP
46a5bb82-515e-5bed-acb1-f31e440b3f28 | note | Responsibility - SE/Site Supervisor
c46d1802-6354-537a-93dd-edbaf37dd340 | note | Verifying Documents - This ITP
cc78d688-5be4-5894-b325-165bfe54a98f | date | Date Completed:
88d2722a-4d78-40d3-9af1-49afebb927f7 | checkpoint | 4.7 - Installing drainmat
30ebebaf-10ff-53d7-803c-2cb7a8e3f26c | note | Reference - IFC drawings
7bd287de-31dd-51e3-ad02-b342ac9ebfba | note | Acceptance Criteria - The drainmat should placed along the verticle wall and ensure it is firmly fixed and no movement happen while placing material.
c8bd4aa3-8612-5ffa-bd28-5a4468726930 | note | ○ Whenever the drainmat laps, a overlap length of minimum 75mm should be kept.
54fc6509-8134-5f78-a9f1-c17bc4b7ddb8 | note | ○ At the top of the drainmat the fabric must either be turned over the core or secured against the wall using tape to prevent ingress of soil into the core
105932c1-e86a-54b1-b9f0-a8acd3971b1c | note | Method - Visual inspection
359b2d97-ec45-5fda-9694-7bbffe5fdf5f | note | Frequency - Each lot
bbd30444-aec4-51f7-b655-bf75539f28d0 | note | Category - IP
74bab6a8-af1f-545c-8b2d-9e38f5839fc0 | note | Responsibility - SE/Site Supervisor
47b10d6b-df48-5b58-93ce-0012cb444e65 | note | Verifying Documents - This ITP
d996a19a-7432-54e9-9338-babe927357cd | date | Date Completed:
058d1262-6bd1-4a23-9595-27daa5f4fecc | section | 5. Post-construction / Post-installation Activities
68116f35-d530-4acb-9c89-f198387aa072 | checkpoint | 5.1 - As Built Information
aec88513-4745-56c3-bae2-2b39f9417167 | note | Reference - Section 702.03
ec58846b-e5f5-5b67-97f3-6db1d9f6fbed | note | Acceptance Criteria - The invert of the sursurface drainage pipe or the megaflow shall not be more than 25mm from the specified level and not more than 50mm from the specified line
bcd151cd-015c-5afe-92b8-1d8a5884bc0b | note | ○ Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length
c6113ba1-f10e-55ff-a020-07a7558dca7d | note | Method - Document Review
31c78c3b-7908-5fe8-93e8-50727e201d5e | note | Frequency - Each lot
5fe2fed1-404c-5994-9d09-2b9373dc30c4 | note | Category - IP
b9b2c0b3-434c-5502-82c8-37e95370db73 | note | Responsibility - Surveyor, SE/PE/SPE
febaf176-25ea-5624-8e4b-e85bd595bac7 | note | Verifying Documents - Attach Survey Conformance Report
dffc7496-4739-50f8-a2d0-c37c8501e86c | date | Date Completed:
d5e2ba63-4066-4855-be88-fca9902e93a4 | checkpoint | Final Inspection
c8f015f2-d120-5ef9-9269-2ded80e6657c | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
31d495e7-4351-5084-808a-ea9f4f16b21e | textbox | Name:
e53fcaca-299d-51fb-97f7-54e2959eb5d3 | textbox | Position:
fc42293c-ce3d-51fc-979f-1fa225a4d9eb | textbox | Date Completed:
ee3e02d6-94e0-4313-9b27-5c6b2cd1a20b | signoff | Sign ITP
3a7835f6-776a-415d-a6dc-4ae1f01ecd80 | checklist | ITP-288-CIV-HOP-L Shape walls installation Rev 0 | itp | ITP-288-CIV-HOP-L Shape walls installation | 2e22b8ba-652f-48a2-8594-96e0be37b584
5821ef3f-3900-474e-97d1-7eb1f191f5c3 | section | 1. Referenced Documentation
c89b7951-3bcf-4fde-b090-f184da24ca7c | checkpoint-no-value | Referenced Documentation
641a4f22-03b8-5d1a-823e-5436761a0432 | note | Document Title: ITP-288-CIV-HOP-L-Shape Walls Installation
4823370e-31bd-5e1c-a6a2-511fe15919c7 | note | ITP Description: HOP-L-Shape Walls Installation
82fe8371-3ebe-54ec-be0f-8efae05abfc0 | note | Discipline (e.g. CIV/STR/RAIL): 288-CIV
b9428a9d-08f9-51b0-b386-d078e3576b79 | note | Revision Number: 0
eaea6ee3-1ddb-5711-b45b-b10ebf9b63a3 | note | Revision Date: 8/07/2025
ad75a78f-5df4-5cb8-a5f6-b922a00f3c2f | note | ITP created by: Cedric Guico
bc7f4478-0631-5bac-9949-9e4f56093d4c | note | ITP approved for use by: Pradeep Talasila
66ad9c48-c7fb-54c8-a4b5-6693e0f12d90 | note | 1.1 - Non Dependent
7668d9fa-decf-5ba8-b91f-6659ff47b0b7 | note | Reference - VicRoads Section 610 November 2018
e5c677c0-f05c-5fb4-928a-692b2f27a105 | note | 1.2 - Non Dependent
463e87ec-d46e-52b3-ab85-7c7f60de6c02 | note | Reference - VicRoads Section 610 June 2019
a231401c-1432-584c-990f-25178d559c2e | note | 1.3 - Non Dependent
41f92767-ecf9-59d4-b9a0-5512c3ac77c6 | note | Reference - VicRoads Section 620 May 2009
e23dadba-6813-532e-82c7-d73e5f8dfc67 | note | 1.4 - Non Dependent
62e26fce-c190-515b-a296-9731211a88a2 | note | Reference - VicRoads Section 630 October 2013
c9f5d07b-7aab-423b-ac1c-3d05b7df5a20 | section | 2. Preliminaries-Materials
d09799dc-005d-42ca-884c-a6cf9cfa9b46 | checkpoint | 2.1 - Precast Elements
aaaae68f-5aad-5465-8987-ec020c0e5db3 | note | Reference - IFC Drawings
b590c522-567e-5fa0-a67b-983f6f7265b1 | note | ○ 610.46 (a), Table 610.463 (November 2018)
002f4475-dfdd-5e53-b2ee-a761d737baf0 | note | ○ 610.47 (a), Table 610.473 (March/June 2019)
a8fe2a1f-0ba3-5269-aa04-eaf1b489971d | note | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
61151b21-c38f-52d3-ad8b-1e9d28db7c0c | note | i. Certificate of Compliance / Birth Certificate
f98b029f-065d-57c8-a115-fd1f4a52ebc1 | note | ii. Compressive strength test results
78a379c0-7ca0-54d6-919b-eedd2e405fe7 | note | iii. Precast Lifting Design
8013c91b-1712-5744-afa0-f384a08174dc | note | iv. Pre-pour check sheet / ITP
908d552a-3691-56f1-a4f7-cf852446577e | note | v. Post-pour check sheet / ITP
52f7663d-8534-53bb-9b77-54efd59c3043 | note | vi. Covermeter check record
c7bc0f40-ba03-5d4b-be37-5bff3dd9a043 | note | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast shown on table 610.463 (November 2018) / 610.473 (March/June 2019).
c74297e1-5a19-5932-9c60-657b732ebbb1 | note | ○ Note: Different revisions of 610 have different clause numbers
c6ce6416-eef4-5014-b3c6-b17a7d6411e9 | note | ○ Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
0366da84-f12d-562b-acc0-9172ac53a8f5 | note | Method - Document Review
7f128951-a39b-5a9a-957f-ffbba14974ab | note | Frequency - Each element
49c3233c-c33f-5a4a-bce3-b32414e6bd2f | note | Category - IP
dceee158-113b-50bc-a454-5e73adfb7b03 | note | Responsibility - PE/SE/SPE
d4d58354-8de8-5594-94c1-4b08165fc205 | note | Verifying Documents - This ITP
e3d2ee42-179f-5bef-b930-5479399672b7 | date | Date Completed:
c373ab8c-3625-4677-9274-e33265ac0ad8 | checkpoint | 2.2 - Backing Rod and Joint Sealant
68977a7f-ac2d-5d7b-98e4-d446a1f02ae5 | note | Reference - MRPA Quality Management Plan
5be2b289-0f70-53b3-ad74-65e9514bd77a | note | Acceptance Criteria - Details of the backing rod and joint sealant used to seal around the precast element to be submitted for review to the Nominated Authority.
1515c140-04ae-5f25-8610-f4933fe40825 | textbox | Enter: Teambinder Material Approval number
db7d160f-a883-5a7e-98a6-325227d8f6e4 | note | Method - Document Review
72005709-7239-5adc-aaa4-75f3319c823c | note | Frequency - Once, for each product
ac393fd9-c4a9-5f9f-915f-f86e83148389 | note | Category - IP
95f544e3-7d49-5ae4-b588-2d7673fffdca | note | Responsibility - Nominated Authority
9ced2205-a271-56a8-98e7-a39821aec4ff | note | Verifying Documents - This ITP
b98d1098-3aef-5af6-83e3-7ddf1cc46ce2 | date | Date Completed:
2b418c7b-f6a1-4856-ab3e-88df230d6612 | section | 3. Preliminaries-Procedures
23f705e3-d437-4d12-a122-d1b5f75e32d9 | checkpoint | 3.1 - AC Geo inspection
7d30bae1-1461-5e2f-a836-64c1491bda33 | note | Acceptance Criteria - The formation level of the foundations shall be approved by the Geotechnical engineer before placement of blinding concrete commences.
dc57f3eb-c534-54bc-b699-3e8db25b5312 | note | ○ Bearing capacity of the founding material of L-shaped retaining wall needs to be verified by the Geotechnical engineer. The founding material is required to have a minimum undrained shear strength of 100 kPa to satisfy the bearing capacity.
aa8202ba-16e7-5933-bf54-7b64ed696b19 | note | Verifying Documents - This ITP
fb660b45-f58a-52fa-aadd-8f1090b06bd1 | date | Date Completed:
a48b3fbf-851d-4187-bc9a-442d78bee013 | checkpoint | 3.2 - Materials Inspection Checklist
008ee70d-a473-56f3-8058-c67b10d61a3b | note | Reference - 620.06, 620.07 MRPA Quality Management Plan
12e3e541-8ac3-5a7f-9d35-72ee131a131d | note | Acceptance Criteria - General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
7426b67e-5f42-5165-90b6-236a9036be4a | note | ○ Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
fa5579df-0baf-508e-8f68-70ca1818c62b | note | ○ Elements shall have unique identification and orientation marked (if applicable).
c6b9c03c-3446-571f-b184-0c1ad03a6745 | note | ○ Complete: Materials Inspection Checklist in ConQA
4830dd56-fa00-5af4-a284-c4b5b660d755 | note | Method - Measure, Visual
8d8a2aa5-e25e-52df-9360-3bdf23ad55b6 | note | Frequency - Each element
a76d0116-fb80-5efe-9cb7-e93781ac5fce | note | Category - IP
76eb8396-2b72-5d5f-9788-01a24036a795 | note | Responsibility - SE/PE/SPE
ad974856-d065-599c-ba9e-8569b3e9df83 | note | Verifying Documents - This ITP
cab7ee81-198e-5af2-b934-e6304d1c8057 | date | Date Completed:
65bdcf4c-f6c6-4947-adff-408d77103eac | section | 4. Pre-installation Activities
b9893ce5-61bd-4e3e-83bc-34c56a1f006c | checkpoint | 4.1 - Survey Set-out of Precast Elements
310031a0-7c4b-5874-aaf9-b6f96dfec9e2 | note | Reference - IFC Drawings
ea4336de-b6ba-5ae1-85c5-c8149b068b09 | note | ○ 610.46 (a), Table 610.462 (November 2018)
1edc730f-4c9d-5c7e-abd1-98578df917ce | note | ○ 610.47 (a), Table 610.472 (March/June 2019)
b05a87e0-ec47-5859-9d70-94e2008d948c | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 / 610.472 as applicable to the element.
52a1a122-ce0d-5870-bc2d-6f0b077af7a5 | note | ○ Where anchor bolts or steel posts are cast in to the concrete, ensure that these are within tolerance.
ec30afc5-9305-5acf-9831-01c03620b40a | note | ○ Wall alignment will be surveyed and marked using control points.
8729822d-ffc4-5998-81ec-7765a54416e8 | note | ○ If the precast elements are being connected with a stitch pour, mark any clashes from protruding reinforcement with the planned locations from the precast.
4560f859-7721-510b-b1a1-97f64431609e | note | ○ Note: Any clashes should be levered out of the way using a crow-bar or similar - avoid hitting with a hammer on bars with a tight radius.
6b82a53d-53d1-5cc0-92df-8a907af31455 | note | Method - Measure, Visual
625ba077-1329-5e68-a3fc-13fd040e9d8e | note | Frequency - Each element
64239b68-0379-5f70-8fc1-97c28f70f88c | note | Category - IP
d6398ffa-eea5-5997-8e51-4d4ece706d8b | note | Responsibility - Surveyor, SE/PE/SPE
125d90a8-10fb-58e1-9b39-7bdf703b8b6a | note | Verifying Documents - This ITP
3c68e73f-2abf-563c-9aa6-5ebd799bc67e | date | Date Completed:
06154296-ab4e-49e5-a055-dcbd559965fc | checkpoint | 4.2 - Pouring the blinding Concrete
df74bfdc-6b7e-5e1f-8a83-1a7b96863929 | note | Reference - IFC Drawings 610.18
767aa7c2-2d3e-5724-a889-dd9a98e02c41 | note | Acceptance Criteria - 50mm of blinding concrete (32Mpa) will be placed over the compacted ground to provide a clean, level, and stable working surface.
d5f4a57d-5358-5a9b-af4e-8c959442a259 | note | ○ The blinding is to be saturated before proceeding with precast L-Shape wall installation
1a713b5c-f037-5f22-85f3-b4a286dbbf5a | note | Method - Visual
f3d45c89-1291-5c04-939f-04dee5891b98 | note | Frequency - Where applicable, each installation location
ab2ab6e3-6986-5e6d-93df-cf34af10314f | note | Category - IP
ceea7ac6-6375-5c41-9ce1-1d6b6f51aa4e | note | Responsibility - Surveyor, SE/PE/SPE
23ef4b0d-a33a-5943-aaf4-6bb4e504a78b | note | Verifying Documents - This ITP
e2a9eaa9-0b6e-51b2-bd0d-db4da840d1e8 | date | Date Completed:
d18838ac-5057-414a-94e8-8e22136aeac8 | section | 5. Installation Activities
8b334a9f-42cf-49b7-9c3a-2bb66a4ab65c | checkpoint | 5.1 - Precast Handling
a3f8918f-04ef-527e-94d6-60df20f89e7c | note | Reference - 620.07 Crane Lift Study
d9ec7872-7c2f-550d-9e2c-2c4946619e90 | note | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
4fd80c17-a635-5c79-aa30-f96c868811c9 | note | ○ JYC will position and align the precast L-wall using crane (type TBC) and rigging equipment which will be as per the approved lift study and it will be added to (07 Lift Study)
6217f15d-aa0e-551b-8750-f9f6773a8a0c | note | ○ Only certified riggers and dogmen will handle lifting operations.
bef422ca-c8b8-596a-8c18-c1c62e33d1e8 | note | ○ Lifting clutches will be attached at designated lifting points on the precast units as per Westkon’s Lifting design which will be part of the approved lift study.
832358d8-d8f5-5229-bf4d-8e9ce453d902 | note | ○ Verticality of the upright section shall be maintained throughout lifting operations
9ef1872a-6535-514b-a192-fb362cbc03ae | note | ○ Taglines will be used to control movement of the precast unit.
1ced93c7-7a9f-579c-904c-0f29fd9d8ec3 | note | ○ The units will be lifted smoothly and slowly to minimize dynamic loads on the lifting gear.
1b21dfa7-8249-5b68-9905-32b10142f9f2 | note | ○ The L-wall will be lowered onto the blinding concrete, ensuring alignment with survey markers.
2d8349fc-66db-5644-9f57-12f7acf78b45 | note | ○ Positioning may be adjusted manually using crowbars if required.
cd29188d-5c42-5a06-b913-7a732f9b14ce | note | Method - Visual
d8cefe20-77e7-5481-8f60-4e2d8db0b0c7 | note | Frequency - Each element
f11a8e65-be09-5554-8ae0-a0454a2e0603 | note | Category - IP
ac1ce312-baf8-5ce3-8dba-1da6756307a7 | note | Responsibility - SE/PE/SPE
dac1571b-31ce-5d6c-a7da-a69658c833f5 | note | Verifying Documents - This ITP
ba2ae33d-6bcd-5eb7-84b7-464bd91c1a68 | date | Date Completed:
f3ef579d-c75d-45c7-b51c-91a051cf1b0c | checkpoint | 5.2 - Precast Placement
d631bc41-5144-574b-ba6d-01d787db2f8d | note | Reference - IFC Drawings, Temporary Works Design 610.27
030e4f4a-f463-5ec9-b998-3ea72f195798 | note | Acceptance Criteria - Precast elements shall be placed into location or and not released from the crane until sufficiently braced, wedged or restrained by bolted connection, in accordance with the approved Temporary Works Design and/or IFC drawings.
60f6e50b-10ca-5639-bb83-c5a72c415db1 | note | ○ Make any adjustments necessary so that alignment between units, minimum end bearing, overall height and position remains in tolerance.
0c384887-4e10-5f60-852e-c70daf9b5cc2 | note | ○ The nominal gap between elements is as per the IFC Drawings.
fd47c95f-480c-5d5e-b426-aa7895bcd904 | note | ○ To ensure the horizontal alignment on the L-walls are maintained, the precast units will be held together on top using 150x150mm Z-plate and 15mm Z ties + nut:
d709540a-47a0-5387-8475-65c7cadabc15 | note | ○ Ensure 20mm gap is in place, as per the IFC drawings
9ef7ba10-30d3-5346-9eed-a8c2525da55a | note | Method - Measure, Visual
25b3692d-5ce5-5edd-afb4-81f833b7d1ed | note | Frequency - Each element
a88e8414-6034-56b0-9735-8011aef55490 | note | Category - IP
5acf2da5-73fe-5636-a6ee-21599c0057e6 | note | Responsibility - Surveyor, SE/PE/SPE
a5540334-494b-54ee-a02e-da70108b0b53 | note | Verifying Documents - This ITP
af18bcc6-583b-55e6-a3fa-90ffa505f1d1 | date | Date Completed:
0c4d4c12-9fab-473e-bfa7-26fc7d9cd06a | checkpoint | 5.3 - Waterstop Seals, Compressible Seals
dc57e703-1639-5a85-854f-26bae612f3a1 | note | Reference - IFC Drawings, Product TDS
9d9e78ed-9fa6-557f-b24d-b912c0b1d63d | note | Acceptance Criteria - Materials shall be the system(s) nominated on the IFC drawings - any changes must be approved by the designers if no approved equivalent exists.
06316f1e-8dbb-56fd-bf7f-07c2bcd6d0a3 | note | ○ Adhere any waterstop seals or expansion materials full height of the structural element(s) and located as per the IFC drawings.
fbfcc353-bfc1-595a-b940-2aef06889bb0 | note | ○ Once all the Precast Units are tied together, the panels must then be grout flooded underneath to ensure full contact between the underside of the panel and the fill material. The side of the panels will be shuttered or sealed to ensure grout doesn’t flood the entire area. A high early strength grout mix will be delivered on a truck. The grout will be pumped from the top – through the pre-formed holes to ensure the entire space is filled.
a5a0982b-f61a-5647-b35f-a22ba57977c6 | note | ○ Grout samples will be tested at 6 hours, 8 hours, 10 hours, 12 hours, 14 hours, 16 hours, 18 hours, 20 hours, 22 hours and 24 hours. 10MPa is required to be achieved on the grout prior to any backfilling works commencing
dfff1054-0bd1-53e6-bf6f-42a15b63dc77 | note | ○ The process will be repeated for each L-wall unit, maintaining consistent joint spacing of 20mm. 20x20mm Proseries Flexi Seal Industrial grade sealant and Expanded Polyethylene backing rod will be installed to all joints along full height of the Precast Panels:
3407ceb7-5c08-572b-8ea4-37db74175c51 | note | Method - Measure, Visual
d3e967c7-e213-510a-98f8-56f6acf609e5 | note | Frequency - Where applicable, each installation location
71a681f4-f2f9-5282-9a95-8c9a036a85d6 | note | Category - IP
f10e865c-56b7-5e11-82a7-04403499d636 | note | Responsibility - Surveyor, SE/PE/SPE
8d1c05fb-72d7-5318-9ab2-9092e80d52df | note | Verifying Documents - This ITP
0e329d27-52e2-5c07-914a-9d51432bc525 | date | Date Completed:
0e17b690-f0f3-4325-952c-664d6fb60382 | checkpoint | 5.4 - Subsurface Drainage (Megaflow)
8cfd140d-2d6a-56e0-8889-5b5c003e85be | note | Reference - IFC Drawings
7ab2fcbc-dae2-5c15-8921-33dd3d3126c3 | note | ○ 702.03
80019cea-e32e-53c5-8c62-ace6f6e7e9eb | note | ○ 702.06
fad3c827-62ac-50a5-8d3c-afe22b3a7924 | note | ○ 702.07
9c4d0142-d998-5c0b-adc6-3f6fd31f7e7b | note | ○ 702.09 (f)
f2d33ffb-d045-5ca0-b52a-21e542c97fd8 | note | Acceptance Criteria - Subsurface drains shall be the type nominated on the IFC drawings - any changes must be approved by the designers if no equivalent exists.
c73d9548-c594-51cf-b41b-8c58f9f935c2 | note | ○ The drainage shall be wrapped in geotextile, full height of the structure and located as shown on the IFC drawings.
8dc6a0d5-fdb2-5f86-a89c-3f14c11236df | note | ○ Joints in the drainage shall be over-lapped 450mm min. by the geotextile.
df655565-b44d-546f-b7d5-cdeba2b96bbd | note | ○ Weep holes shall be checked for obstructions.
3b3c4cab-7a16-5180-b752-29199dbfc0b5 | note | ○ Drainage installation will be completed progressively after each Precast element is installed in the steps outlined below.
025c65cf-7f90-5b38-98bc-ebed7460f3bc | note | ○ Prior to commencing the drainage install for the L-Shape wall, the surface of the L-Shape wall will be cleaned to remove dirt, dust, and debris before applying waterproofing.
9af51345-e741-5628-a67c-534b1897054c | note | ○ TamSeal 10GM High performance Elastomeric liquid is to be applied to the back of the L-Shape wall using spray as per the manufacturer’s instructions ensuring 2mm target dry film thickness is achieved for proper waterproofing and allowing the membrane to cure. The TamSeal 10GM is to be applied 300mm high up precast wall and 300mm wide along base slab.
720008ef-528c-5f9b-a7f8-c7d45c556f5a | note | ○ The 50mm thick blinding layer (either compacted sand or lean mix concrete) will be placed along the base of the L-Shape wall on the TamSeal 10GM, ensuring the surface is level and smooth and allowing sufficient curing time (if concrete is used) before proceeding.
cc05f69f-5bb1-5665-930b-6bfb84ce2b61 | note | ○ The Megaflo Green Drainage System @ 1:200 gradient will be positioned at the base of the L-Shape wall as per the design drawings ensuring proper alignment and connection to the stormwater drainage outlet. The drainage pipe will be secured in place before backfilling with Type A Fill.
3262a9ba-4e99-5d93-bd57-2283afc5ba8c | note | ○ The Drainmat Geosynthetic medium with A34 Geotextile Fabric will be fixed against the back of the L-wall, ensuring full coverage. The mat will be secured using approved fasteners or adhesive.
2b31a888-4276-5d03-98d5-8f98aeb3009a | note | ○ Free draining granular backfill to VicRoads Spec 702 will be placed on the MegaFlo, wrapped with BIDIM A14 to discharge at a suitable point at end of wall down slope.
83fba176-b060-5def-a784-e306fc1423fa | note | ○ Install approved Drainmat Geosynethtic Medium with A34 Geotextile Fabroc or Approved Equivalent as per the IFC drawings
35bc727c-1b76-5c65-911b-96650d5ed2b1 | note | Method - Measure, Visual
cdf859c9-1555-5e8e-ac90-74795622633f | note | Frequency - Where applicable, each installation location
31ccc8c2-e011-52c8-b37f-df7699862674 | note | Category - IP
53c54fc9-a467-50cd-b5f3-305d9964a374 | note | Responsibility - Foreman, SE/PE/SPE
f49dcd0c-ed33-58ff-91a7-4fcc3485871f | note | Verifying Documents - This ITP
0d79e34f-e0af-5ce9-bb5e-cf12ff9323ad | date | Date Completed:
7608345f-06b9-412c-bc7f-f014b92d2d05 | checkpoint | 5.5 - Precast Traceability
911aaf59-9be2-57aa-8b73-8d5a5d9ed18b | note | Reference - 620.09
01f65965-4f3b-5123-b71f-1de0d1078bac | note | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
3acf3e79-b194-535c-b82b-aaac341d09be | note | ○ Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
d22e763f-3a1b-5509-b1d7-acad87e28a8f | note | Method - Visual
4759fc36-3d11-5f3e-adc1-5aeb8afea05e | note | Frequency - Each element
ae536084-ff9d-5360-8e65-ad3986a3a09d | note | Category - IP
84d45ea3-aa0a-5330-a99a-3a9f5b99f956 | note | Responsibility - SE/PE/SPE
a67f076b-505a-56c2-bfca-40d18c84ef81 | note | Verifying Documents - This ITP
53bed233-c5f7-57e3-a4d8-06b6536fb4bb | date | Date Completed:
9c923443-6b83-4473-ab96-51cc3edda511 | checkpoint | 5.6 - Product Testing - Compressive Strength Cubes
c6671b57-3b75-5550-af08-10dad8a9ccb8 | note | Reference - 610.28, 610.33
655637d6-ead4-5f7b-99ee-0538abc7b557 | note | Acceptance Criteria - Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
07210819-c201-58c2-86b5-1e8e198a6213 | note | ○ Testing is be in accordance with the following frequencies:
9096e1a2-f7e9-5bf3-9170-2021ed4ae06a | note | — First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
5aa9d62a-2c34-54d0-aaf1-779bf58639c5 | note | — Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
72961608-166a-57d3-a2a7-348030dcb882 | textbox | Enter: Required information on the Grout Pour Record.
d21b7198-9c8b-5d37-91f9-6347890a8cc8 | note | Method - Test
cc6f2c27-5537-50d2-b5a4-b81b6050442e | note | Frequency - Each element
33783bbb-b568-5d39-8266-2e20d418b40f | note | Category - IP
aed354f0-eddc-52a0-a441-68b21ef312f3 | note | Responsibility - Tester, SE/PE/SPE
ca282012-5eab-5290-8156-2848708b9e54 | note | Verifying Documents - This ITP
c0281f5d-5a4c-541d-9974-e1075247f6d7 | date | Date Completed:
895676c8-5fc9-4c63-8912-4edc57e68394 | section | 6. Post-installation Activities
e8a7d5f3-121c-4824-ad02-66b44fc7b48f | checkpoint | Compressive Strength Test Results
57bf3579-f5a9-540e-a20a-5c1f4060adb9 | note | Reference - IFC Drawings, Product TDS
cc7acee6-70ca-5059-8f8a-f128af2985cf | note | Acceptance Criteria - 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
ee556ecc-ba0e-5490-bf85-7420dd7b5d40 | note | ○ 28 day compressive strength per sample comply with the design strength.
2a5f98c7-c130-53eb-b7a3-8346c3239ea1 | note | ○ Attach: Compressive Strength Test Results
25475f9f-1c17-5978-bf05-3bc0c9bb4732 | note | Method - Document Review
fabb9a44-51f7-54d6-a072-5234aeef2e6e | note | Frequency - Each cube
6c107e63-ed17-59e6-9120-cec635a82e46 | note | Category - IP
f294e696-cf9e-5e5c-b8de-0f5685f035d6 | note | Responsibility - SE/PE/SPE
65bf13e7-7105-5090-bb9f-a27e096320ac | note | Verifying Documents - This ITP
f7d394f7-a79b-59b1-98f2-7e79c7b90d4e | date | Date Completed:
4a981ff1-bdf4-45df-9d4d-51bce9fe0d5e | checkpoint | 6.1 - Joint Sealant Application
093c4d35-873d-54b2-9bcc-459d446e5b41 | note | Reference - IFC Drawings
ad91d4c0-dca1-5c6d-9752-77b26ec57b5f | note | Acceptance Criteria - The gap between each precast element or at interfaces with other structures should be sealed with an the approved sealant on top of a backing rod.
fed7e4e8-7489-5449-9898-1372dea9678a | note | Method - Visual
5e684057-19a7-56e2-8012-4f1b6025ae4a | note | Frequency - Where applicable, each element
2bc731e1-cd1c-583f-bb71-5934e77796d5 | note | Category - IP
52a543a0-172e-5a8f-9774-558584b07478 | note | Responsibility - Surveyor, SE/PE/SPE
67055f61-9f1f-524e-a42b-4855bd4bf91f | note | Verifying Documents - This ITP
98ef443c-7b0c-5d40-8225-e79e6c601636 | date | Date Completed:
3c12e35f-71b4-44bd-b46a-381f34782ad2 | checkpoint | 6.4 - As-built Survey
a8f5ca23-a7dd-59a3-9be3-e5a69fca4a29 | note | Reference - IFC Drawings
cdd5f0b2-b8c2-5f94-bcf9-cf7a449e4851 | note | ○ 610.46 (a), Table 610.462 (November 2018)
46f02ca0-d4b6-539b-8ce2-40fb89b25377 | note | ○ 610.47 (a), Table 610.472 (March/June 2019)
a1153994-58e1-53e8-9979-ba0f50dad229 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 (November 2018) or 610.472 (March/June 2019) as applicable to the element.
ef3dcbef-cfb5-5720-84b9-c68e30738970 | note | ○ Attach: Survey As-builts / Survey Report
3c6feed0-eb3b-5fea-a672-53133c645a44 | note | Method - Document Review
42076c92-e035-5cff-bdab-603d42a4a790 | note | Frequency - Each element
6c8cc516-d42a-5433-ac6a-d98f3738862c | note | Category - IP
434f89c0-3d7d-519c-a719-042579d7c025 | note | Responsibility - Surveyor, SE/PE/SPE
ae0b1370-49f1-5a3b-8ae8-de2d0c627ad8 | note | Verifying Documents - This ITP
8c746f61-f24e-5d5a-8778-b34da7e34ce5 | date | Date Completed:
93217199-c15f-402b-a792-d043ca40d145 | checkpoint | 6.5 - Non-conformance Report (NCR) Closure
519e76ee-a61f-5037-a5af-ec55f2ea94de | note | Reference - MRPA Quality Management Plan
067e82e8-09d7-5cb5-8776-eae7f011eff0 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
6ad8cdd4-9d47-5eb3-92e0-044bb16991ce | note | Method - Document Review
55d32bbe-b329-5446-8acc-17311f244f8c | note | Frequency - Once, prior to closure of this lot / element / Work area
d89e4693-d043-51ea-8f29-8f97c7e78286 | note | Category - HP*
ae83effe-9fcd-58d9-a3f6-11bab8a5d2ea | note | Responsibility - SE/PE/SPE
57402727-e0cd-5020-a829-2b4eaf7e0b42 | note | Verifying Documents - This ITP
84f15f26-4c25-5fc7-909a-d83971304114 | date | Date Completed:
07086de4-3c07-4b74-b133-bbff40cb4e0d | checkpoint | 6.6 - Monitoring of L-Shape Wall
cb9c7af8-cfa2-5a2d-95b7-0f1f24587964 | note | Reference -
df341559-3d9b-5ff4-a77e-4f0ed00616ad | note | Acceptance Criteria - Allowances shall be made for monitoring of L-Shape wall movements during construction. Minimum two survey markers for each 10m at the top of the wall and middle of the wall (only for wall more than 3m) shall be installed to monitor the displacement in three directions. Monitoring shall be carried out once a week during construction to the end of practical completion and once in every six months following practical completion up to defects liability period by installing Prisms. The construction team to maintain and not damaging the survey markers at all time.
010c52ad-cdf3-5e45-be39-aa40312d3e92 | note | Method - Visual
9380c91a-791e-50cf-9665-c2a8061667db | note | Frequency - Where applicable, each element
e2008cd4-7524-58d6-b33c-ad0ed90dc55b | note | Category - IP
218320e9-a2c0-5fc0-aceb-682334ee7e51 | note | Responsibility - Surveyor, SE/PE/SPE
2c2599a1-7d85-585a-a773-d4ace1ee684e | note | Verifying Documents - This ITP
3e6f0d70-2761-529b-a56f-d83592010099 | date | Date Completed:
0a0f172f-734a-48a3-b9ba-063e16c4a485 | checkpoint | Final Inspection
dfed08f0-0776-5456-a6b6-66143d826ff3 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
536b35e8-a559-5a86-bfce-fad6047f8eee | textbox | Name:
9921f09d-53b1-52aa-ac2a-d36e6d270ddc | textbox | Position:
3268f519-d1ec-542f-9449-4a82a9988445 | textbox | Date Completed:
9b108a1c-a348-47fd-88e6-2991239f0bdc | signoff | Sign ITP