## res_ITP-217-CIV-HOP-Subgrade Pr
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-239-CIV-HOP-Stormwater Drainage Pits-Headwalls Supply and Installation | itp |  |  |  |  | ITP-239-CIV-HOP-Stormwater Drainage Pits-Headwalls Supply and Installation Rev 2
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-238-CIV-HOP-Stormwater Drainage Pits Supply and Installation
label | ITP Description: HOP-Stormwater Drainage Pits Supply and Installation
label | Discipline (e.g. CIV/STR/RAIL): 238-CIV
label | Revision Number: 2
label | Revision Date: 6/08/2025
label | ITP created by: Cedric Guico
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - VR 701
section | 2. Preliminaries - Materials
checkpoint | 2.3 - Precast Drainage Pit
label | Reference - Section 705.07, Section 705.04, Section 705.09
label | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with Section 705.07 & 705.09
label | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of Section 705.04. Concrete grades shall comply with Table 705.041
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Precast Headwall
label | Reference - Section 701
label | ○ Section 703
label | ○ Section 610
label | ○ Standard Drawing 1941C
label | ○ Standard Drawing 1921C
label | ○ Standard Drawing 1992A
label | ○ Standard Drawing 1991A
label | Acceptance Criteria - Precast headwalls shall be manufactured, supplied and installed in accordance with Sections 701, 703, 610 and relevant standard drawings as per the IFC package
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Cast in Place Drainage Pit / Headwall
label | Reference - Section 705.06 IFC Drawings
label | Acceptance Criteria - Cast in place drainage pits shall be constructed in accordance with the requirements of Section 705.06 and at the locations and to the dimensions shown on the drawings.
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Drainage Pit - Step Irons
label | Reference - Section 705.04, Section 705.12
label | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
label | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with Section 705.12
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures & Documentation
checkpoint | 3.1 - Subcontractor QA Submissions and ITP
label | Reference - VR 701
label | Acceptance Criteria - Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications..
label | ○ ATTACH: Subcontractor Signed ITP
label | Method - Document Review
label | Frequency - Each Lot (in case undertaken by subcontractor)
label | Category - HP*
label | Responsibility - SE
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
section | 5. Construction Activities
checkpoint | 3.1 - Survey Set Out
label | Reference - VR 701.10
label | Acceptance Criteria - Survey activities undertaken to ensure and validate the plan location, height and line of pits in accordance with design documentation and 701.10
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.2 - Pit Excavation
label | Reference - VR 705.05
label | Acceptance Criteria - Excavation shall be to the depth indicated on the design documentation. Precast pits must have a clearance of 400mm from excavation face and external face of pit.
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.3 - Excavation Foundation
label | Reference - VR 705.05
label | Acceptance Criteria - Bedding conforming to to 710.09 shallbe supplied, placed and compacted to a thickness:
label | ○ > 80mm for clay foundations
label | ○ > 150mm for rock foundations
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.4 - Jointing
label | Reference - VR 705.11
label | Acceptance Criteria - All connections shall be finished to provide a smooth surface, uniform with the inner of the pit structure. Saw cut surrounding hole shall not exceed 50mm greater than the pipe diameter.
label | ○ Exposed reinforcement shall be coated with an approved epoxy treatment
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.5 - Shaping of Floor
label | Reference - VR 705.13
label | Acceptance Criteria - Pit floors are smoothly shaped from inlet to outlet for a height one third the diameter of the outlet pipe.
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.6 - Step Irons
label | Reference - VR 705.12
label | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with AS 1657. Ladder rungs shall not obstruct openings and that water does not discharge on them.
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.7 - Fitting of Covers
label | Reference - VR 705.17
label | Acceptance Criteria - Frames for drainage pit covers shall be cast in place or or bedded on fresh mortar, 5mm thick, consisting of 2 parts sand and 1 part cement.
label | ○ Height shall be within 10mm of the design level
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.8 - Backfilling Around Drainage Pits / Headwalls
label | Reference - VR 705.18
label | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300mm loose thickness and compacted to refusal
label | Method - Visual inspection
label | Frequency - Each Lot
label | Category - IP
label | Responsibility - SE
label | Verifying Documents - This ITP
date | Date Completed:
section | 6. Post-construction Activities
checkpoint | 6.1 - Placement of Pit-Conformity with drawings
label | Reference - VR 701.10
label | Acceptance Criteria - The location of each run of underground drainage shall be verified by a survey certificate prior to backfilling the culverts and shall be recorded progressively on the Contractor’s as constructed drawings
label | ○ Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
label | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
label | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
label | (c) invert level of pipes at pits ±50 mm
label | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | ○ ATTACH: Survey Report
label | Method - Measure
label | Frequency - Each Lot
label | Category - HP*
label | Responsibility - SE
label | Verifying Documents - Survey Report
date | Date Completed:
checkpoint | 6.2 - CCTV Inspection
label | Reference - VR 701.30
label | Acceptance Criteria - All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
label | ○ ATTACH: CCTV Report (PDF):
label | Method - Document Review
label | Frequency - Each Lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - CCTV Reports
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP