## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 02.01 - Traffic Management | itp |  |  |  |  | 02.01 - Traffic Management
section | Details
checkpoint | The Contractor's Nominated Traffic Officer submitted to the Administrator and meets the requirements as specified
label | Acceptance Criteria & Frequency (Project Specific) - Accreditation Supplied to Administrator
label | Check Item - Check Item
label | Reference - MRTS02 Cl. 5.2
textbox | Submitted with TMP |  |  | SE/PE/WS/SS (Submitted with TMP __/__/____)
checkpoint | No traffic rearrangements shall be carried out until after the Administrator has advised the Contractor that the submitted, and amended as directed, TMP is approved and suitable for use.
label | Acceptance Criteria & Frequency (Project Specific) - Approval via Contract Notice - Per NTO
label | Check Item - Hold Point 1
label | Reference - MRTS02 Cl. 5.3
holdpoint | HOLD POINT
checkpoint | All traffic control devices inspected and records kept in accordance with the specification
label | Acceptance Criteria & Frequency (Project Specific) - Site Records - Daily
label | Check Item - Check Item
label | Reference - MRTS02 Cl. 5.6.4
checkpoint | In the event of a traffic crash/incident within the site, the Contractor shall record the date and take time and date stamped photographs of the signs/devices in the vicinity of the crash.
label | Acceptance Criteria & Frequency (Project Specific) - Incident Report - Per incident
label | Check Item - Check Item
label | Reference - MRTS02 Cl. 5.6.5
checkpoint | All TGS's prepared by a suitably qualified person and submitted to the Administrator for review and shall be accompanied with a specific risk assessment, as required. Innovations, alternatives and departures from standards shall be certified by a RPEQ.
label | Acceptance Criteria & Frequency (Project Specific) - TMD sign off of TGS and, RPEQ Risk Assessment as required
label | Check Item - Hold Point 2
label | Reference - MRTS02 Cl. 6.2
holdpoint | HOLD POINT
checkpoint | The Traffic Management Inspection report to the Contractor for action, together with documentation of any actions taken in regard to findings.
label | Acceptance Criteria & Frequency (Project Specific) - Submission of report to Administrator - Per inspection
label | Check Item - Milestone
label | Reference - MRTS02 Cl. 7.5
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 03.09 - Removal of Existing Drainage Structures and Concrete Slabs | itp |  |  |  |  | 03.09 - Removal of Existing Drainage Structures and Concrete Slabs
section | Details
checkpoint | Culverts and culvert end structures shall be removed or demolished where specified in the drawings.
label | Acceptance Criteria & Frequency (Project Specific) - Culvert Removal - Per Culvert
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.2
checkpoint | If existing culvert components are to be removed and re-used, they shall be removed and stacked in a manner which avoids damaging the components.
label | Acceptance Criteria & Frequency (Project Specific) - Visual - Per Culvert
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.2
checkpoint | Removed components which are not to be salvaged, nor reused, shall be removed from the Site and disposed.
label | Acceptance Criteria & Frequency (Project Specific) - Visual - Per Culvert
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.2
checkpoint | Excavations carried out and the void left by the removed culvert or end structure shall be backfilled to reinstate the area to a safe and free draining state.
label | Acceptance Criteria & Frequency (Project Specific) - Visual - Per Culvert
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.2
checkpoint | Existing kerbs, channels, kerbs and channels, kerb crossings and concrete slabs shall be removed or demolished where specified in the drawings.
label | Acceptance Criteria & Frequency (Project Specific) - Visual - Per Kerb
label | Check Item - Check Item
label | Reference - MRTS03 Cl 9.4
checkpoint | Any Kerb and Channel or concrete slab to be removed is saw cut at removal extents or removed to existing joint (or removed in its entirety) where specified in the drawings and no damage shall occur to adjacent work
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl. 9.4
checkpoint | Kerb excavations shall be backfilled to flush with the surrounding area.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl. 9.4
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 03.10 - Supply and Installation of Precast Concrete Culverts | itp |  |  |  |  | 03.10 - Supply and Installation of Precast Concrete Culverts
section | Details
checkpoint | Maximum Lot Size - 1 Culvert
label | Acceptance Criteria & Frequency (Project Specific) - Lot size </= 1 Culvert - Per lot
label | Check Item - Check Item
label | Reference - MRTS04 Table A.2
checkpoint | Concrete Pipe culvert components comply with MRTS25/26 Box Culverts Comply with MRTS24
label | Acceptance Criteria & Frequency (Project Specific) - Manufacture and Test Certificates
label | Check Item - Check Item
label | Reference - MRTS03 Cl10.2
checkpoint | All pipes of diameter 800 mm or less shall have spigot and socket joints with rubber sealing rings. Joints for other sizes shall be as specified on the drawings.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl10.2
checkpoint | Component size, wall thickness and class is as specified in the drawings
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl10.2
checkpoint | Bandage Covers are a Proprietary Product, either: Synthetic or Rubber Band, samples inspected by administrator
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 1
label | Reference - MRTS03 Cl11.2
holdpoint | HOLD POINT
checkpoint | Culvert Construction Procedures to be accepted prior to commencement of Installation
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS03 Cl11.3.1
holdpoint | HOLD POINT
section | Excavation
checkpoint | Excavations shall be carried out in accordance with Clause 13 of MRTS04 General Earth works
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl.11.3.1
checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially unsuitable Material is encountered on site the contactor shall, before proceding with removal, shall notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.3 and CL.11.3
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS04 Cl. 9.4
holdpoint | HOLD POINT
checkpoint | Bottom of excavation compaction tested. 0 - 150mm below foundation -RDD Q140A
label | Acceptance Criteria & Frequency (Project Specific) - Cl 15, Table 15.3(b) CV 95% minimum (1 tests / 50m2 - min 2 / lot)
label | Check Item - Test results
label | Reference - MRTS04 Table A.2
section | Culvert Installation
checkpoint | Components are assembled as per manufaturers specifications, and if possible, contruction commenced at outlet
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl11.3.3, Cl11.3.4
checkpoint | Pipes shall be placed with their external grooved ends or spigot ends facing the culvert outlet
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl11.3.5
checkpoint | The pipes shall be laid with the lifting hole or "TOP" marking uppermost. Lifting holes shall be plugged or otherwise closed off in accordance with the manufacturer’s instructions after the pipe is installed.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl11.3.5
checkpoint | Placed with external groove or spigot end facing outlet with minimum of 50mm bedding material
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl11.3.5
checkpoint | The horizontal alignment of culverts shall not vary from the location specified in the Drawings by more than ± 100 mm
label | Acceptance Criteria & Frequency (Project Specific) - ± 100mm (All points shown on drawings - min 1 per 20m or 3 points)
label | Check Item - Survey Results
label | Reference - MRTS03 Cl.8.2
checkpoint | The invert heights of culverts shall not vary from those specified by more than ± 10 mm and nowhere shall the grades of culverts depart from those specified by more than 1%
label | Acceptance Criteria & Frequency (Project Specific) - ± 10mm, ± 1% grade (All points shown on drawings - min 1 per 20m or 3 points)
label | Check Item - Survey Results
label | Reference - MRTS03 Cl.8.3
section | Backfill
checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS03 11.3.10
holdpoint | HOLD POINT
checkpoint | Backfill material shall not be placed until culverts, structures, pipes, conduits, pits, etc have been completed and inspected, and any specified curing periods have elapsed.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 14
label | Reference - MRTS04 Cl.19.3.3
holdpoint | HOLD POINT
checkpoint | Overlay material within 300 mm of the structure, culvert, pipe, etc shall be general back fill Class A1, A2 or B material conforming to MRTS04 Cl.19.2.2 excep 100% material shall pass 25.0mm test sieve.
label | Acceptance Criteria & Frequency (Project Specific) - Class A1:
label | ○ Class A2:
label | ○ Class B:
label | ○ Except: 100% passing 25mm
label | Check Item - Witness Point
label | Reference - MRTS04 19.3.1, 19.2.2 Table 14.2.2
checkpoint | Compaction - Q142A, Q141B
label | Acceptance Criteria & Frequency (Project Specific) - Top 300mm below Subgrade Level ≥97%, Greater than 300mm below Subgrade Level ≥95% (1 test / 50m3, min 1 per lot)
label | Check Item - Test results
label | Reference - MRTS04 Table 15.3(b)
checkpoint | Moisture content within ranges specified Rainfall Zone: HIGH
label | Acceptance Criteria & Frequency (Project Specific) - Class A1/A2: 70-100%, Class B: 80-110%
label | Check Item - Test results
label | Reference - MRTS04 Table 15.3(c)
section | Completion
checkpoint | CCTV inspection undertaken, report submitted and accepted by administrator. Visual inspection may be approved by the Administrator in lieu of CCTV inspection.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 3
label | Reference - MRTS03 Cl11.3.5
holdpoint | HOLD POINT
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 03.11 - Installation of Culvert Components and Structures - Precast or In-Situ | itp |  |  |  |  | 03.11 - Installation of Culvert Components and Structures - Precast or In-Situ
section | Details
checkpoint | Maximum Lot Size - 1 Culvert
label | Acceptance Criteria & Frequency (Project Specific) - Lot size </= 1 Culvert - Per lot
label | Check Item - Check Item
label | Reference - MRTS04 Table A.2
checkpoint | Culvert Construction Procedures accept prior to commencement of Installation
label | Acceptance Criteria & Frequency (Project Specific) - Administrator Approval - Per Project
label | Check Item - Hold Point 2
label | Reference - MRTS03 Cl 11.3.1
holdpoint | HOLD POINT
section | Excavation
checkpoint | Excavations shall be carried out in accordance with Clause 13 of MRTS04 General Earthworks.
label | Acceptance Criteria & Frequency (Project Specific) - Visual - Per lot
label | Check Item - Check Item
label | Reference - MRTS03 Cl 12.3.1
checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially unsuitable Material is encountered on site the contactor shall, before proceding with removal, shall notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl. 9.2 and CL.11
textbox | Reference Unsuitable Lot No. :
label | Acceptance Criteria & Frequency (Project Specific) - Visual - Per lot
label | Check Item - Hold Point 4
label | Reference - MRTS04 Cl 9.4
holdpoint | HOLD POINT
checkpoint | Bottom of excavation compaction tested. 0 - 150mm below foundation - AS 1289.5.4.1 or AS1289.5.7.1
label | Acceptance Criteria & Frequency (Project Specific) - Cl 15, Table 15.3(b) CV 95% minimum (1 tests / 50m2 - min 2 / lot)
label | Check Item - Test results
label | Reference - MRTS04 Table A.2
section | Installation
checkpoint | Cast In Situ material: In accordance with MRTS03 Cl.6.1, MRTS 70 and MRTS71
label | Acceptance Criteria & Frequency (Project Specific) - MRTS03
label | ○ Cl.15: End Structures
label | ○ Cl.21: Gullies
label | ○ Cl.21: Access Chambers
label | Check Item - Check Item
label | Reference - MRTS03 Cl.6.1
checkpoint | Precast: Installed in accordance with MRTS03-Components shall be laid on a foundation bedding which provides continuous even support to the structures.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | ○ Cl.19: Precast End Structures
label | ○ Cl.21: Precast Gullies
label | ○ Cl.21.5.1 Precast Access Chamber
label | Check Item - Check Item
label | Reference - MRTS03 Cl. 16, Cl. 21, Cl. 21.5.1
checkpoint | Precast: Culverts shall be joined to shafts/pits to form watertight joints using cement mortar. Cement mortar shall be used within one hour of mixing and shall not be re-tempered. The joints shall be finished to given smooth surfaces which are uniform with the surfaces of the shafts.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl. 21.3
section | Tolerances
checkpoint | Gullies/Chambers: Vertical Tolerances: Invert heights shall not vary from those specified by the Drawings by more than ± 50 mm
label | Acceptance Criteria & Frequency (Project Specific) - ±50mm (All points specified on drawings)
label | Check Item - Survey Results
label | Reference - MRTS03 Cl.21.4.2
checkpoint | Gullies/Chambers: Vertical Tolerances: The heights of the tops of back-units, grates and frames shall not vary from those described in the Drawings by more than ± 10 mm
label | Acceptance Criteria & Frequency (Project Specific) - ±10mm (All points specified on drawings)
label | Check Item - Survey Results
label | Reference - MRTS03 Cl.21.4.2
checkpoint | Horizontal tolerances: Gullies: shall not vary from those specified in the Drawings by more than ± 100 mm in the direction of the construction centre line and ± 50 mm in the direction at right angles to the construction centre line. Access Chambers: shall not vary from those specified in the Drawings by more than ±100mm
label | Acceptance Criteria & Frequency (Project Specific) - Gullies:
label | ○ ±100mm in road direction
label | ○ ±50mm perpendicular to road
label | Access Chambers:
label | ○ ±100mm (All points specified on drawings)
label | Check Item - Survey Results
label | Reference - MRTS03 Cl.21.4.1
checkpoint | Gullies/Chambers: join neatly to existing drainage structures, do not pond water unnecessarily and are at heights compatible with other adjacent structures.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl.21.4.2
checkpoint | Gullies/Chambers: Grates on gullies or Concrete top slabs on precast concrete access chambers shall not be installed until all the surveying requirements have been met and notice of such works provided to the Administrator
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 5, Hold Point 6
label | Reference - MRTS03 Cl.21.3
holdpoint | HOLD POINT
section | Backfill
checkpoint | Backfilling of culverts shall not commence until all the conformance and As Constructed Survey requirements have been met and notice of such works provided to the Administrator
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS03 11.3.10
holdpoint | HOLD POINT
checkpoint | Prior to incorporating any Backfill material into the Works, the Contractor shall submit stockpile or source tests results as specified in Appendix A which demonstrate the source meets the specified material requirements
label | Acceptance Criteria & Frequency (Project Specific) - Quarry Material Test Results
label | Check Item - Hold Point 8
label | Reference - MRTS04 Cl. 14.2.1
holdpoint | HOLD POINT
checkpoint | Material for backfill shall be as shown on the drawings or as specified elsewhere in the ContractEarth Backfill Material shall comply with the requirements of Earth Fill Material Class A1, Class A2 or Class B specified in Clause 14.2.2 except that 100% of the material shall pass 25.0 mm test sieve.
label | Acceptance Criteria & Frequency (Project Specific) - Test Results
label | Check Item - Witness Point 5
label | Reference - MRTS04 Cl. 19.3.1
checkpoint | -
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 12
label | Reference - MRTS04 Cl.19.3.3
holdpoint | HOLD POINT
checkpoint | Overlay material within 300 mm of the structure, culvert, pipe, etc shall be general back fill Class A1, A2 or B material conforming to MRTS04 Cl.19.2.2 except 100% material shall pass 25.0mm test sieve. Else where material may contain stone sized up to 150mm maximum dimension
label | Acceptance Criteria & Frequency (Project Specific) - Class A: WPI < 1200, PI > 7, % passing 0.075mm: 15 - 30
label | ○ Class B: 1200 < WPI < 2200
label | ○ Class A/B: 100% passing 25mm
label | Check Item - Witness Point
label | Reference - MRTS04 19.3.1, 19.2.2
checkpoint | Compaction - Q142A, Q141B
label | Acceptance Criteria & Frequency (Project Specific) - Top 300mm below Subgrade Level ≥97%
label | ○ Greater than 300mm below Subgrade Level ≥95% (1 test / 50m3, min 1 per lot)
label | Check Item - Test results
label | Reference - MRTS04 Table 15.3(b) MRTS03.1 Cl.1
checkpoint | Moisture content within ranges specified Rainfall Zone: HIGH
label | Acceptance Criteria & Frequency (Project Specific) - Class A: 70-100%, Class B: 80-110%
label | Check Item - Test results
label | Reference - MRTS04 Table 15.3(c)
section | Completion
checkpoint | A water test on a side inlet gully shall be carried out where the longitudinal grade is less than 1%. Water shall be discharged into the side inlet gully to check uniformity of flow. After the flow has ceased, water shall not pond to a depth of more than 5 mm in any section of the channel.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS03 Cl. 21.6.2
checkpoint | CCTV inspection undertaken, report submitted and accepted by administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 3
label | Reference - MRTS03 Cl11.3.5
holdpoint | HOLD POINT
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off