## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 03.22 - Subsoil Drainage | itp |  |  |  |  | 03.22 - Subsoil Drainage
section | Details
checkpoint | Subsoil Drains constructed to appropriate dimensions, inspect trench prior to backfill
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - BSD-2041
checkpoint | Backfill material shall be damp when placed in trench. Material shall be carefully placed in layers not exceeding 200mm loose thickness. Shall be compacted to achieve effective mechanical interlock between particles.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl 22.3
checkpoint | Subsoil Drains shall be constructed in the locations and in accordance to the drawings. Subsoil Drains shall be installed to the grades specified in the drawings. Where the grades are not specified, the bottom of trenches shall be trimmed to provide not less that 0.5% longitudinal fall towards outlets for pipe type drains and not less that 1% longitudinal fall towards outlets for strip filter type drains.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl 22.3
checkpoint | Cleanout and outlet pipes, Geotextiles, trench backfill, concrete for headwalls and surrounds, marker posts shall be as per specification
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl22.2 BSD-2041
checkpoint | Clean-outs shall be located at the heads of all subsoil drains and at subsequent spacings not exceeding 60m for Type B subsoil drains and 50m for Type D subsoil drains. Cleanouts shall be constructed in accordance with the details shown on Standard Drawings 1116.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl22.3 TMR SD 1116
checkpoint | Marker posts installed where and when required as shown in the project drawings or standard drawings.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS03 Cl22.2.7 TMR SD 1116
checkpoint | Where directed by Administrator, drains shall be flushed until outlet water is clean and flows consistently
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS03 Cl22.3
checkpoint | As Constructed drawings prepared
label | Acceptance Criteria & Frequency (Project Specific) - As constructed drawings submitted to administrator
label | Check Item - Witness Point
checkpoint | All geometric tolerance requirements met
label | Acceptance Criteria & Frequency (Project Specific) - Survey
label | Check Item - Check Item
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 03.35 - Rock Protection | itp |  |  |  |  | 03.35 - Rock Protection
section | Details
checkpoint | Rock employed as per drawings. If not specified, between 150 - 500mm, with at least 50% larger than twice the minimum size
label | Acceptance Criteria & Frequency (Project Specific) - Visual Inspection
label | Check Item - Check Item
label | Reference - MRTS03 Cl 35.2
checkpoint | Uniform appearance overall, and shall not have noticeable overall irregularities in horizontal and vertical alignments. The layers of placed rock shall be of even thickness and of even grading
label | Acceptance Criteria & Frequency (Project Specific) - Visual Inspection
label | Check Item - Check Item
label | Reference - MRTS03 Cl 35.3
checkpoint | Ordering Geotextile Documentation which demonstrates that the design of the geotextile is in accordance with MRTS27 Cl. 6 submitted to the administrator and accepted prior to ordering.
label | Acceptance Criteria & Frequency (Project Specific) - Written Approval
label | Check Item - Hold Point 1
label | Reference - MRTS27 Cl 8.1
holdpoint | HOLD POINT
checkpoint | Geotextile Inspection of product to be incorporated into works. Where Lot sites are greater than 5000m2, a representative sample covering approximately 15 m² of geotextile shall be cut from each sampled roll but not within two metres of the start or end of the roll. Where directed by the Administrator, samples shall also be cut and supplied to the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Visual Inspection
label | Check Item - Witness Point 1
label | Reference - MRTS27 Cl 10.2
checkpoint | Compliance of delivered Geotextile. Geotextile shall not be placed prior to acceptance of the test results by the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Visual Inspection
label | Check Item - Hold Point 2
label | Reference - MRTS27 Cl 10.4
holdpoint | HOLD POINT
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 04.07 - Clear and Grub | itp |  |  |  |  | 04.07 - Clear and Grub
section | Details
checkpoint | Any trees, shrubs and overhanging branches to be left undisturbed shall be clearly marked prior to clearing operations reaching the areas concerned.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS04 Cl. 7.2.2
holdpoint | HOLD POINT
checkpoint | Any trees required by the Administrator for use as marketable timber shall be as nominated in Clause 1.3 of Annexure MRTS04.1. Such trees shall be clearly marked by the Contractor prior to clearing operations reaching the areas concerned
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 3
label | Reference - MRTS04 Cl. 7.2.3
holdpoint | HOLD POINT
checkpoint | As soon as practicable and prior to initial earthworks operations (clearing and grubbing) for any stage or section of the Works, erosion and sediment controls associated with drainage paths flowing through the Works area shall be installed.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS52 Cl. 7.1
holdpoint | HOLD POINT
checkpoint | Hollow timber which is identified as being suitable for fauna habitat logs relocated to areas clear of construction activities
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 7.2.5
checkpoint | Surplus topsoil material and material considered not suitable for use as planting media in accordance with Cl. 8.3 shall be assessed for suitability for use as fill or deemed as unsuitable and disposed in accordance with Cl. 11
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 8.4.2
checkpoint | The scope of clearing and grubbing shall include the items as per Annexure MRTS04.1 Cl. 1.2 and Cl. 1.4
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 7.2.8, MRTS04.1 Cl 1.2 Cl 1.4
checkpoint | The additional width for clearing (no grubbing) is 3.0m as per Annexure MRTS04.1
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - Annexure MRTS04.1
checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 8.4.3
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 04.08 - Stripping of Topsoil | itp |  |  |  |  | 04.08 - Stripping of Topsoil
section | Details
checkpoint | Where site topsoil is required to be supplied in accordance with MRTS16 Landscape and Revegetation Works, topsoil shall be stripped 75mm (+/-25mm) depth, or from areas and depths as specified in Clause 2.1 of Annexure MRTS04.1
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | ○ All areas within the earthworks footprint; beyond the back of existing kerb or where there is no kerb, beyond the existing road formation shall be stripped to an average depth of 75mm
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 8.2, MRTS04.1 Cl. 2.1
checkpoint | Soil stripped from site which is considered suitable for use as a manufactured site topsoil shall be tested and ameliorated in accordance with MRTS16 Landscape and Revegetation works
label | Acceptance Criteria & Frequency (Project Specific) - Insitu topsoil - 1/2500m2, min.1/soil type
label | ○ Stockpile Topsoil - 2/500m3, min.1/soil type
label | ○ Manufactured Site Topsoil Compliance - 2/500m3, min.1/soil type
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 8.3
checkpoint | Surplus material and material considered not suitable for use as planting media in accordance with Cl. 8.3 shall be assessed for suitability for use as fill or deemed as unsuitable and disposed in accordance with Cl. 11
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 8.4.2
checkpoint | Material not to be removed from within drip lines of existing plants to be retained except where this would result in unsuitable material being left beneath embankments. Root systems of existing plants to be retained are preserved where practical.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 8.4.3
checkpoint | Stripped material shall be stockpiled in the locations nominated by the Contractor and approved by the Administrator, as stated in Cl. 2.2 of Annexure MRTS04.1 All costs associated with undertaking necessary earthworks required for the stockpile sites shall be deemed to be included in the Contractor’s scheduled unit rate for the corresponding earthwork items
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 8.4.1, MRTS04.1 Cl. 2.2
checkpoint | All stripped areas, other than areas beneath road embankments or above road cuttings, shall be left in a neat, free-draining condition with side slopes not steeper than one in four unless otherwise specified. They shall be treated to conform with the landscape, revegetation and environmental requirements of the Contract.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl 8.4.5
checkpoint | Prior to any further Works over the stripped area, an As Constructed survey of the stripped area shall be undertaken as specified in MRTS56 Construction Surveying and notice of such Works provided to the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - As Constructed Survey
label | Check Item - Survey Report
label | Reference - MRTS04 Cl 8.4.5
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 04.09 - Unsuitable Material | itp |  |  |  |  | 04.09 - Unsuitable Material
section | Details
checkpoint | The identification of unsuitable material shall include items listed in MRTS04 Cl. 9.2
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 9.2
checkpoint | Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, notify the Administrator and provide any test results required to justify such a claim.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS04 Cl. 9.4
holdpoint | HOLD POINT
checkpoint | Excavated as per MRTS04
label | Acceptance Criteria & Frequency (Project Specific) - MRTS04 (General Excavation ITP)
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13
checkpoint | Backfilling of the excavation shall not commence until an As Constructed Survey of the excavation have been met as specified in MRTS56 and notice of such Works provided to the Administrator
label | Acceptance Criteria & Frequency (Project Specific) - Survey Report
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13.3.2.2
checkpoint | Backfill as per MRTS04 Replacement fill material shall be placed uniformly in layers and compacted using compacted layer method
label | Acceptance Criteria & Frequency (Project Specific) - MRTS04 (Backfill ITP)
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13.3, MRTS04 Cl 15.3
checkpoint | After backfilling of the excavated area has been completed, an As Constructed Survey shall be undertaken.
label | Acceptance Criteria & Frequency (Project Specific) - Survey Report
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13.3.2.2
checkpoint | All surplus material and/or Unsuitable Material shall be disposed of off the Site
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 11.3
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 04.12 - Ground Surface Treatment | itp |  |  |  |  | 04.12 - Ground Surface Treatment
section | Details
checkpoint | Testing for acid sulfate potential and reporting of test results shall be carried out on all excavated material and exposed cuttings on the Site which could reasonably be expected to have a possible acid sulfate potential.
label | Acceptance Criteria & Frequency (Project Specific) - Field pH testing As per National Acid Sulfate Soils Guidance
label | Check Item - Hold Point 5
label | Reference - MRTS04 Cl. 10.1.4 Table A2
holdpoint | HOLD POINT
checkpoint | Ground Surface Treatment carried out on all areas beneath road embankment/pavement (except where special treatment or subgrade preparation is required)
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 12.2.1.1
checkpoint | Holes and localised depressions filled with similar material to the surrounding ground surface or material specified and compacted in accordance with Cl. 15
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 12.2.1.2
checkpoint | Where Unsuitable Material or potentially Unsuitable Material is encountered on the Site, the Contractor shall, before proceeding to remove or cover such material, notify the Administrator and provide any test results required to justify such a claim
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS04 Cl. 9.4
holdpoint | HOLD POINT
checkpoint | Existing surface scarified >150mm deep and compacted in accordance with Cl. 15. If material is too wet or too dry to compact and does not classify as unsuitable, moisture content adjusted to a maximum depth of 300mm using appropriate methods. Material below this depth shall be assesed under Clause 9.2.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 12.2.1.3
checkpoint | Relative Compaction - AS 1289.5.4.1 or AS 1289.5.7.1 After any clearing and grubbing, stripping of Topsoil and replacement of Unsuitable Material, the exposed ground surface on which an Embankment is to be placed shall, as a minimum, be scarified and re-compacted to a depth of at least 150 mm
label | Acceptance Criteria & Frequency (Project Specific) - CV 95% minimum - 1 tests per 500 m2 (min 1 per lot)
label | Check Item - Test
label | Reference - MRTS04 Table 15.3(b) App. A
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 04.13 - General Excavation | itp |  |  |  |  | 04.13 - General Excavation
section | Details
checkpoint | Where Unsuitable Material (in accordance with the provisions of Cl. 9.2) or potentially Unsuitable Material is encountered on site, the Contactor shall, before proceeding to remove or cover such material, notify the Administrator. Once Identified the Unsuitable material shall be removed and disposed of in accordance with the provisions of Cl.11
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS04 Cl. 9.4
holdpoint | HOLD POINT
checkpoint | When the level of excavation has reached subgrade level, the Contractor shall carry out the requirements of the relevant provisions of Clause 18.3.3 and cease excavation until the subgrade treatment type has been determined in accordance with Clause 18.3.3.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 8
label | Reference - MRTS04 Cl. 13.3.2.1
holdpoint | HOLD POINT
checkpoint | Excavation completed to the shapes, lines and dimensions and other requirements shown on the drawings and tolerances specified
label | Acceptance Criteria & Frequency (Project Specific) - Survey
label | Check Item - Check Item
label | Reference - MRTS04 Cl.13.3.1, Cl. 6
checkpoint | Protection of excavations in accordance with MRTS04 Cl.13.3.3.3
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13.3.3.3
checkpoint | Dewatering of excavations shall comply with requirements of EMP
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13.3.8
checkpoint | Batters in cuttings shall be free of loose material and shall be trimmed neatly to the shapes specified.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 16.1
checkpoint | If any section of a batter has been over-excavated beyond the tolerance limit specified, the Contractor shall re-form the batter to the average batter slope shown on the drawings, using an approved rectification method
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Cl. 13.3.2.4
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 04.14 - Embankment | itp |  |  |  |  | 04.14 - Embankment
section | Details
checkpoint | Earthworks construction procedure shall be sumbitted to the Administrator at least seven days prior to commencing the Works.
label | Acceptance Criteria & Frequency (Project Specific) - Construction Procedure Acceptance
label | Check Item - Hold Point 1
label | Reference - MRTS04 Cl. 5.2
holdpoint | HOLD POINT
checkpoint | Define lot size.
label | Acceptance Criteria & Frequency (Project Specific) - Normal : Max 2000m2, Reduced Level : Max 4000m2
label | Check Item - Check Item
label | Reference - MRTS04 App. A Table A.2
checkpoint | Earth Fill Material stockpile or source material results submitted to Administarator
textbox | Reference Stockpile Lot No. :
label | Acceptance Criteria & Frequency (Project Specific) - Stockpile Lot Acceptance
label | Check Item - Hold Point 10
label | Reference - MRTS04 Cl. 14.2.1
holdpoint | HOLD POINT
checkpoint | General fill material used for the construction of road embankments sourced from general excavations on site or imported, complies with General fill Class A1, A2 or B and is homogeneous.
label | Acceptance Criteria & Frequency (Project Specific) - Stockpile Lot MRTS04 Table 14.2.2
label | Check Item - Test reports
label | Reference - MRTS04 Cl. 14.3.1
checkpoint | Compacted Layer Method: Fill material placed uniformly in layers. Uncompacted layer thicknesses;
label | – General Fill 150-300m
label | – Fill material in water-retaining embankments 150- 200mm
label | – Backfill except Sand 100-150mm
label | – Sand 150-300mm
label | ○ Fill compacted to required density (by Characteristic Value)
label | Acceptance Criteria & Frequency (Project Specific) - AS1289.5.4.1 or AS1289.5.7.1
label | ○ Top 300mm below Subgrade Level ≥97%
label | ○ Greater than 300mm below Subgrade Level≥95%
label | ○ Normal: 1 per 500m2 (per layer), 4 per lot
label | ○ Reduced Level: 1 per 1000m2 (per layer) or 4 per lot
label | Check Item - Test reports
label | Reference - MRTS04 Cl. 15.3 Table 15.3(b)
checkpoint | Compacted Layer Method: Embankment moisture ratio within ranges specified Rainfall Zone: HIGH
label | Acceptance Criteria & Frequency (Project Specific) - AS1289.5.4.1 or AS1289.5.7.1
label | ○ Class A1/A2: 70 - 100
label | ○ Class B: 80 - 110
label | ○ Normal: 1 per 500m2/layer or 4 per lot
label | ○ Reduced Level: 1 per 1000m2/layer or 4 per lot
label | Check Item - Test results
label | Reference - MRTS04 Cl. 15.3 Table 15.3(c)
checkpoint | Testing of Each Layer: Each layer shall be tested to conform the requirements as per Clause 5.6 before placing the subsequent layers.
label | Acceptance Criteria & Frequency (Project Specific) - Testing after compaction on site
label | ○ Gradings: AS1289.3.6.1
label | ○ PI: AS1289.3.3.1 or AS1289.3.3.2
label | ○ WPI: Test Method Q252
label | ○ 1 per 1000m2(per Layer), 2 per Lot
label | Check Item - Witness Point 5
label | Reference - MRTS04 Cl. 15.3
checkpoint | Mechanical Interlock Method: Each layer rolled until no further permanent visible lowering of the surface occurs and layer thickness no greater than specified in Table 15.4
label | Acceptance Criteria & Frequency (Project Specific) - Table 15.4
label | Check Item - Witness Point 6
label | Reference - MRTS04 Cl15.4
checkpoint | Geotextile placed at interchange between compaction methods
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 14.3.2
checkpoint | Within Vertical Geometric Tolerance
label | Acceptance Criteria & Frequency (Project Specific) - Subgrade level ± 25, average ± 10, 1 test /20m
label | Check Item - Dip Sheet Records
label | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 04.18 - Subgrade Testing | itp |  |  |  |  | 04.18 - Subgrade Testing
section | Details
checkpoint | All sampling shall be undertaken by the Contractor, in the presence of the Administrator, unless directed otherwise by the Administrator
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point 6
label | Reference - MRTS04 Appendix B.4
checkpoint | Each different material encountered within this depth in Clause 18.1 shall be sampled and tested in accordance with this Technical Specification unless otherwise approved by the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Testing
label | ○ 1.5m below subgrade in CUT
label | ○ 2.0m below subgrade in EMBANKMENT
label | Check Item - Check Item
label | Reference - MRTS04 Appendix B.3
checkpoint | Untreated subgrade material shall be sampled from their natural location in accordance with AS1289.1.2.1. Untreated subgrade materials that break down under environmental and service conditions due to weathering shall be pre-conditioned by artificial weathering in accordance with Test Method Q101E
label | Acceptance Criteria & Frequency (Project Specific) - Testing
label | Check Item - Check Item
label | Reference - MRTS04 Appendix B.4.1
checkpoint | Fil Materials from Stockpile:Materials which breakdown, degrade or fracture during construction, such as highly and extremely weathered rocks, shall be pre-conditioned prior to compacting the specimens for testing. Preconditioning may include:
label | – Lab preconditioning
label | – Field compaction using construction methods propsed for the works
label | ○ The pre-conditioning method shall be recorded in the in the submission of the test results detailed in MRTS04 Clause B.5
label | Acceptance Criteria & Frequency (Project Specific) - Pre-Conditioning
label | Check Item - Check Item
label | Reference - MRTS04 Appendix B.4
checkpoint | Fill Materials after Field Compaction: Obtain samples from the completed fill (after compaction and proof rolling) in accordance with AS 1289.1.2.1. Samples shall be taken over the full depth of the compacted layer.
label | Acceptance Criteria & Frequency (Project Specific) - Test Reports
label | Check Item - Check Item
label | Reference - MRTS04 Cl. B3.2.2
checkpoint | All testing shall be undertaken by the Contractor, in the presence of the Administrator, unless directed otherwise by the Administrator
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point 6
label | Reference - MRTS04 Appendix B.4
checkpoint | Each untreated subgrade material sampe and each fill material sample shall be tested for: laboritory CBR, swell, PSD, maximum aggregate size of fill materials, liquid limit, plastic limit, plasticity index, weighted plasticity index, insitu moisutre content
label | Acceptance Criteria & Frequency (Project Specific) - Testing per material type
label | Check Item - Check Item
label | Reference - MRTS04 Cl. B.5.1
checkpoint | The contractor shall provide all the information to the Administrator as detailed in Clause B.6.2 or B.6.3 as relevant.
label | Acceptance Criteria & Frequency (Project Specific) - Test Reports
label | Check Item - Hold Point 14
label | Reference - MRTS04 Cl. B.6.1
holdpoint | HOLD POINT
checkpoint | For each untreated subgrade lot, the lot CBR, lot swell, and lot expansive nature classification shall be determined in accordance with Cl B.7 MRTS04. For each source and type of fill material, an assigned CBR and an assigned swell shall be determined in accordance with Cl. B.5.2 MRTS04.
label | Acceptance Criteria & Frequency (Project Specific) - Testing per material type
label | Check Item - Check Item
label | Reference - MRTS04 Cl. B.6.1
checkpoint | Untreated subgrade material testing
label | Acceptance Criteria & Frequency (Project Specific) - Test Reports
label | ○ Soaked and Insitu CBR:lower value of the lower 10th percentile of laboratory CBR - per material
label | ○ SWELL: the upper 10th percentile of the swell test results - per material
label | ○ PSD, PI, WPI, LL, PL, Moisture - per material
label | Check Item - Check Item
label | Reference - MRTS04 Cl. B.4
checkpoint | Fill material subgrade testing
label | Acceptance Criteria & Frequency (Project Specific) - Test Reports
label | ○ Soaked CBR:lower value of the lower 10th percentile of laboratory CBR
label | ○ SWELL: the upper 10th percentile of the swell test results
label | ○ Maximum aggregate size, PSD, PI, WPI, LL, PL, Moisture
label | Check Item - Check Item
label | Reference - MRTS04 Cl. B.4
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off