## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 04.181 - Subgrade Level | itp |  |  |  |  | 04.181 - Subgrade Level
section | Details
checkpoint | Define Lot
label | Acceptance Criteria and Frequency (Project Specific) - Normal: Max Lot Size : 4000m2, Reduced: Max Lot Size : 2000m2
label | Check Item - Lot Records
label | Reference - MRTS04 App A
checkpoint | Reporting Pavment Design Requirements. For Contracts where the Principal has supplied the pavement design (that is, Construct Only or similar Contracts), the Contractor shall submit the following information to the Administrator for each existing Subgrade Lot:
label | a) test pit logs
label | b) all test results for each layer encountered within the test pit, including certified test certificates, and
label | c) marked-up drawings accurately showing all test locations within the Lot.
label | ○ The Contractor shall allow a minimum period of 14 days for the Administrator to review the information prior to any Subgrade treatment and the placement of any overlying materials.
label | Acceptance Criteria and Frequency (Project Specific) - Submission to Administrator
label | Check Item - Hold Point 16
label | Reference - MRTS04 App B.6.2
holdpoint | HOLD POINT
checkpoint | Bottom of Excavation for Cuttings: Where subgrade is reached in cutting works shall cease until subgrade treatment type has been directed by the Administrator in accordance with Clause 13.3.2.1
textbox | Subgrade Treatment Type Directed:
label | Acceptance Criteria and Frequency (Project Specific) - As directed by Administrator
label | Check Item - Hold Point 8
label | Reference - MRTS04 Cl13.3.2.1, Cl 18.3.3
holdpoint | HOLD POINT
checkpoint | Subgrade Treatment Type A: As ordered by the Administrator at subgrade level on all section. The material below Subgrade Level shall be to compacted a density of not less than that stated in Table 15.3(b) and to a depth of 150 mm.
label | Acceptance Criteria and Frequency (Project Specific) - Treatment Depth - 150mm
label | ○ Compaction Standard: min 97%
label | ○ Normal: 1 per 500m2, 4 per lot
label | ○ Reduced: 1 per 1000m2, 1 per lot
label | Check Item - Test Reports
label | Reference - MRTS04.1 Cl 12.3, MRTS04 Cl 18.3.3.1
checkpoint | Subgrade Treatment Type B: As ordered by the Administrator at subgrade level on all section. The material below subgrade level shall be compacted to a density of not less than that stated in Table 15.3(b) and to various depths, as directed by Administrator, typically between 150mm and 250mm.
label | Acceptance Criteria and Frequency (Project Specific) - Treatment Depth - 150mm-250mm
label | ○ Compaction Standard: min 97%
label | ○ Normal: 1 per 500m2, 4 per lot
label | ○ Reduced: 1 per 1000m2, 1 per lot
label | Check Item - Test Reports
label | Reference - MRTS04.1 Cl 12.3, MRTS04 Cl 18.3.3.1
checkpoint | Subgrade Embankment: Material to be compacted to requirements not less than that specified in Table 15.3(b) Subgrade relative density tested to Q140A
textbox | Material Source Stockpile Lot Ref:
label | Acceptance Criteria and Frequency (Project Specific) - Top 300mm below subgrade level -
label | ○ Embankment Fill at subgrade: Class A1, B, Unbound Granular or stabilised material : min 97%
label | ○ Normal: 1 per 500m2, 4 per lot
label | ○ Reduced: 1 per 1000m2, 4 per lot
label | Check Item - Test Reports
label | Reference - MRTS04 Cl15.3(b) App A
checkpoint | Proof Roll: Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by:
label | – pneumatic-tyred roller > 4.5T/tyre and 600kPa pressure, or
label | – 10,000L water tanker with 600kPa tyre pressure.
label | Acceptance Criteria and Frequency (Project Specific) - Visual, No Deflection, Continuous
label | Check Item - Witness Point 8
label | Reference - MRTS04 Cl18.3.2 Q723
checkpoint | Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
label | Acceptance Criteria and Frequency (Project Specific) - Subgrade level ± 25, average ± 10, 1 test /20m
label | Check Item - Dip Sheet Records
label | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
checkpoint | Straight Edge Testing: The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
label | Acceptance Criteria and Frequency (Project Specific) - 1 test per 20m (Left and rigt)
label | Check Item - Dip Sheet Records
label | Reference - MRTS04 Cl. 6.3.2
checkpoint | Subgrade shall not pond water and be free draining.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Clause 6.3.2
checkpoint | The subgrade shall be constructed and tested to subgrade level in accordance with the requirements, prior to construction of the pavement.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 12
label | Reference - MRTS04 Cl. 18.3.1
holdpoint | HOLD POINT
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 04.182 - Subgrade Treatment Type A | itp |  |  |  |  | 04.182 - Subgrade Treatment Type A
section | Details
checkpoint | Define Lot
label | Acceptance Criteria and Frequency (Project Specific) - single layer produced in a continuous operation in one day
label | Check Item - Lot Records
label | Reference - MRTS04 App A
checkpoint | Trim and compact existing: Subgrade Density requirements Q140A -Material to be compacted to a density of not less than that stated in Table 15.3(b)
label | Acceptance Criteria and Frequency (Project Specific) - Top 300mm below subgrade level - Existing material in cuttings: min 97%
label | ○ Normal: 1 per 500m2, 1 per lot
label | ○ Reduced: 1 per 1000m2, 1 per lot
label | Check Item - Test Reports
label | Reference - MRTS04 Cl15.3(b) App A
checkpoint | Proof Roll: Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by:
label | – pneumatic-tyred roller > 4.5T/tyre and 600kPa pressure, or
label | – 10,000L water tanker with 600kPa tyre pressure.
label | Acceptance Criteria and Frequency (Project Specific) - Visual, No Delfection, Continuous
label | Check Item - Witness Point 5
label | Reference - MRTS04 Cl18.3.2 RMS T198
checkpoint | Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
label | Acceptance Criteria and Frequency (Project Specific) - Subgrade level ± 25, average ± 10, 1 test /20m
label | Check Item - Dip Sheet Records
label | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
checkpoint | Straight Edge Testing: The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
label | Acceptance Criteria and Frequency (Project Specific) - 1 test per 20m (Left and rigt)
label | Check Item - Dip Sheet Records
label | Reference - MRTS04 Cl. 6.3.2
checkpoint | Subgrade shall not pond water and be free draining.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Clause 6.3.2
checkpoint | The subgrade shall be constructed and tested to subgrade level in accordance with the requirements, prior to construction of the pavement.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 10
label | Reference - MRTS04 Cl. 18.3.1
holdpoint | HOLD POINT
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 04.183 - Subgrade Treatment Type C | itp |  |  |  |  | 04.183 - Subgrade Treatment Type C
section | Details
checkpoint | Define Lot
label | Acceptance Criteria and Frequency (Project Specific) - single layer produced in a continuous operation in one day
label | Check Item - Lot Records
label | Reference - MRTS04 App A
checkpoint | Unbound Granular Material incorporated into unbound treatment shall be as specified in MRTS04.1 Cl. 12.1 and meet the material requirements specified in MRTS05 Cl. 7.
textbox | Material Type:
textbox | Material Source Stockpile Lot Ref:
label | Acceptance Criteria and Frequency (Project Specific) - Unbound Granular Material Stockpile Lot
label | Check Item - Check Item
label | Reference - MRTS04.1 Cl 12.1, MRTS05 Cl 7
checkpoint | Subgrade Density requirements - Material to be compacted to a density of not less than that stated in Table 15.3(b)
label | Acceptance Criteria and Frequency (Project Specific) - Top 300mm below subgrade level - Existing material in cuttings: min 97%
label | ○ Normal: 1 per 500m2, 1 per lot
label | ○ Reduced: 1 per 1000m2, 1 per lot
label | Check Item - Test Reports
label | Reference - MRTS04 Cl15.3(b) App A
checkpoint | Proof Roll: Subgrade material provides a stable dense surface displaying no vertical movement under proof roll by:
label | – pneumatic-tyred roller > 4.5T/tyre and 600kPa pressure, or
label | –10,000L water tanker with 600kPa tyre pressure.
label | Acceptance Criteria and Frequency (Project Specific) - Visual, No Delfection, Continuous
label | Check Item - Witness Point 5
label | Reference - MRTS04 Cl18.3.2 RMS T198
checkpoint | Subgrade constructed to tolerance as stated in Table 6.3.1 Primary Vertical Tolerances unless it cannot be trimmed by a grader
label | Acceptance Criteria and Frequency (Project Specific) - Subgrade level ± 25, average ± 10, 1 test /20m
label | Check Item - Dip Sheet Records
label | Reference - MRTS04 Cl. 6, Cl.13.3.1 Table 6.3.1
checkpoint | Straight Edge Testing: The gap beneath a three metre-long straight-edge placed anywhere on the surface at Subgrade Level shall not exceed 25 mm, due allowance being made for design shape where relevant.
label | Acceptance Criteria and Frequency (Project Specific) - 1 test per 20m (Left and rigt)
label | Check Item - Dip Sheet Records
label | Reference - MRTS04 Cl. 6.3.2
checkpoint | Subgrade shall not pond water and be free draining.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS04 Clause 6.3.2
checkpoint | The subgrade shall be constructed and tested to subgrade level in accordance with the requirements, prior to construction of the pavement.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 10
label | Reference - MRTS04 Cl. 18.3.3.1
holdpoint | HOLD POINT
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 05.01 - Unbound Pavement | itp |  |  |  |  | 05.01 - Unbound Pavement
section | Details
checkpoint | Define lot size. Maximum lot size for unbound pavements is 5000 tonnes for supply and the lesser of "A single continuous layer completed in one day's production" and 500m for construction
label | Acceptance Criteria and Frequency (Project Specific) - Supply of unbound pavement materials - 5000tn
label | ○ Maximum lot size - A continuous single layer constructed in 1 day's production
label | ○ Road rouhness testing: maximum lot size 100m
label | Check Item - Check Item
label | Reference - MRTS05 App. A Table A1
checkpoint | Copies of current Quarry Registration Certificate (Type 1, 2 or 3) or quarry assessment (Type 4) forwarded to the Administrator at least 7 working days before material deliveries to the stockpile / pavement are to commence.
label | Acceptance Criteria and Frequency (Project Specific) - Submission of Registration Certificate per quarry
label | Check Item - Milestone
label | Reference - MRTS05 Cl.6.2
checkpoint | No unbound pavement works shall commence until all relevant construction procedure have been accepted by the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Approval of procedure by from the Administrator
label | Check Item - Hold Point 1
label | Reference - MRTS05 Cl 5.2.1
holdpoint | HOLD POINT
checkpoint | The Material Production Procedures shall be submitted to the Administrator at least seven days prior to the commencement of material production for the works.
label | Acceptance Criteria and Frequency (Project Specific) - Submission of production procedure
label | Check Item - Milestone
label | Reference - MRTS05 CL 5.2.2
checkpoint | Submission of Construction Procedure for unbound pavement construction at least 14 days prior to commencement of works.
label | Acceptance Criteria and Frequency (Project Specific) - Approval of procedure by from the Administrator
label | Check Item - Milestone
label | Reference - MRTS05 Cl 5.2.3
checkpoint | The written permission from the Administrator to use the quarry or source is required prior to material being supplied to or used in the works.
label | Acceptance Criteria and Frequency (Project Specific) - Written Permission from Administrator
label | Check Item - Hold Point 2
label | Reference - MRTS05 Cl.6.1
holdpoint | HOLD POINT
checkpoint | Layer Thickness between 75mm and 250mm for all subtypes excluding Type 1 (HSG).
label | Acceptance Criteria and Frequency (Project Specific) - Visual, Layer Thickness: 75mm - 250mm
label | Check Item - Check Item
label | Reference - MRTS05 Table 8.3.3
checkpoint | Minimum value of Relative Dry Density Requirements C.V of RDD = 100% MDD for Base course 2.1, 2.2, = 100% SDD for other than base course 2.1, 2.2 and 100% SSD for all layers of 2.3, 2.4 and 2.5.
label | Acceptance Criteria and Frequency (Project Specific) - C.V of RDD >= 100% MDD
label | ○ Normal: 1 test / 500m2, 4 per lot,
label | ○ Reduced: 1 test / 1000m2, 4 per lot
label | Check Item - Check Item
label | Reference - MRTS05 Table 8.4.3
checkpoint | Unless agreed otherwise, a trial placement of materials of a minimum size of 1000m2 is required.
label | Acceptance Criteria and Frequency (Project Specific) - All tests as described by this ITP and MRTS05
label | Check Item - Hold Point 3
label | Reference - MRTS05 Cl. 8.2
holdpoint | HOLD POINT
checkpoint | Moisture content such that the degree of saturation is less than 70%(modified).
label | Acceptance Criteria and Frequency (Project Specific) - S < 70%
label | ○ Normal: 1 test / 500m2, 4 per lot,
label | ○ Reduced: 1 test / 1000m2, 4 per lot
label | Check Item - Hold Point 4
label | Reference - MRTS05 Table 8.3.4.1
holdpoint | HOLD POINT
checkpoint | No visible segregation of material. Partical Size Distribution Q103A.
label | Acceptance Criteria and Frequency (Project Specific) - Min 1 per lot. Additional tests as directed by the Administrator.
label | Check Item - Check Item
label | Reference - MRTS05 Table A3
checkpoint | Geometric Tolerances in accordance with MRTS05 Cl.8.4.4.3
label | Acceptance Criteria and Frequency (Project Specific) - ±10mm when covered by AC ±15 mm in all other cases (1 test / 20m)
label | Check Item - Check Item
label | Reference - MRTS05.1 Cl.8.4.4.3
checkpoint | Geometric Tolerances: Horizontal tolerance of ±50mm, or -50 / +250mm for pavement edges not adjacent to any other section of pavement and not adjacent to any structure or adjoining road
label | Acceptance Criteria and Frequency (Project Specific) - ±50mm, or -50 / +250mm if not adjacent to adjoining pavement (1 test / 25m)
label | Check Item - Check Item
label | Reference - MRTS05 Cl.8.4.4.2 Table A4
checkpoint | Deviation from a 3m straight edge shall be less than 5mm for material types 1,2,3 and 4
label | Acceptance Criteria and Frequency (Project Specific) - Straight Edge Test, Less than 5mm, 1 test per 20m
label | Check Item - Check Item
label | Reference - MRTS05 Cl. 8.4.5
checkpoint | Each unbound pavement layer shall be tested for perceptable surface deformation by 'proof rolling' the pavement, in the presence of the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Visual, Continuous testing
label | Check Item - Witness Point 2
label | Reference - MRTS05 Cl.9.4.7
checkpoint | Additional Geometrics (final layer only). The crossfall shall not depart from the corresponding crossfall shown in the Contract by more than 0.5% absolute.
label | Acceptance Criteria and Frequency (Project Specific) - 0.5% deviation from crossfall (1 test / 25m)
label | Check Item - Check Item
label | Reference - MRTS05 Cl.8.4.4.4
checkpoint | The contractor shall provide a methodology and calculations to determine the road roughness to the administrator for acceptance. Roughness shall be less than 2.31m/km.
label | Acceptance Criteria and Frequency (Project Specific) - Less than 2.31m/km, 1 test per 500m
label | Check Item - Check Item
label | Reference - MRTS05 Cl.8.4.6
checkpoint | The finished surface of any unbound pavement layer shall:
label | – be hard and homogenous in appearance
label | – not have any loose, segregated or contaminated areas
label | – have the coarse particles slightly exposed
label | – not be affected by delamination
label | – not show signs of water pumping, and
label | – not visibly deflect under load when proof rolled in accordance with Cl 9.4.7
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS05 Cl.8.3.5.1
checkpoint | The Contractor shall not incorporate materials into the work unless it has demonstrated that the material complies fully with the requirements of this Technical Specification before delivery of the material to site
label | Acceptance Criteria and Frequency (Project Specific) - Test Results per lot
label | Check Item - Hold Point 5
label | Reference - MRTS05 Cl.9.1
holdpoint | HOLD POINT
checkpoint | Unless otherwise approved by the Administrator, no unbound pavement layer shall be covered by a subsequent layer of pavement or by a surfacing until Hold Point 6:
label | a) all testing has been completed
label | b) the surface finish of the layer complies with the requirements of Clause 8.3.5
label | c) all test results comply with the requirements of this Technical Specification, or any nonconformances have been submitted, with corrective actions proposed by the Contractor, and accepted by the Administrator
label | d) the layer has been presented to the Administrator for inspection, and
label | e) the As Constructed Survey requirements of the lot have been met as specified in MRTS56 Construction Surveying and notice of such works has been provided to the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Adminstrator Acceptance
label | Check Item - Hold Point 6
label | Reference - MRTS05 Cl.9.5.1
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 10.01 - Plant Mixed Lightly Bound Pavements | itp |  |  |  |  | 10.01 - Plant Mixed Lightly Bound Pavements
section | Details
checkpoint | Construction Procedure
label | ○ Documented procedure shall be prepared for all construction processes as defined in Clause 6 of MRTS50 and shall be submitted for approval at least 14 days prior to commencement of lightly bound pavement works (No work shall commence until accepted by the Administrator)
label | Acceptance Criteria and Frequency (Project Specific) - Acceptance
label | Check Item - Hold Point 1, Milestone
label | Reference - Clause 5.2 MRTS10
holdpoint | HOLD POINT
checkpoint | Material Requirements - Unbound Pavement Material
label | ○ The Contractor shall not incorporate unbound pavement material into the works unless it has been demonstrated that the unbound pavement material lot conforms fully to the requirements of MRTS10. All conformance results shall be no more than six months old.
label | Acceptance Criteria and Frequency (Project Specific) - Acceptance
label | Check Item - Hold Point 2
label | Reference - MRTS10 Clause 6.1.1
holdpoint | HOLD POINT
checkpoint | Mix Design Report
label | ○ A mix design must be submitted at least 14days before mixing operations commence. Construction of the lightly bound pavement layer shall not proceed until a conforming mix design (refer to Clause 7.2) has been deemed suitable and accepted by the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) - Acceptance
label | Check Item - Hold Point 3
label | Reference - MRTS10 Clause 7.1
holdpoint | HOLD POINT
checkpoint | Moisture Content
label | ○ The Contractor shall nominate upper and lower moisture content limits as part of their Mix Design that will ensure:
label | a) there is adequate moisture to achieve the specified compaction standard
label | b) the constructed lightly bound pavement layer is trafficked in accordance with requirements of Clause 8.2.11, and
label | c) the lightly bound pavement material does not exceed the optimum moisture content (OMC), determined in accordance with Test Method Q142A.
label | Acceptance Criteria and Frequency (Project Specific) - Testing - AS1289.2.1.1, 1 per 500m2, 4 per lot
label | Check Item - Test Report
label | Reference - MRTS10 Clause 8.2.5, Clause 9.4.8 Table A3
checkpoint | Construction - Trial Pavement
label | ○ Unless otherwise agreed by the Administator, a trial of the manufacturing and laying operations shall be caried out prior to commencement of the work.
label | ○ The trial pavement shall be located within the site and be not less than 1000m2. It shall determine the characteristics highlighted in Clause 8.1 MRTS10. The trial may be incorporated into the permanent works at the Administrators discression.
label | ○ The Contractor is to undertake the material and construction compliance testing nominated in Clause 8.1 and the finished pavement complies with the technical specification of MRTS10. If deemed not conforming, further trialing shall be undertaken.
label | Acceptance Criteria and Frequency (Project Specific) - Visual & Check
label | Check Item - Witness Point 1 /Hold Point 4
label | Reference - MRTS10 Clause 8.1
holdpoint | HOLD POINT
checkpoint | Material Compliance Testing
label | ○ Each supply lots shall be sampled and tested for compliance in accordance with the testing frequencies specify in MRTS05. No material shall be incorporated into the work unless it has demonstrated compliance fully with the requirements of MRTS05 and MRTS10
textbox | Material Type:
textbox | Material Stockpile Lot Ref:
label | Acceptance Criteria and Frequency (Project Specific) - MRTS05 Cl. 7, Table A1, MRTS10 Cl.6, Table A2
label | Check Item - Check Item
label | Reference - MRTS05 Clause 7
checkpoint | Equipment
label | ○ Equipment as specified in approved construction procedure
label | Acceptance Criteria and Frequency (Project Specific) - Construction Procedure Approval
label | Check Item - Contract Notice
label | Reference - MRTS10 Cl.8.2.1.4
checkpoint | Weather Conditions
label | ○ CMB material shall not proceed when:
label | a) air temperature is less than 10°C or greater than 40°C
label | b) during rain or when rain is likely to fall during placement
label | c) evaporation rate due to the combined effect of air temperature, wind and relative humidity may result in excessive drying of the CMB
label | Acceptance Criteria and Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS10 Clause 8.2.4
checkpoint | Allowable Working Time
label | ○ Define as the maximum period between mixing the modifying binder into the unbound granular material and the completion of compaction.
label | ○ The allowable working time for the plant-mixed lightly bound pavement is to be the lesser of the following
label | a) Working time determined in accordance with Test Method Q136A
label | b) Four hours
label | Acceptance Criteria and Frequency (Project Specific) - Monitor
label | Check Item - Check Item
label | Reference - MRTS10 Clause 8.2.3
checkpoint | Construction Joints
label | ○ Deemed to be fresh when the material compacted on each side of the joint has been modified, placed and compacted within the allowable working time. In multi layer of lightly bound pavement, longitudinal joints of each layer shall be offset from the underlying layer by a minimum of 150mm.
label | Acceptance Criteria and Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS10 Clause 8.2.10
checkpoint | Fresh Joints
label | ○ Where fresh joint between adjoining or adjacent run is to be compacted, the outside 300mm of material from the first run shall be left uncompacted until the adjacent run is ready for compaction.
label | Acceptance Criteria and Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS10 Cl. 8.2.10.1
checkpoint | Other (Cold) Joints
label | ○ Joints that are not fresh shall be cut back to form a neat, clean vertical face.
label | ○ Cutback distance shall be a minimum of 150mm and before placing the adjoining layer or adjacent layer, the cut back edge of the existing layer shall have a cement/water slurry at a rate of 2kg/m2. The slurry cement/water ratio to be 0.6 and 0.7.
label | Acceptance Criteria and Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS10 Cl. 8.2.10.2 Cl.6.4
checkpoint | Curing of CMB Layers
label | ○ The surface of an existing layer of lightly bound pavement shall be water cured until placement of the next layer and/or bituminous surfacing is applied. Unless approved, within 7 days of placement the lightly bound pavement shall be covered by a subsequent layer and/or bituminous treatment. Water curing shall be completed in accordance with Cl. 8.2.1.5
label | Acceptance Criteria and Frequency (Project Specific) - Check & Verify
label | Check Item - Check Item
label | Reference - MRTS10 Clause 8.2.9
checkpoint | Trafficking of CMB Layers during Construction
label | ○ Unless approved by the Administrator, lightly bound pavement layers shall not be opened to either construction traffic or general traffic until the lot has been tested for, and passes proof rolling (Cl 9.4.10)
label | Acceptance Criteria and Frequency (Project Specific) - Check
label | Check Item - Check Item
label | Reference - MRTS10 Clause 8.2.11
checkpoint | Compaction Standard
label | ○ The characteristic value of relative compaction shall not be less than 100% standard, except for the upper most layer of lightly bound base which shall not be less than 102% standard
label | Acceptance Criteria and Frequency (Project Specific) - 102% standard upper most layer
label | ○ 100% standard lower layers
label | ○ (1/500m2, min 4/lot)
label | ○ (1/1000m2, min 4/lot)
label | Check Item - Test Report
label | Reference - MRTS10 Clause 8.3.4
checkpoint | UCS
label | ○ Unconfined compressive strength between 1 - 2MPa
label | Acceptance Criteria and Frequency (Project Specific) - UCS 1-2MPa (1 per lot)
label | Check Item - Check Item
label | Reference - MRTS10 Clause 9.4.9
checkpoint | Stabilising Agent Content
label | ○ The actual content of stabilising agent for each lot shall be represented by both the:
label | a) minimum characteristic value of the actual content of stabilising agent, and
label | b) maximum characteristic value of the actual content of stabilising agent.
label | ○ When UCS tests are being undertaken, the sample being used must also be tested for stabilising agent content.
label | Acceptance Criteria and Frequency (Project Specific) - Target content minus MPV, Min. test 1 per lot
label | Check Item - Check Item
label | Reference - MRTS10 Clause 9.4.6
checkpoint | Geometrics - Horizontal Tolerances
label | ○ Shall not be more than ± 50mm except for the following:
label | a) Pavement edges not adjacent to any other part of the pavement and not adjacent to any structure or adjoining road, transverse tolerance shall be -50mm + 250mm
label | b) Where alignment of the pavement with an existing structure is necessary, the new work shall be joined neatly to the existing in a smooth manner
label | Acceptance Criteria and Frequency (Project Specific) - -50mm/+250mm (1 per 20m)
label | Check Item - Survey Report
label | Reference - MRTS10 Clause 8.3.5.2
checkpoint | Geometrics - Primary Vertical Tolerances
label | ○ The vertical tolerances specified in Table 8.3.5.3 shall apply or:
label | – the surface level measured at any point on the surface of any layer.
label | – The average total thickness of the constructed course compared to the specified total thickness.
label | Acceptance Criteria and Frequency (Project Specific) - ±15mm for layers that have been hard cut ±10mm for all other layers
label | ○ Layer thickness -20mm, +unspecified (1 per 20m at shoulders, lane lines & grade changes)
label | Check Item - Survey Report
label | Reference - MRTS10 Clause 8.3.5.3
checkpoint | Geometrics - Deviation from a Straight - Edge
label | ○ Deviation of a straight edge place anywhere on the surface shall not exceed 5mm over 3m
label | Acceptance Criteria and Frequency (Project Specific) - 5mm over 3m (1 per 20m and at joints)
label | Check Item - Check Sheet
label | Reference - MRTS10 Clause 8.3.6
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 14.07 - Demolition of Road Furniture | itp |  |  |  |  | 14.07 - Demolition of Road Furniture
section | Details
checkpoint | Road furniture to be removed are as listed in MRTS14.1.
label | Acceptance Criteria and Frequency (Project Specific) - Signange/REGP's and Lighting to be removed
label | Check Item - Check Item
label | Reference - MRTS14.1
checkpoint | Existing road furniture demolished and removed in a manner which avoids damaging any adjacent work.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl.7.3
checkpoint | Resulting excavations are backfilled and finished so the area is in a safe and free-draining state.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl.7.3
checkpoint | The Constractor shall submit (7 days prior to work) a schedule of items of existing road furniture to be salvaged in accordance with the provisions of the design documentation
label | Acceptance Criteria and Frequency (Project Specific) - Submission of Schedule
label | Check Item - Milestone
label | Reference - MRTS14 Cl8.2
checkpoint | Dismantling and removal shall not commence until expiration of the seven day period
label | Acceptance Criteria and Frequency (Project Specific) - Expiry of 7 days since submission of Schedule
label | Check Item - Hold Point 1
label | Reference - MRTS14 Cl8.2
holdpoint | HOLD POINT
checkpoint | The Constractor shall submit (7 days prior to work) a schedule of items of existing road furniture to be dismantled for re-erection in accordance with the provisions of the design documentation
label | Acceptance Criteria and Frequency (Project Specific) - Submission of Schedule
label | Check Item - Milestone
label | Reference - MRTS14 Cl9.2
checkpoint | Dismantling and removal shall not commence until epiration of the seven day period
label | Acceptance Criteria and Frequency (Project Specific) - Expiry of 7 days since submission of Schedule
label | Check Item - Hold Point 2
label | Reference - MRTS14 Cl9.2
holdpoint | HOLD POINT
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 14.13 - Supply and Installation of Road Signs | itp |  |  |  |  | 14.13 - Supply and Installation of Road Signs
section | Details
checkpoint | Not less than seven days prior to commencement of dismantling and removal of existing road furniture, the Contractor shall submit a schedule of items of existing road furniture to be disamantled or re-erection in accordance with the provisions of the design documentation.
label | Acceptance Criteria and Frequency (Project Specific) - Submission of Schedule
label | Check Item - Milestone
label | Reference - MRTS14 Cl 9.2
checkpoint | Dismantling and removal shall not commence until the experation of the seven day period.
label | Acceptance Criteria and Frequency (Project Specific) - Expiry of 7 days since submission of Schedule
label | Check Item - Hold Point 2
label | Reference - MRTS14 Cl 9.2
holdpoint | HOLD POINT
checkpoint | All legend elements, including letters, numerals, symbols, colours and borders in all sign faces conform to the MUTCD and project drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 CL 13.2
checkpoint | Dimensional Tolerances conform to the requirements detailed in AS1743 and legends and lettering conforms to AS1744.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 CL 13.2
checkpoint | Sign Material conforms with the requirements as set out in Cl 13.3.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl 13.3
checkpoint | The sign substrate shall be manufactured from aluminium. Other materials may be considered but evidence of the full approval of the department will be provided to the administrator prior to their use.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 3
label | Reference - MRTS14 CL 13.3.1.1
holdpoint | HOLD POINT
checkpoint | Sign faces are fabricated in accordance with the requirements of Traffic and Road Use Management Manual (TRUM) Volume 3, Part 5.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl 13.4
checkpoint | Sign posts shall be circular or rectangular hollow sections unless specifically shown otherwise in the design documentation.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl 14.2.3
checkpoint | Post sizes and spacings shall conform to the design documentation with slip bases and fuse plates as required.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl 14.2.3
checkpoint | Concrete footings shall conform to MRTS70 and to the dimenesions shown in the design documentation.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl 14.3
checkpoint | Erection of Road Signs.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point 1
label | Reference - MRTS14 Cl 14.4
checkpoint | Signs erected at the locations shown in the design documentation and the orientation shall be in accrodance with the MUTCD.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl 14.4.2
checkpoint | Sign faces installed on the posts and/or frame once all other erection is complete.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl14.4.5
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 14.20 - Installation of Steel beam Guardrail and End Treatments | itp |  |  |  |  | 14.20 - Installation of Steel beam Guardrail and End Treatments
section | Details
checkpoint | Manufacture of steel beam guardrail post, panel components and end treats are maufactured by an approved manufacturer.
label | Acceptance Criteria and Frequency (Project Specific) - Approved Manufacturer
label | Check Item - Check Item
label | Reference - MRTS14 Cl. 20.2
checkpoint | Steel beam guardrail components and end treatments shall only be supplied by an approved supplier.
label | Acceptance Criteria and Frequency (Project Specific) - Approved Supplier
label | Check Item - Check Item
label | Reference - MRTS14 Cl 20.3
checkpoint | Hexagonal head bolts and nuts shall be manufactured to the dimensions shown on Standard Drawings, and tested in accordance with MRTS78. Mushroom head (C) bolts shall be manufactured to the details shown on Standard Drawing 1479 Circular washers shall conform to the requirements of AS 1237.
label | Acceptance Criteria and Frequency (Project Specific) - Test Certificates
label | Check Item - Check Item
label | Reference - MRTS14 Cl 20.4.7
checkpoint | All panels, steel posts and blockouts shall be batch stamped during the manufacturing process with manufacturer's ID, Metal grade and thickness, and batch number. Single batch LESSTHAN2000 items.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl20.4.2.2 Cl. 20.4.3.2
checkpoint | All steel components shall be hot-dipped galvanised after manufacture in accordance with the requirements of AS/NZS 4680.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl20.4.1
checkpoint | All the steel manufacturer material test certificates shall be supplied to the Administrator. The test certificates shall show the full chemical composition including the carbon equivalence, and mechanical test results for yield, tensile and elongation
label | Acceptance Criteria and Frequency (Project Specific) - Test Certificates
label | Check Item - Hold Point 7
label | Reference - MRTS14 Cl20.4.5
holdpoint | HOLD POINT
checkpoint | If required, the Administrator shall randomly select two post and two panels from each batch number for audit testing.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Witness Point 3
label | Reference - MRTS14 Cl20.4.6.1
checkpoint | Installation shall not commence until the Administrator has confirmed the materials tested match the material test certificates supplied for the batch of guardrail components.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 8
label | Reference - MRTS12 Cl20.4.6.3
holdpoint | HOLD POINT
checkpoint | A list of component parts and fabrication drawings defining the dimensions and weld sizes of the various components and the grade of materials and relevant standards with which the component materials are required to comply shall be provided to the Administrator prior to commencement of installation of the device or system.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 11
label | Reference - MRTS14 Cl21.2
holdpoint | HOLD POINT
checkpoint | Once the initial set out is complete the Administrator will determine the design appropriateness of the set out with regard to the actual site conditions
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 1
label | Reference - MRTS01 Cl.8
holdpoint | HOLD POINT
checkpoint | Dial before you dig consulted and services located where required prior to excacation or driving of posts
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
checkpoint | Steel Beam guardrail installed in the locations shown in the design documentation and in accordance with the Standard Drawings.
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl20.6.1
checkpoint | A proprietary road safety barrier system and/or end treatment shall be installed as shown in and required by the design documentation, and in accordance with the requirements of the installation manual
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl.21.4.1
checkpoint | Public Domain (Departure Terminal): Soil plate on type 2 departure terminal shall not be ommitted
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl20.6.3
checkpoint | Delinerators installed on steel beam guardrail in accordance with the MUTCD Part 2
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS14 Cl20.6.5 Cl21.4.5
checkpoint | Installed within Geometric Tolerances
label | Acceptance Criteria and Frequency (Project Specific) - Post Verticaloty: ± 15mm
label | ○ Post Height: ± 10mm
label | ○ Rail Height: ± 10mm
label | Check Item - Check Item
label | Reference - MRTS14 Cl21.4.6.2
checkpoint | Adminstrator accepts guardrail installation as per the design documentation
label | Acceptance Criteria and Frequency (Project Specific) - Visual
label | Check Item - Hold Point 10
label | Reference - MRTS14 Cl 20.6.7
holdpoint | HOLD POINT
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off