## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 16.01 - Landscape and Revegetation Works | itp |  |  |  |  | 16.01 - Landscape and Revegetation Works
section | Details
checkpoint | Soil Management Plan prepared in accordance with Form A of Appendix MRTS16. Construction and regular Updates submitted to the Administrator for approval
label | Acceptance Criteria & Frequency (Project Specific) - Written Acceptance
label | Check Item - Hold Point 1
label | Reference - MRTS16 Cl 5.2.1
holdpoint | HOLD POINT
checkpoint | Non-Potable Water Plan and permits submitted to the Administrator
label | Acceptance Criteria & Frequency (Project Specific) - Plan
label | Check Item - Hold Point 2
label | Reference - MRTS16 Cl 5.2.2
holdpoint | HOLD POINT
checkpoint | Seed Supply Proposal submitted to the Administrator within 30 days of Possession of Site
label | Acceptance Criteria & Frequency (Project Specific) - Plan
label | Check Item - Hold Point 3
label | Reference - MRTS16 Cl 5.3.1
holdpoint | HOLD POINT
checkpoint | Plant Supply Proposal submitted to the Administrator within 30 days of Possession of Site
label | Acceptance Criteria & Frequency (Project Specific) - Plan
label | Check Item - Hold Point 5
label | Reference - MRTS16 Cl 5.3.3
holdpoint | HOLD POINT
checkpoint | Plant Harvesting Proposal submitted to the Administrator prior to harvesting plants
label | Acceptance Criteria & Frequency (Project Specific) - Plan
label | Check Item - Hold Point 6
label | Reference - MRTS16 Cl 5.3.4
holdpoint | HOLD POINT
section | Materials
checkpoint | Materials imported to Site shall be free of prohibited or restricted biosecurity matter
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 7
checkpoint | Materials are stored to ensure no deterioration or contamination occurs, including the potential for environmental harm
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 7
checkpoint | Materials; including pesticides, soil amelioration agents, soil, seeding, turf, mulch, matting, plants water, plant bed edging and irrigation systems, comply with requirements and specifications set out in MRTS16 Clause 7 where applicable
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 7
checkpoint | Containerised plants and ex ground stock in accordance with MRTS16 Cl. 7.6.2
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 7.6.2
checkpoint | The extent and types of vegetation treatments are installed as specified in the contract and/or shown on the drawings
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8
section | Subsoil and Topsoil Amelioration
checkpoint | Site is weed free prior to ground preparation operations
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point 2
label | Reference - MRTS16 Cl 8.3
checkpoint | Administrator notified at least 3 days before each of the following:
label | ○ Application and incorporation of amelioration agents
label | ○ Ripping
label | ○ Cultivation
label | ○ Roughening
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point 3, 4, 5
label | Reference - MRTS16 Cl 8.1.1 Cl 8.4.1.1 Cl 8.4.1.2 Cl 8.4.1.3 Cl 8.4.1.4
checkpoint | Amelioration agents, where specified in the Soil Management Plan – Construction, shall be spread over the subsoil surface at the specified rates prior to subsoil operations
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 8
label | Reference - Cl 8.4.1.1
holdpoint | HOLD POINT
checkpoint | Manufactured site topsoil shall be in accordance with Form D of MRTS 16 Appendix prior to being used.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 7
label | Reference - MRTS16 Cl 8.2.1
holdpoint | HOLD POINT
checkpoint | The Contractor shall give at least three days notice before installation of topsoil. Topsoil installed evenly over the surface, within 3 days of subsoil preparation and Topsoil shall be spread to the depths described in the relevant vegetation works operation, and allow for settlement after installation.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point 6
label | Reference - MRTS16 Cl 8.4.2.1
section | Grass seeding, Hydromulching and Turfing
checkpoint | Turf shall be installed within two days from the completion of the topsoil operations, Turf shall be installed by:
label | a)spreading fertiliser over the topsoil and raking the surface smooth
label | b) to the prepared surface that has been moistened with a solution of water and wetting agent
label | c) on the day turf is delivered to site
label | d) by laying rolls parallel to the contour, in a staggered brick pattern, and
label | e) by watering, within 2 hours of installation, with a solution of water and wetting agent until the topsoil layer is moist. Watering shall be applied in multiple applications to ensure surface erosion does not occur.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8.5.2
checkpoint | Turf installed within 2 days of topsoil, within 24 hours of delivery and in accordance to Table 8.5.2 with initial watering on the day of installation and at least 25L/m2
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 8.5.2
checkpoint | For seeding operations, the Contractor shall prepare a sample instillation to provide an agreed quality control for further instillations. The sample instillation shall be established as per Cl 8.5.1
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 9
label | Reference - Cl 8.5.1
holdpoint | HOLD POINT
checkpoint | All seed, wetting agents and fertilisers shall be brought on site in seperately labelled containers and mixed on-site to allow verification of materials and quanitities
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 7
label | Reference - Cl 8.5.1
holdpoint | HOLD POINT
checkpoint | Broadcast seeding installed as per Cl 8.5.1.2
label | Check Item - Check Item
label | Reference - Cl 8.5.1.2
checkpoint | Hydrumulch bonded fibre matrix installed as per Cl 8.5.1.4
label | Check Item - Check Item
label | Reference - Cl 8.5.1.4
section | Establishment, Monitoring and Finalisation
checkpoint | Commencement of the Establishment Period
label | Acceptance Criteria & Frequency (Project Specific) - Issue of Certificate of Commencement of the Establishment Period by the Administrator
label | Check Item - Milestone
label | Reference - MRTS16 Cl 9.1
checkpoint | The Contractor shall care for the installed vegetation treatments to ensure their long term sustainability and to meet the completion criteria of Clause 9.1.2
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 9.1.1
checkpoint | Commencement of the Monitoring Period
label | Acceptance Criteria & Frequency (Project Specific) - Issue of Certificate of Commencement of the Moitoring Period by the Administrator
label | Check Item - Milestone
label | Reference - MRTS16 Cl 9.2
checkpoint | All Monitoring operations; including, watering, fertilising, weed, pest and disease control, mowing, slashing and brush cutting, pruning, and repair and reinstallation of failed plants, comply with Clause 9.2.1
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS16 Cl 9.2.1
checkpoint | Certificate of finalisation of landscape and revegetation works monitoring period issued
label | Acceptance Criteria & Frequency (Project Specific) - Issue of Certificate of Completion of the Moitoring Period by the Administrator
label | Check Item - Milestone
label | Reference - MRTS16 Cl 9.2.2
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 28.01 - Contractor's Camp and Site Facilities | itp |  |  |  |  | 28.01 - Contractor's Camp and Site Facilities
section | Details
checkpoint | Location of facilities within areas given in MRTS 28.1 Cl. 1 or through private arrangements.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS28 Cl. 4.2
checkpoint | Properly constructed toilets, rubbish receptacles and wash facilities provided.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS28 Cl. 4.3
checkpoint | Camp and facilities provide safe egress and ingress and do not impact on existing through traffic.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS28 Cl. 4.5.6
checkpoint | Contractors camp complies with all requirements of MRTS52 and included in the E&SC plan.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS52 Cl. 6
checkpoint | Contractors camp complies with all requirements of MRTS28 annexure with a proposed site facility layout submitted to the administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS28.1
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 45.01 - Road Surface Delineation | itp |  |  |  |  | 45.01 - Road Surface Delineation
section | Details
checkpoint | All material conforms to requirements set out in Clause 6
label | Acceptance Criteria & Frequency (Project Specific) - Material product sheets
label | Check Item - Check Item
label | Reference - MRTS45 Cl 6
checkpoint | Pavement markings not applied when freshly applied pavement markings may become damaged by rain, fog or condensation before they have dried or set.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.2
checkpoint | Pavement surface is thoroughly dry and free from all dirt, loose material and other contaminants immediately before applying the pavement markings
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.3
checkpoint | In addition to the above requirements, new bitumen sealed surfaces which are to receive pavement markings shall be free of volatile material and solvents.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 1
label | Reference - MRTS45 Cl 7.3
holdpoint | HOLD POINT
checkpoint | Spotting approved by the Administrator prior to any application of pavement markings
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS45 Cl 7.4.1
holdpoint | HOLD POINT
checkpoint | Construction procedure for application of pavement markings submitted to the Administrator
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.5
checkpoint | All Markings are of uniform thickness and intensity
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.5.2.3
section | Waterborne
checkpoint | Waterborne Paint not heated to greater than 65°C and consists of two coats of paint and glass beads with application rates for the paint as per Table 7.5.2.4
label | Acceptance Criteria & Frequency (Project Specific) - Visual Table 7.5.2.4
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.5.2.3 Cl 7.5.2.4
section | Thermoplastic
checkpoint | If required, a primer of type recommended by manufacturer of the thermoplastic material shall be applied to the surface immediantly in advance of, but concurrent with, the application of thermoplastic material
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.5.3.1
checkpoint | Thermoplastic shall be applied at a temperature between 180C-200C or as per the manufacturers specifications
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.5.3.2
checkpoint | Thermoplastic applied at a minimum of 2mm thickness
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.5.3.3
section | Cold Applied Plastic
checkpoint | If required, a primer of the type reccommended shall be applied to the surface immediately in advance of, but concurrent with the application of the Cold Applied Plastic materials
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.5.4.1
checkpoint | Cold Applied Plastic shall be applied at a temperature as per the manufacturers specifications
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.5.4.2
checkpoint | Cold applied Plastic shall be applied at the rates specified in Table 7.5.4.2
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.5.4.2
checkpoint | The use of Raised Retroreflective Pavement Markers shall be in accordance with Cl 5.6.2 of the MUTCD Part 2
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.6.14
checkpoint | Material complies with luminance and retro-reflectivity requirements.
label | Acceptance Criteria & Frequency (Project Specific) - Test procedure AS 4049.4
label | Check Item - Check Item
label | Reference - MRTS45 Cl 5.3 & Cl 7.7.6
checkpoint | Material protected from damage by traffic or other causes until paint is dry and thermoplastic has hardened
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.8
checkpoint | Completed Pavement Markings shall be uniform, clean and well-defined edges without deformation and conforms to dimensions as set out in the MUTCD
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.9
checkpoint | Pavement Markings conform to all tolerances
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS45 Cl 7.9.1
checkpoint | Final Verification
label | Supervisor/QA Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Project Manager Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 51.01 - Environmental Management Systems | itp |  |  |  |  | 51.01 - Environmental Management Systems
section | Details
checkpoint | Environmental Management Plan (Construction) EMP (C) submitted in accordance with General Conditions of Contract.
label | Acceptance Criteria & Frequency (Project Specific) - Submission of EMP
label | Check Item - Milestone
label | Reference - MRTS51 Cl. 6.3
checkpoint | Works under the Contract shall not start until the EMP (C) is assessed for suitability by the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - EMP Approved by Administrator
label | Check Item - Hold Point 1
label | Reference - MRTS51 Cl. 6.3
holdpoint | HOLD POINT
checkpoint | Any amendments to the EMP (C) shall be submitted on a monthly basis and be assessed for suitability by the Administrator.
label | Acceptance Criteria and Frequency (Project Specific) -
label | Check Item - Hold Point 2
label | Reference - MRTS51 Cl. 6.4
holdpoint | HOLD POINT
checkpoint | Environmental site inspections to be conducted daily, against all licences, permits, approvals and other environmental performance requirements. All Inspection to be documented with records being submitted to the Administrator on a monthly basis.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 7.1
checkpoint | Environmental records are to be included in the Quality Records under the Contract. Table 7.8 of this Technical Specification identifies environmental record requirements. Records and registers shall be made available to the Administrator upon request.
label | Acceptance Criteria and Frequency (Project Specific) -
label | Check Item - Hold Point 3
label | Reference - MRTS51 Cl. 7.8
holdpoint | HOLD POINT
checkpoint | The Contractor shall be responsible for the management of Indigenous and non-Indigenous cultural heritage artefacts, sites and values within the worksite
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.4.1
checkpoint | The contractor shall at all times take measures to assist in minimising noise associated with construction activities so as not to cause environmental nuisance or harm.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.5.2
checkpoint | Project records shall include all noise monitoring results if required
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.5.3
checkpoint | Condition survey may need to be conducted prior to commencement of activities as per Annexure MRTS51.1 Cl. 5.5 Copies of condition survey to be forward to Administrator 5 working days before any works that cause vibration start.
label | Acceptance Criteria & Frequency (Project Specific) - Visual (Survey Recorded)
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.6.2.3
checkpoint | Project records that show compliance with the VMP and shall include all noise monitoring results (if required)
label | Check Item - Check Item
label | Reference - MRTS51.1 Cl. 8.6.2
checkpoint | The contractor shall at all times take reasonable and practicable management measures to avoid cuasing environmental nuisance or harm due to air quality. Burning of material shall not be permitted
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.7.2
checkpoint | The contractor shall be responsible for the management of acid Sulphate Soils and shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.8
checkpoint | The contractor shall be responsible for the management of contaminated sites ( contaminated soils, waste dumps, unexploded ordinances ) within the worksite . The contractor shall address the requirements of MRTS04 General earthworks including the requirements concerning the management of acid sulphate soils
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.9.1
checkpoint | The contractor shall take all due care to not harm native fauna. Areas of significance and related management requirements are stated in Cl. 7 of Annexure MRTS51.1. Contact details for emergency wildlife care shall be included on project emergency contact list.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.10.1
checkpoint | No waste or litter shall be burnt on site. No waste or litter shall be buried on site unless approved by the Administrator and the administering authority.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.13.2
checkpoint | The contractor shall be responsible for the management of all chemicals and fuels within the worksite so as not to cause environmental nuisance or harm. The contractor shall ensure spill kits response equipment are available on site for use in emergency
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.14.1
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 52.01 - Erosion and Sediment Control | itp |  |  |  |  | 52.01 - Erosion and Sediment Control
section | Details
checkpoint | Clearing and grubbing (or the use of the area for stockpiles) for that section shall not start until the ESCP for that section is assessed as suitable by the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Approval of ESCP by Administrator
label | Check Item - Hold Point 1
label | Reference - MRTS52 Cl. 6.1
textbox | Approved in TMR Correspondence dated |  |  | PE/WS/SS __/__/____
textbox | Approved in TMR Correspondence dated |  |  | CQR to Verify 1__/__/___
textbox | Approved in TMR Correspondence dated |  |  | Administrator __/__/___
holdpoint | HOLD POINT
checkpoint | Prior to initial earthworks operations, the Contractor must install erosion and sediment controls associated with drainage paths flowing through the works area.
label | Acceptance Criteria & Frequency (Project Specific) - In accordance with approved ESCP.
label | Check Item - Hold Point 2
label | Reference - MRTS52 Cl. 7.1
holdpoint | HOLD POINT
checkpoint | Releases from site must not cause scour at the area of discharge. Water must only be released at the discharge point nominated within the ESCP and as deemed acceptable by the Administrator.
label | Check Item - Check Item
label | Reference - MRTS52 Cl. 8.1
checkpoint | The Contractor shall install a proprietary rain gauge and keep record of the rainfall depth of each rain event
label | Check Item - Check Item
label | Reference - MRTS51 Cl. 8.2.3.2.1
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 70.01 - MRTS70 Concrete | itp |  |  |  |  | 70.01 - MRTS70 Concrete
section | Details
checkpoint | The Contractor shall nominate the special class concrete mix to be used in the Works not less than four weeks prior to the commencement of concreting operations.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl 9.2
checkpoint | Procedure for hot weather concreting submitted 2 weeks prior to first concrete pour.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl 13.1
checkpoint | Procedure for curing submitted 2 weeks prior to first concrete pour.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl 15.11.1
checkpoint | Procedure for temperature control submitted 4 weeks prior to first concrete pour.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl15.5
checkpoint | When requested by the Adminstrator, mix designs shall have a trial mix completed. Each trial mix shall be a Witness Point with a notice peroid of 3 days. The minimum volume of trial mix is 25% of the rated capacity of the mixer.
label | Acceptance Criteria & Frequency (Project Specific) - f'c Each Mix
label | Check Item - Witness Point 1
label | Reference - MRTS70 Cl 15.1.1
checkpoint | No concrete shall be placed in the Works until approval of the mix design has been obtained from the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 1
label | Reference - MRTS70 Cl 15.1
holdpoint | HOLD POINT
checkpoint | Concrete placed within 75minutes (conc. Temp<=32 degrees) or 1hour (32>conc. temp < 35 degrees) from the time of charging the mixer. These times may be extended at the Administrator's discretion where set-retarding admixtures are used. No concrete may be placed the temperature of the concrete is less than 10°C or exceeds 35°C.
label | Acceptance Criteria & Frequency (Project Specific) - 10< Temp <35 Continuous
label | Check Item - Check Item
label | Reference - MRTS70 Cl 13.1
checkpoint | Falsework details provided to Administrator at least 4 weeks prior to erection.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS70 Cl 15.3
checkpoint | Design and erection of falsework, its founding, support and time, order and manner of release approved by the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS70 Cl 15.3
holdpoint | HOLD POINT
checkpoint | All formwork shall be subject to inspection and approval by the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 3
label | Reference - MRTS70 Cl 15.4.1
holdpoint | HOLD POINT
checkpoint | Concrete operations shall not commence until all relevant procedures, listed in Table 5.2 have been approved by the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS70 Cl 15.6
holdpoint | HOLD POINT
checkpoint | No concrete shall be placed in the Works until:
label | a) the formwork and reinforcement have been inspected
label | b) all foreign material has been completely removed from the forms
label | c) the mixing, batching, and compaction equipment have been approved by the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 5
label | Reference - MRTS70 Cl 15.6.1
holdpoint | HOLD POINT
checkpoint | Administrator to be present for placement of concrete, given 24 hours notice.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point 2
label | Reference - MRTS70 Cl 15.6.1
checkpoint | Concrete slump is within tolerance (AS 1379 table 6) of approved target slump.
label | Acceptance Criteria & Frequency (Project Specific) - Slump Test:
label | ○ <60 - ±10
label | ○ 60<80 - ±15
label | ○ 80<110 - ±20
label | ○ 110<150 - ±30
label | ○ 150< - ±40
label | ○ Every Load
label | Check Item - Check Item
label | Reference - MRTS70 AS 1379 Table 6
checkpoint | Samples for testing taken as required in accordance with claus 12. - min 2 cylinders/sample.
label | Acceptance Criteria & Frequency (Project Specific) - 1-3 Loads - Every Load
label | ○ 4-10 Loads - 4 Samples
label | ○ 11-23 Loads - 5 Samples
label | ○ >23 Loads - 1 per 4 loads
label | Check Item - Test Results
label | Reference - MRTS70 Cl 15.2.1 Table 15.2.2
checkpoint | Compaction of concrete commences immediately after deposition in accordance with approved procedures and equipment - The number of vibrators to be used by the Contractor shall be not less than one for each 10 m³ of concrete placed per hour.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS70 Cl 16.5.2
checkpoint | Fresh concrete shall not be placed against concrete which has taken its initial set. If an interruption greater than 45 minutes occurs, without prio approval from the Administrator, or a cold join occurs, the precast member shall be rejected.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Check Item
label | Reference - MRTS70 Cl.16.5.1
checkpoint | Construction joints shown in the Drawings are mandatory. The use of construction joints elsewhere in the concrete work shall require the prior approval of the Designer.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 7
label | Reference - MRTS70 Cl 15.13
holdpoint | HOLD POINT
checkpoint | Forms, falsework and centring shall remain in position until the times stated in Cl15.8 and table 15.8 have elapsed after completion of concreting.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 6
label | Reference - MRTS70 Cl 15.8
holdpoint | HOLD POINT
checkpoint | Forms shall be removed with care, without hammering and wedging, and in a manner which shall not injure the concrete or disturb the remaining supports. Centres shall be lowered gradually and uniformly in such a manner as to avoid injurious stress in any part of the structure.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point 4
label | Reference - MRTS70 Cl 15.8
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off
checklist | 71.01 - Reinforcing Steel | itp |  |  |  |  | 71.01 - Reinforcing Steel
section | Details
checkpoint | Submission of proposed supplier to Administrator at least 7 days prior to supply of reinforcing. Supplier must be TMR approved and a member of ACRS (Aust Certification Authority for Reinforcing Steel).
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS71 Cl. 6.1
checkpoint | Steel reinforcing not delivered to site prior to written acceptance from the Administrator
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 1
label | Reference - MRTS71 Cl. 6.1
holdpoint | HOLD POINT
checkpoint | Submission for alternative bar grip screw couplers must be presented to Administrator at least 14 days prior to proposed use with full technical data sheet.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS71 Cl. 11.3
checkpoint | Mechanical reinforcing bar splices permitted for use are to be listed in Clause 1 of Annexure MRTS71.1. Alternative registered mechanical reinforcing bar splices shall not be used without prior approval of the Administrator.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 4
label | Reference - MRTS71 Cl. 11.3
holdpoint | HOLD POINT
checkpoint | Substitution of different size steel shall not be made unless written application to Administrator at least 3 weeks prior to date required.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Milestone
label | Reference - MRTS71 Cl. 13
checkpoint | Substitution of steel shall not take place until approved by the Administrator
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 5
label | Reference - MRTS71 Cl. 13
holdpoint | HOLD POINT
checkpoint | Where authorised by Administrator, bars may be hot bent on site following conditions in Cl. 8.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 2
label | Reference - MRTS71 Cl.8.2
holdpoint | HOLD POINT
checkpoint | Installation of bar grip couplers to position as shown on drawings.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Witness Point
label | Reference - MRTS71 Cl. 11.3
checkpoint | No welding to commence until Welding Procedure Specification Sheet, process and consumables for welding of splices are approved by the Administrator
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 6
label | Reference - MRTS71 Cl.14.2
holdpoint | HOLD POINT
checkpoint | All reinforcing cages which are required to be lifted or transported into position, shall have dedicated lifting points. For large cages RPEQ certified drawing must be submitted to administrator for approval
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 8
label | Reference - MRTS71 Cl.15.1
holdpoint | HOLD POINT
checkpoint | Placement of reinforcing within the concrete formwork shall not proceed until the Administrator has approved all splice welds.
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 7
label | Reference - MRTS71 Cl. 14.5
holdpoint | HOLD POINT
checkpoint | All steel reinforcing in position shall be inspected and approved before placement of concrete commences
label | Acceptance Criteria & Frequency (Project Specific) - Visual
label | Check Item - Hold Point 3
label | Reference - MRTS71 Cl. 10
holdpoint | HOLD POINT
checkpoint | Final Verification
label | Contractor's Quality Representative Verify that the Above has been Constructed according to Specification
textbox | Print Name:
date | Date:
label | Administrator's Representative Verify that the Lot Records is in accordance with Specification (only applicable when lot ITP is being audited)
textbox | Print Name:
date | Date:
holdpoint | Sign ITP
section | Final Sign Offs (to be completed at closure of Lot)
checkpoint | Agreed Quantities
holdpoint | Agreed Quantities Sign Off
checkpoint | Closure of Lot
holdpoint | Closure of Lot Sign Off