## ITP Cover Page
Traffic Islands Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DN1205 - 134 - Rev A
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 134
Project Number: |  |  | DN1205 |  |  |  |  | ITP Status: |  |  | Approved
ITP Description: |  |  | Concrete Islands |  |  |  |  | Revision: | 1000 |  | A
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | 146000-002A-3100-3124
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification, Appendices & RITS
Quality Specified: |  |  | RITS
Review / Update History | [9 empty] | Verification Activity
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key
A | Approved | 2024-04-22 |  | Emil Karlsson |  | Comments by BBO Amended |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager
[10 empty] | E | Examine |  | OP | Operations Manager
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Traffic Islands Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | Site Requirements | [6 empty] | Draft for Review
3.01.01 | Construction Pack | Methodology and ITP to be submitted to the Engineer and approved prior to works beginning | Downer | Construction Pack | Submit 10 days prior to commencement of works | HP | ENG
3.01.02 | Survey Setout | Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed. | Downer | Survey Records | Prior to Works | H | SV
3.01.03 | Service Location | Complete the Excavation permit process to identify, locate and protect all services. | Downer | Excavation Permit | Prior to Excavation | H | SE
3.01.04 | Internal Permits | Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. | Downer | Internal Permits | Prior to Excavation | H | SE
3.01.05 | External Permits | Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc. | Downer | External Permits | Prior to Excavation | H | PE
3.01.06 | Approved Construction Drawings | Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version. | Downer | IFC Drawings | Prior to works start | H | PE
3.01.07 | Previous Completed Work Packs | Review previously completed workpacks to ensure work completed meets the contract requirements | Downer | CONQA | Prior to works start | H | PE
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | SUB ACTIVITY
4.01.01 | GAP20 | Record material type used and source testing of that material | BBO | Source Test/Site Notes | 1 source test per material type | R | SE
4.01.02 | Conrete Mix | The strength of concrete as defined in NZS 3109 shall be 28-day cured in-place minimum strength 20MPa. With a 13mm size aggregate. | NZS 3019 | Source Test/Site Notes/ Concrete Dockets | Each Pour | R | SE
SECTION 5 – CONSTRUCTION ACTIVITY
5.01 | Traffic Islands Construction
5.01.1 | Islands Set-out | After set-out and prior to installation of footpaths | PS - 2.2.16 | Hold Point Release | Min 24h Notice | HP | SE
5.01.02 | Concrete boxing and Base | Surveyor to check boxing for concrete pour, this includes the boxing for slots. For the front side of island aprons top boxing to be 50mm above F.L. | Downer | Hold Point Release | Min 24h Notice | HP | SE
5.01.03 | Concrete Strength & Reinforcing (Island Apron Kerb (mounatble kerb) and Infill) | Concrete to be at minimum of 350mm on the back side of the kerb with a max of 400mm thickness for construction tolerance, with 20MPA broom finish. Island Apron/Mountable Kerb reinforcing to be D12 Bars & R5 Stirrups @ 600 centers (min 75mm cover). For the infill, two layers of 665 Mesh (75mm min cover bottom cover and 50mm top cover). | Downer | Hold Point Release | Each Pour | HP | SE
5.01.04 | Concrete Pre-Pour | The Contractor shall give due notice to the Engineer of the time it is intended to place any concrete and no concrete shall be placed until approval has been obtained from BBO. Pre pour check wil includes checks on cover, lap length, spacing and bar sizes are followed per drawings specifications etc. | RITS - 3.4.5.3 | Hold Point Release, Pre-Pour Check | Min 48h Notice | HP | ENG
5.01.05 | Ground Preparation | Immediately before placing the concrete, the foundations shall be lightly dampened, and formwork shall be cleaned out. In all cases surplus water shall be removed before concrete is placed. Any foreign or organic material hall be cleaned out. | RITS - 3.4.5.3 | Pre-Pour Check | Each Pour | H | SE
5.01.06 | Frozen Ground & Unfavourable Conditions | Concrete shall not be placed on frozen ground nor shall it be placed in unfavourable conditions, which may be detrimental to the quality and finish of the concrete (i.e rainfall) | RITS - 3.4.5.3 | Pre-Pour Check | Each Pour | I | SE
5.01.07 | Curing Of Concrete | Immediately after placement, concrete shall be protected from premature drying, excessively high or low temperatures and mechanical damage and shall be maintained with minimal moisture loss for the necessary curing period and hardening of the concrete. In hot dry weather sprinklers or damp covers will need to be used. | RITS - 3.4.5.5 | Post Pour Check | Each Pour | I | SE
5.01.08 | Concrete Compressive Strength | Concrete to meet a placed 28-day compressive strength of 20-Mpa | RITS - D3.3.5 | Concrete Dockets | Each pour | R | SE
5.01.09 | Finished Work | Methods shall be used that will provide a smooth, clean and even surface on the exposed faces of all concrete work. | RITS - 3.4.5.7 | Post Pour | Each Pour | I | SE
5.01.10 | Contraction/Expansion Joints | Contraction/Expansion joints shall be formed or cut along the kerb at a maximum spacing of 3.0m. The slot shall penetrate the concrete by not less than 50mm and the mortar dressed over the cut face. The contractor shall ensure that cold joints are accurately marked and setout via total station so that the subsequent saw cut is in the cold joint. Should cracking occur adjacent to the saw cut a minimum section of 1.5 metres of the traffic island shall be removed and re-cast. | RITS - 3.4.5.8 | Post Pour | Each Pour | I | SE
5.01.11 | Finished Concrete (Surface Finish & Final Levels) | All final path and vehicle crossing surfaces shall be true to the lines and levels Specified and ‘broom’ finished. Design considerations aside, the final surface shall not vary by more than 5mm when checked with a 3m straight edge. No finished surface shall hold water. | RITS - 3.4.5.10 | Post Pour Check | Each Pour | I | SE
SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.01 | General
7.01.01 | Construction Record Compilation | Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted. | Downer | Records | Post construction | H | SE
7.01.02 | Survey Records | Ensure all items have been surveyed and records are assembled for asbuilting | Downer | Records | Post construction | H | SV
7.01.03 | Redline Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any changes to footpath location or basecourse depth. | Downer | Redlines | Post construction | H | PE
7.01.04 | Defect, Snag and Punch List | Update the project Defect, Snag and Punch List Register | Downer | Register | Post construction | H | PE