## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - Pavement Drains - Rev B | itp |  |  |  | Yes | ITP - Pavement Drains - Rev B | 07617a3d-1690-4fea-8873-e597f52837f9
checkpoint-group |  |  | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint-status |  |  | checkpoint | 3.01.01 - Construction Pack
label | f9f905ec-dac3-502f-bb0c-10f8858f0b9e |  | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
label | 64202acb-dcc4-53ad-a7c8-b0edb777bdc3 |  | note | Standard / Specification - Downer
label | 0e4649de-7aaa-5b42-b147-fc3af9edce0b |  | note | Verifying Document - Construction Pack
label | 99e69b24-2ef8-559a-8b36-853cb81f4080 |  | note | Frequency - Submit 10 days prior to commencement of works
label | 62f27ab6-cd9a-5e30-8824-fd5102c3dc6e |  | note | Activity - H
label | 1c5f89a8-cb44-594e-9268-a2c140fb894e |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.02 - Survey Setout
label | e8398258-2279-5bf9-a5b7-9ff664595e60 |  | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | 5816aeb8-9264-5828-b482-fe53c2cb6552 |  | note | Standard / Specification - Downer
label | f37c6830-756c-5cff-8a65-d31b68f3c4ba |  | note | Verifying Document - Survey Records
label | b09e40a4-5de5-5202-a114-0d8c5269a277 |  | note | Frequency - Prior to Works
label | ebc91c34-ab8c-5188-813c-aeae8fa3bcdf |  | note | Activity - H
label | ab80a7c3-9993-5b5b-bd1d-36bb7b2216d3 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 3.01.03 - Approved Construction Drawings
label | 5dd3cf45-0f1e-5179-a129-76755e28ce4e |  | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | 4986bf31-15c7-5782-b32b-ffc4e530cbcb |  | note | Standard / Specification - Downer
label | 7091b149-f5f8-57d4-ba8e-474e7db85504 |  | note | Verifying Document - IFC Drawings
label | 1fa87834-82d3-5a29-8c87-4ce1da32837b |  | note | Frequency - Prior to works start
label | d7a880fb-ee40-5de3-bed9-57e309c271d8 |  | note | Activity - H
label | ea67c3b9-7d45-549a-8fbf-e9469ca18927 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.04 - Topographic surveys for measurement
label | 3270d049-2f44-501a-8d00-f1ee3abb8282 |  | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
label | beb20a08-9dac-5a7a-8b7f-c9aa5fccf934 |  | note | Standard / Specification - PS 2.2.12
label | 1c1d5108-bae1-5026-b409-4c885281efc6 |  | note | Verifying Document - As-built
label | 65a51382-d93a-598e-8f98-972b6ebdbf49 |  | note | Frequency - Prior to works and Post Works
label | 4749ceef-fab7-5f70-9251-d1ada48d7c50 |  | note | Activity - H
label | 02840a85-27c0-527f-9ef6-145c8754fa88 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.05 - Permits
label | 50807822-529d-505b-a163-5260822af788 |  | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
label | 90b6e93b-e6e1-58c0-9936-c6693972fc15 |  | note | Standard / Specification - ITP Register
label | 536c9218-f180-54c7-bfd0-48076237f10a |  | note | Verifying Document - ITP Sign Off
label | 04cc1cf9-2d9d-5bfe-98df-804c10b36d4a |  | note | Frequency - Prior to commencement of construction activity
label | 06a73eb2-aa91-559e-8f70-68e42bc28d2a |  | note | Activity - R
label | c4bc4db5-753d-5597-954b-c24cf6203150 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.06 - Stakeholder Management
label | 86a06a11-d37c-5901-a3c7-4170d371020f |  | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works, Agree plans for maintaining access to properties during construction with landowners
label | 7f6c4578-84b1-5cc5-bf3d-44319a87a4ad |  | note | Standard / Specification - Project Stakeholder Management Plan
label | 1e9ebef0-55a8-5fdf-b99e-a12ee2df4cee |  | note | Verifying Document - ITP Sign Off
label | 5566c7d3-d686-5ed2-b4bc-0bc271c44753 |  | note | Frequency - Prior to Construction with continue updates throughout the works
label | 68b35d31-4a79-5437-badd-6b93a5b58f90 |  | note | Activity - R
label | bc6f5e99-7b6b-57a8-8e41-e1d5262397a6 |  | note | By - SE
checkpoint-group |  |  | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint-status |  |  | checkpoint | 4.01.01 - Pavement Pipes
label | 96b1a7f1-85cc-5d66-b770-6f76866fd3c9 |  | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 100mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
label | 0f69f95d-6aec-5570-9b13-d8eacf3060b2 |  | note | Standard / Specification - GWS 3.2.1
label | 4434c9c7-43b7-5f1b-8b22-c4453c52bad5 |  | note | Verifying Document - Datasheet
label | 754a3cf0-725b-5cd1-a08a-e2d078c31fe7 |  | note | Frequency - Prior to installation
label | 2d7c460e-131e-5907-8d9f-1c8f104f048d |  | note | Activity - C
label | cac7a427-106b-5f9c-b5c7-e4a37b7aeb41 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 4.01.02 - Pavement Drainage Aggregate (20/40)
label | 3b6dca9c-61bd-5bc5-b686-03fbe0eeedfd |  | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/5 including gradings
label | 2fae3c1e-3bfd-5ef7-9d9d-4dae40916943 |  | note | Standard / Specification - GWS 3.2.2 & 3.4
label | 2b8f8a7c-4e73-59e1-83ff-4ef962505cf0 |  | note | Verifying Document - PSD, CR
label | af4c9b13-db0d-5519-aae1-62da809db0cc |  | note | Frequency - Prior to installation
label | eed3aa0b-0614-5487-9549-b87c73f1a53e |  | note | Activity - C
label | 537db11d-3155-5bfb-ae34-d8a3c5ee89cb |  | note | By - SE
checkpoint-status |  |  | checkpoint | 4.01.03 - Filter Cloth
label | d29b7dfc-b211-5b9c-9984-0ba0bf576307 |  | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
label | 28bad559-4928-5e5f-9f41-7122fcb75523 |  | note | Standard / Specification - GWS 3.2.3
label | 43db19b4-f454-5c15-beae-a67d9cbde2bc |  | note | Verifying Document - Datasheet
label | e55becd8-4595-555d-beec-d2ea73ad571b |  | note | Frequency - Every 1,000m3. At least two weeks prior to works.
label | 56a52d32-7c27-5128-b939-c78098c959da |  | note | Activity - C
label | 6976b6dc-e081-5550-a1e7-0468e98a8f95 |  | note | By - SE
checkpoint-group |  |  | section | SECTION 5 – CONSTRUCTION ACTIVITY
checkpoint-status |  |  | checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
label | 9e165128-781e-549d-89fe-6ba0bca83d9d |  | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain.
label | 75acbafd-f4b7-564a-8f2e-7e3b8e6175ac |  | note | Standard / Specification - GWS 3.2.2
label | 2601e94e-bfc9-5ba4-9935-34bc6e32d41a |  | note | Verifying Document - Site Record
label | f1472b9f-081e-501c-97bc-997a7550c79a |  | note | Frequency - Prior to backfilling
label | 574ae29e-835a-5d55-851e-15072719c473 |  | note | Activity - HP
label | 2a1aa356-e8e2-5dc1-8a69-e3bee66a163c |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.02 - Trench Backfill
label | c32fb6b0-6d31-50b5-a9f9-b15ce15cb266 |  | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through
label | a350e562-5565-563b-be45-c7de757f35e3 |  | note | Standard / Specification - GWS 3.3
label | eb589190-0764-5bd8-b196-ab9f89aeadd3 |  | note | Verifying Document - Site Record
label | ec64a5de-6292-5125-afc8-6e484dc921d5 |  | note | Frequency - Each trench
label | 96223a88-c42f-59bc-8a2f-75d750191bf5 |  | note | Activity - I
label | 0fe3e741-b0c9-5b4a-950e-675b8e7a8cb4 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
label | 3c810906-ab97-5027-8b14-018bdbf84883 |  | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each pavement drainage system to enable flushing of the system once the earthworks are complete.
label | 8625e483-70ac-58fa-a63c-5b505f19c155 |  | note | Standard / Specification - GWS 3.6
label | acf2d88b-83dc-5f64-9576-d0852ac6e813 |  | note | Verifying Document - Site Records
label | cdb25d2a-550a-504f-b06c-c084ae70a89e |  | note | Frequency - Each Subsoil Line
label | c9725a45-5a3f-5375-8852-34fce7841b01 |  | note | Activity - I
label | 3fa79c56-5063-5667-b1ed-187effecba41 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.04 - Subsoil Flushing
label | 146b43a4-7c16-57cc-a6cf-da5fc2dc11fa |  | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
label | 3dc5f9d6-6b7e-598a-bcf1-9ef49a626c66 |  | note | Standard / Specification - GWS 3.6
label | 40597163-48fe-5bb4-abed-f49a4ab3f727 |  | note | Verifying Document - Site Records
label | 81138943-d4c0-5721-8706-938fd6ea6c1e |  | note | Frequency - On completion of earthworks
label | 77f50290-a8cc-5b36-8fbd-7ebde75092c5 |  | note | Activity - HP
label | 80964aa3-b2e1-5303-8e6f-9b2b7f6e2b61 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.05 - Survey
label | 83dfab8a-5f1d-5b7b-a954-59c2747642a3 |  | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | 6c26521b-8245-5d7e-b411-4c900816384e |  | note | Standard / Specification - Downer
label | 2c583d67-eb6e-53d2-b2ab-3baa3432b8a6 |  | note | Verifying Document - Records
label | f17845ff-202a-5027-9bf4-c357176b925e |  | note | Frequency - Post construction
label | 35f5336e-12df-51d7-be76-3fbfd57b0294 |  | note | Activity - H
label | 00a72da5-033b-540e-8cfe-fd04d992fbb1 |  | note | By - SV
checkpoint-group |  |  | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint-status |  |  | checkpoint | 6.01.01 - Construction Record Compilation
label | 94904fe6-c43b-559a-aef9-d0a9d69d2747 |  | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | 76fe4fd9-d793-5a9b-9bb6-1ba89c817758 |  | note | Standard / Specification - Downer
label | 41b86b8f-efcf-5168-92e9-5c3a7cbe723e |  | note | Verifying Document - Records
label | bf359400-b405-5c46-8907-c725b0286925 |  | note | Frequency - Post construction
label | c38a501d-bb9a-5874-b05e-cc342037f315 |  | note | Activity - H
label | 4abd56a4-d3e0-50b3-b3f4-45abf498776e |  | note | By - SE
checkpoint-status |  |  | checkpoint | 6.01.02 - Survey Records
label | 342e2dfe-333c-563c-ac47-bf2ad8809947 |  | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
label | 3ecd713b-e021-58a2-b407-73e34039e4c7 |  | note | Standard / Specification - Downer
label | f2c7697f-6ab7-5136-85d0-2c87cabad9fe |  | note | Verifying Document - Records
label | b8b21edf-472a-5f12-821e-5aa99e216de4 |  | note | Frequency - Post construction
label | c05c2993-8167-58db-91d5-a3321df9a3e2 |  | note | Activity - H
label | a58f2874-0112-5df0-af4c-ec4b73c7c8fa |  | note | By - SV
checkpoint-status |  |  | checkpoint | 6.01.03 - Redline Drawings
label | 85b5a3e2-2bbe-5298-b838-18c0854aaacc |  | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | 48e37755-862a-50fb-9b1a-5b2267c78356 |  | note | Standard / Specification - Downer
label | 76233806-0448-5389-9e1d-3a92930e7685 |  | note | Verifying Document - Redlines
label | 2d0fd7b7-749a-58dc-8dc7-75b5936b0277 |  | note | Frequency - Post construction
label | f3817025-ebd0-5ca4-a077-81025f6261cd |  | note | Activity - H
label | 39ae6ec5-d5c7-5a26-9e5e-2bdfc068a03b |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.01.04 - Defect, Snag and Punch List
label | f0159e04-a466-5fe4-adc3-81a376e60577 |  | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | c3d28e82-3281-543a-84af-218e8ea0f0a9 |  | note | Standard / Specification - Downer
label | 59d7e756-18b4-5b6a-a587-817b68df5f6a |  | note | Verifying Document - Register
label | 72cbc43b-53fd-515c-ad00-f2d831c67180 |  | note | Frequency - Post construction
label | 95193713-c4ce-52ef-84a6-aad9ad724f57 |  | note | Activity - H
label | 7316119c-849d-55ef-985d-6b8f77e1038d |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.01.05 - Photos
label | 03b319ab-784d-5a7a-a8b1-8411dd191456 |  | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
label | da852884-2aaf-536d-9dcf-952353840ca1 |  | note | Standard / Specification - Downer
label | b08880c2-7512-5591-b327-dc150a36a882 |  | note | Verifying Document - Photo Records
label | 0b59f7aa-0b29-5389-a957-c398d4254551 |  | note | Frequency - Post construction
label | 2f5bb31c-dc18-5378-b91d-1fb9c4ec1d18 |  | note | Activity - H
label | f0e156ea-88a2-5ba3-9cbf-1dd50dce592f |  | note | By - SE
checklist-sectioned |  |  | checklist | ITP - Pavement & Surfacing - Subbase - Rev E | itp |  |  |  | Yes | ITP - Pavement & Surfacing - Subbase - Rev E | 0f5e5930-b295-4394-bef5-bf0647e45f2a
checkpoint-group |  |  | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
checkpoint-status |  |  | checkpoint | 3.01.01 - Construction Pack
label | ec4e551b-3f47-528c-ae6c-fdfb3458be34 |  | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence
label | eb1c5ab0-d958-5aff-9e01-8f56d5db5c3c |  | note | Standard / Specification - Downer
label | 95e813a5-8719-5ac9-9ed3-db95c88daa4f |  | note | Verifying Document - Construction Pack
label | 805d2c95-dc1c-508e-8b9e-fbca9c1eeaf6 |  | note | Frequency - Prior to Works start
label | fc39fb4d-ffff-5e1f-8d56-399758b18a65 |  | note | Activity - H
label | 802be262-7e7e-53e8-b8bf-6038d6e34751 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.02 - Survey Setout
label | 27f3be6b-b818-5263-817f-5ba924480d35 |  | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | 1f441f83-2c34-577a-90e0-73818924a2cf |  | note | Standard / Specification - Downer
label | a4fa1ba9-6110-5364-ab83-c9684041414a |  | note | Verifying Document - Survey Records
label | 7fe5d102-a89b-537b-849f-5cc7bf99618c |  | note | Frequency - Prior to Works start
label | d378e4fb-1992-5af0-8e29-ab8e511f0e7e |  | note | Activity - H
label | ed48a75e-9faa-5783-b481-e3f0f2090547 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 3.01.03 - Service Location
label | 07cf3e6e-2226-5ee4-b1f5-8fff7d3c89fe |  | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | e5694d8a-f45f-52e8-b573-2ce535af9e31 |  | note | Standard / Specification - Downer
label | b2970209-fe08-5050-ba93-b0537bd69e94 |  | note | Verifying Document - Excavation Permit
label | e872e4d7-566c-548c-8e05-f649772197fa |  | note | Frequency - Prior to Excavation
label | 0ef56c5b-7c85-56e8-9a7e-aab9f6807218 |  | note | Activity - H
label | 53f0bb53-59d4-5d30-9a93-b3b481462cec |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.04 - Internal Permits
label | 8f9ece01-d727-5876-8560-edbd9d82bcf8 |  | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. if applicable.
label | a7ee36d2-9b73-5f58-b71b-db5ca41fe4a2 |  | note | Standard / Specification - Downer
label | 85ad478e-6552-52d0-b8b4-54e1f7ffbc8d |  | note | Verifying Document - Internal Permits
label | 93d4943e-f796-520a-9124-ecb481319afe |  | note | Frequency - Prior to activity being undertaken
label | ea702c86-97c6-5605-ba1e-bfeeb7f387ec |  | note | Activity - H
label | a2718418-fc15-5b59-89c6-07251b3f0c0b |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.05 - External Permits
label | f23abc2d-c8ee-50ea-854a-9f64a7d9d86a |  | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc, if applicable.
label | 6b62d5fe-af97-5ca3-b301-bd92f2791dc8 |  | note | Standard / Specification - Downer
label | a02559dc-175e-589a-9b8a-8eab68d69cad |  | note | Verifying Document - External Permits
label | b2f5d673-8cc4-5dbc-8d75-deccfbe742fe |  | note | Frequency - Prior to commencment of activity
label | d3a90524-e3a6-5f9e-b9d3-b83ba77aa7bf |  | note | Activity - H
label | 13bc7be9-6edd-55c9-a267-e302e9aee166 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.06 - Approved Construction Drawings
label | f56d4abb-1946-538b-aad6-86aea7955913 |  | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | 09117102-46e6-57a9-9743-cdcaf0e4e481 |  | note | Standard / Specification - Downer
label | 46964b83-84c6-5336-b6bd-922be5cef306 |  | note | Verifying Document - IFC Drawings
label | 39dfba69-75f7-5742-968e-a4c90dbb0b22 |  | note | Frequency - Prior to works start
label | 68e4c5de-58e0-5dec-91c6-170e024e015a |  | note | Activity - H
label | 3d527e69-1c47-5f3d-8273-fc7878a3c156 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.07 - Stabilising Methodology
label | f31947ca-c372-52b1-9187-bb4248d3254b |  | note | Acceptance / Conformance Criteria - Written approval of the Engineer with the approval of the methodology
label | a161a67c-8a7a-5dd1-9557-f02e91f6b027 |  | note | Standard / Specification - PS - 7.3.3
label | 07fd60c0-fd43-5cf7-befe-31b3417972ce |  | note | Verifying Document - Correspondence
label | 5f17963d-05de-50a8-9578-9003dcf71a00 |  | note | Frequency - Prior to stabilisation start
label | 4c607593-a8eb-5c32-8ec8-95b0db6dee42 |  | note | Activity - HP
label | b8772278-c47a-56b1-a98c-0284beffbb55 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.01.08 - Acceptance of the SIL layer
label | f6339289-345f-5f4c-9a10-88376f46e5fd |  | note | Acceptance / Conformance Criteria - Written approval of the Engineer - All compliant test results for subgrade, SIL, all road crossings, storm water, wastewater, watermain, subsoil/pavement drains and any other activity that has been completed in the pavement area.
label | 02730cba-a67f-5416-abdc-90b5998957c6 |  | note | Standard / Specification - PS - 4.8.3, Table 4.3
label | 847b87f3-2330-5a62-abcc-ad8b65920f34 |  | note | Verifying Document - Hold point relesed / Testing reports
label | 683e6528-9871-5c86-b102-a59b4f362661 |  | note | Frequency - All sections before proceeding to the next layer
label | c2f09181-52a5-56b6-a1b5-1c437cb54f45 |  | note | Activity - HP
label | ad1d82fa-b960-58f5-b406-029832fbcf42 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.02 Sub-base - Non stabilised AP65
checkpoint-status |  |  | checkpoint | 6.02.01 - Sub-base MDD and OMC
label | f168b349-b948-59e0-834f-0b2ba45e5df5 |  | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | 94791044-7035-5d70-836b-5bd471f60add |  | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | 72003631-2a30-59ed-9ccd-8bb41b9e6939 |  | note | Verifying Document - IANZ Lab Reports
label | a294e292-acfa-5d4d-8bb2-ac429ec82d86 |  | note | Frequency - No less than 1 test every 5,000m³ (in place)
label | f3890077-fa2d-5c9d-ac37-159c3531b5d4 |  | note | Activity - R
label | a55f805a-3e05-57ce-9887-0771a0f2e46b |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.02.02 - Plasticity Index
label | 1a02b294-b8c7-54a8-88ad-4b2eadf677b4 |  | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Liquid Limit shall be ≤ 25 when tested
label | de15fba3-2af3-5447-92e4-0ff93b28081b |  | note | Standard / Specification - Table 7.2
label | c8b38c01-7756-58f6-b0f0-b99d29d920dc |  | note | Verifying Document - IANZ Lab Reports
label | bfa862fa-eabc-5114-9532-f6da19c44f1a |  | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
label | bb7cea44-7b13-513c-8a99-abf001a2a74e |  | note | Activity - R
label | eadf6b0e-0f1f-54ef-b126-27840805effb |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.02.03 - Clay Index
label | d48bd89a-2cde-500f-a65a-9c0ead3920c3 |  | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Plasticity Index shall be ≤ 8 when tested
label | 24123e95-13ac-553f-becd-8e344e653d5b |  | note | Standard / Specification - Table 7.2
label | 5041442d-2667-52e6-a388-347fcd1cc8bc |  | note | Verifying Document - IANZ Lab Reports
label | 864c5f20-dd61-50e0-9e7c-7c6a82ee48d0 |  | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
label | 2c66b3e5-64c2-50ca-add7-1f48a636da59 |  | note | Activity - R
label | 84b352e3-3712-5479-adda-d025a9ad206a |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.02.04 - Sand Equivalent
label | ee50526c-e9ec-5c79-91e8-670f2c1bb39e |  | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Clay Index shall be ≤ 5 when tested
label | c3d6c15e-6c07-5af7-84c6-1527766f8f9a |  | note | Standard / Specification - Table 7.2
label | 8181ba8f-30d8-5506-b06d-a29546a00eb8 |  | note | Verifying Document - IANZ Lab Reports
label | 7f791590-653e-5bbc-b299-61b3e8ad6c10 |  | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
label | d7befb75-e056-5ad0-9068-054f15d42590 |  | note | Activity - R
label | 068d12a9-5531-5e68-ad78-ad8c0ed428d7 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.02.05 - Particle size distribution
label | 1a8c69dd-c0e2-5b47-94bb-913d372659c7 |  | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1
label | ceeab263-cfbd-5a84-ae44-c53ca329d997 |  | note | Standard / Specification - Table 7.1
label | 7ea3aa39-7de2-5b9f-a333-ab9d10071ce9 |  | note | Verifying Document - IANZ Lab Reports
label | 836f527e-24cd-55ae-8a9c-b4fcff7cf69f |  | note | Frequency - 2 tests per 1000m3 (in place) - Test on Mat Samples
label | 4df9e8bd-bbda-58ac-aec9-614f3c35ec32 |  | note | Activity - R
label | 519ac218-21ef-581c-bc55-b73daef7619a |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.02.06 - Average Uncompacted Layer Thickness
label | 6b32e036-d252-594f-8ce0-3eb80aff0240 |  | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
label | 648b2fed-46ce-540e-9f51-a18bfb12ba86 |  | note | Standard / Specification - TNZ B/02: 2005 - 7.3
label | a42810de-1507-53dc-be0f-446a8c7d0ee8 |  | note | Verifying Document - Survey / Level Checks
label | a0f4bd8f-6e11-51e8-bc6d-c882447e2666 |  | note | Frequency - 1 test per 20m
label | 67978ffa-b835-59d4-9b56-3c8a6dad8a32 |  | note | Activity - I
label | 72a4512d-e758-58f5-9856-07e0d6ca6500 |  | note | By - SV / PE
checkpoint-status |  |  | checkpoint | 6.02.07 - Plateau Density Test
label | bc29dd99-a71a-51dc-8d02-33bf0f61312d |  | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
label | a31f8a84-a71e-59ae-80d8-12cc4a5710e9 |  | note | • Testing shall be at OWC.
label | a79e6939-4ab3-5aa1-a23e-dc5097a70f43 |  | note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
label | 4db60e69-808f-52cd-b326-970523d0b24a |  | note | Standard / Specification - PS - Table 7.2 - 2.3
label | d156f274-aee5-52c1-bb6b-8c7211c6a105 |  | note | Verifying Document - Plateau Density Report
label | 22cb08a8-dbdb-5f03-aa42-cd222fd52a80 |  | note | Frequency - 5 tests per 10,000m2
label | 0da96e90-93be-5ae0-8294-d4d6764a24d9 |  | note | Activity - I
label | bd2aacaa-57e0-578e-ab16-49fcbb5e5588 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.02.08 - Sub-basecourse Pavement Layer Compaction
label | a565c723-69ac-5886-b35c-2693ff3155e2 |  | note | Acceptance / Conformance Criteria - Mean Value ≥ 95 Minimum Value ≥ 92
label | 3051c527-6171-5f07-a895-8e8d848accaf |  | note | Standard / Specification - TNZ B/02: 2005
label | fbf04794-d375-5824-a102-a8516cf4f602 |  | note | Verifying Document - NDM Report
label | 001719f7-47b0-537b-8df8-97351cfd4bb3 |  | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
label | 4b955460-5c4e-5883-ab40-c8250043fc8c |  | note | Activity - I
label | 6329ddc7-ac2c-5ed4-9026-9cdc6dfcb567 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.02.09 - Surface shape control
label | f6d19746-988e-53c0-bd07-7cf2bbecfe30 |  | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
label | 4a673db2-094e-5953-9808-6c7c3a311467 |  | note | • Vertical: - 25mm +5mm
label | 3bda55bc-9b4e-5f0b-8a0e-8913bca49280 |  | note | • Cross fall: 0.5% on 2m straight edge
label | f0699e7d-4488-5930-bc24-e6bde8144145 |  | note | Standard / Specification - TNZ B/2
label | 1b64c389-5f95-5892-ab77-39b0c10f8109 |  | note | Verifying Document - Total station Topo showing levels compared to design
label | 2c19adde-02f1-5f99-b87f-abae30ebd503 |  | note | Frequency - Continuous
label | d69e2e2d-e889-5d9e-9ec6-25206323c908 |  | note | Activity - I
label | e95c8e22-5607-581f-acaf-8299ff2bd117 |  | note | By - SV / PE
checkpoint-group |  |  | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.03 Sub-base Stabilisation trial
checkpoint-status |  |  | checkpoint | 6.03.01 - Stabilization Production Plan
label | c9ddb8f7-8811-5c24-a98e-4a7b7bde9d00 |  | note | Acceptance / Conformance Criteria - Production plan sent to engineer for review 48 hours prior to stabilising commencing. This is to include all information set out in NZTA B/6 7.2.3.
label | da0f5c1e-3efd-569f-b2ef-0d62230cc56f |  | note | Standard / Specification - NZTA B/6 7.2.3
label | 503a87ad-53dc-5338-b7d6-41d39018bdad |  | note | Verifying Document - Correspondence
label | 4b686472-ead5-5dca-9e19-e1a7af89afd6 |  | note | Frequency - 48H hours prior sabilising commencing
label | cb4be3d2-1fc8-5f91-99ab-ff9da052c5f2 |  | note | Activity - HP
label | abad576a-df96-543f-9ab1-765a1ff468b2 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.03.02 - Longitudinal Joints
label | f2cfb2e7-40b5-5204-868e-224c0ffe7c5f |  | note | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 200 mm or half the layer thickness, whichever is the greater.
label | 7b7caba1-a9c4-5c5d-a3af-5fea17a64691 |  | note | Standard / Specification - NZTA B/6 7.5.2
label | 1ac5d31f-9758-50ae-9f72-48d864679110 |  | note | Verifying Document - Stabilisation Prodution Plan
label | 9af7f4d5-44b2-586a-b84d-14083db10bdc |  | note | Frequency - 48H hours prior sabilising commencing
label | 703a7061-48ec-50a2-bf67-28fd4c8b61f9 |  | note | Activity - H
label | 3ecbad6b-6769-52d3-8371-9bae9e3e68bc |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.03.03 - Stabilisation trial
label | aaf3fcc6-69cf-5107-bdd2-324afb462409 |  | note | Acceptance / Conformance Criteria - A trial shall be conducted on a minimum stabilised area of 2,000m2 to verify the performance of the stabilising operation and finished product prior to full scale production.
label | 32d89166-cc92-5257-8a02-b42deb788bcf |  | note | Standard / Specification - PS - 7.3.3
label | fc6cde74-b4bb-53b0-8942-0552487547d2 |  | note | Verifying Document - Triall Report
label | 835b815b-b849-51c9-8abc-91b75b5897e4 |  | note | Frequency - prior to full scale production
label | 10b65111-54b2-5545-b5b5-be46c4838f88 |  | note | Activity - HP
label | c72f6072-5eca-5743-b96b-117fc11d2cf9 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.03.04 - Stabilising Equipment
label | b85e3249-9895-5172-a001-1466f4265669 |  | note | Acceptance / Conformance Criteria - The Contractor shall use stabilising plant purpose built and appropriately adjusted for the in-situ stabilisation of roading aggregates, as opposed to plant designed for soil stabilisation or re-cycling.
label | 1ee3589b-5081-5efc-bdad-6aba26d6e9a5 |  | note | • The stabiliser drum shall have a straight tooth pattern and the drum speed must be adjustable in real time during stabilisation.
label | a3776b5d-7d91-53eb-bb08-1af17fb325a2 |  | note | Standard / Specification - PS - 7.3.2
label | 3b65390a-1386-58dd-8d6a-5e763cde91a7 |  | note | Verifying Document - Plant Approval
label | 88a73c18-536b-5f46-bb46-d7b80e90b423 |  | note | Frequency - Prior to works
label | 83e5610e-6576-5395-a4fa-7274e96a60c7 |  | note | Activity - H
label | 64cc6353-220e-5907-bfcd-449c0bc979dc |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.03.05 - Stabilising Supervisor
label | 4892293b-c97e-5f7b-8af6-863f1c449d64 |  | note | Acceptance / Conformance Criteria - During stabilisation the Contractor shall employ a suitably experienced person to continuously walk behind the stabiliser to assess the uniformity of the mixture and water distribution and to check the stabilisation depth every 100m.
label | b82eadfd-0943-56e1-8a03-094e7c34f50c |  | note | Standard / Specification - PS - 7.3.2
label | 3551a47b-12a0-5a1a-8ea5-7b63cff98b4c |  | note | Verifying Document - Supervisor Approval
label | 8251bbf9-5e57-58ad-aee4-43bbe9f37c78 |  | note | Frequency - Prior to works
label | a4146f77-cb32-5f0c-9c04-6338cd5be9c9 |  | note | Activity - H
label | 21f6550a-d45f-508e-b98b-d3e37a65df52 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.03.06 - Before Stabilisation Surface shape control, layer thickness
label | 04e2ce5c-fc23-51ac-b996-8b395cb81ee1 |  | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
label | c79417a1-d3da-5554-8196-a20418d2f028 |  | note | • Vertical: - 25mm +5mm
label | be91c280-43e7-5a2f-b532-dea6df56a8d0 |  | note | • Cross fall: 0.5% on 2m straight edge
label | 7ce457fc-836f-5cc6-a269-ba8371d1833a |  | note | Standard / Specification - TNZ B/2
label | 84a096bf-3ee3-5f72-a1d9-f550bc29364f |  | note | Verifying Document - Total station Topo showing levels compared to design
label | 038c979c-acff-5c79-bdf8-95a17d456d70 |  | note | Frequency - 1 test per 20m
label | 25a6b6d3-0568-511b-98c0-be8b869b3e71 |  | note | Activity - I
label | 80588976-67d6-54ca-9d40-618b6fdcc383 |  | note | By - SV / PE
checkpoint-status |  |  | checkpoint | 6.03.07 - Average Uncompacted Layer Thickness
label | 57abe783-f1ed-53d3-84cc-34e27300e213 |  | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
label | f3e06d3b-2107-5ca4-ab1d-8e980c44d108 |  | note | Standard / Specification - TNZ B/02: 2005 - 7.3
label | b91bd336-8e5c-532c-ad9d-fea08ac6590e |  | note | Verifying Document - Survey / Level Checks
label | 46a082e0-947d-55f6-9700-208f12e701e9 |  | note | Frequency - 1 test per 20m
label | b0e66bd0-e4af-5d26-8d47-bf34fe7b8ca6 |  | note | Activity - I
label | 7b9507c3-415a-57b6-ad99-2fa7d63f6ca9 |  | note | By - SV / PE
checkpoint-status |  |  | checkpoint | 6.03.08 - Pre Stabilisation Compaction
label | 2de608fd-6034-5977-8b48-ace7c120a2de |  | note | Acceptance / Conformance Criteria - The full thickness of the layer to be modified shall be compacted between Value ≥ 95% and Minimum Value ≥ 90% Prior to stabilisation, this will be reviewed following the stabilising trial and adjusted to suit and the updated target shall be added after the stabilising trail. DN1205-DOW-RFI-0043.01
label | c076cd42-6e8e-5b46-a0df-e078704d7870 |  | note | Standard / Specification - PS - 7.3.2
label | f288a3ff-d1e2-5f20-920c-7fa4a3abc914 |  | note | Verifying Document - IANZ NDMS
label | f0c423cb-1eba-5011-80ac-05005e695439 |  | note | Frequency - Min 5 Tests per lot 1000m2 max lot size (Prior to stabilisation)
label | 35184592-ddea-5789-9628-76295e981225 |  | note | Activity - I
label | 5948452b-0aae-5278-993c-de000a64b387 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.03.09 - Pre Stabilisation Crossfall
label | 7dcc80a1-3999-5c00-bfc3-bf293b8a8647 |  | note | Acceptance / Conformance Criteria - Before stabilisation the Contractor shall check the crossfall by string line to confirm compliance with the design.
label | cf25e97d-2159-5462-a6ce-4196b9d4293a |  | note | Standard / Specification - PS - 7.3.2
label | 3b2b548d-399e-519d-9d69-9a2927c0b6b1 |  | note | Verifying Document - Total station Topo showing levels compared to design
label | 5303e7de-4445-5c0f-9266-790d456b0644 |  | note | Frequency - 1 test per 20m Prior to stabilisation
label | de272e7d-a2c4-580c-9190-796fa51c3638 |  | note | Activity - I
label | ca2a2111-0158-5182-be1b-445174fedcb3 |  | note | By - SV / PE
checkpoint-status |  |  | checkpoint | 6.03.10 - Stabilising Visual appearance
label | 8f8865c0-7ffc-5b16-807d-503d621cbc5a |  | note | Acceptance / Conformance Criteria - The stabiliser shall produce a uniform particle size distribution behind the stabiliser, both laterally, vertically and longitudinally and produce minimal break down of the coarse aggregate particles during mixing.
label | cf749d9a-5bf1-50bf-a203-7e3c464d3673 |  | note | Standard / Specification - PS - 7.3.2
label | aa34d7ad-4e05-5677-b27c-5f6f1411f00b |  | note | Verifying Document - Site Notes
label | 69f6c763-0a03-51d9-bfa5-534ccacaf6ef |  | note | Frequency - every 100m
label | d91ec8a3-6ce2-52e2-80f0-1b03438f13ee |  | note | Activity - I
label | 87e701c1-161f-5285-9b2e-cd20ebb3e36d |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.03.11 - Cement Mat Test / Spread Rate
label | da3f72b4-b1e3-5657-808e-2bc54fe47d04 |  | note | Acceptance / Conformance Criteria - The stabilising agent shall be uniformly spread at the specified application rate across the pavement to Within ±0.5 kg/m2 of the specified rate
label | 24f9b6df-5b16-5895-9f6b-b49960501d8d |  | note | Standard / Specification - Table 7.2
label | 94fee484-a5b3-5490-bb40-6bf4b0938f69 |  | note | Verifying Document - Stab. Sheet
label | 99cdf68f-0152-5f34-b1a5-3760076113bb |  | note | Frequency - One per each run of cement spreading, until the Contractor can demonstrate consistency in cement spreading and/or demonstrate accuracy of on-board computer equipment calibrated/compared against weighing cement mats.
label | 7ddb2bae-c964-5cf3-8183-009d7060c3bb |  | note | • Upon successful demonstration of this, the 1 per 500m2 minimum can applya
label | 1cfad76f-afa0-56a5-94e6-cd4c58e6b657 |  | note | Activity - I
label | e92ba43f-b2f2-5c8a-9649-ee66f9671721 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.03.12 - Cement Average usage test
label | 201f6146-1817-5edb-a22c-c29f7f45f2a0 |  | note | Acceptance / Conformance Criteria - Compare tonnes used (from delivery docket) with measured area Within ±2.5 % of the specified rate
label | f17dd1db-7f20-5312-b139-97755128b80c |  | note | Standard / Specification - TNZ B6
label | 749b65f8-ccd4-520b-90d3-1e9fdbd250c1 |  | note | Verifying Document - Stab. Sheet / Delivery Doc.
label | 6586c6f9-d9c7-524c-beaf-40df78cc4131 |  | note | Frequency - Upon emptying the spreader and bulk tanker
label | 914cde35-1363-5dfb-920a-556fed6e74b9 |  | note | Activity - R
label | 658e3f08-7984-52e5-8b16-f6fa47795fdf |  | note | By - SE
checkpoint-status |  |  | checkpoint | 6.03.13 - Control of cut depth
label | 46b9f88e-99c9-5a60-a968-15cc96292ceb |  | note | Acceptance / Conformance Criteria - Maximum variation from the specified depth of cut is –5 mm and +15 mm. Without picking up sand from SIL
label | 8f09f694-78a6-5532-93a0-59f7ad96ba2a |  | note | Standard / Specification - TNZ B6
label | 4afa3e59-c79c-5e6c-b5c5-86d8c9c5c9b0 |  | note | Verifying Document - Stab. Sheet
label | 2be0fa1c-b437-5b11-a13e-69e22b6f8b08 |  | note | Frequency - First check of cut depth should be immediately behind the stabiliser at the start of each run, then again every 200m, or as requested by the Engineer
label | ce80a921-3335-5a15-a8f6-c9b7326838fd |  | note | Activity - R
label | 5f9d6dc1-3b64-5181-89c5-19a73f488add |  | note | By - SE
checkpoint-status |  |  | checkpoint | 6.03.14 - Plateau Density Test
label | decd180e-26e7-56c8-a3c1-c00f8720c9e0 |  | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
label | c865ae35-c13e-5881-99c9-18bc78a225a6 |  | note | • Testing shall be at OWC.
label | f64e7a3a-7098-52be-8784-a85fae85996e |  | note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
label | 177e1bb7-f470-50c1-bb79-20e420d6426e |  | note | Standard / Specification - PS - Table 7.2 - 2.4
label | f69b2107-9d61-5d1d-afc0-990e1ee682b7 |  | note | Verifying Document - Plateau Density Report
label | 572e474c-67c5-55ad-aa87-750d7a624c7e |  | note | Frequency - 5 tests per 10,000m2
label | 1e50156b-7f28-5a92-98ef-c62f718b4864 |  | note | Activity - I
label | f832f683-84fa-54d1-b808-402011fa634a |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.03.15 - Particle size distribution behind stabilizer (Wet Sieve)
label | 9a4fb5ed-bd27-535b-a022-bebf285b6004 |  | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1. A Wet sieve analysis will be completed within 4 hours after stabilizing
label | 00eb80fa-3200-5417-b532-c46d18a37a6a |  | note | Standard / Specification - NZS 4407: 1991 Test 3.8.1 Standard Method by Wet Sieving
label | c1e6242b-b982-5e22-a725-33ef54319773 |  | note | Verifying Document - IANZ Lab Reports
label | d2116d61-7adf-57d3-8106-1c51336749a8 |  | note | Frequency - 3 samples bag per stabilise day post hoe
label | a2dcec01-55c7-552c-b0b0-ddc1a435ae63 |  | note | Activity - I
label | ca9469bb-b5fa-592e-b002-a0f30567b1c6 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.03.16 - Mixed material testing (ITS)
label | e2b5c14a-af27-5eb6-b955-0adb175e234a |  | note | Acceptance / Conformance Criteria - During mixing, the contractor shall take a pair of representative samples behind the mixing plant per lot or at a minimum of 2 pairs of representative samples per day.
label | d688278a-6706-534e-8852-c900e1806fab |  | note | • These samples shall be placed in a sealed plastic bag and cured for 1 hour before compacting into a mould and testing the indirect tensile strength (ITS) of the mixed material according to NZTA T/19
label | 47d240fd-1755-530d-8cb6-4e1fc7b7bf94 |  | note | Standard / Specification - TNZ B6 7.5
label | 773ab540-931e-5436-96b7-b637f29e940a |  | note | Verifying Document - Test Results
label | b5a4545b-eeba-56b5-ac7c-309e3f13ba69 |  | note | Frequency - 2 tests per stabilise day
label | 9405b5d3-7923-5d1c-ab1e-7daadd0fb3c8 |  | note | Activity - R
label | a81873b5-9bab-5d3c-bab6-8f7d512b6321 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.03.17 - NDM Water correction
label | c25bbffd-26b9-5cd1-9007-ea0430d5425a |  | note | Acceptance / Conformance Criteria - Daily Laboratory water content tests shall be carried out on samples taken and used to correct the NDM measured dry density.
label | 7094f35a-7333-5c0e-a9fd-b35dd164b270 |  | note | • Will get the Moisture correction factor from the Plateau report itself. That is the difference between the Moisture reading on the NDM vs the actual moisture when dried in the oven.
label | a4a8ac4a-1615-59b8-a711-d27a3ceeb43a |  | note | Standard / Specification - NZS 4407
label | d9b5523a-05b2-58fd-9e57-a9303f0304c4 |  | note | Verifying Document - Corrected NDM Results
label | 9249129b-f15a-54ce-b381-d81ad35dac4b |  | note | Frequency - Per Stabilise day
label | 245a86d9-a73e-59fa-aa80-37e87cd97e1e |  | note | Activity - R
label | 8af1dd0a-24d3-5a19-a2b8-7017f0a60f45 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.03.18 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
label | 5d68a0f4-4196-5761-9790-d8be3e07e987 |  | note | Acceptance / Conformance Criteria - The sub-base compaction requirements in Table 2 of B/6 shall be replaced with a Mean Value ≥ 98% and Minimum Value ≥ 95%. - Direct Transmission
label | 71e6b7a8-57ce-5ca8-a855-be653ee16563 |  | note | Standard / Specification - PS - 7.3.2
label | c38c893e-c4af-5435-8b10-5cea4af66292 |  | note | Verifying Document - IANZ Lab Reports
label | 09c7affc-1350-5f10-b8e6-a01c82222f60 |  | note | Frequency - Min 5 Tests per lot 1000m2, minimum 7 days after stab.
label | f13edf28-3a07-5e5e-8f90-380006fa79fa |  | note | Activity - I
label | 766ab5be-df67-5b77-9a8a-613a23d83192 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.03.19 - Post Stabilisation Surface shape control, layer thickness
label | 8b976792-3213-50e1-9b79-b17bfa92e2cd |  | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
label | bb1aaf06-ac2a-5c01-b59c-99c125149d3d |  | note | • Vertical: - 5mm +10mm
label | 826abe9c-7624-52b5-81ae-9dba7f27ccbe |  | note | • Cross fall: 0.5% on 2m straight edge
label | c94a6cad-a425-5c8c-b31f-1d39bfc23390 |  | note | Standard / Specification - TNZ B/2
label | 504e543b-ebf4-5caa-97da-11e2e571a421 |  | note | Verifying Document - Total station Topo showing levels compared to design
label | 844977c8-ff1d-5b87-8ce8-15c352b20022 |  | note | Frequency - 1 test per 20m
label | d1b3ec14-8717-5fd1-aff6-6d207298a937 |  | note | Activity - I
label | 7badf766-988c-53cd-9bbf-3c397b0a935d |  | note | By - SV / PE
checkpoint-status |  |  | checkpoint | 6.03.20 - Protection, Curing and Maintenance before Overlaying
label | 3d71e903-b505-5839-85cf-cc631955ea52 |  | note | Acceptance / Conformance Criteria - The Contractor shall protect, maintain and cure the completed cement bound sub-base until the next layer is applied. Besides construction traffic required for the above curing no other construction traffic shall be permitted onto the layer within 7 days of stabilisation
label | 2ccf6b0a-db10-5b23-b23c-8b040512c59a |  | note | Standard / Specification - TNZ B6 - 7.8
label | a1ab7aa0-62a0-586d-85bb-84e441f89c33 |  | note | Verifying Document - Site Notes
label | 13fbbedb-5f36-5063-a677-5482008a00f9 |  | note | Frequency - For 7 days after stabilisation / Photos
label | aafc97a3-8cfb-53f8-b823-b6d7c5d4fecc |  | note | Activity - R
label | 54e81eef-18ff-5283-8882-1692dfd66af4 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.03.21 - Benkelman Beam
label | 86073cf5-cb7d-5788-8fad-6c6c432370b0 |  | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer.
label | f46ea1ac-e9f1-5874-9372-f9aea3a5d9c8 |  | note | • Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
label | 3efa5857-763b-54d3-8278-799e35daacd2 |  | note | Standard / Specification - PS - 7.3.2
label | 9e77db51-97a0-5170-bcaa-6857975a2049 |  | note | Verifying Document - Benkelman Beam Report
label | 265fb537-4cec-53b7-86ff-39b6861b114d |  | note | Frequency - Every 10m of each lane – staggered between left and right wheel path.
label | 96390e81-b614-50bb-93c7-f3d2b0c95b35 |  | note | Activity - R
label | eb2d27cd-0b0d-5dd3-b96e-e4eb2ff8392a |  | note | By - SE
checkpoint-status |  |  | checkpoint | 6.03.22 - MDD / OMC / SD
label | 4f4ed41d-cb8c-59e9-8606-f95b6bac1490 |  | note | Acceptance / Conformance Criteria - Post hoe, stabilised MDD, OMC, and SD. 1 test per 2000m² or a days work whichever gives the greater number of testing.
label | 8ed938ff-2157-5aa2-ba7c-f6efdb4d2cfc |  | note | Standard / Specification - NZS 4402:1986, Test 4.1.3
label | ec991d8f-7516-5322-a5ea-fb77853e2a97 |  | note | Verifying Document - Lab Report
label | f69218dc-8c78-51c4-8c14-62b6a43378b7 |  | note | Frequency - 1 test per 2000m² or a days work whichever gives the greater number of testing.
label | 8330547e-cf6f-5e95-ae6d-e1e3125e40a5 |  | note | Activity - I
label | 8e65f206-c8d3-53c9-9d6e-4c3adf41f08d |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.03.23 - Sub-base stabilisation trial
label | 33db0125-cfac-51c2-bb13-8f2039ec729c |  | note | Acceptance / Conformance Criteria - After the sub-base stabilisation trial, prior to proceeding with further stabilisation.
label | 97852424-7570-5606-b7c8-390f1c5314de |  | note | Standard / Specification - PS - 2.2.16
label | 1b5a9b91-a178-56d2-a4d1-b6f3efed76b6 |  | note | Verifying Document - Hold Point Release
label | 09d9073d-8a0f-5d5e-afa6-7c41e1c3daed |  | note | Frequency - Min 48h Notice
label | f548d775-5ebc-56b3-bf85-04c9216f346a |  | note | Activity - HP
label | bf8a7659-4300-5770-8079-4c595911ef49 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.04 Stabilised sub-base
checkpoint-status |  |  | checkpoint | 6.04.01 - Stabilization Production Plan
label | 4bc5963e-cd2c-51c9-aca5-69592b28e7b2 |  | note | Acceptance / Conformance Criteria - Production plan sent to engineer for review 48 hours prior to stabilising commencing. This is to include all information set out in NZTA B/6 7.2.3.
label | 71cb6c20-295f-57d5-a171-0161932e085a |  | note | Standard / Specification - NZTA B/6 7.2.3
label | a63946e0-13fc-5f8f-af3f-dd8702db5ce8 |  | note | Verifying Document - Correspondence
label | 21058093-260c-502c-9a10-4289560be62c |  | note | Frequency - 48H hours prior sabilising commencing
label | e8b8790c-3ca2-5fdb-89d4-45c8244f3825 |  | note | Activity - HP
label | 3f7f445d-4e23-5bda-9bff-1d2d926e9369 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.04.02 - Longitudinal Joints
label | 22db6f42-ec9d-5643-90f1-7b79fa348ab3 |  | note | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 200 mm or half the layer thickness, whichever is the greater.
label | 719e890d-d568-55b5-84e6-bed77f0f46a3 |  | note | Standard / Specification - NZTA B/6 7.5.2
label | 78c93c41-abe6-58db-a342-afd7b48c2a61 |  | note | Verifying Document - Stabilisation Prodution Plan
label | 6c9b5431-1a5a-52bb-9e62-0e81f150c6d6 |  | note | Frequency - 48H hours prior sabilising commencing
label | f59876a0-5a1f-53f6-b4bf-cb2e0bcdacd0 |  | note | Activity - H
label | 1ced5c1f-5106-5c18-8962-145b62d99b22 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.04.03 - Stabilising Equipment
label | b8341bd7-673c-5dc2-808a-b5591245a41d |  | note | Acceptance / Conformance Criteria - The Contractor shall use stabilising plant purpose built and appropriately adjusted for the in-situ stabilisation of roading aggregates, as opposed to plant designed for soil stabilisation or re-cycling.
label | 13969d9f-b85a-5f7a-9aa8-66e1e0edae96 |  | note | • The stabiliser drum shall have a straight tooth pattern and the drum speed must be adjustable in real time during stabilisation.
label | 2deb8519-49c2-5487-9cf7-444377be1b25 |  | note | Standard / Specification - PS - 7.3.2
label | 20980237-258c-5659-ade7-2366ac0b8b3f |  | note | Verifying Document - Plant Approval
label | 5cdb0063-1c4f-5b26-af41-f8037bdb887a |  | note | Frequency - Prior to works
label | fd180c27-27ce-546e-80c4-4d43ec441f4b |  | note | Activity - H
label | 3524338e-2ce4-5f52-b118-b96a05ccca61 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.04.04 - Stabilising Supervisor
label | 840c29c2-0a8c-5ea5-ba9e-1cbbf8bf56ed |  | note | Acceptance / Conformance Criteria - During stabilisation the Contractor shall employ a suitably experienced person to continuously walk behind the stabiliser to assess the uniformity of the mixture and water distribution and to check the stabilisation depth every 100m.
label | 459a0a17-3115-50b1-8574-e577b9fa3289 |  | note | Standard / Specification - PS - 7.3.2
label | 4931d8f6-9541-5ae3-bcab-bf8298c7c272 |  | note | Verifying Document - Supervisor Approval
label | 527ee89c-1792-57ee-a5a9-287bcfcbc472 |  | note | Frequency - Prior to works
label | 5f19806f-af48-5c20-b1eb-99d26cdcd076 |  | note | Activity - H
label | ed8cc6f7-ff4c-5eed-9210-4c62bf32bba9 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.04.05 - Before Stabilisation Surface shape control, layer thickness
label | 9d8c8e5e-11ce-58a7-860d-c33d6c7859b2 |  | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
label | 616c8ede-e9b2-5437-b1f6-ce66bcd2f0e7 |  | note | • Vertical: - 25mm +5mm
label | bdb504a7-1ca9-50f7-b822-c9b3a4acf4c6 |  | note | • Cross fall: 0.5% on 2m straight edge
label | f92c3ee3-0fce-5b0f-8b35-7932831125a2 |  | note | Standard / Specification - TNZ B/2
label | 71e702c3-1afe-5980-aab7-e902f1ec27f2 |  | note | Verifying Document - String sheet
label | 69ce19e3-2200-5312-b708-210d89c586eb |  | note | Frequency - 1 test per 20m
label | 5f7c86d0-2816-5f16-b69f-5c2bed0014c7 |  | note | Activity - I
label | 16cf3505-f954-591c-92f1-db3b12cd003e |  | note | By - SV / PE
checkpoint-status |  |  | checkpoint | 6.04.06 - Average Uncompacted Layer Thickness
label | 9570be19-0fe8-57ce-bcb1-ef4816b0e78c |  | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
label | 3aa0923e-f1c9-58dc-a8ae-da58cae7c067 |  | note | Standard / Specification - TNZ B/02: 2005 - 7.3
label | 876ae953-7cdc-56d4-b12f-0969f34eb79e |  | note | Verifying Document - Survey / Level Checks
label | 7eb6d98c-375e-576e-ac51-7e0c32aeb52e |  | note | Frequency - 1 test per 20m
label | 1364f684-6351-556e-8189-03544cf0bdf0 |  | note | Activity - I
label | 15f9afb4-4f6e-561c-9b64-85ec16932a31 |  | note | By - SV / PE
checkpoint-status |  |  | checkpoint | 6.04.07 - Pre Stabilisation Compaction
label | 395eae28-4c8d-59bc-bd7b-7283b16b67bb |  | note | Acceptance / Conformance Criteria - The full thickness of the layer to be modified shall be compacted between Value ≥ 95% and Minimum Value ≥ 90% Prior to stabilisation, this will be reviewed following the stabilising trial and adjusted to suit and the updated target shall be added after the stabilising trail. DN1205-DOW-RFI-0043.01
label | 614970bc-9f95-51d2-85d7-240c03166f66 |  | note | Standard / Specification - TNZ B/02: 2005
label | 03cd9565-736a-5c41-b2bb-2c62bef5a03a |  | note | Verifying Document - IANZ NDMS
label | 7d062746-9063-552a-8600-70c701e6de9c |  | note | Frequency - Min 5 Tests per lot 1000m2 max lot size (Prior to stabilisation)
label | 819a1ad6-5e53-520b-ad5f-c702560be83c |  | note | Activity - I
label | ec31e201-c41b-5fc2-9b67-fefc9467feff |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.04.08 - Pre Stabilisation Crossfall
label | 9e8fe53f-a4f1-5780-8ccb-6c86d9016322 |  | note | Acceptance / Conformance Criteria - Before stabilisation the Contractor shall check the crossfall by string line to confirm compliance with the design.
label | 71360f74-312e-57d7-bb04-30fff5aea2e0 |  | note | Standard / Specification - PS - 7.3.2
label | de23d183-7039-5637-980c-457a089db70b |  | note | Verifying Document - Total station Topo showing levels compared to design
label | 60c78e68-7cc6-5c38-8fa6-1f1e015f1735 |  | note | Frequency - 1 test per 20m Prior to stabilisation
label | fc9d3184-55ac-5435-a416-d61089d7c36f |  | note | Activity - I
label | a514a1b0-5d8e-57ef-b0a0-53b72199740d |  | note | By - SV / PE
checkpoint-status |  |  | checkpoint | 6.04.09 - Stabilising Visual appearance
label | 5271a85c-4033-5182-87d5-e949d8805412 |  | note | Acceptance / Conformance Criteria - The stabiliser shall produce a uniform particle size distribution behind the stabiliser, both laterally, vertically and longitudinally and produce minimal break down of the coarse aggregate particles during mixing.
label | 7099c8a2-8d24-5440-a12e-deca0db77cbc |  | note | Standard / Specification - PS - 7.3.2
label | ea995418-cd6c-5018-87a7-dbda26d9543b |  | note | Verifying Document - Site Notes
label | 51ab3f3a-0703-53a4-909f-ab0246c7ba52 |  | note | Frequency - every 100m
label | bbb26c31-a3d5-5e57-9c1f-0918ac1187c8 |  | note | Activity - I
label | 26a05264-4d7b-5c54-8b74-ae3956ac22bd |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.04.10 - Cement Mat Test
label | 46c51070-6f39-5c90-b926-7f40ec685408 |  | note | Acceptance / Conformance Criteria - The stabilising agent shall be uniformly spread at the specified application rate across the pavement to Within ±0.5 kg/m2 of the specified rate
label | f4280e81-30e6-5494-bf91-f3f1fd2bf034 |  | note | Standard / Specification - TNZ B6
label | e50e070d-6787-5c4a-9684-171f12480f21 |  | note | Verifying Document - Site Notes
label | 797abd0c-2fe3-51b1-a8c0-306322b0abdb |  | note | Frequency - One per each run of cement spreading, until the Contractor can demonstrate consistency in cement spreading and/or demonstrate accuracy of on-board computer equipment calibrated/compared against weighing cement mats.
label | 6377a24c-c013-5ceb-a8f8-7b0711433e34 |  | note | • Upon successful demonstration of this, the 1 per 500m2 minimum can apply
label | 991cd70b-faf9-5183-8e93-ca3425890e1e |  | note | Activity - R
label | e201a738-c914-5bbe-ada2-7f7d94fe58ed |  | note | By - SE
checkpoint-status |  |  | checkpoint | 6.04.11 - Cement Average usage test
label | 68b97820-43ef-5f18-975e-3fc3c9960e38 |  | note | Acceptance / Conformance Criteria - Compare tonnes used (from delivery docket) with measured area Within ±2.5 % of the specified rate
label | aca9e915-5aec-53eb-bc48-4f755a7c2c21 |  | note | Standard / Specification - TNZ B6
label | e3228326-a428-5903-8a5f-45c605273519 |  | note | Verifying Document - Site Notes
label | d679f51e-32a8-5a92-bb32-fecca5ba6b2c |  | note | Frequency - Upon emptying the spreader and bulk tanker
label | d541f030-6686-527f-a67e-eb3922abd445 |  | note | Activity - R
label | 75111d96-39ac-520b-bbad-af92c278c2f1 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 6.04.12 - Maintain OMC during stabilising
label | 67a7bf6e-5925-5f91-8b98-58f13ec66fc4 |  | note | Acceptance / Conformance Criteria - The water content during compaction shall be in the range of 90% to 100% of the material’s optimum water content by NDM
label | 221c45c9-9783-5127-ae8a-4d9fdc76cb94 |  | note | Standard / Specification - TNZ B6
label | df070077-c6a5-5b64-b8fe-57ffd4c9d52e |  | note | Verifying Document - Site Notes
label | 1d3ac4db-33db-5204-be5b-4cce824f0fa7 |  | note | Frequency - Continuous
label | afc29ce6-1580-50c0-875a-7d3aab9a5e13 |  | note | Activity - R
label | 9db2b5c8-defd-582c-a4ca-837200747cbb |  | note | By - SE
checkpoint-status |  |  | checkpoint | 6.04.13 - Control of cut depth
label | 0ddfa63a-fd18-5bae-a74a-6c98f04519f3 |  | note | Acceptance / Conformance Criteria - Maximum variation from the specified depth of cut is –5 mm and +15 mm.
label | 25ee1494-9d5b-5d4d-b5a3-a40e2a8cd101 |  | note | Standard / Specification - TNZ B6
label | ca9c51c8-b702-5df5-bf81-99449144462d |  | note | Verifying Document - Site Notes
label | 37d1ce92-57b8-5546-b45e-95aa72e6d33d |  | note | Frequency - First check of cut depth should be immediately behind the stabiliser at the start of each run, then again every 200m, or as requested by the Engineer
label | 9b9978ae-2445-5c30-b771-a7c7e932bc80 |  | note | Activity - R
label | 479a411d-566d-5a03-84db-2ef8e0048266 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 6.04.14 - Mixed material testing (ITS)
label | 182a9fe4-2949-5d3e-b7d3-fa5b4add3c9e |  | note | Acceptance / Conformance Criteria - During mixing, the contractor shall take a pair of representative samples behind the mixing plant per lot or at a minimum of 2 pairs of representative samples per day.
label | a16b5584-eb92-5996-a447-640616a6119e |  | note | • These samples shall be placed in a sealed plastic bag and cured for 1 hour before compacting into a mould and testing the indirect tensile strength (ITS) of the mixed material according to NZTA T/19
label | 794886b0-a9e7-5160-9efb-77c08cfa7659 |  | note | Standard / Specification - TNZ B6 7.5
label | d8b792e0-ef84-513a-be03-c931ca889de2 |  | note | Verifying Document - Test Results
label | aa8aa106-429b-510b-8ded-44d4974a6b19 |  | note | Frequency - 2 pairs of representative samples per day
label | 2cce68a2-8e49-577d-8452-1338d837f301 |  | note | Activity - R
label | d9dd5959-3630-54c0-be19-04a149b58bc7 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.04.15 - Particle size distribution behind stabilizer (Wet Sieve)
label | 1595fc51-d5fc-5df3-a8b1-0773e76f8c91 |  | note | Acceptance / Conformance Criteria - A Wet sieve analysis will be completed within 4 hours after stabilizing, and consist of a minimum of 3 sample bags per lot.
label | e177ed60-e00e-51b1-895a-acc923dfc0f0 |  | note | Standard / Specification - TNZ B6 7.5
label | b07b0c57-20d3-5c59-9388-46d75e9923ed |  | note | Verifying Document - Test Results
label | 0c70ede9-d3ba-5994-b6d1-9957929423c4 |  | note | Frequency - 3 sample bags per lot.
label | 574bf161-e84e-5d84-ae04-3162922faf6f |  | note | Activity - R
label | f1ad340c-ef06-5def-a22c-94cd6377d488 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.04.16 - Plateau Density Test
label | 68a2ad58-5808-5d0c-819d-28b10696645c |  | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site.
label | 6d0085de-57cf-557c-91b6-4672f368d027 |  | note | • Testing shall be at OWC.
label | d22a0b2c-00d9-5356-b5e9-2c972d6ecf9f |  | note | • First plateau test to be completed at the start of compaction, and highest out of plateau and lab MDD shall be used for compaction testing.
label | 7bea7d1c-f70f-56a2-8442-27215f842acc |  | note | Standard / Specification - PS - Table 7.2 - 2.3
label | 068b6962-d280-59ef-82e1-3d35849927d3 |  | note | Verifying Document - Plateau Density Report
label | 6adfe101-3863-5448-b479-fed6fb6eecfd |  | note | Frequency - 5 tests per 10,000m2
label | 6077f9fc-e466-501e-83cb-2e4a91af231b |  | note | Activity - I
label | 87cbce07-02e0-52d7-a53f-d13045dca5c8 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.04.17 - Post Stabilisation Compaction Using Highest MDD from Lab or Plateau Testing
label | b1a1c4c4-a226-5240-9436-4b643503254b |  | note | Acceptance / Conformance Criteria - The sub-base compaction requirements in Table 2 of B/6 shall be replaced with a Mean Value ≥ 98% and Minimum Value ≥ 95%. - Direct transmission
label | 227b8354-585b-5405-b88c-7c7fcdcfeec4 |  | note | Standard / Specification - PS - 7.3.2
label | f36eb166-000e-58bf-be19-f92bb30d703b |  | note | Verifying Document - IANZ NDMS
label | cd6f29e3-2a32-5b63-ab04-d66b4b185db8 |  | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
label | d9507bce-a48c-50aa-ab82-c8811ad35072 |  | note | Activity - I
label | 58b68c5a-e4b7-5f89-a3b2-685edfa044cd |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.04.18 - NDM Water correction
label | f071d565-d785-572a-922d-f08a064dbc0b |  | note | Acceptance / Conformance Criteria - Daily Laboratory water content tests shall be carried out on samples taken and used to correct the NDM measured dry density
label | 2e044633-d7c7-5d9e-b5dd-dafff9d7c0bd |  | note | Standard / Specification - NZS 4407
label | 836d50b3-7c26-50b4-baaf-bbe5282e1ec4 |  | note | Verifying Document - Corrected NDM Results
label | c8f85b5b-bbd3-5b8c-ab68-033d78da6733 |  | note | Frequency - Per Stabilise day
label | 7e936f2b-4eb0-5b41-ab57-92180a1d77ef |  | note | Activity - R
label | 83e332d0-a668-5154-84ac-e7fbc301bf14 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.04.19 - Post Stabilisation Surface shape control, layer thickness
label | 9526862f-91c5-5dac-95ad-70cd020f619e |  | note | Acceptance / Conformance Criteria - Width: -20mm +100mm (Unconstrained)
label | 6522fc0e-4196-5f03-afbd-9b75927f8d6d |  | note | • Vertical: - 5mm +10mm
label | f4863cc8-486b-5be9-a731-8bfa42984a1e |  | note | • Cross fall: 0.5% on 2m straight edge
label | 6954ac89-9caf-5018-b91d-b28e25c03733 |  | note | Standard / Specification - TNZ B6 8.2
label | 3daf20d1-728d-5007-97c3-0bb9105461f6 |  | note | Verifying Document - Total station Topo showing levels compared to design
label | d07c63a7-48c1-5be3-b5cc-1adac4534f34 |  | note | Frequency - Continuous
label | 98fcf74d-8e60-596d-8907-88b9d7ef90f9 |  | note | Activity - R
label | bc888039-e7fd-5dc3-aee8-ae317a7d7b11 |  | note | By - SV / PE
checkpoint-status |  |  | checkpoint | 6.04.20 - Protection, Curing and Maintenance before Overlaying
label | e92392ec-97c2-50e1-821a-33d79ed2472f |  | note | Acceptance / Conformance Criteria - The Contractor shall protect, maintain and cure the completed cement bound sub-base until the next layer is applied.
label | c8bc45de-bc79-5b30-864f-5bf260d7c2d1 |  | note | • Besides construction traffic required for the above curing no other construction traffic shall be permitted onto the layer within 7 days of stabilisation
label | e0059b71-6b51-5fd4-8250-d3218d19768e |  | note | Standard / Specification - TNZ B6 - 7.8
label | c2673520-0068-526c-b733-bd1c5e249159 |  | note | Verifying Document - Site Notes with photos
label | c4df2b91-2813-55d7-a6f8-582b3ae81f62 |  | note | Frequency - For 7 days after stabilisation
label | 5b871b77-b3c3-5fbe-b180-46fc780076ee |  | note | Activity - R
label | 565020ac-19d7-5868-a1ba-35b0f8e9edd9 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.04.21 - Benkelman Beam
label | 70de7fe9-6b26-586f-899f-398eec09a3f7 |  | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer.
label | e954676f-2098-54d1-ab59-fe6251457716 |  | note | • Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
label | 68252c7e-3e47-53cf-bf1d-ef2c070c1ef6 |  | note | Standard / Specification - PS - 7.3.2
label | 81139e68-a273-5646-81ae-6695ea090e1f |  | note | Verifying Document - Benkelman Beam Report
label | 053563ae-5872-575a-8948-c0b3e4514eb3 |  | note | Frequency - Every 10m of each lane – staggered between left and right wheel path.
label | bdccd325-dd78-5064-9cc2-edf57d634663 |  | note | Activity - HP
label | 93770925-a868-5d26-a5e0-1f1fd3e3eb92 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.04.22 - MDD / OMC / SD
label | 2630dcc7-1a5c-52aa-a82f-67d5bf7350e1 |  | note | Acceptance / Conformance Criteria - Post hoe, stabilised MDD, OMC, and SD. 1 test per 2000m² or a days work whichever gives the greater number of testing.
label | 173d78d7-805d-513b-b61d-766211856e8c |  | note | Standard / Specification - NZS 4402:1986, Test 4.1.3
label | 290efdc4-fa23-54c6-85e0-bab5dc5134d8 |  | note | Verifying Document - Lab Report
label | 44cbef68-a14f-5753-a329-5e07e7fc9006 |  | note | Frequency - 1 test per 2000m² or a days work whichever gives the greater number of testing.
label | b0f23bc1-17a6-5c33-b386-f2fee8d0dfe5 |  | note | Activity - I
label | fbe34ad3-62fb-5820-bbff-e6bdea491916 |  | note | By - PE
checkpoint-group |  |  | section | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
checkpoint-status |  |  | checkpoint | 7.02.01 - Redline Drawings
label | e9831178-47b0-59a6-9d3e-db8fe82d67ba |  | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen mark up showing lot numbers and areas stabilised in different days including clear delineation of all joins.
label | 42ae6479-0812-5f6c-9c07-a74a778776a8 |  | note | Standard / Specification - Downer
label | 46a567d6-e788-5ef8-9b53-7728cb226c3d |  | note | Verifying Document - Redlines
label | 52a691ee-b7b7-55cf-b940-d4a415e252dd |  | note | Frequency - Post construction
label | e23418a8-3819-5731-b4b1-40b53b1be0dc |  | note | Activity - H
label | c5e2fca2-dd50-5ce1-b220-2d2b1f521bff |  | note | By - PE
checklist-sectioned |  |  | checklist | ITP - Subsoil Drainage - Rev B | itp |  |  |  | Yes | ITP - Subsoil Drainage - Rev B | 1147af78-4cf8-4527-ab44-ec7519302617
checkpoint-group |  |  | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint-status |  |  | checkpoint | 3.01.01 - Construction Pack
label | e3e4320b-0ae2-5934-8f86-f48691f90a6d |  | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
label | a5cff262-b410-5ef3-a4ed-c68ff3ccedfc |  | note | Standard / Specification - Downer
label | ed9bd141-5b48-5aad-97ce-36073ad871fe |  | note | Verifying Document - Construction Pack
label | f85a1e6e-b3ee-5bb9-8cc8-e9cfe23826e0 |  | note | Frequency - Submit 10 days prior to commencement of works
label | d94ea74e-8904-5764-8156-a617a6ac5fc7 |  | note | Activity - H
label | bc1e6f46-f6c8-598f-ba1d-340b08b6912e |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.02 - Survey Setout
label | 66f5e34e-d324-54c8-8b73-6557f7a98a92 |  | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | fcead67b-af71-5ce8-8593-1f4cf7fe5175 |  | note | Standard / Specification - Downer
label | 6b14f005-ad29-5551-90c6-e9748d55704d |  | note | Verifying Document - Survey Records
label | 2922226c-8e5b-5dd5-b869-a226857e8214 |  | note | Frequency - Prior to Works
label | fb6b461f-dfa6-5b91-9443-7737b0ef96a5 |  | note | Activity - H
label | f1cd4e61-b516-5014-a260-98792eea5814 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 3.01.03 - Approved Construction Drawings
label | fde2da03-ff8d-5b00-a0b9-84eaa06a0153 |  | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | 0752b5eb-71af-54dc-bb93-4cf9c204bd79 |  | note | Standard / Specification - Downer
label | dffe62dd-1ef0-51e7-aac4-0fabcb726105 |  | note | Verifying Document - IFC Drawings
label | 9c70aef2-39e1-51c0-814f-d725d260b35d |  | note | Frequency - Prior to works start
label | 9d1a3400-5b43-5b12-9930-7ff952aa762c |  | note | Activity - H
label | 6da2d4f1-345b-5e86-bc5b-84d2012936f5 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.04 - Topographic surveys for measurement
label | 247ba338-8e35-5709-9cab-dadbbba10a43 |  | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
label | 4dbb98dd-29b1-52dd-9a5c-8a652de07099 |  | note | Standard / Specification - PS 2.2.12
label | 3ae9b607-c597-5bfb-9af8-f8c5783c9711 |  | note | Verifying Document - As-built
label | c2a3b149-b534-56d2-a2aa-fcccf7b87d6f |  | note | Frequency - Prior to works and Post Works
label | 55219e30-e8ae-52f1-bb10-3d6fc1d24903 |  | note | Activity - H
label | 849ec13f-9f1a-5628-8a2a-f193408133a4 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.05 - Permits
label | 6ce3adac-36c3-5bce-b254-8cfcea71578f |  | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
label | e69af894-0cdf-50fd-b743-4abf087bfb2d |  | note | Standard / Specification - ITP Register
label | 9294d374-5eea-5067-9d6c-a8f6fa839752 |  | note | Verifying Document - ITP Sign Off
label | 89e12c86-d074-50e1-8928-59e72a1a5c3f |  | note | Frequency - Prior to commencement of construction activity
label | 32991eac-0b64-550a-ab84-ebf1587c4b7b |  | note | Activity - R
label | c206fb6c-57e6-55e5-8e8f-d54261253461 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.06 - Stakeholder Management
label | 20f0f9cb-1274-5fb3-8d3f-e17434c67467 |  | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works, Agree plans for maintaining access to properties during construction with landowners
label | 4cf723b9-eb44-5949-8b79-80925a2b783d |  | note | Standard / Specification - Project Stakeholder Management Plan
label | 9f36a72e-254c-5020-a432-7a482ca704be |  | note | Verifying Document - ITP Sign Off
label | 0198f785-e291-5042-ba9d-db23179da972 |  | note | Frequency - Prior to Construction with continue updates throughout the works
label | 968643e6-cfa8-5234-be55-6b7dda886fda |  | note | Activity - R
label | 01ed8ab7-4614-553d-a7cb-9e105236fd40 |  | note | By - SE
checkpoint-group |  |  | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint-status |  |  | checkpoint | 4.01.01 - Subsoil Pipes
label | 37447c21-d9bd-500c-aa31-0993a799cb1c |  | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 160mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
label | 2dad1c15-6feb-55ce-abf9-6797ac003351 |  | note | Standard / Specification - GWS 3.2.1
label | dceab4c2-2c90-57bf-8251-d7850b54fd8e |  | note | Verifying Document - Datasheet
label | 0f33bfda-b27d-591d-ae27-6d5df859df2c |  | note | Frequency - Prior to installation
label | 5d5cc8ae-9729-5ed8-b644-c4f5f81cb84c |  | note | Activity - C
label | 95ca03e1-3a8f-54d1-8c87-a4e56696c92c |  | note | By - SE
checkpoint-status |  |  | checkpoint | 4.01.02 - Subsoil Drainage Aggregate
label | 08f26c5a-ddb7-5f41-aebf-e033745f7d70 |  | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate)
label | 46bc154b-8396-506c-a819-88adb2206f91 |  | note | Standard / Specification - GWS 3.2.2 & 3.4
label | 5b88fb0c-66a1-5e49-a8d5-cdf52ccf2b07 |  | note | Verifying Document - PSD, CR
label | e2794ec9-d4ea-5a33-b94d-af86ab431f4e |  | note | Frequency - Prior to installation
label | f52c5012-1778-5580-b1ac-b7a9546f876f |  | note | Activity - C
label | b115e0dd-3911-5ce4-a236-f8e0c0966a0c |  | note | By - SE
checkpoint-status |  |  | checkpoint | 4.01.03 - Filter Cloth
label | 922f59cc-c9ee-5af3-846d-3832e8976376 |  | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
label | 754bd53c-6759-508d-9c9f-42b977e4a2d9 |  | note | Standard / Specification - GWS 3.2.3
label | e740d2e6-4fd6-5b6e-903e-921217257ade |  | note | Verifying Document - Datasheet
label | 630075fd-f369-5692-bfda-bdfbf36ddb1a |  | note | Frequency - Every 1,000m3. At least two weeks prior to works.
label | 49e776b5-1c83-5b94-a552-ee1609d1a684 |  | note | Activity - C
label | 6dff5458-8576-5ab5-a9ae-2cd0058980d6 |  | note | By - SE
checkpoint-group |  |  | section | SECTION 5 – CONSTRUCTION ACTIVITY
checkpoint-status |  |  | checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
label | a7f90523-9f49-5e26-ab91-47fa5191045a |  | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain.
label | 5c00adcd-b649-524d-893b-30f87ba37b4f |  | note | Standard / Specification - GWS 3.2.2
label | 14873811-9be7-5dd0-a934-8fc540eaca5e |  | note | Verifying Document - Site Record
label | 91c15215-cc28-5f2e-90d9-af4254081fd5 |  | note | Frequency - prior to backfilling
label | 70b304fc-caab-5b41-aa65-ba20611aef2c |  | note | Activity - HP
label | 258d4f9b-854f-5091-8ede-a89602b5f9eb |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.02 - Trench Backfill
label | 66ad9e85-7ae4-5d97-bde4-fd6893820dde |  | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through
label | 8ae9bdfe-7318-5d5c-acd2-e4f904e06bd3 |  | note | Standard / Specification - GWS 3.3
label | 268d3ca8-6fa2-5c5a-aa75-5773709bba2c |  | note | Verifying Document - Site Record
label | feb75e03-0258-585e-a689-11cbdf8e701f |  | note | Frequency - Each trench
label | de040a19-fbe0-566c-acf3-e60467c03c18 |  | note | Activity - I
label | 55ab3706-dfae-54c7-b76d-3052fcb93c10 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
label | 344525eb-1d74-5815-a443-95266cb8a6a2 |  | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete.
label | 545c0bc8-2804-5fa2-9d40-968af904fbd1 |  | note | Standard / Specification - GWS 3.6
label | d84dca0a-bd73-5dfd-a8ae-1c5fa6f17cb7 |  | note | Verifying Document - Site Records
label | 8a03718e-b66f-56de-8367-759667fee5ce |  | note | Frequency - Each Subsoil Line
label | 53639ece-8919-5cae-b3d2-853054daaddb |  | note | Activity - I
label | dc89290d-cdb7-5804-8bc6-c147bef29a5b |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.04 - Subsoil Flushing
label | 4d1389a4-8de2-59a9-b825-54b9750ee56a |  | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
label | b3a0eaa6-caf8-59c8-a10d-74f5d1a1950b |  | note | Standard / Specification - GWS 3.6
label | 584ba4fd-01d5-5f82-9b0c-a9d438b3ce71 |  | note | Verifying Document - Site Records
label | 7256c455-ef41-567d-828b-7342b5c18c49 |  | note | Frequency - On completion of earthworks
label | c55063df-be7e-5b70-8482-b2b112768188 |  | note | Activity - HP
label | 77c543ea-72b4-55d3-845a-47fb7b5fc0ea |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.05 - Survey
label | db1a13ff-dba0-5145-8e56-f359fb847c48 |  | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | 78e8a5ad-c326-5d9a-b4c0-9541320123f3 |  | note | Standard / Specification - Downer
label | d4cfc897-ac31-5109-8f62-93afcbd35528 |  | note | Verifying Document - Records
label | d218082c-7b29-5f91-b6c0-b03dc6b27398 |  | note | Frequency - Post construction
label | c7830048-5534-5a01-bb5e-179b0df836fb |  | note | Activity - H
label | 15844533-95cb-5a12-93d4-001d05753d55 |  | note | By - SV
checkpoint-group |  |  | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint-status |  |  | checkpoint | 6.01.01 - Construction Record Compilation
label | ee1978d8-0e6d-5526-b6a7-946047814c4c |  | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | 67362158-2834-5d84-ade0-ae6f1b6d0ec8 |  | note | Standard / Specification - Downer
label | a24007a3-c872-524f-b455-163c07c8e5c8 |  | note | Verifying Document - Records
label | 5a7e31a5-0820-545c-b971-e36ddbf1729c |  | note | Frequency - Post construction
label | 77a7e5f8-02ef-530a-91af-e607f05c7651 |  | note | Activity - H
label | e5d35e8d-f86b-5af7-ba05-d945435e2114 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 6.01.02 - Survey Records
label | a0ac0cc4-631a-5133-b6fd-245b319aa958 |  | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
label | 180a867c-7a92-5f9f-a0fd-91b82f256260 |  | note | Standard / Specification - Downer
label | f7904889-fdb4-5a7c-a63b-71ef8b5cc375 |  | note | Verifying Document - Records
label | ee7885ad-839a-50d2-8da3-d7324de5c9b0 |  | note | Frequency - Post construction
label | 8e415304-8692-5b9c-ae6f-9fdacca84ec7 |  | note | Activity - H
label | 01269d07-f711-5592-bd77-e4c52e9edc87 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 6.01.03 - Redline Drawings
label | 550c52a2-03c4-52ad-89da-69f702697ea6 |  | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | bbd2f293-3849-57a7-b0f4-a1cb5997d079 |  | note | Standard / Specification - Downer
label | c46c584a-56df-561d-b43a-c0c3fe670d6b |  | note | Verifying Document - Redlines
label | 7c2c55cb-1dba-50a9-b56b-7f21c8f7e44b |  | note | Frequency - Post construction
label | e60bc891-dbaf-5d0d-a7dc-20912d3afc1a |  | note | Activity - H
label | 6749ce7f-a61b-584d-ac29-3573b9e1fca6 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.01.04 - Defect, Snag and Punch List
label | b67c12f0-4350-5fa1-844b-97db4ad2689b |  | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | e13536f3-0c26-5388-ac21-72bb33e681f9 |  | note | Standard / Specification - Downer
label | 4bda5a0e-18b6-5cb1-9464-06e06fddf0e8 |  | note | Verifying Document - Register
label | 22da4f4a-2e8d-52e6-8d1e-86cec3f847bd |  | note | Frequency - Post construction
label | 9445d37f-44a8-5181-a21a-9092a2fe6a28 |  | note | Activity - H
label | 4ff92d37-6aeb-5c70-af9d-64d16a45ff29 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.01.05 - Photos
label | a95c32cc-8cc6-5355-b4f2-5e1bb87ec90e |  | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
label | 0a4eb8cb-ee4d-505e-a512-5b983f330bba |  | note | Standard / Specification - Downer
label | f1452100-2a8d-508d-b79d-8fde17341213 |  | note | Verifying Document - Photo Records
label | c69c16fa-03e6-5513-9158-4e8e0523f491 |  | note | Frequency - Post construction
label | ebc7cd71-fbb0-547b-8b4a-7904c436de14 |  | note | Activity - H
label | c5e2515f-f88b-5bcc-b12a-51916f38e97e |  | note | By - SE
checklist-sectioned |  |  | checklist | ITP - Retaining Walls |  |  |  |  | Yes | ITP - Retaining Walls - Rev C | 160ff124-05ca-4c84-bec2-5dd2af07e02a
checkpoint-group |  |  | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint-status |  |  | checkpoint | 3.01.01 - Construction Pack
label | dfb723bb-584a-5713-be6d-07b0f19feadc |  | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
label | e2830cdf-362b-5f0e-8d22-f68f1a98219d |  | note | Standard / Specification - Downer
label | 14282032-c33f-55dc-9ae6-ba093f01c0fa |  | note | Verifying Document - Construction Pack
label | 9e7ee91d-d82a-5694-af12-0f67083b3c87 |  | note | Frequency - Submit 10 days prior to commencement of works
label | 2a4ab9d4-071d-53fa-ac91-77f26febe2a2 |  | note | Activity - HP
label | d5d6a8c7-50e2-54b9-96ba-d6ed63ed046c |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.01.02 - Survey Setout
label | dc572b14-0ed6-54c7-bc8f-85ed00c03dfe |  | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | 3e946a9d-b5c8-50e7-96e0-0400e8f6e89c |  | note | Standard / Specification - Downer
label | 34bb53e5-aed2-52e3-a5c2-9f81d0a823ca |  | note | Verifying Document - Survey Records
label | 61d76f5d-0ad9-583f-ac76-86ad184fa739 |  | note | Frequency - Prior to Works
label | 376f33df-3b2b-5b0c-ab68-eb1a544a497d |  | note | Activity - H
label | c900da17-59f9-5691-b9d1-3bcd5996d491 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 3.01.03 - Service Location
label | b9f21eeb-7675-5741-9a79-4af249ac51cd |  | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | 434102cd-5777-54cc-b4b5-32744d498024 |  | note | Standard / Specification - Downer
label | 07a728fa-eece-56e9-af95-f512783809d3 |  | note | Verifying Document - Excavation Permit
label | 077eeafa-3bad-5034-9687-5e46d0d70d1b |  | note | Frequency - Prior to Excavation
label | f621f899-2387-5113-900d-6bf9fc014ca0 |  | note | Activity - H
label | 765fd8e2-b34a-5911-8b80-bd9e215f5033 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.04 - Internal Permits
label | b356337b-ff8b-5218-b916-0250a1283683 |  | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | a1b106e9-f9c2-5c82-9b78-bc7a5e36b3d8 |  | note | Standard / Specification - Downer
label | 62309b3c-27a8-5c74-8629-890633f13944 |  | note | Verifying Document - Internal Permits
label | 83e97ed8-8c87-565f-9e65-f307d506c6a2 |  | note | Frequency - Prior to Excavation
label | d9a60eb7-5a01-5a8f-8f3f-6ce4ccaaa502 |  | note | Activity - H
label | 3d563ef1-3b79-577d-b94f-308e34e1ca4e |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.05 - External Permits
label | b3b0e978-a810-584e-aa53-c42ce3c97641 |  | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | da4f0b71-5efa-5c01-ad1a-988c4ed5ce74 |  | note | Standard / Specification - Downer
label | 9637f9ab-b7c6-54c8-8436-24c62804f0c4 |  | note | Verifying Document - External Permits
label | 86a70157-a919-5dd5-aa32-c8681501a34c |  | note | Frequency - Prior to Excavation
label | bdcdc434-1b5d-5073-8411-b8512f1171ba |  | note | Activity - H
label | 9a96dd8f-f51a-5d85-90aa-2277fca1a9b8 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.06 - Approved Construction Drawings
label | 9ff0acba-9273-52f4-a0a4-2ab6d34c8a37 |  | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | 35f67329-e2c7-5487-a6d4-58b982b7c249 |  | note | Standard / Specification - Downer
label | 3dfe5430-9c4a-5998-aade-3c0355af63af |  | note | Verifying Document - IFC Drawings
label | 2b7e4a6a-c00a-5a00-ac72-61e46e5f805a |  | note | Frequency - Prior to works start
label | 64beb55c-164d-586e-993a-71bf994ecd03 |  | note | Activity - H
label | 16b491c1-6520-5184-a1cd-e89a84b6dddc |  | note | By - PE
checkpoint-group |  |  | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS
checkpoint-status |  |  | checkpoint | 4.01.01 - Stone Strong Block Molds
label | 24a4862f-20e9-5858-9e47-682e8ebdcd0f |  | note | Acceptance / Conformance Criteria - Stonestrong blocks to be supplied by an approved supplier. The Contractor shall liaise with the Principal-appointed Cultural Artist to coordinate carving of the supplied blanks and the production of moulds & blocks
label | b7e1ac9b-4fd0-5aed-91f1-207545543544 |  | note | Standard / Specification - PS - 12
label | 4fbb56e2-610f-5ab3-b571-8d5a95c19942 |  | note | Verifying Document - Conforming Molds Post Carving
label | 4ea6de2e-aec5-50b2-a438-bd4bd870e686 |  | note | Frequency - Before Installation
label | d4a2256c-c353-57e5-9fce-3979c4f41a52 |  | note | Activity - H
label | 1c7d0313-833b-5b02-8452-76e926b94d30 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.01.02 - MSE retaining wall backfill Material
label | cc3d6c38-7cdf-5ccc-b3de-82e5fa7d81b3 |  | note | Acceptance / Conformance Criteria - Backfill is to comprise a well graded, granular material such as GAP65 or site won Hinuera Sand, which must be free of any deleterious material. Sand backfill shall have a fines content (less than 0.075mm diameter) of no more than 10%. Labratory MDD (x2 per material type) at standard compaction
label | 22721888-49d4-5ebd-a823-b786fde9c2dd |  | note | Standard / Specification - GWS - 5.3.3
label | f760ee7e-3e30-5748-ac8d-dd6f4cff2189 |  | note | Verifying Document - Lab Results
label | ac1f5c71-71b7-5418-a6b3-d83649055b3c |  | note | Frequency - Prior to works
label | 951e9d5f-bd61-5982-b242-bf9f0c0caffb |  | note | Activity - H
label | 8ebf4f1b-07e1-53f7-b331-bcd4af254b27 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.01.03 - Geogrid
label | a5ac5972-5125-5559-af6d-1c6c4e7dedcc |  | note | Acceptance / Conformance Criteria - Geogrid to be Miragrid GX200/30 or similar approved
label | 9f8013ff-90e1-57c2-9d72-3a9dffbf0e78 |  | note | Standard / Specification - GWS - 5.3.1
label | 0a7a8e2c-6643-54d0-a7a9-d2756a3ae4b4 |  | note | Verifying Document - Datasheet
label | 8616060a-d369-50b8-aaba-ef3009718c94 |  | note | Frequency - Before Installation
label | a58b35f4-bec7-526e-a186-cb8cfac7ff0c |  | note | Activity - H
label | 96867ef7-72bf-5c39-9276-a8fa57a392dc |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.01.04 - Para web
label | 1caebfdf-02c1-5487-a1c2-99494d3a7d32 |  | note | Acceptance / Conformance Criteria - Paraweb to be the correct grade: Paraweb 2D-50
label | fc6b5ecc-9ae5-5429-b362-4e4e740b858a |  | note | Standard / Specification - GWS - 5.3.2
label | c6a61179-13b0-5cce-86df-0b2aee73ba18 |  | note | Verifying Document - Datasheet
label | d6d44771-ac67-536d-add9-852624175da7 |  | note | Frequency - Before Installation
label | 9d9aac6a-b187-50c7-bcbc-e7f671b406f3 |  | note | Activity - H
label | 55508e0c-9e1b-52b3-a5d1-64da039c0ec6 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.01.05 - Drainage Pipes
label | 7a5b659a-8903-53d2-923a-b6d92a4b1645 |  | note | Acceptance / Conformance Criteria - Shall be 110mm diameter NZTA F/2 compliant smooth bore perforated corrugated pipe with filter sock
label | 7794d7ea-668a-5c32-bb0f-3680b36f6de3 |  | note | Standard / Specification - GWS - 5.3.4
label | ea8e0216-d0f1-54d5-92d8-9b9fa06b7076 |  | note | Verifying Document - Datasheet
label | d56eee96-b50c-5a01-acdc-8056d052ceaa |  | note | Frequency - Before Installation
label | 395116fd-81ab-5fbc-8151-6255ffeb4a71 |  | note | Activity - H
label | 8fb5b411-f437-5583-8180-b42cdf2a2a99 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.01.06 - Geocomposite drainage board
label | cd6be02c-c749-5f25-acc3-4ffb2cefa944 |  | note | Acceptance / Conformance Criteria - Shall be Cirtex Armour flow, or similar accepted by the Engineer
label | ebf65b67-521d-5975-ac96-0b04a5a626cd |  | note | Standard / Specification - PS - 12
label | 1de52d81-e41e-553d-9c21-f0f6340ab64c |  | note | Verifying Document - Datasheet
label | 0987a3f2-09ee-5a15-a403-5dac4b2b4eb3 |  | note | Frequency - Before Installation
label | f2e98e9e-bba5-51b9-b10c-728c27a797b5 |  | note | Activity - H
label | 29b83dfe-e46e-5abc-a914-d0df434d4e6f |  | note | By - PE
checkpoint-group |  |  | section | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS
checkpoint-status |  |  | checkpoint | 5.01.01 - Excavation to subgrade
label | a44eca19-0903-53b8-b909-f430fbf6b9bf |  | note | Acceptance / Conformance Criteria - The foundation materials are to comprise natural Hinuera sand material, stiff Hinuera Silt or imported clean sand and must achieve a minimum of 4 blows per 100mm when tested with a Scala penetrometer. Any exposed silts must have vane shear strengths greater than 70kPa.
label | 5722bcfc-454b-577a-9ad1-d3e3205134b4 |  | note | Standard / Specification - GWS - 5.2
label | 915e6908-c8fe-5ac1-9db4-a947962d0041 |  | note | Verifying Document - Scala Results
label | a490c5fe-167a-5b44-ab44-b30841d751aa |  | note | Frequency - Every 10m
label | 6289dc62-ab20-571f-9d3e-14f5140d96a5 |  | note | Activity - H
label | b7a8ce23-7996-5bcd-af78-3797ae943025 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.02 - Foundation Approval
label | 88bbf40b-3a7e-5106-a1eb-b04cac8b3276 |  | note | Acceptance / Conformance Criteria - Results of the foundation material testing shall be supplied to the Engineer for approval and the prepared ground shall be inspected by the Engineer. Construction may not proceed until receiving Engineer’s approval.
label | 87cf84f3-b265-54c8-91f4-8fe99cf580ac |  | note | Standard / Specification - GWS - 5.2
label | 1686d54b-8287-51df-86cf-43bc7127c4b6 |  | note | Verifying Document - Approval
label | 92f82e7a-8f29-5590-9360-08dca36f2305 |  | note | Frequency - Prior to proceeding. Min 48h notice to Engineer
label | 75d2a1b0-4525-5583-9519-6b0bab956b25 |  | note | Activity - HP
label | 13ca0be8-8086-5cfa-835c-649526f18337 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.03 - Undercut subgrade
label | 3a1426c3-4a4b-50d6-8c92-de9a0f129814 |  | note | Acceptance / Conformance Criteria - Any unsuitable materials, such as uncontrolled fill, contaminated materials or any weak or organic materials, shall be undercut and replaced with compacted granular fill (WHAP65 or equivalent) or Hinuera Sand. Surveyor to capture extent of undercut (if any) to include in asbuilt.
label | a162c6e4-10cd-5f4e-aee1-19aebcb4c8b1 |  | note | Standard / Specification - GWS - 5.2
label | f1f6c15f-6596-5cfe-9cd1-5734db4e100b |  | note | Verifying Document - Survey Record/ Photo record
label | 37cd6678-71f7-5b8a-aaae-7266b0c53b90 |  | note | Frequency - If required
label | 09fca302-cdb5-5d57-a109-7acf55153583 |  | note | Activity - I
label | 839acd88-9afc-5d25-87e1-5dc15047bc55 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.04 - Undercut backfill compaction
label | 686827fe-56ed-5bab-9d64-495ebf6340bf |  | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
label | e5515d9a-8cc8-5f73-9ca8-e055c4cc041f |  | note | Standard / Specification - GWS - Table 3
label | 08c502fa-14b9-5b61-b1a0-0533d2b91f20 |  | note | Verifying Document - NDM Results
label | 49be031b-95ea-5b55-97e3-3536950c4134 |  | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
label | 14a27680-1a25-52b8-bd00-1fab40f44075 |  | note | Activity - H
label | c95dd2e2-6397-5c53-ba34-465a08f15a20 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.05 - Geogrid Installation
label | 7c06f150-6a83-5a7f-bf9e-26add933060a |  | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets. Engineer to inspect 1 layer prior to backfill.
label | 8150c2df-f463-5e1e-9900-9baeb8241b95 |  | note | Standard / Specification - GWS - 4.1
label | 502aec9f-4e98-5c7b-ade9-d8d49f08c81f |  | note | Verifying Document - Photo record
label | 956b32f9-ff13-55e8-a916-4c3f79f7faac |  | note | Frequency - Each layer - 1 layer per abutment to be inspected
label | 1f4aba03-43ec-52d8-9410-bef8fd128ad6 |  | note | Activity - HP
label | 2ce0bc49-bf59-54a7-a221-56df0205defd |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.06 - Backfill Installation
label | c7c2d1b0-c2f8-5768-8d67-067103ab63da |  | note | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts and compacted to the following standards.
label | 523bffe5-aaee-5a9b-8e89-14e05f013cba |  | note | Standard / Specification - GWS - 5.3.3
label | 11658044-8281-56e6-9f67-20faad0299fb |  | note | Verifying Document - Photo record
label | ac859c0c-278d-5b8e-a292-46ad56fb0962 |  | note | Frequency - Each layer
label | ef9db130-4c9f-5391-867a-972b372090fa |  | note | Activity - I
label | a3687b6e-7c6b-53f0-b274-e31e41cd696f |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 5.01.07 - Backfill Compaction (NDM) (Gap 65)
label | f8d240d7-018f-5b3f-8c5e-fe7537ae63e0 |  | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
label | ad7fa407-e378-5634-ab93-1828e1f82e34 |  | note | Standard / Specification - GWS - Table 3
label | 84067f73-90f3-5c9f-bcc9-3412062ae46f |  | note | Verifying Document - NDM Results
label | 215fd151-1567-5313-ab16-40cc8c973c76 |  | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
label | b1904192-86c4-5dc0-983d-0c4625692197 |  | note | Activity - H
label | 1759d2ab-8aaf-5e44-8271-0bca9708cfa4 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.08 - Clegg/Proofroll (Gap 65)
label | 98614c55-f750-506f-9503-10c3e30e1881 |  | note | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test. Engineer to proofroll/inspect final layer of load transfer platform.
label | 2f9fe1ac-2fbc-57be-ac76-85de65fe652e |  | note | Standard / Specification - GWS - Table 3
label | 4e604154-4a81-55e9-b377-2b88c923b018 |  | note | Verifying Document - Clegg Result sheet
label | bd438c47-31e5-566a-944c-a5b5c76088c7 |  | note | Frequency - Each layer - final layer to be inspected
label | 774d86f1-ba7c-50b6-94d6-30bf5a948c3f |  | note | Activity - HP
label | 7364a921-2ff7-5c35-9159-3054bb9afa4c |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.09 - Scala Penetrometer (Hinuera Sand)
label | 0de6b358-0f29-58af-ad62-e6befe37e01e |  | note | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
label | 723574f2-3e35-56ba-972d-31c4f942de55 |  | note | Standard / Specification - GWS - Table 3
label | 950d9fe5-4c1e-50e8-b794-ead1b2cf7d81 |  | note | Verifying Document - Scala Results
label | 1f645c31-308b-548f-8dde-196580b6b892 |  | note | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
label | 6720fe90-9a00-56ad-8968-01ae35b290ac |  | note | Activity - H
label | 714be469-f8be-5424-9050-e3ecf0a94400 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.02.01 - Level founding platform
label | 9c8eb987-df2c-50a7-95ae-edac73b9c3d4 |  | note | Acceptance / Conformance Criteria - The Contractor shall construct a 200 mm thick levelling pad on top of the load transfer platform to create a level founding platform to accept the MSE retaining wall.
label | ca1e2ed9-2c2b-5b18-a741-e994b2b723df |  | note | Standard / Specification - PS - 12
label | 43ce2579-fec0-5318-87c6-4a8e9b3a20bb |  | note | Verifying Document - Site Photo / Checksheet
label | 1b680dd9-e479-578f-bbde-69c1729e3ee9 |  | note | Frequency - Prior to Stone Strong block installation
label | a9c7ed43-8613-5ebc-857e-690eca1a5585 |  | note | Activity - I
label | b5fbdddf-aa08-5620-83bd-7340b7acd380 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 5.02.02 - Installation of blocks
label | 90ef02e4-593b-5fb9-a2a3-b68fe5c81ecb |  | note | Acceptance / Conformance Criteria - Blocks to be installed to the height and location as detailed on the construction drawings. The table below details acceptable tollerances.
label | 32d1b68c-0bfe-5bb2-abd7-26cb71e423d5 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | b12d3329-7987-5247-b922-ec1c92c9ed00 |  | note | Table 4: MSE Tolerances
label | dfcb71bb-f02b-56d1-bd66-3ef672ac4eab |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | 8d01ee4b-e521-522d-8a7a-9bd9cf9cf39e |  | note | Element ¦¦ Vertical Position ¦¦ Horizontal Position ¦¦ Vertical Alignment ¦¦ Horizontal Alignment
label | c9b8de3b-7e7d-54be-a648-be447dff7dc0 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | 18339fca-9026-508b-96e4-2fb4655e0c6a |  | note | Soil Surface ¦¦ ± 100mm ¦¦ N/A ¦¦ N/A ¦¦ N/A
label | 7e0bf557-a381-509d-8795-4822c3e0c715 |  | note | Facings and wall structures ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
label | a3fbd331-d3ef-513a-8a89-9470f7fdb303 |  | note | Footings or supports ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
label | 3c7b2ddd-a24b-5b7f-9049-436a8e69bce4 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | 07037d56-3fae-5229-bb84-bcd2d797e781 |  | note | Standard / Specification - GWS - 5.4
label | 48c1e9a8-8b89-527a-91c8-f72b261b72e0 |  | note | Verifying Document - Site Photo / Checksheet
label | 54fda68a-448a-5dcd-8ed6-0a86c20b0e5a |  | note | Frequency - Each layer
label | 913f0a58-b1ca-5bfb-8468-b952a9389447 |  | note | Activity - I
label | 2396be86-4697-57ce-b7b9-b3a1d1c2257a |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 5.02.03 - Paraweb Installation
label | 0bef5334-c77a-5d85-8b74-f29c3c8ca7fc |  | note | Acceptance / Conformance Criteria - The correct number of parawebs are to be installed as shown on the construction drawings.
label | 622c6a80-827b-564b-a1b0-826cc8553560 |  | note | ○ Para web is to be placed flat or with a 1% fall toward the rear of the wall. The Para web must be free of wrinkles and lightly tensioned prior to and during placement of backfill. Shallow trench to be dug toward the end of the paraweb, pin to be used to pull paraweb taught prior to backfilling.
label | 50d68f77-c004-52f2-a57e-49698bdf2f38 |  | note | ○ The Para web must be continuous over the design embedment length and no joins are permitted unless adequately lapped and spliced according to the Manufacturer’s instructions.
label | 8668a89a-332f-5adb-87ff-04813367b41f |  | note | ○ 150mm of fill cover is required before construction equipment can travel over the area
label | 302495c3-5f3f-555b-bf19-8ba352b3798f |  | note | Standard / Specification - GWS - 5.3.2
label | e0f8ebd4-b7ce-5d74-8e8e-61d1497a1d0e |  | note | Verifying Document - Site Photo / Checksheet
label | 19a36404-73ee-57c2-ad94-ea23f2a50577 |  | note | Frequency - Each layer
label | 4ed90da9-8014-54fc-aff4-4d93fce754c9 |  | note | Activity - I
label | 62c634e1-5096-505b-a986-ddb7ae13ae72 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 5.02.04 - Geocomposite drainage board
label | c4be583a-f1eb-5cd7-8b53-c99e616f142c |  | note | Acceptance / Conformance Criteria - Geocomposite drainage board shall be installed continuously along the back face of the block facing of all MSE retaining walls using an approved adhesive recommended by the manufacturer. Check for correct layout, orientation, and any damage prior to backfilling
label | 78a5af09-b43a-593b-9bb0-cca35aca7587 |  | note | Standard / Specification - PS - 12
label | 118e3434-7671-5ed3-835d-7fc4d8175aa3 |  | note | Verifying Document - Site Photo / Checksheet
label | 660025ef-3ab6-58f4-8765-86925343e3ef |  | note | Frequency - During Installation
label | f0897641-79a2-502d-bcea-6e4441ba74e5 |  | note | Activity - I
label | d79c9d3d-ecfc-5167-a08b-44cff7e6fe7e |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 5.02.05 - Drainage Outlet Installation
label | a3d090c3-4428-5e0a-b209-adf7336af691 |  | note | Acceptance / Conformance Criteria - Drainage pipe wraped in filter sock to be installed along the base of the wall. Drainage outlets shall be connected to the reticulated stormwater system or other approved outlet structure at the discretion of the design engineer
label | 6cfacb22-26fd-5135-a015-17dab1cd0170 |  | note | Standard / Specification - GWS - 5.3.4
label | 2f5a5615-723b-5d5e-8c70-f4b89d64455c |  | note | Verifying Document - Site Photo / Checksheet
label | f38b6aaa-750a-5eb3-81e7-0481324cad07 |  | note | Frequency - During Installation
label | 63a09817-83ab-53aa-95b2-fbb6cbd5e6e6 |  | note | Activity - I
label | 64e8f6bc-35c8-50a6-aeff-2ac4d35244b0 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 5.02.06 - Backfill Installation
label | 68b82bbb-bd2b-500a-9ace-74ec7c5ebb50 |  | note | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts adnd compacted to the following standards.
label | 31c539fd-4460-53ad-bfdf-2e97fcb8b655 |  | note | Standard / Specification - GWS - 5.3.3
label | 633cfa75-f662-58c2-a120-4024e3c6b0a4 |  | note | Verifying Document - Site Photo / Checksheet
label | 6d4d0c18-479a-58d2-a5ec-cf710b5f1faa |  | note | Frequency - Each layer
label | 5972cd9e-2fb0-509b-bef1-f765dd7cccb7 |  | note | Activity - I
label | b83ffa94-0016-517c-bb97-f82c899c2703 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 5.02.07 - Nuclear Densometer (NDM) (Gap 65)
label | f13ff92b-3515-51d0-a988-a8689f2dd02b |  | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
label | 4a4d2b6a-8a2e-5174-a75c-a0f7cf753f69 |  | note | Standard / Specification - GWS - Table 3
label | 6554928e-3918-5c68-b1ac-81e6cb332423 |  | note | Verifying Document - NDM Results
label | 98493087-ecca-5702-9b92-25f0664f918b |  | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
label | 554f611d-c99e-592d-bee2-843015f016da |  | note | Activity - H
label | ccf5b3da-cdf5-5795-9145-2a6b32d69f7e |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.02.08 - Clegg/Proofroll (Gap 65)
label | 003d8931-bc62-5135-b7be-32aa75313eac |  | note | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test.
label | 3874ad51-8f8b-575e-9170-0695e7fdc9bc |  | note | Standard / Specification - GWS - Table 3
label | 4d765a6d-f986-55ae-a453-6684618ffc0e |  | note | Verifying Document - Clegg Result sheet
label | 12a070cf-7dac-57ab-a68e-41e36105e8a1 |  | note | Frequency - Each layer
label | 0313e548-65cb-50f0-85a4-231e5e4b576b |  | note | Activity - H
label | dcd71dcd-85cb-5dee-945b-745855383c9a |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.02.09 - Scala Penetrometer (Hinuera Sand)
label | 4efbde40-a847-5874-adf2-744ee100a9d9 |  | note | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
label | 78e0595b-f746-5ce0-b84e-30718f228843 |  | note | Standard / Specification - GWS - Table 3
label | afe343f9-b761-5bae-855e-8f1669892985 |  | note | Verifying Document - Scala Results
label | 3242c858-14d8-526d-8fce-da11c78994d1 |  | note | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
label | 3b61ccc5-55eb-529c-ab6e-c36b4195619a |  | note | Activity - H
label | f0eff603-e0e2-56fe-a76e-7f727936301e |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.03.01 - Settlement Pins
label | 6be00cc8-35f7-58b4-9aac-3e2f7da37af6 |  | note | Acceptance / Conformance Criteria - Settlement pins shall be installed within 24 hours of reaching design subgrade level. Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
label | a15120ed-c718-5d31-baef-0c8bf1202b40 |  | note | Standard / Specification - GWS - 6.3
label | c328b2c9-2589-5ea8-a5a5-29f4fbb679b6 |  | note | Verifying Document - Survey Results (in paper as well as electronic format)
label | c44e4189-f4cd-5c8a-94c5-7045748d766f |  | note | Frequency - Weekly for the first month, then monthly
label | 976b9f25-82ac-5367-a238-3dc87271bf9f |  | note | Activity - R
label | f42af643-c395-58bc-a22e-585a9ebaf8f8 |  | note | By - SV, ENG
checkpoint-status |  |  | checkpoint | 5.03.02 - Settlement Targets
label | 08507682-93c4-5452-97e2-8150c20bfab6 |  | note | Acceptance / Conformance Criteria - Targets shall be fixed immediately after completion of the first row of retaining wall blocks at each location and the initial baseline survey reading made prior to the subsequent row of retaining wall blocks placed.
label | 480b8b47-6145-593e-9237-ad72d6db0cee |  | note | ○ Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
label | 28d6069c-16cb-52bf-8b0f-2855091f5e5d |  | note | Standard / Specification - GWS - 6.4
label | 4d86ed34-2564-57a8-98f7-1460af0da7f9 |  | note | Verifying Document - Survey Results (in paper as well as electronic format)
label | ee49474b-e7c1-5904-abb4-5613386fddb2 |  | note | Frequency - Weekly for the first month, then monthly
label | 67d177c4-6ae0-544d-8cca-4963c96f1e14 |  | note | Activity - R
label | cd844407-15dc-5abf-ab6a-581e0b72a97e |  | note | By - SV, ENG
checkpoint-status |  |  | checkpoint | 5.03.03 - Engineers Approval
label | 129d7748-60d8-5b2a-9b1a-b1ea68c4b7f9 |  | note | Acceptance / Conformance Criteria - Geotechnical engineer assesment required before commencement of Pavement construction
label | 9c535da8-1110-57cf-bd8b-4b3a4cb67048 |  | note | Standard / Specification - BBO
label | c03b5ad1-5238-50bf-94b3-a6d95d7561a5 |  | note | Verifying Document - Written approval
label | 43a8c2cd-762b-5905-a363-f38629034b45 |  | note | Frequency - Prior to pavement construction
label | e735b9e1-02c3-5526-9bcd-5fbbcfc69b4f |  | note | Activity - HP
label | 655aedea-3982-579f-8070-73df15d33ff2 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint-status |  |  | checkpoint | 6.01.02 - Draft As-Builts
label | fa2526ab-b8b9-509f-b4ec-43a5d96dfe8c |  | note | Acceptance / Conformance Criteria - Draft as-builts completed on the completion of MSE wall including red pen mark up to IFC drawing changes.
label | 1b08806c-38dd-54fa-9d51-79482791edaf |  | note | ○ The draft as-builts shall be provided on a continual basis throughout the project for verification by the Engineer, and as a minimum shall be provided in electronic form prior to application for Practical Completion.
label | 71c7e106-4037-5b64-8bc7-4d64f708bf04 |  | note | Standard / Specification - PS 2.2.17
label | a9791038-927a-56e8-92bc-092094da73cb |  | note | Verifying Document - Draft As-Builts Drawings
label | 8b640c55-480e-521c-b672-75b78b29968d |  | note | Frequency - Prior to PC
label | 66bc92ec-3655-5cdd-82f9-c85ade2d83b3 |  | note | Activity - H
label | 0f0c9cf5-c28d-5026-9f36-cb989728faad |  | note | By - SV / PE
checklist-sectioned |  |  | checklist | ITP - Precast Barrier | itp |  |  |  | Yes | ITP - Precast Barrier | 22e13ecd-e913-42ad-bbc5-d10e61b39c0d
checkpoint-group |  |  | section | 1.0 Pre Construction Tests
checkpoint-status |  |  | checkpoint | 1.1 - Concrete Mix Desisgn Approval
label | d8c1387e-f340-5cb6-a9cf-119cf09ff8a4 |  | note | Acceptance Criteria - 50 MPa at 28 days (S5019MS8)
label | 82822e8f-c181-529b-8ae6-9b7c3e8ee282 |  | note | Inspection or Test: Method - Review
label | 17e1e32a-d78f-5fb1-9f9d-d80575a7af30 |  | note | Inspection or Test: Freq. - Once per Mix design / per supplier
label | 922f1a8b-5a26-5977-8b57-0cac27c84dba |  | note | Inspection or Test: Responsible Person - PRECO
label | 6e97688f-cb5f-547d-9922-2f73763498cf |  | note | Verifying Document - Confirmation of Approval
label | 590495b6-fb84-5ea7-b9b2-a2e350925859 |  | note | Records required for handover package: Yes/No - Y
label | b24f9295-91b2-525a-bc27-a17dc6de323f |  | note | Inspection / Test Authority: Conduct - 1
label | a4a94b2c-233f-5b8c-8b94-42a42d0f34c7 |  | note | Inspection / Test Authority: Witness - D
label | 21479b33-a765-589f-997e-a1e9506e3e0b |  | note | Inspection / Test Authority: Produce Record - 1
label | ead0723a-e8ec-56ee-8426-2f4945e60bf1 |  | note | Inspection / Test Authority: Approval - C
label | e84d0568-c9d5-5add-9e54-6d49955cd793 |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.2 - Reinforcement Supply – Certificate of Origin
label | 6a3b2ea9-9c3a-5aad-9002-842ec48435f1 |  | note | Controlling Documents - Approved Drawings
label | e11db8b4-4148-5e5f-8a96-d6daf72989f5 |  | note | Acceptance Criteria - Provide certificate of origin for all steel reinforcing supplied.
label | 92472c27-961a-5122-be14-5ff33260c473 |  | note | Inspection or Test: Method - Review
label | 41843fb2-e96d-58a0-8f59-7428c40b6ed5 |  | note | Inspection or Test: Freq. - Per Size, Per Supplier
label | 1d32e0c0-28aa-5c23-807e-31c15534bbc1 |  | note | Inspection or Test: Responsible Person - PRECO
label | 851cb19b-14e9-583e-9fb7-444b361cb39b |  | note | Verifying Document - Supplier Mill Certificates
label | 8bcd55e9-b715-562c-aeb7-35db9a2d1780 |  | note | Records required for handover package: Yes/No - Y
label | d0897f08-0a46-5ab2-a2aa-26b4cc70e071 |  | note | Inspection / Test Authority: Conduct - 4
label | 5f717aef-d570-55f5-a7e9-588facad603c |  | note | Inspection / Test Authority: Witness - D
label | 978c43fd-466c-5213-8c70-200dd0e727c5 |  | note | Inspection / Test Authority: Produce Record - 4
label | 8b09c1ac-afd5-5f14-9319-cb632d46e505 |  | note | Inspection / Test Authority: Approval - C
label | 2b805cb5-8bd6-5a2a-a47f-e4826f8c3386 |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3 - Shop Drawing Approval
label | 01f24f63-a8a8-5533-9795-d54100f46f05 |  | note | Controlling Documents - IFC Drawings
label | 82a163aa-5ebb-5a1f-be85-a4d3dd3f1988 |  | note | Acceptance Criteria - Shop drawings including, concrete strengths, surface finishes, location of cast in items and set-out information
label | 05e7ca4a-ae0a-5f34-a26e-5b9670930949 |  | note | Inspection or Test: Method - Review
label | 695835da-bf07-5525-8b1c-47c5b4e314cc |  | note | Inspection or Test: Freq. - Once Prior to Casting
label | 997d69a6-5c30-5ad6-87d5-923d6035c8e8 |  | note | Inspection or Test: Responsible Person - PRECO
label | 62d2c64d-62fe-5e04-a810-579213f4ac7e |  | note | Verifying Document - Approved Shop Drawings, Issued for Construction
label | 839e54a5-4a5c-5f3d-a108-fcd224e34d4a |  | note | Records required for handover package: Yes/No - Y
label | f4fd2d1a-3534-58ab-9235-c15f5cbada6d |  | note | Inspection / Test Authority: Conduct - C
label | ab881588-246c-5c6b-a63f-3332cb50be3d |  | note | Inspection / Test Authority: Witness - C
label | b0e4bc24-e62f-5ec1-a1bd-2e8c11a5e6f0 |  | note | Inspection / Test Authority: Produce Record - C
label | 190341d8-174d-5b38-a15b-1870094d5a12 |  | note | Inspection / Test Authority: Approval - D
label | 20a5d1e7-b4cb-515f-b447-f892596aea77 |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.4 - Form Release Agent
label | 3ae381ed-20c5-51b1-97f3-1f566263548a |  | note | Acceptance Criteria - Not detrimental to the application of any subsequent finishes
label | 20128331-ac7c-5ce1-999f-2a235b14700b |  | note | Inspection or Test: Method - Review
label | 7d670198-1d1a-524a-b380-7af2ceb3ef58 |  | note | Inspection or Test: Freq. - Once
label | 22eb0f03-2aee-54a6-9e46-92b83d40a4ae |  | note | Inspection or Test: Responsible Person - PRECO
label | e5a880a0-5942-5372-9568-9fcbf5f0458f |  | note | Verifying Document - Material Data Sheet
label | aa2035b9-00ae-5b2f-a8a3-77293821f2c6 |  | note | Records required for handover package: Yes/No - Y
label | 6a8e216c-3a6d-5a39-a1d4-e0d1cc53f8aa |  | note | Inspection / Test Authority: Conduct - C
label | 437aac02-281f-549e-8aa4-dba7011957da |  | note | Inspection / Test Authority: Produce Record - S
label | 8dafda5f-5c6d-5397-97d9-fd57a8fadd13 |  | note | Inspection / Test Authority: Approval - C
label | 0d828057-93e9-5e69-8d1e-079094db6520 |  | note | Hold Point - N
checkpoint-status |  |  | checkpoint | 1.5 - Cast-in Items
label | 191fdecd-efd8-52c3-bf6f-fb59fbd5baa1 |  | note | Acceptance Criteria - Provide certificate of origin for cast-in-items
label | fc62b7b0-cad3-531f-b28a-dca8e9324524 |  | note | Inspection or Test: Method - Review
label | 7b724a24-18dd-518e-9580-d4c69eed6379 |  | note | Inspection or Test: Freq. - Per batch delivered
label | c706b1fd-9a71-5789-84a6-97e8f67a1258 |  | note | Inspection or Test: Responsible Person - PRECO
label | 76a37be5-fbc7-531b-b323-6e2757c8b25d |  | note | Verifying Document - Suppliers Mill Certificate
label | 5b9e05d2-a92b-51ac-910c-0a990b6a07db |  | note | Records required for handover package: Yes/No - Y
label | c5d321b4-8305-5159-a1cb-2b116d474a21 |  | note | Inspection / Test Authority: Conduct - 4
label | 3dc93ab7-004e-56a4-8fad-e30442f4cf2a |  | note | Inspection / Test Authority: Witness - C
label | 474dd962-a1cb-5aa2-a069-a4dec55c6dd8 |  | note | Inspection / Test Authority: Produce Record - 4
label | 2cb46a60-93aa-5849-8620-5df7c6b2f17a |  | note | Inspection / Test Authority: Approval - C
label | 4078a876-a52a-5bcd-8995-a003a05e0174 |  | note | Hold Point - N
checkpoint-group |  |  | section | 2.0 In Process Testing
checkpoint-status |  |  | checkpoint | 2.1 - Inspection of The Reinforcing
label | 8dda2c2a-6ce2-5130-a053-532dfee26c60 |  | note | Acceptance Criteria - 40 mm min. clear cover to all reinforcing including stirrups and ties
label | 9482d366-67a4-5ebe-be2b-03e80b5a4174 |  | note | ○ Steel to be securely tied and fixed with no movement
label | 22ac8de6-6e72-584e-ac23-0d37e0e42adc |  | note | Inspection or Test: Method - Inspect
label | 59b84c6c-85b2-5826-b7bf-4afa30c31b4b |  | note | Inspection or Test: Freq. - Per Unit
label | 4eab1891-96b6-59c3-957f-05e9e7f8c667 |  | note | Inspection or Test: Responsible Person - PRECO
label | 980bd4e2-fede-5d11-b49a-00ca53cdf45d |  | note | Verifying Document - Pre pour checksheet, photos
label | 52dd7dcb-9fb5-5455-9c91-18ea7e926987 |  | note | Records required for handover package: Yes/No - Y
label | 646d609a-8a56-5657-ae06-8224973902ea |  | note | Inspection / Test Authority: Conduct - C
label | c3248dcf-db60-5ea8-987f-6b8cb50642c5 |  | note | Inspection / Test Authority: Witness - D
label | 78951cc8-b562-545c-8fd6-473256170749 |  | note | Inspection / Test Authority: Produce Record - C
label | a075679e-8bd9-57ae-82a3-8853d4e7fc6f |  | note | Inspection / Test Authority: Approval - C
label | 1c40571c-d8e9-536e-814a-f22448a2afff |  | note | Hold Point - N
checkpoint-status |  |  | checkpoint | 2.2 - Checking Formwork
label | d59f7513-cf1d-528f-87ee-7f54243a1361 |  | note | Acceptance Criteria - Dimension including edge details and rebates as per drawing
label | 1175cfb5-e783-560d-a6a9-d91dda4acea1 |  | note | Inspection or Test: Method - Inspect
label | f29a3f3b-d608-50aa-9650-55fc0a38d3ce |  | note | Inspection or Test: Freq. - Per Unit
label | aacc72e0-9968-58ff-92b3-8e6e4f2f5b89 |  | note | Inspection or Test: Responsible Person - PRECO
label | af983bfb-d586-5e80-9fc4-583a4cbf32a0 |  | note | Verifying Document - Pre pour checksheet, photos
label | 5cac43b4-6466-5164-a815-c76dc171549c |  | note | Records required for handover package: Yes/No - Y
label | 58763972-25fd-5ac6-a1d8-ef95cfabe5a5 |  | note | Inspection / Test Authority: Conduct - C
label | ecd6bf87-85e5-553c-95f0-c5d61bc48ecb |  | note | Inspection / Test Authority: Witness - C
label | f98de228-e39b-5174-9a7f-8bb2d6f92974 |  | note | Inspection / Test Authority: Produce Record - C
label | e64ec3aa-a4bc-52e1-9339-c7a2ad308c5e |  | note | Inspection / Test Authority: Approval - C
label | 802ea10b-5e2f-5af8-854d-5ff010bdc2d6 |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.3 - Pre Pour Inspection Prior to concrete placement
label | 9ab5217c-e2cd-5fdb-9388-5f25adfb5d63 |  | note | Acceptance Criteria - Completed pre-pour inspection, permission to commence concrete placement
label | 444c6e66-1951-5b7b-8799-659954e74703 |  | note | Inspection or Test: Method - Inspect
label | 10fa7972-4848-5030-92c5-a39c41f0179e |  | note | Inspection or Test: Freq. - Per Unit
label | b39d3345-104b-5d2a-901d-766e47400126 |  | note | Inspection or Test: Responsible Person - PRECO
label | 273b5932-9a67-5edc-af41-00ff28326c5f |  | note | Verifying Document - Pre-Pour Check Sheet/ photos
label | 87e0b84d-92d4-51f0-b63e-fb69c1e86fac |  | note | Records required for handover package: Yes/No - Y
label | 6365b53b-d5f9-5e8f-b8fe-0aa99e7506be |  | note | Inspection / Test Authority: Conduct - C
label | ea11e90c-e0bb-5340-9710-b5df8f2cfde8 |  | note | Inspection / Test Authority: Witness - D
label | 208f718f-0a75-5f36-aa38-1a35ca59f7a9 |  | note | Inspection / Test Authority: Produce Record - C
label | e3b7a418-9b94-5f4d-a64d-cde7d8ac481e |  | note | Inspection / Test Authority: Approval - C
label | 1317ad0a-ce1c-56b9-9d31-51ef2fd53508 |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 3.0 Concrete Testing and Inspection
checkpoint-status |  |  | checkpoint | 3.1 - Concrete Delivery
label | 296c0544-627f-5cb8-8ccf-fa3c00e0c563 |  | note | Acceptance Criteria - Approved Mix Design (S5019MS8)
label | e09836e7-e944-5b41-a628-e3f722fd1112 |  | note | Inspection or Test: Method - Inspect
label | 73172d08-d70c-5c91-8a6d-abc43520e3bb |  | note | Inspection or Test: Freq. - Per Concrete Delivery
label | 6491128f-374a-59e8-8c93-46f50daa8abf |  | note | Inspection or Test: Responsible Person - PRECO
label | 76468661-1f35-509e-987c-bb8ddef86349 |  | note | Verifying Document - Delivery Dockets
label | 6a509483-7609-5bea-b5d3-42e77bb27926 |  | note | Records required for handover package: Yes/No - Y
label | 7e5c1ae7-4654-51e1-a97e-8b3a557b59d6 |  | note | Inspection / Test Authority: Conduct - C
label | 1d1cadf0-d5ad-5ab5-92e1-51052729e03e |  | note | Inspection / Test Authority: Witness - C
label | 5fa8589e-5b9c-571f-bac9-db74040c9459 |  | note | Inspection / Test Authority: Produce Record - C
label | de346339-d61a-55a7-ba96-207fe74e50e4 |  | note | Inspection / Test Authority: Approval - C
label | 70768a97-bb2e-5c6c-bb41-b6dffa215225 |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.2 - Concrete Placement
label | b7612537-785b-5c47-897f-0dffa8459c5c |  | note | Controlling Documents - NZ 3109
label | 03d33a90-5556-5f22-8d9c-46cd3ffee61d |  | note | Acceptance Criteria - Vibration of concrete to ensure suitable compaction
label | f92b1f4a-62e7-54be-b0f6-06940e48a240 |  | note | ○ Slump within target 100+/-40
label | 58a16842-dc9d-5669-81a9-f9cce43d1705 |  | note | Inspection or Test: Method - inspect
label | a09d97af-f824-5dce-98df-b0de190ff109 |  | note | Inspection or Test: Freq. - Per unit
label | 077c5cd0-3f48-5446-9775-52c6ce128d2e |  | note | Inspection or Test: Responsible Person - PRECO
label | 27d1c5c3-6b9a-5d30-acf9-519451febdf5 |  | note | Verifying Document - Witness inspection
label | 3a7fe327-77c7-53f8-8685-610a5c572c56 |  | note | Records required for handover package: Yes/No - N
label | 762ee824-9acb-51e9-80eb-fc021982475c |  | note | Inspection / Test Authority: Conduct - C
label | 4bb788dd-8ff2-5043-99e2-67aa9adccb74 |  | note | Inspection / Test Authority: Witness - C
label | 1b6a9469-9659-527b-9fcb-b8b9b191f43f |  | note | Hold Point - N
checkpoint-group |  |  | section | 4.0 Post Concrete Testing and Inspection
checkpoint-status |  |  | checkpoint | 4.1 - Concrete smpling / testing
label | ac8036a4-52c9-55c5-9048-7e4424a39e53 |  | note | Acceptance Criteria - 1 x 7d and 3 x 28d - 50 MPa at 28 days
label | cb06f198-2fc0-5a49-96ff-af413b4280e6 |  | note | Inspection or Test: Method - Concrete Sampling
label | 1d3ac0ba-70e5-5047-94ee-68ff84fbdb5c |  | note | Inspection or Test: Freq. - Per 75 m3 (not part thereof)
label | 73dc4b4d-6d20-50e7-a00c-53beb9e7e682 |  | note | Inspection or Test: Responsible Person - Subcontractor
label | 867bc4d8-1c15-5688-8f7c-d12e26deeafe |  | note | Verifying Document - Concrete Sample Test Results (IANZ Accredited Laboratory)
label | 6a8dd5b4-8114-53f0-a625-9f2a10d108ec |  | note | Records required for handover package: Yes/No - Y
label | fb47404f-d673-51d1-9dde-96e1c28ec324 |  | note | Inspection / Test Authority: Conduct - C
label | 2a5b41ca-7ced-5247-a3b5-592077b03b9d |  | note | Inspection / Test Authority: Witness - C
label | 555306d6-43ec-5ead-96da-7a4dadecdaed |  | note | Inspection / Test Authority: Produce Record - 3
label | a04b5bc2-3ceb-5151-9f28-03ee5bed39a1 |  | note | Inspection / Test Authority: Approval - C
label | 8580c40a-f952-5a4e-b4de-ed19a5b5b4e0 |  | note | Hold Point - Y (Designer to be notified immediately if specimen fails)
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.2 - Surface Finish Requirements
label | 970ed5bd-ceb8-5bb4-9cd6-a51374433d88 |  | note | Controlling Documents - IFC Drawings
label | 3a816951-23ae-5c00-be0d-9bf406e64319 |  | note | Acceptance Criteria - F5 / Type B construction joint to NZ 3109
label | 2cfd5b87-68dd-5eb0-86dc-9d4f396b91b9 |  | note | Inspection or Test: Method - Inspect
label | bbcab98e-e450-5f80-96b7-dd2bc0853272 |  | note | Inspection or Test: Freq. - Per Unit
label | 730970bd-c98c-5426-8a15-749f3ebf02e8 |  | note | Inspection or Test: Responsible Person - PRECO
label | d9dc372c-d89b-5b40-9169-08a8380efbea |  | note | Verifying Document - Post Pour Checksheet
label | f1075e86-4059-5992-ace8-f806ec58a37e |  | note | Records required for handover package: Yes/No - Y
label | b2e4f0f2-e6fe-537d-a7be-93bd9deb8d21 |  | note | Inspection / Test Authority: Conduct - C
label | f3c88a89-d0e9-59f4-8308-4a403d177b96 |  | note | Inspection / Test Authority: Witness - C
label | 4bb6e2f2-8054-5fa2-a8f2-5fe75440994c |  | note | Inspection / Test Authority: Produce Record - C
label | 7d325357-f7e2-5bf4-8242-6b2eb96e5fce |  | note | Inspection / Test Authority: Approval - D
label | cb6579f7-877d-5b49-b14f-556ce8468624 |  | note | Hold Point - Y (Designer to be notified if finish requirement not meant)
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4.3 - Concrete Curing
label | 6d81ae7e-5250-5248-9ee3-94b487944a98 |  | note | Acceptance Criteria - Curing with curing compound (e-cure)
label | 8e9da9c3-29f5-5d7b-96e9-5695fa15434d |  | note | Inspection or Test: Method - Inspect
label | 2026a907-8246-52c2-afbc-9c7e1cb8da2f |  | note | Inspection or Test: Freq. - Per Unit
label | 72b915a8-7450-50ee-9e42-0fbe53eaf8b6 |  | note | Inspection or Test: Responsible Person - PRECO
label | 3c0231eb-070d-54e7-9229-07e3271c5cb3 |  | note | Verifying Document - Post Pour Checksheet
label | 115a294b-f979-5d22-9393-cfeb8bbedc79 |  | note | Records required for handover package: Yes/No - Y
label | a3a2c096-c118-5c4e-9165-c4ad75f5c906 |  | note | Inspection / Test Authority: Conduct - C
label | 4e8933ed-b582-5d65-8d62-5dbe6846e0a7 |  | note | Inspection / Test Authority: Witness - C
label | 82c6c6c3-8dd7-5b6c-a6ec-04d5507d41de |  | note | Inspection / Test Authority: Produce Record - C
label | 775663b2-4b2f-52e6-9523-c4da7e95f922 |  | note | Inspection / Test Authority: Approval - C
label | 45785fe4-d994-5bd7-9d20-b13f8492185d |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 5.0 Final Documentation
checkpoint-status |  |  | checkpoint | 5.1 - Producer Statement (PS3)
label | 1a1341a6-c738-5453-a224-d291e69b0bec |  | note | Acceptance Criteria - Signed PS3
label | 0cb2d76c-afdd-5abf-863e-08404ef07f13 |  | note | Inspection or Test: Method - Report Production
label | 1d9396f6-ea72-58e8-8c21-22cf717d212a |  | note | Inspection or Test: Responsible Person - PRECO
label | 38b5f39c-b2bd-5bd8-a5a8-7e63a9478b96 |  | note | Verifying Document - Signed PS3
label | c684c088-1b8e-5e64-9f95-d76853df1aae |  | note | Records required for handover package: Yes/No - Y
label | 0d43f981-bf55-57a3-ac91-131e1ebce22c |  | note | Inspection / Test Authority: Conduct - C
label | b1fb543e-72a2-57cf-a247-ac4f7222d82d |  | note | Inspection / Test Authority: Produce Record - C
label | 063d5691-9cda-5cb6-901b-6e036a4af6e0 |  | note | Inspection / Test Authority: Approval - D
label | c599dcef-8922-57d8-8daa-4b939c9f4ea3 |  | note | Hold Point - N
checklist-sectioned |  |  | checklist | Concrete Pre-pour Inspection |  |  |  |  | Yes | Concrete Pre-pour Inspection | 29f4e71f-35f0-4034-a2e5-ded8ecbaf6dd
checkpoint-group |  |  | section | Preliminary
checkpoint-status |  |  | checkpoint | Engineer notified of pour
text | 98ffea72-4951-5484-a1cb-4a448e1233c5 |  | textbox | Date
text | 7006f770-0251-5e19-ad15-3a83db9ada77 |  | textbox | Drawing Number and Revision
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | Installed as per formwork design
checkpoint-status |  |  | checkpoint | Permit to load issued
checkpoint-status |  |  | checkpoint | Dimensions correct
checkpoint-status |  |  | checkpoint | Position and orientation correct
checkpoint-status |  |  | checkpoint | Forms vertical, plumb and true
checkpoint-status |  |  | checkpoint | Forms coated with release agent
checkpoint-status |  |  | checkpoint | Forms clean and clear of debris
checkpoint-status |  |  | checkpoint | Joints sealed
checkpoint-status |  |  | checkpoint | Pour level marks
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | Correct grade reinforcement
checkpoint-status |  |  | checkpoint | Correct bar size
checkpoint-status |  |  | checkpoint | Correct number of bars
checkpoint-status |  |  | checkpoint | Correct spacing
checkpoint-status |  |  | checkpoint | Starters bars included
checkpoint-status |  |  | checkpoint | Correct cover (min 75mm against ground, 50mm where protected from soil during casting, 40mm otherwise. max 100mm end cover on hoizontal bars)
checkpoint-status |  |  | checkpoint | Correct weld lengths (min 10 x bar diameter)
checkpoint-status |  |  | checkpoint | Correct lap length (min 50 x bar diamenter or as per drawing)
checkpoint-status |  |  | checkpoint | Correct lap position (staggered appropriately)
checkpoint-status |  |  | checkpoint | Longitudinal bars terminate with 90 or 180 deg hook)
checkpoint-status |  |  | checkpoint | Reid bar couplers tightened fully and filled with EPCON C8 Extreme
checkpoint-status |  |  | checkpoint | Reinforcing adequately tied
checkpoint-status |  |  | checkpoint | Chairs or spacers fixed in place
checkpoint-group |  |  | section | Embedded items
checkpoint-status |  |  | checkpoint | Block-outs, ducts & cast in items installed
checkpoint-status |  |  | checkpoint | Correct position, level & alignment
checkpoint-status |  |  | checkpoint | Securely fixed in place
checkpoint-group |  |  | section | Construction Joints
checkpoint-status |  |  | checkpoint | Correct location
checkpoint-status |  |  | checkpoint | Adequately prepped
checkpoint-status |  |  | checkpoint | Joint board installed
checklist-sectioned |  |  | checklist | ITP - Watermain PVC |  |  |  |  | Yes | ITP - Watermain PVC | 32e6b2e5-b60f-4e12-88ad-ddd4a32c832c
checkpoint-group |  |  | section | 1. Pre-construction (P&G / Establishment)
checkpoint-status |  |  | checkpoint | 1.1 - Extent of Line Setout
label | 2188c8af-1b0e-5f69-b95b-5375efd86476 |  | note | Acceptance / Conformance Criteria - Ensure line and level of Stormwater has been marked out and agreed with Engineer in accordance with Watermain drawings Identify any clashes before construction.
label | 52de05b7-2523-5da6-8f80-d5d818ab628f |  | note | Standard / Specification - Design Drawings
label | e61c2fd1-b475-5e0b-9891-8eb078397d5c |  | note | Verifying Document - ITP Sign Off
label | 4c435d60-892e-549b-ad93-35365a7448d1 |  | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
label | 1b47d63b-488e-5cb4-9561-a648677e6e11 |  | note | Activity - M
label | 74725284-9d13-53b3-adb8-e716dfb7ab4f |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.2 - Environmental Protection
label | 2daa111b-fb92-56cb-95f0-a0893bb7d5a7 |  | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
label | 90e89d68-cdce-5951-807d-af0f8df8df9d |  | note | Standard / Specification - Project ESCP Plans
label | 0c7e2196-45e7-501f-b491-48fbc3679d4b |  | note | Verifying Document - ITP Sign Off
label | 183c9709-e340-589b-8e50-25dde0b61fe6 |  | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
label | 58063758-ff8f-5ae4-8b2f-6df8e28b5bd3 |  | note | Activity - M
label | cb9fe534-57a2-5c13-bc53-f991d52f3827 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.3 - Stakeholder
label | 9989e892-ba99-5f46-94d1-2ad757eaa13b |  | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
label | 7d849347-4c2f-51c4-9572-a3141cde43c8 |  | note | Standard / Specification - Project Stakeholder Management Plan
label | 92486058-ca48-5a73-8b08-5850dfbedada |  | note | Verifying Document - ITP Sign Off
label | e0d10c68-8f54-592b-ae3e-ce2b6314547a |  | note | Frequency - Prior to Construction with continue updates throughout the works
label | 86e0b0bb-7529-57e6-9e4e-984c639ef986 |  | note | Activity - M
label | f0b731bf-77b1-5b67-9e5f-a719015147f2 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.4 - Permits
label | 6dc1956a-3aec-55c3-ba28-fa3b08efcdc1 |  | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
label | 37f81dcf-5bd4-55f4-acf6-85e9f7454b47 |  | note | Standard / Specification - Section 2.2.10 Project Specification
label | 858dc8ce-814c-557c-8854-687c8c26c1a9 |  | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
label | 484256f6-9cf4-5e56-bc22-cd9ce8cca84f |  | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
label | 8f71f728-3673-5fbe-9e40-0033bce41387 |  | note | Activity - H
label | c9df6b3c-5476-5a0f-a223-54b76ae6401d |  | note | By - PE
checkpoint-group |  |  | section | 2. Material, Personnel & third party approval
checkpoint-status |  |  | checkpoint | 2.1 - Pipes & Fittings
label | cb6bd198-cb74-5f66-a3a6-58ecf46e544e |  | note | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/fittings are correct and in good condition and compliant.
label | 25841545-1c58-586f-9e80-ecf24d1107b7 |  | note | Verifying Document - Delivery Dockets
label | 0b67eb3e-77fd-5648-bc0e-f15359c84a7b |  | note | Frequency - Each Delivery to Site
label | 436ec73b-2a28-5f66-a0d0-4cacba4928ce |  | note | Activity - S
label | e86680e5-61d2-5449-9f68-97554420befe |  | note | By - PE
checkpoint-status |  |  | checkpoint | 2.2 - Bedding/Overlay
label | ac3ee39b-6f57-5478-a442-c7b907d45e1b |  | note | Acceptance / Conformance Criteria - Confirm material grading and density of pit sand or other approved material
label | 5d3234bd-54fe-55b6-b03b-87c35187af3b |  | note | Verifying Document - IANZ Lab Test Reports
label | 61ba510d-a74b-5af1-ad03-82e66121b21c |  | note | Frequency - 1 Test per 1000m3
label | f97c4424-e8b9-5ca9-a68e-bbbec2432e03 |  | note | Activity - H
label | 8057e399-7390-53b4-a075-ad6c78bb59fb |  | note | By - PE
checkpoint-status |  |  | checkpoint | 2.3 - Backfill Material Compliance
label | 0fd748e4-0fb9-504a-adf6-f623c6b4d7af |  | note | Acceptance / Conformance Criteria - Confirm material grading and density of pit sand or other approved material Use selected native soils in berm
label | 8fa15a36-e044-5740-a8a2-9311781670ef |  | note | Verifying Document - IANZ Lab Test Reports
label | 77be99f0-dc14-540f-91ce-14cf9920a5d0 |  | note | Frequency - 1 Test per 1000m3
label | c80191a8-c3bd-5a2a-bc63-9e54b7a980cc |  | note | Activity - H
label | a8b7c56f-354d-5900-86a1-235d2be3eda1 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 2.4 - Undercut Backfill Material
label | 3cb47e54-1418-5622-ab41-d615c9382364 |  | note | Acceptance / Conformance Criteria - Engineer to Specify Material to meet specifications dependant on material selected
label | 675eb2f7-2d4e-5dd8-9a6a-44367de039b6 |  | note | Verifying Document - IANZ Lab Test Reports
label | 5c0e5624-6b46-5f4e-8374-970dee1428ec |  | note | Frequency - 1 Test per 1000m3
label | 6cfa0a74-20c1-5572-80f3-2efc11be00d6 |  | note | Activity - HP
label | c075b68e-f3e8-556b-a880-b2e139659d80 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Geotextile/Geogrid
label | 92069664-6ed8-5673-8056-9568d2bfba26 |  | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used in the undercut. Geotextile or Geogrid that is used in the undercut is to be documented / marked up on drawing
label | c0adf8e0-1d1f-5027-ac8a-bae157691020 |  | note | Standard / Specification - Project Specification
label | 1217c2d7-7332-559c-b7f7-4a23ae4e0757 |  | note | Verifying Document - Certification Photos of Delivery Dockets
label | 8ae1e8ac-9cc7-5151-a8b3-88d75e34bda1 |  | note | Frequency - Material Used
label | 08f4eefd-17ae-566f-9c7a-c4931b9dc2b4 |  | note | Activity - C
label | 305ec3b4-fd80-5ba6-9290-213684fa245d |  | note | By - PE
checkpoint-status |  |  | checkpoint | 2.6 - Warning Tape
label | f1e47766-a3f3-5215-a1ce-135f9e9dbb47 |  | note | Acceptance / Conformance Criteria - Obtain Warning Tape from supplier
label | b71ee51d-495e-5b89-b505-abbfb185ea0b |  | note | Verifying Document - Delivery Dockets
label | 90b99526-3ed0-5be3-9aea-1e794c893eae |  | note | Frequency - Each Delivery to Site
label | c663b7c0-cb53-5627-ad7d-f5d83742f76e |  | note | Activity - S
label | 1121b458-64ce-5dca-b110-8108945ceb30 |  | note | By - PE
checkpoint-group |  |  | section | 3. Construction Activity
checkpoint-status |  |  | checkpoint | 3.1 - Trench Excavation
label | f12678f6-c0fd-5ed9-9d41-7545f383290c |  | note | Acceptance / Conformance Criteria - Excavate trench to design height, placing spoil in approved area and benching as required Visual Inspection to any hard stones or rocks to be removed Any archaeological finds to be reported Inspections to any formation of soft spots
label | b510b474-29a2-5d0c-81a5-9a5212a8460f |  | note | Standard / Specification - Project Specification 4.3
label | 4b59d9da-33f7-53d4-8f30-f408e131b057 |  | note | Verifying Document - Scala test result
label | cda8a064-9dfd-5a8c-8458-f1134750ce46 |  | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
label | 78a2c85b-1eaa-5acb-bf9f-a76a82062ae1 |  | note | Activity - H
label | 46695756-bbb6-58f9-8696-bed72f90f8fd |  | note | By - QE
checkpoint-status |  |  | checkpoint | 3.2 - Foundation Compliance
label | 276d0ce0-dfa4-5bd5-a550-9580a3b5dd3e |  | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
label | cf10a023-8a94-5086-b4a7-7c0d119805d7 |  | note | Standard / Specification - Project Specification 4.3
label | f2dc0382-c218-52d7-8977-e280dd16c5b1 |  | note | Verifying Document - Scala test result
label | d4810fc8-9e04-5194-9ec3-fc30e1853e85 |  | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
label | 06a8366a-dfc5-5baa-9e15-0b508bbbed80 |  | note | Activity - H
label | 26295be7-846f-5ad0-9afa-1dd19a084b78 |  | note | By - QE
checkpoint-status |  |  | checkpoint | 3.3 - Undercut Backfill Compliance
label | 34324fc7-d773-54db-8aeb-fc5b1c2f454a |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average98%) of MDD
label | a38999ed-4542-576e-9f74-959326a18952 |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
label | baf96eeb-3529-5ca7-b763-cf0dfe756ffc |  | note | Verifying Document - IANZ Lab Test Report
label | 1a703f4d-039c-5d00-ac58-61d47565037c |  | note | Frequency - Based on Undercut Section
label | 02dcf23e-0ddf-5af9-9f2f-489a85c3bd0f |  | note | Activity - H
label | 96a5d9f8-dd74-57ae-b8fd-a669eca0bac1 |  | note | By - QE
checkpoint-status |  |  | checkpoint | 3.4 - Bedding Compaction Testing
label | 08a3cf70-2b4a-517e-9869-336e34e1f911 |  | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average98%) of MDD
label | cbf448d3-5bf3-5c35-be34-24363e0e426b |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
label | c18f590f-57f1-5d88-b849-183772593ece |  | note | Verifying Document - IANZ Lab Test Report
label | 05c60a7a-bba7-500d-bb44-44a474905a1f |  | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
label | d3c46b89-d758-5e27-b802-1ad98e98ab2b |  | note | Activity - H
label | 1798524e-a004-51ef-af4b-104ac3f8c2da |  | note | By - QE
checkpoint-status |  |  | checkpoint | 3.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
label | bfbf2e9a-fbc9-5fd0-973b-8095fcfb763b |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
label | 969fa821-e653-5c9f-8897-7ec7ae2f0083 |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
label | 028a07b5-3f8a-52e8-8de4-6fba06ab734f |  | note | Verifying Document - IANZ Lab Test Report
label | 437a0105-39f6-512b-b69b-44bd64fab130 |  | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
label | 9260299f-8ef5-52bc-bd37-83f49bdb4e74 |  | note | Activity - H
label | a5e58f80-6f41-59e1-af0d-001fe6c370e9 |  | note | By - QE
checkpoint-status |  |  | checkpoint | 3.6 - Backfill Inspection
label | 990919b2-90bb-5bf4-bc57-bdc954877ec6 |  | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
label | 106a340e-9051-54e1-89a9-15bf607d4d77 |  | note | Standard / Specification - Project Specification 4.3
label | 7ed35f7c-4b27-5ebd-8390-370abfc9f814 |  | note | Verifying Document - Photographs
label | 6b2fe735-3696-533d-bab8-16980d8f1304 |  | note | Frequency - Continuous
label | 2e70d804-bb9d-5d4f-9903-b55ab30e5653 |  | note | Activity - S
label | da1687ab-91ab-58e9-91b6-1b6e97041a12 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.7 - Install Warning Tape
label | 89ad8ee1-db8e-53c5-b079-f92974f40951 |  | note | Acceptance / Conformance Criteria - For open trenching, detector tape shall be placed approximately 200mm below final ground level and metallic ‘detector’ tape coloured blue, stipulating ‘Danger – Water Main Below’ (or similar) shall be laid.
label | d0d4470d-e0c0-5649-9097-5dea6fc91f18 |  | note | Standard / Specification - RITS
label | 21b7fcef-c235-5990-a6fd-f5e7757bfb27 |  | note | Verifying Document - Photographs
label | 30ab73b0-3683-507d-ac37-9477ae9dc08e |  | note | Frequency - Continuous
label | 1927f6e7-bf71-5f57-b600-bc4d095c4728 |  | note | Activity - S
label | ec5e7354-bd30-5124-93d6-dd96acb2018c |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.8 - Survey
label | a5d031ac-99e2-5ea8-bc94-c509b478106f |  | note | Acceptance / Conformance Criteria - All Water Mains shall be laid in a straight line or following street layout. The deviation from approved design alignment permitted either in plan or elevation shall be: Open Cut – ± 50mm on straight and 100mm in curves All pipes, fitting and thrust blocks to be as built prior to backfilling
label | 681466f1-4732-5e3b-b0ea-286d982015e0 |  | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
label | 2c0c5481-84e6-5bff-8007-7a844c38bedf |  | note | Verifying Document - Survey Data
label | 66759fe9-2a36-5335-a22c-25c4b5dd3229 |  | note | Frequency - Continuous
label | 9ba33e89-78d1-5cef-9805-8f994815413b |  | note | Activity - C
label | 69778e5c-9b81-5ce5-8d17-dd4ed98cc005 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 3.9 - Backfill Compaction Testing
label | c788c146-bfb9-5a96-b95c-3518e3b3e9f7 |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC.
label | 931f3c70-962d-5967-b81f-1b19a97e7bf3 |  | note | Standard / Specification - RITS
label | c9458d99-170d-53ae-8103-b196f1f0fa35 |  | note | Verifying Document - IANZ Lab Test Report
label | e9547088-f957-51a1-8c0e-ee8a1f0b6997 |  | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
label | 298dad17-495a-52c9-be43-f3bbe3b937ed |  | note | Activity - H
label | c9717a72-4c7f-5c9d-a696-26defe658e28 |  | note | By - QE
checkpoint-status |  |  | checkpoint | 3.1 - Pressure Testing
label | 5d69a420-1957-5b1c-9290-3c51d88e388b |  | note | Acceptance / Conformance Criteria - At least one working day advance notice shall be given to council for pressure testing of pipelines. All pipelines shall be pressure tested and backfilled after anchor blocks, specials and fittings are completed, but with joints and connections visible. The final tests are to be witnessed by Council prior to the pipe being connected to the ‘live’ network. No further connections will be permitted after this stage. Refer to NZS 4404 Appendix C3 for the requirements or if this not available, the pipe manufacturer’s procedure.
label | 5b2454ea-1cc6-594d-a88e-513232a2193d |  | note | Standard / Specification - 6.3.10 RITS
label | 6e90bbf9-09d4-54e5-b7e6-9a44629abfc2 |  | note | Verifying Document - Visual Inspection & Report
label | f2c3c247-ebb0-5874-a6dc-294338df015c |  | note | Frequency - Completion of Works
label | 5bde098e-eb81-5021-b0e8-32eedf795680 |  | note | Activity - S
label | 6b55841c-7a86-5f6e-a16d-f8ba94e5ce4c |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.11 - Disinfection & Flushing
label | a04ef4c3-e232-5cb6-bf4a-b48be7c1cbb3 |  | note | Acceptance / Conformance Criteria - Appendix D of NZS 4404 – Water Supply Disinfection Specification shall apply Discharge of Testing or Chlorinated Water from pipelines may require a resource consent from the regional council
label | 72e62171-3897-5595-bacf-de1ed94ce84e |  | note | Standard / Specification - 6.3.11 RITS
label | 1a077abb-5e7e-54ee-b677-bc5d79b10d96 |  | note | Verifying Document - Visual Inspection & Report
label | 012e07a0-eb0d-5930-b43a-b7ed3ebb79d4 |  | note | Frequency - Completion of Works
label | 480678f5-c94c-5bce-9be6-d7378074e353 |  | note | Activity - S
label | 80577bfd-b617-5499-b284-b5dae1307d01 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.12 - Bacteriological Test
label | ecf71ef6-9afe-54ef-b387-99bad42254b0 |  | note | Acceptance / Conformance Criteria - In commissioning new pipelines, Council shall be given 24 hours’ notice as to when sampling for bacteriological tests is to be carried out. Water in the pipeline shall be sampled between 12 hours and 48 hours after postchlorination flushing and the samples tested for the presence of E.coli, Coliforms and Heterotrophic Plate Count by a Ministry of Health Approved laboratory with IANZ accreditation for this type of test. The number of samples shall be at least one for projects involving less than 100m of pipe, two for projects up to 200m length, etc. “A satisfactory result is s <1 MPN/100ml for E.coli and Total Coliforms and less than 20 CFU/ml for Heterotrophic Plate Counts.” If E.coli is detected the pipeline shall be swabbed, flushed, disinfected, flushed again and then the bacteriological tests repeated. The process shall be repeated until such time a clear test is recorded. Note: There are high risks of test failure due to sample contamination so it is recommended that the testing laboratory is also involved in collecting the sample.
label | 8458ae3b-7797-5a0a-814d-f2e6b72268ae |  | note | Standard / Specification - 6.3.11.2 RITS
label | e3bb0c54-bcd9-5b91-92e8-cb2da86ad9a5 |  | note | Verifying Document - Visual Inspection & Report
label | 1c926b7a-e073-5363-94e9-287f94a4c5f7 |  | note | Frequency - Completion of Works
label | 1cb5f6b7-91a6-5b74-b072-c914ba3092a9 |  | note | Activity - S
label | 6a48d096-0034-56d8-868a-c78b608d8349 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.13 - Reinstatement
label | 8ec17bcc-d926-596a-8ec1-55e292b11670 |  | note | Acceptance / Conformance Criteria - Quality Check on New Works
label | 12c240a7-5851-5a10-a894-dfc1f21a71de |  | note | Standard / Specification - Reinstate and Tie into existing surrounds
label | 26665455-42e7-5cf8-af92-81a44a978efc |  | note | Verifying Document - Photographs
label | cf7cef0f-8302-5fa6-8771-1d4718d773d3 |  | note | Frequency - Continuous
label | 6b0fbabb-ce6a-568c-be52-0fa22a06b6a6 |  | note | Activity - S
label | 606b0568-359a-5ac7-a423-5451cf87de4f |  | note | By - PE
checkpoint-group |  |  | section | 4. Post-construction (Final Inspection & Handover)
checkpoint-status |  |  | checkpoint | 4.01.01 - Survey As-Builts
label | 970a77da-11d9-53d6-a1c1-82d62e20424c |  | note | Acceptance / Conformance Criteria - Quality Check on New Works based on the tolerances in RITS
label | 989fa426-033b-5cca-bab8-65ba09ef6e49 |  | note | Standard / Specification - Project Specification
label | f78817de-6c2e-573e-ac02-c1c19369129d |  | note | Verifying Document - Survey Data As Built Drawings Photographs
label | 8c5281e5-f67d-50b7-b542-966288db2b75 |  | note | Frequency - Post Works Completion
label | 45c3f513-76b5-5f0e-a367-64bc9aaa06ad |  | note | Activity - H
label | 5dc829e6-c403-5afa-9d2f-41b4948b6ec6 |  | note | By - SV
checklist-sectioned |  |  | checklist | ITP - Pavement & Surfacing - Basecourse - Rev 1 | itp |  |  |  | Yes | ITP - Pavement & Surfacing - Basecourse - Rev 1 | 33752cb8-b125-4be2-a64d-64570c780a4a
checkpoint-group |  |  | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint-status |  |  | checkpoint | 1.01.01 - Construction Pack
label | 86b41d6e-7a57-54f0-acd4-9e40ed52643f |  | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled, uploaded and transmitted on InEight before works commence
label | 48b32bc9-0a62-50c7-92a9-de4758e2d5b9 |  | note | Standard / Specification - Downer
label | c2407745-6aec-5335-a45f-487d44e0628d |  | note | Verifying Document - Construction Pack
label | 635d558b-83ae-53b6-8c28-324ff841586c |  | note | Frequency - Prior to Works start
label | 179c0622-56ca-569d-ba6e-cef8dd739f70 |  | note | Activity - H
label | 07f5d58b-597f-5e2a-9f4c-03dbb5fe0c94 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.01.02 - Survey Setout
label | ec56372d-7f16-5af7-9f23-164babafc370 |  | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | 28cbcb6f-c9fb-5f99-97ef-82f133603fab |  | note | Standard / Specification - Downer
label | 571e6655-cf54-56a2-9cc4-32c6cf1b01a8 |  | note | Verifying Document - Survey Records
label | f8e4441a-1fc7-5887-bc24-e5e60ee6611a |  | note | Frequency - Prior to Works start
label | b24be07a-99c7-505d-bcb1-651936634b9e |  | note | Activity - H
label | eb0f9fe1-4d71-5775-8d5e-50050bef0de8 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 1.01.03 - Service Location
label | cd865226-1847-5604-87bf-c74fdf0f19a3 |  | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | 806a9f08-5828-5c64-bc3e-a0cb61d5562b |  | note | Standard / Specification - Downer
label | 5ddce83b-fb05-5414-958c-e8cb3781aa33 |  | note | Verifying Document - Excavation Permit
label | 867bcb55-3fec-55a1-b73e-5f950b8c745d |  | note | Frequency - Prior to Excavation
label | f7a63b5b-8d8b-5f81-ba95-3bfcd9af5f72 |  | note | Activity - H
label | b2a6ad39-f65a-58c5-b7c7-7bde258f6dd4 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 1.01.04 - Internal Permits
label | 8ef54786-5417-587e-b131-af96f335f981 |  | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc. if applicable.
label | d05b2ec1-4b76-5f23-95bc-f96aab74703d |  | note | Standard / Specification - Downer
label | 3480ef1e-9618-5dc4-a9a1-7d1d972a0262 |  | note | Verifying Document - Internal Permits
label | 5674f571-bbd2-58e6-ae20-7a40c27a268a |  | note | Frequency - Prior to activity being undertaken
label | 21fbf00a-0cdf-5c56-b06f-31055c0966db |  | note | Activity - H
label | c5e199e6-c2fe-53c2-9477-f27de993e720 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 1.01.05 - External Permits
label | 61f5d04c-2805-5c3f-abc9-de003443ecb3 |  | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc, if applicable.
label | fe163655-f22f-5068-bc08-29a102908d62 |  | note | Standard / Specification - Downer
label | 9f87a84d-c1e7-5534-9993-4b54a1767bfd |  | note | Verifying Document - External Permits
label | 843356da-df80-5dec-8e71-df4baaa2d60a |  | note | Frequency - Prior to commencment of activity
label | 33c77b62-d5e6-5d1d-bf39-72822d0fa627 |  | note | Activity - H
label | 093b1822-81bb-5110-af70-8af678b7a11e |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.01.06 - Approved Construction Drawings
label | faadc6af-5fc5-5d53-850f-a7ec9dc5cd62 |  | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | 4bb0d13c-160f-5d2a-8221-f236cbe9a59b |  | note | Standard / Specification - Downer
label | ce420d1e-c0ed-5cdd-aa45-43bd7850568d |  | note | Verifying Document - IFC Drawings
label | 5e753f69-7365-5fc6-9c5a-7b100bcdf085 |  | note | Frequency - Prior to works start
label | 4b246132-854c-59e0-b14e-8bf9a1b68ab3 |  | note | Activity - H
label | b25acc76-bd2a-5e63-a65f-bfc35c711d0e |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.01.07 - Subbase Approval
label | 0c114bd5-9799-56e0-b63a-0ad5d4fb9e0b |  | note | Acceptance / Conformance Criteria - All subbase QA to be sent to Engineer for review 48 hours prior to placing basecourse. Final inspection of subbase required, looking for any cracks in stabilised pavement and pavement is clean, free of and contamination
label | 22226472-fa19-56c0-a111-b205214c4dad |  | note | Standard / Specification - PS - Page 42
label | 854702a8-e776-568c-a112-a6486a17a17f |  | note | Verifying Document - ConQA
label | a90e1905-ceb6-558f-80c3-6a4abce9955a |  | note | Frequency - Before proceeding to the next layer
label | 29b3dba1-842b-5a4e-8b73-4613dc36d483 |  | note | Activity - HP
label | a16e36c3-e5cd-5bfe-99b1-d56bc2c4dbae |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | SECTION 3 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
checkpoint-status |  |  | checkpoint | 3.01.01 - Average Uncompacted Layer Thickness
label | dbbd429c-71bb-5812-85da-dcc9a18eedc9 |  | note | Acceptance / Conformance Criteria - The average uncompacted thickness of any layer shall not be less than 2.5 times the maximum particle size of the aggregate except for tapers and more than 200 mm for the basecourse layer.
label | a371278e-8f76-5b57-b0e1-d6b44c03d6d2 |  | note | Standard / Specification - TNZ B/02: 2005 - 7.3
label | b40b0852-21dd-5607-a013-f8e6812c5725 |  | note | Verifying Document - Survey / Level Checks
label | 8ead24d5-9c8f-5d9f-b807-27ff02162e82 |  | note | Frequency - 1 test per 20m
label | 030068ab-38a5-5036-82f6-7ac7a7c1bd1e |  | note | Activity - I
label | 659025bf-5cfa-55f8-856f-5b915f8d83d3 |  | note | By - SV / PE
checkpoint-status |  |  | checkpoint | 3.01.02 - Basecourse MDD and OMC
label | 9fb00a71-854c-50c7-beeb-d555fad763b0 |  | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Test to be at heavy compaction vibrating hammer, Test on Mat Samples on site.
label | d7dcc15a-3087-5bd3-8abd-001433a8da70 |  | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | 9938c1d4-af1e-54ec-ab05-56cbfcbe7dab |  | note | Verifying Document - IANZ Lab Reports
label | 97c4a02d-759c-5772-a5d0-568ae3601e2a |  | note | Frequency - No less than 1 test every 5,000m³ (in place)
label | 667eba4a-5457-54fb-b177-accc707507cc |  | note | Activity - R
label | 02b79946-e421-55fa-8f12-ece77e587346 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.03 - Plateau Density Test
label | 92929d68-63f0-57fb-ac65-531cb6e97659 |  | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
label | 7ae1ef54-9208-5e9a-9fa2-285c104c3707 |  | note | • Every plateau to be completed at start of works and witnessed by a member of BBO.
label | 80a36b75-0644-57d6-b71a-01cbf8adf488 |  | note | Standard / Specification - PS - Table 7.2 - 2.3
label | 1c6e177a-3638-54ba-b5da-acd2905a56f3 |  | note | Verifying Document - Plateau Density Report
label | 23d37c95-78a9-507c-934c-2f3070031b71 |  | note | Frequency - 5 tests per 10,000m2
label | 45af7d7f-9458-53aa-8eec-57f4e7c57ee8 |  | note | Activity - I
label | d61ec9d0-c82c-5d5b-b51c-8d408366ffc7 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.04 - Plasticity Index
label | e71f59ac-edd0-5e70-beca-82c70dca5b37 |  | note | Acceptance / Conformance Criteria - The Plasticity Index shall be ≤ 8 when tested in accordance with NZS 4407 Test 3.4
label | b86b747b-e06f-56e2-b657-241efaf003a0 |  | note | Standard / Specification - PS - 7.2.3
label | c489a8b1-a8ea-5f82-80ba-4ff4eded1c9a |  | note | Verifying Document - IANZ Lab Reports
label | d0adc64e-bcd5-5457-86b4-ec52e3ab0aa1 |  | note | Frequency - 2 tests per 1000m3 (in place)
label | 90bd30ec-e53e-5268-94dc-d9959a20dc19 |  | note | Activity - R
label | a78cabee-87cf-590d-9de2-bf174b81ae9d |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.05 - Clay Index
label | 3a8afc40-bfb2-549a-9089-5e6cbffcfc0d |  | note | Acceptance / Conformance Criteria - The Clay Index shall be ≤ 5 when tested in accordance with NZS 4407 Test 3.5.
label | 18e72bbf-5f3e-5c0a-b3e4-b741b323ed91 |  | note | Standard / Specification - PS - 7.2.3
label | 2cfd3280-099b-589e-b0ad-7f3ef4136fe4 |  | note | Verifying Document - IANZ Lab Reports
label | f2948c97-c966-5ad9-a79d-7bcb312db057 |  | note | Frequency - 2 tests per 1000m3 (in place)
label | 3d3935ec-fb55-5601-bae8-b23d5ec8039c |  | note | Activity - R
label | 512ba664-826d-5b63-aede-02a1b8d62ee4 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.06 - Sand Equivalent
label | e166ae74-624b-5e5b-8d9a-3a8218aff852 |  | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407 : 1991, Test 3.6 Sand Equivalent Test.
label | de055241-e1a2-5d0b-af5e-54efa88d6216 |  | note | • If Sand Equivalence is < 40, then Clay Index shall not be > 3 and Plasticity Index shall not be > 5 (both being tested in accordance with the methods described above).
label | 3bcda7c7-cfe0-5d4e-9e67-ea1bf377c756 |  | note | • The Sand Equivalent shall be determined using the Wet Method in NZS 4407: 1991 Test 3.6
label | c0544496-3ce2-5232-addd-e6938e540abe |  | note | Standard / Specification - TNZ M/4: 2006, 4.2.1.1
label | 95f11bf1-a8e0-5084-9d61-adb3d2756506 |  | note | Verifying Document - IANZ Lab Reports
label | a9ad710d-e165-5ea8-9e4a-195b132d5d53 |  | note | Frequency - 2 tests per 1000m3 (in place)
label | dc69b47a-7de9-58a0-8dc6-5dfc49859c1a |  | note | Activity - R
label | 9a56c638-031b-545e-9eb5-c0d4183f3245 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.07 - Particle size distribution
label | dc243aeb-782c-5f73-b035-5d90192571f4 |  | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 2 and 3 from TNZ M/4:2006.
label | b0c97723-290e-5e45-b606-54c180dd52e6 |  | note | Standard / Specification - TNZ M/4: 2006
label | c9462b1e-4a16-5f8f-a838-4b695ad099c3 |  | note | Verifying Document - IANZ Lab Reports
label | de976264-2028-5f1e-8b40-58405ee4b2d9 |  | note | Frequency - 2 tests per 1000m3 (in place)
label | b5a313f0-8f07-5136-8235-a6fc300ace71 |  | note | Activity - R
label | b094c546-d0d7-50d0-91ac-5751b343c6f2 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.08 - Basecourse Pavement Layer Compaction
label | 8450682a-d54d-54ca-a371-5bb0648b9165 |  | note | Acceptance / Conformance Criteria - Mean Value ≥ 98 Minimum Value ≥ 95, Backscatter.
label | 8e0dcf5b-a8df-5f00-b697-e5b4bce57cf6 |  | note | Standard / Specification - TNZ B/02: 2005 - 7.6
label | b8033767-e17d-51ab-bb92-a013d34318a7 |  | note | Verifying Document - NDM Report
label | bab4c537-af20-54f8-af38-8deb39ed41a2 |  | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
label | 278f4a50-e7d8-5134-80fb-5ad235f4576a |  | note | Activity - I
label | 3423ebfa-0c74-5182-b8a1-5bd4e9ada4e3 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.09 - Surface Shape
label | aa160684-d90c-5c2f-8670-9c7345013797 |  | note | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual..
label | 6fd83484-45a3-58f8-9dfb-7c1c0a96d94b |  | note | Standard / Specification - TNZ B/02: 2005 - 7.7
label | 96340ffb-3e65-5eac-96b6-68c84daeac5e |  | note | Verifying Document - Survey / Straight edge Report
label | baf33aa0-13cb-5856-9ee2-6358746e87ea |  | note | Frequency - Prior to sealing
label | c7ebfe0c-56a3-53c5-927d-4715673a2ac2 |  | note | Activity - I
label | 2e63751b-2609-5a3d-a6ec-0035cf8985f6 |  | note | By - SV / PE
checkpoint-status |  |  | checkpoint | 3.01.10 - Holding Water
label | 9d5e3f97-39f7-5393-8985-e46df7d9353c |  | note | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
label | 9e6d2939-557c-5f76-9ccd-0aaf26976c71 |  | note | Standard / Specification - TNZ B/02: 2005 - 7.7
label | e2d3939b-60a7-5161-99e9-c40aa73acc53 |  | note | Verifying Document - Visual Inspection / Site Note
label | a9885a41-188f-5625-9424-581588ef206f |  | note | Frequency - Prior to sealing
label | c2a0b25b-48f3-5d30-9933-3bc05f48181c |  | note | Activity - I
label | a5393c6e-4bf8-5dc9-b8a0-9fe9bf6779f0 |  | note | By - SV / PE
checkpoint-status |  |  | checkpoint | 3.01.11 - Maximum Width Variation
label | c54a8880-c803-53c9-905e-907270e1e49d |  | note | Acceptance / Conformance Criteria - Unconstrained : –20 mm +100 mm
label | 4f2614cf-5d0f-5220-b839-2250b118dac0 |  | note | • Constrained : Zero
label | 0a07615c-bdc7-587d-93e7-0fa6ef846f00 |  | note | Standard / Specification - TNZ B/02: 2005 - 5.1
label | 509cb0c4-b4c6-5133-83a7-abddb21b59b5 |  | note | Verifying Document - Survey / Level Checks
label | 8546fa8e-8880-5859-9034-8b5f93cc0f54 |  | note | Frequency - Before Next layer or Surfacing
label | 88f457ae-d9e2-5dda-96de-604c02b89acd |  | note | Activity - I
label | 1b214982-fb22-5d0e-ad43-16521eead8bc |  | note | By - SV / PE
checkpoint-status |  |  | checkpoint | 3.01.12 - Maximum Vertical Basecourse With Concrete Channel Variation
label | b4a7ebbb-018c-5af9-9c36-b41eb6e36384 |  | note | Acceptance / Conformance Criteria - At or close to the lip of channel: –5 mm +5 mm
label | a908229c-118d-555b-8caa-30536f9ea3d8 |  | note | • At other locations on pavement: –5 mm +15 mm
label | 2a799e2e-2862-583b-9ee6-f85293c43566 |  | note | Standard / Specification - TNZ B/02: 2005 - 5.1
label | f7bac258-a191-5284-b56a-383259c8f3bc |  | note | Verifying Document - Survey / Level Checks
label | b45a69e9-5f6f-5327-84db-99e2e8e8e8ac |  | note | Frequency - Before Surfacing
label | d88b2f97-bb88-5415-8669-2314cddde2d5 |  | note | Activity - I
label | 732ddd51-a403-5cbd-8243-c72ee577856a |  | note | By - SV / PE
checkpoint-status |  |  | checkpoint | 3.01.13 - Maximum Crossfall Variation
label | 5c67f160-a2f0-52f8-bd42-ca23ee461ed7 |  | note | Acceptance / Conformance Criteria - The crossfall between any two points more than 2m apart, transverse to the centreline, shall not depart from the crossfall shown in the documents by more than 0.5%
label | ea889ddb-0e1d-5c83-bc77-c98178a4b221 |  | note | Standard / Specification - TNZ B/02: 2005 - 5.1
label | 9c527da4-f334-5def-9908-16581146a1d7 |  | note | Verifying Document - Survey / Level Checks
label | 12ebf109-2be6-5908-ab45-7c266f20332a |  | note | Frequency - Before Surfacing
label | 11e72989-7bc6-5b31-9135-f0d7b62160fe |  | note | Activity - I
label | 888d745c-7ad7-5f0a-9f6e-38e8a8b6c5ca |  | note | By - SV / PE
checkpoint-status |  |  | checkpoint | 3.01.14 - Benkelman Beam
label | 4b5b3f0a-183d-5bad-a8f7-b0818fd4feff |  | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be reported to the Engineer to verify that that the sub-base stiffness meets the requirements of the pavement design, before proceeding with the next layer. Benkelman Beam testing shall be completed no sooner than 7 days after stabilisation. The rate of testing is specified in Table A7.3. - INFORMATION ONLY
label | 8126b007-cc77-532a-bd21-14c073978c8d |  | note | Standard / Specification - PS - 7.3.2
label | 44fa1f00-8205-5566-8533-f958b07c388e |  | note | Verifying Document - Benkelman Beam Report
label | 09ab0245-b2b2-5a04-ace4-d10a308c257c |  | note | Frequency - every 10m of each lane – staggered between left and right wheel path.
label | be216873-42cc-5f8a-9ca4-94e7e2d5e346 |  | note | Activity - R
label | 678cb500-e4e0-5f55-a9d7-eae559b8cca6 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.15 - NAASRA roughness
label | cbc72159-c7a3-5248-b9fa-4b94345cd365 |  | note | Acceptance / Conformance Criteria - The longitudinal smoothness of the final surfacing layer shall comply with the maximum NAASRA roughness value detailed in the specific contract requirements. (Recommended but not required)
label | e65d3e44-613d-58e9-815d-8d6ee333a610 |  | note | Standard / Specification - TNZ B/02: 2005 - 7.7
label | f1bbe188-bfad-554e-9963-e3f3b39545ba |  | note | Verifying Document - Test Report
label | 802ff844-fdea-55c2-93c0-8ab81c71a1f2 |  | note | Frequency - Prior to sealing
label | b5a75739-990b-5360-a212-bfef6bf93040 |  | note | Activity - R
label | f6c7ac08-c956-5cb3-9ea3-82b27ff339de |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.16 - Running Course
label | 6ddc7923-4ea0-538c-ae2e-d8a58e7ee576 |  | note | Acceptance / Conformance Criteria - If running course is used it shall be spread uniformly over the pavement surface and maintained until removed. During working hours traffic shall be channelised by suitably defined traffic lanes with frequent transverse shifts of the defined lanes to obtain an even spread of traffic over the entire surface.
label | 97ad3067-b7f0-5183-9345-e0fee5d98b01 |  | note | Standard / Specification - TNZ B/02: 2005 - 10.1
label | 02bd5c5e-5d29-59e1-8ff6-cae122d46f05 |  | note | Verifying Document - Site Notes
label | f865adc9-6ac9-5412-824c-c1bc4657fe59 |  | note | Frequency - Prior to sealing
label | 4f958e86-7437-5460-81fa-2c20b405c6af |  | note | Activity - S
label | 307c7f07-0e69-5b30-9a9c-742cac6987f0 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 3.01.17 - Surface Finish post sweeping
label | 79301678-cdc5-526b-92a5-ec40a58b15ca |  | note | Acceptance / Conformance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
label | f1193419-55d8-5a46-bbc4-268999939f01 |  | note | Standard / Specification - TNZ B/02: 2005 - 7.8
label | 2c5eaac8-6be2-5db5-9e07-971bcecf801f |  | note | Verifying Document - Photos
label | f4da713c-d90c-560a-bec2-643d270444e3 |  | note | Frequency - Prior to sealing
label | 06cb4779-3c73-5927-bd81-50253589081b |  | note | Activity - R
label | 650e5f29-2aab-5136-a6e5-352e41824e4c |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.18 - Tie in into Existing Pavement
label | e47c839e-10ab-52bc-9da5-4b3f5302db06 |  | note | Acceptance / Conformance Criteria - Where tapering of basecourse including finishing layer aggregate is necessary to provide a smooth transition from the new surface to an existing surface, placement of the basecourse or finishing layer shall be stopped at the minimum uncompacted thickness specified in clause 7.3(a).
label | f49955e8-2930-5eaa-8fff-4aa29fef0f12 |  | note | • The Contractor shall then saw cut the existing seal at the tie-in (end of taper), remove existing pavement material and replace it with approved basecourse to an average uncompacted thickness of greater than 2.5 times the maximum particle size of the basecourse used.
label | 79ff790a-0eb1-5f0b-bdb3-8bd78d10ad67 |  | note | Standard / Specification - TNZ B/02: 2005, 7.4
label | 29ad3d21-5e2a-5945-88fa-8b02f6537760 |  | note | Verifying Document - photos, and survey data of undercut
label | bd7ebd18-69e0-5efd-ba7c-bb5f6c987414 |  | note | Frequency - Every tying into existing pavements
label | 91296060-7787-5b8d-8503-893e4f648768 |  | note | Activity - I
label | 623ed7a7-5277-5241-9051-22912d88a908 |  | note | By - SV / PE
checkpoint-group |  |  | section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint-status |  |  | checkpoint | 4.01.01 - Survey Records
label | 61996f2a-360d-58ca-b002-d0ec112979d3 |  | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and record.
label | ef33a047-ce94-5d83-9ec1-97210b4bb05d |  | note | Standard / Specification - PS - Page 42
label | 9f15b713-aa3c-537d-a7c5-4acc6e9e898e |  | note | Verifying Document - Records
label | ee3094fe-e7d2-51aa-bc36-b1fa4b41ea8e |  | note | Frequency - Post construction
label | ce7486bf-d5e6-58ba-9bf6-7f600631abc4 |  | note | Activity - H
label | beea42b2-951f-576f-9550-2639c1a409ef |  | note | By - SV
checkpoint-status |  |  | checkpoint | 4.01.02 - Redline Drawings
label | 6b4ad168-19a5-5e59-baa8-dd5981f8c644 |  | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | e38cab94-b76a-53bd-a428-60832ee679fb |  | note | Standard / Specification - Downer
label | 95e8391a-7508-5b76-8a26-3cf9c3b3a58b |  | note | Verifying Document - Redlines
label | 1808be42-969c-5144-9ffb-757393ac708f |  | note | Frequency - Post construction
label | 5e63c918-6e2f-5606-9087-3b173c5b56a6 |  | note | Activity - H
label | a8b3b982-00ae-54bb-bc28-91cd1ff00f38 |  | note | By - PE
checklist-sectioned |  |  | checklist | ITP - Utility Trench |  |  |  |  | Yes | ITP - Utility Trench | 41e0c77e-6824-42d9-a9e9-788cd01154b8
checkpoint-group |  |  | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint-status |  |  | checkpoint | 1.1 - Extent of Line Setout
label | 1a28f932-4256-53f4-8e4a-e589e1a2a356 |  | note | Acceptance / Conformance Criteria - Ensure line and level of Utility Trench has been marked out and agreed with Engineer in accordance with Utility drawings Identify any clashes before construction.
label | e9c10589-2e58-525d-9972-a8bb57e1b6ea |  | note | Standard / Specification - Design Drawings
label | 6b76dc85-10ae-5e6b-8376-49e4b134b896 |  | note | Verifying Document - ITP Sign Off
label | f9922ebe-f7cb-5b0a-a655-f0e94ea3e5ca |  | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
label | 2e5d0e79-8bb5-5576-9395-510ec96d4620 |  | note | Activity - M
label | 5de18377-15ae-5482-9288-87089e16f418 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.2 - Construction Drawings- Berm
label | c9c9b3e2-adae-50ec-9477-5b9c379c72a0 |  | note | Acceptance / Conformance Criteria - Provide full construction drawings as agreed upon by the Service Providers including agreed Cross Sections
label | 71ffa5a0-dba5-5cd6-b388-7cab3c17f796 |  | note | Verifying Document - Drawings
label | 2733522c-3170-5982-8f04-83454cbef071 |  | note | Frequency - Prior to Construction
label | 37adc687-791d-597c-82ea-c0f3e6523730 |  | note | Activity - HP
label | 7b80468f-df7b-5bd0-84ed-190a83d4d579 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Construction Drawings-Road Crossings
label | 6ef1f90b-a514-5f74-b178-c3ca3c76b3e8 |  | note | Acceptance / Conformance Criteria - Provide agreed upon Cross Sections from Utility Providers for any road crossings
label | 38a47eff-b723-55d6-88ac-a60f6c7ce80b |  | note | Verifying Document - Drawings
label | b36b68dd-ccb3-53ac-8fb5-241006f9ff6c |  | note | Frequency - Prior to Construction
label | 0ddb8441-3937-525c-b62d-749ce21e391e |  | note | Activity - HP
label | cf0b9879-0582-5b3a-8fce-3437eb240640 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.4 - Environmental Protection
label | 9e0ab3fc-be7c-5604-b9aa-51ea43847668 |  | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
label | 239d1081-6c8f-595d-9a88-e7f1a434afec |  | note | Standard / Specification - Project ESCP Plans
label | cf6fdba6-58e7-5d42-b38f-fb7593b3d6e5 |  | note | Verifying Document - ITP Sign Off
label | b1795489-b8ec-5af5-b5ef-1a9532f6c47e |  | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
label | d102b365-417e-5f88-b2d1-aaec33477065 |  | note | Activity - M
label | a19d99c5-e611-5073-bbb5-e1886d74f59e |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.5 - Stakeholder
label | 14360796-9a7b-536b-9f8d-f74126ac8feb |  | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
label | fe08ae50-bd03-5b8b-af4c-0ec7f7634f81 |  | note | Standard / Specification - Project Stakeholder Management Plan
label | b1c20ff8-3e6c-5bb7-a4f5-3e1c100216d1 |  | note | Verifying Document - ITP Sign Off
label | ab6e4055-f100-52ba-b36a-6b93a14d7954 |  | note | Frequency - Prior to Construction with continue updates throughout the works
label | e6bf2580-1570-5fc8-980e-e6aa25c9ee25 |  | note | Activity - M
label | a86c2579-b1f2-5f9c-9bcb-d8f8eaae3ae8 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.6 - Permits
label | 02ae71fd-9fe0-5153-96f8-7431f8b30552 |  | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
label | 419aadfe-9db5-5cad-ab0f-e9876ebf69cc |  | note | Standard / Specification - Section 2.2.10 Project Specification
label | 3765baed-457c-5b64-bc01-9488eff7b0d3 |  | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
label | c5994fec-79d5-5e19-a835-51e8ca8c6f6a |  | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
label | 78f32b25-1076-51a0-bc10-c820e2403e07 |  | note | Activity - H
label | 7bc7f061-bae2-50e5-8dd1-9fa1f9851eeb |  | note | By - PE
checkpoint-group |  |  | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint-status |  |  | checkpoint | 2.1 - Duct Bedding
label | 444cf632-a93a-5dcf-8297-b82fca3ec4eb |  | note | Acceptance / Conformance Criteria - Confirmation from service providers on bedding and shading material required
label | 0a3b0101-aa8a-5c69-b05a-20ad1f3e289a |  | note | Standard / Specification - Section 10 PWRBSS Project Specification Sand from Source Specified by WEL
label | 0a0c45ef-ce6f-5ab7-ac13-38b2bd1fbf36 |  | note | Verifying Document - Delivery Dockets
label | eca7e6d9-795a-56ac-a05d-de5961e268bb |  | note | Frequency - Every Delivery
label | 52e259fc-94fa-5ac2-9e2c-b3df15087154 |  | note | Activity - S
label | ad6978ac-eb7d-5a81-9185-88b267694f46 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 2.2 - Trench Backfill
label | 07df4993-1ad4-5481-be9e-9f3c64467672 |  | note | Acceptance / Conformance Criteria - Native soil backfill must have no stones or "hard clods" of cohesive material. Max clod or particle size to be 7mm. Trench Backfill material in carriageway to be Pit Sand
label | 9a606214-ee38-5637-808b-5b1d731ea7f1 |  | note | Standard / Specification - Section 10 PWRBSS Project Specification Utility Company Requirements
label | f299d433-7a82-57f0-9b2b-4a356b15b9d2 |  | note | Verifying Document - Visual Inspection/Pictures PSD and MDD
label | b9de21f8-0904-58d5-bdd1-49c59ed61c4b |  | note | Frequency - Ongoing
label | 57b53d57-cfee-5dc1-bf7f-e32d3bdac779 |  | note | Activity - S
label | 032bb84e-ae4f-5361-bcdd-2c3971ef799d |  | note | By - PE
checkpoint-status |  |  | checkpoint | 2.3 - Duct / Pipe Material
label | 7d4133ae-1b6d-5113-bba3-97d11bb91482 |  | note | Acceptance / Conformance Criteria - Obtain duct / pipe from Utility Provider Confirmation required from service providers on ducting size
label | e47d48e4-9a8f-51e4-9cf7-8232d79733a3 |  | note | Standard / Specification - Section 10 PWRBSS Project Specification Utility Company Requirements
label | 392046a7-d9f1-57a5-9b4e-c6e930e9cf30 |  | note | Verifying Document - Delivery Dockets Email
label | b27fdf1a-8714-5c7e-9bae-2d1a3bb916ee |  | note | Frequency - Every Delivery
label | 6e1de9e2-2fae-50c3-91eb-57f984033568 |  | note | Activity - S
label | 750b4f6a-4226-5ce1-9da0-1ae038b7496f |  | note | By - PE
checkpoint-status |  |  | checkpoint | 2.4 - Warning Tape & Mag Slabs
label | 9c3d76f2-41f7-503f-a557-e5bbadbf185b |  | note | Acceptance / Conformance Criteria - Obtain warning tape and mag slabs from Utility Provider Confirmation required from service providers if mag slab and warning tape required.
label | b6618b37-a549-587e-909a-3b5acb2a9649 |  | note | Standard / Specification - Section 10 PWRBSS Project Specification Utility Company Requirements
label | e05cabbd-4118-5782-b951-d4bf9879d825 |  | note | Verifying Document - Delivery Dockets Email
label | 51cbeb2d-7cb7-5b8b-9128-aceabf5907bf |  | note | Frequency - Every Delivery
label | 89bc29c9-bdaa-5beb-ac6a-0ce5218ed3b4 |  | note | Activity - S
label | bffc547a-b7af-5006-b596-c230ed7ea3ad |  | note | By - PE
checkpoint-group |  |  | section | SECTION 3 – CONSTRUCTION ACTIVITY
checkpoint-status |  |  | checkpoint | 3.1 - Excavate trench
label | ca5b4c07-7b26-58ec-ba8e-30c9c2f74bdc |  | note | Acceptance / Conformance Criteria - Excavate trench and stockpile excavation arisings. Visual inspection of excavation arisings to identify presence of stones / hard clods. Inspection of formation to identify any soft spots.
label | a6c1f659-2ed7-5ca7-8ada-98099357c35c |  | note | Standard / Specification - Section 10 PWRBSS Project Specification
label | 030fc257-bb20-5c49-9ba8-25b478c38139 |  | note | Verifying Document - Visual Inspection
label | 54c76830-99fb-5518-a371-d7df97efb890 |  | note | Frequency - Ongoing
label | 13c504a9-9d2e-59df-a4fe-9fd8e57becc8 |  | note | Activity - S
label | 24b694bf-079e-5b4b-aade-5cb8aabf0dd2 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.2 - Install duct bedding
label | bf7a3739-d868-5588-adfc-63ab2de93d47 |  | note | Acceptance / Conformance Criteria - Place sand as per WEL detail
label | 4cd8021f-35cc-5a06-8c06-546e4132a1c8 |  | note | Standard / Specification - Section 10 PWRBSS Project Specification
label | 5d1f8269-de16-50bb-93ad-32496650b741 |  | note | Verifying Document - Visual Inspection/Pictures
label | b6b588eb-42b6-5e62-bb33-90827527af43 |  | note | Frequency - Ongoing
label | f377a399-92d5-51f0-8583-1b5c7d72033a |  | note | Activity - S
label | e861d23c-8062-5427-9707-75cd0a76d49c |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.3 - Install Ducts
label | 4dbc32a3-b84a-57dc-98da-5b40b9cdc1ed |  | note | Acceptance / Conformance Criteria - Place ducts to line and level shown on design drawings and in accordance with utility provider requirements
label | 94ce0b08-8205-5e0b-9ca0-2c97f41808fd |  | note | Standard / Specification - Section 10 PWRBSS Project Specification
label | 0c88a5ba-a134-5101-be66-0dc602cf86c9 |  | note | Verifying Document - Visual Inspection/Pictures
label | f9e36f3c-7cda-58c6-b1eb-647e8e775764 |  | note | Frequency - Ongoing
label | 0e569a63-4871-5955-ac8a-8f07b69bbdca |  | note | Activity - S
label | 34c4bae7-851e-5b52-b133-97f0373851af |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.4 - Install Draw Cord
label | 0a01dc1d-d4f5-5798-a683-21f160cd883b |  | note | Acceptance / Conformance Criteria - Install draw-cord to all service ducts
label | f175bd4a-e569-5d92-9fc3-a56848ca48a2 |  | note | Standard / Specification - Section 10 PWRBSS Project Specification
label | bf41177c-6e86-51de-a70c-c6eabc8f7ab2 |  | note | Verifying Document - Visual Inspection
label | c4efeddb-335e-5891-8d8b-5df5424422bb |  | note | Frequency - Ongoing
label | 10573828-9cb6-5e52-bb4a-18e93abfa6c4 |  | note | Activity - S
label | 70b47ba3-6fd1-5144-ac39-447299d2bd92 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.5 - Install End Caps
label | 57fa27a2-c6e1-5cbb-a097-a1b24f08367a |  | note | Acceptance / Conformance Criteria - Install end caps to all service ducts
label | 414df3a8-84ae-55f3-a017-17db6429d45e |  | note | Standard / Specification - Section 10 PWRBSS Project Specification
label | a5269469-2d07-5dc2-b6d6-15cfcc39f1e9 |  | note | Verifying Document - Visual Inspection/Pictures
label | 73ed089c-7649-5cf9-961d-b714e30a0b87 |  | note | Frequency - Ongoing
label | 0520f1ba-2c93-5c96-90f4-c80216482e42 |  | note | Activity - S
label | 8a792c63-b312-51df-98e4-7e2a75391244 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.6 - Backfill
label | bbb881e7-094f-52af-b460-4c169d175b2d |  | note | Acceptance / Conformance Criteria - Backfill and compact with selected native soils (no stones or hard clods, max. size for all soil particles and clods is 7mm) Photos of Ducts prior to backfill
label | 43072781-cf7a-5067-9ddc-f430181c43a6 |  | note | Standard / Specification - Section 10 PWRBSS Project Specification
label | e4f7f5f6-b92b-598c-adde-b645857dd598 |  | note | Verifying Document - Visual Inspection/Pictures
label | 05313ce5-ff97-53c7-b1db-5149e5ba6337 |  | note | Frequency - Ongoing
label | 4c778149-df86-58c7-8eb9-b90d6215b157 |  | note | Activity - S
label | 7ef44f1e-7e46-58ed-9701-946cc3f3d646 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.7 - Install Warning Tape & Mag Slabs
label | 65648a43-d930-5e62-88da-60fdb6a41ae2 |  | note | Acceptance / Conformance Criteria - Install warning tapes and mag slabs to all service ducts Photos of Warning tape and Mag slabs prior to backfill
label | 392f46e7-9361-55a4-8f16-be0ab5d8df21 |  | note | Standard / Specification - Section 10 PWRBSS Project Specification
label | a14c3b49-d5b2-5308-b18b-4cddf0ccc8d5 |  | note | Verifying Document - Visual Inspection/Pictures
label | 239154e0-ed43-5bed-9b58-d0a1ba786e8e |  | note | Frequency - Ongoing
label | ce322fe5-f01b-5aa5-bf30-385cf6d073be |  | note | Activity - S
label | 036e7290-08e0-5af2-9c6e-81b10789df74 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.8 - Trench Backfill (Berm)
label | 86af2f05-aa5c-594a-9055-664c4f903fdf |  | note | Acceptance / Conformance Criteria - See below:
label | d991b9d2-a7a6-5c6d-887a-79eccf1f91dd |  | note | LOCATION: Within Road Corridor - SIL or within 1m of the base of SIL (Subgrade fill) GRANULAR FILL: NDM: 98% MDD; Scala: 5blows/100mm COHESIVE FILL: N/A
label | 369ca596-9790-56c1-81f9-b5d09e93136f |  | note | LOCATION: Within Road Corridor - Deeper than 1m below base of SIL (Bulk fill) GRANULAR FILL: NDM: 95% MDD; Scala: 4blows/100mm COHESIVE FILL: Air Voids: Average 10%, single maximum of 12%; Sheer Vane: Average 120kPa, minimum single value of 110kPa
label | ff0b27e4-8370-58f4-b3f7-a401b25883ca |  | note | LOCATION: Berm - Beneath Footpath GRANULAR FILL: NDM: 98% MDD; Scala: 4blows/100mm COHESIVE FILL: N/A
label | 8ef1d158-2321-53f9-8cf5-5cf3dda02a5d |  | note | LOCATION: Berm - Outside of Footpath GRANULAR FILL: Scala: 3blows/100mm COHESIVE FILL: Sheer Vane: 70kPa
label | a7340a2f-39c2-5ba7-9532-124d4fd062fd |  | note | Standard / Specification - As Per General Correspondence from BBO GCO-0072
label | f2bc8c5d-8642-5678-8ec5-0cbfee46ce3a |  | note | Verifying Document - Testing Reports
label | 6d793839-d120-54e1-972d-352b30dd00f2 |  | note | Frequency - every 20m along trench 1 test every 5m² at driveways and footpaths
label | df92b3d8-9c08-5c78-b7ec-7c40c1d9e38c |  | note | Activity - S
label | 441fb3cf-2c66-5172-a6c7-eff8dcaebfdc |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.8 - Trench Backfill (Road Crossings)
label | e3069caf-ac7b-5938-ba5e-b7af23e05ba1 |  | note | Acceptance / Conformance Criteria - See below:
label | 64f5a35a-24fd-5b65-982e-293bb7ab9d3b |  | note | LOCATION: Within Road Corridor - SIL or within 1m of the base of SIL (Subgrade fill) GRANULAR FILL: NDM: 98% MDD; Scala: 5blows/100mm COHESIVE FILL: N/A
label | f971f735-834e-5f57-8210-d3aac1ebf2ae |  | note | LOCATION: Within Road Corridor - Deeper than 1m below base of SIL (Bulk fill) GRANULAR FILL: NDM: 95% MDD; Scala: 4blows/100mm COHESIVE FILL: Air Voids: Average 10%, single maximum of 12%; Sheer Vane: Average 120kPa, minimum single value of 110kPa
label | df159860-a002-5dfa-9c42-f60ca8545b9f |  | note | LOCATION: Berm - Beneath Footpath GRANULAR FILL: NDM: 98% MDD; Scala: 4blows/100mm COHESIVE FILL: N/A
label | 15dbe736-f4fd-56c3-a62e-04748e3b5a7e |  | note | LOCATION: Berm - Outside of Footpath GRANULAR FILL: Scala: 3blows/100mm COHESIVE FILL: Sheer Vane: 70kPa
label | 646446e1-42ed-5641-a553-f997e0b07cc9 |  | note | Standard / Specification - As Per General Correspondence from BBO GCO-0072
label | 2ec6e3f8-a1fc-524a-a509-fadacc262ad6 |  | note | Verifying Document - Testing Reports
label | 6c48dc5d-c3a7-5239-b270-9c799050ad89 |  | note | Frequency - Every 10m along trench
label | 7fd95c35-09f9-51fa-a8e9-e81c379639ac |  | note | Activity - S
label | b919f3fd-1dcd-5342-9a40-fca4b36e9f95 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.9 - Install Service
label | 33c58a5f-ead1-560e-8234-9fd01dd58d82 |  | note | Acceptance / Conformance Criteria - Services installed in ducts by Utility Providers
label | 8fa09378-46fa-56da-8ea1-8e25e99b2856 |  | note | Standard / Specification - Performed by Utility Provider under their QA / QC Systems and Controls
label | 7b2545f6-36ec-50af-8442-0d8dbe9ae8d6 |  | note | Verifying Document - N/A
label | d067f1f0-dadd-52cc-a908-8dca32195346 |  | note | Frequency - N/A
checkpoint-status |  |  | checkpoint | 3.1 - Reinstate
label | ae1b20e6-8844-5778-baf8-35d5bf01eff6 |  | note | Acceptance / Conformance Criteria - Reinstate and tie-into to existing surrounds
label | 9acb322c-e4b7-59ea-b319-1e3c41a5b5ca |  | note | Verifying Document - Visual Inspection/Pictures
label | f9b96b11-ccf2-5513-84d7-cc0dd1d0061e |  | note | Frequency - Upon Completion of Each Section
label | fc9bc56e-4c60-5d68-8bdd-8768a6bfe8f6 |  | note | Activity - S
label | 10383bc4-81b4-5272-bad5-9684ca75a2d1 |  | note | By - PE
checkpoint-group |  |  | section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint-status |  |  | checkpoint | 4.1 - Survey As-Builts
label | dc1c3dda-d46d-5493-83a4-ed992a74c7eb |  | note | Acceptance / Conformance Criteria - GPS Survey of every joint in every duct / 6m centres on continuous pipe. Survey point naming protocols to be agreed between subcontractor and Downer Survey Manager. Draft As Built Drawings. Photograph of formation, all ducts immediately before backfill, warning tape / mag slabs immediately before backfill.
label | f81e2f98-ab70-599e-8fab-14dd0ea09089 |  | note | Standard / Specification - Section 2.2.17 PWRBSS Specification
label | a7188ac8-db8a-5504-857c-c81ffc2501cc |  | note | Verifying Document - Survey Data As Built Drawings Photographs Red-Pen Asbuilt including Undercuts/Any changes from original design, including any change in road crossing locations
label | f73d8d9f-3c77-58f6-b89a-f0b8d113ae6f |  | note | Frequency - Post works completion
label | 377e2c0a-cce7-5704-877f-d5cfb42a2d24 |  | note | Activity - H
label | b9d2b744-054c-52aa-b0ca-673b30e6246e |  | note | By - SV
checklist-sectioned |  |  | checklist | ITP - Piling | itp |  |  |  | Yes | ITP - Piling | 5005b436-682d-4485-80e7-3dcfaa4b8b14
checkpoint-group |  |  | section | 1.0 Pre-Construction
checkpoint-status |  |  | checkpoint | 1.1 - Accepted Method Statement
label | 62f24d58-7b8d-5c3c-877a-87b9c30bd50d |  | note | Standard / Spec Reference - Project specification
label | a0b5d7c8-4a0d-5607-8b54-315563f25d70 |  | note | Acceptance Criteria - Engineer’s acceptance
label | 28af8229-fd5f-5619-8cd4-8a74166f2400 |  | note | Frequency - Once prior to commencement of piling
label | cdf61e20-5f96-5025-bb8b-a720e08c10d0 |  | note | Responsibility - CLL
label | 42dbd898-35a4-5d93-9470-cbe81a90cfc2 |  | note | Hold Point H/W/S - DO: H
label | a1ec3af8-c244-5f77-86b8-956c98095f24 |  | note | Hold Point H/W/S - BBO: H
label | 70b032bf-215e-54b0-aa18-0d92e380695b |  | note | Hold Point H/W/S - CLL: H
label | 3c8ff899-625e-54c0-8499-92db7435fcbc |  | note | Verifying Record - Email Confirmation
label | 4a44b871-e815-52b1-ad16-4142fb42906c |  | note | Comment - To be submitted at least 10 days in advance.
holdpoint |  |  | signoff | HOLD POINT (DO/BBO/CLL)
checkpoint-status |  |  | checkpoint | 1.2 - Accepted Inspection and Test Plan
label | 2ce3b27d-4838-5fdf-8ea1-5777c3137557 |  | note | Acceptance Criteria - Issue
label | 06dee5e8-d630-5c38-8931-a607754c1810 |  | note | Frequency - Once prior to commencement of piling
label | dc72a423-376b-5cae-937b-223b0a105f3c |  | note | Responsibility - CLL
label | 0c173d62-8c26-58af-a7a3-39f4347d19c7 |  | note | Hold Point H/W/S - DO: H
label | 3df5f23f-af35-55a9-9587-e32a590ad958 |  | note | Hold Point H/W/S - BBO: H
label | 5f9fee3e-3c65-5efa-9192-259130cafef3 |  | note | Verifying Record - Email Confirmation
holdpoint |  |  | signoff | HOLD POINT (DO/BBO)
checkpoint-status |  |  | checkpoint | 1.3 - Accepted Safety Plan - SSSP
label | ff600164-3277-50b6-94a3-86ea098289f5 |  | note | Acceptance Criteria - Issue
label | 06052266-f1f1-54b6-a031-cb2d8e0c405d |  | note | Frequency - Once prior to commencement of piling
label | bf30a35e-ff8b-5b6f-9447-5647b88ecdf7 |  | note | Responsibility - CLL
label | 97ebb5fd-1f19-5b3e-8f91-58c1104c5a15 |  | note | Hold Point H/W/S - DO: H
label | eca49034-bb54-5944-af21-bcd279d2168a |  | note | Verifying Record - Email Confirmation
holdpoint |  |  | signoff | HOLD POINT (DO)
checkpoint-status |  |  | checkpoint | 1.4 - Accepted support fluid details
label | 9d9e6f8d-9bfd-52de-bbdc-1f7f1dc34fce |  | note | Acceptance Criteria - Issue
label | 841f33af-4eb0-587a-88aa-b73cd866eb6d |  | note | Frequency - Once prior to commencement of piling
label | d5496b4c-34d2-531a-beb3-ae08c31d0301 |  | note | Responsibility - CLL
label | f3f25f47-92c5-56a5-b797-8c25e7eca7f7 |  | note | Hold Point H/W/S - DO: H
label | 1aee7c34-a76d-50c3-8ffa-ed0ce8228d6c |  | note | Hold Point H/W/S - BBO: H
label | 44f5d988-5199-51e2-bc00-c0aa67df1d6b |  | note | Verifying Record - Email Confirmation
holdpoint |  |  | signoff | HOLD POINT (DO/BBO)
checkpoint-status |  |  | checkpoint | 1.5 - Permits issued
label | 33d41727-c9f2-5083-9bd9-49bba94dbb0e |  | note | Acceptance Criteria - Issue
label | 4c345aab-e5df-5b13-a11f-0b728c28b7e9 |  | note | Frequency - Once at commencement of piling
label | fb36ee4d-02af-585e-889c-13435199ceda |  | note | Responsibility - DO
label | 439a55e4-8990-5dd9-9727-13cdb6f987e9 |  | note | Hold Point H/W/S - DO: H
label | 57a2c843-280f-5427-9e97-d1a4df1a33ad |  | note | Hold Point H/W/S - CLL: H
label | 296af5e8-e172-5439-9015-be08147b2c9c |  | note | Verifying Record - Site Hardcopy
holdpoint |  |  | signoff | HOLD POINT (DO/CLL)
checkpoint-status |  |  | checkpoint | 1.6 - Concrete Design Mix Verification
label | 9fe70b6a-6f02-56e1-bb40-4a94473b735a |  | note | Acceptance Criteria - Issue
label | 9cc52df2-2af2-5401-94e7-bf56e94fb584 |  | note | Frequency - Once prior to commencement of piling
label | 942686fb-326b-5357-831a-0ea14c4b61de |  | note | Responsibility - DO/BBO
label | 7ad59786-5dd0-52fd-81bf-5124f748ce8f |  | note | Hold Point H/W/S - DO: H
label | 7a6a55e0-45ce-557d-9deb-ec74e6509fef |  | note | Hold Point H/W/S - BBO: H
label | 6882a143-762d-5a98-8b9f-902ff910d6af |  | note | Verifying Record - Email Confirmation
holdpoint |  |  | signoff | HOLD POINT (DO/BBO)
checkpoint-status |  |  | checkpoint | 1.7 - Reinforcement Steel – mill cert
label | f6de07d6-4d18-5c75-81da-f08f6fb541bd |  | note | Acceptance Criteria - Project specification
label | 141b17c5-9fc2-586b-9410-b96125cc12a9 |  | note | Frequency - Post Construction for every pile
label | b80a6d66-54c7-55bd-95eb-f59fff342051 |  | note | Responsibility - CLL
label | cad41ae2-3493-53ae-b614-f1959efe03f1 |  | note | Hold Point H/W/S - DO: H
label | d26751fd-462b-5396-a946-21163b38326a |  | note | Hold Point H/W/S - BBO: H
label | 02860350-2e3b-59fb-83e4-62c11e383e7e |  | note | Verifying Record - Issued by supplier - email confirmation
holdpoint |  |  | signoff | HOLD POINT (DO/BBO)
checkpoint-group |  |  | section | 2.0 Pile Boring
checkpoint-status |  |  | checkpoint | 2.1 - Client Notification
label | 127d74af-39ee-57b4-a28a-8cf89457a511 |  | note | Acceptance Criteria - Issue
label | 49626cce-3ba4-5b4b-8e30-da4c6b2583bc |  | note | Frequency - Once at commencement of piling
label | 17ffa176-be6e-5b07-ba5c-b7dd57754998 |  | note | Responsibility - DO
label | 130ab38d-2a4f-5193-a58a-f7e4a2988b03 |  | note | Hold Point H/W/S - DO: H
label | f3b265fb-d836-5d1f-8d1c-866a9f0de264 |  | note | Hold Point H/W/S - BBO: H
label | 21e632d0-2534-530c-871b-2a9bdf651709 |  | note | Hold Point H/W/S - CLL: H
label | 77455024-dec7-509f-b8d8-de5cf34c0984 |  | note | Verifying Record - Email Confirmation
label | fdb7c117-096d-5971-a534-fcbd3b2e8936 |  | note | Comment - 48 hours’ notice of pile drilling commencement.
holdpoint |  |  | signoff | HOLD POINT (DO/BBO/CLL)
checkpoint-status |  |  | checkpoint | 2.2 - Check drill tool diameter
label | d89977b4-e455-589d-bda2-95d41c40471b |  | note | Standard / Spec Reference - As per HCC 1298/2022
label | 02263750-9fb4-5713-9e34-ab9cc0be1904 |  | note | Acceptance Criteria - Visual Inspection
label | 84df2b0a-dbe3-594f-aad1-ec57437387ad |  | note | Frequency - Prior to commencement of piling
label | 6df99fc9-0967-5811-acba-87a73fc2c335 |  | note | Responsibility - CLL
label | 2933e753-6f07-5d06-8e7a-e42ae959ac36 |  | note | Hold Point H/W/S - DO: W/S
label | 393df755-3739-5884-9e6c-94e1f8fadaea |  | note | Hold Point H/W/S - CLL: W/S
label | 0d6ee654-a922-56c2-8592-9d75ffecf944 |  | note | Verifying Record - As per pile QAC
label | 6d6df6d9-b3b8-519c-b879-061a4b65ada3 |  | note | Comment - Minimum agreed diameter is 870 mm for 900 DIA piles, due to ID of permanent casing supplied by DO, and 1200 mm for 1200 DIA piles.
checkpoint-status |  |  | checkpoint | 2.3 - Check depth gauge/instrumentation of piling rig
label | d6a54a60-5171-50d0-a2fb-bbf927dcb062 |  | note | Standard / Spec Reference - Operators Manual
label | 065bc6b8-60ce-578b-af89-e217a11acdcb |  | note | Acceptance Criteria - Visual Inspection
label | a2d08314-7d81-5714-80c3-c8f1bc580566 |  | note | Frequency - Daily
label | db42a45b-c24c-5d96-bbde-0abc33e268e1 |  | note | Responsibility - Rig Operator
label | 99da9c5d-0d27-543e-a1bf-2f05b9b06576 |  | note | Hold Point H/W/S - DO: W/S
label | 740ec1ab-51f6-5ac2-900f-93198bfac9d9 |  | note | Hold Point H/W/S - CLL: H
label | a31142ee-a7b2-52b4-972f-ffc06e078136 |  | note | Comment - Operator daily checks
holdpoint |  |  | signoff | HOLD POINT (CLL)
checkpoint-status |  |  | checkpoint | 2.4 - Ground penetration and extraction with due diligence
label | f8c37aee-8bcf-566e-a8f8-a9904e57e933 |  | note | Standard / Spec Reference - Operators Manual
label | 8d566718-caad-5858-81ad-cc6ea83eaf2d |  | note | Acceptance Criteria - Visual Monitoring
label | 0a48287b-b7a0-5a5f-9fa3-bc09c323b0aa |  | note | Frequency - Every Pile
label | 356f007f-dde7-5250-8a44-73fe0a500963 |  | note | Responsibility - Rig Operator
label | ee6e25eb-084a-523b-9584-20acecc2b8e1 |  | note | Hold Point H/W/S - DO: W/S
label | b3f2d9ff-8a74-5efe-9170-f5230537c108 |  | note | Hold Point H/W/S - BBO: S
label | 8886fd93-785d-5ce6-9209-95c655a90763 |  | note | Hold Point H/W/S - CLL: S
label | ea32cdba-2701-54b6-9e29-f89140d2a1e9 |  | note | Comment - Operator to penetrate/extract with due diligence, no adverse effect on bore integrity.
checkpoint-status |  |  | checkpoint | 2.5 - Check pile position/pile numbers
label | cc8a5683-4085-548b-a06d-f7650d7005d9 |  | note | Standard / Spec Reference - Drawings
label | 92a5ffa7-ae71-57cc-85b8-cffec705debf |  | note | Acceptance Criteria - Visual Inspection
label | 2cef91b0-b80f-5093-8153-34079e147fb8 |  | note | Frequency - Every Pile
label | 476f8d0a-1369-57ff-88e7-0f0ac2ec346e |  | note | Responsibility - CLL
label | ed3b6a51-fe04-5388-8892-b10ac93febc3 |  | note | Hold Point H/W/S - DO: W/S
label | c59e9228-3d42-55b0-a461-1f58e181c916 |  | note | Hold Point H/W/S - CLL: W/S
checkpoint-status |  |  | checkpoint | 2.6 - Pile Setout/Offsets
label | 5265d5f9-82d3-5dd6-9a58-f8eff57c8283 |  | note | Standard / Spec Reference - Drawings
label | f24a2128-74bc-5847-8af6-c497eeafbfa7 |  | note | Acceptance Criteria - Hz +/- 10mm
label | 7c7906c8-387d-5188-9b49-236c00fa0047 |  | note | Frequency - Every Pile
label | 8e098ff8-97b2-5f13-ab15-adcf0b176acb |  | note | Responsibility - DO
label | 84f8b9a2-ac2c-5ebd-a7ca-4c37f2f7bdb6 |  | note | Hold Point H/W/S - DO: W
label | 00f62530-9241-5485-bf60-6e174363a69d |  | note | Hold Point H/W/S - CLL: W
label | d425f2f4-e41d-532b-b7f6-71474f6300f4 |  | note | Verifying Record - Survey record
label | d29e8f1c-a503-5d7b-a47b-10953ba557eb |  | note | Comment - Due to tight plan tolerances set-out is critical
checkpoint-status |  |  | checkpoint | 2.7 - Casing Inspection
label | b1d70420-7211-5b5d-a523-795c11cee7fa |  | note | Standard / Spec Reference - As per HCC 1298/2022 – note minimum agreed diameters at ITP item 2.2
label | 2a09fa2c-6c38-537f-88a4-0b7f4d770363 |  | note | Acceptance Criteria - Visual Inspection
label | 1e31b424-6d87-54fe-95c5-21c32676d495 |  | note | Frequency - Length/diameter/Wall thickness at start of piling, RL every pile
label | 19666f1f-b9e2-5641-93d7-5a1a94cf3d38 |  | note | Responsibility - CLL
label | d7248886-5235-5b47-938a-355fca0b2588 |  | note | Hold Point H/W/S - DO: H
label | 27468874-90c7-5246-bae6-faccfa31dcab |  | note | Hold Point H/W/S - CLL: H
label | a34bd4c1-a19f-5bb3-9e49-e017835f383b |  | note | Verifying Record - QAC - Pile Card
label | 3ac82270-8df9-5a7a-af3e-2ded1a6f9e18 |  | note | Comment - RL check pre-concrete & pre- drill
holdpoint |  |  | signoff | HOLD POINT (DO/CLL)
checkpoint-status |  |  | checkpoint | 2.8 - Measure and check position and verticality
label | 23eddc2e-82ab-516b-92d0-61bbdcfeecfd |  | note | Standard / Spec Reference - As per ASGPILES - Rev G
label | 38af7733-fcbe-538e-ae27-d87df6ad910a |  | note | Acceptance Criteria - Visual Inspection Permitted deviation from vertical shall be not more than 1:75 or 0.8 degree.
label | f96ea33d-aa2a-5392-8fcc-36c22987bf7f |  | note | Frequency - Every Pile
label | f89ccee3-f773-50f8-80e1-ba63b89582f5 |  | note | Responsibility - CLL
label | 1bcaf796-ce95-5492-b124-fd429a98dfdf |  | note | Hold Point H/W/S - DO: W
label | f2a11210-b84a-5872-8699-0eae8aeedcd2 |  | note | Hold Point H/W/S - CLL: H
label | 145715cb-ad7b-58c5-8371-d3a2c6719f7d |  | note | Verifying Record - QAC - Pile Card
label | 69c0eac7-e7d5-504b-aba6-266beb30f2f6 |  | note | Comment - Spirit level has a +-0.5 degree accuracy. Verticality of pile to be checked via use of electronic level on the side of the casings & against Kelly bar.
holdpoint |  |  | signoff | HOLD POINT (CLL)
checkpoint-status |  |  | checkpoint | 2.9 - Bentonite checks
label | 062d9b9d-4b1d-56b5-9efd-059c3b888bec |  | note | Standard / Spec Reference - Fluid Specification
label | 5fe673aa-6ab8-5bb8-af0d-76175afc840c |  | note | Acceptance Criteria - Visual Inspection/Testing
label | 86b6f252-d5b4-5f79-80ac-39e90ae7c1b9 |  | note | Frequency - Per batch, each pile prior to concreting
label | dc20cc6e-41b5-5948-a9f3-0d2a2b13cefa |  | note | Responsibility - CLL
label | 4d57e3db-de1d-56e9-9095-d4f971652c07 |  | note | Hold Point H/W/S - DO: W
label | fccbd892-06f0-5f86-97c1-e84026cf31b1 |  | note | Hold Point H/W/S - CLL: H
label | 80030517-2764-5cfb-98fe-42a66de35365 |  | note | Verifying Record - QAC - Pile Card
holdpoint |  |  | signoff | HOLD POINT (CLL)
checkpoint-status |  |  | checkpoint | 2.10 - Bentonite level
label | 7110409d-ae16-5282-86de-3aa5ca979499 |  | note | Standard / Spec Reference - As per construction specification - Methodology
label | aada31d1-5145-5d1d-96f4-e39f66fd25b4 |  | note | Acceptance Criteria - Visual Inspection Bentonite head to be maintained at 0.5m above groundwater level or adjusted as required.
label | 6a7aaae7-3195-5b64-9426-50157cf84b48 |  | note | Frequency - Each pile
label | 6b92b846-b8e7-5b82-8593-683a180e5ef0 |  | note | Responsibility - CLL
label | ea1f1680-0813-5a0b-8b60-50e9e28c2657 |  | note | Hold Point H/W/S - DO: W
label | 28a4502f-6369-56c9-bf97-85320653eacf |  | note | Hold Point H/W/S - CLL: H
label | 99e7656a-56b5-587f-8b3f-d755d44ad5cf |  | note | Verifying Record - QAC - Pile Card
label | e22b5738-9a18-534e-931c-ee4065ed4aaa |  | note | Comment - Any significant fluid loss/stability will be addressed with Project Engineer.
holdpoint |  |  | signoff | HOLD POINT (CLL)
checkpoint-status |  |  | checkpoint | 2.11 - Soil logging and bagging
label | 05a5cf28-2374-5f59-9c31-3616a8a99710 |  | note | Standard / Spec Reference - As per HCC 1298/2022 11.7
label | fbd76925-eca8-59d2-a939-d88d07abe294 |  | note | Acceptance Criteria - Visual Inspection Engineer Inspection
label | 0a151c42-9cdf-530d-bee4-76c07ab75bf1 |  | note | Frequency - Every Pile
label | 7356630e-687f-5d18-a2bb-5d85ce4ea06c |  | note | Responsibility - DO/CLL
label | 1702070a-6cc6-5e5c-b0ef-d303f17de8fc |  | note | Hold Point H/W/S - DO: S
label | 643415d9-95d7-5382-a7c1-9e4fab189209 |  | note | Hold Point H/W/S - BBO: S
label | 2d8e6ed3-f642-558f-8257-536dd4a3f482 |  | note | Hold Point H/W/S - CLL: S
label | eb6034dd-7c82-5fbc-9d02-e8f393445fc1 |  | note | Verifying Record - QAC - Pile Card Labelled, bagged core samples
label | f1fdf6c2-d77c-55c9-a0ef-1e61e7398409 |  | note | Comment - Boreholes are to be continuously logged on QAC - Pile Card. Material from the base will be bagged, labelled and securely stored on site for Engineer’s inspection.
checkpoint-status |  |  | checkpoint | 2.12 - Confirmation design minimum toe depth achieved
label | f50e9dec-3595-5314-ae00-dd46e1835e51 |  | note | Standard / Spec Reference - Construction Specification/ Drawings
label | adb9a044-27ee-5b93-afda-4c2160bd656a |  | note | Acceptance Criteria - By means of weighted tape Designer Hold Point: Maximum depth exceedance
label | b0040e5d-93ff-57bb-9c57-0322b1aa89c1 |  | note | Frequency - Every Pile
label | c3fdff0a-1bf1-5832-a0cc-5d34b56ba509 |  | note | Responsibility - BBO & DO Rep/CLL
label | 545a7558-dd79-53b1-b2af-9bac40f9f4db |  | note | Hold Point H/W/S - DO: H
label | 6544d048-4b5e-57ee-9cd1-d0d118c09b42 |  | note | Hold Point H/W/S - BBO: H
label | 90620fbf-5ac0-5b79-a5c2-f951fd7f12ba |  | note | Hold Point H/W/S - CLL: H
label | 2a3ddc38-bb98-51d1-98e0-68311e26d69f |  | note | Verifying Record - QAC - Pile Card
label | 35ac5247-116a-50fd-a332-d2212b87d98a |  | note | Comment - Visual inspection not possible due to drilling under fluid. Engineer to agree correct drill depth. Designer to be notified if drilling reaches >300mm below design RL for pile toe. Maximum depth exceedance to be 40m from piling platform.
holdpoint |  |  | signoff | HOLD POINT (DO/BBO/CLL)
checkpoint-status |  |  | checkpoint | 2.13 - Base cleanliness
label | e1f9cbcd-2a01-5ebe-bb7c-269e23ae51e1 |  | note | Standard / Spec Reference - Construction Specification
label | 82257d50-4b95-5b95-9d48-328d7f1c16da |  | note | Acceptance Criteria - By means of weighted tape
label | ee5d6323-0a66-52d8-9bc0-e825aa8ff225 |  | note | Frequency - Every Pile
label | 30bdf695-1094-5aee-9fb2-eca1e3b47259 |  | note | Responsibility - BBO & DO Rep/CLL
label | 98e336f8-cdf7-55c4-b3bb-cde97b83c563 |  | note | Hold Point H/W/S - DO: H
label | c3bd29d6-5ba4-537b-bdb1-ad8279ec335b |  | note | Hold Point H/W/S - BBO: H
label | 8fbb5c9f-d190-5f21-bd03-c9ce09194916 |  | note | Hold Point H/W/S - CLL: H
label | 6457918b-7bef-52a5-b94f-5d9dd88a9dc1 |  | note | Verifying Record - QAC - Pile Card
label | 09fa7eea-a4cd-5d30-b66d-1618849fd90d |  | note | Comment - Visual inspection not possible due to drilling under fluid.
holdpoint |  |  | signoff | HOLD POINT (DO/BBO/CLL)
checkpoint-status |  |  | checkpoint | 2.14 - Pile Boring Monitoring
label | da5690c2-364c-54ba-b5bb-c44b04b0d497 |  | note | Standard / Spec Reference - Construction specification
label | a6065435-836f-5a15-8633-d9964351b9cc |  | note | Acceptance Criteria - Visual Monitoring
label | f6f28ca6-10a8-549b-888c-201999d02812 |  | note | Frequency - Every Pile
label | 3a3807e6-8ce3-5acf-97a5-9c3a73876454 |  | note | Responsibility - Rig Operator
label | 9b483e89-f254-5424-99b4-94ba331da17f |  | note | Hold Point H/W/S - DO: S
label | e4e7c507-d7e4-5582-849a-f80b0dcf2c7a |  | note | Hold Point H/W/S - BBO: S
label | 6a180e2b-611a-5e21-be53-009e8f2c2989 |  | note | Hold Point H/W/S - CLL: S
label | 6eb9b0f5-7f5c-56ba-b44b-618e668925ae |  | note | Verifying Record - QAC - Pile Card
label | 66c0ec2a-e112-57cd-bd96-8583d38bf0c4 |  | note | Comment - Depth check, possible collapse, changing ground conditions, any unexpected occurrences
checkpoint-group |  |  | section | 3.0 Pre-Pour Inspection
checkpoint-status |  |  | checkpoint | 3.1 - QA check on previous pile
label | d9ffa3b0-f2fc-5ffb-856b-d9d0845faecb |  | note | Standard / Spec Reference - Engineer Specification
label | 9a7315d4-da70-50ea-8600-34cee05752e2 |  | note | Acceptance Criteria - Client notification/Engineer’s Approval
label | dcefb148-106b-5e4f-8706-4172893e6f2c |  | note | Frequency - Every Pile Ongoing Engineer’s approval
label | e8801f3e-fb09-57f6-9efc-2d002ec58f1d |  | note | Responsibility - DO Rep/CLL
label | da467a95-7061-5faf-9080-31eea866c4a1 |  | note | Hold Point H/W/S - DO: H
label | ffd50456-cf6e-5bb2-beed-fbf83ed7e06a |  | note | Hold Point H/W/S - BBO: S
label | 66620fd5-c1e0-54d9-9de7-342197c68564 |  | note | Hold Point H/W/S - CLL: H
label | 9063f978-984c-53db-958a-bd6fe16cbb1c |  | note | Verifying Record - QAC - Pile Card
label | 91ce59a3-8964-5126-94c0-09cb8f71bdf3 |  | note | Comment - Engineer’s approval to proceed with subsequent piles
holdpoint |  |  | signoff | HOLD POINT (DO/CLL)
checkpoint-status |  |  | checkpoint | 3.2 - Reinforcement Cage inspection/ check spacers, pile bore tolerances
label | 32332388-f3b4-55a2-9d5c-c08b1c59ed2c |  | note | Standard / Spec Reference - BBO SS 2110 Rev 9
label | 48b7e1b9-800d-56cf-83a8-c0e4f9770b27 |  | note | Acceptance Criteria - Alignment lesser of +- 4% DIA or +-75mm
label | d5540b5f-3471-5520-9228-6539eb73f067 |  | note | • Height +- 50mm
label | e72c4a70-0261-5b44-9219-ded85717bbf0 |  | note | • Reinforcement Type- As per drawings
label | 553844e0-efd1-5c21-8bfe-bf0e46735eb0 |  | note | • Concrete cover: 75mm, 50mm minimum
label | ec2f10f5-139d-59cd-ad7c-18817e2a9d83 |  | note | • Bottom of pile position lesser of +-1% pile length, +-12.5% of shaft diameter, or +-400mm
label | 0377f0a6-1588-5155-80df-064446b2858d |  | note | Frequency - Every Pile
label | b2c5375a-93e3-5631-bb55-b566d619b2bf |  | note | Responsibility - DO Rep/CLL
label | edc040f2-1b2a-5360-b2fe-f9d6b91be355 |  | note | Hold Point H/W/S - DO: H
label | c2ad4d47-631d-5ab3-8369-f005614c714b |  | note | Hold Point H/W/S - BBO: S
label | 08169f5b-32ca-5a6d-9a2f-c323e831759d |  | note | Hold Point H/W/S - CLL: H
label | b7c36495-da2e-5fca-ba1f-b0783430ad08 |  | note | Verifying Record - QAC - Pile Card
label | 818a252f-b1d9-5349-a139-880703f85f88 |  | note | Comment - Pre-installation check required of all pile sections
holdpoint |  |  | signoff | HOLD POINT (DO/BBO/CLL)
checkpoint-status |  |  | checkpoint | 3.3 - Stabilising Fluid Verification
label | 5db9a565-4b7d-520a-ab7a-5002ffb8ec92 |  | note | Standard / Spec Reference - Construction Specification
label | 61003af8-6099-572f-878d-f618d906d86a |  | note | Acceptance Criteria - <4% sand content acceptable
label | 96895dee-5600-5b2f-899a-5649edfadb0d |  | note | Frequency - Every Pile
label | 1b730cb4-d0e4-5279-aabd-d0ae4e97bf0c |  | note | Responsibility - DO Rep/CLL
label | 5d5d8ccd-c809-5a56-b041-88f09e37347a |  | note | Hold Point H/W/S - DO: H
label | abe3398c-d030-5b8b-89e8-32292c3e894f |  | note | Hold Point H/W/S - BBO: S
label | 17422081-e128-5f7e-af79-f85ad3432e47 |  | note | Hold Point H/W/S - CLL: H
label | e042cbd3-73aa-5b5d-a1bf-188e90bb416b |  | note | Verifying Record - QAC - Pile Card
holdpoint |  |  | signoff | HOLD POINT (DO/CLL)
checkpoint-status |  |  | checkpoint | 3.4 - Pile cage installation
label | c14f16e2-c6e0-5fe2-9a6a-c08be4f34bed |  | note | Standard / Spec Reference - BBO SS 2110 Rev 9
label | a366130f-a6ec-5928-b165-74f227cf6450 |  | note | Acceptance Criteria - Engineer Inspection
label | 2f85f743-0569-5391-804e-03a846d65820 |  | note | Frequency - Every Pile
label | 2ffb28ec-ad8b-5994-8c3c-8cd898a3b850 |  | note | Responsibility - BBO/CLL
label | d2f62d4b-a998-5546-84f9-cfe0f3c21dc2 |  | note | Hold Point H/W/S - DO: H
label | c4c98d6c-9521-536c-9071-c2245c4f36df |  | note | Hold Point H/W/S - BBO: H
label | b7c7ccec-7d4f-5066-a1aa-488ab9fa68e4 |  | note | Hold Point H/W/S - CLL: H
label | d282ff52-af4e-5eb2-a129-3fb0d079f068 |  | note | Verifying Record - QAC - Pile Card
label | 5d35f620-2870-5913-9055-a5c03c33d726 |  | note | Comment - Pile cage to be installed immediately after Engineer inspection and acceptance
holdpoint |  |  | signoff | HOLD POINT (DO/BBO/CLL)
checkpoint-group |  |  | section | 4.0 Concrete Placement
checkpoint-status |  |  | checkpoint | 4.1 - Verify Concrete Mix – batch times, mix
label | 987a0787-d2b3-5b07-9263-e7e9494c1061 |  | note | Standard / Spec Reference - BBO SS 2140 Rev 5
label | 103db8b0-60cb-5751-9268-1b15d271c6b0 |  | note | Acceptance Criteria - 401T4504R
label | 2be52e69-9efb-5473-8caf-f9bc414ab1d7 |  | note | Frequency - Each delivery
label | 33819dc0-5bb9-5115-88db-863b5140a336 |  | note | Responsibility - DO Rep/CLL
label | d23d2690-5722-5931-b595-fee021a5f480 |  | note | Hold Point H/W/S - DO: W/S
label | 43bd3a62-328b-5f77-a0cb-b0132d6b601a |  | note | Hold Point H/W/S - BBO: S
label | a4459d03-2dc6-5823-a5ba-cd9e516f3176 |  | note | Hold Point H/W/S - CLL: W/S
label | f8d935ff-2af5-5d7e-b866-f9d9e2dbeae4 |  | note | Verifying Record - Concrete Docket
checkpoint-status |  |  | checkpoint | 4.2 - Slump/ Spread test
label | fa08a831-c5de-53eb-9558-6f592339dead |  | note | Standard / Spec Reference - BBO SS 2140 Rev 5
label | 45987288-bffe-5d95-8ebe-2a340eccaec8 |  | note | Acceptance Criteria - Slump 100-130mm +- 25mm
label | dbe3811c-1311-5d5f-a209-c1cd9ff2821f |  | note | • Spread 500mm +-100mm
label | 2415bb64-12b8-5cfb-ab35-82ebf82ed75f |  | note | Frequency - Each delivery
label | 80f8af05-ec45-587d-a244-c2ed7ba804fd |  | note | Responsibility - DO Rep/CLL
label | d5b5124b-2f99-50ca-9008-15ff5672228e |  | note | Hold Point H/W/S - DO: H
label | 689c9610-76fd-5b70-9a87-5b00a6e3df64 |  | note | Hold Point H/W/S - BBO: S
label | 61c250cd-15f7-5e49-91ae-e4c2264ed653 |  | note | Hold Point H/W/S - CLL: H
label | 85ef6231-6847-5b11-ab6e-38c97f93da77 |  | note | Verifying Record - QAC - Pile Card
holdpoint |  |  | signoff | HOLD POINT (DO/CLL)
checkpoint-status |  |  | checkpoint | 4.3 - Concrete level
label | cf5c32d9-8b2e-5212-87e3-a22f3b3a6b60 |  | note | Standard / Spec Reference - BBO SS 2140 Rev 5
label | 616a5865-4d49-5b8f-90bf-938f9945c06f |  | note | Acceptance Criteria - Design +50mm
label | d1462899-cdaa-5978-924c-52b8512a87a9 |  | note | Frequency - Every Pile
label | bdc77f32-0256-5520-a294-f327d7b77df6 |  | note | Responsibility - DO Rep/CLL
label | a3393c8c-6837-5251-ada2-d9b693e96a0c |  | note | Hold Point H/W/S - DO: H
label | 8920593f-b999-56b4-bb76-4988cac6b525 |  | note | Hold Point H/W/S - BBO: S
label | 74fd1a5b-2a16-5da8-9dca-a87ff8167a7d |  | note | Hold Point H/W/S - CLL: H
label | 02286bfc-65f6-52c1-8372-112c2bf4c366 |  | note | Verifying Record - QAC - Pile Card
holdpoint |  |  | signoff | HOLD POINT (DO/CLL)
checkpoint-status |  |  | checkpoint | 4.4 - Concrete placement
label | 4b2d27f3-d304-5954-97ca-42e3ad806688 |  | note | Standard / Spec Reference - HCC 1298/2022
label | 50ec78e8-7a60-590b-880a-90d07cb85e3d |  | note | Acceptance Criteria - ITP Item 3.3
label | b99e46f2-3d8f-5c8f-97ba-a1b6aaada3e5 |  | note | Frequency - Every Pile
label | aadd7598-b457-5050-bb50-1e4909442eac |  | note | Responsibility - BBO/CLL
label | 5ec50698-bb96-5c58-90fc-e33bbec12743 |  | note | Hold Point H/W/S - DO: W/S
label | b2c8600c-42f1-543e-b39d-2871d135a7cc |  | note | Hold Point H/W/S - BBO: S
label | 2b2362b2-b4ac-5f42-858d-9d482142d396 |  | note | Hold Point H/W/S - CLL: W/S
label | f7a9c4b9-b545-533f-8e2a-85395f12c4e5 |  | note | Verifying Record - QAC - Pile Card
label | 8296c2e6-2872-5b02-b7e0-6bdbca76b520 |  | note | Comment - Pile to be concreted within the same day as Engineer’s acceptance of reinforcing cage installation, ITP Item 3.3.
checkpoint-status |  |  | checkpoint | 4.5 - Concrete pouring – Check volume
label | f3e683a1-f21f-5432-b184-5ac50c69bd57 |  | note | Standard / Spec Reference - Construction Specification
label | cce7751b-fd79-593a-a271-f53492199ba3 |  | note | Acceptance Criteria - As per QAC - Pile card
label | 983417f3-6810-5eef-a4b7-f594983ade3a |  | note | Frequency - Each delivery
label | 26737af6-8647-5ac3-8e1c-e95412dc9700 |  | note | Responsibility - DO Rep/CLL
label | 384298bd-f756-5bfc-83da-38bfaaeb5852 |  | note | Hold Point H/W/S - DO: W
label | 28138a08-16cb-5f31-a057-4da8dd96c255 |  | note | Hold Point H/W/S - BBO: S
label | 145cef34-c356-59b3-a213-248300218be7 |  | note | Hold Point H/W/S - CLL: W
label | 78cb32b7-ba2d-59e8-bffb-afc56409d1a0 |  | note | Verifying Record - Concrete docket, QAC - Pile Card
label | 4bd8d361-e465-5bed-8717-bfa87d4bcb5c |  | note | Comment - Concrete volumes and Tremie records to be maintained as per QAC - Pile Card
checkpoint-status |  |  | checkpoint | 4.6 - Pile concrete overpour
label | 6b7c9fec-bb14-52a8-966e-2c2739099dfd |  | note | Standard / Spec Reference - HCC 1298/2022
label | fba889d8-b628-516c-9809-6f56ff55c148 |  | note | Acceptance Criteria - Visual check - Sign off by Engineer
label | 6c87a0ad-b23b-52d9-a9f0-3b007a8513f0 |  | note | Frequency - Every Pile
label | 13a64774-e81c-53d5-b24a-bac36a2941d4 |  | note | Responsibility - BBL/CLL
label | ba236230-a27e-53a6-9dcb-4239f6ee7a1e |  | note | Hold Point H/W/S - DO: W
label | 5a84510a-0eda-5b08-9220-d0e33b82945d |  | note | Hold Point H/W/S - BBO: W
label | 6f3a1949-8b26-5c23-9f67-fb6e263dc4c4 |  | note | Hold Point H/W/S - CLL: W
label | 5fbfce19-4d3e-5a01-abaa-3efa57f45c03 |  | note | Verifying Record - QAC - Pile Card
label | 8536857f-2eab-5bad-9af8-1141c44eae76 |  | note | Comment - Pile to be overpoured and slurry at the top of the head removed until only sound concrete is present.
checkpoint-status |  |  | checkpoint | 4.7 - Formation of construction joint
label | f581d9e2-cf40-5b7c-9b91-1cee11e67b4f |  | note | Frequency - Every Pile
label | 79fb3271-da92-539e-9432-4c34ce89a05a |  | note | Responsibility - DO Rep/CLL
label | 6b7303eb-5980-5128-8213-65756c332029 |  | note | Comment - Formation of construction joint by others.
checkpoint-status |  |  | checkpoint | 4.8 - Concrete curing (tops of piles)
label | 3ab9db28-18b1-58b9-8375-29b082114500 |  | note | Standard / Spec Reference - BBO SS 2146 Rev 4
label | adeffec9-e085-532b-b412-08212435cc08 |  | note | Acceptance Criteria - 7-day wet curing required
label | 47ea7a56-bad4-5e05-83d5-65cfcfc01141 |  | note | Frequency - Every Pile
label | 348082e8-a6fd-58d0-b953-7227dbd8ff1a |  | note | Comment - Concrete curing by others. Curing requirements will depend on the thickness of concrete which to be removed after concreting and weather conditions.
checkpoint-status |  |  | checkpoint | 4.9 - Compressive Strength Sampling
label | 522b68f4-7f1a-5bd3-adbe-25fbf41c7d31 |  | note | Standard / Spec Reference - NZS 3112
label | c3c8a389-8e3f-5e23-ac9e-53b49815cf55 |  | note | Acceptance Criteria - 28 day - 40MPa
label | c5b425b0-91f0-5222-af98-f0b2dc7b10bd |  | note | Frequency - Batch plant sampling and testing per piles – 4no cylinders – 1no @7 days, 3no @ 28 days
label | 3c52277d-9bc0-545f-b820-abddd70359a4 |  | note | Responsibility - Concrete Supplier – samples cast at plant
label | 67d5fa2a-2c19-5428-913e-81ca3f22e876 |  | note | Hold Point H/W/S - Sub: H
label | 62e37f45-5d3b-56a4-be03-47ee6d03fb66 |  | note | Hold Point H/W/S - DO: S
label | 92a92103-e907-5e5b-af77-1c42ce1d2964 |  | note | Hold Point H/W/S - BBO: S
label | bff9179e-3d25-5c50-b266-6d4335e05e1f |  | note | Hold Point H/W/S - CLL: S
label | b9194c85-45aa-537b-90aa-386b69c592a8 |  | note | Verifying Record - Lab. Test Record
label | 6e5ebf70-a293-5979-8666-1c5743f59f04 |  | note | Comment - On site independent testing to be done by others. Samples to be taken at batch plant.
holdpoint |  |  | signoff | HOLD POINT (Sub)
checkpoint-status |  |  | checkpoint | 4.10 - Post pour/ Post casing removal - Reinforcement and concrete RL, orientation check.
label | 5da39c36-338e-5d61-a610-cad927166bfc |  | note | Standard / Spec Reference - As per Auckland Structural Group Piling Specification
label | 988a0b99-7530-5211-a1ea-809b054a8511 |  | note | Acceptance Criteria - Alignment lesser of +- 4% DIA or +-75mm Height +- 50mm Concrete cover: 75mm, 50mm minimum
label | 445109f9-c35c-5735-afb4-9bf9e584066d |  | note | Frequency - Every Pile
label | dfbcc84e-ca31-5d63-a996-cedd4ed942ac |  | note | Responsibility - DO Rep/CLL
label | f805c3db-43a5-528a-848f-dcfcdb3914b8 |  | note | Hold Point H/W/S - DO: W
label | 63899f76-220b-5c2a-ae75-8e9eb90a4f96 |  | note | Hold Point H/W/S - BBO: S
label | 0c25cf28-8d08-5695-a159-a4380545d5b7 |  | note | Hold Point H/W/S - CLL: W
label | f3708420-2a35-54c9-aa00-3b636a2bb2fc |  | note | Verifying Record - QAC - Pile Card
label | 79d0df54-b810-5bfd-ae22-b36a0dc1cbeb |  | note | Comment - As builts by others.
checkpoint-group |  |  | section | 5.0 Close out
checkpoint-status |  |  | checkpoint | 5.1 - Pile Cut off level verification
label | 60e6bef7-48b9-5403-bec6-e68922ffa1d3 |  | note | Standard / Spec Reference - Construction Specification
label | d1dff8dd-ad15-57db-94c3-8538a13d2789 |  | note | Acceptance Criteria - +/- 10mm
label | ac152506-9a0d-558b-8ab6-d519b419ff0e |  | note | Frequency - Every Pile
label | 1dc3fc39-ff34-5147-aef0-8828f79642ab |  | note | Responsibility - DO Rep
label | fa793d5d-0fbc-523e-b022-a779407e78a5 |  | note | Hold Point H/W/S - DO: S
label | 4c0297bb-3fc0-50a4-9bf7-e53e27873c43 |  | note | Hold Point H/W/S - BBO: S
label | 08375f72-a0fc-53ff-b22c-04f7c7b8cc76 |  | note | Verifying Record - Survey Record
checkpoint-status |  |  | checkpoint | 5.2 - Pile & Reinforcement Cleaning
label | f10bacc4-6c83-59dc-ae57-0e47e11d700a |  | note | Standard / Spec Reference - Construction Specification
label | bbc7e2a8-6728-5dc4-ae5d-9f4d738d5319 |  | note | Acceptance Criteria - Visual
label | 54efc8f7-eac3-5e18-861f-28439453975b |  | note | Frequency - Every Pile
label | 55699227-4f9c-56b9-996a-f2468339df0c |  | note | Responsibility - DO Rep
label | 25389885-052a-54dd-83c3-ef60830d729f |  | note | Hold Point H/W/S - DO: S
label | 98f9e32b-e020-5b9d-ac8b-befaf733daae |  | note | Hold Point H/W/S - BBO: S
label | 67785e7e-86e3-5d48-97e6-e288a24d6435 |  | note | Verifying Record - QAC - Pile Card
checkpoint-status |  |  | checkpoint | 5.3 - Reinforcement to specification
label | e2231008-11df-5670-ab3f-458806c1c46d |  | note | Standard / Spec Reference - Construction Specification
label | cd4704b4-6f33-50e1-92b0-7e2d5e19ca43 |  | note | Acceptance Criteria - Visual
label | 4a0b20bc-43a1-50e6-ad70-4be701ee1b8a |  | note | Frequency - Every Pile
label | eaaaf82c-5480-50e5-9298-582fac5dcd44 |  | note | Responsibility - DO Rep
label | e2c90418-6ab8-594b-a1d3-8c51b06d6859 |  | note | Hold Point H/W/S - DO: S
label | 75e11b29-a15b-5b1f-a177-b23bfa350852 |  | note | Hold Point H/W/S - BBO: S
label | cc52a099-c4a8-5d40-9fab-5352cf304efc |  | note | Verifying Record - QAC - Pile Card
checkpoint-status |  |  | checkpoint | 5.4 - Pile records
label | c027e63f-fd56-5676-a6d3-e5084e17b286 |  | note | Standard / Spec Reference - Construction Specification
label | efd3822b-78c4-56fb-a0a2-4afec4dd0e0d |  | note | Acceptance Criteria - Collation and Submission of records
label | 4abf990d-cf56-502c-94fa-403039ac85d0 |  | note | Frequency - Within 24hrs of completion, Every Pile
label | cf5d8ca2-1b61-55d9-9a96-c2d50d40a909 |  | note | Responsibility - CLL
label | 75c2c23e-5b26-5df6-8591-b673e576d090 |  | note | Hold Point H/W/S - DO: H
label | 243147c3-4704-5bb6-a66c-ab5c836f8356 |  | note | Hold Point H/W/S - BBO: S
label | 3a6b8d88-311d-5206-92a9-770062142582 |  | note | Verifying Record - Email Confirmation
holdpoint |  |  | signoff | HOLD POINT (DO)
checklist-sectioned |  |  | checklist | ITP - Streetlighting - Rev C | itp |  |  |  | Yes | ITP - Streetlighting - Rev C | 506f46bc-6df3-48ba-a3ef-ccee4a094673
checkpoint-group |  |  | section | 1.1 - General
checkpoint-status |  |  | checkpoint | 1.1.1 - Drawings
label | a3de2d74-21d0-5582-92b4-1ae7bc58ac16 |  | note | Acceptance / Conformance Criteria - Prior to starting works, ensure that the construction drawings are both IFC and the Current Version.
label | 8f9725e5-dffa-5475-b513-f3c7a432abda |  | note | Standard / Specification - Downer
label | 48977b38-2a3c-5563-b98c-9206b4725e94 |  | note | Verifying Document - IFC Drawings
label | 06dc42aa-f4c7-5de2-ba65-f7ab71ce7356 |  | note | Frequency - Prior to work planning and start
label | 3c8f00a4-011a-5c2f-9675-062f8e61effa |  | note | Activity - M
label | 3168ccd6-ebc3-5d7f-a7d5-863e0c0bf506 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.1.2 - Power Connection Application
label | ccd54300-d4d7-5058-b31c-7d6d34ba8fcd |  | note | Acceptance / Conformance Criteria - Submit new streetlighting connection request via WEL Connect portal.
label | 4c5eae55-5181-56bd-99f7-93457375ae5f |  | note | Standard / Specification - WEL Requirements
label | cf6da2e8-7fbf-50a0-a5db-29a5aa8f0244 |  | note | Verifying Document - Application Form
label | 1db5b030-fd3c-57bf-aa68-601f31651c04 |  | note | Frequency - Once
label | 6a2ebb1a-804e-5c37-9f5f-2bb31b01449d |  | note | Activity - H
label | 7dcb24ca-8578-5a58-94a7-c7aebeaba83e |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.1.3 - Construction Pack (1)
label | 8a6216df-bc96-5a7b-a5d6-508324b8e2b0 |  | note | Acceptance / Conformance Criteria - ITP to be submitted to the Engineer and approved prior to works beginning
label | 99a26ea9-263d-5b32-813b-3bdaa137025d |  | note | Standard / Specification - Downer
label | adfe312a-266c-5b24-ba0a-62cd06db1fd8 |  | note | Verifying Document - In-Eight Document Approval/Acknowledgement
label | acd68749-24f5-5aea-9762-8580ee45d332 |  | note | Frequency - Submit 10 days prior to commencement of works
label | bb80e0e9-e097-569c-a112-fb905f182e87 |  | note | Activity - H
label | 58718269-f871-5198-84d0-0c12964f5d6a |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.1.3 - Construction Pack (2)
label | d68c3e67-fc7e-5393-abff-6c3a11024596 |  | note | Acceptance / Conformance Criteria - Methodology and associated documents to be prepared, reviewed and approved internally prior to work commencement.
label | 5c2199e1-2a20-5368-85e1-19c004989898 |  | note | Standard / Specification - Downer
label | 83e6e0d1-2866-53b3-a1d3-98be7f650486 |  | note | Verifying Document - Construction Pack Sign Off
label | 832a34b8-c26b-57c3-8cb6-abbdfd99d78b |  | note | Frequency - Prior to Construction & after any major incident
label | b90921d0-c20e-5c18-aeed-42bb1346090b |  | note | Activity - M
label | 47b29234-b37b-539a-b7ac-022807ed6a3f |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.1.4 - Survey Set-out
label | 076e2c3d-7984-5a7c-9409-aef47385f457 |  | note | Acceptance / Conformance Criteria - Ensure streetlight locations are set out per IFC drawings/data.
label | 948f3092-04ec-5e4a-89ff-64e7987cfdc2 |  | note | Standard / Specification - Design Drawings
label | ea90aa83-5866-51e7-a527-82b168584f4b |  | note | Verifying Document - ITP Sign Off
label | b465bc9b-e0be-5348-b733-88cceb9f6b03 |  | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
label | f84c7a7c-a29e-5e94-9896-143af8ffb392 |  | note | Activity - M
label | eb825140-f341-575f-853a-599d96e1d56d |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.1.5 - Environmental Protection
label | 82db6031-9ffa-50e7-93b9-b0240c35b755 |  | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
label | 62fec460-e442-58e6-a255-638e495550d2 |  | note | Standard / Specification - Project ESCP Plans
label | eec13850-623f-5b2f-a4c3-5f53916dbd39 |  | note | Verifying Document - ITP Sign Off
label | b22e0258-66e6-5635-8a28-52bfa8c69cf5 |  | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
label | 231e5c4a-1751-5a4b-8293-ec3381d1809c |  | note | Activity - M
label | ade57c56-b692-5aa7-95ca-e191cdaa2f71 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.1.6 - Stakeholder
label | d0ff9ed4-8621-510b-92f2-c0d228d4a2b4 |  | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works. Agree plans for maintaining access to properties during construction with landowners.
label | fe50bc8b-5efa-5ea9-828b-35c73834152c |  | note | Standard / Specification - Project Stakeholder Management Plan
label | 1a1b544b-cd6a-5b70-a36e-072d0c6fd792 |  | note | Verifying Document - ITP Sign Off
label | dee95153-7e76-5f5a-ac7a-c74e016e71b6 |  | note | Frequency - Prior to Construction with continue updates throughout the works
label | 0a41c492-74cc-5b7e-ae98-bdfe791ac4c4 |  | note | Activity - M
label | fa4ce277-bace-5414-9b1e-2e809d05421f |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.1.6 - Permits
label | 0da166e2-d8ce-54bd-a796-84c21a2ec108 |  | note | Acceptance / Conformance Criteria - Ground Disturbance Permit must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip.
label | c4fa453b-967a-59a2-9b46-8f3c119a56ef |  | note | ? Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. Doner Permit encompasses external provider permit requirements.
label | f221c398-07cf-5fe9-8262-e64bd9dbb056 |  | note | ? All known services must be clearly marked on site and briefed to the workforce .
label | 35ccb006-0e03-5ff7-9338-01382db03d15 |  | note | Standard / Specification - Section 2.2.10 Project Specification
label | f0d8c0b3-c31a-5c8d-918e-02309cc3acb8 |  | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
label | 5d46cde5-8510-552f-824f-5978bc315f07 |  | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
label | 78ad1714-004e-53d8-ad4e-d23d0ea1d896 |  | note | Activity - H
label | b01936ac-c17e-5be5-aff7-167214ad7479 |  | note | By - PE
checkpoint-group |  |  | section | 2.1 - General
checkpoint-status |  |  | checkpoint | 2.1.1 - Walk-over
label | 2d143d4c-8c17-5af2-a95a-3b2808340849 |  | note | Acceptance / Conformance Criteria - BBO representative to walk over and confirm/approve locations for install. Including reviewing accessibility of doors.
label | 67ae121c-bcd5-5155-bf07-1aa9e02704c7 |  | note | Standard / Specification - Design Drawings / RITS 3.6.3
label | 77440c7f-dd26-5957-a2a7-140dc7778cc8 |  | note | Verifying Document - Written correspondence
label | 99c519b7-ab20-5881-8d41-faee9e08d22c |  | note | Frequency - Prior to construction
label | 3306da5c-16d6-5fe1-810b-3ba7c39bf4c5 |  | note | Activity - HP
label | b94539ae-bd38-52ef-87b1-b7df994d4c54 |  | note | By - PE / BBO
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.1.2 - Light Poles Materials/Delivery
label | 2df090cd-abe8-5432-86cd-70cd721474f2 |  | note | Acceptance / Conformance Criteria - Evidence of manufacturer and product name.
label | a42a8f65-8703-5eab-b13c-913fd6d7ac4c |  | note | Standard / Specification - BBO Request
label | e8ab109f-73f6-5d53-877b-dc2187455ada |  | note | Verifying Document - Delivery Dockets
label | 9927671c-c4d0-56d4-b6e9-7ed16b3f8f9c |  | note | Frequency - Once per pole group installation
label | 2b52bb6d-2046-5761-8aba-b5cffdfd2f56 |  | note | Activity - M
label | 90bce1d5-b3fe-58e5-8754-8b9bee86752d |  | note | By - IBEX
checkpoint-group |  |  | section | 3.1 - Civil (Pole) Installations
checkpoint-status |  |  | checkpoint | 3.1.1 - Ducting Backfill Material
label | 8222565c-699f-5a03-9f0a-4e96d0da6f75 |  | note | Acceptance / Conformance Criteria - COVERED UNDER UTILITY TRENCH ITP.
label | 72a9835d-dcaa-57dc-b623-07a7798b36c3 |  | note | ? Where there is any exposed part of the cable (i.e. between termination of the duct and entry into streetlight pole underground hatch), surround with min. 100mm thickness sand material.
label | 90df0d16-05a1-5b62-9f6d-69ce9e4aab72 |  | note | Standard / Specification - WEL Requirement
label | 3325b3eb-a509-5bad-addc-6d9349885307 |  | note | Verifying Document - Photographs
label | ed60b599-34f8-501e-8dfd-e934ea3c2cd1 |  | note | Frequency - Verification on random selection of poles
label | 899316fc-6aba-5ba1-add1-e507dad579c4 |  | note | Activity - M
label | 1fa822c1-9461-5929-afc8-52b6980b2bb9 |  | note | By - IBEX / PE
checkpoint-status |  |  | checkpoint | 3.1.2 - Access Hatch/Door Accessibility
label | ee96db52-4f63-5782-8241-a5f44a5029a9 |  | note | Acceptance / Conformance Criteria - Visual check to ensure accessibility of doors.
label | 1008970d-3942-50fe-a9c1-17c117b79c13 |  | note | Standard / Specification - RITS 3.6.3
label | cd84f61d-ee2b-5661-90c9-435ff63f05da |  | note | Verifying Document - Nil - Visual Check
label | 84446c3e-6c42-59f2-8de0-292bd9e4ba71 |  | note | Frequency - Each pole
label | 006b666d-12db-5bba-b683-47532f57fae9 |  | note | Activity - M
label | 6e2178ef-8c03-5b83-96c6-076e813002ff |  | note | By - IBEX / PE
checkpoint-status |  |  | checkpoint | 3.1.3 - Pole Installation Positions
label | 86ac0252-2e53-537f-915d-dc7a37d49d13 |  | note | Acceptance / Conformance Criteria - Poles within following tolerances:
label | e3084716-5af0-5451-8b30-b3b98c5729ae |  | note | ? +/- 0.5m parallel to the carriageway
label | 1fb4a3b2-13a7-511d-8231-ee27be182692 |  | note | ? +/- 0.2m perpendicular to the carriageway
label | 1955698b-f110-5875-ac0a-bb6d94af9676 |  | note | ? +/- 0.2m vertically
label | df0db22f-1601-5121-a804-6d9ab2e09d5e |  | note | Standard / Specification - Design Drawings
label | 8ba4e170-2fef-5cde-ba48-4c970f277719 |  | note | Verifying Document - As-builts
label | 3a035543-9c9e-5149-ba5d-d3cdb785caa6 |  | note | Frequency - Each pole
label | 0fa1f756-81b0-5590-b768-76d84fd7f25a |  | note | Activity - H
label | fc89723f-6e6c-5b63-9b4c-b6cb8b60b179 |  | note | By - PE
checkpoint-group |  |  | section | 3.2 - Cabling, Electrical Testing and Commissioning
checkpoint-status |  |  | checkpoint | 3.2.1 - Earth Wiring
label | 04e0591b-bffb-5dd0-8d3c-405231de065a |  | note | Acceptance / Conformance Criteria - Photos of streetlight earth once completed.
label | 11ba273d-db14-5bba-899f-d13ee78f2190 |  | note | Standard / Specification - BBO Request
label | 52da4e9c-f6fe-5966-8b40-b123e87bda76 |  | note | Verifying Document - Photograph
label | 80e8fb9f-55b8-53d3-8904-d0a53bba398b |  | note | Frequency - Each earth
label | fe02b727-f9db-5bf5-864e-7f3c6a20d15e |  | note | Activity - M
label | 0f99849b-2d19-545b-a63f-a65f354fc19b |  | note | By - IBEX / PE
checkpoint-status |  |  | checkpoint | 3.2.2 - Electrical Certification
label | 60ed628e-c347-5e43-a2cf-313e39e188cf |  | note | Acceptance / Conformance Criteria - Completed and signed certificate of electrical compliance (COC) and record of inspection (ROI).
label | 8cd95bbb-2165-561a-95f2-cdfa4e1c6a7e |  | note | Confirm that poles are:
label | 2940a440-c09b-5946-9270-6a42b9d8b611 |  | note | ? Earthed to AS/NZS 3000:2018
label | 916b87fa-0ffe-53c6-bafd-6c7ba048d95e |  | note | ? Wired to AS/NZS 3000 and AS/NZS 3008:1.2
label | a56cd35c-ebfd-5101-bb1d-2850a326c5ef |  | note | ? Conforming to the NZ Electrical (Safety) Regulations
label | 20dc2bd8-e318-5d56-b92a-2e3cf9194ab3 |  | note | Standard / Specification - Design Drawings
label | 3fba7efc-79c2-5e27-b97b-046dfb789646 |  | note | Verifying Document - Certificate
label | 86bb62e9-5297-59f4-937d-aaf7b81a59cf |  | note | Frequency - Each pole
label | f55925cf-b786-5b43-a307-65616f5f8eb1 |  | note | Activity - H
label | c7c12ee1-0517-519c-8622-e88996d84bd9 |  | note | By - IBEX
checkpoint-status |  |  | checkpoint | 3.2.3 - Network Company Acceptance
label | 5d99ecc1-c413-5887-a3a6-3919ec19957d |  | note | Acceptance / Conformance Criteria - Written acceptance of all underground cabling and circuitry, including acceptance of assumed responsibility for future maintenance and renewal.
label | 1f0a9489-1b13-5cd4-88ae-2fa58ca1546a |  | note | Standard / Specification - RITS 3.6.8
label | 5d1abee3-2209-5100-8bdc-68a137f45aa6 |  | note | Verifying Document - Written Correspondance/Acceptance
label | 3b03f4d6-bc3b-5261-bc7b-7838647e1721 |  | note | Frequency - Once prior to comissioning
label | 9a8c39f0-3f9e-55fe-9953-c44bd15ca842 |  | note | Activity - H
label | e7c1bdf1-00be-5b9a-af09-67b81949a1ff |  | note | By - WEL
checkpoint-group |  |  | section | 4.1 - General
checkpoint-status |  |  | checkpoint | 4.1.1 - Survey As-Builts
label | 3d242e5a-b3c9-55f0-9521-a042a3d4928d |  | note | Acceptance / Conformance Criteria - Asbuilts reviewed and submitted showing final location of all poles
label | d991739a-0e59-5272-9a31-ded1a4dfe9a9 |  | note | Standard / Specification - Project Specification
label | 9f595855-e3bd-59de-ad0b-c42a74766405 |  | note | Verifying Document - Survey Data As Built Drawings, Photographs, Red Pen As- Builts including Undercuts
label | c34cd3ea-534b-5a69-9490-940ab4263809 |  | note | Frequency - Post Works Completion
label | c2416c06-035d-5532-b108-88fa948554bd |  | note | Activity - H
label | 73a5bd3b-dd02-59cf-85fb-aa4a3e2ae993 |  | note | By - PE
checklist-sectioned |  |  | checklist | ITP - Mangakootukutuku ST Rev 3 | itp |  |  |  | Yes | ITP - Mangakootukutuku ST Rev 3 | 519d0b94-e8d8-4a7b-b487-a3b9f2765890
checkpoint-group |  |  | section | A. Pre-Construction
checkpoint-status |  |  | checkpoint | 1 - Shop Drawing Approval
label | 7f551341-4092-5f41-b608-365d16f7af0a |  | note | ACTION (Hold, Monitor, Witness) - Hold
label | 21a25c85-7669-5e43-b881-cb382d0cdcf1 |  | note | Detail - Shop drawings to be submitted for approval.
label | bffa2df9-33f7-511b-b3fc-ab1be1a76bea |  | note | Reference - Structural drawings
label | 665c516d-76b1-5aa6-9126-10f6537864fd |  | note | Frequency - Prior to casting
label | f573a840-2c00-5fb2-b5ab-a06cf4dd26d7 |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | 94e10edb-c26e-5561-a211-7af1d2f73c9a |  | note | Conformance Criteria - Approved IFC Shop Drawings
label | a578b38c-a938-5cc7-a081-f444b003b6cc |  | note | Records - Client approval
label | 0eb78f61-f25f-583d-9e72-ec868b88f33f |  | note | Responsibility - Project Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - Concrete Mix Design Approval
label | b4a7e83d-f7e2-5386-a8d0-bdce94a58340 |  | note | ACTION (Hold, Monitor, Witness) - Hold
label | a361c484-876b-5df1-ab52-16c3d4d3a3d1 |  | note | Detail - Concrete mix design to be submitted for approval prior to concrete being supplied to site.
label | 1742277d-7193-50aa-8080-d6b50de0bcde |  | note | Frequency - Prior to casting
label | 9dc02ba3-edcd-52e5-ae2e-27beb06afe27 |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | 8aed14d2-9e72-5d42-9292-552147cc8c76 |  | note | Conformance Criteria - Minimum compressive strength at 28 days 60MPa. The mix design to comply with aspects of the contract specification.
label | 3eb4a396-88d9-5085-a6a0-3eff50c8f8db |  | note | Records - Client approval
label | 8c70c253-b98f-5db0-aa4d-6fe8b1c7b33c |  | note | Responsibility - Project Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3 - Lift Design
label | 72a3e126-69fe-5331-8d3c-3cb9bed90c53 |  | note | ACTION (Hold, Monitor, Witness) - Hold
label | 8e3c3373-6ac1-5937-81fe-bad027c8e376 |  | note | Detail - Lift design provided for units demoulding, storage and transportation.
label | 247154f6-4b94-573f-b348-c9c4696d731f |  | note | Frequency - Prior to casting
label | e2060d2f-34fe-57ac-b22f-dc007a76e3d5 |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | a79b995c-26bc-5e0f-9381-9f98a434f799 |  | note | Conformance Criteria - Specific Lift design (Lifting eyes and position) produced and followed
label | 3483a0fd-cc1f-59a7-b920-e5e057f9c41b |  | note | Records - Lift design Shop Drawings
label | b905620a-4d8d-5d4e-a3a7-53824569a358 |  | note | Responsibility - Project Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 4 - Steel Reinforcement compliance
label | 8a87d0fa-e2d7-5382-abbb-7559965df98c |  | note | ACTION (Hold, Monitor, Witness) - Hold
label | dc2aa740-0704-5c57-9315-5bd3434e5084 |  | note | Detail - Mill certificates for steel reinforcing to be provided
label | 84b89b85-f301-5869-80df-0741626d9978 |  | note | Reference - AS/NZS 4671
label | 0be59b34-46b4-59f8-be20-5324c088df7b |  | note | Frequency - Prior to casting
label | e18e88e4-798f-5709-9d17-caeba780f4f5 |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | 435840fc-5c7e-5ed7-8196-c57795815028 |  | note | Conformance Criteria - Steel to be manufactured with ACRS certificate details and verification
label | 9aef982d-f1ee-5d4b-8c43-aa4585465456 |  | note | ○ Mill certificates to match ACRS certificates.
label | 4a9eef66-564d-52e1-bdb1-749ac415648e |  | note | Records - Mill Certificates Detail sheets Test Certificates
label | 224e08df-d43c-5baa-850c-365e78cbec56 |  | note | Responsibility - Production / Quality Coordinator
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 5 - Steel pre-stressing material (Strands) compliance
label | 31c2bab4-6967-5982-8252-679329640788 |  | note | ACTION (Hold, Monitor, Witness) - Hold
label | e6226ee2-84ea-510d-a413-1f05e36cbfda |  | note | Detail - Mill certificates for prestressing strand coils to be provided
label | 32cd856e-af64-555b-bbcb-beafca175edb |  | note | Reference - AS/NZS 4672
label | 0d6a44bf-7515-528e-b9ff-e27410caf60a |  | note | Frequency - Prior to casting
label | 24a4e194-84f5-5cc7-bc56-9844e407437b |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | ad0406fe-662b-544c-87dc-3fa17e11c21e |  | note | Conformance Criteria - Prestressing strands (coils) to be supplied by ACRS accredited Manufacturer.
label | e681fcf6-ed21-5216-bdd0-c80ff47f280a |  | note | ○ Mill certificates checked against size, type and strand - mill certificate to match ACRS certificate
label | 661a7406-1789-5ca9-8dd1-9ff81b2232f8 |  | note | Records - Mill Certificates ACRS Certificate
label | f3e0a21c-8f19-552d-acf6-27af1d03f4df |  | note | Responsibility - Production / Quality Coordinator
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 6 - Design Stressing calculation
label | 02e5ba00-1841-508e-88e9-39d62acb03da |  | note | ACTION (Hold, Monitor, Witness) - Hold
label | b61dc034-995f-5a8f-b50b-d857eafda1d1 |  | note | Detail - Design stressing calculation and calibration certificates to be submitted to the Design Engineer
label | c04a58dc-439f-5d7d-8fa1-63ff20c0c2d8 |  | note | Reference - Structural drawings
label | 22e98be8-f1e3-57fc-a027-d820b4865448 |  | note | Frequency - Prior to casting
label | 84a194d4-cd04-59ef-bc72-be360077947b |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | 23dbf582-8563-551b-b047-6676ee83726d |  | note | Conformance Criteria - Expected extensions and gauge readings to be calculated for each cast.
label | 0460bfcb-18af-53d5-84e9-334ab18aa823 |  | note | Records - Design Stressing Calculation Calibration Certificates Client Approval
label | b7f2b866-abde-5ca0-9e68-6218a4aed178 |  | note | Responsibility - Project Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | B. During Casting
checkpoint-status |  |  | checkpoint | 7 - Steel Reinforcement cage assembly
label | bbb86996-1306-53de-92bd-7b21db04436e |  | note | ACTION (Hold, Monitor, Witness) - Monitor
label | d6e9e554-3562-5659-b411-0a6dbf8fd943 |  | note | Detail - Steel reinforcing cage to be assembled and inspected.
label | d724b6cc-c017-5e9a-9bea-8e52bbcf82ee |  | note | Reference - Approved shop drawings
label | d7ab26fa-5758-5365-8712-d8e50b24bf35 |  | note | Frequency - Prior to each cast
label | 3f6e926d-9ab1-5a6e-bdcc-89f9f4436e82 |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | 15bc6d2f-fa18-5f0b-ad6a-c27f4c806501 |  | note | Conformance Criteria - Cage assembly to comply with correct size, class, length, shape and location/spacing as specified in shop Dwgs.
label | a5492493-815d-5d4a-900f-e4bce94a1b05 |  | note | ○ Free from visual damage.
label | 022fa99d-8580-5db1-94d3-9fbbb8691e3b |  | note | Records - Pre-Pour Inspection sheet REO detail sheets
label | 9cfbf8d0-b2c5-52d9-bb65-65a95a91455f |  | note | Responsibility - Production / Quality Coordinator
checkpoint-status |  |  | checkpoint | 8 - Mould Preparation
label | 43fe340e-b9b0-538d-8621-ba7f3318bfb9 |  | note | ACTION (Hold, Monitor, Witness) - Witness
label | fe206031-d2ba-5e19-857b-d0740b5960e0 |  | note | Detail - Before casting ensure mould has been prepared to comply with tolerances.
label | 0c681922-0513-523e-bd51-52e5225d4a57 |  | note | Reference - NZS3109 Table 5.1
label | 91ae295d-84a2-5001-8bba-931750dbddd5 |  | note | Frequency - Prior to each cast
label | 4663dd7a-dc7f-5241-a762-c541366ac4a8 |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Measure
label | c26ea311-eda5-540f-89f0-1c218f3670a9 |  | note | Conformance Criteria - Tolerance on placement of moulds shall be a per NZS 3109
label | 00d231e6-2d84-5b52-b840-9513bd292965 |  | note | Records - Pre-Pour Inspection sheet
label | 76e7dcf0-de89-5a71-b6bf-23284989ec0c |  | note | Responsibility - Production / Quality Coordinator
checkpoint-status |  |  | checkpoint | 9 - Pre-Stressing
label | 9c5e267f-852c-5784-bb06-b77b0f341dd4 |  | note | ACTION (Hold, Monitor, Witness) - Monitor
label | 156da291-3e2f-538c-a6f1-8f01b26d7867 |  | note | Detail - Review actual strand extension/pressure compliance with approved design calculation. Draw-in measurements to be taken and recorded
label | 89d5f0b4-87a3-513c-a8bb-fde46de78203 |  | note | ○ Check that debonding has been included as required. Debonding shell be by plastic sleeves around the strand.
label | 53513eea-415b-5397-bace-18380b39200a |  | note | Reference - Approved shop drawings Design Stressing calculation
label | f6443357-0e8a-5be2-920f-9388d9a4ce65 |  | note | Frequency - Prior to each cast
label | dc95e6dd-a9f5-513b-ac08-2eb177d117ce |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection/Measure
label | ee1c4d01-6f3b-50de-a259-994acbbcca4a |  | note | Conformance Criteria - Stressing data/records reported on stressing calculation sheet.
label | d94f394f-2237-54c6-ba30-aaa4093be6d7 |  | note | Records - Stressing Calculation sheet Pre-Pour Inspection sheet
label | 6c33327f-4ece-5777-8fbe-9a8e26d44332 |  | note | Responsibility - Stressing Controller
checkpoint-status |  |  | checkpoint | 10 - Steel Reinforcement Placement
label | 71101c6f-a534-50b3-9511-2c6063359adb |  | note | ACTION (Hold, Monitor, Witness) - Witness
label | f1dd1e46-5c1b-5492-8045-ebc58b503aa4 |  | note | Detail - Reinforcing steel shall be handled, placed as per NZS 3109.
label | 340e129f-d759-5aab-bbf0-6227e531e49b |  | note | Reference - Approved shop drawings NZS 3109
label | b691864c-eca4-5a3e-8d5e-a3aa6ddb08bd |  | note | Frequency - Prior to each cast
label | 6c971a7b-073f-51bc-b5a5-0e8064f8f469 |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | 697d608b-a8b9-5e91-9866-7308204ce618 |  | note | Conformance Criteria - Steel reinforcing cage placed as per approved shop drawings.
label | c043c1fb-3973-50ca-80a1-8f4434cc8a56 |  | note | ○ Spacers shall be installed evenly to ensure correct cover as per shop drawings achieved.
label | 4d4e6ca6-fc8c-567f-8dad-6d34b9197e87 |  | note | Records - Pre-Pour Inspection sheet
label | 7f2a04b5-c7b0-53ef-b90e-14b915df5dc7 |  | note | Responsibility - Production / Quality Coordinator
checkpoint-status |  |  | checkpoint | 11 - Cast-in Items
label | fe536922-ec0a-562b-8b32-da5cfe699326 |  | note | ACTION (Hold, Monitor, Witness) - Witness
label | 7e6518c4-5902-5d48-880a-df652300e336 |  | note | Detail - All cast in items positioned as per shop drawings Lifters positioned as per lift design
label | fd745cbd-6b98-54d4-962f-e79c3285daac |  | note | Reference - NZS3109 Table 5.1 Approved shop drawings Approved Lift Design
label | f6f59f88-e7d5-54ce-9107-a68ee4b8806c |  | note | Frequency - Prior to each cast
label | 662e8aa6-b9aa-58e6-9bb8-f5657702a15d |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | aca746dd-5131-5204-9a2b-f1cc75f1b6e6 |  | note | Conformance Criteria - Correct type and number of cast in items used Correct Lifters used, positioned in accordance with approved lift design
label | 2ef43b5d-e49e-58dd-bb51-00dc5a337802 |  | note | Records - Pre-Pour Inspection sheet
label | eab0fc36-07a8-5e5a-b470-6c5fe90648d8 |  | note | Responsibility - Production / Quality Coordinator
checkpoint-status |  |  | checkpoint | 12 - Pre Pour Inspections
label | 9610250c-a6e8-5748-a901-50d9ec1f58d5 |  | note | ACTION (Hold, Monitor, Witness) - Hold
label | e169089e-503c-584e-a545-6ea525b5872e |  | note | Detail - Pre Pour Inspection shall be carried out before casting.
label | a73a93b7-54bf-577d-b463-728716aa1f09 |  | note | ○ The Engineer's Rep shall be advised at least 48 hours before the proposed pour.
label | 5b7e1687-4e07-5373-ae80-e6e4c22163a3 |  | note | Reference - Approved shop drawings
label | ea266cef-f33e-5e17-8cb4-cddabe92dbd0 |  | note | Frequency - Prior to each cast
label | 1a8e14fa-821b-5cbe-aba4-f90cedbbed80 |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Measure, Document review
label | 019ed32d-6966-5225-8f76-2a67e4bf6b5d |  | note | Conformance Criteria - Confirmation that the unit has been cast in accordance with approved shop drawings and NZ standards for tolerances.
label | a01183aa-1c69-5ad0-8267-d0479f1bcdb3 |  | note | Records - Pre Pour inspection sheet Marked up shop drawing, Stressing records
label | b5baa92c-78a5-5ac1-8c60-3f962fd9fa84 |  | note | Responsibility - Foreman & Production / Quality Coordinator
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 13 - Concrete Mix Conformance
label | 311117ac-3155-5539-a777-674b996bf619 |  | note | ACTION (Hold, Monitor, Witness) - Hold
label | 6db8b1b3-2817-561e-bf0c-593f1b25912e |  | note | Detail - All concrete dockets reviewed at time of delivery.
label | a165b695-2965-535c-bc57-2d3d04cb5ace |  | note | Reference - Approved mix design
label | 9370f9fa-3cf8-5619-a925-3d62e5b8fe41 |  | note | Frequency - Prior to placement of concrete
label | 6148a39e-7d5d-5efa-9bcb-455615636d8b |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | 0c458253-3efd-59d6-8e91-7791f4319959 |  | note | Conformance Criteria - All concrete delivered to site shall be produced in accordance with the approved mix design
label | b811b79f-2d25-572e-975a-a02276a48af2 |  | note | Records - Concrete Delivery Dockets
label | 4c842c98-2566-5e00-ad8c-cc5d77f34cd3 |  | note | Responsibility - Supervisor & Production / Quality Coordinator
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 14 - Concrete Mix Workability
label | 7a334b4b-7737-5c51-866a-9c853b5cf709 |  | note | ACTION (Hold, Monitor, Witness) - Hold
label | fd3bc877-8753-5f64-9e66-453baed60ccd |  | note | Detail - Fresh concrete to be visually assessed for its workability compliance.
label | e46c0b51-3685-5315-8d13-c30cdecb41a5 |  | note | Reference - Approved mix design
label | 0142e3c7-3508-5acc-9f85-df8e25e44292 |  | note | Frequency - Prior to placement of concrete
label | 768a44ca-4a4a-5073-8b4f-c7328566a890 |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | 92f4fa5e-031d-5a99-ac4d-b449dec86fb0 |  | note | Conformance Criteria - Workability as per mix design.
label | 90070146-4e54-5605-a12f-dcd06ee86053 |  | note | ○ Concrete slump test to be performed by concrete supplier before delivery
label | b6789452-9098-557d-b59a-48a6433402e6 |  | note | Records - Concrete Delivery Dockets
label | 8595d649-ab63-5660-a481-42756681bb5b |  | note | Responsibility - Supervisor & Production / Quality Coordinator
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 15 - Concrete Finish
label | ffda2a76-6528-5d93-a851-c9706278b15e |  | note | ACTION (Hold, Monitor, Witness) - Witness
label | 48b8c739-dca4-5c03-b99a-a6d0e0aa3f04 |  | note | Detail - Concrete to be placed to achieve the specified formed and unformed finishes
label | 42cd536b-8b98-5dbb-a933-2ab4e9951e9e |  | note | Reference - Approved shop drawings NZS3114
label | 319497f6-1355-533d-b8d1-69845caef18f |  | note | Frequency - During and after placement of concrete
label | 561d4630-0862-5e59-ad24-4fe0a5e8d775 |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | 47874d4f-1668-58a0-a01a-346d8df68456 |  | note | Conformance Criteria - ST Beam to be Type F4 finish
label | 3ad84433-4b23-5d29-ba07-1b5d516cb884 |  | note | ○ All construction joints - Type B / UNO
label | d8c14651-d0e7-5a17-b51c-a4ff74c0bb2c |  | note | ○ Top surface Type B / CJ and U2 where specified
label | 333da850-fdda-5870-9d8c-89652d76e88e |  | note | Records - Pre-Pour Inspection sheet
label | f7cb8e4d-b176-500d-9ca2-f77e871b02c6 |  | note | Responsibility - Foreman & Production / Quality Coordinator
checkpoint-group |  |  | section | C. Post-Construction
checkpoint-status |  |  | checkpoint | 16 - Curing and Release Strength
label | 83fe2645-c52a-5ed2-b008-4d454814155d |  | note | ACTION (Hold, Monitor, Witness) - Hold
label | 67eb983b-0580-5566-84c6-27120456b012 |  | note | Detail - Heat accelerrated curing as per approved methodology.
label | 71c95f64-4e80-52b8-9214-c5d34640cd49 |  | note | ○ 7 Day post mould water curing as per approved methodology
label | 2e1e5b66-8947-5034-8df6-9cace7b9ee3e |  | note | Reference - NZS 3109, NZS 3112
label | 1b3bb031-68ca-5dce-9cee-1faf40c0532e |  | note | Frequency - Prior to every unit transfer
label | 29171571-516c-5465-aa92-036c69d303c3 |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Testing (Schmidt hammer or Compressive strength test)
label | 75ce6f2f-056e-5814-9266-d4528833d946 |  | note | Conformance Criteria - Minimum compressive strength at transfer of prestressed units to be 40MPa prior to stripping and demoulding.
label | a6a1b21e-1b8d-5ec7-8363-c7038caef5c4 |  | note | Records - Post-Pour Inspection sheet
label | 35e0f182-6c39-5260-b30a-0f1e47a13019 |  | note | Responsibility - Production Manager
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 17 - Transfer
label | dca831aa-0a41-55d3-bdb9-23f9f12f80a4 |  | note | ACTION (Hold, Monitor, Witness) - Monitor
label | 86efa140-caa3-5d23-a936-c12143ffdc1e |  | note | Detail - Visual inspection to ensure strands are tight and no slippage of strand into concrete. Locallised spalling around full bonded strand at transer as result of excessive slippage will be identified as non conformance and the unit will be rejected and remade.
label | 2c15f307-7610-5f79-928a-5f76b2be7231 |  | note | Reference - Approved shop drawings
label | 2f770336-c37d-5921-88d2-d5adbe33ac34 |  | note | Frequency - Prior to transfer
label | 7c20d68e-d849-53fe-a90a-9e62feba776e |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | e2c67bcd-cc11-595d-81dc-e2a00aff1b10 |  | note | Conformance Criteria - Stressing data/records reported on stressing calculation sheet.
label | e4cb9fd6-82be-54a2-8137-19bf8139eb78 |  | note | Responsibility - Production / Quality Coordinator
checkpoint-status |  |  | checkpoint | 18 - Draw-in
label | 7a0c13e9-093c-5682-8d1b-e60370172781 |  | note | ACTION (Hold, Monitor, Witness) - Monitor
label | 1e2fe925-028d-5379-890f-a0bd96d228bb |  | note | Detail - Strand draw-in to be measured on each cast. If ave draw-in for group exceeds 2mm, or 4mm for single strand, then results to be submitted to Eng
label | bff52761-f10d-5b32-9a96-c2e6f259adf6 |  | note | Reference - NZS3109 C8.72.3
label | 66b150d8-cf4d-5c53-a9a8-19989e9dc75e |  | note | Frequency - Every unit - at transfer
label | 941faba9-d19c-563d-a257-c361b146104c |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Measure
label | 868bbe88-0540-544f-bde0-c635769310b0 |  | note | Conformance Criteria - Draw-in to be measured on each beam at transfer
label | efc87e3d-5551-5bc7-8473-64158b9bb748 |  | note | Records - Post-Pour Inspection sheet
label | 3f5e4a31-7372-5378-8977-0209a93256c0 |  | note | Responsibility - Production / Quality Coordinator
checkpoint-status |  |  | checkpoint | 19 - Lifting
label | c49d51f6-a795-5014-b414-bd86d118b587 |  | note | ACTION (Hold, Monitor, Witness) - Monitor
label | 13ede2b5-5b4c-5a09-8046-aef69baa9e0e |  | note | Detail - Units are to be demoulded following lift design
label | 60dab494-c2a1-50de-bfa2-3dc3b9ff4694 |  | note | Reference - Approved lift design
label | 46f2cc6e-738f-5188-9f4b-ba8db6bbfd7e |  | note | Frequency - Every unit
label | 7bfb66b1-e02d-576a-a838-e48e020d9746 |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | ea91a55e-6c8b-59bb-9f0b-92c4eebc6c0e |  | note | Conformance Criteria - Approved lift design to be followed.
label | 00d14c8c-7757-5442-8152-ec5f786dcde2 |  | note | Responsibility - Production / Quality Coordinator
checkpoint-status |  |  | checkpoint | 20 - Marking
label | 6ff1f621-a675-540a-aae3-a86d79a29035 |  | note | ACTION (Hold, Monitor, Witness) - Hold
label | c7fd609e-b2ac-5f38-885c-beb54ed5a4a5 |  | note | Detail - Units are to be clearly marked each end with unique number, cast date and installation direction (Super T).
label | 161bd468-0322-5036-93be-26ac20754dc0 |  | note | Reference - Approved shop drawings
label | 27d71e1f-5d89-55d0-8cc6-b04510b589b7 |  | note | Frequency - Every unit - after demoulding, prior storing
label | 4abfe7b5-7b7c-5e98-b96d-29b109203c9e |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | abc4c0ea-d7ac-580a-9dbf-539e63312f44 |  | note | Conformance Criteria - Ensure every unit is clearly marked
label | 80cebd3c-1d86-5073-baf7-4db5179ad035 |  | note | Responsibility - Production / Quality Coordinator
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 21 - Concrete Supply Testing
label | a50a5106-58ac-5154-b636-4e9d9baf5168 |  | note | ACTION (Hold, Monitor, Witness) - Hold
label | 524723cd-0b10-5b32-a705-0aaf1f106914 |  | note | Detail - Concrete compressive strength test to be carried out by supplier. 1 Set per beam with additional set for any truck with water added after leaving the batch plant
label | 3fe6190e-caa7-5090-99f8-40eaaf9458cb |  | note | Reference - NZS 3112, Part 2
label | 331227d1-8d3c-5dc4-b1b8-7ec0f3ee2639 |  | note | Frequency - 1 test sample for every beam [1 cylinder - at 7 days age, 3 cylinders - at 28 days age, 3 cylinders - transfer strength]
label | ef3e12d0-76f2-5b65-9cfb-0b4f1a44dc33 |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Testing
label | 025465c7-5017-563b-a711-8ca08e0408b2 |  | note | Conformance Criteria - Compressive Strength result to be a minimum orf 60MPa at 28 days
label | 0f0c4a8d-861c-5471-969e-3658197a17f5 |  | note | Records - Concrete suppliers Test Reports
label | ee7efde4-c434-5036-a461-9dcb8ab13561 |  | note | Responsibility - Concrete Supplier + Production / Quality Coordinator
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 22 - Post Pour Inspection
label | 721abcd0-5901-5c3e-b54f-0ea4ebb89e4e |  | note | ACTION (Hold, Monitor, Witness) - Hold
label | f8c468dd-cbfc-59fa-840e-626b72f8d26d |  | note | Detail - All units shall be inspected for its compliance prior to delivery
label | 139fc4d8-86d9-5641-a088-8d6a6481b470 |  | note | Reference - Approved shop drawings
label | f176d10f-98c5-5a13-b724-be54170c4ad9 |  | note | Frequency - Every unit - prior delivery
label | 8d5e7b13-a589-5f24-9b46-c5b8cbcd54fe |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Visual Inspection
label | a403cc31-9e23-5f4a-9c73-ac4489955d3b |  | note | Conformance Criteria - Confirmation that the unit has been cast in accordance with approved shop drawings and NZ standards
label | 8b0f1bbd-a572-581f-953d-7b495ef12b98 |  | note | Records - Post-Pour Inspection sheet (red pen mark-up - as-built)
label | f321ff1b-89d3-5b73-b0d5-a61c496aa4bd |  | note | Responsibility - Production / Quality Coordinator
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 23 - QA Package / As-Built
label | 2f204df4-bf44-5875-8ed5-2fc070b896f3 |  | note | ACTION (Hold, Monitor, Witness) - Hold
label | e5e86938-3e39-559e-b0f1-f12261960b37 |  | note | Detail - Compliance documentation is to be collated as per project requirements
label | 9b670fca-7b98-5440-a777-b5d556f58b3f |  | note | Frequency - At Delivery and installation
label | b6d92ed9-8b0d-58f3-b32e-7c0f31b46779 |  | note | Inspection / Test Method (submission, visual inspection, testing, measure, review) - Document Review
label | 308eecf0-d585-5ce6-9006-1532ba7cb0b0 |  | note | Conformance Criteria - Compliance documentation is to be submitted to the Engineer.
label | 9c00f19f-17d7-56d7-a209-5abed1961002 |  | note | Records - Post Pour inspection sheet Marked up shop drawings - as built
label | 3a897618-00a4-59f5-88ac-593de51db2e6 |  | note | Responsibility - Production / Quality Coordinator
holdpoint |  |  | signoff | HOLD POINT
checklist-sectioned |  |  | checklist | ITP - Stormwater |  |  |  |  | Yes | ITP - Stormwater | 5bc76927-2573-4c4a-9088-318a8fd2547a
checkpoint-group |  |  | section | 1. Pre-construction (P&G / EStablishment
checkpoint-status |  |  | checkpoint | 1.1 - Extent of Line Setout
label | 447440a5-2c0a-5624-85c7-5c5695b6237d |  | note | Acceptance / Conformance Criteria - Ensure line and level of Stormwater has been marked out and agreed with Engineer in accordance with Stormwater drawings Identify any clashes before construction.
label | c2a79509-fed9-5e36-b6c2-55161fc3b698 |  | note | Standard / Specification - Design Drawings
label | ca3ef045-41f3-51eb-926d-2360a7098b93 |  | note | Verifying Document - ITP Sign Off
label | 98ad0bfb-34bb-5a09-9755-5781e4c3ebe3 |  | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
label | 9f6fba78-f4fa-5da9-aba5-069ad45174ef |  | note | Activity - M
label | 8de4d596-b054-5659-bc84-16e38ba8fb5f |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.2 - Environmental Protection
label | 6612df47-d954-53c4-b894-edb8ce9af6f9 |  | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
label | 062afe7b-306f-5969-b9db-f7d2dc2afc15 |  | note | Standard / Specification - Project ESCP Plans
label | 7a2cc52d-ca2a-57de-905e-1840593283b1 |  | note | Verifying Document - ITP Sign Off
label | b38eb8cb-5d9d-5cd6-aae7-aace11a0a128 |  | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
label | de4a0ce0-290c-5f62-9d8d-6caf8dc1f487 |  | note | Activity - M
label | 052d5bf8-5a20-5976-ac01-5a2ef8b5e4f3 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.3 - Stakeholder
label | 964041ce-8f47-5f43-9ecb-4bc963a55457 |  | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
label | 8b5fbeb7-f07a-5d9a-8009-c74944313641 |  | note | Standard / Specification - Project Stakeholder Management Plan
label | eb2ede20-7062-5ae6-ae42-6281a683f1fd |  | note | Verifying Document - ITP Sign Off
label | d15bcff4-95f0-5150-accf-6527317b301c |  | note | Frequency - Prior to Construction with continue updates throughout the works
label | 5ec3de2c-4b7c-5ade-a197-bd5ea77fcabe |  | note | Activity - M
label | 4c067108-806e-5e92-9370-1ad1b8a35d89 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.4 - Permits
label | 4c825895-8c78-55b8-b08e-a8351d233bd8 |  | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
label | 1d27dde7-938b-501b-832f-694ad3898bab |  | note | Standard / Specification - Section 2.2.10 Project Specification
label | ebcd1d8c-89e5-5cf8-892d-b66059936aa9 |  | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
label | e8bbb9a1-2854-5867-a418-82b8a8d75d70 |  | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
label | 50b252e4-9a1b-55a1-8fcd-272b57170589 |  | note | Activity - H
label | 05b3ff20-3c01-57de-94a8-610a07e19afa |  | note | By - PE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2. Material, Personnel & third party approval
checkpoint-status |  |  | checkpoint | 2.1 - Pipes, Fittings and Pre-cast Structures
label | 8cc73743-a549-5b8a-9972-bd0ed83002b2 |  | note | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/manholes/catchpits are correct and in good condition and compliant.
label | 99c3e5ae-e54f-5495-9913-be9258ec6a39 |  | note | Verifying Document - Delivery Dockets
label | c00daa9a-8446-5e5a-80c6-f2424b52f9d1 |  | note | Frequency - Each Delivery to site
label | a6e87c58-81fd-59d2-a37c-c5b5ea4ddfbd |  | note | Activity - S
label | 34dca5cd-53ed-5e78-9eca-2b4049551dea |  | note | By - PE
checkpoint-status |  |  | checkpoint | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
label | 2f2b959f-0b91-593e-af76-befcf5d8037b |  | note | Acceptance / Conformance Criteria - Confirm material grading and density
label | df46ccd2-8662-5f7d-b6ba-bec7f384f640 |  | note | Verifying Document - IANZ Lab Test Report
label | 9c4db143-fb28-5f31-bc3c-43f6c7034508 |  | note | Frequency - 1 Test per 1000m3
label | 245aee90-a07b-5d58-8087-a5a14ee20ed3 |  | note | Activity - H
label | f3b05688-3c15-54c6-8fba-318cf71f63e7 |  | note | By - PE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Undercut Backfill Material
label | fe88c77f-3e70-515d-bb22-3fd140cb3a92 |  | note | Acceptance / Conformance Criteria - Engineer to Specify Material to meet specifications dependant on material selected
label | 07567e87-88a2-541c-b30e-632f15b06a13 |  | note | Verifying Document - IANZ Lab Test Report
label | 54e4e4a8-5298-504a-a852-f33bcd7d4d87 |  | note | Frequency - 1 Test per 1000m3
label | 8c66e4e0-bc8f-506b-a85f-f5d65b949fb1 |  | note | Activity - HP
label | 3d96e459-1e65-5754-b945-41afc0373867 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Geotextile/Geogrid
label | d07e6c50-2ff7-59c3-8fea-34e730e14a76 |  | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used in the undercut. Geotextile or Geogrid that is used in the undercut is to be documented / marked up on drawing
label | 6dbbe61e-6416-5303-b213-94a8c466f688 |  | note | Standard / Specification - Project Specification
label | e0bf4fe2-31b6-5f29-9c4a-9c35585633c8 |  | note | Verifying Document - Certification
label | 9db1ab35-a02a-50b0-a859-3077e8340c2f |  | note | Frequency - Material Used
label | 14c378a1-3d7d-5e88-b0b4-dc90aa22f05a |  | note | Activity - C
label | 3fd12297-a538-5970-b61b-2ca319e65cd8 |  | note | By - PE
checkpoint-group |  |  | section | 3.1 SW Pipeline Construction
checkpoint-status |  |  | checkpoint | 3.1.1 - Foundation Compliance
label | 7a04d12b-d747-5ffd-b944-2bd05ad77fc9 |  | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
label | 4f0e99a5-bfaf-5f02-a719-5a24a42d5913 |  | note | Standard / Specification - Project Specification 4.3
label | a9f17d3b-c88e-50fe-8d6f-ab8064428d69 |  | note | Verifying Document - IANZ Scala test result
label | f3841af3-80ba-5c41-8777-03f1b887719b |  | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
label | 3575732c-7133-5f5c-849a-1c506255b232 |  | note | Activity - H
label | ff25d653-974a-54e0-a0d3-32abec523435 |  | note | By - QE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.2 - Undercut Backfill Compliance
label | e1ff91fe-c3fb-58ee-9e70-19bef3c46199 |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average98%) of MDD
label | a64090ac-0958-5091-b76f-c28c35eb76a9 |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
label | 93d8490e-c5e1-5da8-888e-c2e3ae4d55d2 |  | note | Verifying Document - IANZ Lab Test Report
label | 8b1bde27-f241-50c2-a50d-193151536635 |  | note | Frequency - Based on Undercut Section
label | 021146ef-473d-5414-88e2-ce3b10842f12 |  | note | Activity - H
label | 905f63e2-3f0e-5d40-8280-5163a1b608af |  | note | By - QE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.3 - Bedding Compaction Testing
label | e3797ba1-d525-5fd9-a978-8a5831163f09 |  | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average98%) of MDD
label | a2064d5a-38c8-55fd-a7dc-82c5a0133fc2 |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
label | 1d9d16c0-cfa7-5e49-8d48-39ef0a0d8c21 |  | note | Verifying Document - IANZ Lab Test Report
label | 499bcee3-0521-5833-b992-397bfa037601 |  | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
label | 730ed117-3d39-5268-949a-02db9efa951e |  | note | Activity - H
label | 82f85a51-88c4-5669-8e7c-07d8953148f8 |  | note | By - QE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.4 - Haunch Zone Compaction Testing Haunch Zone shall extend from top of bedding to 0.3 times the outside dia of pipe
label | 943c75a0-548a-5877-b083-6d8b113d77be |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
label | 98d9189b-0f93-5541-86a3-f57e2e828180 |  | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
label | b6029590-f98f-5925-9315-855030e5fe08 |  | note | Verifying Document - IANZ Lab Test Report
label | db6a89fc-c15b-5eaf-9b4e-48577b15dbce |  | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
label | aa4f8012-e8f7-54c9-a4ac-7df2a309121b |  | note | Activity - H
label | c1462d73-a82d-5e15-9b73-6b6f3fd47075 |  | note | By - QE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.5 - Side Zone Compaction Testing Side Zone shall extend from top of Haunch Zone to 0.5 times the outside dia of pipe
label | c71bafd6-9b9a-586e-a9c4-1a21adf96b38 |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
label | 24f21671-d0d3-5a9e-bc01-b6a76b22570d |  | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
label | 13b55999-794e-5122-af3b-a8aa97997815 |  | note | Verifying Document - IANZ Lab Test Report
label | 32feea1a-ae98-558d-9737-dbd1f32fab48 |  | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
label | 4a48af67-2ab9-5de9-9c40-82b43aee0a97 |  | note | Activity - H
label | fd47be6f-6c6a-5ff9-94b2-800c521a7759 |  | note | By - QE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
label | 05192b11-1a31-586d-905f-5659d3cebd1e |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
label | 50b2983f-227f-536d-b0eb-3584ee19e873 |  | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
label | 8a3c30b9-73dc-5a8a-838b-86b5b0bd2ed5 |  | note | Verifying Document - IANZ Lab Test Report
label | 3d025453-8849-5aed-8278-b85d2c7e3df9 |  | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
label | bea3a1ac-8116-579e-9399-b859af1663b6 |  | note | Activity - H
label | b5599516-b1eb-5110-99be-fa5c76828b21 |  | note | By - QE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.1.7 - Backfill Inspection
label | 1adaab6a-26da-5cfd-b3e6-23db6fc87b44 |  | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
label | 3084c2a0-39cc-51ad-a0a2-094544a82dc1 |  | note | Standard / Specification - Project Specification 4.3
label | 57109279-457b-5e21-a601-66ebf67dfde3 |  | note | Verifying Document - Photographs
label | 191df840-3870-5720-a4de-26fffe4f3f34 |  | note | Frequency - Continuous
label | 8feee862-4ff9-5b2c-96aa-b341303a3086 |  | note | Activity - S
label | 398a1038-926f-5031-b65a-f2b2a115b4ea |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.1.8 - Survey
label | 74d6bc52-ea28-5f9e-a46e-d8a11a8a62aa |  | note | Acceptance / Conformance Criteria - Invert Levels The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified. Horizontal Alignment The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm. Gradient For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point.
label | 377dd711-8851-5fde-899f-26d3b19d6e49 |  | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
label | 779ac31a-8be8-5b43-a12a-7ce6784654ce |  | note | Verifying Document - Survey Data
label | 0758b277-e14d-5292-8882-bfddd9492976 |  | note | Frequency - Continuous
label | 666f3657-a9b9-5643-8c00-9d8c5e540590 |  | note | Activity - C
label | 7c5f006f-2bf8-54b5-bf65-9f6706fc2204 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 3.1.9 - Backfill Compaction Testing
label | dd1b4c81-03ce-519d-86b6-a52d4bb8409b |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC.
label | 5a0adf60-74ff-5fe6-b4d0-bd4064d2a01e |  | note | Standard / Specification - Project Specification 4.3
label | 57b31059-a1ef-5138-ac81-a2c861002c3d |  | note | Verifying Document - IANZ Lab Test Report
label | 2ca7f613-162c-5ee2-83fc-db1a58a8a44f |  | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
label | 3ca2a53a-d16f-538d-8f33-c2e7d8481abf |  | note | Activity - H
label | ba3f57e7-fa79-5100-999c-4e83448459c4 |  | note | By - QE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.2 SW Manhole Construction
checkpoint-status |  |  | checkpoint | 3.2.1 - Foundation Compliance
label | dcec4b76-a35a-5a06-9a8d-29d8238c9847 |  | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
label | 00c8b96c-19a5-5475-912e-4316d41e6e37 |  | note | Standard / Specification - Project Specification 4.3
label | 7d677d75-abd9-53e8-b241-5dcf600e67ef |  | note | Verifying Document - IANZ Scala test result
label | 5d063390-2611-5165-8299-86528408eea5 |  | note | Frequency - 1 Test/Manhole
label | dbd0670e-e320-5db0-84a5-dd06c660d2bf |  | note | Activity - H
label | bd3b026b-9a06-55d4-bdb5-132aa5be49ca |  | note | By - QE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2.2 - Undercut Backfill Compliance
label | 39adc7b4-7c09-5d68-b4de-2afda2fef248 |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average98%) of MDD
label | 2e017776-83f1-57c1-b446-0ea74d0331e5 |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
label | 97f1d62b-680b-5711-ba4b-7f5b0f2b1450 |  | note | Verifying Document - IANZ Lab Test Report
label | b82b0243-c431-5bf6-bef2-54f9e9604ed4 |  | note | Frequency - 1 Test/Manhole if Undercut required
label | db6d6ab5-d974-5cc2-b57c-e9036d4fe47f |  | note | Activity - H
label | 51b8047d-5ab9-52d7-b996-5a03129f824d |  | note | By - QE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2.3 - Bedding Compaction Testing
label | 2ae700cd-cdff-561f-9c54-c990abd4899e |  | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average98%) of MDD
label | 8eb8191a-61be-5741-99e3-a38fa32a2bd4 |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
label | 15e97f48-55d1-5511-b25c-c3910dd31d24 |  | note | Verifying Document - IANZ Lab Test Report
label | 6596043b-5c4a-581d-b4bd-86665c83b1dd |  | note | Frequency - 1 Test/Manhole
label | 003075f7-e290-5eb6-a26a-9457ff57961c |  | note | Activity - H
label | 75d1fa86-4533-5a8f-b029-aec3817e6ed7 |  | note | By - QE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2.4 - Backfill Inspection
label | 80e98b3b-70ee-589d-99a7-8585136c48f5 |  | note | Acceptance / Conformance Criteria - Inspection of manhole prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the manhole
label | c72fb28c-e022-5303-a650-9e008cf50310 |  | note | Standard / Specification - Project Specification 4.3
label | 87c71e3f-7a35-5568-bb19-d8524210f6d0 |  | note | Verifying Document - Photographs
label | 6e2b4e89-bad4-5a42-96c2-1a70cf38076d |  | note | Frequency - Continuous
label | c5f29725-7a10-5c82-a80d-e13fc08c62b8 |  | note | Activity - S
label | 5ea80f2a-4b35-53da-a64f-0b12bc74d1c2 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.2.5 - Survey
label | 6b93d645-4ecf-56be-a7fa-df9892ec778e |  | note | Acceptance / Conformance Criteria - Invert Levels The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified. Horizontal Alignment The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm. Gradient For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point.
label | 1ac3f541-1f81-5dc6-8556-14d6f56de1d6 |  | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
label | 2ef1a085-438f-59d5-b3fd-50ead3ef546b |  | note | Verifying Document - Survey Data
label | 235d4e1e-4ebb-569d-b7c5-6ef33aa85739 |  | note | Frequency - Continuous
label | 5483ddd0-7ac7-592a-bc95-d7f40b712b95 |  | note | Activity - C
label | caf7d5bb-97cc-5104-9b91-f1fdf092b1af |  | note | By - SV
checkpoint-status |  |  | checkpoint | 3.2.6 - Backfill Compaction Testing
label | 318dea9e-f21a-516d-998f-cefd11329da4 |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC.
label | 3fcf6580-7b80-5d37-8434-4a4bf5773b2f |  | note | Standard / Specification - Project Specification 4.3
label | 41973aa3-f55c-5b99-af6c-3e7072fe92c3 |  | note | Verifying Document - IANZ Lab Test Report
label | 085388e7-2c92-5ba2-a83e-694ebd60d6ab |  | note | Frequency - 4 Density test per layer at Quarter Points around the Structure
label | c006baea-7876-523a-b03d-5b741204d653 |  | note | Activity - H
label | 6e4a94cc-536c-56b9-9988-83741cadbbc5 |  | note | By - QE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2.7 - Haunching
label | 5659e5ec-fb84-5ec0-9f8c-a5b25af378c7 |  | note | Acceptance / Conformance Criteria - All the MH's needs to be haunched as per the specifications
label | 40a23dd4-539d-586c-b1b7-6b350a9581dc |  | note | Standard / Specification - RITS
label | d9a6375d-0eef-528f-9a15-48556a44142e |  | note | Verifying Document - Photographs
label | 2799a095-3978-5051-aa95-4d0db01a222c |  | note | Frequency - Continuous
label | 6f9a12d4-fd19-5973-8db6-606ab7a73450 |  | note | Activity - S
label | 08a70049-a942-524f-91d4-b28a82d75d02 |  | note | By - PE
checkpoint-group |  |  | section | 3.3 SW Catchpit Construction
checkpoint-status |  |  | checkpoint | 3.3.1 - Foundation Compliance
label | b5bcd2e4-2d17-56bd-a5db-81d297579443 |  | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
label | 6bbdf8da-2c8e-5d2b-b460-d0096881e4c4 |  | note | Standard / Specification - Project Specification 4.3
label | 18d529ea-89eb-59fb-97f7-391b734c33f8 |  | note | Verifying Document - IANZ Scala test result
label | 87595e9e-bb05-5747-87d5-a4ed3ece4f65 |  | note | Frequency - 1 Test/Catchpit
label | e726b3b3-be6d-5a7c-a618-aa07aebbec81 |  | note | Activity - H
label | bd723658-bc76-5c1f-bc44-f3eca7d562d1 |  | note | By - QE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3.2 - Undercut Backfill Compliance
label | 80cc47a7-b6e1-5136-81bd-f07069b91b8e |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average98%) of MDD
label | c4c34550-803d-55f4-838d-e8392fdf9fd2 |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
label | b7643824-0758-5387-ac1b-54ba81825658 |  | note | Verifying Document - IANZ Lab Test Report
label | f9947440-9d2b-53b7-832d-0d9d1f819fbb |  | note | Frequency - 1 Test/Catchpit if Undercut required
label | 11bfade2-10e4-5df8-a782-7f7e1df7d556 |  | note | Activity - H
label | ad79f347-8d68-53d4-8203-fd74f1958ad5 |  | note | By - QE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3.3 - Bedding Compaction Testing
label | 648a2b95-dd00-54ea-ac31-e22564f82a91 |  | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average98%) of MDD
label | 5646338b-6181-5b18-b998-28102fa4c4b3 |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
label | 60218604-2f09-54fd-9073-ae1aaed2a405 |  | note | Verifying Document - IANZ Lab Test Report
label | e7c00a95-6aa8-5929-87fa-96e4a3c4dde4 |  | note | Frequency - 1 Test/Catchpit
label | f0a01638-4414-5fa4-a096-f22a36e03247 |  | note | Activity - H
label | d558e9a6-05a1-54d6-9592-b7fe56f33911 |  | note | By - QE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3.4 - Backfill Inspection
label | c467db57-ff4b-5807-8eee-15fae2cf0df7 |  | note | Acceptance / Conformance Criteria - Inspection of catchpit prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the catchpit
label | ffb11fbc-3b83-5abd-913a-240698c4df57 |  | note | Standard / Specification - Project Specification 4.3
label | 32b11a35-8a77-5aaa-bdb1-d7cf228e6aaf |  | note | Verifying Document - Photographs
label | b6eafff6-bdea-547a-8a04-1cb3793877d3 |  | note | Frequency - Continuous
label | a1f137a5-0c59-59e3-b70b-62dc170cc355 |  | note | Activity - S
label | c9cef0a2-1b0e-535b-8f99-d8e4d17c3ecd |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.3.5 - Survey
label | 7197b535-45c2-5809-829e-ebe391e834c7 |  | note | Acceptance / Conformance Criteria - Invert Levels The permissible deviation from the designated level of the invert at each manhole or structure shall be ± 50mm, provided that the fall between successive manholes or structures shall be at least 90% of that specified. Horizontal Alignment The permissible deviation of the horizontal alignment between manholes or structures shall be ± 100mm. Gradient For straight gradients, the permissible deviation from the specified gradient shall be ± 50mm from a straight line drawn between the inverts of successive manholes, provided that no point in the pipeline is lower than any downstream point.
label | a1ee0ca8-a47b-5917-bd54-f5214297b86b |  | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
label | 76fa5315-b0f5-58e3-acfe-56024a1d6ac4 |  | note | Verifying Document - Survey Data
label | e150227c-5e94-5830-b10d-ea0b898175bf |  | note | Frequency - Continuous
label | 5d550601-8749-5225-a5ab-5b74c1aa57c8 |  | note | Activity - C
label | 16a0960f-ef12-5ca6-ba4b-afc4551b968b |  | note | By - SV
checkpoint-status |  |  | checkpoint | 3.3.6 - Backfill Compaction Testing
label | eb686d29-26c4-5f20-adc9-e52220561e9e |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC.
label | 3e46d6be-d908-593c-b47a-2cdd80cb0094 |  | note | Standard / Specification - Project Specification 4.3
label | b1763e05-12f1-56b7-8fe0-96265442db5b |  | note | Verifying Document - IANZ Lab Test Report
label | 5bcd4b69-2adf-5059-bc82-158e8c321dbf |  | note | Frequency - 4 Density test per layer at Quarter Points around the Structure
label | a5f5cba0-c703-577a-af89-de2bad6a32ee |  | note | Activity - H
label | ebbf3c75-97de-50a0-b256-7d083ae04ea3 |  | note | By - QE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.4 Riprap & Boulders Installation
checkpoint-status |  |  | checkpoint | 3.4.1 - Rip-Rap Material
label | b321cd8c-5e46-5864-aba5-f794ff7ad43c |  | note | Acceptance / Conformance Criteria - The material shall comprise imported screened quarry blasting's and/or crushed basalt, greywacke or other angular hard rock which shall conform to Density, Crushing Resistance , Weathering Classification, Abrasion Resistance, Calcite intrusions, Grading, Shape. No rock riprap or boulders shall be placed until the Contractor has provided test results to prove compliance with the requirements and obtained approval of the Engineer.
label | b68f6a88-b769-531b-b43d-ea229b1af715 |  | note | Standard / Specification - Project Specification 4.7.1
label | 710b49eb-0085-53e1-9708-0c05bc07c290 |  | note | Verifying Document - IANZ Lab Report
label | 509fd158-cd61-5f76-9574-a828fce7ffd9 |  | note | Frequency - Prior to placement
label | c4be62b1-dd9b-5431-9751-6efbea20f7f2 |  | note | Activity - HP
label | 08dd237a-e262-5a54-9704-4d1aafdb9aa1 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4.2 - Soil Rip-Rap Material
label | ae586004-69f3-51f9-a2ab-3fb9c500fb06 |  | note | Acceptance / Conformance Criteria - Where soil riprap is specified on the Drawings, approved riprap rock shall be pre-mixed with topsoil from on site at a ratio of 70% riprap to 30% soil by volume.
label | 4585a3e6-61dc-5271-b76a-4db994ee98c2 |  | note | Standard / Specification - Project Specification 4.7.4
label | 5afcc23e-4686-5030-adc5-8cf217b29856 |  | note | Verifying Document - Dockets/Site Notes
label | 1b6e59a7-08e6-5461-b23a-b005331f1c91 |  | note | Frequency - Each Batch
label | 4f1355f3-bfa8-5d3e-95e0-b69bb3f6889a |  | note | Activity - R
label | e0e2ab75-0816-5f19-955a-022b76b98747 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.4.3 - Void Filling Rip-Rap Material
label | 0fb9879d-1dc8-5b88-8be9-e9d76f5bee87 |  | note | Acceptance / Conformance Criteria - Where void-filled riprap is specified on the Drawings, the riprap rock shall be premixed with well graded granular material with a maximum particle size of 40mm (GAP 40) at a ratio of 70% riprap to 30% GAP 40 by volume.
label | 4cd86cc3-8c69-5de8-943f-2ea0f7b3290f |  | note | Standard / Specification - Project Specification 4.7.5
label | 72cb2c30-925b-5688-bcae-53c504748bb8 |  | note | Verifying Document - Dockets/Site Notes
label | 2c5fc2af-b150-58a3-871e-7fda26bfac99 |  | note | Frequency - Each Batch
label | 55719c40-e0df-5036-a089-ee1c0d9c9da6 |  | note | Activity - R
label | 0dc87d3c-994a-52bd-bcde-99f769a51b07 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.4.4 - Grouted Boulder
label | 5d119a4a-7190-56ea-a138-60a8225dc9f2 |  | note | Acceptance / Conformance Criteria - Boulders must be approved by the Engineer, prior to placement Grout used for grouted boulder structures shall meet the requirements of NZS 3109
label | e49b26c5-3d8c-535e-a12c-c23ce98772d4 |  | note | Standard / Specification - Project Specification 4.7.6
label | 79b8a383-a5a9-5a06-969f-f6aba483cb0e |  | note | Verifying Document - Site Records Data Sheet
label | b03711ab-ad6c-5f3b-b345-55a98e6258f5 |  | note | Frequency - Prior to placement
label | 1b8ab041-d166-5770-a6f6-2e79d7c9116c |  | note | Activity - HP
label | 5191a328-e62a-5de8-9966-507dbde63370 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4.5 - Achieving Required Depths
label | 953e1403-bb20-5da8-8128-631b97ed3482 |  | note | Acceptance / Conformance Criteria - As per IFC Drawings
label | 830943ec-076f-5cb7-bc84-87871c978dea |  | note | Standard / Specification - Project Specification
label | 4c48f30e-2955-567f-a1dd-288e00897eac |  | note | Verifying Document - Photos showing thickness/depth Each Section Labelled
label | 969c046d-ac38-5cd9-9eb3-4264be2d77bf |  | note | Frequency - After Placement
label | b22883ca-794f-5d96-a004-b5aa14482988 |  | note | Activity - H
label | dc639aaa-e29a-5d1e-a35b-050828c37bdb |  | note | By - PE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3.5 CCTV & Reinstatement
checkpoint-status |  |  | checkpoint | 3.5.1 - CCTV Inspection
label | f0fab8de-949c-5ebc-a248-d79779f581c8 |  | note | Acceptance / Conformance Criteria - Quality Check on New Works
label | 18687b5c-cc85-5a1b-b730-2eb46416a2ca |  | note | Standard / Specification - Project Specification 4.4 NZ Pipe Inspection Manual
label | 63f2aecc-85a2-59a9-9b6d-adc6a21fed50 |  | note | Verifying Document - CCTV Report
label | 69d35b40-75fe-5dd2-b466-ea0d100bbaa8 |  | note | Frequency - 1 per line
label | 66432b17-ac2c-5cfd-967e-78fc98c03e74 |  | note | Activity - S
label | 488fadbe-90bf-5b0d-8b6b-8eb71925a20a |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.5.2 - Reinstatement
label | a312f052-372d-50f9-9883-57a8dbe105e1 |  | note | Acceptance / Conformance Criteria - Quality Check on New Works/All the MH Lids and Cespit Levels should align with the pavement specification in terms of level & alignment
label | 7be67543-bfaa-5a20-997e-ed431314971f |  | note | Standard / Specification - Reinstate and Tie into existing surrounds
label | d1cee765-ff68-569f-93cc-97c4f195f95c |  | note | Verifying Document - Photographs & Level Checks
label | 4d5922ad-a59f-5136-9229-4b0ba6edc19b |  | note | Frequency - Continuous
label | a287eccd-79c8-502e-9bf6-c7365abc4ed2 |  | note | Activity - S
label | 63711978-92e4-5993-a92f-a80b22d2f3bd |  | note | By - PE
checkpoint-group |  |  | section | 4. Post-construction (Final Inspection & Handover)
checkpoint-status |  |  | checkpoint | 4.1 - Survey As-Builts
label | 53857957-862a-5c02-affb-420f8bbcb2d4 |  | note | Acceptance / Conformance Criteria - Quality Check on New Works based on the tolerances in RITS
label | 0a6e7516-d189-58bf-b63f-ed3019cfa3f0 |  | note | Standard / Specification - Project Specification
label | 97975fe6-bf31-533e-aa46-c1eb07ef0da3 |  | note | Verifying Document - Survey Data As Built Drawings Photographs Red-Pen As Built
label | 64440248-836a-5ff7-84fb-19292f75fdaf |  | note | Frequency - Post works completion
label | eca96e49-ee5e-5cc0-966e-5e8083612ee8 |  | note | Activity - H
label | f0c23b4c-fd20-5916-b85f-437a97b969e5 |  | note | By - SV
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Pavement & Surfacing - Sealing - Rev 1 | itp |  |  |  | Yes | ITP - Pavement & Surfacing - Sealing - Rev 1 | 5d91c9cd-e20b-412e-acdf-1cd05718ba55
checkpoint-group |  |  | section | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
checkpoint-status |  |  | checkpoint | 16.08.01 - Sealing Chip - Source Property Tests and Sampling
label | f72cc165-27da-5cd3-a2a3-8738244d63b5 |  | note | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
label | 423c1f2c-1b85-59ee-8837-db3ca86913c7 |  | note | Standard / Specification - TNZ M/6: 2019 - 4, PS - 7.2.8
label | 1e6e13d0-5040-53d8-a28e-9351742ac8da |  | note | Verifying Document - IANZ Lab Reports
label | b5fef9e4-b133-5ca3-aebb-24d6529f7588 |  | note | Frequency - 10,000m3
label | 0702d244-1f93-5b2d-8150-2e02e09d0069 |  | note | Activity - HP
label | 656e0c67-8bf9-5da6-a7f0-979ef2070a8f |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 16.08.02 - Sealing Chip - Production Property Test Sampling
label | 59d0648b-965c-593d-8c54-ee1f33d05fdf |  | note | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
label | 0778486d-802b-5642-b787-54b28b889813 |  | note | Standard / Specification - TNZ M/6: 2019 - 5, PS - 7.2.8
label | 71a87208-8ff3-548d-b433-5608c6ddf464 |  | note | Verifying Document - IANZ Lab Reports
label | 7224cf73-2afe-5bed-822b-111c2b0a2550 |  | note | Frequency - 500m3
label | 66a555cc-52d6-5318-9e0e-990e309fedc7 |  | note | Activity - HP
label | c9c0dd8c-5162-5885-93bc-dfc24d77576e |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 16.08.03 - Bitumen
label | a4923ef6-0f75-58cb-87e4-5fab4ca68408 |  | note | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification.
label | 9407e156-6df1-5d9d-b127-2eea90e91ff0 |  | note | Standard / Specification - NZTA M10:2020 - 2.3.1, NZTA M01-A, PS - 7.2.8
label | 54c4067b-6883-5adb-9b44-8a1a385fb181 |  | note | Verifying Document - IANZ Lab Reports
label | 94a8dcbe-885f-567a-8ca3-44642a550665 |  | note | Frequency - Prior to use
label | 2b3e5074-080a-5dd8-8c22-8959c9398141 |  | note | Activity - H
label | 6de56487-3a96-5453-bffc-225d597963ff |  | note | By - PE
checkpoint-status |  |  | checkpoint | 16.08.04 - Sprayer E-2 certification
label | c1ed1d90-0a52-5602-b37e-1d951a9dedb8 |  | note | Acceptance / Conformance Criteria - E-2 certification and is up to date
label | 750c4b85-0fdc-555e-9f7c-71e36e534785 |  | note | Standard / Specification - BCA E/2 Specification
label | 8deada11-0ecf-5e45-8b19-e048947f9d87 |  | note | Verifying Document - Certificate
label | 66742a5f-1fe3-5787-b935-c3b3e56445d7 |  | note | Frequency - Prior to use
label | d2acc12a-3ccd-5ded-91be-d3335f36ff2a |  | note | Activity - C
label | e315cf47-680d-58f6-a2a8-6ccd76b1ee3d |  | note | By - PE
checkpoint-status |  |  | checkpoint | 16.08.05 - Sealing Design
label | 9c9a2b3a-3972-5a7d-8895-4e4ec59e36cd |  | note | Acceptance / Conformance Criteria - Chip seal type, chip source, bitumen and/or emulsion grade, % kerosene, AGO and diluents, polymer (if applicable), sand report reports, hot application rate(s) including spray rates
label | 85646657-8972-5bc1-a519-126ae5edaaba |  | note | Standard / Specification - PS 7.3.4.
label | 17074ecd-fecd-57f9-92a3-b9081866afc3 |  | note | Verifying Document - Design Document
label | 08a63143-714b-548f-927f-4814682e7088 |  | note | Frequency - Prior to use
label | c651762d-d5d2-5bda-8cb5-b9edd01dc852 |  | note | Activity - HP
label | 66421952-0624-562d-af31-bae357bd0170 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 16.08.06 - Bitumen approval
label | ef41b259-4f32-5713-aaf4-8c949aa03238 |  | note | Acceptance / Conformance Criteria - Applications for approval shall contain the information required by NZTA Q05 clause 4 and the testing information required by Table 5.1
label | b9cb265a-75c9-5f3e-a319-bc00a27e782d |  | note | Standard / Specification - table 5.1 of NZTA M1:2022
label | 8a9787cf-c73f-5593-b9e7-8034e115c3c4 |  | note | Verifying Document - Report
label | 3494da08-2937-55d7-be14-8cb442e30733 |  | note | Frequency - Prior to use
label | 1ace09e4-9546-575a-86ac-9231abcff70f |  | note | Activity - C
label | 8adbad93-1366-5fbf-9710-0a3b9e97c223 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 16.08.07 - Bitumen Quality
label | 61d2add7-8f3f-529f-a4c6-2c9bdeeab619 |  | note | Acceptance / Conformance Criteria - All bitumens used for road pavements construction, supplied or blended by New Zealand-based bitumen blending facilities shall meet all the requirements of Table 6.1 or M01-A specification for the grade supplied.
label | 3f47ea2d-af01-517a-b556-fa1a953cb7f2 |  | note | Standard / Specification - table 6.1 of NZTA M1:2022
label | 3fa8115b-491d-5715-9759-01bb6995f189 |  | note | Verifying Document - Report
label | ae50f405-62a6-56c2-9693-183b399ada46 |  | note | Frequency - at least one test per grade supplied following delivery of a shipment into a bulk blending facility.
label | 09b80dd6-dd9f-5329-a000-96a30cec77c1 |  | note | Activity - C
label | 02ad4278-edce-5860-939c-4aa811a1de72 |  | note | By - PE
checkpoint-group |  |  | section | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
checkpoint-status |  |  | checkpoint | 28.07.01 - Sealing Procedure
label | dba6e33f-1c8b-5569-9fda-1cd45f031f5a |  | note | Acceptance / Conformance Criteria - Sealing shall be carried out in accordance with TNZ or NZTA Specifications M/1, M/6, M/13, P/3, and Q/1.
label | a4a4f0c9-6e21-5f44-b95d-433b8ef1d6b7 |  | note | Standard / Specification - M/1, M/6, M/13, P/3, and Q/1.
label | 5fc5d2df-ff01-5bd2-9ffb-10b00f3635f5 |  | note | Verifying Document - Methodology / Construction Pack
label | ed9de7e0-e62a-5439-b8a5-e510536d69f3 |  | note | Frequency - Prior to sealing
label | 9f8e4f9f-c752-51d7-8bdb-f6a4a9129f2d |  | note | Activity - H
label | 272e3268-25e7-5506-8897-5d0b5eb0b69e |  | note | By - PE
checkpoint-status |  |  | checkpoint | 28.07.02 - Sealing Inspection
label | e13f8aab-ed03-55f5-8e78-f98b839e92bf |  | note | Acceptance / Conformance Criteria - Before sealing and resealing. A pre-seal walkover with the Engineer to ensure that the surface is swept clean of loose aggregate, dust, dirt and other deleterious matter and the sweepings shall be removed to the satisfaction of the Engineer.
label | 281850fc-cf15-536b-9f5f-324fb470bcf2 |  | note | Standard / Specification - PS - 2.2.16
label | 0f39351b-d7e3-58fa-b711-5f9a347a6ac9 |  | note | Verifying Document - Hold Point Release
label | 112d7768-c8f8-57bb-ad76-f1cf1b734677 |  | note | Frequency - Min 48h Notice
label | f44c5759-933f-5e05-a26f-09374ba9092f |  | note | Activity - HP
label | 157cd6f5-9fae-5594-9f70-b18acffa1e96 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 28.07.03 - Presealing Requirements
label | 6bfc3f46-9301-5932-903b-18a175248417 |  | note | Acceptance / Conformance Criteria - Further to Clause 12 of NZTA B2, the degree of saturation of the basecourse prior to sealing shall be less than 60%.
label | e43ae18f-91be-5454-a63a-b509872abb85 |  | note | Standard / Specification - PS - 7.3.4
label | 481fc55c-a247-558a-abe5-eef34f4994ac |  | note | Verifying Document - NDM Report
label | 7e15df9c-a8d2-5ecc-adfc-72c8a3ed2d1b |  | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
label | 2a6f4a94-045d-5ea9-8ab1-787a40b218e3 |  | note | Activity - HP
label | cc0fc382-4bdc-54b7-acb7-8d673f72ea57 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 28.07.04 - Adhesion Agents
label | 714e7f71-3f88-5c80-b683-ebba7a9bc233 |  | note | Acceptance / Conformance Criteria - An adhesion agent approved and blended in accordance with the requirements of TNZ M/13 Specification for Adhesion Agents shall be incorporated in the sealing binder.
label | 9fcef9d2-abf5-544d-966d-7797e5229986 |  | note | Standard / Specification - TNZ M13
label | 5a1c992a-9d0e-54bb-b63c-2f47a5134230 |  | note | Verifying Document - Site Notes
label | 9a6c9667-0e13-5c8f-bf79-8ba0f02bbb4f |  | note | Frequency - Prior to sealing
label | 957e939a-0437-509b-9cd1-d721bd205a3a |  | note | Activity - R
label | 9c44be23-e462-51a2-a526-12d7653abe12 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 28.07.05 - Post Seal Inspections
label | 4de718da-c59f-5c40-8b3e-057ea10e2816 |  | note | Acceptance / Conformance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
label | 0f87b092-2b0d-5b7e-a8a5-64a8d21119e3 |  | note | Standard / Specification - TNZ P3
label | 0dce8072-911c-516a-9a63-42116abbb3b3 |  | note | Verifying Document - Engineers Acceptance
label | b8cb5257-62e6-54ed-bd7e-097972155e2d |  | note | Frequency - Prior to TM removal and after final sweeping
label | c39f97eb-0abf-51ec-84e4-bd67e0b31185 |  | note | Activity - HP
label | 30538ae5-fdf0-507d-84f3-4cb464919235 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 28.07.06 - Bedding in Chip
label | 73313444-c073-515b-88db-5885511e9ac4 |  | note | Acceptance / Conformance Criteria - If no traffic on site to bed in Chipseal, 3 days of constant rolling with PTR's and laden HCV's will be applied to bed in the Chipseal.
label | f4f59b8c-77bb-5856-a645-e4801f47a3e2 |  | note | Standard / Specification - PS - 7.3.4
label | 11d7b076-b24b-566a-9534-0d19043973b9 |  | note | Verifying Document - Site Notes
label | f72333df-bde2-5b2d-aeeb-28a6b881847b |  | note | Frequency - Post Sealing
label | 81931cdd-bf2c-5546-b7ee-38044ba55f72 |  | note | Activity - R
label | 4ddec918-3ba6-5820-8ba0-fddba1a45d6f |  | note | By - SE
checkpoint-status |  |  | checkpoint | 28.07.07 - Surplus Chip Removal
label | ef706484-67aa-5993-8ad5-a5d28c1bc76c |  | note | Acceptance / Conformance Criteria - If no traffic on site, removal of surplus chip will occur 2-3 days after rolling has been completed. If traffic on site, sweeping and removal of chip will be within 48hrs.
label | 2d0127d6-6d7d-5ab8-b035-c9fb11052ce8 |  | note | Standard / Specification - TNZ P3
label | 0019d5cd-a080-599a-bf39-6dbee283253c |  | note | Verifying Document - Site notes
label | 2e4999ee-a3e4-5d3a-80ba-71327225d785 |  | note | Frequency - 24 hours of completion of any section of seal.
label | 7c70c37b-7cdb-5548-8118-d8554ac64740 |  | note | Activity - R
label | 777fa846-33d2-508b-b217-ca42693a2721 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 28.07.08 - Chipseal Repairs
label | 01937e39-1bfb-59ba-95cf-cfd96da7518d |  | note | Acceptance / Conformance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used
label | 42158fc7-a86e-52a8-9201-74679aeb85d9 |  | note | Standard / Specification - TNZ P3
label | 0bf8e279-9ac8-50a4-a204-62abf8cf26b6 |  | note | Verifying Document - Approved repair Methodology
label | ee3b471d-6939-5602-9644-fd38c86c7090 |  | note | Frequency - Prior to repairs
label | c0d25fdd-a140-5c55-b79c-71845879df7e |  | note | Activity - HP
label | 0eda0423-5ccc-58ca-9b86-55421513367d |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 28.07.09 - Weather
label | 2b32c452-707f-5c90-8adf-e5750f1e15d6 |  | note | Acceptance / Conformance Criteria - Ensure that weather is suitable prior to spraying & pavement temperature checked. Pavement surface temperature ≥ 10C.
label | 8859ee9a-271b-54c7-9124-9a3ab5113dfa |  | note | Standard / Specification - Requested by BBO
label | c9d1dee2-1f09-54e4-9743-1ace0a24604f |  | note | Verifying Document - Site Notes
label | 6195f572-a5aa-5e68-b3d2-b075afb7b1af |  | note | Frequency - Prior to sealing
label | c0d4ec4c-7ad4-5001-8a51-1a76af47a494 |  | note | Activity - C
label | ff877007-8fb3-5893-a34e-f93cbf8806f1 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 28.07.10 - Protect Road Furniture
label | 33905c35-66dc-5422-bca0-d10eba9003dd |  | note | Acceptance / Conformance Criteria - Paper cover any concrete that could get sprayed by bitumen such as kerbs and barriers
label | 813f33b5-0cc5-54d5-bae0-6d8c6db63a43 |  | note | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – 11.2.5.
label | 1ae76e23-a4e2-5798-9c4e-a7d3daab8da7 |  | note | Verifying Document - Site Notes
label | 02b452e3-3c94-547a-925b-3721bb9b11d9 |  | note | Frequency - Prior to sealing
label | ae6f69cf-c324-5cca-980e-1cc39acec6a2 |  | note | Activity - C
label | 38846de8-a4de-51fc-8ce9-b2da71097d02 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 28.07.11 - Joins, Overlaps & Hand Spraying
label | 5b9230a4-10bd-582c-bdd1-7427ce9045f6 |  | note | Acceptance / Conformance Criteria - Set up Spray Plan ensuring joins, overlaps and hand spraying is kept to a minimum; joins are not in wheel paths and overlaps are appropriate for curves, channels, straights
label | ef6da712-6974-5b5f-9560-3774b85e7112 |  | note | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – Section 11
label | ac3922fc-604e-5bf5-a54c-858085c3c2f0 |  | note | Verifying Document - Site Notes
label | 380f76ed-c2ca-5f93-8d62-d09c60583e4a |  | note | Frequency - Prior to sealing
label | 3cd1d841-702e-556f-8455-3c4a6a081375 |  | note | Activity - C
label | a6f72d9f-ead0-5257-bb80-bd4acd5db742 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 28.07.12 - Binder Temperature
label | 0369770c-20bf-5e77-9cbc-4c9b666ce9af |  | note | Acceptance / Conformance Criteria - Temp. appropriate to base binder and additives +/- 10 degrees. Daily records
label | dd4e915f-62e4-5296-9b92-4a7572e088ae |  | note | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – Section 11
label | f9948422-218b-57c0-a169-db3d459da9f7 |  | note | Verifying Document - Site Notes
label | e2481c47-962d-5dd4-a274-5239383c5218 |  | note | Frequency - Prior to sealing
label | e514c9ce-b115-5273-afd5-6ccc70480e1b |  | note | Activity - C
label | 9d75c0b4-1a1b-5a7c-ae77-8edd53c6ae5e |  | note | By - PE
checkpoint-status |  |  | checkpoint | 28.07.13 - Binder Application Rates
label | 16b8e348-6a57-51aa-9757-4e828599a2c8 |  | note | Acceptance / Conformance Criteria - Confirm spray rate is correct by comparing actual spray rate to that calculated. Note error in measurement increases as area reduces. Within 0.1l/m² from target on spray run.
label | 8fe8f093-73ea-5fc8-bb93-56349251e1e6 |  | note | Standard / Specification - Requested by BBO
label | 68c9a18f-0b99-505a-a999-e43d898af2e0 |  | note | Verifying Document - Site Notes
label | a2d0ac60-2a79-540d-b9d4-cf395a3e735b |  | note | Frequency - Daily
label | 89d74fa4-a686-5c5f-b459-13ce3afb2eae |  | note | Activity - C
label | f18395c8-2757-5cd9-ad6b-67b6412136dc |  | note | By - PE
checkpoint-status |  |  | checkpoint | 28.07.14 - Chip Application Rate
label | cebefc05-edac-519a-a52d-ba7f6e15b3c1 |  | note | Acceptance / Conformance Criteria - Monitor chip spread rate and compared to target, record volume of chip used
label | 134a9b0d-32ef-515d-b97f-4f8762d20b07 |  | note | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – Section 11.3.7
label | 60861daf-849e-59b6-8747-c19ed36c06b1 |  | note | Verifying Document - Site Notes
label | 0784a178-482e-5ee7-ba3c-8a3d13346758 |  | note | Frequency - Daily
label | 1d6ed067-6108-5e8e-87de-b6d4278e8d60 |  | note | Activity - C
label | 39a55291-edb7-56fb-8bea-114c65df0b67 |  | note | By - PE
checklist-sectioned |  |  | checklist | ITP - 114 - Footpath Construction Rev B | itp |  |  |  | Yes | ITP - 114 - Footpath Construction Rev B | 670305c0-583f-4333-98b7-bec1651ba9bd
checkpoint-group |  |  | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 - Site Requirements
checkpoint-status |  |  | checkpoint | 3.01.01 - Construction Pack
label | ce5284c7-af2d-529e-9acd-6ec3ffb48e55 |  | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
label | 351562d1-6be9-57f5-a2a1-90f7a1de99c7 |  | note | Standard / Specification - Downer
label | 5a6d6486-ffec-5112-abc7-f47263382980 |  | note | Verifying Document - Construction Pack
label | db83dee9-c593-52bc-a602-a6cadf51d587 |  | note | Frequency - Submit 10 days prior to commencement of works
label | f1eb0f48-6a23-52f4-98e0-e3236e6e8124 |  | note | Activity - HP
label | 9c8b9328-ba74-5759-9146-307748f2deae |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.01.02 - Survey Setout
label | 4f71c412-f4d9-5424-be4a-38cecbf3a2ae |  | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | ecd7cf5c-246e-5523-9530-b5ac0afce4c3 |  | note | Standard / Specification - Downer
label | 23415da0-6c29-58f4-91e9-27f1db880189 |  | note | Verifying Document - Survey Records
label | 367bc75c-07f2-54c5-82ef-82ebac414fca |  | note | Frequency - Prior to Works
label | 3f9d6745-524d-5c0f-9f9e-e00336e8723a |  | note | Activity - H
label | 06f3dcac-1bec-5cc5-bb25-44064608dba7 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 3.01.03 - Service Location
label | af821ed1-3204-55d2-ba32-4e8fd4b8731f |  | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | 019d9f89-86ac-56b9-b69e-c6689f37786a |  | note | Standard / Specification - Downer
label | e9f13907-7099-5fc0-93b3-9e29f29ca377 |  | note | Verifying Document - Excavation Permit
label | 4e839873-9cd7-5043-9740-f050b3a36d73 |  | note | Frequency - Prior to Excavation
label | f6ce9bea-ef92-543d-8768-b0cf3de2e03b |  | note | Activity - H
label | 65bb7491-2f5d-5b9d-9714-5edf55aa18a3 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.04 - Internal Permits
label | d96df4ad-67ee-567c-b3e6-cbe90d1e2e84 |  | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | c790c451-26c9-50f7-a4c9-d677f961b25b |  | note | Standard / Specification - Downer
label | 57e06db8-d314-5a24-996f-9ca6d49aaeee |  | note | Verifying Document - Internal Permits
label | c8cb4af0-690d-5c60-a2ac-f11d47ce54c7 |  | note | Frequency - Prior to Excavation
label | 0c71dc81-2b73-5fb6-9d2e-8ea5f544d523 |  | note | Activity - H
label | 6ea247ce-2e7e-59b3-ae88-b640f7987ec7 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.05 - External Permits
label | 8f833f4b-5061-5ae6-a522-f5f7164954d7 |  | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | 48e6ca0e-685c-5a45-9bec-86009bdb3e80 |  | note | Standard / Specification - Downer
label | be490c86-2175-553f-9801-0d1b5d5e5690 |  | note | Verifying Document - External Permits
label | f90cf7da-aa05-56ba-88d5-f09dd8f19558 |  | note | Frequency - Prior to Excavation
label | 0aa33499-6971-597d-b391-87306aa055e1 |  | note | Activity - H
label | 52769e5d-c5ad-540a-8f47-f78f8bba2793 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.06 - Approved Construction Drawings
label | 2fef669d-2fa1-5fe9-9686-0b9e5a3adf42 |  | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | 98d59d68-4988-5e46-a739-d42e96b5479e |  | note | Standard / Specification - Downer
label | 76a8fc04-ad6c-53b7-96fd-1db1d14ae33f |  | note | Verifying Document - IFC Drawings
label | a27455cf-46c0-5643-be87-e2c99e316aaf |  | note | Frequency - Prior to works start
label | ff94ef36-92ec-5834-82bc-4454151210f4 |  | note | Activity - H
label | 7c42344c-de3d-5823-87a1-fac75afdf675 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.07 - Previous Completed Work Packs
label | da7166a4-431d-55a0-ae99-d8950516c21a |  | note | Acceptance / Conformance Criteria - Review previously completed workpacks to ensure work completed meets the contract requirements
label | 8d486b5e-27ae-5c1e-9584-8249cf992fb6 |  | note | Standard / Specification - Downer
label | d0b5cd3e-3506-522b-b6dd-ac02ad557d85 |  | note | Verifying Document - CONQA
label | 24b235fb-91b1-55c5-b134-b0d11fbb7d2a |  | note | Frequency - Prior to works start
label | 7c5220b5-f554-5315-8e16-be315e901353 |  | note | Activity - H
label | 1b2d4d84-9278-5b0f-a62e-6c709860ee28 |  | note | By - PE
checkpoint-group |  |  | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 4.01 Sub Activity
checkpoint-status |  |  | checkpoint | 4.01.01 - Bedding Sand
label | e1226926-429c-594f-962e-99cb82b9bdaa |  | note | Acceptance / Conformance Criteria - Record material type used and source testing of that material
label | 1f48d203-bdad-5681-853d-4716eac5a361 |  | note | Standard / Specification - BBO
label | 01ecc247-fb68-54b5-91a3-f911bd3bf5b5 |  | note | Verifying Document - Source Test/Site Notes
label | c3a5a8fe-74db-53b6-aa5e-56199009a08d |  | note | Frequency - 1 source test per material type
label | 3cdc5de5-8449-591b-81d2-37302573b3e2 |  | note | Activity - R
label | 52244458-0278-561b-bb96-4e1b8ad41ffc |  | note | By - SE
checkpoint-status |  |  | checkpoint | 4.01.01 - Undercut Backfill
label | 1ada175c-0e6c-5bef-8cf2-e274ce0d201e |  | note | Acceptance / Conformance Criteria - Record material type used and source testing of that material
label | 388d2ba7-1567-5ba8-80bd-ad1403a1fb90 |  | note | Standard / Specification - BBO
label | 50497f66-815a-5188-b1fc-3a7a56cff965 |  | note | Verifying Document - Source Test/Site Notes
label | 1b33edc8-73da-5d3f-b973-824077cb9694 |  | note | Frequency - 1 source test per material type
label | 59430bc5-bbc0-509d-a9cf-799c20b1e24f |  | note | Activity - R
label | 6d730eae-f596-57a2-95d1-b5297c57238c |  | note | By - SE
checkpoint-group |  |  | section | SECTION 5 – CONSTRUCTION ACTIVITY - 5.01 - Footpath Construction
checkpoint-status |  |  | checkpoint | 5.01.1 - Footpath
label | 87df6cff-9150-52f4-8f4e-b460bb53e57f |  | note | Acceptance / Conformance Criteria - After set-out and prior to installation of footpaths
label | 045ed956-718d-59ca-a233-0cb4ff073a44 |  | note | Standard / Specification - PS - 2.2.16
label | 73268c21-979d-5072-879a-2c1e760517d6 |  | note | Verifying Document - Hold Point Release
label | 24f26b00-03b9-52b9-ac50-90aee9287b65 |  | note | Frequency - Min 48h Notice
label | 73b646fc-b543-5076-a666-1efda5849508 |  | note | Activity - HP
label | 66332c55-8d87-5db6-99f8-f5ae783b95ea |  | note | By - SE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.2 - Subgrade Preparation
label | bb9313c5-53ef-59ac-bc5a-c524c2b15c64 |  | note | Acceptance / Conformance Criteria - The exposed subgrade (excavated to trial subgrade level or pavement depth) shall be tested by using a Scala Penetrometer for compliance with a CBR value >10 (4 blows per 100mm)
label | a0c62e94-6b18-59cd-945e-60dd7363dd8e |  | note | Standard / Specification - RITS - 3.4.9.4
label | 6a55b29c-ef44-5495-92f7-38cabf543236 |  | note | Verifying Document - Scala Results
label | f4f9195d-bb3b-5220-ad16-effb38497ecd |  | note | Frequency - Every 15m
label | da7f1d8b-983c-5ba7-8ba9-658d90e76999 |  | note | Activity - I
label | da6e6413-b571-5c5a-9533-d24f66bed276 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.3 - Subgrade Undercut and Subgrade Backfill
label | 1b9bb59b-f2bc-5821-89f1-1829e8f9f3ca |  | note | Acceptance / Conformance Criteria - If subgrade does not meet the requirements of a CBR > 10 (4 blows per 100mm), and undercut and backfill of the CBR will be required. Backfill material will either be GAP or sand material and will be instructed by the engineer.
label | 40aaf3d2-a6e2-5325-af34-6072b05658bc |  | note | Standard / Specification - RITS - D3.3.5
label | 11fb04f6-fd2d-5fbe-9928-99afb580c869 |  | note | Verifying Document - Hold Point Release
label | 5bc9ff8c-7d6d-5f14-b2ae-5e927b65d288 |  | note | Frequency - Every 15m
label | 4bf00c67-c95a-534e-beb5-dce6b1084b20 |  | note | Activity - HP
label | 922dce0a-f6d6-509d-93c9-84e6132b2a85 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.4 - Subgrade Backfill Fill Compaction Testing - Aggregate Subgrade
label | 5e1c8060-3239-517f-b79e-d796aaa1f784 |  | note | Acceptance / Conformance Criteria - Aggregate Subgrade Fill shall be compacted to Clegg Impact Value (CIV) 15
label | 5b19ab62-ede7-57e1-b588-ff92f513f966 |  | note | Standard / Specification - RITS - 3.4.6.5
label | d5196ad3-c7a3-5031-befd-092d0bad6076 |  | note | Verifying Document - Clegg Results
label | 5421eec4-6911-5b15-b886-70a328b74561 |  | note | Frequency - Every 15m
label | b1c9f53a-a48b-5415-a1c1-0ffbad81cd92 |  | note | Activity - I
label | 712e3587-fd40-5f4e-a449-a464158d0c59 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.5 - Bediding Sand
label | 898b9b6e-5251-5e27-b84d-e7ef46583e4e |  | note | Acceptance / Conformance Criteria - Bedding Sand to be placed at a consistent thickness of 75mm free of foreign materials, bedding surface must be level and free of any peaks or troughs
label | 0907a616-cae8-5b56-b766-b2bb240362dc |  | note | Standard / Specification - RITS - 3.8.3.3
label | 73139c0a-8565-59f2-b8a2-4f396af58e13 |  | note | Verifying Document - Site Notes / Photos
label | 8ec36ad8-2eee-5081-8f9a-583ec83f48b8 |  | note | Frequency - Every 15m
label | 1db253e7-1fc2-5821-9b36-b520e490e789 |  | note | Activity - I
label | 1f149fc6-c2fd-50a0-a6a8-3af067210be4 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.6 - Concrete Pre-Pour
label | eeac9f18-9036-5812-9937-730b30252219 |  | note | Acceptance / Conformance Criteria - The Contractor shall give due notice to the Engineer of the time it is intended to place any concrete and no concrete shall be placed until approval has been obtained from Council.
label | 4afd2489-822f-5cae-b486-590641667334 |  | note | Standard / Specification - RITS - 3.4.5.3
label | 50189b59-5091-5422-b9bd-798a5f0a8e5f |  | note | Verifying Document - Hold Point Release, Pre-Pour Check
label | f92e6219-d0cc-5ddb-b96e-323df356d3b1 |  | note | Frequency - Min 48h Notice
label | 886439f7-e505-5825-ac09-3872edf1a489 |  | note | Activity - HP
label | 0287aadd-6648-5077-a2d9-59647c8f3134 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.7 - Ground Preparation
label | 955dea00-b2e9-5c44-9ef2-78a9e100eedf |  | note | Acceptance / Conformance Criteria - Immediately before placing the concrete, the foundations shall be lightly dampened, and formwork shall be cleaned out. In all cases surplus water shall be removed before concrete is placed.Any foreign or organic material shall be cleaned out.
label | 2be0f46a-270b-5441-9f78-b88fa06c1712 |  | note | Standard / Specification - RITS - 3.4.5.3
label | f5f979be-859b-56ed-8ad4-6046e3ee6887 |  | note | Verifying Document - Pre-Pour Check
label | 072374df-ff13-5c27-9d2a-279c6526a4ed |  | note | Frequency - Each Pour
label | 8d443340-6a04-5d9a-9b45-97cda6f3a4a1 |  | note | Activity - H
label | e2f2916f-bfa5-5092-8d73-252243305eaa |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.8 - Frozen Ground & Unfavourable Conditions
label | 240798d5-5645-5742-8a9f-607fbe3971cf |  | note | Acceptance / Conformance Criteria - Concrete shall not be placed on frozen ground nor shall it be placed in unfavourable conditions, which may be detrimental to the quality and finish of the concrete (i.e rainfall)
label | 43bd83ac-2572-5183-8894-44f3d96d21b4 |  | note | Standard / Specification - RITS - 3.4.5.3
label | 68549b75-f80c-5fee-a15a-605038807a6d |  | note | Verifying Document - Pre-Pour Check
label | 94ed8cd1-303b-5b11-bc17-589e7e799173 |  | note | Frequency - Each Pour
label | 8e2024b6-338d-573d-96da-f21e306e7138 |  | note | Activity - I
label | 8f41a3a1-e13f-5b3e-9557-e2dc960d3548 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.9 - Curing Of Concrete
label | 7b0506c4-fbea-51f1-bf28-698579515344 |  | note | Acceptance / Conformance Criteria - Immediately after placement, concrete shall be protected from premature drying, excessively high or low temperatures and mechanical damage and shall be maintained with minimal moisture loss for the necessary curing period and hardening of the concrete. In hot dry weather sprinklers or damp covers will need to be used.
label | df50fab9-c0f7-513a-bbb5-de0ced2b1bc9 |  | note | Standard / Specification - RITS - 3.4.5.5
label | e6298ec8-a5e6-5088-a5da-f5bba4a20c56 |  | note | Verifying Document - Post Pour Check
label | e17b0b60-f439-5ea9-9585-d5130438d714 |  | note | Frequency - Each Pour
label | 785fced2-0338-59f7-80e0-5eb43b95a71e |  | note | Activity - I
label | a1248d1f-1114-546e-a761-9f98704a38c0 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.10 - Concrete Compressive Strength
label | 126f30a0-7173-5dca-9c71-6aa5392eab45 |  | note | Acceptance / Conformance Criteria - Concrete to meet a placed 28-day compressive strength of 20-Mpa
label | a6647773-4132-5272-909c-c1ab1add4a52 |  | note | Standard / Specification - RITS - D3.3.5
label | 8f725eda-f28c-575a-bcde-30dcbcd20f3c |  | note | Verifying Document - Concrete Dockets
label | 60ef0079-98be-594d-a669-f4be24fd41dc |  | note | Frequency - Each pour
label | 08ec14ed-9ebd-5d0d-9f4f-7fc9502ea89c |  | note | Activity - R
label | 1e9d039b-480d-5127-a51e-fff86c8bed4c |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.11 - Finished Work
label | fe6f5a11-c908-52a1-938f-460cd9c0f8b0 |  | note | Acceptance / Conformance Criteria - Methods shall be used that will provide a smooth, clean and even surface on the exposed faces of all concrete work.
label | b7a68477-03d7-58b2-8f02-66ff8f6d634a |  | note | Standard / Specification - RITS - 3.4.5.7
label | 313b25bc-ad5e-5784-baee-c15211ff8daf |  | note | Verifying Document - Post Pour
label | 6c43aed2-8f84-56de-9028-ac3910f744f6 |  | note | Frequency - Each Pour
label | f75df3ca-2395-52b1-8d71-9487a9b7eedf |  | note | Activity - I
label | 44cf6397-57b4-568b-b8bd-b3b9ef22d565 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.12 - Contraction/Expansion Joints
label | 6a775d3b-5758-5070-ace9-f3d5ec9cc1eb |  | note | Acceptance / Conformance Criteria - Contraction/Expansion joints shall be formed or cut along the kerb at a maximum spacing of 3.0m. The slot shall penetrate the concrete by not less than 50mm and the mortar dressed over the cut face. The contractor shall ensure that cold joints are accurately marked and set out via total station so that the subsequent saw cut is in the cold joint. Should cracking occur adjacent to the saw cut a minimum section of 1.5 metres of the footpath shall be removed and re-cast.
label | 29c98797-12b0-51d9-8fe5-c8ab27c292d8 |  | note | Standard / Specification - RITS - 3.4.5.8
label | 5f655169-cd8e-51bb-bb0a-69de9d3fe1c5 |  | note | Verifying Document - Post Pour
label | 51a01500-016f-5bd2-b2c5-8c6a7a8c9b9a |  | note | Frequency - Each Pour
label | abe05d06-8549-5dc0-bab9-aa27230a6fb5 |  | note | Activity - I
label | 8ecfac3a-ec12-58e4-8bd9-29473e9601a8 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.13 - Backfilling against Concrete Work
label | d11f5586-c5c9-5f71-beae-1c199d6008bf |  | note | Acceptance / Conformance Criteria - Backfilling against the poured footpath shall take place as soon as practicable after the concrete has reached sufficient strength, with particular emphasis at curves, corners, intersections and pedestrian kerb crossings but not prior to 36 hours after pouring.
label | 0d10d705-4ed7-5c84-a8f3-b833192f4aa1 |  | note | Standard / Specification - RITS - 3.4.5.9
label | 6e141db8-3130-53a5-9895-f0cc0b7aad57 |  | note | Verifying Document - Site Notes
label | d72556a9-a38b-5ba4-b2e5-0e31285af35d |  | note | Frequency - Not prior to 36 hours after pouring
label | 3cf19196-701c-5e5d-a4ee-764329620ffa |  | note | Activity - I
label | a876d563-56d1-519c-8ce8-6663eb4b3538 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.14 - Finished Concrete (Surface Finish & Final Levels)
label | 39e9b9c1-18ef-5983-a0e8-b7b4a0a8149d |  | note | Acceptance / Conformance Criteria - All final path and vehicle crossing surfaces shall be true to the lines and levels Specified and ‘broom’ finished.
label | 9d8f96e1-9bd2-59b3-90bb-8afb5feab005 |  | note | Design considerations aside, the final surface shall not vary by more than 5mm when checked with a 3m straight edge. No finished surface shall hold water.
label | 0e6bcd81-9749-528e-b559-18cd42691988 |  | note | Standard / Specification - RITS - 3.4.5.10
label | 3e7a0871-1eb2-5dcc-8917-e55de59f1c0d |  | note | Verifying Document - Post Pour Check
label | 35efb868-bd76-5de2-9bd7-d2d38d750fca |  | note | Frequency - Each Pour
label | e3174e0b-e036-5c55-ac66-9bb138488758 |  | note | Activity - I
label | 9bbe291a-4b09-5e2c-9140-235b645b6509 |  | note | By - SE
checkpoint-group |  |  | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 6.01 - General
checkpoint-status |  |  | checkpoint | 7.01.01 - Construction Record Compilation
label | 66a905ef-67fd-5577-9a07-1c6eb5d9f84f |  | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | 7ef3391f-aa1d-567a-99c4-7a2f909a6923 |  | note | Standard / Specification - Downer
label | 3f9c50f8-ae85-5327-baaf-0e91dfaa5081 |  | note | Verifying Document - Records
label | c8332514-2bd9-507e-a938-7e75a58cb1c2 |  | note | Frequency - Post construction
label | fadad837-b793-5499-958f-6bbb5fcd9bde |  | note | Activity - H
label | 3295bdaf-8b72-5cb5-8139-990564ce17d7 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 7.01.02 - Survey Records
label | 7a4f52a0-cd0b-5fa0-bf31-4f8b7d021a0a |  | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | f18df727-6fa5-5726-a49e-bd8f7e5e4b75 |  | note | Standard / Specification - Downer
label | d80c503c-1987-5ae1-b647-6fdb82cec402 |  | note | Verifying Document - Records
label | fe6e2180-4efc-5918-bf4c-63501e87e517 |  | note | Frequency - Post construction
label | 139ecf52-71c9-5073-b035-35a7e1477ce4 |  | note | Activity - H
label | cd75a03c-9c8c-5818-a845-e1e9531da55b |  | note | By - SV
checkpoint-status |  |  | checkpoint | 7.01.03 - Redline Drawings
label | 4c6290cf-839f-5763-9a5c-7804fdab4b5c |  | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any changes to footpath location or basecourse depth.
label | d0eece7e-d556-5eb0-958f-e221547ec3fc |  | note | Standard / Specification - Downer
label | da045d72-d79a-5ac7-afb9-a36da44bd43a |  | note | Verifying Document - Redlines
label | b76c2f29-b580-5d90-a029-494d807f2995 |  | note | Frequency - Post construction
label | 6387ecfa-7d2c-5d4a-8330-3e6f14310148 |  | note | Activity - H
label | b615ee2a-9ea1-5aa9-bd0f-90ff5d3526e3 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 7.01.04 - Defect, Snag and Punch List
label | 67ccddcc-a441-5a00-9e8b-0a8be75384b9 |  | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | 4415ff06-d7c8-5fcd-bef1-c2884ed83a47 |  | note | Standard / Specification - Downer
label | ed5f01e7-9815-5abb-8b01-1f10e8d18694 |  | note | Verifying Document - Register
label | cbf60885-6788-5f0c-83d5-f2e33d34ae14 |  | note | Frequency - Post construction
label | 32a5d262-0d30-57f3-b2dc-f5fcb00addb2 |  | note | Activity - H
label | 0b6639fc-aad3-5a9e-b281-d0385eee7f91 |  | note | By - PE
checklist-sectioned |  |  | checklist | ITP - 107 - Pavement Drains |  |  |  |  | Yes | ITP - 107 - Pavement Drains | 6a922d6e-460a-401f-a8b8-39505e8a4626
checkpoint-group |  |  | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint-status |  |  | checkpoint | 3.01.01 - Construction Pack
label | eef00716-4e5d-5b03-b172-716ad54d042a |  | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
label | 765b1048-c088-5b6f-9623-8c5346ff99e7 |  | note | Standard / Specification - Downer
label | 397a1e6d-4464-5f66-b1bb-bdf001298e8b |  | note | Verifying Document - Construction Pack
label | 05d4a935-0ef3-5cde-80aa-4d1301943a80 |  | note | Frequency - Submit 10 days prior to commencement of works
label | eac0916a-6ddb-5a54-949e-98cefbbc2210 |  | note | Activity - H
label | 806a65ec-353e-5e0d-935c-204f576001c3 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.02 - Survey Setout
label | 180417cf-f085-5ace-9953-f519ccf1706c |  | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | 96347aea-037b-5640-95a4-1d4dfc132a6e |  | note | Standard / Specification - Downer
label | 16eacf5e-a788-546e-a0cd-1aedc5ee8570 |  | note | Verifying Document - Survey Records
label | be32c357-44f6-529a-8363-67b4f3529304 |  | note | Frequency - Prior to Works
label | c4af63f6-c85f-59f1-809e-59bc586c641c |  | note | Activity - H
label | f104ef54-18ca-50f8-b622-564b36e5dd3e |  | note | By - SV
checkpoint-status |  |  | checkpoint | 3.01.03 - Approved Construction Drawings
label | c494c038-e47d-5ce7-b618-58b9f20e4c67 |  | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | c6ecdd42-653b-5c87-9072-43a0eadf906c |  | note | Standard / Specification - Downer
label | 4e3ba869-ecd5-51a9-8e80-40f8a3e0199e |  | note | Verifying Document - IFC Drawings
label | 988c6302-1576-5fe0-ad37-e6e63e58da1e |  | note | Frequency - Prior to works start
label | 4d176dba-b452-553e-a533-5a82796a3ab1 |  | note | Activity - H
label | 526d4aa1-d98f-5698-8a92-deeccd5de232 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.04 - Topographic surveys for measurement
label | f927db23-c857-5010-bccb-337cc5a5dab9 |  | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
label | 91b1b8ba-eb23-5cb1-89e8-90e6c32ba274 |  | note | Standard / Specification - PS 2.2.12
label | 795d7fbf-075a-5c81-8f14-b524bc83a870 |  | note | Verifying Document - As-built
label | 8e12b724-0f78-51b2-bdef-fa392fd5d083 |  | note | Frequency - Prior to works and Post Works
label | 46002215-7271-508f-b388-aa1c2f73fb15 |  | note | Activity - H
label | a41ac510-4c8f-5101-a059-58a692208e38 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.05 - Permits
label | 22e6ad25-092d-5548-a2d8-51e8a1593b0a |  | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
label | 409b7359-80e8-5acc-9198-5d34ac52ec2d |  | note | Standard / Specification - ITP Register
label | 1f3e89f2-4480-5fe8-b063-4a578a27d691 |  | note | Verifying Document - ITP Sign Off
label | ad52a87c-f310-5834-bdc5-abb31ce9ac1e |  | note | Frequency - Prior to commencement of construction activity
label | 5eb73539-c018-532f-b744-52ab274ca51f |  | note | Activity - R
label | a7fc22a5-8f14-5766-918d-63b3cecf0195 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.06 - Stakeholder Management
label | 6772a3a5-74ae-5849-b0e0-b36ea6baf81f |  | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
label | 435660c9-5625-5888-837f-0a6f88ce611a |  | note | Standard / Specification - Project Stakeholder Management Plan
label | 58ea1067-5df3-58c6-9b10-edbf2c8e408c |  | note | Verifying Document - ITP Sign Off
label | 74cc34a4-f0aa-5202-9a03-dd52ea46867e |  | note | Frequency - Prior to Construction with continue updates throughout the works
label | 89dcf2fb-9078-588c-aaa1-bf271fd79ee4 |  | note | Activity - R
label | 96a554b1-43eb-5bc7-8a17-143409cfd62e |  | note | By - SE
checkpoint-group |  |  | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint-status |  |  | checkpoint | 4.01.01 - Subsoil Pipes
label | 6d376193-63a5-5f57-8e40-316e71973266 |  | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 100mm diameter complying with NZTA F/5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
label | 34ad6500-373e-5051-9826-4a1d20223e96 |  | note | Standard / Specification - GWS 3.2.1
label | bc934418-5005-5ef9-bd0e-73582085601a |  | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
label | 84cc8e48-b25d-50dd-b493-0872459f881f |  | note | Frequency - Every Delivery to Site
label | 4d7be173-4c31-5cd2-8ec4-6235ebf15736 |  | note | Activity - C
label | c58e9fbc-5f93-5b00-8e1c-6ccd13b803d9 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 4.01.02 - Subsoil Drainage Aggregate
label | fcc12b20-cca2-512b-a937-1f951a99ded4 |  | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate). Be open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11 Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1: App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification: Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate) Test Sieve Aperture (mm) Percentage Passing (%) 53 100 13.2 10 (max)
label | fa485186-b96a-52c9-9058-24ec2e833fe9 |  | note | Standard / Specification - GWS 3.2.2 & 3.4
label | 061ef45c-ffd4-58e4-87df-e8fd7f8adeb1 |  | note | Verifying Document - PSD, CR
label | b8c5182b-9ee9-5d26-aedc-1ebac092ca1b |  | note | Frequency - Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required.
label | c09d35b2-6d0a-5e65-8a73-0442d1581335 |  | note | Activity - C
label | 8aeb1063-a1e3-53e1-bd84-41c3848cad13 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 4.01.03 - Filter Cloth
label | 4d00d963-e5b2-5ec4-bdbe-7b83a09ad16d |  | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
label | 3dbf25b6-cae4-5c3a-8e05-2898bf99e521 |  | note | Standard / Specification - GWS 3.2.3
label | c126941f-b768-5b30-ae2e-6798b6457186 |  | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
label | 4c219803-133a-5171-bab3-8ae8749045f5 |  | note | Frequency - Every Delivery to Site
label | 54eaf21a-b3ea-5116-b8f4-0d0045c266e9 |  | note | Activity - C
label | b5976aef-6260-5629-816e-6e4bacaedafe |  | note | By - SE
checkpoint-status |  |  | checkpoint | 4.01.04 - Securing Pins
label | d845c3e0-ef7e-5b4e-838b-d83b5a360f76 |  | note | Acceptance / Conformance Criteria - Pins for securing the geotextile shall be of steel, a minimum of 5mm in diameter and at least 400mm in length
label | 8521468b-b01b-5e26-93aa-3e63694682c7 |  | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class,.
label | 24f277e3-b638-5d86-91c5-3dd99a8884dd |  | note | Frequency - Every Delivery to Site
label | 335ffb25-ee69-51f3-a9b7-28e2ed59402a |  | note | Activity - C
label | 9c92a1d5-c2c7-544b-8af9-16d4f18d2241 |  | note | By - SE
checkpoint-group |  |  | section | SECTION 5 – CONSTRUCTION ACTIVITY
checkpoint-status |  |  | checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
label | 6811ea07-5a89-50d9-81a0-240052de7a0d |  | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain. TNZ F/6, PWRBSS Geotechnical Specification - The geotextile shall be placed in the tench so as to conform loosely to the shape of the trench. Cloth must fully encapsulate the aggregate. Geotextile longitudinal overlap to be minimum 300 mm (as indicated on drawing 3051 and required by NZTA F/6). Additional sheets to overlap by minimum 500 mm and anchored with securing pins (F/6 requirement). Verifying document, photos of trench prior to backfill, every line.
label | ec53cdb7-cc25-54c6-b78e-5e162d0a5055 |  | note | Standard / Specification - GWS 3.2.2
label | 4fcd2436-ca61-55b6-9fe5-fe0251ec6f08 |  | note | Verifying Document - Every line
label | 5b1a35ef-fdc0-5fab-867b-ab02e3ba5f75 |  | note | Frequency - Photos of trench prior to backfill
label | e8addc07-99ec-5073-b4b5-509d0438c645 |  | note | Activity - HP
label | 36b45a2b-5f18-58e7-9e19-1aeca008b0c0 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.02 - Trench Backfill
label | 5a6ef704-1262-5cee-8cd3-1ca88e235869 |  | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through. Drainage aggregate to be placed in layers of 150mm or less. Only light compaction such as tamping with the back of an excavator bucket is to be applied.
label | 3948db19-ece7-585a-af0f-11b4d7488df2 |  | note | Standard / Specification - GWS 3.3
label | d255d60e-c712-5220-9d3c-cb1bb86d98e7 |  | note | Verifying Document - Site Record
label | facea8de-cba0-5eaa-81b6-121bf1de9fe3 |  | note | Frequency - Each trench
label | cfd6590f-8894-55b7-86ae-a17a69dd2407 |  | note | Activity - I
label | 7c6101e5-bd07-56fa-a1d6-fc30d486d76a |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
label | e0e0dfdd-c152-5d0c-9412-91a6bd87c0fb |  | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete.
label | bc1e3839-cba4-575f-a42b-a8f7f6333d04 |  | note | Standard / Specification - GWS 3.6
label | af9a4333-12f2-5026-b386-959aed450a8a |  | note | Verifying Document - Site Records
label | f4c8e8e7-af68-5172-8727-d91b9dd9213b |  | note | Frequency - Each Subsoil Line
label | d5c01f6c-5dd3-57ae-a617-02ae9b57ca57 |  | note | Activity - I
label | aaed1beb-c26a-539c-a9dd-5c85e83ad979 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.04 - Subsoil Flushing
label | 8d739b34-85cd-547a-8247-18cc3b18c86b |  | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
label | 1d5f0a20-d2df-5e6f-b48a-0e7cdb078918 |  | note | Standard / Specification - GWS 3.6
label | 4beb6424-e2fd-57df-a7c9-4d3712506bf3 |  | note | Verifying Document - Site Records
label | 5719ebbd-4e3f-5c51-a425-06bc997661d4 |  | note | Frequency - On completion of earthworks
label | f9a6100d-206f-59c5-b591-faca25ca1a54 |  | note | Activity - HP
label | 41c18113-5b1c-5d8e-8d40-7bff82d6cc82 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.05 - Survey
label | 73f805ec-1be1-5740-aa84-faa7472fe6ac |  | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | 719cc0d7-da0b-50cf-b857-21dac2d03368 |  | note | Standard / Specification - Downer
label | 80ec50c7-3501-5099-aad9-d3107d575a5b |  | note | Verifying Document - Records
label | 38279792-2520-5b5f-ad7e-c1d3dde7b3a6 |  | note | Frequency - Post construction
label | 9dcc6c76-d7ee-5853-8a71-9bc96d68aa03 |  | note | Activity - H
label | 0123bb12-7443-55a7-be46-bb5296d14b9d |  | note | By - SV
checkpoint-status |  |  | checkpoint | 5.01.06 - Excavation
label | 4f174c16-c79f-5a5f-bc71-b199753d4ed3 |  | note | Acceptance / Conformance Criteria - Trenches shall be cut in such manner as will ensure that the geotextile wrapped aggregate pavement drains, and pipes if included, will be laid true to the depths, grades and lines shown on the drawings
label | c2c9c1ae-73f5-5d4c-8575-26ff0a4b5f5a |  | note | Standard / Specification - Downer
label | 6cf18612-24aa-5169-8377-5ee893f5aafa |  | note | Verifying Document - Records
label | 050f8690-1a18-59af-a187-0ae929cb0cd6 |  | note | Frequency - Prior to laying filter cloth
label | 59222acb-af43-5e0d-a2a8-9d1ecc17b8de |  | note | Activity - I
label | f93a0bce-6383-52de-b82c-c023bba5a452 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.07 - Bedding
label | 2876f6cf-4450-58ef-a4e2-7e7506c0a1eb |  | note | Acceptance / Conformance Criteria - TNZ F/5 - Bedding thickness shall be no less than 100mm
label | 8da47c77-5900-5d5c-939a-24a45d93b9c8 |  | note | Standard / Specification - Downer
label | e1e57d95-3cfa-5486-9252-177719884e87 |  | note | Verifying Document - Records
label | 99282874-7427-5646-80c4-cf2d5c909736 |  | note | Frequency - Prior to laying Novacoil
label | 1cde5baa-6f9e-594b-a1a1-92fe408db88b |  | note | Activity - I
label | dec6f213-96b0-5480-b5d3-821cf0ca163b |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.08 - Joining Pipes
label | 0ef64d31-9581-5189-b3ad-fac7edb017e9 |  | note | Acceptance / Conformance Criteria - TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations
label | def28e6a-7bc3-51ba-a899-fd9dc500b9c1 |  | note | Verifying Document - Copy of delivery dockets, photos of pipes onsite with tag showing class
label | 260824f4-3576-52b7-a7c0-82ca028678f3 |  | note | Frequency - Every join
label | d30d276f-a5c3-59dc-887d-a339a38e82d2 |  | note | Activity - I
label | 532c1d45-176c-5ea0-83bb-5e82f111d571 |  | note | By - SE
checkpoint-group |  |  | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint-status |  |  | checkpoint | 6.01.01 - Construction Record Compilation
label | 41282f40-d6cb-5103-bf6e-958dd729ff05 |  | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | dd7a487e-b81d-579c-a71f-0077755339d5 |  | note | Standard / Specification - Downer
label | 1b01aacd-4fa9-5e67-bcee-f13a4f84057c |  | note | Verifying Document - Records
label | 93c49c84-ab62-5d90-b6fe-8220b0513eb4 |  | note | Frequency - Post construction
label | 443d80b3-29dc-5bc2-9371-f8aa81bb76cb |  | note | Activity - H
label | 24d1b142-e483-53ee-b2e7-c01e05550ac7 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 6.01.02 - Survey Records
label | 3989569f-afea-526f-b341-32ff9a57d0a2 |  | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
label | efdca4bd-743a-5bae-a775-15a6dc53a42e |  | note | Standard / Specification - Downer
label | 13d9852a-104e-5ddd-a414-a0b3c8436476 |  | note | Verifying Document - Records
label | 0fddb792-cd96-5f76-99a6-ec5d92f65f44 |  | note | Frequency - As-builts taken every 10m prior to backfill
label | bd9d5d94-7a2f-5dc0-b4ab-68c25b7e617c |  | note | Activity - H
label | 03d57b79-a84e-5ad6-8f79-e3d9e35c407c |  | note | By - SV
checkpoint-status |  |  | checkpoint | 6.01.03 - Redline Drawings
label | 09d83736-3d59-5664-876d-9b1e1a8010df |  | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all subsoils, including temporary subsoils that become part of the permanent works, to show all outlet locations
label | 183aab9b-8a98-55b8-a516-5e4f702ae200 |  | note | Standard / Specification - Downer
label | f64d0f7d-04c7-5770-8bad-bc787444a8e3 |  | note | Verifying Document - Redlines
label | fa0c06a6-38af-5efd-adbf-da3e7ed08767 |  | note | Frequency - Post construction
label | 62ca144a-fde4-5465-929a-b048f4828032 |  | note | Activity - H
label | e5945e0b-7d3d-5ef9-a8bf-da45d937a369 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.01.04 - Defect, Snag and Punch List
label | 368f63a3-db77-5204-aaa7-aa01669bfbc1 |  | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | 33ffc0bb-b4aa-5232-bf57-e66ad40668fe |  | note | Standard / Specification - Downer
label | 33c668aa-88b6-5645-b971-30a3df4321e2 |  | note | Verifying Document - Register
label | 2de9d500-3a86-5f99-a7fc-4eefa15fef75 |  | note | Frequency - Post construction
label | 398eada4-e6f2-55aa-a516-2137af9b8da7 |  | note | Activity - H
label | 82ab9b6a-b5a4-5adb-9c72-1b795d84926e |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.01.05 - Photos
label | 36a80c93-c9dc-55ff-b483-5aa242fff911 |  | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
label | 01466be1-a2c6-517a-8f95-3cd5e3a2c397 |  | note | Standard / Specification - Downer
label | 05d2b333-6235-5b98-a18f-eaa87e514051 |  | note | Verifying Document - Photo Records
label | 4b223c81-de6d-5f09-96b9-2a7a39248c1b |  | note | Frequency - Post construction
label | 66ef3d51-81b5-513d-9327-50fbd4284aae |  | note | Activity - H
label | ddc4612f-097a-5490-aa75-735a94bdffde |  | note | By - SE
checklist-sectioned |  |  | checklist | ITP - Retaining Walls - Rev E | itp |  |  |  | Yes | ITP - Retaining Walls - Rev E | 6cec8363-521e-436f-9cd1-098d4f4cec3a
checkpoint-group |  |  | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint-status |  |  | checkpoint | 3.01.01 - Construction Pack
label | 8a0d1e79-aa30-51a2-ba44-7e773615758e |  | note | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
label | 12169806-1115-5ff0-ba3e-50d4314ff524 |  | note | Standard / Specification - Downer
label | af51c198-73b7-5f4f-be92-be712d6ddde9 |  | note | Verifying Document - Construction Pack
label | 48603452-d2df-56b3-9899-8d1d2c56c91f |  | note | Frequency - Submit 10 days prior to commencement of works
label | 5f4f30a6-272d-5089-ab98-f393eefa5a13 |  | note | Activity - HP
label | 338fe5c7-f79d-5c0c-82b7-78c44e04ec25 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.01.02 - Survey Setout
label | dddde4ec-2ce4-5cca-b048-84ba820ffcc4 |  | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | 639f83cc-1519-586e-9361-968b514b9a9f |  | note | Standard / Specification - Downer
label | 0c896799-a5c4-516e-b4c3-42555bb915b1 |  | note | Verifying Document - Survey Records
label | 20c85229-60c2-503f-9538-b2beb431a551 |  | note | Frequency - Prior to Works
label | 86423e76-30d9-525d-8808-f96fbd6ed7fc |  | note | Activity - H
label | ce2fcaac-b474-5060-99e2-e7888842fb8a |  | note | By - SV
checkpoint-status |  |  | checkpoint | 3.01.03 - Service Location
label | f5628cab-5077-5102-9f11-504f9c8b3bff |  | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | 27fe4e06-bf24-51ae-ae35-8c94c3add973 |  | note | Standard / Specification - Downer
label | f3850256-943c-5b46-b361-b26f02b009ed |  | note | Verifying Document - Excavation Permit
label | 32418d8f-d2d7-54c7-b906-b4de1c2fcd78 |  | note | Frequency - Prior to Excavation
label | 102a84f6-f432-51ed-a382-1be410f6a54a |  | note | Activity - H
label | 4bb0a952-5ee1-5e53-9b56-e6e11ef925d0 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.04 - Internal Permits
label | e0db3084-6898-5399-a920-c969ddebc22d |  | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | 08d928a0-089f-5a43-87c8-7d5b384d90ee |  | note | Standard / Specification - Downer
label | 9fecac0d-4892-5ecb-94e5-ab2719336490 |  | note | Verifying Document - Internal Permits
label | b865ee54-2bb4-50c9-b34c-86b0bf4e81f7 |  | note | Frequency - Prior to Excavation
label | 068c0dd7-62c5-5950-98c8-e67082eb895b |  | note | Activity - H
label | 6ab2c64e-5cde-5a51-ac12-f1744f451166 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.05 - External Permits
label | a3982939-a09b-5f65-930a-83594b1a59aa |  | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | b2d0d73e-f7e2-5875-b911-e85ff1d240c9 |  | note | Standard / Specification - Downer
label | 011655fb-a45e-501f-86b9-6cc831676b0d |  | note | Verifying Document - External Permits
label | 16b6c62e-5868-5a39-b7c0-20e9059ab261 |  | note | Frequency - Prior to Excavation
label | 9e8a8bbc-0fe7-57ea-97a1-ecb01eafcbff |  | note | Activity - H
label | 546353b2-ed6c-54d3-bf31-dade141b15f2 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.06 - Approved Construction Drawings
label | 60849391-f32f-54e4-8e16-62402da84e44 |  | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | 045af579-5f15-52c8-9546-02f8db13abb9 |  | note | Standard / Specification - Downer
label | 904b65ac-f718-589a-95c3-4f074bd25870 |  | note | Verifying Document - IFC Drawings
label | 6084e46b-70e4-51cb-b498-19cfd82da7e1 |  | note | Frequency - Prior to works start
label | 68fc39e6-7547-5e92-8708-44c16e49cfdd |  | note | Activity - H
label | 205ac354-d64b-5142-beea-3b7eaa98ecd2 |  | note | By - PE
checkpoint-group |  |  | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL – RETAINING WALLS
checkpoint-status |  |  | checkpoint | 4.01.01 - Stone Strong Block Molds
label | 2bd89bae-07b6-5306-a504-fa7d87898321 |  | note | Acceptance / Conformance Criteria - Stonestrong blocks to be supplied by an approved supplier. The Contractor shall liaise with the Principal-appointed Cultural Artist to coordinate carving of the supplied blanks and the production of moulds & blocks
label | 5be549d7-8210-58bc-a46b-b4bdbbefdcaf |  | note | Standard / Specification - PS - 12
label | 2e6b8cf7-45ab-51bb-a94d-de3b08c4ed0a |  | note | Verifying Document - Conforming Molds Post Carving
label | 8cdfbb95-eb11-56c4-83d8-dc0efbed5003 |  | note | Frequency - Before Installation
label | 7dbec491-e5e0-5c7d-b569-801b75228eed |  | note | Activity - H
label | 1d495b03-9a7d-5d9a-bf8d-8c1d1b108639 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.01.02 - MSE retaining wall backfill and drainage Material
label | 5f015f0a-32ca-5098-8f7e-01b6ab150fe8 |  | note | Acceptance / Conformance Criteria - Backfill is to comprise a well graded, granular material such as GAP65 or site won Hinuera Sand, which must be free of any deleterious material. Sand backfill shall have a fines content (less than 0.075mm diameter) of no more than 10%.
label | bf2155e0-85ae-5718-a69c-542b4ce59d21 |  | note | ○ Drainage metal to be 20/40 drainage aggregate or similar approved by engineer.
label | 75fab186-5801-5e68-9100-4a34687cbb97 |  | note | ○ Labratory MDD (x2 per material type) at standard compaction
label | 8f7afa0b-5b75-5f6b-92de-0cd7f64fce3a |  | note | Standard / Specification - GWS - 5.3.3
label | 83502b73-a1c5-5a72-a2a1-987eb3f77198 |  | note | Verifying Document - Lab Results
label | e8b815d5-61b7-5376-917d-312c8aa6e454 |  | note | Frequency - Prior to works
label | b04a20ad-42ff-541f-bf2c-d10818b0936e |  | note | Activity - H
label | 015ea7d7-f005-5d0b-bdf4-46bd41480460 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.01.03 - Geogrid
label | c06baadf-ef00-5ca8-bca2-64a9f1f46702 |  | note | Acceptance / Conformance Criteria - Geogrid to be Miragrid GX200/30 or similar approved
label | 4478a1a1-70ad-5088-b9c4-8a7ddf82c58f |  | note | Standard / Specification - GWS - 5.3.1
label | 144d0adb-5334-5c39-a0c9-92958b3efaae |  | note | Verifying Document - Datasheet
label | 1ea05c3d-ee6a-524c-8230-329e985e9c82 |  | note | Frequency - Before Installation
label | 072791d9-790d-52c3-aad4-c4a3e5c2c5fa |  | note | Activity - H
label | 6b54ee3c-ecfb-57bf-9a29-f9dcb8d80120 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.01.04 - Para web
label | 5934a350-5f2e-5022-8dfd-c10537e5288a |  | note | Acceptance / Conformance Criteria - Paraweb to be the correct grade: Paraweb 2D-50
label | f82987c4-1411-5e76-83d5-61542e7b1c87 |  | note | Standard / Specification - GWS - 5.3.2
label | 209066d1-282d-5039-90e0-c0d53068ff9c |  | note | Verifying Document - Datasheet
label | 0a1827ff-240b-53b7-a030-375286a892cf |  | note | Frequency - Before Installation
label | c2e8d5fd-723a-5ef3-b4a6-d9041b635f41 |  | note | Activity - H
label | 5420955b-884e-51fd-b9d9-29af2ff49edc |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.01.05 - Drainage Pipes
label | bbf9a41e-2354-54ca-9352-18bebc8e6b8e |  | note | Acceptance / Conformance Criteria - Shall be 160mm diameter NZTA F/2 compliant smooth bore perforated corrugated pipe with filter sock
label | 93e7a20f-f527-5dfd-acd2-d1e2db74cc60 |  | note | Standard / Specification - GWS - 5.3.4
label | 44558f33-7964-532d-8691-62d48d83acaf |  | note | Verifying Document - Datasheet
label | 5da2d153-ac8e-55a4-a9e8-94503c1b61f0 |  | note | Frequency - Before Installation
label | 929dcb63-f7b4-5c8a-bfdd-3ca7a972b9ed |  | note | Activity - H
label | dd3d1dc4-897b-5ec6-ba98-9ab5fc052a03 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 4.01.06 - Geocomposite drainage board
label | 646bb77c-96b0-50dd-a508-936005ea6d9a |  | note | Acceptance / Conformance Criteria - Shall be Bidim A39 geotextile or similar equivalent
label | dcdea1a2-f37e-566e-9c49-5d39f3a8b913 |  | note | Standard / Specification - SS - 12
label | 5a3869e5-a16f-533b-812f-86cb749ae79f |  | note | Verifying Document - Datasheet
label | e84e1b4b-607c-540b-b627-aa5ee4b4bee6 |  | note | Frequency - Before Installation
label | 115e5717-fcfc-5841-8335-d0172b615d64 |  | note | Activity - H
label | 5c2be74e-8680-5260-a593-221b1b1dc1fa |  | note | By - PE
checkpoint-group |  |  | section | SECTION 5 – CONSTRUCTION ACTIVITY – RETAINING WALLS
checkpoint-status |  |  | checkpoint | 5.01.01 - Excavation to subgrade
label | 98c4fafd-ab95-510b-9274-83170e7fb1ee |  | note | Acceptance / Conformance Criteria - The foundation materials are to comprise natural Hinuera sand material, stiff Hinuera Silt or imported clean sand and must achieve a minimum of 4 blows per 100mm when tested with a Scala penetrometer. Any exposed silts must have vane shear strengths greater than 70kPa.
label | 56174934-ed1b-5740-8f1b-6dcfb3a2cf63 |  | note | Standard / Specification - GWS - 5.2
label | e135ce3d-fd9f-5a99-b2f9-9d52d6c35183 |  | note | Verifying Document - Scala Results
label | fa1199dc-6eab-5131-af89-dbbde3ab9d25 |  | note | Frequency - Every 10m
label | 93a2abe7-a982-5303-a0e4-50f54484400e |  | note | Activity - H
label | 4a8c3298-ba99-5b17-ac28-48838788e2e1 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.02 - Foundation Approval
label | b103f257-35bb-5294-a2a6-4f86aee86d31 |  | note | Acceptance / Conformance Criteria - Results of the foundation material testing shall be supplied to the Engineer for approval and the prepared ground shall be inspected by the Engineer. Construction may not proceed until receiving Engineer’s approval.
label | 8c864b0f-f0a3-595f-8266-70e555cee82f |  | note | Standard / Specification - GWS - 5.2
label | 01bbc8ec-34b7-5895-9e25-71a8c9322222 |  | note | Verifying Document - Approval
label | 41e279c5-4f96-5aa2-a9d6-b9714b99a680 |  | note | Frequency - Prior to proceeding. Min 48h notice to Engineer
label | 7cfa6829-b695-5c46-9e68-e9c742de5bcf |  | note | Activity - HP
label | 2feb039d-a053-5cbe-86e2-9b523e9ec7cf |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.03 - Undercut subgrade
label | 80ceed1b-5540-5ba5-8e69-aabd21c7c4d1 |  | note | Acceptance / Conformance Criteria - Any unsuitable materials, such as uncontrolled fill, contaminated materials or any weak or organic materials, shall be undercut and replaced with compacted granular fill (WHAP65 or equivalent) or Hinuera Sand. Surveyor to capture extent of undercut (if any) to include in asbuilt.
label | fe9af0e2-afc8-58e2-86ac-8a827f1e04f2 |  | note | Standard / Specification - GWS - 5.2
label | 16b49003-06c2-577d-a206-032e2453f7c1 |  | note | Verifying Document - Survey Record/ Photo record
label | 9a7c2aa7-d9db-58b4-aadc-5c7ff886dffa |  | note | Frequency - If required
label | 28e9d57c-b860-5593-a71d-e9e4ede87632 |  | note | Activity - I
label | 54ca8536-8ed8-56b3-97c9-264f25e0f011 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.04 - Undercut backfill compaction
label | 24a7cc88-aa3d-55c8-bc85-b0d51bf4e1a5 |  | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
label | eeeb1e4d-ef2e-57a5-92df-6e015891d7e6 |  | note | Standard / Specification - GWS - Table 3
label | 89e8e2fb-8c6e-5f0e-824b-142686613834 |  | note | Verifying Document - NDM Results
label | 7f2d9b74-c157-5148-821d-bf10570eaa83 |  | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
label | 01e4886b-f8ea-5200-85aa-46b2e0927993 |  | note | Activity - H
label | 12ce8d52-3adb-53a3-b4eb-1c300b027d18 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.05 - Geogrid Installation
label | 4416f2f8-5c15-57a0-8811-a39439e0f963 |  | note | Acceptance / Conformance Criteria - Geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets. Engineer to inspect 1 layer prior to backfill.
label | abe05164-12c7-5ef3-80ef-9c9cad1fa87f |  | note | Standard / Specification - GWS - 4.1
label | 63ee82fa-9a46-521b-b7a9-09a559835c33 |  | note | Verifying Document - Photo record
label | 3510d9fe-2161-50d8-b854-c10320454d31 |  | note | Frequency - Each layer - 1 layer per abutment to be inspected
label | 325c9edb-3634-5b38-a1ec-8a9ec1144d30 |  | note | Activity - HP
label | c5b7876f-6bc0-53f2-b207-4773516e899e |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.06 - Backfill Installation
label | 899e5bd8-adca-5159-96db-eb250698bf99 |  | note | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts and compacted to the following standards.
label | 85edcc97-c060-51e9-bf7d-481a4344728c |  | note | Standard / Specification - GWS - 5.3.3
label | 40d64713-6f83-55a1-b70f-66fa466ddd1c |  | note | Verifying Document - Photo record
label | cd63bee6-886d-509d-8958-fa0e37587f60 |  | note | Frequency - Each layer
label | 2fa77c66-32c4-5683-86b7-11496ca08d24 |  | note | Activity - I
label | 15afce54-64d6-571f-a5dd-803ba962ca64 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 5.01.07 - Backfill Compaction (NDM) (Gap 65)
label | 87407d10-62b7-5ff5-ba90-5593726c5faa |  | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
label | 30f2408f-adbe-53df-aa2c-74ef756e47a1 |  | note | Standard / Specification - GWS - Table 3
label | 0b85a524-7f9b-5708-bc76-3abb9d4be284 |  | note | Verifying Document - NDM Results
label | eb4bbfde-b9a0-59ca-b3f1-42814e28d5a6 |  | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
label | e4bbee84-89d6-50b3-ac3d-d4e33075692f |  | note | Activity - H
label | 5d10d11b-0675-5e18-8326-8a2ebbdb6366 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.08 - Clegg/Proofroll (Gap 65)
label | 6af11bef-2749-5a8a-8a5a-fff40f1bb2ab |  | note | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test. Engineer to proofroll/inspect final layer of load transfer platform.
label | 2f991953-3d11-5eb4-ba38-2cfe91f0bee8 |  | note | Standard / Specification - GWS - Table 3
label | 6d8ab319-c5ea-5f8b-bc11-b91a60e1c8ff |  | note | Verifying Document - Clegg Result sheet
label | e1ef96ea-02ac-5c4c-9717-9314287dfdc8 |  | note | Frequency - Each layer - final layer to be inspected
label | 7cbbabb3-ac98-52a5-abc3-2deb617bbf37 |  | note | Activity - HP
label | cf5ab66c-e5fe-583b-8691-03257766dc41 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.09 - Scala Penetrometer (Hinuera Sand)
label | cde21a07-5d67-5ca1-9a7f-b339b50bc5e9 |  | note | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
label | 972a1ee8-7b07-5741-89ee-e1b26a5ed84e |  | note | Standard / Specification - GWS - Table 3
label | 41a92435-c912-5c80-9abf-7fe925708fdd |  | note | Verifying Document - Scala Results
label | cf752176-b0a8-5b9a-b7b8-75529c330a51 |  | note | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
label | bd1f19b6-b73f-56e2-be79-b5258d2a4ce7 |  | note | Activity - H
label | 1b40fc59-8332-5ce0-908e-9cbe7280ce66 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.02.01 - Level founding platform
label | cd3652ed-252c-58b6-bcc5-2a17f3e24677 |  | note | Acceptance / Conformance Criteria - The Contractor shall construct a 200 mm thick levelling pad on top of the load transfer platform to create a level founding platform to accept the MSE retaining wall.
label | 361f02ab-fbd9-50de-99da-cf6960afddf7 |  | note | Standard / Specification - PS - 12
label | 06408132-2b51-593f-9345-3f6af46d9fea |  | note | Verifying Document - Site Photo / Checksheet
label | a4b51cc9-1120-52fa-bc34-10b3e5a57a98 |  | note | Frequency - Prior to Stone Strong block installation
label | 5745bbcd-406f-5d59-b220-74e9d988a65e |  | note | Activity - I
label | 8f522c83-6a6b-521c-9eae-0f46bf135fae |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 5.02.02 - Installation of blocks
label | 82f65001-8ff9-5f81-b3aa-8868c968a8eb |  | note | Acceptance / Conformance Criteria - Blocks to be installed to the height and location as detailed on the construction drawings. The table below details acceptable tollerances.
label | 6f3ab58a-1676-5555-804e-c46e1b83cc25 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | aaadf9ec-7382-571e-9fda-0ba6552d382f |  | note | Table 4: MSE Tolerances
label | 43c7f889-085c-5eec-840e-f3ba927d88d9 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | 1bc65494-f9e6-5e2e-94ec-9988e9527c8b |  | note | Element ¦¦ Vertical Position ¦¦ Horizontal Position ¦¦ Vertical Alignment ¦¦ Horizontal Alignment
label | a0f0bf7c-c8cf-5f63-9415-9e0dde785dfb |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | 5078d3e4-8089-5243-ac7f-1f93b304c28c |  | note | Soil Surface ¦¦ ± 100mm ¦¦ N/A ¦¦ N/A ¦¦ N/A
label | b657d697-7696-53ab-b5bd-0d38b6d42719 |  | note | Facings and wall structures ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
label | bb919e11-3810-5383-8a20-35ee44bd53f8 |  | note | Footings or supports ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
label | 63c06ce9-9952-5a63-a6e3-96a18dcdfb35 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | 96022c5e-a42b-5b78-b512-7f105236804a |  | note | Standard / Specification - GWS - 5.4
label | 78c121e1-c205-57fa-aee8-157df0802bd3 |  | note | Verifying Document - Site Photo / Checksheet
label | 5e801a16-ca92-5ad3-a6e3-7164a3742bfa |  | note | Frequency - Each layer
label | 148c9f71-1619-543a-8ac0-328293eeafa0 |  | note | Activity - I
label | fb3bb93e-e224-5154-ab88-dd27f30a4a78 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 5.02.03 - Paraweb Installation
label | b2308c38-b919-5d53-ac15-1229842d1da0 |  | note | Acceptance / Conformance Criteria - The correct number of parawebs are to be installed as shown on the construction drawings.
label | 19388c80-71ce-5f88-b8e0-e795761d0f72 |  | note | ○ Para web is to be placed flat or with a 1% fall toward the rear of the wall. The Para web must be free of wrinkles and lightly tensioned prior to and during placement of backfill. Shallow trench to be dug toward the end of the paraweb, pin to be used to pull paraweb taught prior to backfilling.
label | f89b9399-2faa-5b45-bff7-5e47f63da2f9 |  | note | ○ The Para web must be continuous over the design embedment length and no joins are permitted unless adequately lapped and spliced according to the Manufacturer’s instructions.
label | 5700ca77-1484-5112-9811-8f89dd8ddf31 |  | note | ○ 150mm of fill cover is required before construction equipment can travel over the area
label | 45bca719-125c-5539-a255-2122fa63fb47 |  | note | Standard / Specification - GWS - 5.3.2
label | edb3ac52-82b7-529f-be91-f62e742f6e5f |  | note | Verifying Document - Site Photo / Checksheet
label | 81123ea4-c795-5c40-b10f-fbf99c68426b |  | note | Frequency - Each layer
label | 5fe8ff9b-e494-5042-812f-c84ae57f4f72 |  | note | Activity - I
label | 10f788f3-9055-53de-8e2d-1687d0b95e68 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 5.02.04 - Geotextile
label | f1a8bb54-9914-5908-800a-019f85bc7027 |  | note | Acceptance / Conformance Criteria - Geotextile to be placed against rear excavated face with a minimum overlap of 400mm between adjacent geotextile strips. Further Geotextile required to separate drainage aggeragate and MSE wall backfill, if sand is used. Short widths of geotextile to be placed across the internal open join area on the rear face of each Stonestrong block join to contain internal block void hardfill. Geotextile to be used to block paraweb voids within Stonestrong blocks that are not in use.
label | 94cc05b3-7ed4-549e-b03a-e2ee7b360416 |  | note | Standard / Specification - SS - 5
label | 647f2bf3-b023-5467-aedc-97bbb0515d40 |  | note | Verifying Document - Site Photo
label | 7279ff2c-aff4-5b1d-a3f4-f63375d504cb |  | note | Frequency - Each Layer
label | a7b243d3-c6cb-535d-90b5-65a181495255 |  | note | Activity - I
label | bd118e8a-bc42-5377-b62a-9b6acb61244a |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 5.02.05 - Drainage Outlet Installation
label | 9ee8df9f-b706-55ee-8519-02e9f3ab549c |  | note | Acceptance / Conformance Criteria - Two x 160mm Drainage pipe wraped in filter sock to be installed along the external perimeter of the Load Transfer Platform.
label | a8364235-fc92-5b0f-b783-499970ee5864 |  | note | ○ Drainage aggregate to be placed along external perimeter of Load Transfer Platform for each MSE wall layer backfill, forming a Chimney Drain. Chimney Drain to be a minimum width of 300mm and extend to the base of the Load Transfer Platform.
label | bfdccc2a-f87a-559a-a09d-f22ca6b2550d |  | note | ○ Internal block void hardfill to be 20/40 drainage aggregate or similar approved by engineer.
label | f50624df-79b1-5d2c-a119-85e58c1d959e |  | note | ○ Additional Drainage pipe wrapped in 0.75m3/m run of drainage metal only required beneath wall embedment at toe of the outside of the wall if the slope doesn’t grade away from the toe of the wall.
label | a9df338d-dd93-5a01-b470-27f025b047c8 |  | note | ○ Drainage outlets shall be connected to the reticulated stormwater system or other approved outlet structure at the discretion of the design engineer
label | ba32300a-18c6-51ad-9b3e-f5c37464fe0b |  | note | Standard / Specification - SS - 5
label | 53567f00-05db-5a58-917d-b1a978e56890 |  | note | Verifying Document - Site Photo / Checksheet
label | 6be29782-2749-5e9e-acd2-446695c190cf |  | note | Frequency - During Installation
label | 342b7fa8-1803-5fd1-9c9b-a45f3d56f346 |  | note | Activity - I
label | fd19484e-4527-5d4c-ba92-996f5eaf5baa |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 5.02.06 - Backfill Installation
label | af9d4419-c84d-5922-b84f-e4b5f9fba21f |  | note | Acceptance / Conformance Criteria - All backfill is to be installed in 250mm lifts adnd compacted to the following standards.
label | 2ff5acbc-2441-5914-b466-eceb1bb021f9 |  | note | Standard / Specification - GWS - 5.3.3
label | 4a7c55ba-2c0a-5085-b17c-dd45445553f8 |  | note | Verifying Document - Site Photo / Checksheet
label | 30810479-7899-5c37-82a0-b47fdd9f12c6 |  | note | Frequency - Each layer
label | 123779de-51e8-57df-9006-afe3c5d732e0 |  | note | Activity - I
label | 8dfe733a-517e-59b2-8b5f-794fa672edb5 |  | note | By - SUP
checkpoint-status |  |  | checkpoint | 5.02.07 - Nuclear Densometer (NDM) (Gap 65)
label | b847ce07-00bc-5608-ad0f-d3a81d9f94ed |  | note | Acceptance / Conformance Criteria - NDM (DT 300mm deep or backscatter with GAP65), with MDD of 95% or greater
label | 4328a99a-5536-59cb-b110-ccb710847e94 |  | note | Standard / Specification - GWS - Table 3
label | c7971168-a004-5036-9f2b-1ed3ea128222 |  | note | Verifying Document - NDM Results
label | e5023db2-34bb-57e5-afed-29b12bed2459 |  | note | Frequency - 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
label | 8cdff723-0bb1-5eda-b0dd-3311715e1015 |  | note | Activity - H
label | db8b0f3f-ff9c-577e-b319-25d981210cd2 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.02.08 - Clegg/Proofroll (Gap 65)
label | 34f46bc0-660e-59a9-87b3-f7d46d61f7b1 |  | note | Acceptance / Conformance Criteria - Proofroll of each layer. 4 Cleggs to be undertaken per NDM test.
label | 55b742a7-f1db-531f-a649-27c88e7838c1 |  | note | Standard / Specification - GWS - Table 3
label | d5b9941f-faf4-5d61-a2c3-0e5aaee11ab4 |  | note | Verifying Document - Clegg Result sheet
label | e3522a14-a2a0-5082-bd51-44a43486a497 |  | note | Frequency - Each layer
label | 240afa7e-52fe-51d3-92d6-41ad2714d903 |  | note | Activity - H
label | 7ac8ff9e-7fbb-570a-97d4-35d1bbc41844 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.02.09 - Scala Penetrometer (Hinuera Sand)
label | 62504378-93e1-5436-8f83-4677141f4acc |  | note | Acceptance / Conformance Criteria - Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
label | e2de32a1-2c6d-518a-abca-f3d6ceabb328 |  | note | Standard / Specification - GWS - Table 3
label | 4977a5a6-2522-5a87-8b18-23854d812a24 |  | note | Verifying Document - Scala Results
label | be1fc94d-8950-5572-91b8-2af6e059fc7f |  | note | Frequency - 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
label | 12ad0ee7-bc51-5cd4-9a23-aa3216f918ed |  | note | Activity - H
label | 6478289f-1f2c-5ec0-83ab-fedda90f9e95 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.03.01 - Settlement Pins
label | 7df0273f-2726-573c-8319-234334b15439 |  | note | Acceptance / Conformance Criteria - Settlement pins shall be installed within 24 hours of reaching design subgrade level. Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
label | a8caf30b-b9d1-5a46-aeb5-4dbe3f8a424c |  | note | Standard / Specification - GWS - 6.3
label | 235db810-ad9d-56f9-9b7a-832a7715a7a1 |  | note | Verifying Document - Survey Results (in paper as well as electronic format)
label | 9cf7e1c7-e135-5b40-918e-94fc4847f36e |  | note | Frequency - Weekly for the first month, then monthly
label | 5494d2e5-3ff5-587e-afa6-7da2c5782e66 |  | note | Activity - R
label | 9ea475f8-54c7-5150-b398-7d78ec86a5f7 |  | note | By - SV, ENG
checkpoint-status |  |  | checkpoint | 5.03.02 - Settlement Targets
label | bdf89470-9cbc-5946-80fc-b3956bda633d |  | note | Acceptance / Conformance Criteria - Targets shall be fixed immediately after completion of the first row of retaining wall blocks at each location and the initial baseline survey reading made prior to the subsequent row of retaining wall blocks placed.
label | cc54a364-6dce-5b48-9181-dadf83f2781b |  | note | ○ Survey measurements are to be undertaken to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
label | 2bf0e43a-b99a-57be-895d-15eca0dfe222 |  | note | Standard / Specification - GWS - 6.4
label | 7dc30c5f-7c95-56a7-be44-1e1575e44215 |  | note | Verifying Document - Survey Results (in paper as well as electronic format)
label | c191b3a4-241a-5dce-9f28-f631fd35ecfb |  | note | Frequency - Weekly for the first month, then monthly
label | 455b2891-a1a2-519d-a193-7630a3c712b2 |  | note | Activity - R
label | da1b9953-f7b3-5ba8-a6b6-1889d694713e |  | note | By - SV, ENG
checkpoint-status |  |  | checkpoint | 5.03.03 - Engineers Approval
label | 68ab0ad8-4387-5097-a8b1-ebe274ec1bb0 |  | note | Acceptance / Conformance Criteria - Geotechnical engineer assesment required before commencement of Pavement construction
label | daf4f6df-f633-5b49-aa86-a6ffbbe52acc |  | note | Standard / Specification - BBO
label | c0a8b60a-f1db-58b1-a845-681f2ca879f8 |  | note | Verifying Document - Written approval
label | dc733efa-8e48-5814-ac8a-c3c3cf3be8eb |  | note | Frequency - Prior to pavement construction
label | f98910be-3ed3-55ca-b6df-4fc2d1b26c55 |  | note | Activity - HP
label | c8e8760d-cc9c-5702-afd5-a55af9baf9d9 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint-status |  |  | checkpoint | 6.01.02 - Draft As-Builts
label | 4420550a-537f-5032-818b-40f1768a8347 |  | note | Acceptance / Conformance Criteria - Draft as-builts completed on the completion of MSE wall including red pen mark up to IFC drawing changes.
label | 66d1e4c9-6287-50dd-9a72-f96d4f113dcc |  | note | ○ The draft as-builts shall be provided on a continual basis throughout the project for verification by the Engineer, and as a minimum shall be provided in electronic form prior to application for Practical Completion.
label | 5477e57b-d05e-5d5f-8996-79cc3de0e690 |  | note | Standard / Specification - PS 2.2.17
label | 894a9d79-71c5-5fe8-b709-aff0019a8dca |  | note | Verifying Document - Draft As-Builts Drawings
label | f119bd10-b211-59ef-9d97-9a27ed553bb0 |  | note | Frequency - Prior to PC
label | c19c636b-ce51-5f62-ab48-0d6a79b16cfc |  | note | Activity - H
label | eab67930-078b-512e-bef4-5b6f5727abd7 |  | note | By - SV / PE
checklist-sectioned |  |  | checklist | ITP - Hollowcore | itp |  |  |  | Yes | ITP - Hollowcore | 77befa5c-bfab-4027-abf5-fb80bd972b74
checkpoint-group |  |  | section | 1.0 Pre Construction Tests
checkpoint-status |  |  | checkpoint | 1.1 - Concrete Mix Design Approval
label | 78f211aa-5a6d-5d2e-952f-d156b3567228 |  | note | Acceptance Criteria - 60 MPa at 28 days (S6014PC)
label | aa858af4-1c11-5fec-9807-c8bf6701d980 |  | note | Inspection or Test: Method - Review
label | d2c184e8-b5f4-5905-b93d-788ab91ca0db |  | note | Inspection or Test: Freq. - Once per Mix design / per supplier
label | 17809666-3917-5c98-a776-b11dfa4ff31c |  | note | Inspection or Test: Responsible Person - PRECO
label | 7fcbf47b-08ac-57d4-8bb0-1afe56b12559 |  | note | Verifying Document - Confirmation of Approval
label | 3a201943-a2a7-5359-9283-ea1ac7d0928d |  | note | Records required for handover package: Yes/No - Y
label | eca077c5-ed8a-5b97-9a5e-cdf67be56ace |  | note | Inspection / Test Authority: Conduct - 1
label | cb8fb411-2aa4-5950-8709-3a3592e01c28 |  | note | Inspection / Test Authority: Witness - D
label | ab4ec765-bf98-5ad9-a7c4-5858a57c8569 |  | note | Inspection / Test Authority: Produce Record - 1
label | ffd7e38e-39d7-51a4-a0e2-e393ee9f3d6a |  | note | Inspection / Test Authority: Approval - D
label | 12b13299-31df-5e0f-8a3d-1c23f32e0df1 |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.2 - Reinforcement Supply
label | c3138b85-2b05-5574-a3a6-a2e04a6675a3 |  | note | Acceptance Criteria - Micro Alloying Deformed Bars Grade 500E (HD)
label | 14abb13d-df41-55f5-9965-079418bf4584 |  | note | Inspection or Test: Method - Review
label | 017175fb-024a-571d-8bc6-53d393f584c2 |  | note | Inspection or Test: Freq. - Per Size, Per Supplier
label | 1c69872e-6d91-5364-849d-51759dbd028a |  | note | Inspection or Test: Responsible Person - PRECO
label | 70142f81-b14b-5339-ba6e-ca12006cd9e4 |  | note | Verifying Document - Supplier Mill Certificates
label | 98f163b4-fae4-5b01-a913-d13ec9072468 |  | note | Records required for handover package: Yes/No - Y
label | a86b2e81-f72c-5ede-82ea-29331059eb45 |  | note | Inspection / Test Authority: Conduct - 4
label | 8cca54ad-ae01-5eaa-ba78-9a4ebd814399 |  | note | Inspection / Test Authority: Witness - D
label | 3f1214ed-d4af-5cd2-b9e7-7438fb04eb89 |  | note | Inspection / Test Authority: Produce Record - C
label | 73d8ecd9-f1e6-524d-89af-5c9fdf3d6927 |  | note | Inspection / Test Authority: Approval - D
label | 8cc5fdc0-8b51-54b7-a5c5-f6e9b2d88efa |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.3 - Strand Supplier Verification
label | 4255b8e1-7562-54e5-9b12-d10442fcc85e |  | note | Acceptance Criteria - ACRS accredited supplier
label | 867cf9d8-c10b-58e5-afcd-c49485bd82f8 |  | note | Inspection or Test: Method - Review
label | 121bd0c4-24de-5c78-8319-dfa08a2d08c3 |  | note | Inspection or Test: Freq. - Per Supplier
label | 1f928294-bd9a-58d3-9820-099b51484fcb |  | note | Inspection or Test: Responsible Person - PRECO
label | ea7943bd-f313-59cc-9d64-d02695513371 |  | note | Verifying Document - ACRS Accreditation
label | d661eee4-fff8-5c68-a2dd-5cbc821d7825 |  | note | Records required for handover package: Yes/No - Y
label | 9ece86f8-116f-5b4e-ab33-20db39efcaae |  | note | Inspection / Test Authority: Conduct - 4
label | fedf724f-dd9f-50fc-9f5d-3b1ad3296fad |  | note | Inspection / Test Authority: Witness - D
label | af4df6dd-cf0c-5cc4-9bf0-f29f3fd06cf2 |  | note | Inspection / Test Authority: Produce Record - C
label | f27b0868-6259-51c2-b8d4-57ea5c1652c8 |  | note | Inspection / Test Authority: Approval - D
label | cf2a1c14-b965-53b9-ae4e-47d7133f1bbf |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.4 - Strand Supply
label | d5831ee0-71a7-52e2-bec8-36e284be9840 |  | note | Controlling Documents - NZS 3109
label | 214a8a5c-c23a-5aad-80bb-b71fba686a79 |  | note | Acceptance Criteria - 15.2mm diam. Prestressing superstrand
label | 4997169f-dac4-54b3-97eb-791c68fa8684 |  | note | Inspection or Test: Method - Review
label | 721a8e30-e897-53a4-9c2c-d656c7765c60 |  | note | Inspection or Test: Freq. - Per Size, Per Supplier
label | 1c599276-26d7-54b6-995a-2fbf01dfb740 |  | note | Inspection or Test: Responsible Person - PRECO
label | 57792685-2729-5a0e-b18f-8f70006bbe90 |  | note | Verifying Document - Supplier Mill Certificates
label | a49d69ed-5b55-567a-9f10-5ed2fbd98508 |  | note | Records required for handover package: Yes/No - Y
label | 72e2b36c-de11-5d10-8e79-8724da027cc1 |  | note | Inspection / Test Authority: Conduct - 4
label | 286462b3-aa49-5f42-8bb2-3945620a72f2 |  | note | Inspection / Test Authority: Witness - D
label | f7a2b0f5-5fed-5c04-a321-1e58b66cbe3f |  | note | Inspection / Test Authority: Produce Record - C
label | 24164605-5635-550c-b0f1-bfc4f5cd702e |  | note | Inspection / Test Authority: Approval - D
label | 3e178ecb-70b8-5db9-8bc5-e9342cbd7384 |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.5 - Strand Certification
label | 8dfef4d5-d92c-526e-9fa6-9601130558b1 |  | note | Controlling Documents - AS/NZS 4672
label | 7e6982e4-94b6-548f-ad67-108003a3a0b5 |  | note | Acceptance Criteria - Conformance to AS/NZS 4672 in relation to:
label | 4ab239d3-ccca-5821-9c30-2522ff9ea8d8 |  | note | ○ Chemical analysis
label | f801015e-c684-5f3d-81af-9a989c6bf888 |  | note | ○ Geometrical characteristics
label | 6680d36a-67e8-5105-b2d1-df651faad111 |  | note | ○ Breaking force or tensile strength
label | 6bd53a41-3a23-5b28-b2c4-2cfff7519141 |  | note | ○ Proof load or proof stress
label | 6ba44543-2775-5a07-857c-e7c719cd7e0d |  | note | ○ Elongation at maximum load
label | 8689ff12-aed6-5bac-83f6-908935756478 |  | note | ○ Load extension diapgram
label | a5bdc635-cac4-59f8-8203-4209902dc1c4 |  | note | ○ Ductility
label | 2c5e90a6-933b-5cd5-b6c8-6cfbe18c960f |  | note | ○ Relaxation
label | 5d19aab5-7d19-5c52-a24c-8aeec7741395 |  | note | Inspection or Test: Method - Review
label | 958460c4-0198-51fc-920c-462c63ee5024 |  | note | Inspection or Test: Freq. - Per Size, Per Supplier
label | e2d1b5b3-1c0a-525d-a81b-a05b984bd7e1 |  | note | Inspection or Test: Responsible Person - PRECO
label | 15936079-2d8c-520a-af28-448cfe987c26 |  | note | Verifying Document - Material Test Certificates
label | bfdf3393-8341-5999-998a-d2735a598c0f |  | note | Records required for handover package: Yes/No - Y
label | 307908f2-fb06-5ef2-ba11-fc63bb9efe67 |  | note | Inspection / Test Authority: Conduct - 4
label | 31b58e15-b7bc-5d95-aef4-f912fd8bc2a3 |  | note | Inspection / Test Authority: Witness - D
label | 392c27e9-938c-5e17-a0b9-61668440771f |  | note | Inspection / Test Authority: Produce Record - C
label | cb9ba18e-2436-50fb-a937-167b8367d118 |  | note | Inspection / Test Authority: Approval - D
label | d1711e2b-a249-53e0-9908-a4e885436191 |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.6 - Shop Drawing Approval
label | d81037e6-4cfd-59f6-88d8-0adca4305fac |  | note | Controlling Documents - IFC drawing
label | db0fa714-a011-5b85-b0c9-658975aa0039 |  | note | Acceptance Criteria - Shop drawings including strand type, arrangement and stressing notes, details of debonding lengths, concrete strengths, surface finishes, location of cast in items and set-out information
label | b8d6e591-4cf9-585e-a730-1862fb7924e5 |  | note | Inspection or Test: Method - Review
label | 054cb47b-59e4-501a-a990-f771ee88e529 |  | note | Inspection or Test: Freq. - Once Prior to Casting
label | ce166315-bb6e-5ca4-8679-0383c87297b6 |  | note | Inspection or Test: Responsible Person - PRECO
label | a45c3f2a-0cd5-50b4-bed9-cb4c47078bdc |  | note | Verifying Document - Approved Shop Drawings, Issued for Construction
label | 29014ed0-46ce-5fb5-b72f-17479d57fcf2 |  | note | Records required for handover package: Yes/No - Y
label | 89e8fd82-8ecd-5ef5-a4fa-572afc64881c |  | note | Inspection / Test Authority: Conduct - C
label | 0be08783-6b2c-5068-964f-61ab966f482e |  | note | Inspection / Test Authority: Witness - D
label | 9bad79f3-7095-5b16-be96-c68c07c5953c |  | note | Inspection / Test Authority: Produce Record - C
label | 1e55555d-5f65-5029-97ad-db570de73f9d |  | note | Inspection / Test Authority: Approval - D
label | 9d941f41-78fc-5299-85e9-44f1f8a921a5 |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.7 - Stressing Calculations
label | 4142e4e5-f1ad-5627-9e33-d40bf29187f7 |  | note | Acceptance Criteria - Force remaining in each 15.2 mm dia. strand at midpoint of beam immediately after release of tensioning jacks
label | 26fd898b-b0f5-5dd6-b3e1-6a81f4df8d9d |  | note | Inspection or Test: Method - Review
label | 2125f996-2afa-5c9b-bc65-24a87238ecb8 |  | note | Inspection or Test: Freq. - 5 Days Prior to Casting
label | 40427a1d-5c44-52d7-8417-b474dba02533 |  | note | Inspection or Test: Responsible Person - PRECO
label | 0a3172c5-7508-5e53-847e-3213b5f29a5a |  | note | Verifying Document - Approved Stressing Calculations
label | 8de58f1f-2e0e-5d67-a886-ef2d7360f8b6 |  | note | Records required for handover package: Yes/No - Y
label | 698e7976-4c4a-562c-a5af-00ec5dca396d |  | note | Inspection / Test Authority: Conduct - C
label | c8e399ef-8561-5cb6-b5c6-5ca02bd6bce3 |  | note | Inspection / Test Authority: Witness - D
label | 6b5065be-2022-5538-b577-8240c957fc7d |  | note | Inspection / Test Authority: Produce Record - C
label | 943c788e-a1f4-5e22-869b-904e215411b3 |  | note | Inspection / Test Authority: Approval - D
label | e5d40d4a-6c54-5927-9d2d-14a8667156ae |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.8 - Jack Calibration
label | 4912747c-2bce-5136-babf-2c5ef48c651d |  | note | Acceptance Criteria - Calibrated within tolerance
label | 25e0f232-4bd1-517b-9285-35d662af5218 |  | note | Inspection or Test: Method - Certificate Inspection
label | c74194b3-f0c2-5267-aeca-fbb84bb25b1e |  | note | Inspection or Test: Freq. - Every 6 Months, Per Jack
label | a3976cd2-6eba-5e77-8a63-1f5b81365120 |  | note | Inspection or Test: Responsible Person - PRECO
label | d1724d1b-2de4-50e4-a7b4-db0ec34db939 |  | note | Verifying Document - Calibration Certificate
label | 6687e253-a060-5987-93e6-45cc92317bfc |  | note | Records required for handover package: Yes/No - Y
label | 5da45a7a-f9b6-5eee-8f02-d1e2502013f5 |  | note | Inspection / Test Authority: Conduct - C
label | 5a6cfbc4-f71e-55cf-9638-1cffcab231c5 |  | note | Inspection / Test Authority: Produce Record - C
label | 5b7d0374-3060-5c70-b637-56c03fb20930 |  | note | Inspection / Test Authority: Approval - C
label | ac280ed7-60d4-5318-9c00-e527014ce062 |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 1.9 - Form Release Agent
label | 4a2f920f-06fa-5ca5-9440-2d784383edfc |  | note | Acceptance Criteria - Not detrimental to the application of any subsequent finishes
label | 929a89b7-7a51-512f-a27b-dc18d97f6602 |  | note | Inspection or Test: Method - Review
label | 3595fc7d-8930-5042-b0a6-bb4e2198d229 |  | note | Inspection or Test: Freq. - Once
label | 3e905d85-7513-531e-8bf7-aaa26a8e6b8f |  | note | Inspection or Test: Responsible Person - PRECO
label | f13606ae-27d3-5641-bf45-a7c1536b7fb3 |  | note | Verifying Document - Material Data Sheet
label | 9a6b2806-6e07-58fe-8a46-2fb8720007f5 |  | note | Records required for handover package: Yes/No - Y
label | bb7392da-1876-52b1-b66c-4332597659b9 |  | note | Inspection / Test Authority: Conduct - C
label | a11e2481-f601-5d2b-9949-dd42b7d87f04 |  | note | Inspection / Test Authority: Produce Record - C
label | 0a89bb81-a0a4-5da9-9180-1e2537240abc |  | note | Inspection / Test Authority: Approval - C
label | 8b999de5-2dd0-55a6-8c77-eda64208c51e |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 2.0 In Process Testing
checkpoint-status |  |  | checkpoint | 2.1 - Reinforcement Traceability
label | 61ccf0a1-8c43-5f03-ab35-a3c7e776a72e |  | note | Acceptance Criteria - Mill Certificate, Heat Number and Bend Schedule traceability
label | d1191534-d8b5-5a18-ab8f-9683ebb998b1 |  | note | Inspection or Test: Method - Review
label | e0f9d9c5-9dd9-5fce-ad34-5f3bc667a60d |  | note | Inspection or Test: Freq. - Per Unit
label | 936505a9-7a6c-5f3f-8e24-0ad2c911c846 |  | note | Inspection or Test: Responsible Person - PRECO
label | 79a6200d-a523-5ba8-bf8a-d8c222392f92 |  | note | Verifying Document - Pre-Pour Check Sheet
label | a2529bb7-64a7-5f1c-9f48-8fc49fe5e1d1 |  | note | Records required for handover package: Yes/No - Y
label | c06454a1-11cd-587b-8afc-f3091ffc8473 |  | note | Inspection / Test Authority: Conduct - C
label | 100a881a-2b07-5500-8986-e757666b171a |  | note | Inspection / Test Authority: Witness - C
label | 133786a1-f514-5b7a-b002-ef08f5898a12 |  | note | Inspection / Test Authority: Produce Record - C
label | b68e1c03-cf17-5cb6-9316-db5166e91af3 |  | note | Inspection / Test Authority: Approval - C
label | fb2e7852-2574-5cd3-ad63-6811ed026e03 |  | note | Hold Point - N
checkpoint-status |  |  | checkpoint | 2.2 - Reinforcement Fixing
label | 6d21fe64-6a0a-5282-99bf-2e718a847467 |  | note | Controlling Documents - NZS 3109
label | 348f0eea-a018-5038-bf44-b5b8d3539582 |  | note | Acceptance Criteria - clear cover as per drawing to all reinforcing including stirrups and ties
label | 47db6c98-d89e-5e0f-8df3-8cf606190dc2 |  | note | ○ Steel to be securely tied and fixed with no movement
label | 91ba1cf8-25d4-59c5-97e9-7cc8f53ffe8b |  | note | Inspection or Test: Method - Inspect
label | b9149e45-01b4-5203-9eeb-3a2de6ff413b |  | note | Inspection or Test: Freq. - Per Unit
label | 386d206d-d2c5-5da1-824a-1080525fc590 |  | note | Inspection or Test: Responsible Person - PRECO
label | 52e37810-5c7f-5a82-96e5-05fd9b7853bc |  | note | Verifying Document - Pre pour checksheet, photos
label | eb431f8e-5183-57ee-9da9-e63271c0eb6c |  | note | Records required for handover package: Yes/No - Y
label | 1ccf093b-81ca-591f-89b9-eee4a5a2084c |  | note | Inspection / Test Authority: Conduct - C
label | e0d5d116-4616-5a98-8058-45ed77b042d5 |  | note | Inspection / Test Authority: Witness - D
label | 0f221cfb-6b22-56da-8523-eeabfec6955c |  | note | Inspection / Test Authority: Produce Record - C
label | a14218b6-312d-5ea1-ad99-a57fd49b362d |  | note | Inspection / Test Authority: Approval - D
label | 80b3119a-03c3-5c6a-a60c-a208d6c10ad0 |  | note | Hold Point - N
checkpoint-status |  |  | checkpoint | 2.3 - Pre Pour Inspection
label | d636d527-87a5-59bd-a560-2e45f82dffdf |  | note | Acceptance Criteria - Completed pre-pour inspection (dimension/inserts/ reo) permission to commence concrete placement
label | 1ce3f275-5a5a-5ad5-ad39-0e8c1c6aa2a5 |  | note | Inspection or Test: Method - Inspect
label | b22b9cc4-ebad-53ca-9105-c89f97d45417 |  | note | Inspection or Test: Freq. - Per Beam, Per Pour
label | e28ca6b4-e0e2-5f69-bb6f-0c16a10e0eba |  | note | Inspection or Test: Responsible Person - PRECO
label | 3f42244e-32c9-5520-b6ac-2b7f00939e36 |  | note | Verifying Document - Approved Pre-Pour Checksheet
label | 429807ba-ab0c-51d3-a509-f182bc3fada0 |  | note | Records required for handover package: Yes/No - Y
label | 2ee5eb8f-a096-5e8b-b2c7-2a27643b9c07 |  | note | Inspection / Test Authority: Conduct - D
label | b2709ce4-a224-523b-919a-db37d24f51b1 |  | note | Inspection / Test Authority: Witness - D
label | 4bc57f2f-9ba0-5b43-b5dc-e85d3acbc1d3 |  | note | Inspection / Test Authority: Produce Record - C
label | fc9ab214-1fa1-5317-9cf0-49661b16d828 |  | note | Inspection / Test Authority: Approval - C
label | 7e57bdb0-35a3-5ab9-9eca-17fde2f2be2a |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.4 - Concrete Placement
label | 39fafecd-b2e9-5b48-8c7b-daf98a4d5755 |  | note | Controlling Documents - NZS-3109
label | 3a3612b0-39ea-5b3c-95d5-86105f296f6c |  | note | Acceptance Criteria - Slump within target 120 +/-40, all concrete to be properly vibrated
label | cc2863c6-eb35-512c-88ee-d78aac832397 |  | note | Inspection or Test: Method - Inspect
label | b5ae8a11-7555-51c9-a5b0-828f6b61015c |  | note | Inspection or Test: Freq. - Per Concrete Delivery / Per Placement
label | 97cc9910-052d-5ee8-8fe0-979d2b08d2fe |  | note | Inspection or Test: Responsible Person - PRECO
label | d0d71ce8-ae9f-568b-b2e1-01ab7409b823 |  | note | Verifying Document - In-Pour Checksheet / Delivery Docket
label | dd891b55-3834-559f-a59c-f5a4d769d5d3 |  | note | Records required for handover package: Yes/No - Y
label | 1863c022-8047-5deb-8720-aa7a43389550 |  | note | Inspection / Test Authority: Conduct - C
label | de9063fe-7287-5f4b-8ab9-6fe3e1ecc0a0 |  | note | Inspection / Test Authority: Witness - C
label | 92efaba6-6645-5395-8bff-9c46a435f71b |  | note | Inspection / Test Authority: Produce Record - C
label | 7acaa081-f417-528c-9e45-3c8341c68e11 |  | note | Inspection / Test Authority: Approval - C
label | 2721098c-0c32-5e5f-88de-48ba461fd82b |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.5 - Concrete Sampling/Testing
label | 15f240f6-87cc-500e-b08d-3abc9de99072 |  | note | Acceptance Criteria - Compressive test 1 x 7d and 3 x 28d results + 2 stress transfer cylinder (1 for test + 1 spare) stored at curing temperature
label | c17174e3-fd7c-599b-bbe5-c57e91af8e4c |  | note | ○ 60 MPa at 28 days
label | d118ff8f-c305-5261-93e2-b9629fa6eaae |  | note | Inspection or Test: Method - Concrete Sampling/Testing
label | 396500ee-9dd4-50cd-a15d-cd478f6fa682 |  | note | Inspection or Test: Freq. - One set per precast beam with an additional set taken from any truck which has water added after leaving the plant
label | e4182f51-8d06-50ff-b4ff-f7c4e06fb709 |  | note | Inspection or Test: Responsible Person - Subcontractor
label | 9646702c-0876-5348-9c9e-85b19ba2767f |  | note | Verifying Document - Concrete Sample Test Results (IANZ Accredited Laboratory for 7 & 28days test)
label | 529fd1b4-3428-5e49-8b72-571ea73d607e |  | note | Records required for handover package: Yes/No - Y
label | 2721c42e-3120-5942-9935-c29f8a846037 |  | note | Inspection / Test Authority: Conduct - C
label | c5c55d80-f4d4-5c14-9844-81e70258326f |  | note | Inspection / Test Authority: Witness - C
label | 672acacb-5ee7-53fe-8c14-1bb41c1c7e33 |  | note | Inspection / Test Authority: Produce Record - 3
label | 0bc79d63-84e3-532c-9e7b-cc29788e9d9f |  | note | Inspection / Test Authority: Approval - C
label | 339cdc9e-5a98-5236-8e67-62fa19d28db1 |  | note | Hold Point - Y (Designer to be notified immediately if specimen fails)
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.6 - Heat Curing
label | 0e5ebd5c-2e94-5ca3-bb7c-08e2ee65d371 |  | note | Controlling Documents - Approved Heat Curing Methodology
label | 88a03694-72e0-5798-91f1-ab548320b5b1 |  | note | Acceptance Criteria - Concrete core temperature shall not exceed 70 degrees
label | d13251b0-a197-5602-8154-d1632a8eab7c |  | note | ○ Steady state inlet and outlet water temperatures recorded
label | 85ada80e-9c11-56e1-95d2-2e0b7844af20 |  | note | Inspection or Test: Method - Temperature Monitoring
label | 620b90c4-8f34-56d4-8094-0c3d4fc5af36 |  | note | Inspection or Test: Freq. - Per Beam
label | d36788b1-ca10-5785-a3e1-dde4fd2f2d22 |  | note | Inspection or Test: Responsible Person - PRECO
label | 02bed0c0-3d6f-507d-a6c8-268d3c1283c3 |  | note | Verifying Document - In Pour Checksheet, Hot Water Curing Methodology
label | d53be086-79b2-5f5b-9004-641ef88b5803 |  | note | Records required for handover package: Yes/No - Y
label | dc210e64-5df0-55b3-883c-d9091295358f |  | note | Inspection / Test Authority: Conduct - C
label | 7c9c17dd-5718-5b5b-af55-ba56a659fe14 |  | note | Inspection / Test Authority: Witness - C
label | 13cf92ff-5eca-5ffc-86a3-70d3bc30ff36 |  | note | Inspection / Test Authority: Produce Record - C
label | 7b832ff4-8065-5318-a882-b758b5faa0df |  | note | Inspection / Test Authority: Approval - C
label | 0acf477d-6168-5666-9c59-a90a8d7aab75 |  | note | Hold Point - Y (Designer to be notified if anomalous temperature readings encountered)
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.7 - Concrete Curing
label | f8bd1996-0eff-587c-82c9-cec2c936c860 |  | note | Controlling Documents - NZS 3109
label | 8b4376c3-5eba-576e-a6d8-96e199a7ea80 |  | note | Acceptance Criteria - 7 days wet curing required following completion of accelerated curing
label | 4ecd5945-223d-581e-84dc-40724e292517 |  | note | Inspection or Test: Method - Inspect
label | 3bd1cb23-136b-580e-8d8a-2158babb60e9 |  | note | Inspection or Test: Freq. - Per Beam
label | 110ce892-d8d3-5df4-9439-61440d31d9f8 |  | note | Inspection or Test: Responsible Person - PRECO
label | b7dfb368-43bb-5749-a772-93f869e24543 |  | note | Verifying Document - Post Pour Checksheet
label | cce69b92-0f21-556c-9148-62ae914dcd4a |  | note | Records required for handover package: Yes/No - Y
label | c6115285-18c6-566c-81e5-f777e6ba92ca |  | note | Inspection / Test Authority: Conduct - C
label | ac33b12b-2462-5132-9745-b874f4c18405 |  | note | Inspection / Test Authority: Witness - C
label | f2312730-daa7-5a4f-98dd-ffaaea72abe4 |  | note | Inspection / Test Authority: Produce Record - C
label | 4c534583-6546-5a29-9845-4a06701677a7 |  | note | Inspection / Test Authority: Approval - C
label | 9b5b94a7-929b-5d7c-9fbf-e4121869caad |  | note | Hold Point - Y (Designer to be notified immediately if water supply interrupted)
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2.8 - Type B Construction Joint
label | a74ae819-b8ef-5103-a472-48df91c81149 |  | note | Controlling Documents - NZS 3109
label | 9dad99db-896b-5d9b-8671-6fce30d46560 |  | note | Acceptance Criteria - 5mm amplitude and free of latinece, cut with water blaster and with use of High Strength Spray on Retarder
label | 48aacd0f-fa6b-51d2-8872-2b9d3e01e1fb |  | note | ○ Top surface of all beams and end blocks of integral beams
label | 0b775548-e859-5652-89c9-b74b9c3e2233 |  | note | Inspection or Test: Method - Inspect
label | 18393de2-a168-5ff5-9392-02646e26fe44 |  | note | Inspection or Test: Freq. - Per Beam
label | 939edf25-0e76-5021-9b62-66ab7e966c1a |  | note | Inspection or Test: Responsible Person - PRECO
label | 0e01020b-276a-5a0b-b2f6-4a095c5a6ebc |  | note | Verifying Document - Post Pour Checksheet
label | 5deaeff2-7c53-50c7-84d4-5d4e1d103bd9 |  | note | Records required for handover package: Yes/No - Y
label | 6ee08dfe-6301-5250-80f5-f3c9a38730f3 |  | note | Inspection / Test Authority: Conduct - C
label | 5c2e87b9-0789-503f-9f77-ce612bd5fb38 |  | note | Inspection / Test Authority: Witness - C
label | 91362d65-3729-5f6e-a392-aeee07db5b54 |  | note | Inspection / Test Authority: Produce Record - C
label | 12d8baf7-0b1f-539b-9636-d888095d76a0 |  | note | Inspection / Test Authority: Approval - C
label | 1432c686-83b0-5622-966b-a7651bdfff37 |  | note | Hold Point - N
checkpoint-status |  |  | checkpoint | 2.9 - Post Pour Inspection / Draw-in Measurement
label | 9162f016-8ac8-5c03-bc38-5f1ff150c065 |  | note | Controlling Documents - IFC Drawings
label | 88c3de0b-d061-58f5-9399-b331de92a632 |  | note | Acceptance Criteria - Surface Finish Requirements- (F5 for seen faces) / Dimension/inserts/cut-outs as per drawing
label | 169eb815-1eaf-5621-bea3-46009f60330a |  | note | Inspection or Test: Method - Inspect
label | e9ad51b9-25a7-5890-b286-1e69b09effdc |  | note | Inspection or Test: Freq. - Per Beam
label | cce9461e-a042-595e-8200-93f01be1ea29 |  | note | Inspection or Test: Responsible Person - PRECO
label | 326621a2-1858-5b67-8699-5f659c336dc8 |  | note | Verifying Document - Post Pour Checksheet
label | 240ec643-e959-55e3-a014-efd764f512a1 |  | note | Records required for handover package: Yes/No - Y
label | c22e7cd1-4c7d-5b5b-8e97-e48c349827b8 |  | note | Inspection / Test Authority: Conduct - C
label | 74c592b4-0d91-5e89-8cd9-88c8ada682eb |  | note | Inspection / Test Authority: Witness - C
label | 838c00c9-44e5-5c3e-b1f7-dd9dd7686d73 |  | note | Inspection / Test Authority: Produce Record - C
label | ffa656c5-4f03-544f-bf7b-96edd380595f |  | note | Inspection / Test Authority: Approval - C
label | cf5c2e86-f608-5900-8099-9073be5f505e |  | note | Hold Point - Y
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 3.0 Stessing Related Operations
checkpoint-status |  |  | checkpoint | 3.1 - Strand Positioning
label | 6258448c-266c-50e8-b3cc-379f62795012 |  | note | Acceptance Criteria - +/- 3 mm in any direction
label | 9efca5fe-1b6c-5003-abbd-77e03a1c4096 |  | note | Inspection or Test: Method - Inspect
label | 95b32a57-8d78-53c4-8a3e-2bdf6503ef42 |  | note | Inspection or Test: Freq. - Per Beam
label | 6ec0141b-4772-5f01-a262-7057c7578087 |  | note | Inspection or Test: Responsible Person - PRECO
label | d5ffe661-b0a9-508a-99eb-a60b5512324d |  | note | Verifying Document - Pre Pour Checksheet
label | 48f5a84c-3824-5589-bace-f0f5e71023d8 |  | note | Records required for handover package: Yes/No - Y
label | 515d378c-5c2f-5665-8908-3eb8f667a100 |  | note | Inspection / Test Authority: Conduct - C
label | 9d3926c5-bb15-571a-84c5-9b4a3303e59b |  | note | Inspection / Test Authority: Witness - C
label | 9de33223-6efa-5178-8d3f-d08f599672e3 |  | note | Inspection / Test Authority: Produce Record - C
label | 39a6e795-e02d-52ea-bdd6-0ebb48890c67 |  | note | Inspection / Test Authority: Approval - C
label | 78d81136-4187-5599-b59d-ced444f5274e |  | note | Hold Point - N
checkpoint-status |  |  | checkpoint | 3.2 - Stressing
label | 3d9002a8-01c5-516f-aa32-0b7fbb69148e |  | note | Acceptance Criteria - Collation of stressing records incl unit ID, strand extention, jack pressures and general comments
label | 3fcf964a-2ab3-5f98-aefc-c745ecd0ec08 |  | note | Inspection or Test: Method - Review
label | b9cb5ece-c8fa-5d67-a4fc-aec54a035324 |  | note | Inspection or Test: Freq. - Per Beam
label | 32ddf547-fd9e-5fe2-9fce-5db1916fb135 |  | note | Inspection or Test: Responsible Person - PRECO
label | 920bcc17-41da-5147-8c8d-46b9929ec7c9 |  | note | Verifying Document - Stressing Checksheet
label | 847a6442-5d0a-579a-9d48-12af8e079d8d |  | note | Records required for handover package: Yes/No - Y
label | 884a3bd6-187e-5df1-a4d6-591ca9a59f33 |  | note | Inspection / Test Authority: Conduct - C
label | 69daa57c-2297-5e68-bfb1-3ea07e1dcc5f |  | note | Inspection / Test Authority: Witness - C
label | 4bcbbc71-5099-5261-bbf6-597958e0ffb9 |  | note | Inspection / Test Authority: Produce Record - C
label | 91eb012b-17b4-5312-9c72-30df09ecf63b |  | note | Inspection / Test Authority: Approval - C
label | a74e6dfd-0701-5fdd-89d5-3ad8a1343262 |  | note | Hold Point - Y (All anomalous readings not in line with Stressing calculations to be submitted)
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3.3 - Stress Transfer
label | 49cbe5f3-da5c-55af-96a5-7d9ba9842cd8 |  | note | Acceptance Criteria - Concrete Cylinder Tests to be minimum 40MPa
label | 94a4b5d2-3479-5f60-8649-f3fedcf16812 |  | note | ○ Cylinder to be kept in similar conditions to beam
label | 4338d86d-a09b-5178-84cd-b178bfcf332d |  | note | Inspection or Test: Method - Cylinder Compressive Strength Test
label | a9408e8b-177c-5e74-a06b-f6120a3e38ae |  | note | Inspection or Test: Freq. - Once Per Beam
label | 2f960902-c5a4-553a-af13-74ba7f058bfc |  | note | Inspection or Test: Responsible Person - PRECO
label | 83b30231-3f61-5b9b-99b7-33a17af6eaf3 |  | note | Verifying Document - Cylinder Compressive Strength Report (In-house)
label | 914099fa-62cd-5cb7-8d1e-ae7aceed26f3 |  | note | Records required for handover package: Yes/No - Y
label | 72a7b8e9-2617-5b6f-bf5d-6fe73f980db7 |  | note | Inspection / Test Authority: Conduct - S
label | 90565c20-cf1a-5784-b374-1500459228bc |  | note | Inspection / Test Authority: Witness - S
label | 2d8519bc-02a3-51a4-bbd8-2ae414fa9f56 |  | note | Inspection / Test Authority: Produce Record - S
label | 1a8e7152-089a-5022-be09-417f308fb7ef |  | note | Inspection / Test Authority: Approval - C
label | f660713d-289f-590f-8588-9bcd8b850288 |  | note | Hold Point - Y (No Stress transfer before 30MPa)
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 4.0 Final Documentation
checkpoint-status |  |  | checkpoint | 4.2 - Producer Statement (PS3)
label | 39010b13-1dce-56dd-9210-021be341f937 |  | note | Acceptance Criteria - Signed PS3
label | 653b297f-415d-5526-b08f-50bafe58ab16 |  | note | Inspection or Test: Method - Report Production
label | b857b720-45a1-5c30-88a0-04a89f5612f3 |  | note | Inspection or Test: Freq. - Once
label | 7e428ed8-e363-517f-ab8d-7ea9d283d61a |  | note | Inspection or Test: Responsible Person - PRECO
label | 30d3f47b-a99b-5876-bf16-2658598ec75d |  | note | Verifying Document - Signed PS3
label | d1299c2a-f6f5-5998-a93b-64a67b2444f5 |  | note | Records required for handover package: Yes/No - Y
label | d6022bd2-cf41-569b-abb4-6a8bbe2b83fa |  | note | Inspection / Test Authority: Conduct - C
label | 61dbf0dc-a414-5c3d-850d-70db3894c313 |  | note | Inspection / Test Authority: Witness - C
label | 6e753d30-ec20-52bf-8bb2-dec744d82f34 |  | note | Inspection / Test Authority: Produce Record - C
label | 23b51786-85de-550e-99b2-67773f6dfc58 |  | note | Inspection / Test Authority: Approval - D
label | 560f212d-257b-50b8-9024-4318b05d7c13 |  | note | Hold Point - N
checklist-sectioned |  |  | checklist | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | itp |  |  |  | Yes | ITP - Pavement & Surfacing - AP40 Material - Rev 1 | 7dd3ad9d-10ed-4b19-84e4-665850891756
checkpoint-group |  |  | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
checkpoint-status |  |  | checkpoint | 2.01.01 - Basecourse CBR
label | 49feefc3-588f-5a18-a041-0e972e47510d |  | note | Acceptance / Conformance Criteria - (a) compacted in accordance with NZS 4402 : 1986, Test 4.1.3 New Zealand Vibrating Hammer Compaction Test at Optimum Water Content and;
label | 60fe236d-5085-5b0d-bf42-d0daecc97a4f |  | note | (b) tested in accordance with NZS 4407 : 1991, Test 3.15 The California Bearing Ratio Test (without a surcharge for at least 4 days). The soaked CBR of the basecourse aggregate shall not be less than 80%.
label | f2d19251-5dc6-5502-b284-ae9daf0e77c5 |  | note | Standard / Specification - TNZ M/4: 2006
label | c0fb680d-688a-5a53-8ee8-018c1be109c8 |  | note | Verifying Document - IANZ Lab Reports
label | 092ee455-c68a-52da-b948-069dbee4c3e5 |  | note | Frequency - 10,000m3
label | a20f305f-4ca6-5475-b922-31e79decface |  | note | Activity - HP
label | 0eea9014-d4d1-5b97-9f91-3ae4d1913b50 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.01.02 - Running Course Material Approval
label | c35c4f61-7668-59a9-8a32-5fa88411ca5e |  | note | Acceptance / Conformance Criteria - The running course shall have a crushing resistance of not less than 130 kN when tested in accordance with NZS 4407: 1991, Crushing Resistance Test, Test 3.10. It shall be free from all non-mineral matter.
label | 00ee2165-c923-52c1-a7c1-c8be26b744a0 |  | note | • The grading of the running course shall conform with Figure 3 of TNZ B/2:2005, 10.2, when tested in the same manner as required for the parent basecourse. (IF USED)
label | 4b73ec4b-e5d5-5465-8748-2724aaf33df6 |  | note | Standard / Specification - TNZ B/02: 2005 - 10.2
label | 09652dfd-98c4-557f-b304-99834837ee0d |  | note | Verifying Document - IANZ Lab Reports
label | d8499938-8384-5e3a-974e-f813ce8ea501 |  | note | Frequency - 1 test every stockpile
label | 30b3ebf3-2c6a-582c-b8dd-ec8a5461615e |  | note | Activity - HP
label | 090b0c2a-58bd-525e-b9df-1cc56bfd03c0 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.01.03 - Basecourse MDD and OMC
label | 4b76bb15-0733-5f17-be70-a7872640bbc9 |  | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC). Test on heavy compaction, vibrating hammer.
label | 231b71bc-a331-597e-9693-4b71838c0655 |  | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | c13ccd03-f4be-578f-9839-018fceb45966 |  | note | Verifying Document - IANZ Lab Reports
label | 89535989-ce9f-5033-b5a5-0d2d0f850ac6 |  | note | Frequency - 1 test per material type
label | 095585ed-5db8-560b-b506-42b6f64bb47f |  | note | Activity - H
label | 4922a46a-ce96-5b3b-9f26-174f9c43f553 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 2.01.04 - Crushing Resistance
label | edb7e3ac-db99-5ab7-b928-75906bda42c0 |  | note | Acceptance / Conformance Criteria - The crushing resistance shall not be less than 130kN when the aggregate is tested
label | d7d65de4-a18b-5fc7-b83b-85abf5a7b5ef |  | note | Standard / Specification - NZS 4407: 1991 Test 3.10.
label | 8556196e-9046-5bbd-ba48-6a9f2df45fa2 |  | note | Verifying Document - IANZ Lab Reports
label | e81886fc-44c2-5966-80d6-283cbbfba1a7 |  | note | Frequency - 2 tests per source 4 weeks before use in the works
label | 367b8f1b-d809-5e45-93cc-53fba2acb9df |  | note | Activity - HP
label | 49c94da8-65cf-53c3-9870-956af1c22f4d |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.01.05 - Weathering Resistance
label | 86ae2acf-2389-5ba7-aa9f-1b3ec70d4642 |  | note | Acceptance / Conformance Criteria - The aggregate shall have a quality index of AA, AB, AC, BA, or CA when tested
label | 98ca51b1-9259-5e18-8408-177657df2e00 |  | note | Standard / Specification - NZS 4407: 1991 Test 3.11
label | bea56576-48b0-5a51-a4b7-025c2d69fdc6 |  | note | Verifying Document - IANZ Lab Reports
label | 3388c215-27fb-5b48-9360-a185b1a46bc0 |  | note | Frequency - 2 tests per source 4 weeks before use in the works
label | cb6be75d-bc7e-5543-8ee6-c9509f04b222 |  | note | Activity - HP
label | 13ddf1ad-108a-5528-8c58-ba360195dc4c |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.01.06 - Particle Size Distribution
label | ea27af91-c4e8-5aca-8207-6ea4a0cd81b8 |  | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 2 and 3 from TNZ M/4:2006.
label | 02b46647-7530-5d7b-a380-a55e3640f4e5 |  | note | Standard / Specification - TNZ M/4: 2006
label | da23db52-ff3f-5278-8584-c1c8331d43c4 |  | note | Verifying Document - IANZ Lab Reports
label | 8d967d1b-3eed-5ec9-9777-0b99a39c3ed2 |  | note | Frequency - 0 to 400m³ - 2 tests
label | 5e5fcd4f-ace5-569d-ad71-4f9f9bed611b |  | note | • 400 to 1,500m³ - 3 tests
label | 2fffda83-5727-5289-aee5-19ffe6c6683e |  | note | • 1,500 to 4,000m³ - 4 tests
label | ee93229f-5f11-51a0-b51d-0029d2a1adb2 |  | note | • >4,000m³ - 1 test for each additional 1,000m³
label | 0dc8fd25-ab31-5aad-82f4-810b3de3a30b |  | note | Activity - HP
label | 00fd27c9-c403-5163-b669-8aa7eb6c25ee |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.01.07 - Sand Equivalent
label | 5572a225-1b12-5ec7-8e4d-976f85ad6de0 |  | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407 : 1991, Test 3.6 Sand Equivalent Test.
label | da6de437-7513-56ce-9a69-3041123d9c89 |  | note | • If Sand Equivalence is < 40, then Clay Index shall not be > 3 and Plasticity Index shall not be > 5 (both being tested in accordance with the methods described above).
label | 684c06d1-5e7b-59d1-b2e8-e5820065c7b1 |  | note | • The Sand Equivalent shall be determined using the Wet Method in NZS 4407: 1991 Test 3.6
label | 7257ff58-571b-5bcc-94a7-16d39d767a16 |  | note | Standard / Specification - TNZ M/4: 2006, 4.2.1.1
label | 25672133-332c-5316-8c22-fb96afcda8d7 |  | note | Verifying Document - IANZ Lab Reports
label | 9404f767-20ec-57bc-8b9a-b05ff4161aa4 |  | note | Frequency - 0 to 400m³ - 2 tests
label | 42fdb336-16c8-5801-9a29-38141af43cbc |  | note | • 400 to 1,500m³ - 3 tests
label | 093f1489-71be-5cc8-a336-d0fa8111d0a5 |  | note | • 1,500 to 4,000m³ - 4 tests
label | b0fae1ce-8a94-5e2a-847a-c05f4aa5aa46 |  | note | • >4,000m³ - 1 test for each additional 1,000m³
label | a4ffeded-c0bb-5d1c-9d42-03a9244068ac |  | note | Activity - HP
label | 092f8827-5d9c-5bfd-beec-decc3e8ca447 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.01.08 - Liquid Limit
label | 94ea2bb8-2f99-505a-8180-8022555be423 |  | note | Acceptance / Conformance Criteria - The Liquid Limit shall be ≤ 25 when tested in accordance with NZS 4402 Test 2.2.
label | f8df0db3-87ee-5e8b-a51f-1abbf517ed5e |  | note | Standard / Specification - PS - 7.2.3
label | 4743447b-1543-5fd0-8df4-19273089b6b8 |  | note | Verifying Document - IANZ Lab Reports
label | dcd6b8fd-0e3f-5326-b0d1-a2ae57b687cd |  | note | Frequency - 0 to 400m³ - 2 tests
label | ed1b49ae-d253-5dd0-a7ca-b88b10599425 |  | note | • 400 to 1,500m³ - 3 tests
label | cbe58cad-de5b-5630-877d-52cabfb0ead7 |  | note | • 1,500 to 4,000m³ - 4 tests
label | 42bf96a7-239a-5fd4-9ffb-4211ff77611c |  | note | • >4,000m³ - 1 test for each additional 1,000m³
label | db9425ad-9a83-5aa4-be0f-e8e02b812dd6 |  | note | Activity - HP
label | caba5892-dec1-557e-830c-eabd731d1d79 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.01.09 - Plasticity Index
label | ca0b0430-ecf9-520f-8416-fab47706e4ad |  | note | Acceptance / Conformance Criteria - The Plasticity Index shall be ≤ 8 when tested in accordance with NZS 4407 Test 3.4
label | b4d6bad6-93f6-5675-bffd-4ee930dad6c3 |  | note | Standard / Specification - PS - 7.2.3
label | 07d5b80a-e1fd-5cd5-bd63-cde18bc7873a |  | note | Verifying Document - IANZ Lab Reports
label | 26da61b9-4fbb-5351-92e6-cd4ebda2f352 |  | note | Frequency - 0 to 400m³ - 2 tests
label | e7ccd9e2-d84e-563c-b72a-5efa3b79d686 |  | note | • 400 to 1,500m³ - 3 tests
label | c9ef1931-3a0c-56a4-93c1-4f20cf8ba5be |  | note | • 1,500 to 4,000m³ - 4 tests
label | e70c514d-ec28-5306-9b1e-309be1e35650 |  | note | • >4,000m³ - 1 test for each additional 1,000m³
label | d9d286ee-3b26-56ce-9fd5-2744c4cc31f4 |  | note | Activity - HP
label | 929aa643-972c-556c-b644-30bbf8e8fd00 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.01.10 - Clay Index
label | c5cb8138-5b5b-5f01-b352-637dda2343de |  | note | Acceptance / Conformance Criteria - The Clay Index shall be ≤ 5 when tested in accordance with NZS 4407 Test 3.5.
label | 2ad9ee32-a09a-5f57-ac4f-c468049aee8c |  | note | Standard / Specification - PS - 7.2.3
label | b9754f71-3ee9-598c-80f5-6eed4874cf24 |  | note | Verifying Document - IANZ Lab Reports
label | d00de851-7991-56ce-854f-29f6020cdd60 |  | note | Frequency - 0 to 400m³ - 2 tests
label | 1b71fb50-1e21-51f7-954d-368e6721ef85 |  | note | • 400 to 1,500m³ - 3 tests
label | 3553b48c-be94-5eaf-933d-43138b9114d5 |  | note | • 1,500 to 4,000m³ - 4 tests
label | 771b5fa2-88f6-5018-a3bb-7822e8da2eb4 |  | note | • >4,000m³ - 1 test for each additional 1,000m³
label | 18ff526f-0935-5e42-b47e-0ba352cb4ff9 |  | note | Activity - HP
label | e7708385-c49e-50f2-af6f-296359364d18 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.01.11 - Accelerated Weathering Testing
label | cdacb3fe-de6e-5c12-ad45-1dbd1af37f24 |  | note | Acceptance / Conformance Criteria - If the difference between the tested sample and the control is >30% in the accelerated weathering test, the Contractor shall undertake additional x-ray diffraction analysis
label | a9d66b2d-7268-5744-8c47-38883fc76356 |  | note | • The levels of smectite clay minerals are not classified as “abundant”
label | ccc5af32-24c9-55f6-90e9-53323ade5810 |  | note | Standard / Specification - In accordance with NZTA Standard Specification T20 Draft Specification
label | 74f995cb-5cbf-5689-a8aa-04f4a1dd8737 |  | note | Verifying Document - IANZ Lab Reports
label | 3b2ff59f-6c50-57e2-b1f9-7295eab28dc6 |  | note | Frequency - 2 tests per source 4 weeks before use in the works.
label | e7c1bd06-7278-50d5-86d3-bb687be7ac91 |  | note | Activity - HP
label | 117a5286-a1a7-5aad-b5f6-b5ad8f6bb408 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.01.12 - Repeat Load Triaxial Test
label | 08b10ea8-0e4d-5cc2-accc-084aca7b4501 |  | note | Acceptance / Conformance Criteria - In accordance with NZTA T15
label | a116e146-494a-5233-bce3-d2b9ff94d20d |  | note | Standard / Specification - NZTA T15
label | f29381aa-0a34-5bd4-90eb-659c4c25497b |  | note | Verifying Document - IANZ Lab Reports
label | 706b2437-18b6-5b03-b048-d2d22378dcf6 |  | note | Frequency - 2 tests per source 4 weeks before use in the works.
label | 1bafa94a-9672-572d-a26e-d49166cc001b |  | note | Activity - HP
label | a08e87bb-c079-574c-bde9-416f9a9578f9 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.01.13 - Broken Face Content
label | 1dee13a2-b73f-5338-b58c-2f21196685fe |  | note | Acceptance / Conformance Criteria - The aggregate broken face content in each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces, when tested according to NZS 4407: 1991, Test 3.14 Broken Face Test.
label | f57c44fc-b5a6-5d80-8fd0-bdfa97109bc1 |  | note | Standard / Specification - TNZ M/4: 2006, 4.2.2
label | 72ce007a-6242-5bbd-a8d8-35849dcb2816 |  | note | Verifying Document - IANZ Lab Reports
label | 184d8c50-9feb-5fae-9a01-4b7ec19c54f9 |  | note | Frequency - 1 Test per Source
label | 285defd3-5103-5420-85c5-e8b8af0b82c9 |  | note | Activity - HP
label | d7fa7ff3-d18c-519a-b767-83a3181df103 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Subsoil Drainage - Rev C | itp |  |  |  | Yes | ITP - Subsoil Drainage - Rev C | 7f743aa3-2ad8-4161-9f58-b77b037f7af8
checkpoint-group |  |  | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint-status |  |  | checkpoint | 3.01.01 - Construction Pack
label | d7be2db3-ea6e-5081-a3fa-9f6578272af5 |  | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
label | 5936e5dc-9132-5d53-b0f0-f9edfbdd1a3e |  | note | Standard / Specification - Downer
label | cfbc549f-882c-5b41-a11d-18be0dc167f0 |  | note | Verifying Document - Construction Pack
label | 0319a400-84a4-55c0-8f70-441f504d8b57 |  | note | Frequency - Submit 10 days prior to commencement of works
label | 598b8731-aef4-573c-9ee4-06c6f222b97c |  | note | Activity - H
label | 24ef8194-9972-500e-adc3-9b62ccb8ba7a |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.02 - Survey Setout
label | 0b9f3034-6658-56f0-bed8-ace15c277a22 |  | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | 9e4ed420-adcf-5040-8a91-5853fed16b09 |  | note | Standard / Specification - Downer
label | a6281da7-de12-5e2e-b68c-2038b57ad103 |  | note | Verifying Document - Survey Records
label | 45bc84e6-beab-520e-969b-361fcb60ac3b |  | note | Frequency - Prior to Works
label | bbb6fcb2-e555-5583-a8a9-9810156a90e3 |  | note | Activity - H
label | d53b4c04-315b-5f54-9469-90c1e8b22600 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 3.01.03 - Approved Construction Drawings
label | bdc2842a-7d3c-5544-8137-d83b5f982a4b |  | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | 5ef2bb59-c850-5c20-b02f-ff31fd4b6d78 |  | note | Standard / Specification - Downer
label | 3b11c33a-f8b5-5aa7-91f1-10782e9fcd4c |  | note | Verifying Document - IFC Drawings
label | 323def97-05b9-5489-b1f2-f8c27a4140fc |  | note | Frequency - Prior to works start
label | 00cf16f7-ade9-5aed-96d5-1472f835be59 |  | note | Activity - H
label | c532f3a9-d2d4-505d-9f4f-94f7ceb8bff4 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.04 - Topographic surveys for measurement
label | e089d5f4-ced8-5485-83ad-883cd2451b09 |  | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
label | 808d2cc8-9cea-5c17-bafa-6c2345d96560 |  | note | Standard / Specification - PS 2.2.12
label | e2834ee1-8f42-5772-8411-554e951bc1c2 |  | note | Verifying Document - As-built
label | b4a1ce01-172e-511d-a93b-50253d6f1411 |  | note | Frequency - Prior to works and Post Works
label | 6605b2b1-c1bd-5cb6-9e50-f19229bfb5c6 |  | note | Activity - H
label | 96c2efd0-54fa-513d-a450-0bd6f9b3055f |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.05 - Permits
label | 468dfa97-219c-50fd-923f-0d9544cbcf74 |  | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
label | 49520b88-dffc-5373-8e83-2849833fa509 |  | note | Standard / Specification - ITP Register
label | 919e8e00-24fc-5e88-8149-179c7690596f |  | note | Verifying Document - ITP Sign Off
label | ac6c3b17-fe3f-594c-807b-37ec131c6fa3 |  | note | Frequency - Prior to commencement of construction activity
label | 300f8782-e48f-5ee4-8055-969ed04e07bf |  | note | Activity - R
label | d10c2e34-7c87-51b7-9288-001049b9f637 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.06 - Stakeholder Management
label | 4037dfc7-c3bd-5aa4-9e8b-fe22489a235f |  | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works, Agree plans for maintaining access to properties during construction with landowners
label | 9e03c87e-42fe-5e7a-a630-a9438155d21a |  | note | Standard / Specification - Project Stakeholder Management Plan
label | 58923489-7e4e-5f9a-8035-03446e1d91ac |  | note | Verifying Document - ITP Sign Off
label | 1ebff814-28de-5b91-beac-5601bddfd866 |  | note | Frequency - Prior to Construction with continue updates throughout the works
label | 929d5338-bda6-5c79-9ed8-ee53912897ca |  | note | Activity - R
label | 673074b5-d940-5c63-88c8-6e7532dee716 |  | note | By - SE
checkpoint-group |  |  | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint-status |  |  | checkpoint | 4.01.01 - Subsoil Pipes
label | d023e47e-0881-5696-b786-b671d17dc843 |  | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 160mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
label | c9763730-9a2a-5ad5-ba5b-077d9dc7bb95 |  | note | Standard / Specification - GWS 3.2.1
label | 6b68e6b6-12fb-5968-9d52-560fe63a6581 |  | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
label | c7beaa27-ccc8-5dbd-a188-c2977568a3a1 |  | note | Frequency - Every Delievery to Site
label | 0cc38bc5-f539-55fd-bc56-03bf014af76d |  | note | Activity - C
label | a60f67ca-2a43-568d-af02-4a88420851c4 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 4.01.02 - Subsoil Drainage Aggregate
label | 7c9b9dfc-297e-5ddf-a2f1-b17179a69881 |  | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings (40/20 aggregate). Be open course grade clean durable aggregate, Have a crushing resistance of no less than 100kN when tested in accordance with NZS 4407:1991 Test 3.11
label | d2089a10-530f-5bea-9d97-e03f611b919a |  | note | • Meet the following gradings when tested in accordance with NZS 4407:1991, Test 3.8.1:
label | 1be6988c-c61e-5bbe-9f18-091fb2c8dbf0 |  | note | • App B - HAM2018-0136AJ Rev. 1 Geotechnical Works Specification:
label | 619f493e-fa37-54ff-a2d4-7dfa142ac2e9 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | ad40829b-6deb-568e-b971-18272b95949b |  | note | Table 2: Filter Material Gradings (Geotextile Wrapped Aggregate)
label | 8ac0fdb2-32b2-5131-910a-4d69cbe8d50a |  | note | Test Sieve Aperture (mm) Percentage Passing (%)
label | 8b672988-c8b6-50c5-aaf2-02fc53ebf6df |  | note | 53 100
label | 0e075548-0ba0-5abb-a495-2f81fee72ea4 |  | note | 13.2 10 (max)
label | cee24c29-e7a4-5fe5-9a66-851bc47a9799 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – – –
label | 4497dc5e-e119-536b-8d5a-d19a998b5f97 |  | note | Standard / Specification - GWS 3.2.2 & 3.4
label | 107e7486-30e9-57fd-98af-3e0ab781e9e4 |  | note | Verifying Document - PSD, CR
label | c62d37bb-463d-5741-90af-459676b5e147 |  | note | Frequency - Material Tests every 1000m³ or change of source. Visual inspection every load, verifying document photos of material onsite, if visual appearance changes, additional testing will be required.
label | 6e631094-f166-58c8-8aff-d3be86d61f18 |  | note | Activity - C
label | 7aa1539d-3550-53e2-a337-8fe3b40077a4 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 4.01.03 - Filter Cloth
label | 5faac559-bd2e-5ffe-9de8-0fa793fdfd22 |  | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings. (A14 Bidim or Equivalent)
label | ef37e272-12eb-522c-b65c-9c3bfe7ca901 |  | note | Standard / Specification - GWS 3.2.3
label | ec905cb2-509e-562c-b9e8-367497b2cff9 |  | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class
label | 6945b2fb-ae9e-5f53-a594-a73692d450c5 |  | note | Frequency - Every Delievery to Site
label | 1ba31876-8f62-5f34-9b5a-5e0d22302dde |  | note | Activity - C
label | e916f350-f892-5b53-8079-3d441131cdb2 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 4.01.04 - Securing Pins
label | fa9c9129-d300-5f24-9ca8-9893d93bff4c |  | note | Acceptance / Conformance Criteria - Pins for securing the geotextile shall be of steel, a minimum of 5mm in diameter and atleast 400mm in length
label | 80f8485c-74a0-56e3-8a13-fd03950209a5 |  | note | Verifying Document - Verifying document to be copy of delivery dockets, photos of pipes onsite with tag showing class,.
label | 26fc6303-993b-580e-9e94-533265455d3f |  | note | Frequency - Every Delievery to Site
label | 573b3469-103f-5d64-bc95-552af65d6f39 |  | note | Activity - C
label | e6e29053-4c45-59de-8849-751676e8cd38 |  | note | By - SE
checkpoint-group |  |  | section | SECTION 5 – CONSTRUCTION ACTIVITY
checkpoint-status |  |  | checkpoint | 5.01.01 - Filter Cloth Wrap Inspection
label | c23e65e9-fd71-5526-a2cc-396855c6c195 |  | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain. TNZ F/6, PWRBSS Geotechnical Specification - The geotextile shall be placed in the tench so as to conform loosely to the shape of the trench.
label | ab0d7d29-29d7-569c-8d74-719e431bc677 |  | note | • Cloth must fully encapsulate the aggregate.
label | 3f79a82e-4f8f-5049-acfe-605be6782794 |  | note | • Geotextile longitudinal overlap to be minimum 300 mm (as indicated on drawing 3051 and required by NZTA F/6).
label | 1483e652-e91f-5bb0-9e6b-f016afc483be |  | note | • Additional sheets to overlap by minimum 500 mm and anchored with securing pins (F/6 requirement).
label | 451c6d88-06a4-5e60-9a96-571e4709de1b |  | note | • Verifying document, photos of trench prior to backfill, every line.
label | a5aca90d-3526-5f03-9d4b-ea2d31054500 |  | note | Standard / Specification - GWS 3.2.2
label | 8458197e-6626-5df2-a733-745266f8ce63 |  | note | Verifying Document - Every line
label | 5cf81d1e-986d-5a1c-8317-123ce26560ac |  | note | Frequency - Photos of trench prior to backfill
label | 236f455f-64de-5e7e-aeaa-2af1a2729ade |  | note | Activity - HP
label | 5a27d893-ed13-5da5-b7cc-d0e0405b49d1 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.02 - Trench Backfill
label | baa6961f-370b-5765-aa80-fe233acc44a2 |  | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard of the material previously trenched through. Drainage aggregate to be placed in layers of 150mm or less. Only light compaction such as tamping with the back of an excavator bucket is to be applied.
label | 0ad68759-e0df-5d72-b8ff-e757fada95ef |  | note | Standard / Specification - GWS 3.3
label | 8cbf68e2-3da2-5f54-9b65-4c777d4168ce |  | note | Verifying Document - Site Record
label | 75aec744-3603-5fcf-b939-cea07fe6f8d9 |  | note | Frequency - Each trench
label | ddefbe9b-d63f-531a-a74c-6802bd2597cc |  | note | Activity - I
label | 9b433955-7419-58fe-a75a-09c05c43ba72 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.03 - Drainage Outlets and Inspection Points
label | fb8bfbe6-7645-5a9f-b2e1-ff0313b2f573 |  | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete.
label | 6bd24fb9-47b1-5e5d-b005-36dc0d7659b5 |  | note | Standard / Specification - GWS 3.6
label | 174559c7-247b-5d06-9388-341126234e2a |  | note | Verifying Document - Site Records
label | e1b74fef-f4c2-5be7-a0c7-42401beaae55 |  | note | Frequency - Each Subsoil Line
label | b34148a7-1ae9-549d-9c79-bb90c1a412e9 |  | note | Activity - I
label | 018d7d09-84a5-51e8-9e37-149a30a9100d |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.04 - Subsoil Flushing
label | 48f356b9-0212-5f71-9f71-4cb92ac42b4e |  | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
label | 38814faf-75f9-5fb4-845a-a5f421a3e6ef |  | note | Standard / Specification - GWS 3.6
label | a5169edf-c580-5bab-8d64-598c905b9298 |  | note | Verifying Document - Site Records
label | 67309611-3ec8-584a-960b-61db5f9e0a97 |  | note | Frequency - On completion of earthworks
label | 2b55c223-fcfd-5c53-bb4c-8b944a45ba1d |  | note | Activity - HP
label | de3999c4-d716-56eb-bf28-b60aa9f23c25 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.05 - Survey
label | a58656a8-b22c-5642-b872-27a204d0207f |  | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | 46d921b2-6be6-5646-9bcb-1afc5ce57d70 |  | note | Standard / Specification - Downer
label | 934afbf8-cde1-5b5c-8f1d-c645411bc0e1 |  | note | Verifying Document - Records
label | 4022de56-c619-53f2-b7c7-8b85fa5c1c0c |  | note | Frequency - Post construction
label | e67df3ba-f8e0-581a-94df-028eac8b1908 |  | note | Activity - H
label | d29b5322-9ddd-542c-a502-b679078edb5e |  | note | By - SV
checkpoint-status |  |  | checkpoint | 5.01.06 - Excavation
label | 9b9ea235-3ac2-5591-acd5-5f26a4bb2cfc |  | note | Acceptance / Conformance Criteria - Trenches shall be cut in such manner as will ensure that the geotextile wrapped aggregate subsoil drains, and pipes if included, will be laid true to the depths, grades and lines shown on the drawings
label | fd79cc91-a199-5010-b0b2-fcd2dedcfea4 |  | note | Standard / Specification - Downer
label | 14e0668a-eb5d-569d-b10b-c1bb1d06e6fe |  | note | Verifying Document - Records
label | ac662a63-510c-54d7-a958-b3497ae10237 |  | note | Frequency - Prior to laying filter cloth
label | 3863aa9b-31d1-5020-92e0-eb4d3adf62f2 |  | note | Activity - I
label | a5ad0346-0cda-551d-9482-b30eef6a49e0 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.07 - Bedding
label | 6a804908-8011-5c5e-8a96-7cb5faf734cf |  | note | Acceptance / Conformance Criteria - TNZ F/5 - Bedding thickness shall be no less than 100mm
label | fc728791-6a66-56da-b5b1-f2ba3b2a6187 |  | note | Standard / Specification - Downer
label | 8c7e7c09-452a-558f-b85d-318a98193232 |  | note | Verifying Document - Records
label | 4010a9fc-e5fa-5a12-9b06-62aa2b2938d4 |  | note | Frequency - Prior to laying Novacoil
label | 34c5d6d8-bae3-517c-a4ad-f770fcd10460 |  | note | Activity - I
label | 8b1f267b-943d-5697-8660-baaeb969238b |  | note | By - SE
checkpoint-status |  |  | checkpoint | 5.01.08 - Joining Pipes
label | 509f6ddd-e8e7-51a6-b823-697d653eae3d |  | note | Acceptance / Conformance Criteria - TNZ F/5 - Joining the pipe shall be done using a purpose made pullout resistant coupling in accordance with manufacturers recommendations
label | c00b7388-1649-5fd0-ace2-fc8bac8049b6 |  | note | Verifying Document - Copy of delivery dockets, photos of pipes onsite with tag showing class
label | c928046d-14eb-576e-9b83-1323a75989d1 |  | note | Frequency - Every join
label | 443663f7-d6b2-544e-969f-6d6289bcd7e3 |  | note | Activity - I
label | 6df4a7c6-4500-5925-9856-6fef7a82c5b7 |  | note | By - SE
checkpoint-group |  |  | section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint-status |  |  | checkpoint | 6.01.01 - Construction Record Compilation
label | ab1b7353-5893-57a3-80bb-d6ff1ee576a6 |  | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | cad1b062-3767-5bfa-82fd-1152ad2d913b |  | note | Standard / Specification - Downer
label | f76eaa0f-f821-5f5e-9139-d0530719ea8a |  | note | Verifying Document - Records
label | f1b37311-80e2-54f9-909e-6ea161a5ea09 |  | note | Frequency - Post construction
label | a1f5e8c7-2e0c-5b65-8b40-cf0f2b87d5ff |  | note | Activity - H
label | cb9dd30f-398b-5a35-b2c6-33209e628017 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 6.01.02 - Survey Records
label | 49ab85d1-17d4-52ba-8ddd-a8233292baf4 |  | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
label | fde8f60a-25f2-5460-9306-ff372f6c3cf0 |  | note | Standard / Specification - Downer
label | 92033783-7b4d-5d01-ac3c-84c3456207e3 |  | note | Verifying Document - Records
label | 998b1506-d623-584c-be5d-cd0820fa307d |  | note | Frequency - As-builts taken every 10m prior to backfill
label | 1bd29fdc-651a-5e99-aee2-e2a3b722f923 |  | note | Activity - H
label | c4047b37-a420-5d21-afc2-67c0aec5fbfb |  | note | By - SV
checkpoint-status |  |  | checkpoint | 6.01.03 - Redline Drawings
label | a066bb4e-c82e-59af-8bba-6af8f6a7e272 |  | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.To show all subsoils, including temporary subsoils that become part of the permanent works, to show all outlet locations
label | f1e52e1d-0b8c-51a4-a9e5-d2600697c49d |  | note | Standard / Specification - Downer
label | f758af7c-1c61-5a10-8a0a-aa023ffe2a87 |  | note | Verifying Document - Redlines
label | 1a359c63-0963-5b55-92b9-c4cc287cb5b9 |  | note | Frequency - Post construction
label | 4ac95717-eebc-5c76-b0e3-4dc3b68120fa |  | note | Activity - H
label | ab194141-d0be-5408-80eb-315e3cfc0123 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.01.04 - Defect, Snag and Punch List
label | 7e05e999-2d6f-5e8b-a62e-c4a1158182c6 |  | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | ab4205d6-15f8-5e34-b898-be52195197a7 |  | note | Standard / Specification - Downer
label | 36a6fe75-c164-5283-8c1a-734be7f9167c |  | note | Verifying Document - Register
label | d1d138f1-e2a5-5c86-b8b3-1103ff26411f |  | note | Frequency - Post construction
label | 870c1870-8b7b-5b34-b350-3a5194c5f72e |  | note | Activity - H
label | 53670f27-89b5-51a6-8533-6ac698884d66 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 6.01.05 - Photos
label | b662aadc-8edf-5b86-a58b-fb6b8f1e8dbf |  | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
label | e7decdde-99c2-5795-9a38-8f781b821623 |  | note | Standard / Specification - Downer
label | 951f2ec0-db06-537b-9c6b-b338465022cb |  | note | Verifying Document - Photo Records
label | 7c139195-7df4-59ba-be0b-4073a6d97f85 |  | note | Frequency - Post construction
label | 5512b932-9243-5b16-afb4-6359730aba0f |  | note | Activity - H
label | 32d2feae-16da-5e27-91f7-9c338fecbe5b |  | note | By - SE
checklist-sectioned |  |  | checklist | ITP - Watermain-PE - Rev C |  |  |  |  | Yes | ITP - Watermain-PE - Rev C | 8acd6cf4-a7a3-4ade-a9e1-fd08547dc0a2
checkpoint-group |  |  | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint-status |  |  | checkpoint | 1.1 - Extent of Line Setout
label | 0a95db99-801f-5b64-b0e4-276d1fa2e264 |  | note | Acceptance / Conformance Criteria - Ensure line and level of Watermain has been marked out and agreed with Engineer in accordance with Watermain drawings Identify any clashes before construction.
label | abc94a23-054b-5d39-b35c-be522fbf1f99 |  | note | Standard / Specification - Design Drawings
label | 1e4a6c2b-0712-54b5-a084-37293bc07f79 |  | note | Verifying Document - ITP Sign Off
label | 04d90d08-9c86-529d-bdc7-d7f606d767e0 |  | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
label | 4e07d6b6-c8ca-5939-a4a0-b2fdc77acff1 |  | note | Verification Activity - M
label | 6512d3fd-65b8-5c93-81fc-3e7f4b28fcc3 |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 1.2 - Environmental Protection
label | 65087ed9-b989-5020-8054-6ed613639f0d |  | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
label | 82587d2b-c8ca-5163-a5e7-9c3bfa2d2f18 |  | note | Standard / Specification - Project ESCP Plans
label | d5236638-585e-5e7f-9e7a-d7121a304080 |  | note | Verifying Document - ITP Sign Off
label | 0fc5d5f1-98f8-5eed-b176-57002e3258b9 |  | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
label | 8366b632-0a70-5798-a741-526e150ce3e0 |  | note | Verification Activity - M
label | 3f118ed7-6930-568c-a87a-51e8ce7b2afa |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 1.3 - Stakeholder
label | a909862c-53af-5e97-a577-a7e558fc1387 |  | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
label | 8b30c912-5308-515f-9011-deff2e5af2d0 |  | note | Standard / Specification - Project Stakeholder Management Plan
label | 22e61624-58fb-5c44-96e6-7405784989c9 |  | note | Verifying Document - ITP Sign Off
label | 56b178e3-75aa-52a2-bcd2-286ca395bd16 |  | note | Frequency - Prior to Construction with continue updates throughout the works
label | cd042eb1-e4a2-5b7f-acb5-bee68734a58c |  | note | Verification Activity - M
label | 6760a1e3-a3d9-563b-b0a8-5e043a724492 |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 1.4 - Permits
label | bd7e3c64-3e2a-5920-be2f-4935d4539398 |  | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
label | 2fdbe04a-4a53-5122-ad61-f3593e431d12 |  | note | Standard / Specification - Section 2.2.10 Project Specification
label | 1d39b83d-12b7-5980-af5f-15e7f1351ef1 |  | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
label | 34edf06c-9560-55bb-ad35-1bd416718184 |  | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
label | fd608052-3027-5806-80c0-b9694cfcbeb7 |  | note | Verification Activity - H
label | 521e991c-018a-531f-b625-69ce492ee8b1 |  | note | Verification Activity - By: - PE
checkpoint-group |  |  | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint-status |  |  | checkpoint | 2.1 - Pipes/Fittings/precast Units
label | 6df1cf8d-1004-5e3d-a742-b98320906274 |  | note | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/fittings are correct and in good condition and compliant.
label | 031c0d23-6b74-5de3-9375-5b4fc963eee6 |  | note | Standard / Specification - Project Specification
label | 149854d4-efea-59df-8950-1b9b3855a0c5 |  | note | Verifying Document - Delivery Dockets
label | 3a9c473c-e0e8-5ebb-992c-60ade1ec1262 |  | note | Frequency - Each Delivery to Site
label | 45508343-caa2-5b23-9604-27047d34681d |  | note | Verification Activity - S
label | e73d70cb-5a38-5e06-b3c8-827da199cece |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 2.2 - Bedding/Side/Haunch/Overlay
label | 3a420734-f6f5-5210-bd48-c7cf30ddb976 |  | note | Acceptance / Conformance Criteria - Confirm material grading and density of pit sand or other approved material
label | 75f33260-14de-5971-9893-aa995af3205e |  | note | Standard / Specification - AS/NZS2566
label | 00009c7b-af45-55d2-a046-86613d201e6d |  | note | Verifying Document - IANZ Lab Test Reports
label | a99f9c72-9a71-5d7e-a194-447c96233017 |  | note | Frequency - 1 Test per 1000m3
label | 681c2fad-bfa9-5648-b36c-f6de1429e902 |  | note | Verification Activity - H
label | c8944537-7fca-59e6-99ce-a66dad5e2739 |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 2.3 - Backfill Material Compliance
label | 3825299a-25b8-5dca-9c50-d60dda320558 |  | note | Acceptance / Conformance Criteria - Confirm material grading and density of pit sand or other approved material Use selected native soils in berm
label | f19d87bf-d6e5-5fa9-a4f6-2af14e24867e |  | note | Standard / Specification - AS/NZS2566
label | b6a0cd45-5a4a-5990-b006-f25f752d2a22 |  | note | Verifying Document - IANZ Lab Test Reports
label | 8c338912-06e8-5281-97d2-89075e2694d6 |  | note | Frequency - 1 Test per 1000m3
label | 5330899a-c227-532d-836c-d2203b881d90 |  | note | Verification Activity - H
label | f9a7db0a-0db0-52bb-9e7d-8028f23c799e |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 2.4 - Undercut Backfill Material
label | 5d62f13b-d2e3-5bbe-8ebb-6190edba7f68 |  | note | Acceptance / Conformance Criteria - Engineer to Specify Material to meet specifications dependant on material selected
label | 67edce20-2cbe-58dd-9fbc-e4a3dc0042fe |  | note | Standard / Specification - Engineer to Specify
label | 9877596e-c4ed-50c6-a42c-cea5098163f0 |  | note | Verifying Document - IANZ Lab Test Reports
label | 325f4fc4-0dcf-51e4-b273-c3021feac7ad |  | note | Frequency - 1 Test per 1000m3
label | 43683a3d-d98b-5349-b20c-8bdb7293c3f8 |  | note | Verification Activity - HP
label | 49593a74-948e-5827-b1fb-ad1dbd727d6a |  | note | Verification Activity - By: - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Geotextile/Geogrid
label | f631587e-0e63-5d52-ae7b-6ffab6e6b11d |  | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used in the undercut. Geotextile or Geogrid that is used in the undercut is to be documented / marked up on drawing
label | 2fa75ace-6055-55c3-a40c-3d5ec1a96d1e |  | note | Standard / Specification - Project Specification
label | 32ac1128-ed5e-5ed9-9488-502f284d6511 |  | note | Verifying Document - Certification Photos of Delivery Dockets
label | 2d807760-f4c3-59a1-a843-389e3e17cb23 |  | note | Frequency - Material Used
label | d41ab3eb-8b17-5d1d-b5f2-8814b53290d0 |  | note | Verification Activity - C
label | b2953535-89b8-5b39-bdfe-ffa0646ea0d4 |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 2.6 - Warning Tape
label | da40fc40-9a2f-5faa-b5fb-0c2ca4185b52 |  | note | Acceptance / Conformance Criteria - Obtain Warning Tape from supplier
label | 1d59ac43-680f-55b0-86a5-141a8a35ca49 |  | note | Standard / Specification - Project Specification
label | 6d3e8edf-e66b-5f5f-ab2a-78a7e021b887 |  | note | Verifying Document - Delivery Dockets
label | 1316695c-b14e-56f8-977f-b319f1fc1d28 |  | note | Frequency - Each Delivery to Site
label | 692ce30d-cceb-518e-8220-c671d05aada5 |  | note | Verification Activity - S
label | afd1ceba-7788-5d54-9c23-413cd9057004 |  | note | Verification Activity - By: - PE
checkpoint-group |  |  | section | SECTION 3 – CONSTRUCTION ACTIVITY
checkpoint-status |  |  | checkpoint | 3.1 - Trench Excavation
label | 07477a63-9617-55fe-adb6-e93d735206cf |  | note | Acceptance / Conformance Criteria - Excavate trench to design height, placing spoil in approved area and benching as required Visual Inspection to any hard stones or rocks to be removed Any archaeological finds to be reported Inspections to any formation of soft spots
label | f06a3223-84cd-5d5a-9609-ec670899afad |  | note | Standard / Specification - Project Specification 4.3
label | 5a7fbfbe-688e-5eeb-b7ad-2fc27a97a8fd |  | note | Verifying Document - Scala test result
label | e34b1620-5292-5b32-81ad-7a8792e3f85c |  | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
label | b0059aa8-b108-581e-b180-24bb3e22c386 |  | note | Verification Activity - H
label | fd57b629-7db9-5b42-9417-98d7db9f76de |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.2 - Foundation Compliance
label | a9462c7a-cf46-5d7b-82df-bea3402e54c1 |  | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
label | 6f1a316b-9b79-5dcd-999c-40cdb0a8b150 |  | note | Standard / Specification - Project Specification 4.3
label | b1d4f6de-755d-5514-a8cb-7f021fc05aa7 |  | note | Verifying Document - Scala test result
label | c28a2bf1-3c70-5baa-b8ce-f3dd98ceaa12 |  | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
label | c6f79caa-eb63-5d79-b8ac-95e2d42eddc3 |  | note | Verification Activity - H
label | 4028434b-9d26-5617-9fdd-438d79ac0013 |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.3 - Undercut Backfill Compliance
label | 7289baf5-ae7e-54ed-846a-4a2383392ef2 |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average 98%) of MDD
label | 36e66f02-4614-53f2-a456-2561cb8cc4ab |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 95% of MDD AS/NZs 3725:2007
label | 44b1bd3c-6feb-5286-881e-7f19a7d026a6 |  | note | Verifying Document - IANZ Lab Test Report
label | 9f9226ea-523e-5a2b-bc38-72889a5f5bba |  | note | Frequency - Based on Undercut Section
label | 035f96b5-9059-5337-a1d4-fb0b83a58c03 |  | note | Verification Activity - H
label | a2f6e221-4bf9-5a06-ba86-7797617bc26e |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.4 - Bedding Compaction Testing
label | 1df4c996-99ab-53f7-942f-6ca7ac2aff57 |  | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average 98%) of MDD
label | c28e6dab-f53d-508b-be11-e11c00e05aa9 |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
label | f3d231c1-3db3-5089-8245-ea9d51c272f4 |  | note | Verifying Document - IANZ Lab Test Report
label | 73ee2aa1-dd52-5ff3-bf59-3d7fa4631d99 |  | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
label | 5db05c3a-ef53-5db7-bc65-5a25040b4841 |  | note | Verification Activity - H
label | e0ef5f15-9aea-5074-a24e-658ad51bd8b1 |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.5 - Haunch & Side Zone Compaction Testing
label | 5a8cedb3-7758-52f9-ae98-349a03eb9a84 |  | note | Acceptance / Conformance Criteria - Side zone shall extend from top of haunch zone to 0.5 times the pipe outside diameter 100mm if >75 , <150 150mm if >150 , <300 200mm if >300 , <450 NDM DT Minimum Compaction 92% of MDD
label | 22c67c7a-4f0f-5f27-b916-79dc9fcd70bf |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
label | e044652c-b18c-5d5c-97ac-f94df5e912de |  | note | Verifying Document - IANZ Lab Test Report
label | 9fc2191d-c30b-56cd-b959-798fdeb8ab74 |  | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
label | a7e6fd8b-8b1c-5028-b00d-f5ab364e28b8 |  | note | Verification Activity - H
label | 55e5af02-e543-5e18-8b81-0f6967bb0813 |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.6 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
label | 73c47ed0-cbf2-5993-934d-120bdd476cee |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 92% of MDD
label | 15511fb1-9695-53bd-88f4-1bb6eb4a68eb |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 92% of MDD AS/NZS 3725:2007
label | 71d57a91-6ae9-52a3-842f-a526707ddbee |  | note | Verifying Document - IANZ Lab Test Report
label | 8d60ce92-fb60-5a80-b904-b95a5faaee5b |  | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
label | ef0d9e80-b8db-56c6-8afb-6cc3e21ec69d |  | note | Verification Activity - H
label | c0779ffe-29b9-5921-b18c-a5822fe94a17 |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.7 - Collection of Waipa ITPs
label | db16c050-4db8-553b-b5ac-c707c111faf3 |  | note | Acceptance / Conformance Criteria - ITP 02 Manhole and Valves ITP 04 Butt Welding ITP 05 Commissioning
label | a542d803-defa-5fd1-b771-2d607713ed81 |  | note | Standard / Specification - PWRBSS Quality Management Plan
label | 407354aa-ee45-5aef-81cc-93cd41c63f9a |  | note | Verifying Document - Document Review
label | 26782718-d70a-5d80-bd2b-82c07cf499d1 |  | note | Frequency - Once
label | 0ae112fd-56f4-526f-9070-382d1a63f2a0 |  | note | Verification Activity - HP
label | 8d2e5d47-b8ba-5d26-a3a6-82ce5b197b84 |  | note | Verification Activity - By: - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.8 - Backfill Inspection
label | dc6de0af-115b-5843-b061-6be7817ecf46 |  | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
label | 675da3b2-fd26-56a3-a501-da6826f06731 |  | note | Standard / Specification - Project Specification 4.3
label | 6965b7d0-334b-59e2-aa93-25fa3229f737 |  | note | Verifying Document - Photographs
label | e95ccae1-d1a3-52a4-9d3b-e564218e2637 |  | note | Frequency - Continuous
label | f015779c-9373-5743-a646-802c363d4478 |  | note | Verification Activity - S
label | 8cf4bc20-61bc-5eeb-a074-a44f5fdd7d96 |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 3.9 - Install Warning Tape
label | 275cc7b9-aa03-59b1-a9ef-15d48a4251a0 |  | note | Acceptance / Conformance Criteria - For open trenching, detector tape shall be placed approximately 200mm below final ground level and metallic ‘detector’ tape coloured blue, stipulating ‘Danger – Water Main Below’ (or similar) shall be laid.
label | 89fe7a2a-2b50-544d-bdad-97e00f5130ea |  | note | Standard / Specification - RITS
label | f6fa2374-a03a-5ce2-bf54-c4c85325f636 |  | note | Verifying Document - Photographs
label | afddf2df-94e0-505b-8909-48f846096047 |  | note | Frequency - Continuous
label | 84edf32f-7f89-51cf-ae66-6b1336689710 |  | note | Verification Activity - S
label | f36fa6dc-2bba-5148-8f6f-6e84f2679186 |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 3.1 - Survey
label | a294f9b0-4c02-5c4d-a1a3-5fc5966b04b4 |  | note | Acceptance / Conformance Criteria - All Water Mains shall be laid in a straight line or following street layout. The deviation from approved design alignment permitted either in plan or elevation shall be: Open Cut – ± 50mm on straight and 100mm in curves All pipes, fitting and thrust blocks to be as built prior to backfilling
label | bd943e00-f1ef-5548-9855-abc4a6da9574 |  | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
label | e578e240-102e-52d9-8bf4-4b212aa765eb |  | note | Verifying Document - Survey Data
label | 7162641a-4e07-5fd2-b4a5-1f9598843f3a |  | note | Frequency - Continuous
label | 715dba86-0507-520f-9d7c-b7ff9bba058f |  | note | Verification Activity - C
label | 03bed1e0-d9a5-5761-9444-e30df7766f80 |  | note | Verification Activity - By: - SV
checkpoint-status |  |  | checkpoint | 3.11 - Backfill Compaction Testing
label | dcb0cf94-74d4-51d1-8687-dfbb3bd0606b |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC Average of 98%
label | 3655ad07-7eb9-5add-99a7-f46a315bd015 |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
label | d6ae28a0-eb28-58ef-82ea-58ef1e0541c9 |  | note | Verifying Document - IANZ Lab Test Report
label | 860a494c-b3af-53b1-be11-fdc81ccaed51 |  | note | Frequency - Every 20m along trench 1 test every 5m² at driveways and footpaths
label | 85d03948-9207-55e4-9ec0-aeae0b9cf4a2 |  | note | Verification Activity - H
label | d5659d13-9af2-564d-b799-0641cdf4eb19 |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.12 - Manhole Foundation Compliance
label | d2bb9c59-ced0-5fcb-b60d-aba2e6b81c43 |  | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
label | eca8b52f-be49-5686-a1ac-7e03b5cddfd5 |  | note | Standard / Specification - Section 4.3 PWRBSS Project Specification
label | cce2838a-eb0a-530a-8a34-51b66141f36c |  | note | Verifying Document - IANZ Lab Test Report
label | f0e0bf59-c689-530f-b43b-3271b1b807bd |  | note | Frequency - 1Test/MH
label | 370ed67e-4d14-5680-bfb7-0014a22de54a |  | note | Verification Activity - H
label | 5c327065-fbe3-5f72-88e3-56f05f100f09 |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.13 - Undercut Backfill Compliance
label | 69d66008-6fab-587a-9ca1-edb57a344028 |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average 98%) of MDD
label | 8989cce0-1ab5-5a3e-8bf4-8902b0256e3c |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 60 or 95% of MDD AS/NZs 3725:2007
label | a7b502ab-05b3-5930-8848-e1bd823626b4 |  | note | Verifying Document - IANZ Lab Test Report
label | 8f433644-ef93-594d-857d-0df99d6be813 |  | note | Frequency - Based on Undercut Section
label | 79b84a28-db63-5020-addd-eefa8c943bb8 |  | note | Verification Activity - H
label | 975e420a-7912-5a09-be21-4e80218f9f86 |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.14 - Bedding Compaction Testing
label | 38cf7141-ec8c-5604-942d-b6b72faaabbf |  | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average 98%) of MDD
label | a847bebf-1df1-581f-8304-5c4b45e6cdd7 |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
label | 1c453333-f6dd-539b-80cc-ae7863c624b9 |  | note | Verifying Document - IANZ Lab Test Report
label | 1badf2d5-f6bc-57c3-aa6a-c5a45440569a |  | note | Frequency - 1Test/MH
label | 627ea6e2-0f21-532f-8fe7-6770a74b9623 |  | note | Verification Activity - H
label | 0d85463d-dab3-51b7-bb97-9b404dff4af2 |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.15 - Backfill Inspection
label | d92fe8a3-ca3a-5430-bfc7-b1328efc2f77 |  | note | Acceptance / Conformance Criteria - Inspection of manhole prior to backfilling to ensure correct installation and that the joints are sealed. Check for any gaps.
label | 0fcf5aa2-04c1-5473-8ae9-cad3834c3bb4 |  | note | Standard / Specification - Project Specification 4.3
label | 71a08e1e-9f9e-5735-b9e7-974aca4bf205 |  | note | Verifying Document - Photographs
label | e1875c14-0f50-58c6-b6ef-352bf1783dad |  | note | Frequency - Continuous
label | 9dcc647f-fddb-5773-90ea-778339343ecf |  | note | Verification Activity - S
label | addfe930-6991-57da-95c7-300e647696b5 |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 3.16 - Backfill Compaction Testing
label | 0b304461-1592-59ec-8f1c-4adbbf43cc1b |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC Average of 98%
label | cb84dbae-3878-5efa-8b06-b15858234554 |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
label | 97ac4fea-d9c9-5c8c-baba-96f47f0b7fde |  | note | Verifying Document - IANZ Lab Test Report
label | 7fc73e23-243b-544c-a192-4cf2db61ca9a |  | note | Frequency - 4 Density Tests per layer at Quarter Points around structure
label | 01211731-cc47-5c7e-9d96-455d5e38e8d5 |  | note | Verification Activity - H
label | f79276d6-10e3-52d0-80a9-20e7c5b178e5 |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.17 - Reinstatement
label | 2d63696d-2d33-5c5c-ac3f-78a5a0fb3fbc |  | note | Acceptance / Conformance Criteria - Quality Check on New Works
label | a3350074-8599-5295-b334-b07bdf8c4d10 |  | note | Standard / Specification - Reinstate and Tie into existing surrounds
label | 0b512309-e2c5-51c7-9586-e8a752f5e706 |  | note | Verifying Document - Photographs
label | e23e2bb4-89dc-5278-9fad-10048a6d915c |  | note | Frequency - Continuous
label | f3a7a097-a0ac-58e8-ae1b-4c6b265514b9 |  | note | Verification Activity - S
label | 388eeb85-5232-5b2b-a1aa-fa731eb4176e |  | note | Verification Activity - By: - PE
checkpoint-group |  |  | section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint-status |  |  | checkpoint | 4.1 - Survey As-Builts
label | fbbf0793-2870-5073-bdad-313d6c053715 |  | note | Acceptance / Conformance Criteria - Quality Check on New Works based on the tolerances in RITS
label | 49d8634e-c761-5a02-8077-f2be6dbcbed0 |  | note | Standard / Specification - Project Specification
label | 8f244533-d06f-5885-b00d-17430dbaf917 |  | note | Verifying Document - Survey Data As Built Drawings Photographs Red Pen As-Builts including Undercuts
label | a6bf5a44-50bf-558b-b3b2-a54478fc7244 |  | note | Frequency - Post Works Completion
label | fb594479-9802-57fc-aeed-4b92904ad9ca |  | note | Verification Activity - H
label | 72121a75-77cb-536b-88c1-a40ae647a69d |  | note | Verification Activity - By: - SV
checklist-sectioned |  |  | checklist | ITP - Traffic Signals - Rev B | itp |  |  |  | Yes | ITP - Traffic Signals - Rev B | 9e88c576-c457-4ac3-9a25-9bedb80ea4fa
checkpoint-group |  |  | section | 1.1 - General
checkpoint-status |  |  | checkpoint | 1.1.1 - Drawings
label | 1a6e2bb1-747c-58ff-8f65-242511a5d3e1 |  | note | Acceptance / Conformance Criteria - Prior to starting works, ensure that the construction drawings are both IFC and the Current Version.
label | dabe18f4-c625-50fa-9b19-8058d312fa5d |  | note | Standard / Specification - Downer
label | 64e92cf0-7324-5c15-ba3b-c5ab5715c984 |  | note | Verifying Document - IFC Drawings
label | 779bfdcd-6116-55e5-9081-81eaab9b7e3d |  | note | Frequency - Prior to work planning and start
label | 3b80ea29-fe30-558a-a97b-6e1446f5d021 |  | note | Activity - M
label | a34f54c2-e4d0-546e-808e-6cb59268bd8f |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.1.2 - Construction Pack (1)
label | 636c29f1-6237-5088-9697-d65a2bec8b3a |  | note | Acceptance / Conformance Criteria - ITP to be submitted to the Engineer and approved prior to works beginning
label | 9c8fa9be-4db8-5c2c-bc7c-40f136388ac1 |  | note | Standard / Specification - Downer
label | a01f6c13-5d40-5e1b-a7f8-bc6467959a75 |  | note | Verifying Document - In-Eight Document Approval/Acknowledgement
label | bfafaa96-f4e3-5a3a-b9ed-edabfc598172 |  | note | Frequency - Submit 10 days prior to commencement of works
label | baaafe56-bd6f-5cf7-b8e0-fe43ecf34f78 |  | note | Activity - H
label | be0f65f1-d87b-50b6-8182-0d7800660487 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.1.2 - Construction Pack (2)
label | 14ea70de-6733-5891-b959-6f6552d388d8 |  | note | Acceptance / Conformance Criteria - Methodology and associated documents to be prepared, reviewed and approved internally prior to work commencement.
label | 23fe48dc-768b-5272-912b-af54827973d4 |  | note | Standard / Specification - Downer
label | 4d473c96-0e45-5bc5-aa81-92d9b81da588 |  | note | Verifying Document - Construction Pack Sign Off
label | e38724a5-9fd2-5ba5-a0e4-8d22d58af085 |  | note | Frequency - Prior to Construction & after any major incident
label | 4a1ca06a-ab84-51b7-880e-6e1d47eaba38 |  | note | Activity - M
label | eb3d56df-ebd9-5f80-97fb-e323803eded7 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.1.3 - Survey Set-out
label | aa347b44-1ebd-50a2-b200-a2c20d36e451 |  | note | Acceptance / Conformance Criteria - Ensure traffic signal pole, access chamber, and controller cabinet locations are set out per IFC drawings/data.
label | b35e099a-d971-59f2-93fb-4438e5f5af1d |  | note | Standard / Specification - Design Drawings
label | 98c0cd01-8203-58c3-bc5a-5a221d8bbfbd |  | note | Verifying Document - ITP Sign Off
label | 21bc99bd-299c-5c2a-b900-9e0be27c2c36 |  | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
label | 3795dc87-6b2d-599b-8a05-ddb0c8eeb8e8 |  | note | Activity - M
label | c0841e63-e883-53f0-938a-fa0892d30222 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.1.4 - Walk-over (1)
label | 1832c688-97be-59a8-b044-a7b25c9d7c1d |  | note | Acceptance / Conformance Criteria - HCC Traffic Engineer, BBO Designer and MSQA rep to walk over and confirm pole locations.
label | 1459bbe7-403d-505d-a96c-7a4b40f4aafd |  | note | – – – – – – – – – – – – – – –
label | 40a04483-7436-5d4f-9c5a-74b4eff50a48 |  | note | HCC 1st Contact:
label | c9340165-e38f-54e6-9d02-ccd653c8944e |  | note | ○ Brandon Harley - Senior Traffic Signal Specialist - HCC City Transport
label | ec49a40c-3897-5eab-8107-1315ed3d40fb |  | note | ○ DDI: (07) 838 6638
label | d5e496b6-d560-5a79-b4c0-c10700271009 |  | note | ○ Mob: 0278086506
label | a184a501-f314-5f66-8bf1-e25f76011dd9 |  | note | ○ Email: Brandon.Harley@HCC.govt.nz
label | 7e0e0362-ccf2-5f07-b6ec-985761eed9f0 |  | note | – – – – – – – – – – – – – – –
label | a4c700ec-3cde-5dd2-9fe7-18da7c6bdd07 |  | note | HCC Alt Contact:
label | 3d4e65f7-eb58-5645-984e-8bbef2b841f6 |  | note | ○ Holly Blackley - Senior Transport Network Operator HCC City Transport
label | 6ca8c43f-d9ca-5be4-9209-6412cb048b38 |  | note | ○ DDI: (07) 838 6817
label | c381824d-576d-5788-bc8f-6af1b4852166 |  | note | ○ Mob: 0278087593
label | 98794dfc-71bb-535a-9cda-4b44f3b51a6a |  | note | ○ Email: Holly.Blackley@hcc.govt.nz
label | 79887ac3-b09d-53cc-8bc5-a2e8b45a5a79 |  | note | – – – – – – – – – – – – – – –
label | b8ceb4fc-f372-554d-84da-ee0b9a35d1da |  | note | HCC 2nd Alt Contact:
label | 37aeffee-2895-52ae-ba62-0f3210deb86a |  | note | ○ John Kinghorn - HCC City Transport
label | 50e954b2-c4dd-5185-aa14-d28eca000faa |  | note | ○ Mobile:
label | 211de02f-f763-50b1-be68-c46327a91b24 |  | note | ○ Email: John.Kinghorn@hcc.govt.nz
label | 9202adf3-377a-5ec0-978e-3e8dfafe3fc8 |  | note | – – – – – – – – – – – – – – –
label | 2aee2570-25b4-54b0-82a5-117485d7d4ee |  | note | BBO MSQA Contact:
label | ae119fd4-f500-559d-80bf-88e7eca3fb59 |  | note | ○ Emil Karlsson - Intermediate Site Engineer
label | d8fc4015-c4bc-5175-8f55-f865cdd411db |  | note | ○ Mobile: 0273371065
label | f503bb0b-95c6-5891-a132-3a0ecbbaaa5f |  | note | ○ Email: ekarlsson@bbo.co.nz
label | 225e9737-66fa-5f08-9c9c-ff28a34dc46f |  | note | – – – – – – – – – – – – – – –
label | f6f3cf06-caef-5a28-955b-b8b213f5aa9e |  | note | BBO MSQA Alt Contact:
label | 4c2a6f4d-39aa-5a63-9552-af47787b9835 |  | note | ○ Ryan Fergusson - Senior Site Engineer
label | c01c80b4-8e40-5532-8b34-92cea38e8707 |  | note | ○ Mobile: 0274060378
label | c0e51264-12f6-5287-a834-5a312abab6df |  | note | ○ Email: rfergusson@bbo.co.nz
label | 5a99e27b-7dec-56f0-a68a-688226ceebc8 |  | note | – – – – – – – – – – – – – – –
label | d8b2b8eb-bea8-558c-ab28-0b54de4d650b |  | note | BBO MSQA 2nd Alt Contact:
label | 7f10ff8c-1154-589c-a17d-2fa750f07249 |  | note | ○ Zion Nordstrom -
label | 96d15509-fba5-54be-843f-81d4598ca211 |  | note | ○ Email: znordstrom@bbo.co.nz
label | c340016b-6fa6-57de-9fbd-8fb904be52fb |  | note | – – – – – – – – – – – – – – –
label | 6a5c3c8b-6248-5406-96a5-6b45ad6b9d6b |  | note | BBO Designer:
label | 7769d0a6-e192-5978-a5ec-f987bf7fbca3 |  | note | ○ TBC - MSQA to contact/bring with.
label | deefc935-cca1-511f-908f-b0e6db3f88dc |  | note | – – – – – – – – – – – – – – –
label | 5fad894c-4d32-57bb-b45e-0de7225b5a27 |  | note | Standard / Specification - Design Drawings
label | 0c344e80-a9b2-5aa2-bb60-0950fb6ef838 |  | note | Verifying Document - Written correspondence / Photographs
label | 7d75a211-1758-5d5d-87c0-190805939914 |  | note | Frequency - Prior to construction
label | fc8b277f-31b6-5c74-bedd-1067a7d813f6 |  | note | Activity - H
label | 9468f4eb-48e2-568a-9ff4-6ffd1a412acf |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.1.4 - Walk-over (2)
label | afab593b-8d3b-5cbd-b9e3-d59a6d2ae234 |  | note | Acceptance / Conformance Criteria - BBO/HCC written confirmation of any changes made to pole positions.
label | d1e9eae5-d663-5988-89f9-c3e195a9c481 |  | note | Standard / Specification - BBO Requirement
label | 0460501b-3fd7-5351-88bc-3760b4a9b774 |  | note | Verifying Document - Written Correspondence (InEight preferred)
label | 3defeba7-8e6e-5fa2-9e6a-d3b650b670b0 |  | note | Frequency - Post walkover, and prior to installation
label | 57f82451-0f3d-5e75-a8e3-be348d120262 |  | note | Activity - H
label | bddd50c6-5a0e-502f-9ba0-c058b35fb5d7 |  | note | By - BBO / HCC / WTOC
checkpoint-status |  |  | checkpoint | 1.1.5 - Environmental Protection
label | 49735070-ff18-5c44-800f-3f7456b0aec4 |  | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans. Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events.
label | 39f5f564-db16-5ed3-9872-0619cc6d1c3b |  | note | Standard / Specification - Project ESCP Plans
label | 2004eeaf-44c8-5df7-af7d-0bf7d2737198 |  | note | Verifying Document - ITP Sign Off
label | 777f47d4-a5af-5da6-87cd-f2bdfa17081e |  | note | Frequency - Prior to Construction. Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events.
label | 519aaf4c-c6cb-5432-81b2-2bdf71e40823 |  | note | Activity - M
label | d914bb68-8d93-50d3-a710-ab61be805d55 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.1.6 - Stakeholder
label | 87ed676c-547e-5965-8e5d-e0de0ebe6371 |  | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works. Agree plans for maintaining access to properties during construction with landowners.
label | c384e116-be96-5400-afad-c61549035099 |  | note | Standard / Specification - Project Stakeholder Management Plan
label | ef5e934f-db4c-55a7-99d4-a4bffadaaac8 |  | note | Verifying Document - ITP Sign Off
label | 042937cd-ae6c-5ced-a50f-c8cd2a063d94 |  | note | Frequency - Prior to Construction with continue updates throughout the works
label | 262aad29-09c9-5202-b8b5-934c1eab70a2 |  | note | Activity - M
label | 9e5e12d0-17f9-56ae-bd78-b09fd79af3ab |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.1.7 - Permits
label | f5c29669-c2c6-5857-94b6-89390bc8dd30 |  | note | Acceptance / Conformance Criteria - Ground Disturbance Permit must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip.
label | 33c003bb-a3cb-5392-a808-9f0554c2d3b3 |  | note | ○ Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. Doner Permit encompasses external provider permit requirements.
label | 90b0cfa1-53b8-5281-b6b6-08dcfb0518f6 |  | note | ○ All known services must be clearly marked on site and briefed to the workforce .
label | cddf3d35-8802-5edb-af89-0ca4b040cc64 |  | note | Standard / Specification - Section 2.2.10 Project Specification
label | f0a7b0cb-f3f4-5e07-8dae-31f300dddf47 |  | note | Verifying Document - Ground Disturbance Permit, DN-ZH-FM043.1
label | f5c8fe38-a90d-5e75-9872-3d0272b52b21 |  | note | Frequency - Prior to Construction. Reviewed and Reissued weekly or when site conditions change.
label | 1ccde223-d279-51ff-8add-1056d45bee31 |  | note | Activity - H
label | a8f2d274-5a2c-52b3-b20a-3b022f77d020 |  | note | By - PE
checkpoint-group |  |  | section | 2.1 - General
checkpoint-status |  |  | checkpoint | 2.1.1 - Pole Producer Statements
label | 25d80bdb-c272-52ca-b144-dd03717e64bf |  | note | Acceptance / Conformance Criteria - PS1 certificate required for all pole types.
label | 82ce7dd2-8928-54e3-97e8-a25f3b3311ed |  | note | Standard / Specification - Project Specification Apendix E 3.16
label | 13231e0a-66e7-573d-93d5-ca5ba43b8e28 |  | note | Verifying Document - PS1 Certificates
label | c0e4cfed-37da-52d8-9185-8c5ffa72ea08 |  | note | Frequency - Prior to pole acquisition
label | a569f554-5998-54f1-b80c-46d8eaba402a |  | note | Activity - H
label | 53f99a72-2921-5bc0-9e32-94f6986403a5 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 2.1.2 - Controller Cabinet
label | 465bdb9f-250a-50f5-9616-e1c7ae31966c |  | note | Acceptance / Conformance Criteria - Unless otherwise specified, VC6 ELV controller (compatible with latest SCATS software) fitted with a generator socket matching existing HCC controller cabinet colours.
label | 09971c60-27e0-5727-a093-33aa48b13689 |  | note | ○ Must be fitted with a sticker indicating the Site ID Number.
label | 9671bed3-752d-5920-a8fe-60cbfe13c19b |  | note | Standard / Specification - Project Specification Apendix E 2.3.5/2.3.6/3.6
label | 0ea75044-d262-5a62-bdce-92a36a5e88fd |  | note | Verifying Document - Nil - Visual Check
label | 64d3e65d-21d8-53fa-b444-64a1d46d48cc |  | note | Frequency - Each controller/intersection
label | 71e9b313-2aa9-5236-9a84-acee2a391a8c |  | note | Activity - M
label | 3d339772-de9e-58c9-8d31-be29d9d4eaa2 |  | note | By - PE/TSL
checkpoint-status |  |  | checkpoint | 2.1.3 - Site ID Number
label | b295847f-acd3-5c08-bc76-5ec8a3ba683a |  | note | Acceptance / Conformance Criteria - HCC to provide Site ID number.
label | 1ce2fa45-c26e-580c-88ae-34a6f93aa804 |  | note | Standard / Specification - Project Specification Apendix E 3.6
label | b5d196f8-9c49-5da5-ac9c-1521ed46d403 |  | note | Verifying Document - Written correspondence
label | b618943c-3c13-5c35-afaf-89296a0c1a10 |  | note | Frequency - Prior to commissioning
label | 4b1b1a3c-3802-5a1d-9069-8817b2cb99ed |  | note | Activity - M
label | c6b09014-2f2d-5835-9036-0e44fa193c6f |  | note | By - PE / HCC/WTOC
checkpoint-status |  |  | checkpoint | 2.1.4 - CCTV camera
label | 2365db74-a0ca-5cec-9c44-6b23eb5b0b56 |  | note | Acceptance / Conformance Criteria - HCC must approve of traffic monitoring camera which should meet requirements. Hardware is required to have a minimum 12 months warranty period.
label | af1ef695-496e-586e-9f67-71c557bc4e20 |  | note | ○ HCC preference is an Axis Q6075-E along with an Axis Q6010-E, using the Axis T91L61 pole mounts.
label | 5d6bb55b-7444-576d-a37a-7abbad9ec41b |  | note | Standard / Specification - Project Specification Appendix E 3.19.1
label | cc32f8f7-8871-5676-9e2a-b211a5d47f2d |  | note | Verifying Document - Written correspondence
label | 7f7b4a6f-1ef4-5723-b396-1b73afba1d8e |  | note | Frequency - Prior to material acquisition
label | 43906920-16a2-50bf-b428-6185c4996fb3 |  | note | Activity - M
label | fd24c82d-58db-5bc8-b111-f89604ce7d8f |  | note | By - PE/TSL
checkpoint-status |  |  | checkpoint | 2.1.5 - Communications Connection
label | 6af1668f-a0c8-5e28-89d1-b6e8dc520cc6 |  | note | Acceptance / Conformance Criteria - Engage HCC to engage Lightwire. Project team to coordinate with for on-site installation.
label | 6962bfe9-bd91-5bd3-a83e-de4b2cda376e |  | note | Standard / Specification - Project Specification Apendix E 3.18
label | 83cc83b2-c3b1-5b32-bdb3-23d0d1f8469f |  | note | Verifying Document - Written correspondence
label | 002dfaa6-6265-521f-a3cf-95d59d1c9ee1 |  | note | Frequency - 3 months prior to connection
label | 29bd6f9a-b4a5-525d-8e19-8e0b19a7bc0a |  | note | Activity - M
label | c4c6481a-ddd6-5ed9-bc5a-d7c341e6311b |  | note | By - PE
checkpoint-status |  |  | checkpoint | 2.1.6 - Electrical Connection
label | b935a22f-96b2-51c2-bc30-eda1979d4079 |  | note | Acceptance / Conformance Criteria - Apply for new commercial electrical connection via the WEL Networks website/login for each new signalised intersection (NC1 Form).
label | e55b3cad-dda8-5a4e-9e1d-2b9c9ed97c87 |  | note | ○ Traffic signals subontractor to confirm electrical requirements.
label | 4ca96c70-00f6-547d-88b8-00cc564c57f2 |  | note | Standard / Specification - Project Specification Appendix E 3.3
label | 9e9dcca0-f6d2-5267-ba00-c5c60d7e9b4d |  | note | Verifying Document - Approval document/NC1 Form with ICP number
label | 342b291e-ef9e-5f9d-81f5-58fd5ce40a13 |  | note | Frequency - 3 months prior to connection
label | 68e139cc-f2a3-5107-8efa-9d4456f050a5 |  | note | Activity - M
label | 8ea2b6e9-b8f0-5008-90c7-5e5eb61232a9 |  | note | By - PE
checkpoint-group |  |  | section | 3.1 - Software
checkpoint-status |  |  | checkpoint | 3.1.1 - Software/personality files and CIS
label | 60cde22b-6c23-5a5c-813a-4b477a912301 |  | note | Acceptance / Conformance Criteria - HCC to provide to contractor (Downer or TSL).
label | 6342b3e5-13e7-5c05-95dd-b1a60b94d0fc |  | note | Contact (s):
label | f082ddc5-a221-5e9c-a9aa-8cc1f2938baf |  | note | – – – – – – – – – – – – – – –
label | 8543e704-77ce-57c4-b4e9-e73f7b102bd0 |  | note | John Kinghorn - HCC City Transport
label | 55f06c78-0723-519e-ae13-4d216022b32f |  | note | ○ Mobile:
label | 47534d1b-9447-50d7-8e89-5346278e4a43 |  | note | ○ Email: John.Kinghorn@hcc.govt.nz
label | 21c0a32c-c675-5dac-848b-83501115b66b |  | note | – – – – – – – – – – – – – – –
label | c9e65987-d52a-518b-ba5b-9a68a4715dce |  | note | Brandon Harley - Senior Traffic Signal Specialist - HCC City Transport
label | bba9017a-b2f6-5ed5-bc10-a9f4ea62acb0 |  | note | ○ DDI: (07) 838 6638
label | 8182b054-1fb8-592a-9258-97a04bfe71a6 |  | note | ○ Mob: 0278086506
label | e54ee533-8490-585a-988f-535c6f0b2342 |  | note | ○ Email: Brandon.Harley@HCC.govt.nz
label | e91ea35b-d1b0-5feb-a2b0-9f09b102491c |  | note | – – – – – – – – – – – – – – –
label | 5bb1260a-e7c2-5c75-86e3-c58e7d01b120 |  | note | Standard / Specification - Project Specification Appendix E 3.15.3
label | 51f28f7e-1ceb-5665-abf7-6de2d4db27e6 |  | note | Verifying Document - In-Eight Documents/Mail
label | ed2cfde4-2677-596a-8c0a-e3ae7e7e0823 |  | note | Frequency - Requested at least 6 weeks prior to bench testing date.
label | 154b9348-11db-54de-a8bf-385fd0859f2a |  | note | Activity - H
label | dda461fc-ee43-5414-baca-e7f4550988f2 |  | note | By - HCC / WTOC
checkpoint-status |  |  | checkpoint | 3.1.2 - Bench Test
label | d8b7e7a4-ac89-54c5-9c42-15994d362acb |  | note | Acceptance / Conformance Criteria - Traffic signals contractor to bench test files.
label | 1d00a791-144c-566e-b2e3-45b0c6259585 |  | note | Standard / Specification - NZTA P43 3.15.4
label | 0578a9b8-7778-52b1-a75c-6568a171f1aa |  | note | Verifying Document - PDF Document
label | 23395378-ae37-5755-92a6-48166eb4a467 |  | note | Frequency - Once per intersection, at least 1 week prior to comissioning
label | 55eb0296-c074-55db-a092-4a8802037d05 |  | note | Activity - H
label | 51ee8e6b-dd34-562f-a3ff-3f23212d7b8c |  | note | By - PE / TSL
checkpoint-group |  |  | section | 3.2 - Civil (Pole / Cabinet / Access Chamber) Installations
checkpoint-status |  |  | checkpoint | 3.2.1 - Soil Bearing Strength
label | 047416b0-54a6-58a8-9b35-c7d290bbd7d1 |  | note | Acceptance / Conformance Criteria - Report results. Check this meets poles deisgn (i.e. >= 50kPa).
label | 88dded6f-381f-5c97-8616-a058211d5a83 |  | note | Standard / Specification - Drawings/PS1/NZTA P43 2.5.1.3
label | 43655bbd-8b87-5a26-b7dc-2809b804c86d |  | note | Verifying Document - Shear Vane
label | 1c28fb49-10a1-5f68-bdf3-27c184d11805 |  | note | Frequency - One pole per intersection corner (i.e. north-west, north-east etc)
label | fb54a97f-5a15-54a5-97ea-9768fb69c336 |  | note | Activity - M
label | 5cc5f5c6-401c-539b-a50e-e67f87b86892 |  | note | By - PE / TSL
checkpoint-status |  |  | checkpoint | 3.2.2 - Pole Base Photograph
label | 58f3023b-21c6-531f-a832-9c06785c5ec2 |  | note | Acceptance / Conformance Criteria - Photographic evidence of each pole base to be submitted as part of PS3
label | 6367cabf-8ed3-5d8f-b2c2-4b7f64356e6c |  | note | Standard / Specification - Project Specification Appendix E 3.16
label | c0698672-7bab-5e49-a950-7961ed3471f8 |  | note | Verifying Document - Photographs
label | 8b3bae35-b336-5692-bdb9-5850f40115c9 |  | note | Frequency - Each pole base prior to foundation pour.
label | 49a3e8ef-a08b-54dd-9f1e-ed513875c8d3 |  | note | Activity - M
label | 9454f899-82fb-56f7-ac1a-7a47cbb5a7da |  | note | By - TSL
checkpoint-status |  |  | checkpoint | 3.2.5 - Identification Numbers (1)
label | 6d0f5826-40b3-56e1-a5b2-11f39ff7d827 |  | note | Acceptance / Conformance Criteria - Ensure poles are fitted with/displaying the correct number and match the CIS sheets (pole numbers match program and diagram numbers).
label | a29d017d-61d7-513e-b5a8-e7f2bb656a65 |  | note | Verifying Document - Nil - Visual Check
label | 58b5e79c-bc8c-58fa-818c-64b1d33a2023 |  | note | Frequency - Each pole
label | 9c451946-5a72-56e3-b7b2-abb1e919889b |  | note | Activity - M
label | baa14c47-4889-5191-906b-0b218feda3ce |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.2.5 - Identification Numbers (2)
label | 0cc4b449-7ef9-52c5-8652-d03c7f6777f5 |  | note | Acceptance / Conformance Criteria - Controller cabinet fitted with Site ID Number sticker.
label | 4fcf2ca3-1367-5071-9ff9-868a8ee714e7 |  | note | Standard / Specification - Project Specification Apendix E 3.6
label | 6756bf93-ef86-5078-9122-e874a74bfcbf |  | note | Verifying Document - Nil - Visual Check
label | 6ce36705-9e67-5d65-bff5-361528dfbedf |  | note | Frequency - Each controller cabinet/intersection
label | 42a6fd31-6a20-5950-b91b-5ab42301b06d |  | note | Activity - M
label | 0fa6aa6c-68bd-5bc4-8e31-9c16f0450e34 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.2.6 - Mow Strip / Concrete Surrounds (1)
label | 232d240e-5671-5ed6-a2b0-302ca86e85b7 |  | note | Acceptance / Conformance Criteria - Access chambers installed in the berm surrounded by 300mm wide concrete apron to 100mm deep. 25MPa 28-day compressive strength concrete.
label | f944099f-582d-5e36-a97c-763d00be0b1d |  | note | Standard / Specification - NZTA P43 4.4.2
label | cc767167-a126-59ef-b153-980e30bee1c1 |  | note | Verifying Document - Nil - Visual Check
label | e0ea8692-d4ca-5644-b352-c2056964a936 |  | note | Frequency - Each access chamber in the berm
label | 1814b540-e146-59bd-b887-e37972d9220a |  | note | Activity - M
label | 949cdb71-8ac2-58cd-9788-1d20b0116dbe |  | note | By - PE / TSL
checkpoint-status |  |  | checkpoint | 3.2.6 - Mow Strip / Concrete Surrounds (2)
label | ebee9d24-a526-5c3f-927a-056b812cf2e6 |  | note | Acceptance / Conformance Criteria - KSJB to have 150mm wide concrete surround to a depth of 150mm.
label | 3758fb48-cf89-5c34-96ae-df1f3fa6d5a0 |  | note | Standard / Specification - NZTA P43 4.7
label | a85b7a70-77ad-5ece-9013-fb27e24b372e |  | note | Verifying Document - Nil - Visual Check
label | 24b8a540-07fb-5888-97d5-131ae361f2cd |  | note | Frequency - Each KSJB in the berm
label | 8938d508-2bac-5413-b699-6114a5d5f346 |  | note | Activity - M
label | 77277e01-16ae-5e18-93f3-b1bd7beb1a76 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.2.6 - Mow Strip / Concrete Surrounds (3)
label | da701216-7ac8-5d5a-a478-2732b2470707 |  | note | Acceptance / Conformance Criteria - Controller cabinet to be surrounded by 300mm wide concrete apron around the base of the controller, widened to 900mm on the side adjacent to the door. 100mm thick, with slight fall away from conroller.
label | 1d860cce-81b7-5a65-bdb7-788a30d57bbd |  | note | Standard / Specification - NZTA P43 3.6
label | 2bf13bfa-98de-5453-b7bc-c5da6df3e0f9 |  | note | Verifying Document - Nil - Visual Check
label | efd3fe0a-0201-5301-90b3-d5a55b3e3ef3 |  | note | Frequency - Each controller cabinet
label | c68904bc-b956-5d41-a345-5a0d48dd3d20 |  | note | Activity - M
label | e4cb13f9-0391-5a88-a30e-e10f370a7e85 |  | note | By - PE
checkpoint-group |  |  | section | 3.3 - Cabling and Electrical Testing
checkpoint-status |  |  | checkpoint | 3.3.1 - Loop Cutting (1)
label | 1fc24752-ab2e-53ee-9538-d5795532dda4 |  | note | Acceptance / Conformance Criteria - Rubberised bitument adhesive sealant applied to all saw cuts in the roadway
label | 62215710-07d8-5e5b-8482-1f579dccb943 |  | note | Standard / Specification - Project Specification Appendix E 3.11
label | 485cffd0-63ee-5286-bab1-2512fcb71f05 |  | note | Verifying Document - Nil - Visual Check
label | def8ee92-d946-512b-ae01-81ca8c78166c |  | note | Frequency - All saw cuts
label | e2cbac1d-d9c7-5cea-9939-aa8e65951079 |  | note | Activity - M
label | a1cf6de2-ec56-58da-bd05-07d8baf20a0b |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.3.1 - Loop Cutting (2)
label | f04a7442-47ee-54fe-a232-1e16949844ef |  | note | Acceptance / Conformance Criteria - Saw cuts made through kerb and channel to be sealed with epoxy resin motar.
label | 4c9bb10d-82ee-5943-97e7-1a27787104aa |  | note | Standard / Specification - Project Specification Appendix E 4.7
label | e45a48bc-06cb-5416-b35b-0ce64ef751c7 |  | note | Verifying Document - Nil - Visual Check
label | fe0d18ea-a423-5dda-b0dc-5e7174766fcf |  | note | Frequency - All saw cuts
label | ca37ddbb-c429-51e0-a71e-f639024d5abd |  | note | Activity - M
label | 6b2e05d3-d61c-592e-957e-8753220698c3 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.3.2 - Electrical Certification (COC)/ Record of Inspection (ROI)
label | 2211f947-11d8-56a7-8d00-7196abb09c7e |  | note | Acceptance / Conformance Criteria - Completed and signed certificate of electrical compliance.
label | 1a2ac56d-141d-5682-8b67-47c1836ae0a9 |  | note | Standard / Specification - NZTA P43 3.16
label | f02677b3-dc72-51f8-8e9d-edccf4ce0a99 |  | note | Verifying Document - Certificate
label | 8df7d6f7-a6d4-55b8-b1f9-b1e80d5f1341 |  | note | Frequency - 1 per intersection prior to commissioning.
label | 6a334c9b-5b91-5ab5-88be-383a65b1f7e7 |  | note | Activity - H
label | 933cf4a3-4ec6-5219-909b-7bb73394bbf1 |  | note | By - TSL
checkpoint-group |  |  | section | 3.4 - Site Acceptance and Commissioning
checkpoint-status |  |  | checkpoint | 3.4.1 - SCATS Connection (1)
label | 0ee420ac-31e8-513c-9903-714658d779d0 |  | note | Acceptance / Conformance Criteria - Signals contractor to notify City Transportation Unit (CTU) Operations Room at least 1 week before SCATS commnications will be available from the controller.
label | c3b871a2-40e3-592b-9e7f-b38d5de736f3 |  | note | Standard / Specification - Project Specification Appendix E 3.15.4
label | 7d10387d-44a0-56dc-aeb4-80fd2a25ba67 |  | note | Verifying Document - Written correspondence
label | 64d19790-d57f-53f5-9a56-522b259836cf |  | note | Frequency - 1 week prior to SCATS communication being available from controller
label | fb357ba3-c899-5d5a-a45c-807791bea248 |  | note | Activity - M
label | ffc8c6e4-d183-5765-846c-44546ff22dea |  | note | By - PE / TSL
checkpoint-status |  |  | checkpoint | 3.4.1 - SCATS Connection (2)
label | 8acbed91-702d-50ac-a156-2c47d4139635 |  | note | Acceptance / Conformance Criteria - SCATS comminication achieved for a minimum of 48hours prior to comissioning.
label | 6133450c-a625-57cb-b2fa-78d892cdf7c8 |  | note | Standard / Specification - Project Specification Appendix E 3.15.4
label | 3574a399-41e8-5e79-9089-bf99a7f1071a |  | note | Verifying Document - Written correspondence
label | 9a46cd34-b991-5fea-9767-ee17f74cccdb |  | note | Frequency - Min 48hrs prior to comissioning
label | 3ab532b2-fa6f-5bae-a9d9-1a49665e25d4 |  | note | Activity - M
label | c34ea619-3344-5de7-ac3d-3639d893b701 |  | note | By - PE / HCC / TSL
checkpoint-status |  |  | checkpoint | 3.4.2 - Documents
label | e890420e-9e7e-5a8a-8f1a-6b361132f646 |  | note | Acceptance / Conformance Criteria - Cable termination chart, CIS and logbook placed in document pocket inside controller cabinet.
label | 7e6dbb80-8205-53bc-a0e9-51264719cfd1 |  | note | Standard / Specification - NZTA P43 3.16
label | fe20d126-549e-509b-9aae-61d194fa264e |  | note | Verifying Document - Nil - Visual Check
label | 1ed93ae0-5283-50af-aeee-69e5daa7135b |  | note | Frequency - Within 2 weeks of commissioning
label | 643e9599-57b6-5c37-a93c-35e760802400 |  | note | Activity - H
label | fb4a655e-8766-5e2d-8e72-e8290d2c148c |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.4.3 - Approval to Commission
label | 6e353e84-4c25-54a8-b595-a71e3835bc71 |  | note | Acceptance / Conformance Criteria - RCA traffic signals representative (City Transportation) approval to switch on.
label | fea3e389-1286-596a-aeb0-09b7e76d04ce |  | note | Standard / Specification - Project Specification Appendix E 3.15.4
label | 664aa9e4-895f-5968-9215-bb4778fb8c01 |  | note | Verifying Document - Written correspondence
label | 7221bfba-f0a6-5bc9-920a-f57024bbfc14 |  | note | Frequency - Once per intersection
label | dd4b687c-67d1-542e-acd4-6c67c15c9af1 |  | note | Activity - H
label | f1efa812-174b-5d56-9a41-4d7e1e37b9f2 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.4.4 - Site Acceptance Chart
label | ebcaad82-2973-536c-a931-0939134b9bff |  | note | Acceptance / Conformance Criteria - Site Acceptance Test Chart to be filled out and signed.
label | 9c10c38f-b4ff-50ba-bd35-ee9915290da9 |  | note | Standard / Specification - Project Specification E 3.15.4
label | 7ed6e949-2e70-5e96-8934-c76ca154c47e |  | note | Verifying Document - SAT Form
label | 184617c7-5954-5eef-8c83-849cb6d97720 |  | note | Frequency - Once per intersection
label | 755906db-2d73-546a-996a-c4440f6a7f64 |  | note | Activity - H
label | 180b763b-fc04-5805-8883-26c49aae1e29 |  | note | By - TSL
checkpoint-group |  |  | section | 4.1 - General
checkpoint-status |  |  | checkpoint | 4.1.1 - Producer Statements (1)
label | 3780b149-2d4f-5eab-b002-9445521762f2 |  | note | Acceptance / Conformance Criteria - PS1 Design Producer Statement from Chartered Professional Engineer
label | 73efe4a7-377c-5b90-9235-45ba20eb933b |  | note | Standard / Specification - Project Specification Appendix E 3.16
label | 4005ac66-5fa0-5ea4-b869-06f1c2fe8d6a |  | note | Verifying Document - Producer Statement 1
label | 7af5f26d-afa3-50d0-a821-821a69b5b35d |  | note | Frequency - Each Pole Type
label | 3134b51f-a8b7-5027-8ee3-5fa2ea75674d |  | note | Activity - H
checkpoint-status |  |  | checkpoint | 4.1.1 - Producer Statements (2)
label | fdf9e640-057b-5829-9b84-9a9fc1671471 |  | note | Acceptance / Conformance Criteria - PS3 Certificate to be accompanied by photographic evidence of each pole (see requirement above).
label | c5249b0d-255e-5dbc-a792-a2534f88289c |  | note | Standard / Specification - Project Specification Appendix E 3.16
label | d88e0f00-a531-5a6b-ad27-9cf58e6c6907 |  | note | Verifying Document - Producer Statement 3
label | 9378fbf1-178f-5984-9917-b44e38bb5169 |  | note | Frequency - Each Pole Post-Installation
label | 1ca31bc1-1a63-556f-be68-9dc95f73e4ba |  | note | Activity - H
checkpoint-status |  |  | checkpoint | 4.1.2 - Site Handover/Acceptance
label | d6f7e099-0f46-5f78-85fd-528252858142 |  | note | Acceptance / Conformance Criteria - Approval from Hamilton City Council and the signals maintenance contractor.
label | d10ecd76-9659-513d-963b-14e34984fa2b |  | note | Standard / Specification - Project Specification Appendix E 2.2.2
label | f0eea7f1-e753-5214-9732-c854bb553359 |  | note | Verifying Document - Written Correspondence
label | 954403f4-97dc-5dd2-bd6a-92468c6aacda |  | note | Frequency - Post Signal Works Completion
label | 734dee76-682b-5d17-8315-a242006e3ca4 |  | note | Activity - H
checkpoint-status |  |  | checkpoint | 4.1.3 - Survey As-Builts
label | 9ff17772-543e-560c-856e-e2cc3ba29db2 |  | note | Acceptance / Conformance Criteria - Asbuilts reviewed and submitted showing final location of all poles, access chambers, KSJB, loops and cabinets.
label | a480559d-f93a-54ae-b37e-c7d89fe072f3 |  | note | Standard / Specification - Project Specification
label | c5a4d5a0-3ebc-5720-bb70-d7c1f5b452e3 |  | note | Verifying Document - Survey Data, As Built Drawings, Photographs, Red Pen As-Builts including Undercuts
label | 90da3462-b053-52b8-a34c-6c263f765ce4 |  | note | Frequency - Post-installation
label | c5acc9be-4937-55f9-bc35-01e685937157 |  | note | Activity - H
checklist-sectioned |  |  | checklist | ITP - Pavement & Surfacing - Kerb - Rev C |  |  |  |  | Yes | ITP - Pavement & Surfacing - Kerb - Rev C | b9ad1a21-d922-4727-a5be-0c8eb017dc8f
checkpoint-group |  |  | section | SECTION 1– PRELIMINARY - KERBING
checkpoint-status |  |  | checkpoint | 1.01 - Survey Set out
label | 7d955466-29de-5316-9cfa-6c42ea873290 |  | note | Acceptance / Conformance Criteria - As per design, the surveyor to install lift pegs
label | 97b6a2ab-3b99-59f3-9237-51a91370b802 |  | note | Standard / Specification - PS - 2.2.12
label | 26c38dfb-9763-53d5-b10c-409bef813166 |  | note | Verifying Document - As per design
label | 4d3edfad-dd12-5daf-a5a1-d1bc12648f78 |  | note | Frequency - As required for Kerb construction
label | 3826f264-8d56-5387-b812-a1268fcd05e7 |  | note | Activity - A
label | 16ed9906-4cce-57a0-82c8-faa1220be6e5 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 1.02 - Kerb construction Set out
label | 7348ea96-65f5-52e4-927c-1588f047e9f4 |  | note | Acceptance / Conformance Criteria - Ensure that steel pins and string line are in accordance with design levels and entranceways and kerb transitions have been marked. Tolerance +/- 5mm (basecourse level tolerance at channel edge)
label | 9adb5bc4-eace-5244-a0fe-0a5e2bc7736a |  | note | Standard / Specification - RITS - Page 201
label | e2521931-9bbb-5066-8e60-a7482a2fc932 |  | note | Verifying Document - Visual inspection and measurement
label | a516095d-e0e6-5907-8bd3-1ba4d085c40c |  | note | Frequency - Prior to slip forming
label | dc8af7b1-bae9-5b97-903e-dc56e1da1340 |  | note | Activity - I
label | b1aa47bb-a769-516e-8eaf-3faecb7c4708 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 1.03 - Approved kerb and Channel profiles
label | 8c78ac23-1bb6-51fc-afb5-2f1a9c74b6b5 |  | note | Acceptance / Conformance Criteria - As per drawing no. 146000-002A-1901
label | 18fcfc32-240f-5474-adc9-80409f710992 |  | note | Standard / Specification - As per drawing
label | 464ca852-6c7f-522f-8227-540c92e95b91 |  | note | Verifying Document - As per drawing
label | 0949db91-0086-5b5d-ab2d-a8f6802232df |  | note | Frequency - Prior to construction
label | 3515316a-d3d8-5a40-882d-b135bce1d1ee |  | note | Activity - I
label | b69c62b9-f656-5e4a-a6c7-a27855f15ba1 |  | note | By - SE
checkpoint-group |  |  | section | SECTION 2– MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - KERBING
checkpoint-status |  |  | checkpoint | 2.01 - Approve mix design from Certified batch Plant
label | e9ef93c1-b0c1-5fd7-9d24-64764cef673b |  | note | Acceptance / Conformance Criteria - Material meets project requirements - 20Mpa Kerbing Mix
label | 5a0ef905-ea0d-5046-bcce-41ec7bcddaff |  | note | Standard / Specification - Refer to RITS - 3.4.5.2 / 3.4.5.6
label | ef13bb40-cf14-58bf-bbb8-a682222869bf |  | note | Verifying Document - INSERT APPROVED MIX CODE
label | 55cbc80b-03cd-5e9c-8a5d-801836757880 |  | note | Frequency - Prior to construction commencing
label | 83948472-7d3f-5c90-8b83-f23ecd63605d |  | note | Activity - C
label | 2465b951-f961-5f00-a62a-e1a9ced4f074 |  | note | By - SE
checkpoint-group |  |  | section | SECTION 3 – CONSTRUCTION ACTIVITY – KERBING
checkpoint-status |  |  | checkpoint | 3.01 - Survey Set out Confirmation
label | 97b3a708-4ec3-5ea4-964c-3f03734ab723 |  | note | Acceptance / Conformance Criteria - Ensure kerb preparation is to design level.
label | 923bc9bc-8d0e-535f-8ab2-f2d5c9e2bec6 |  | note | Standard / Specification - As per design
label | 16f6083f-6ca4-5c31-988f-54abfaca1e06 |  | note | Verifying Document - Survey Records
label | 792c7781-ea5f-555d-aebe-33c0d2cdf6e8 |  | note | Frequency - Every steel pin
label | 1009bd04-9c5d-5563-9afe-afb34af2ca8d |  | note | Activity - I
label | 8b77a263-a130-583b-a57d-6898303d9bff |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.02 - Clegg Hammer Test
label | 3e6f909a-0839-5771-b87d-7ce49744648f |  | note | Acceptance / Conformance Criteria - Only if kerb and channel is constructed separate to the road, the base that the kerb and channel is founded on - Clegg Hammer must be tested every 15m at 25 CIV (where applicable)
label | fb0bfa8f-da6d-54cb-a3cb-70013c6fdcbc |  | note | Standard / Specification - Refer to RITS - 3.8.2.10
label | 2ef0d09c-ce74-5972-bd92-777b04b6e82b |  | note | Verifying Document - Test Records
label | 4ec4f351-5c24-5ba7-8c69-1ece04a4c8bf |  | note | Frequency - Every 15m prior to slip forming
label | be6223ce-c3d6-59d0-a02d-464d8ffbb2dc |  | note | Activity - C
label | d025571d-7664-5551-b043-b5225791faf4 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.03 - Pre-pour inspection
label | 45af77d9-6b82-5f2f-a0de-f716e11e7cb1 |  | note | Acceptance / Conformance Criteria - As per RITS specification 3.4.5.3, BBO Engineer approval to proceed. / reo-inspection with 24 hours’ notice prior to pouring
label | f03b22cb-36fc-5e0d-9952-4a8e452058fb |  | note | Standard / Specification - Refer to RITS - 3.4.5.3 PS - 2.2.16
label | be021b70-d6ba-5cf3-93ba-158dc14da3ca |  | note | Verifying Document - Visual inspection / Photos
label | bf852721-07f3-534b-8942-39cc933eba36 |  | note | Frequency - Prior slip forming
label | 21a22d89-90da-54d7-b43c-0dadef67a690 |  | note | Activity - HP
label | 8001cba0-7ef9-5746-9d63-52760940e199 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.04 - Concrete Cylinders/Slump
label | ddb9f5a2-1b90-5712-9e78-932c193136ba |  | note | Acceptance / Conformance Criteria - Minimum 20MPa strength, 1@7-days and 3@28-days
label | f8ebdf82-eed3-5dde-a8dd-6f55c7ce0d94 |  | note | Standard / Specification - RITS requirement (Drawing D3.3.3, Note 1)
label | 5da12b5e-1aed-553b-903a-b2fb4fe361ea |  | note | Verifying Document - IANZ Test Records
label | d7d20e1a-f544-582c-9f56-08e2a8eae494 |  | note | Frequency - Each pour day
label | 1ed0ab54-0805-545d-9def-36e384b5e2ba |  | note | Activity - I
label | d6de34f8-b1bd-533c-8817-8055611e107c |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.05 - Curing Of Concrete
label | 2d7e457a-1623-518d-9b8b-a99d89e0a4d1 |  | note | Acceptance / Conformance Criteria - Curing period shall not be less than 36 hours
label | b3ff426b-615e-5670-8c03-c611187b5513 |  | note | Standard / Specification - Refer to RITS - 3.4.5.5 / 3.4.5.9
label | 90535db4-5f9b-5af8-b3fd-b755221f2044 |  | note | Verifying Document - Visual inspection
label | 75f8cc93-2962-5300-b563-0f9e23f9fee8 |  | note | Frequency - Throughout the activity
label | 69ea095c-57d5-5861-a60c-8c201100e1e2 |  | note | Activity - I
label | 398ec7d8-bfa2-56ec-a231-3e0b6ae49899 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.06 - Post-pour level check
label | cb1f1576-ba0f-5896-bed6-e6e7e8b0115b |  | note | Acceptance / Conformance Criteria - As per drawings
label | 39811371-720c-5a52-8bfc-b16b362c0efe |  | note | Standard / Specification - PS - 2.2.12
label | 28bc6470-95ac-59d5-833f-033cb02967a4 |  | note | Verifying Document - Total station topo and check prior to carrying on with further pavement layers
label | 1f2a57e0-d01e-5bb3-abd5-3245436761c5 |  | note | Frequency - Every survey peg
label | ee1fe224-ff61-51df-b342-f316a7f93d55 |  | note | Activity - I
label | 1c5b9fe2-4120-5d6e-a238-36aefb19ccde |  | note | By - SV/SE
checkpoint-status |  |  | checkpoint | 3.07 - Contraction/Expansion Joints
label | ac9db46b-4000-5c9a-80ee-f2ac39bb4a78 |  | note | Acceptance / Conformance Criteria - Contraction/Expansion joints shall be formed or cut along the kerb at a maximum spacing of 3.0m.
label | 5a4c419d-4412-5b68-90ec-12aacb6786c7 |  | note | Standard / Specification - Refer to RITS - 3.4.5.8
label | bec91869-f51b-524a-9605-bd5f610022dc |  | note | Verifying Document - Visual inspection
label | 0492c58f-995b-5fc7-b03b-1a99b0dc1fdb |  | note | Frequency - Every 3m.
label | ca5bb3a1-1e2a-5278-beca-5bb81b49f4f2 |  | note | Activity - I
label | be0b39af-554b-5a1f-b5d2-8b6597f4d8b8 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.08 - Concrete Mix Dockets
label | c9399c42-c5a4-5deb-81c7-357117b23aff |  | note | Acceptance / Conformance Criteria - Matches approved mix code
label | 13d4a077-ec71-502a-a1b6-21162c175b8a |  | note | Standard / Specification - As per approved mix
label | 5bf57c96-5735-5dde-b4a4-c6d7f111b5d4 |  | note | Verifying Document - Dockets
label | b6326348-0f0d-5545-9428-805af4e2b492 |  | note | Frequency - Every truck load
label | 1c065f24-baba-5f32-8ac5-e99b9f1fc80b |  | note | Activity - R
label | 273e9cba-6eca-542d-bd1d-cba2738f7296 |  | note | By - SE
checkpoint-group |  |  | section | SECTION 4 – POST CONSTRUCTION – KERBING
checkpoint-status |  |  | checkpoint | 4.01 - Post pour inspection
label | 0f047b9f-8ee3-5bed-bca6-d64c1e72f853 |  | note | Acceptance / Conformance Criteria - Acceptance and sign off by the client Engineer.
label | 83e48047-0b11-5148-b984-ddbddbd42a89 |  | note | Standard / Specification - Surface finish and levels acceptable
label | 65bb29c0-80b3-5be3-af8d-d2bac7629509 |  | note | Verifying Document - Review of total station topo
label | 7f87d946-d5b3-5d3f-ae15-7bbc4d7301c6 |  | note | Frequency - When work is complete
label | bdae422c-284e-5c67-b1f0-ebc7fa266e5d |  | note | Activity - I
label | 169369f3-d955-5506-be6d-13c132ead951 |  | note | By - ENG
checkpoint-status |  |  | checkpoint | 4.02 - As-built
label | 8b1b8286-6eed-5797-a9a9-39828abdaf1b |  | note | Acceptance / Conformance Criteria - Electronic points file to be provided
label | 0d50a8b1-6c63-596e-9ab1-a03435d3780f |  | note | Standard / Specification - PS - 2.2.17
label | e5705a29-9315-5b47-bd59-c92ee73bb244 |  | note | Verifying Document - Total station asbuilts
label | 96c33f0b-bf83-5f1c-b914-125971f39f41 |  | note | Frequency - When work is complete
label | b93fa637-87ea-53b9-8322-c0f6c07828c0 |  | note | Activity - A
label | bf15c63c-7bb5-5654-9fd9-d3b4d797c932 |  | note | By - SV
checklist-sectioned |  |  | checklist | ITP - Pavement SIL |  |  |  |  | Yes | ITP - Pavement SIL | c16731ae-3527-42b0-9337-2cc6a8485ecc
checkpoint-group |  |  | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.01 Site Requirements
checkpoint-status |  |  | checkpoint | 3.01.01 - Construction Pack
label | 4b26e7cb-ace0-58bb-a616-39483fc6b83d |  | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence
label | 39bdd60b-5a55-5725-9d44-67dc819f7e82 |  | note | Standard / Specification - Downer
label | f37b21b6-fe75-518e-99e7-441bb2e54568 |  | note | Verifying Document - Construction Pack
label | e20b4b8a-d1f3-5800-add6-1b620896d23b |  | note | Frequency - Prior to Works
label | 2c256560-e7aa-55c9-98a1-86938a36f071 |  | note | Verification Activity - H
label | 5aa00b7c-8cab-5b58-9c8a-a8ebcd4457f9 |  | note | Verification Activity By - PE
checkpoint-status |  |  | checkpoint | 3.01.02 - Survey Setout
label | e3e94e95-7461-5602-8ae5-1f475a9a9372 |  | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | a9ccfcea-23ab-5f83-98aa-01aa55f14f09 |  | note | Standard / Specification - Downer
label | bd924ba3-e98a-5a37-88f8-deb39c1915c3 |  | note | Verifying Document - Survey Records
label | 21d5543a-b500-5bb2-b23b-7150daaf8fee |  | note | Frequency - Prior to Works
label | 8155419d-e2cb-5987-8b90-4a5df3da5317 |  | note | Verification Activity - H
label | 651d4ceb-5a87-5cee-aa2f-1d5af93f48ca |  | note | Verification Activity By - SV
checkpoint-status |  |  | checkpoint | 3.01.03 - Service Location
label | beea7a1c-046b-5fb7-91cd-46b86eb7ecfd |  | note | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | 8c0340ae-3f3f-57df-8af6-8836db439d12 |  | note | Standard / Specification - Downer
label | eaababd1-32a0-5323-ad8b-8e999dafd51d |  | note | Verifying Document - Excavation Permit
label | 558c19e0-5e33-5b6a-a931-c34e81e92a2c |  | note | Frequency - Prior to Excavation
label | 85387089-5afd-5a2b-974f-78eb26637df0 |  | note | Verification Activity - H
label | 33484b60-704b-5d44-8ca8-0d2f7803fb57 |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 3.01.04 - Internal Permits
label | 24c5b6b2-98a4-589a-a0ad-fa73c558e90d |  | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | f1ead7c5-425d-5829-b8d1-0edd0ebada26 |  | note | Standard / Specification - Downer
label | 7bc080ae-d60d-55ed-9e48-c9efb7f6d7ce |  | note | Verifying Document - Internal Permits
label | f051067e-abc8-58c0-96b0-6932e794b31d |  | note | Frequency - Prior to activity being undertaken
label | 518ffaca-a960-5750-b6b8-c85a4e56025c |  | note | Verification Activity - H
label | cfe1cce4-c9a2-53b0-9062-99d2666b7ccb |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 3.01.05 - External Permits
label | b2e25bb1-ceae-59ce-be7a-ac0fa86efbac |  | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | 26281c77-fff7-5dd4-88f3-7e33e61e9cbf |  | note | Standard / Specification - Downer
label | fb232d0f-a63d-56c9-8cef-c489fe97494c |  | note | Verifying Document - External Permits
label | 9e657bb1-bd49-5ffa-98e1-3b2ad9d187b6 |  | note | Frequency - Prior to commencment of activity
label | 8037d5ba-0dd4-5d90-9102-4cba9dadd771 |  | note | Verification Activity - H
label | 62198747-f56f-5a64-8a05-cde299bdfa49 |  | note | Verification Activity By - PE
checkpoint-status |  |  | checkpoint | 3.01.06 - Approved Construction Drawings
label | bb46b8a2-0124-5764-b4dd-7bdf0e69e95c |  | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | f9faecd7-6ccf-5952-87fc-e7dc6b36747a |  | note | Standard / Specification - Downer
label | 030bf603-8060-5f9d-9f7a-d5e4d6516677 |  | note | Verifying Document - IFC Drawings
label | 73c5b094-94c7-5167-9ef9-037fd27c4209 |  | note | Frequency - Prior to works start
label | cefe589e-775b-5225-b22e-07aa1e40a577 |  | note | Verification Activity - H
label | 434a1998-8714-52c5-bd16-87cddbd9fb72 |  | note | Verification Activity By - PE
checkpoint-status |  |  | checkpoint | 3.01.07 - Previous Layer QA Sign Off
label | 6983331f-cd49-553d-9d1b-2fb72a289629 |  | note | Acceptance / Conformance Criteria - All Previous layers signed off, QA complete. Including subgrade, SW, WW, WM. Ensuring everything up to the bottom of SIL is compliant.
label | 915f2668-b583-53ab-a791-7764dde86a86 |  | note | Standard / Specification - Downer
label | 77414674-0ef9-565c-bd1e-9e79630527df |  | note | Verifying Document - QA Records
label | f3a3f4b4-c411-555b-86c7-ecf46bcdf601 |  | note | Frequency - Prior to works start
label | c6466e5e-b003-544d-bb6f-6a7c079699e2 |  | note | Verification Activity - H
label | e1d16e4b-df18-54d6-933a-5129d5ba5833 |  | note | Verification Activity By - PE
checkpoint-group |  |  | section | SECTION 4 – ENGINEERS HOLD POINTS - 4.01 Engineer Nominated Hold Points (Engineer’s inspections)
checkpoint-status |  |  | checkpoint | 4.01.01 - SIL Inspection
label | 589c641a-aa63-5852-9ee0-74bb69e89f17 |  | note | Acceptance / Conformance Criteria - Prior to placing of sub-base pavement, to include proof roll, inspection of extents of works, general shape, and tidiness, free of organic or contaminated material, review of Benkelman Beaming of the SIL and final levels.
label | 63d5d160-5d5e-5d1c-8f98-de84fd1bffb8 |  | note | Standard / Specification - PS - 2.2.16
label | c3cb4613-e4f5-5cfc-b1af-22f8b68c2820 |  | note | Verifying Document - Hold Point Release
label | c154df35-5954-5684-b09e-81eb77940267 |  | note | Frequency - Min 48h Notice
label | af005a20-54f3-5277-886e-7af9e988939a |  | note | Verification Activity - HP
label | 18fb0707-f3d9-5d50-af1f-10287369254f |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.01.02 - Subgrade Inspection
label | ccdd5453-ce4a-5556-99a1-e628c9df66ef |  | note | Acceptance / Conformance Criteria - Proof roll, Scalar penetrometers, and shear vanes prior to SIL fill commencing
label | 4bc1e182-7aa8-55c3-b605-7ac285d42607 |  | note | Standard / Specification - PS - 2.2.16
label | d3d56a58-b3ff-5de8-80eb-b959f7028b02 |  | note | Verifying Document - Hold Point Release
label | daf11b30-c8b1-541a-9e0a-1f48878bd249 |  | note | Frequency - Min 48h Notice
label | 3f765b21-ec87-5fc9-b2c0-516f6ba42d38 |  | note | Verification Activity - HP
label | 54909fee-8367-537a-913e-c78a0b548259 |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | SECTION 5 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 Subgrade Materials
checkpoint-status |  |  | checkpoint | 5.01.01 - Pavement Subgrade CBR
label | b3e03a0d-8900-51ac-be82-923b82921d09 |  | note | Acceptance / Conformance Criteria - The pavement design requires a soaked CBR of not less than 10 within 1.0m of the bottom of the SIL layer and 4x DCP's to a depth of 1m below subgrade level in a 1m grid around the in-situ CBR test location and 4x NDM's DT with a probe depth of 300mm in a grid around the in-situ CBR location. CBR testing of the subgrade shall be carried out by the Contractor prior to final trimming. If the soaked CBR is less than 10 the Engineer may instruct changes to the pavement design. (Push tube for Cut and Filed sample for Fill). Invitation for engineer to witness CBR testing. To be accurate representation of site
label | 8bc2d425-ceb7-5734-bb77-d28559cf4dd1 |  | note | Standard / Specification - PS 7.1
label | 7a8b0934-9135-54fb-b2a4-e6b80a154256 |  | note | Verifying Document - IANZ Lab Reports
label | 1086e7dd-eabe-514b-87d6-33b88e67f9b1 |  | note | Frequency - One test per 2,000m2, with a minimum of three tests per material type.
label | d8f0f437-a191-57db-ab63-ab5fa84405d2 |  | note | Verification Activity - HP
label | 07eb9ac4-2f53-5c6b-9ec0-d3b5327d7a95 |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5.02 - SIL (Clean Pit Sand)
checkpoint-status |  |  | checkpoint | 5.02.01 - SIL Conformance
label | 7b7cbf9c-e8ee-5e03-b9c4-19e9defd7ac5 |  | note | Acceptance / Conformance Criteria - The SIL shall be pit sand meeting the following requirements: · 4-day soaked CBR (NZS 4402:1986 Test 6.1.1): Shall be ≥ 30. · Organic Matter: It shall be free of organic matter. · PSD (NZS 4407:2015 Test 3.8.1): Shall be <7% passing the 75μm sieve.
label | ab9dc707-18c8-576e-aaac-433561430047 |  | note | Standard / Specification - PS - 7.2.1
label | 68faef9d-392a-59d7-bcaf-6fa1bc1f1e4f |  | note | Verifying Document - Lab Reports
label | c4fedb90-397f-5d70-8393-ddd5f80bc3ef |  | note | Frequency - CBR and PSD testing shall be completed at the rate of 1 test per 2,500m3, and being no less than 1 test every 3,000m2 (placed).
label | 2aa170d9-fa30-5034-aee7-9c13a2cf0362 |  | note | Verification Activity - HP
label | ff1df35a-76b1-5238-93f8-cfc823b7b0f1 |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.02.02 - SIL Maximum Dry Density & Optimum Moisture Content
label | a27e8fb3-c719-5968-a595-666a016a330e |  | note | Acceptance / Conformance Criteria - The SIL shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density & Optimum Moisture Content
label | 9401944b-e210-541c-9a33-a939c9d05c3e |  | note | Standard / Specification - PS - 7.2.1
label | 008a0244-1f95-5a7a-9e8d-80305a50d1ed |  | note | Verifying Document - Lab Reports
label | 05358614-5f37-5794-981b-b6ef430b82c7 |  | note | Frequency - 1 test per material type and no less than 1 test every 5,000m³ (in place)
label | 0e569234-ac64-532c-a6a1-d7a30e8d6b76 |  | note | Verification Activity - HP
label | 73f1f2dc-3ee4-55d4-a027-2e6d2c716e44 |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.02.03 - Plateau Density Test
label | 4d47d092-b781-5579-afbe-d0a041d3ac9d |  | note | Acceptance / Conformance Criteria - Compaction shall be undertaken using the higher of the two density targets. Plateau tests to be spread out evenly to be an accurate representation on what is coming into site.
label | 3646b1f1-33f8-54ed-978d-3519e10c9441 |  | note | Verifying Document - IANZ Lab Reports
label | 292f8656-46b5-5e25-9d81-b6c1be49f298 |  | note | Frequency - 5 tests per 10,000m2
label | cf700307-c8b6-5b85-8348-1951da8bab5f |  | note | Verification Activity - C
label | c2e994f8-60dc-5a5e-808d-82e1602f55ad |  | note | Verification Activity By - ENG
checkpoint-status |  |  | checkpoint | 5.02.04 - NDM
label | a65fdecb-7522-5aef-8f72-c9c72775f831 |  | note | Acceptance / Conformance Criteria - Mean Value ≥ 98, and Minimum Value ≥ 95. All NDM testing shall be undertaken via Direct Transmission method at 300mm probe depth.
label | 737f32a6-ca14-58fd-aea3-8aff714c61e6 |  | note | Standard / Specification - PS - 7.3.1
label | e55891f8-d0de-516a-b9c8-54ad6ca789e9 |  | note | Verifying Document - IANZ Lab Reports
label | df80991c-456f-5a22-94b9-66aea17bf2ea |  | note | Frequency - 5 tests per layer per 1,000m2
label | ddeea918-5e1e-53c5-bdb0-567b4a7edd31 |  | note | Verification Activity - C
label | fa4e54ea-eb3c-5011-b31b-85f88f881e0f |  | note | Verification Activity By - ENG
checkpoint-status |  |  | checkpoint | 5.02.05 - Benkelman Beam
label | f1e57e77-c46f-5c32-a4b7-5c36a4a04f61 |  | note | Acceptance / Conformance Criteria - Target Benkleman Beam deflections on the top of the SIL layer are 1.6mm (90th percentile) and a maximum of 1.8mm
label | 4f236964-6a78-58bb-a2ad-29ca204c836c |  | note | Standard / Specification - PS - 7.3.1
label | 9af0f383-b583-5491-8e2a-112b9bbfe9b3 |  | note | Verifying Document - IANZ Lab Reports
label | f7a61f4b-00fa-5389-858d-3782c067994b |  | note | Frequency - every 10m of each lane – staggered between left and right wheel path.
label | 70f2fcc9-b04d-51bc-a428-0e43ad15a03b |  | note | Verification Activity - C
label | e7ad119b-d74a-5d5c-b2d6-3a42d6de70a8 |  | note | Verification Activity By - ENG
checkpoint-status |  |  | checkpoint | 5.02.06 - Organic Material
label | b3e67920-8037-5400-8c1c-642e5ee8991f |  | note | Acceptance / Conformance Criteria - Ongoing visual and physical inspection for any roots/organic material, photos of clean sand, and any organic material removed.
label | a0c385bf-bf9c-5c1c-ac4e-583139a2d735 |  | note | Standard / Specification - PS - 7.3.2
label | 936b6251-f4a7-5a3b-bf3c-24cba6f93080 |  | note | Verifying Document - Site Records, photos of clean sand, and any organic material removed
label | db82440f-7ec5-5382-8705-2ae2bae059b1 |  | note | Verification Activity - I
label | b5079f59-52f0-5920-ac35-007512183c86 |  | note | Verification Activity By - ENG
checkpoint-group |  |  | section | SECTION 6 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING - 6.01 Construction
checkpoint-status |  |  | checkpoint | 6.01.01 - Subgrade Prep
label | 3314eb0a-8401-58d3-a782-af26e847ee14 |  | note | Acceptance / Conformance Criteria - The subgrade shall be prepared in accordance with the requirements of the Geotechnical Works Specification in Appendix B, including proof rolling, Scala penetrometer and NDM testing at the specified frequencies.
label | 4832cdc2-16f0-54fb-b9f5-b13fd4db465b |  | note | Standard / Specification - PS 7.1 GWW
label | 4d5bf8ee-a1ae-53dc-83a1-b890969d9705 |  | note | Verifying Document - Completed Earthworks ITP
label | 81025f5f-e79f-5ae5-98f3-223c68ae7b80 |  | note | Frequency - Prior to Pavement Works
label | 08eae87e-fbb1-52e4-abc1-c936b9f15f93 |  | note | Verification Activity - HP
label | 531c5d6a-0940-5478-b658-d32ba101608b |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6.02 SIL (Clean Pit Sand)
checkpoint-status |  |  | checkpoint | 6.02.01 - SIL Scala Testing
label | dcff1fcc-0468-5c64-97ec-07f5bb15626e |  | note | Acceptance / Conformance Criteria - In addition, the SIL (tested in accordance with PS Clause 7.4 below) shall achieve a Scala penetrometer blow count no less than 10 blows/100mm. Depth to be 1.5m from top of SIL.
label | 4163e9ea-e5a1-5798-9f16-4efc158777b9 |  | note | Standard / Specification - PS - 7.3.1
label | e34d2610-b9ae-5077-ba99-de1bc7d627bb |  | note | Verifying Document - Scala Results
label | 9faf4a1c-754c-5fea-ade0-407e75652614 |  | note | Frequency - 1 test per 200m2
label | 894e4cdf-7c9d-5780-a212-8b8d34c34071 |  | note | Verification Activity - I
label | 7f61f95f-4eb2-5bcd-b43f-2b57f7050d3c |  | note | Verification Activity By - PE
checkpoint-status |  |  | checkpoint | 6.02.02 - Layer thickness
label | 3f529307-5392-5a66-acbb-081265d82c69 |  | note | Acceptance / Conformance Criteria - Each layer shall be checked to ensure the required layer thickness is achieved of Maximum
label | 0fa5048b-d270-5ea1-9593-a35fc1bbadaa |  | note | Standard / Specification - PS - Table 7.2 - 2.2 NZTA B/2
label | f5c571b2-b56a-5c59-8c5f-481204083b8b |  | note | Verifying Document - As-built data
label | 5c79b190-c473-5a2d-9a81-4b6cf4384c9d |  | note | Frequency - 1 test per 20m
label | 940c333f-fade-574e-82a7-6ece487ed079 |  | note | Verification Activity - I
label | da0419c8-3af1-55d4-a644-463ad1be3e53 |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 6.02.03 - Plateau Density Test
label | 20cea371-9a84-570b-8d74-aa280094c8ab |  | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken at a rate of 5 tests per 10,000m2 using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. Plateau tests to be spread out evenly to be an accurate representation on what is coming into site.
label | 0aa05dd5-ffc9-504e-9a7c-60990433443a |  | note | Standard / Specification - PS - Table 7.2 - 2.2
label | 51fc55fa-f4bd-5d31-af32-b4186c256bfb |  | note | Verifying Document - Plateau Density Report
label | 0118de71-b76e-5cdf-8df4-d9032daf63dd |  | note | Frequency - 5 tests per 10,000m2
label | 24168a1d-4d75-5639-b2fc-a4cbf8e189ca |  | note | Verification Activity - I
label | d016790e-e344-529a-93dd-38a52669b805 |  | note | Verification Activity By - PE
checkpoint-status |  |  | checkpoint | 6.02.04 - Sand SIL layer compaction
label | dfb1d2fa-07ef-574d-824b-bdc7ebddb7a7 |  | note | Acceptance / Conformance Criteria - Further to Figure 2 of NZTA B/2, the acceptance criteria for compaction of the sand SIL layer shall be a Mean Value ≥ 98, and Minimum Value ≥ 95.
label | 80e7f2c7-ef44-58a0-a547-4edbf52dec16 |  | note | Standard / Specification - PS - 7.3.1
label | 72f78430-a5d7-5df8-88f4-eb2aab833a7f |  | note | Verifying Document - IANZ NDMS
label | 09a46328-eb63-5bf7-b4b2-789d16cf2ce4 |  | note | Frequency - 5 tests per layer per 1,000m2 (Min per lot)
label | aac1ee29-8af1-503f-a4ab-7102ea90cd06 |  | note | Verification Activity - I
label | b6d28b73-0c57-5903-886a-50e7c7b030f5 |  | note | Verification Activity By - PE
checkpoint-status |  |  | checkpoint | 6.02.05 - Proof roll
label | 07b326c3-ea68-549d-9128-c3000d49c9de |  | note | Acceptance / Conformance Criteria - The SIL shall be tested via Proof roll prior to Benkelman Beam testing. Proof roll to be under supervision of engineer and verifying document to be signed off by engineer.
label | f5e9d4dc-40e8-58cf-a4aa-b27c60255de8 |  | note | Standard / Specification - PS - Table 7.2 - 2.2
label | 564d8205-b741-54d5-b073-d48e5d67d9c6 |  | note | Verifying Document - Site Notes
label | 75ed5345-a8b0-52aa-bbc1-534c1cbcdb82 |  | note | Frequency - 1 test per 20m
label | e7f0260f-c6f5-50d7-84e5-50a351b4280e |  | note | Verification Activity - HP
label | 61899164-dfe5-5bc3-b907-b5b068e82afd |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.02.06 - SIL Benkelman Beam test
label | 1474a3bc-5812-5d34-93c3-2a76dbcbc6d8 |  | note | Acceptance / Conformance Criteria - Benkelman Beam test results shall be carried out on the top of the SIL layer at the rate specified in PS Clause 7.4 and reported to the Engineer. Target Benkleman Beam deflections on the top of the SIL layer are 1.6mm (90th percentile) and a maximum of 1.8mm. Performance verification of these target deflections shall be confirmed by the Engineer on review of results from within the pavement Stabilisation trial (PS Clause 7.3.3).
label | 04c2be5d-e694-5630-ae8f-3cd00f7c3b8f |  | note | Standard / Specification - PS - 7.3.1 PS - 2.2.16
label | b519543d-4049-5ba0-bd30-397138d05564 |  | note | Verifying Document - Benkelman Beam Report
label | 2acdff5b-4e24-5f1d-87a6-475ceff0ac5b |  | note | Frequency - every 10m of each lane – staggered between left and right wheel path. Min 48h Notice
label | e4b7f0ea-806f-538d-9a07-d162c6b4f901 |  | note | Verification Activity - HP
label | 62e03724-57d9-548c-9937-de3062eaf727 |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.02.07 - SIL Inspection
label | add1780d-3465-530b-bd7c-6b3040e3182b |  | note | Acceptance / Conformance Criteria - Before laying of any pavement SIL and metal courses. SIL inspection to be carried out under supervision of engineer, verifying document to be signed off by engineer.
label | aaa691c7-ddbd-559c-b7d2-ece1f6df8a75 |  | note | Standard / Specification - PS - 2.2.16
label | 62109f41-cacd-5114-9387-f25dd7090a0b |  | note | Verifying Document - Hold Point Release
label | 53749f59-1a97-5155-aa0f-01f9dede2b1c |  | note | Frequency - Min 48h Notice
label | 8cf9b4d1-106e-5b75-8410-1d614ffa90d2 |  | note | Verification Activity - HP
label | c500ca95-c927-5ef8-8063-ff8836fab8fe |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.02.08 - Topography
label | bb8d94d0-cad7-5b1c-8c9b-72bfccbba337 |  | note | Acceptance / Conformance Criteria - Carry out level check on trimmed SIL. Survey conformance with Total Station. Tolerance = -30mm +0mm (NZTA F/2).
label | dfea0969-3fe2-5fb8-b6e2-71a12b4b8f40 |  | note | Verifying Document - Survey PDF against IFC or similar
label | c4f76caa-a1e7-5193-a040-20aa641b2936 |  | note | Frequency - every 1m across the road (avoiding islands) at 20m intervals
label | 9af73578-466b-5e6f-8458-cf20471145cb |  | note | Verification Activity - I
label | 0f251313-de06-520b-8bad-69923864004d |  | note | Verification Activity By - ENG
checkpoint-group |  |  | section | SECTION 7 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - 7.02 Site Post Construction Activities
checkpoint-status |  |  | checkpoint | 7.01.01 - Construction Record Compilation
label | e33b7f2d-364e-554c-bbc9-71565eeabdcd |  | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | 02cb16d6-62a9-5c07-b1fd-9212d27af6d9 |  | note | Standard / Specification - Downer
label | d5242ce2-72cf-5b1b-93ee-f2289178affc |  | note | Verifying Document - Records
label | 89f45c46-bd82-5272-9f96-7c18301858fe |  | note | Frequency - Post construction
label | e3b23594-8fa7-5800-9495-7772a6d9da38 |  | note | Verification Activity - H
label | 1f3b92d1-88f6-5192-86a8-d876bfc05b8f |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 7.01.02 - Survey Records
label | 09ede6c8-4248-52cc-ab76-a1b266afc9e7 |  | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | 64e2281b-04ef-5dd0-a95a-ed86a87e480f |  | note | Standard / Specification - Downer
label | c7cbca71-5e4d-5ee2-9c7e-338c155a00cc |  | note | Verifying Document - Records
label | 6bfdd8a6-0e45-5a32-b543-6abfceba1022 |  | note | Frequency - Post construction
label | b936ae2a-5b7f-575c-b00c-96f40edeb440 |  | note | Verification Activity - H
label | 239d20eb-1cda-5151-8ee0-a1a37fa759ad |  | note | Verification Activity By - SV
checkpoint-status |  |  | checkpoint | 7.01.03 - Redline Drawings
label | 4d55e902-6fc9-5949-bd90-3718360ae31b |  | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any increase in SIL depth.
label | 92347465-5877-5da6-87bb-b262af7857d7 |  | note | Standard / Specification - Downer
label | 9dcd9ed1-320f-5caa-9c10-bea4580085c4 |  | note | Verifying Document - Redlines
label | 3bb64a96-941d-58a0-8054-c7df7e8a417b |  | note | Frequency - Post construction
label | 34016d76-9cb7-5f99-ac70-5ccdd07ac80a |  | note | Verification Activity - H
label | dc0a719b-c026-5d33-b5c3-421f855beb57 |  | note | Verification Activity By - PE
checkpoint-status |  |  | checkpoint | 7.01.04 - Defect, Snag and Punch List
label | a813cec3-db3c-59fe-ae89-11ec57536b58 |  | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | 4b87d8eb-15fe-50d6-a4c4-3d238a68c758 |  | note | Standard / Specification - Downer
label | 95b0b9db-0eec-5c01-aca1-4e4b0c7d024b |  | note | Verifying Document - Register
label | 54deb3d9-5e5c-5c40-b241-f30fadd35c16 |  | note | Frequency - Post construction
label | 98e8bc64-2444-52eb-abdc-f1fd9dccc045 |  | note | Verification Activity - H
label | ab26cea9-5803-55d8-a91d-5f75095d1303 |  | note | Verification Activity By - PE
checklist-sectioned |  |  | checklist | ITP - Wastewater-PVC - Rev F |  |  |  |  | Yes | ITP - Wastewater-PVC - Rev F | c542aac1-81a3-495e-8502-c63793504e9f
checkpoint-group |  |  | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint-status |  |  | checkpoint | 1.1 - Extent of Line Setout
label | 0d5eef49-d0fc-5a1c-8a82-fd3a74f4033f |  | note | Acceptance / Conformance Criteria - Ensure line and level of Wastewater has been marked out and agreed with Engineer in accordance with Wastewater drawings Identify any clashes before construction.
label | 0d071870-11c5-5eec-84c9-292c12037ea6 |  | note | Standard / Specification - Design Drawings
label | 0c26aa56-26c6-57ec-a2ad-e0bcf160427c |  | note | Verifying Document - ITP Sign Off
label | 3a52920e-aaf1-52da-881b-91fe241aef3f |  | note | Frequency - Prior to Construction & Every Revision of IFC Drgs / Data
label | 63977a38-fd54-570a-b231-ab58a3755fd8 |  | note | Verification Activity - M
label | 4f7e095f-a708-5e2a-93ee-5ab5f300b976 |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 1.2 - Environmental Protection
label | 7bc6ee02-e63f-597c-b980-314821ff6b01 |  | note | Acceptance / Conformance Criteria - Install Erosion Sediment Control measures in line with PWRBSS ESCP plans Inspect, monitor, and maintain ESCP measures weekly and immediately before & after significant weather events
label | f3e9a12d-8c5a-5a8e-bf90-8ede8d1fa0b1 |  | note | Standard / Specification - Project ESCP Plans
label | 46bfa01b-553c-5913-8caf-ebdd8474fbde |  | note | Verifying Document - ITP Sign Off
label | b29f2714-073d-5b81-bd59-5a1cbe02af26 |  | note | Frequency - Prior to Construction Inspect, Monitor, and Maintain Weekly and immediately before and after significant weather events
label | 93e14ecb-207f-5822-9af8-0cdb07361ee8 |  | note | Verification Activity - M
label | 3ea2dbb3-c6bf-5dc0-aa59-59f7b80d4a4e |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 1.3 - Stakeholder
label | afaf20fc-c54e-5524-8f33-e4380c3567a9 |  | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
label | a09a546d-55fe-5f19-b899-ae01546cb169 |  | note | Standard / Specification - Project Stakeholder Management Plan
label | 967077ad-1d63-5426-901a-2aa6bc33d6d4 |  | note | Verifying Document - ITP Sign Off
label | e5e9c320-9f09-5c08-9a43-e161dbb5bf39 |  | note | Frequency - Prior to Construction with continue updates throughout the works
label | 0ace0bfb-bfcd-5b85-a19a-a83a01875460 |  | note | Verification Activity - M
label | e39f3135-cafb-5b0b-b29c-fb105c9bd876 |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 1.4 - Permits
label | bd0fe073-cba0-5f59-a016-aeda24e18447 |  | note | Acceptance / Conformance Criteria - Permit to Dig must be in place before any ground breaking activity commences, incl. trenching, driving waratahs or survey pegs, and topsoil strip. Permit to Dig will be based on BBO existing Services Drawings, Before U Dig Plans , potholing by the project, CAT & Genny survey, and visual inspections. All known services must be clearly marked on site and briefed to the workforce .
label | 79645441-64ea-58ef-b789-aad531bc2ad6 |  | note | Standard / Specification - Section 2.2.10 Project Specification
label | b67b4743-30a9-590a-9b37-350070f50604 |  | note | Verifying Document - Ground Disturbance Permit DN-ZH-FM043.1
label | 27583fad-0c9b-50eb-8194-8c8a1b4cadbd |  | note | Frequency - Prior to Construction Reviewed and Reissued weekly or when site conditions change
label | 47dad4cc-2d8d-5614-bf1e-4055e6a65556 |  | note | Verification Activity - H
label | e7cd61f0-d1fa-5369-b44a-ccc53d21f64e |  | note | Verification Activity - By: - PE
checkpoint-group |  |  | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint-status |  |  | checkpoint | 2.1 - Pipes, Fittings and Pre-cast Structures
label | 8380fd18-221b-5c3b-b14b-e692cc846559 |  | note | Acceptance / Conformance Criteria - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes/manholes are correct and in good condition and compliant.
label | 89890d6c-4980-5009-8325-2eac61e918d2 |  | note | Standard / Specification - PS Appendix L
label | 825234e5-2d1d-5fcc-bee4-6ba02fbafbc4 |  | note | Verifying Document - Delivery Dockets
label | d408a0c9-efa7-5344-8e51-029ba33d35a3 |  | note | Frequency - Each Delivery to site
label | e04f09b9-b48a-57e2-b870-52ecbafd7093 |  | note | Verification Activity - S
label | f922cdaf-e2bb-5a91-824f-41c0d5865dc0 |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 2.2 - Bedding/Side & Haunch/Overlay/Backfill Material Compliance
label | 5a2cfb08-ad89-50f2-91cf-4777f1275762 |  | note | Acceptance / Conformance Criteria - Confirm material grading and density
label | 08a7f806-f8b9-5dc8-8aa8-cc410ee0a080 |  | note | Standard / Specification - PS Appendix L
label | 382be309-4d8d-5371-87b1-05587f94db3d |  | note | Verifying Document - IANZ Lab Test Report
label | 9a444a70-31d6-5dbc-8f4c-291d55f3dc8e |  | note | Frequency - 1 Test per 1000m3
label | 918e6dc4-ffed-53b9-9f63-766d42c0ad5d |  | note | Verification Activity - H
label | 9bdc96f3-272f-5e88-a260-7aceb61b2360 |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 2.3 - Undercut Backfill Material
label | 4b89be8b-43b8-59cd-815f-9acf1c08a812 |  | note | Acceptance / Conformance Criteria - Engineer to Specify Material to meet specifications dependant on material selected
label | 8097d6a7-b180-5018-87b6-12ab0464a2da |  | note | Standard / Specification - Engineer to Specify
label | eb77f4cc-821b-5bf8-856a-e20ceefb325b |  | note | Verifying Document - IANZ Lab Test Report
label | d3c2e5fa-8c1a-534e-a747-67fbeb9ed6a0 |  | note | Frequency - 1 Test per 1000m3
label | 953f3b31-d3fb-5be7-b265-54d13f455913 |  | note | Verification Activity - HP
label | 1ffea821-fd4e-5674-be51-72fc6127f647 |  | note | Verification Activity - By: - ENG
checkpoint-status |  |  | checkpoint | 2.4 - Geotextile/Geogrid
label | b083675e-9d2f-5fed-89e2-735bd98c3563 |  | note | Acceptance / Conformance Criteria - NZTA F/07 Strength Class C & Filter Class 1 geotextile is to be used in the undercut. Geotextile or Geogrid that is used in the undercut is to be documented / marked up on drawing
label | 5323cb79-91c0-54e4-ba4f-641d2790f3ee |  | note | Standard / Specification - Project Specification
label | e3b2c732-9e5e-55ec-a969-076070e60ae1 |  | note | Verifying Document - Certification
label | 72b70309-dbc1-5449-ab59-d58f87e9de84 |  | note | Frequency - Material Used
label | b0cb6815-4b18-5e59-beae-9613ff549fb5 |  | note | Verification Activity - C
label | ddfd5a19-6932-5ea2-b283-6fcd127b262d |  | note | Verification Activity - By: - PE
checkpoint-group |  |  | section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.1 WW Pipeline & Manhole Construction
checkpoint-status |  |  | checkpoint | 3.1.1 - Foundation Compliance
label | f9114ed8-508c-56c9-a70c-105d2888782a |  | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa
label | a805edc5-2b44-584f-9213-01a09c81f559 |  | note | Standard / Specification - Project Specification 4.3
label | e67b2dea-eeca-538c-b086-d2d763af8ade |  | note | Verifying Document - IANZ Scala test result
label | 76acdc33-ead8-5322-8ee5-98920d33eb07 |  | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
label | 48757397-c016-5f0b-8e74-9a848cff25f1 |  | note | Verification Activity - H
label | 0302830c-7332-59de-ab66-34ab747280cf |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.1.2 - Undercut Backfill Compliance
label | f165b5fe-6212-5080-a1c4-07cc213160c4 |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average 98%) of MDD
label | 05404d60-6262-571c-ab7f-97e9889a0080 |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70% or 95% of MDD AS/NZS 2566.2/2002
label | ada43e11-038b-5cb0-b5ba-bf0ac6a35a16 |  | note | Verifying Document - IANZ Lab Test Report
label | 9fc59673-dcbd-5795-991b-f459c7995aa9 |  | note | Frequency - Based on Undercut Section
label | 457b1941-1530-51c1-bb06-563a243bd414 |  | note | Verification Activity - H
label | e347b3d0-785a-5cf7-bef9-359eb06d128f |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.1.3 - Bedding Compaction Testing
label | 4459e1c9-44f2-5a1e-b6e6-870f04c8b5f9 |  | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average 98%) of MDD
label | 9fee4cc3-00a2-53f5-b535-ebb65125d555 |  | note | Standard / Specification - Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 2566.2/2002
label | d47bb5bc-3ae8-5178-bcf3-82784e72ec0b |  | note | Verifying Document - IANZ Lab Test Report
label | d95580df-35a2-5e6a-a3da-b87260e02da5 |  | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
label | 9977cecc-7656-5d5a-9b70-86e5ef67f597 |  | note | Verification Activity - H
label | e4969a6f-e491-5a9e-bd68-00560b809a5d |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.1.4 - Haunch/Side Zone Compaction Testing
label | 8c6f233a-cfe9-5745-abd0-57f1e432f484 |  | note | Acceptance / Conformance Criteria - NDM Back Scatter Minimum Compaction 95% of MDD
label | 078c54b1-a2cc-5641-8f40-4e135e103f94 |  | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS-25566.2/2002
label | 0d979ae5-b690-5c70-8586-3dcd359bc89c |  | note | Verifying Document - IANZ Lab Test Report
label | ec877efa-f836-5fce-914d-65c42133af1d |  | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
label | 355f9922-7a96-5092-a53c-a6bd5a79e540 |  | note | Verification Activity - H
label | d4d8b25b-c759-58fb-a058-5867a07868db |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.1.5 - Overlay Compaction Testing Overlay zone shall extend from top of Side Zone to 600mm above the top of the pipe. 2 lifts of 300mm should be placed.
label | d7cbb21f-3c7f-5065-be72-bf6e19634a05 |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95% of MDD
label | c3985824-6639-5243-924a-357dafeea0e7 |  | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS-25566.2/2002
label | bdab0c55-e44f-5a38-8d40-da3eb921643f |  | note | Verifying Document - IANZ Lab Test Report
label | 3a706429-ce3b-5a5c-acac-d7b3c99d521d |  | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
label | a97b6fb4-2749-5197-bfd2-9893f23d2fa3 |  | note | Verification Activity - H
label | 52a59d26-f675-5687-bd40-33937c0b61d1 |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.1.6 - Backfill Inspection
label | 12db7e92-b9dc-5d44-b13b-fdedc2975145 |  | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the pipeline.
label | 63a956f9-715e-5e8e-a332-afe4588e4d02 |  | note | Standard / Specification - Project Specification 4.3
label | 60d444b2-3c15-5124-8354-6dfaf78f9c41 |  | note | Verifying Document - Photographs
label | b1ab14f6-6ece-5cb0-adf6-9ae9ae772d75 |  | note | Frequency - Continuous
label | d54c2165-d850-5b0a-b89c-5600270b3fc1 |  | note | Verification Activity - S
label | 166bcfcb-cc5e-5ab0-ac87-a2b26da10865 |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 3.1.7 - Survey
label | d8b2d5c6-c725-5a65-a847-243a2bf19db2 |  | note | Acceptance / Conformance Criteria - The pipes shall be laid with the variation between the specified invert level and invert level laid shall not exceed 10mm. Pipe invert checks shall be carried out at least once per day with a maximum of 30m between checks.
label | a3f876d4-dfde-5223-aecf-28ebe92dcf94 |  | note | Standard / Specification - Vertical tolerance +/- 50mm Horizontal Between Structures +/- 100mm
label | 939644b9-8a94-5996-9d09-89e56788d01b |  | note | Verifying Document - Survey Data
label | ee51bd9c-6cf2-561b-82dd-22c6a02b957a |  | note | Frequency - Continuous
label | be32b652-6e68-51e1-a54e-2bfb34d520dd |  | note | Verification Activity - C
label | 4617b38a-d3e0-5d7a-8052-83f11b5687f0 |  | note | Verification Activity - By: - SV
checkpoint-status |  |  | checkpoint | 3.1.8 - Backfill Compaction Testing
label | 69683509-f357-55f2-b443-9e2678eda21f |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC. Minimum Compaction 95%(Average 98%) of MDD
label | 3132503d-6548-527d-ae32-76e55cc744cf |  | note | Standard / Specification - MDD Average of 98% with minimum of 95% PS 4.5
label | 3960ff87-9875-59b6-9e35-c1e15d31c11b |  | note | Verifying Document - IANZ Lab Test Report
label | 01f28adc-3ecc-512a-82d4-a6d1771e7a6c |  | note | Frequency - 0-5m: 2 Tests 5m-10m: 3 Tests 10m-40m: 4 Tests 40m-100m: 5 Tests 100m: 1 test per 20m
label | 3d0bf983-a5b1-5f0a-ab83-067fc76bcffe |  | note | Verification Activity - H
label | f589be2b-bdcf-5825-b553-dac0aa9a08c9 |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.1.9 - Manhole Foundation Compliance
label | 677d09e1-70bc-5ef1-9c4a-0ad3a5e67cd3 |  | note | Acceptance / Conformance Criteria - Granular Material: Scala 3 blows/100mm Cohesive Material: Vane Shear Strength 70kPa Engineer to confirm undercut depth (If Required)
label | cf849772-ecad-55b4-aa02-0b5fce719a44 |  | note | Standard / Specification - Project Specification 4.3
label | 5aa1ed71-ef58-55c3-983f-29ac1d35e5bc |  | note | Verifying Document - IANZ Scala test result
label | 5c3f2d8c-1fcb-59cf-9887-729cde761a98 |  | note | Frequency - 1 Test/Manhole
label | 97cdda2f-e76e-5655-840e-23cadfc13db6 |  | note | Verification Activity - H
label | f7a9b1b8-70e2-5f25-84bf-26b7e30c2455 |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.1.10 - Undercut Backfill Compliance
label | f5d28d44-e770-5c37-9b43-0262b26bcf56 |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Minimum Compaction 95%(Average 98%) of MDD
label | e237cff0-422d-5a3e-b95b-96ef53bed8f3 |  | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 3725:2012
label | fd7aba61-0d96-53cc-97eb-5cde4f3d2ba1 |  | note | Verifying Document - IANZ Lab Test Report
label | 6fe58900-5a8b-50d7-ab64-590c7c065ad2 |  | note | Frequency - 1 Test/Manhole if Undercut required
label | 800b5487-1c28-541a-8329-d8a94d8e400c |  | note | Verification Activity - H
label | 917fbdb0-418e-5466-a6fe-b12d3fa9290d |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.1.11 - Bedding Compaction Testing
label | 2d183ad2-6329-5085-8bc5-13ac4e92f2d6 |  | note | Acceptance / Conformance Criteria - HS2 Bedding under pavement H2 Bedding outside pavement NDM Back Scatter Minimum Compaction 95%(Average 98%) of MDD
label | e1b29de3-a730-53c7-8d76-2d7e993deabb |  | note | Standard / Specification - HS2 backfill Non cohesive material - Minimum Density Index (DI) of 70 or 95% of MDD AS/NZS 3725:2012
label | aebdbf95-4e5e-5d9a-bab5-737c9a2935ba |  | note | Verifying Document - IANZ Lab Test Report
label | ccdc68b2-6f5b-5697-a585-59cc69549c59 |  | note | Frequency - 1 Test/Manhole
label | b4501a13-5213-5924-ad78-9145b0b42f90 |  | note | Verification Activity - H
label | f423f03e-2f08-5bb3-b771-74422f0c3e41 |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.1.12 - Backfill Inspection
label | 8dacf914-9b08-546f-a9e3-9b3fe5cc4935 |  | note | Acceptance / Conformance Criteria - Inspection of pipes prior to backfilling to ensure correct installation and that the joints are sealed. No damages caused to the manhole
label | 2b084272-b8b6-5df0-84fb-13f3de659b9a |  | note | Standard / Specification - Project Specification 4.3
label | 489cd81e-404c-5c4b-ba53-7198caa05a74 |  | note | Verifying Document - Photographs
label | ff693eec-23da-5e77-803d-4b7e0423c663 |  | note | Frequency - Continuous
label | fe61226b-e6d3-5623-88fe-7475c5d1ae37 |  | note | Verification Activity - S
label | 9dab9a60-219b-5f79-882e-27df70458dac |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 3.1.13 - Backfill Testing
label | fd68ce07-ed6f-58e1-b85d-f91538958ac6 |  | note | Acceptance / Conformance Criteria - NDM Direct Transmission with a probe depth of 300mm Testing to be completed on 500mm lifts of backfill - 95% of MDD at OMC. Minimum Compaction 95%(Average 98%) of MDD
label | 19760d10-412f-548c-9738-59448210c203 |  | note | Standard / Specification - MDD Average of 98% with minimum of 95% PS 4.5
label | 05f3cf0b-31a7-5f95-8904-b79bba7c79f0 |  | note | Verifying Document - IANZ Lab Test Report
label | da9eb4b7-f5d6-5ace-ba2d-717b88dfae8f |  | note | Frequency - 4 Density tests per layer at Quarter Points Around Structure
label | 3b9e8475-dca7-5e35-82ed-7a6cb0da0c7d |  | note | Verification Activity - H
label | 716af32b-ddd9-52de-8389-d6cab9845209 |  | note | Verification Activity - By: - QE
checkpoint-status |  |  | checkpoint | 3.1.14 - Low Air pressure Test of Pipeline
label | 66364606-a2c3-534e-ace6-3048f1d43445 |  | note | Acceptance / Conformance Criteria - Low Air Pressure Testing as per Appendix C2 NZS 4404 Refer to NZ/AS 2566.2 M5 (Constant pressure tests) "NTT 009"
label | de612459-5f70-5818-9692-8bde69981beb |  | note | Standard / Specification - Pump Air to 25kpa and maintain pressure for 3 minutes
label | d81c550e-1daa-5078-9784-1a7264ea80d5 |  | note | Verifying Document - Pressure Test Report
label | 9e335dd2-ef48-5369-8897-e27b45acb834 |  | note | Frequency - 1 Per Line
label | f35c8c92-2a0a-5072-9fde-de6d1b2d5141 |  | note | Verification Activity - H
label | 856a6127-b419-5d5b-b6e4-2b248fae3ec8 |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 3.1.15 - Manhole Vacuum Test
label | 00738fef-8cb6-51f0-87dd-c30b5c6b57c3 |  | note | Acceptance / Conformance Criteria - Manhole Leakage Test hold time as per Table 5-12
label | e87bf1ec-326e-58da-82df-2ee38be298c7 |  | note | Standard / Specification - Draw Vacuum of -254mm Hg
label | 3fcacb97-bdb6-5b03-be3c-d256bf3bce66 |  | note | Verifying Document - Vacuum Test Report
label | b50aef71-5614-53b4-bc87-a8e119ba010b |  | note | Frequency - 1 Per Manhole
label | 606da953-b867-5a2f-87be-2d07646604e2 |  | note | Verification Activity - H
label | 1aa57890-8a66-5cb1-b2f5-79a96fc4593f |  | note | Verification Activity - By: - PE
checkpoint-group |  |  | section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.2 CCTV & Reinstatement
checkpoint-status |  |  | checkpoint | 3.2.1 - CCTV Inspection
label | 49f7fb21-4d94-5678-95fe-f78b9df17770 |  | note | Acceptance / Conformance Criteria - Quality Check on New Works
label | 915e5944-4095-5105-869c-b21edf93b491 |  | note | Standard / Specification - Project Specification 4.4 NZ Pipe Inspection Manual
label | 9f223a2a-a09e-5164-a383-f07deaf708cc |  | note | Verifying Document - CCTV Report
label | bfc6f1be-dacf-5632-8129-6326a89ba06b |  | note | Frequency - 1 per line
label | 5811b338-c224-5676-8dfd-eb01666d8fb5 |  | note | Verification Activity - S
label | d67a37a1-99ff-58c0-a5d0-99876a68a702 |  | note | Verification Activity - By: - PE
checkpoint-status |  |  | checkpoint | 3.2.2 - Reinstatement
label | d84a7d3f-8416-5520-9539-6112b4667f48 |  | note | Acceptance / Conformance Criteria - Quality Check on New Works/All the MH Lids and Cesspit Levels should align with the pavement specification in terms of level & alignment
label | e1ade64f-2cba-5b1a-b0bc-5b8923388c1a |  | note | Standard / Specification - Reinstate and Tie into existing surrounds
label | 7a7a35f1-5faa-523e-b6ef-c17b9712f2e8 |  | note | Verifying Document - Photographs & Level Checks
label | 2a9de3dd-83d1-5702-bc8a-b157cdfdfc7b |  | note | Frequency - Continuous
label | 5e940cb0-86cd-5929-bcdd-a32bb4e182a2 |  | note | Verification Activity - S
label | 861e3c21-a38e-5d21-88fb-f33e9ed47378 |  | note | Verification Activity - By: - PE
checkpoint-group |  |  | section | SECTION 4 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint-status |  |  | checkpoint | 4.1 - Survey As-Builts
label | 591e64be-7b5b-5756-ba5c-5c480cb802b9 |  | note | Acceptance / Conformance Criteria - Quality Check on New Works based on the tolerances in RITS
label | 88b6021a-3110-5045-8d91-2e60fb1249e0 |  | note | Standard / Specification - Project Specification
label | 7237c198-5606-5126-876a-6ef80ae0fee9 |  | note | Verifying Document - Survey Data As Built Drawings Photographs Red-Pen Asbuilt Including Undercut Sections
label | 33e15c37-82ba-5b45-b3a6-055493fdfcdb |  | note | Frequency - Post works completion
label | 394dac1e-4d42-5da3-b3eb-6cd692c55060 |  | note | Verification Activity - H
label | 71d6ef71-a603-5a9e-92cb-01a6dfd75c70 |  | note | Verification Activity - By: - SV
checklist-flat |  |  | checklist | Stone Strong Wall Installation Checklist |  |  |  |  | Yes | Stone Strong Wall Installation Checklist | c6d03f27-e77e-4918-8777-b48ae7f56392
checkpoint-no-status |  |  | checkpoint | Details
text | 5c56ea41-624d-5f8b-a19d-09dc67614506 |  | textbox | Project Name:
text | 19e4224b-ed62-5e46-a533-cec42e4dac20 |  | textbox | Wall Location:
text | 6d6bf996-b548-5dd9-9ee0-d917dd2be190 |  | textbox | Block Layer:
text | e07570dd-33f5-585f-8141-e6b9b1e94af6 |  | textbox | Date:
text | 3453d87e-9319-54a9-acf6-8e0f2f4739a6 |  | textbox | Inspector:
text | 0692e518-3045-51d8-be5c-39c62e4d3b14 |  | textbox | RL of current Block/Backfill Layer:
checkpoint-status |  |  | checkpoint | Level foundation installed as per design. (Base layer only)
checkpoint-status |  |  | checkpoint | 2 x Drainage pipe wraped in filter sock to be installed along the external perimeter of the Load Tramsfer Platform. (Base layer only)
checkpoint-status |  |  | checkpoint | Blocks Installed within specification tollerances & block pattern as per design drawings
label | 0dd331a6-905b-520f-85e7-1d0e1611df25 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | 5e72637e-18b2-53de-82ca-d91284388021 |  | note | Table 4: MSE Tolerances
label | 807cb619-9421-5d28-ab8c-bf2da6ee9b5c |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | e72d7e9e-6340-547b-aadd-a6cedcd6e744 |  | note | Element ¦¦ Vertical Position ¦¦ Horizontal Position ¦¦ Vertical Alignment ¦¦ Horizontal Alignment
label | 981f8e13-85e0-5ab8-88d3-a29a943532b7 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | 3747f6c4-c6b4-53db-b0a0-918d1038abda |  | note | Soil Surface ¦¦ ± 100mm ¦¦ N/A ¦¦ N/A ¦¦ N/A
label | 02105b15-4ea8-52aa-aa5d-d219414087e5 |  | note | Facings and wall structures ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
label | 7fb962c8-aa6b-57e4-980c-845ee2b51feb |  | note | Footings or supports ¦¦ ± 50mm ¦¦ ± 50mm ¦¦ ± 20mm in 3m ¦¦ ± 20mm in 3m
checkpoint-status |  |  | checkpoint | The correct number & length of parawebs are to be installed as shown on the construction drawings.
label | d1b9a8dd-3c74-5dd8-92ee-ba464e7bfa9c |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | cb25453d-184c-5806-8454-04709ba3e357 |  | note | 24SF1.1 BLOCK PARAWEB SCHEDULE
label | 917cf7ae-3f1c-5095-a6af-1e72e4cc8863 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | 8e09984d-6f0d-50f2-abb9-cdcc9fa850cd |  | note | WALL HEIGHT (H) ¦¦ MINIMUM EMBEDMENT DEPTH (E) ¦¦ GRID LENGTH (L)* ¦¦ CONNECTIONS PER BLOCK
label | 571b4987-9d20-5db7-94d0-56578e113fa8 |  | note | – – – – – – – – – – – – – – – – – – – – – – – – – –
label | cc38ae48-88bf-57fa-ba2d-32f679a79148 |  | note | 8.0-10.0 ¦¦ 0.5 ¦¦ 9.0 ¦¦ 4
label | a0f36527-892e-5c8d-868f-3b82ab3d24a3 |  | note | 6.0 - 8.0 ¦¦ 0.5 ¦¦ 7.0 ¦¦ 4
label | bd88976d-5723-503a-aab2-1dfe67a9ad8c |  | note | 4.0 - 6.0 ¦¦ 0.5 ¦¦ 5.0 ¦¦ 4
label | 31674d68-f150-5e7a-abb3-b80d5b50c9a3 |  | note | 2.0 - 4.0 ¦¦ 0.5 ¦¦ 4.0 ¦¦ 4
label | 2ab1aa36-57c5-574a-9159-853a9471fcc3 |  | note | 0 - 2.0 ¦¦ 0.5 ¦¦ 3.0 ¦¦ 4
checkpoint-status |  |  | checkpoint | Paraweb is to be placed flat or with a 1% fall toward the rear of the wall.
label | 21d51e76-0781-5346-b566-b7bce9497e97 |  | note | ○ Paraweb must be free of wrinkles and lightly tensioned prior to and during placement of backfill. Shallow trench to be dug toward the end of the paraweb, pin to be used to pull paraweb taught prior to backfilling.
checkpoint-status |  |  | checkpoint | 150mm of fill cover is required before construction equipment can travel over the area
checkpoint-status |  |  | checkpoint | Backfill installed in max 250mm lifts
checkpoint-status |  |  | checkpoint | Proof roll completed on each layer
checkpoint-status |  |  | checkpoint | NDM testing completed
label | 313e95ff-a74a-5cd3-aca0-96fdfe23b44f |  | note | ○ Acceptance Criteria: Minimum 95% MDD
label | 18e05c73-4c1f-5444-a747-bda68ed498d4 |  | note | ○ Frequency: 1 per 500m3 with at least 1 test per 0.5m lift per 20m run of wall
checkpoint-status |  |  | checkpoint | Clegg testing completed (GAP65 only)
label | 1fa82988-8f1e-568e-9501-5d1fa85b3509 |  | note | ○ Acceptance Criteria: CIV relationship to be developed by testing alongside NDM tests
label | 6aadb3eb-b399-5f77-82e1-875f5b6abe9a |  | note | ○ Frequency: 4 tests per NDM
checkpoint-status |  |  | checkpoint | Scala testing completed (Sand only)
label | de471c65-92b2-5be9-8242-ab26586fb500 |  | note | ○ Acceptance Criteria: Minimum average value over 5 tests of 5 blows per 100mm, minimum single value of 4 blows per 100mm
label | 0d72fa89-8dc8-5a3d-9dd5-e8a34b2db867 |  | note | ○ Frequency: 1 per 500m3, 1 test per 0.5m lift per 20m run of wall
checkpoint-no-status |  |  | checkpoint | ADDITIONAL NOTES:
text | 81dd5416-d172-51ad-8781-a20c3ac7e029 |  | textbox
checklist-sectioned |  |  | checklist | ITP - Earthworks |  |  |  |  | Yes | ITP - Earthworks | c81579b7-fafa-4f2f-8de6-dd90cc97d798
checkpoint-group |  |  | section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 3.04 Site Requirements
checkpoint-status |  |  | checkpoint | 3.04.01 - Construction Pack
label | bfee9e2d-a6b7-5f70-91c0-be5382ad9749 |  | note | Acceptance / Conformance Criteria - Submit a Construction Pack including a Methodology and JESA to the Engineer before works
label | 73019707-9e2c-534c-a05b-3fcde5672553 |  | note | Standard / Specification - Downer
label | fc46177b-d6da-5e5f-b473-8975092b2048 |  | note | Verifying Document - Construction Pack
label | cf028689-ebb3-5192-9152-61a6781b2e1b |  | note | Frequency - Submit 10 days prior to commencement of works
label | 1053d10a-8bc4-5c7e-b34e-717289b9bdf0 |  | note | Verification Activity - H
label | 769b19e6-25c2-51ef-b6c5-d49c93eb7c7b |  | note | Verification Activity By - PE
checkpoint-status |  |  | checkpoint | 3.04.02 - Survey Setout
label | cf831fa4-9e72-5f6f-93bc-7b92ee6d3e7a |  | note | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | 51686e4f-ea10-57de-b465-280fbf293317 |  | note | Standard / Specification - Downer
label | a56c6f04-de46-5fb8-aa75-7917dc94c8f6 |  | note | Verifying Document - Survey Records
label | 77d6aa06-edd2-51e5-b4d1-f50385252962 |  | note | Frequency - Prior to Works
label | e9e2ae26-142d-55ca-80ae-2a4d6a362454 |  | note | Verification Activity - H
label | 5ac007ba-46a3-5bdd-84ea-5f8829d48733 |  | note | Verification Activity By - SV
checkpoint-status |  |  | checkpoint | 3.04.03 - Approved Construction Drawings
label | adac429a-f7e2-5e63-80d0-730d50cbd484 |  | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | 3b02b1a1-aed9-5211-a134-9a04eeffc8ce |  | note | Standard / Specification - Downer
label | 3fdf891e-3ead-5017-b89f-18cf138d101c |  | note | Verifying Document - IFC Drawings
label | 4173a28d-0312-5795-9c8c-5dbbcc1476d8 |  | note | Frequency - Prior to works start
label | cfa53cbe-96bf-5d97-a692-51a01ce4fd25 |  | note | Verification Activity - H
label | 457bb499-0401-57d1-a2a5-f9335bba738f |  | note | Verification Activity By - PE
checkpoint-status |  |  | checkpoint | 3.04.05 - Topographic surveys for measurement
label | b0ac2514-a724-594e-9ebc-d4a1ce86bf41 |  | note | Acceptance / Conformance Criteria - The Contractor shall provide topographic survey reports and electronic survey models (in a dxf or dwg format) to enable the Engineer to verify quantities.
label | aa70e3c8-aabb-5a4e-bbe9-5a344f485278 |  | note | Standard / Specification - PS 2.2.12
label | f4e73635-e745-53ec-9c27-42e5b3f88ffa |  | note | Verifying Document - As-built
label | c95d9ef2-4b07-5466-a47b-37893c42864a |  | note | Frequency - Prior to works and Post Works
label | e0c41ef4-e1d7-542e-b948-53432b22e03a |  | note | Verification Activity - H
label | 666286b2-083d-59cc-9c48-2306a176d1d0 |  | note | Verification Activity By - PE
checkpoint-status |  |  | checkpoint | 3.04.06 - Permits
label | 1086a7b0-b8fe-576d-8430-21b79737c40c |  | note | Acceptance / Conformance Criteria - The contractor shall complete internal and external permits for construction requirements
label | 5795d95a-16ee-5ff4-9521-bbea691dbe15 |  | note | Standard / Specification - ITP Register
label | abf5a4ad-1f5e-5db4-adc9-de90fce74b16 |  | note | Verifying Document - ITP Sign Off
label | d59d5929-0aa7-5d0b-89cb-e4bd1357d609 |  | note | Frequency - Prior to commencement of construction activity
label | 4c981c6f-8b77-5d6e-8556-3aabf085e93c |  | note | Verification Activity - R
label | 412821e0-a96c-5a47-92ad-7cf6c94f8d6b |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 3.04.07 - Stakeholder Management
label | 07f0300b-dee9-5f28-9128-a0d9daf1509f |  | note | Acceptance / Conformance Criteria - Inform stakeholders of upcoming works Agree plans for maintaining access to properties during construction with landowners
label | 66cd92a6-7a53-540f-9e88-afdef00c9aed |  | note | Standard / Specification - Project Stakeholder Management Plan
label | e422661f-e345-5a54-8688-d7cd237acb92 |  | note | Verifying Document - ITP Sign Off
label | 4b556bcf-42b1-56a5-bfdf-aff9f8fc919d |  | note | Frequency - Prior to Construction with continue updates throughout the works
label | b486a5da-ac9f-5a37-89a1-e4205d6f2fb7 |  | note | Verification Activity - R
label | f1c12282-a223-563a-b4af-025210d3be65 |  | note | Verification Activity By - SE
checkpoint-group |  |  | section | 3.05 Engineer Nominated Hold Points (Engineer’s inspections)
checkpoint-status |  |  | checkpoint | 3.05.01 - Environmental Controls Inspection
label | 220fb01b-d745-5045-be14-134205e9c4ca |  | note | Acceptance / Conformance Criteria - After installing measures to meet environmental requirements, before any earthworks begin.
label | 12810a36-7076-5fa3-9309-fa15bd838414 |  | note | Standard / Specification - PS 2.2.16
label | b6e38161-1c28-58dd-8003-e06fc54c07b5 |  | note | Verifying Document - Site Records
label | 2468b7fa-2b30-5143-9a17-d0cf723c63b6 |  | note | Frequency - Min 48h Notice
label | 82fc3266-7242-50e7-adfc-5b87a9456b0a |  | note | Verification Activity - HP
label | 6fe76645-582f-5023-93da-ab8501b34efd |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-status |  |  | checkpoint | 3.05.02 - Bulk Fill Inspection
label | 39705f9c-e934-5b3b-8800-e537f4d47d3c |  | note | Acceptance / Conformance Criteria - Prior to beginning bulk filling operations.
label | bd28e4f6-5513-5ca5-b0b9-8f398af9b0bf |  | note | Standard / Specification - PS 2.2.16
label | 7f620750-7037-5f90-b423-8458b93e4bfd |  | note | Verifying Document - Site Records
label | 4cc87978-3af0-54f2-a37c-2861c60b4f3f |  | note | Frequency - Min 48h Notice
label | bcaf12cf-0efa-51ad-9ded-5b8f62c0353f |  | note | Verification Activity - HP
label | 4c8ec7d8-3e90-5a24-957b-45c963ead5e2 |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-status |  |  | checkpoint | 3.05.03 - Service Ducting Bedding Inspection
label | 57a8445d-fd38-5977-b749-a3db5394a8c6 |  | note | Acceptance / Conformance Criteria - Prior to laying any service duct, drainage/water/sewer pipeline and associated pits, fittings and structures
label | 0bd2a218-cf77-58c3-be8b-00842a9fa36c |  | note | Standard / Specification - PS 2.2.16
label | 241bcb23-ff2f-5e2e-bd32-1b66435db087 |  | note | Verifying Document - Site Records/ Refer to Services ITP for testing requirements
label | 305f24c2-0703-584a-9e40-ce3157339d1e |  | note | Frequency - Min 48h Notice
label | 1bc05559-a503-5c5f-8fd1-27d0207c0609 |  | note | Verification Activity - W
label | f5ac7004-e040-5094-b259-35cbbf4b3574 |  | note | Verification Activity By - ENG
checkpoint-status |  |  | checkpoint | 3.05.04 - Service Ducting Backfill Inspection
label | 7e4a7988-03c3-5c7e-87af-ed5a4d520a43 |  | note | Acceptance / Conformance Criteria - After laying, before backfilling any service duct, drainage/water/sewer pipeline and associated pits, fittings and structures.
label | 5397b13e-25a0-53f7-90e6-21d21174ffa1 |  | note | Standard / Specification - PS 2.2.16
label | 38f7b901-ce61-5b82-ba86-2c9d95552aab |  | note | Verifying Document - Site Records/ Refer to Services ITP for testing requirements
label | e019faaf-8fe0-58e4-a4b1-8950d688b682 |  | note | Frequency - Min 48h Notice
label | d6a597bf-c1ae-5f05-a332-0e409159e8ac |  | note | Verification Activity - W
label | 9abd5920-382a-5c80-a2b5-d604334cd91e |  | note | Verification Activity By - ENG
checkpoint-status |  |  | checkpoint | 3.05.05 - Geotextile Inspection
label | 30235357-ba2a-5d0d-bf32-e108465a9ab7 |  | note | Acceptance / Conformance Criteria - Before placement of any geotextile.
label | af850139-ab11-59d3-8d6a-5ded512dd2e8 |  | note | Standard / Specification - PS 2.2.16
label | 0ce6ff77-7be6-5200-8852-5d53e2272e01 |  | note | Verifying Document - Site Records
label | 5cc966d5-e906-56ef-8ad4-2635435e73de |  | note | Frequency - Min 48h Notice
label | 2e6fd158-bfe1-590a-9fbb-55341e4c9b58 |  | note | Verification Activity - HP
label | f63cd949-8628-5163-86d2-5e2ab51aae46 |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-status |  |  | checkpoint | 3.05.06 - Subgrade Inspection
label | bea3bd3e-1a67-59b3-b150-ca5c3595fab9 |  | note | Acceptance / Conformance Criteria - Subgrade inspection/stripped surface inspection, to include proof roll, scalar penetrometer and/or shear vanes.
label | 70fc358c-d354-5c6c-8df9-908d48a52f10 |  | note | Standard / Specification - PS 2.2.16
label | 714db9ad-f46f-52ef-a07e-a27fc0f7ea8d |  | note | Verifying Document - Site Records/ Test Results
label | 089e3007-f9b2-53da-8767-6fb0c3a01dd8 |  | note | Frequency - After surface is stripped
label | 40c00e8f-59e9-50f6-b11f-195e2cab0563 |  | note | Verification Activity - HP
label | fb26b3b6-d7be-55a5-b920-f8455c493cc5 |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-status |  |  | checkpoint | 3.05.07 - Undercut Inspection
label | 205f430b-1d40-5338-820a-fc895c69c6b2 |  | note | Acceptance / Conformance Criteria - Undercut (if required) inspection, to include proof roll, scalar penetrometer and/or shear vanes.
label | 04d27b24-5e7b-5476-a7ea-cd82483eb3f5 |  | note | Standard / Specification - PS 2.2.16
label | 65d11e86-28dd-584c-80fe-f09a9af7f41b |  | note | Verifying Document - Site Records/ Test Results
label | 3ff38dd2-5471-58e4-ae4a-e9a347932bd0 |  | note | Frequency - Prior to Subgrade Fill
label | cc051a3c-b0ae-58ed-85a3-2f3963327f46 |  | note | Verification Activity - HP
label | 1feae0c2-2658-5f77-98b9-3f71b3aea196 |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-status |  |  | checkpoint | 3.05.08 - Settlement Monitoring
label | 977450d1-fc9f-55e5-817a-1b9283275032 |  | note | Acceptance / Conformance Criteria - Settlement monitoring (Settlement pins & Targets) to be assessed by Geotechnical Engineer.
label | 6d2a8eb6-7a7b-5db6-b4f9-6b3941313504 |  | note | Standard / Specification - Drawing 5200
label | 70cf0c56-fdd1-5590-bef1-518c0f108a8c |  | note | Verifying Document - Site Records
label | 1a1b650a-d510-553b-b01c-32e36162d83f |  | note | Frequency - Prior to constructing pavement and wall
label | f7da49b3-2c9b-5dd0-bd85-3aeaf35709bb |  | note | Verification Activity - HP
label | 111c8e86-e703-5fd2-8eb8-e9bc46da9b4a |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-status |  |  | checkpoint | 3.05.09 - Subgrade Fill
label | 3b6d39e4-aded-5525-9a05-2f3ba7d4111b |  | note | Acceptance / Conformance Criteria - Inspection of completion of sub grade fill prior to placing SIL, to include proof roll.
label | 1e9e7ca8-b008-5387-b5a7-47972e295356 |  | note | Standard / Specification - PS 2.2.16
label | 53267922-2588-5542-83ec-dcce3f7fd14f |  | note | Verifying Document - Site Records
label | 9c59b01f-1e26-5caf-bc10-e68acc082366 |  | note | Frequency - Prior to placing SIL
label | c72eeff7-163c-5f7e-80c2-3f277204adcb |  | note | Verification Activity - HP
label | a33638a4-2802-5015-8b04-2758f810735c |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-group |  |  | section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - Earthworks General Materials
checkpoint-status |  |  | checkpoint | Imported Fill Approval
label | 45fd01c7-e910-54d4-bec7-c51dc5e869fb |  | note | Acceptance / Conformance Criteria - Due to the fill-deficit on this project, imported fill will be required and should be discussed with and approved by the Engineer to verify its appropriateness and quality control testing requirements prior to use.
label | 00224ad9-b44c-5c64-925b-0bdf2c3ad0b9 |  | note | Standard / Specification - GWS 2.4.1
label | 034eb994-bff4-5dce-a8f5-5ca2e39e8efb |  | note | Verifying Document - Lab Tests
label | 7bda6704-2e88-5a6c-903a-5abc136f5367 |  | note | Frequency - At least 2 days prior to placement and compaction.
label | be698d53-8e18-584e-b59e-5008a430fece |  | note | Verification Activity - HP
label | 1b3a4554-bdab-544a-b0fe-2f429c05b292 |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-status |  |  | checkpoint | Re-Use Suitability Approval
label | 41060b61-19fa-58c6-8795-3e53e1d8ca7d |  | note | Acceptance / Conformance Criteria - The Contractor shall test representative samples of the site-won material to be used as Bulk Fill and Subgrade Fill and the results are to be sent to the Engineer for approval.
label | 71239f25-057a-5495-a65b-8059f502eb40 |  | note | Standard / Specification - GWS 2.4.2.1
label | 91ac6848-60d0-5318-9a00-ed4c631f5ddb |  | note | Verifying Document - MDD, OMC, Shear Vane, PSD
label | 51318647-1fc0-5090-a5bb-df5e632715e4 |  | note | Frequency - At least 2 days prior to placement and compaction.
label | 4017e19b-6c59-58e0-a358-c2fb46c5bd2f |  | note | Verification Activity - HP
label | 2738daad-13e6-56e2-850b-dbfe698f6491 |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-status |  |  | checkpoint | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
label | 13cb71d6-c1af-54a6-b7bd-21510996a303 |  | note | Standard / Specification - GWS
checkpoint-status |  |  | checkpoint | Eastern Gully Weir Cohesive Fill Material Testing
label | 7e475385-e59b-545a-a386-0317f85d7e4f |  | note | Acceptance / Conformance Criteria - Eastern Gully Weir Fill shall be tested for Standard Compaction, Solid Density, Plasticity Index (PI), Particle Size Distribution, and Liquid Limit for
label | 5599aacf-9b19-556b-8071-03ee88a79288 |  | note | Standard / Specification - GWS 2.9.4
label | 291d7143-24d1-5bea-a541-b52e6e678f66 |  | note | Verifying Document - Test Results
label | c80900c5-6f26-514c-925c-08033d42fde0 |  | note | Frequency - At least 2 days prior to placement and compaction.
label | 5e1dd57d-db29-5032-93c2-fc611966f113 |  | note | Verification Activity - I
label | 2acb792c-7756-591a-9291-3d52f360c47d |  | note | Verification Activity By - SE
checkpoint-group |  |  | section | Subsoil Drainage
checkpoint-status |  |  | checkpoint | Subsoil Pipes
label | 3f94bf73-bf5b-5437-9da8-17e3ae97576d |  | note | Acceptance / Conformance Criteria - Drainage pipes used in subsoil drainage shall be smooth bore perforated corrugated 160mm diameter complying with NZTA F5 unless otherwise stated on the drawings. Pipes shall not have a geofabric filter sock unless requested by the Engineer.
label | f9a94957-2d43-5bcb-b341-3538bb894ea7 |  | note | Standard / Specification - GWS 3.2.1
label | b629c8f6-6dfd-5ea2-b72e-17917646bbc1 |  | note | Verifying Document - Datasheet
label | f4e1f338-8fa7-504b-a4cb-56b41896398e |  | note | Frequency - Prior to installation
label | 1a71e582-8f83-564e-92ab-12f86985a0e1 |  | note | Verification Activity - C
label | 33c9ad80-23dd-5d83-a970-60e5f6105c12 |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | Subsoil Drainage Aggregate
label | 157dd5fd-3914-5a7d-b6cd-82a7e9a4aafb |  | note | Acceptance / Conformance Criteria - When placing geotextile wrapped drainage aggregate, the drainage material shall be in accordance with TNZ F/6 including gradings
label | aa2baf26-c5d7-5049-ab44-ef2f743b3ebe |  | note | Standard / Specification - GWS 3.2.2 & 3.4
label | 1248aa8d-7bc1-58cb-a514-3c47b2467f19 |  | note | Verifying Document - PSD, CR
label | 7a23c5b4-57d0-5aa9-9f7e-07c02b92409f |  | note | Frequency - Prior to installation
label | 5e0a201a-911e-5ee8-b97a-d9332fbdcfe8 |  | note | Verification Activity - C
label | 506f0618-6e1c-5102-87bc-d361e1022c7b |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | Filter Cloth
label | 40786ed1-1abb-5eab-b26d-821b1c62bf75 |  | note | Acceptance / Conformance Criteria - Any filter cloth surround specified on the drawings shall meet the requirements of Transit Specification TNZ/F7, Filtration Class 2 and Strength Class B unless otherwise specified on the drawings.
label | a0219122-25d9-528f-ae9a-22dbaf87c7a8 |  | note | Standard / Specification - GWS 3.2.3
label | f610f319-f379-53fa-8154-8b4d5bca6c13 |  | note | Verifying Document - Datasheet
label | 2e3e366f-ba60-5836-9a55-28f1ba3a5d70 |  | note | Frequency - Every 1,000m3. At least two weeks prior to works.
label | 951ef335-8d62-5c06-be73-7eec18ac3d1f |  | note | Verification Activity - C
label | fe3a95d8-88a3-576f-aa42-613286c0653d |  | note | Verification Activity By - SE
checkpoint-group |  |  | section | Geotextile and Geogrid
checkpoint-status |  |  | checkpoint | Geotextile Approval
label | 9a3d2597-ebe2-539a-aa42-61368c2611c3 |  | note | Acceptance / Conformance Criteria - The Contractor shall submit to the Engineer for approval the details of the filter fabric they propose to use at least two weeks prior to commencement of works, including compliance certificates.
label | a79a093a-64b5-5be4-812d-9f9f7aa9450c |  | note | Standard / Specification - GWS 4.1
label | 561e97cf-103c-5838-ac55-be14acc86d5e |  | note | Verifying Document - Compliance certificates
label | 79bd7770-6037-5577-8954-1c2bdc4582d9 |  | note | Frequency - At least two weeks prior to works
label | 067be5b6-4d6d-5483-92ea-3e46a124d9a9 |  | note | Verification Activity - HP
label | 967372ea-a3a3-54c8-9a64-18ddb723d059 |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-status |  |  | checkpoint | Uniaxial, Biaxial and Triaxial Geogrid
label | 20af9f1b-6c10-5787-a2c6-f3c6221c2cc6 |  | note | Acceptance / Conformance Criteria - All uniaxial, biaxial and triaxial geogrid shall be manufactured in accordance with a management system that complies with BS EN ISO 9001 and BS 14001 and shall submit to the Engineer for approval.
label | ef41addc-1cbe-5c0d-9ca5-8d1ef6fdbe67 |  | note | Standard / Specification - GWS 4.2
label | 0c7958a6-3ee8-5743-b5ce-19e007a5a8f6 |  | note | Verifying Document - Datasheet
label | 913b2d66-4c18-5767-a5e9-17b67944114f |  | note | Frequency - At least two weeks prior to works.
label | aea6a083-cef0-5f4f-85d7-58111f8e5b2e |  | note | Verification Activity - HP
label | 2fb75c33-4757-5988-8eb9-2f85068131e8 |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-group |  |  | section | Settlement Monitoring
checkpoint-status |  |  | checkpoint | Settlement Baseplate Design
label | b2e13714-0793-5134-9aba-dff3f3e49e11 |  | note | Acceptance / Conformance Criteria - Equipment shall consist of 600mm x 600mm base plate (typically 20mm thickness),150mm PVC duct, 32mm diameter threaded bar with couplers for extensions at 1m intervals and waratahs and coloured flagging for protection following installation.
label | ab58a620-29e1-5cd5-9913-2c7857009c45 |  | note | Standard / Specification - GWS 6.2
label | 9dc5bee6-37ba-5834-afe8-f7ef22fcf6eb |  | note | Verifying Document - Datasheet
label | 177044c2-7b5a-56d8-b467-6a11c2a05f8d |  | note | Frequency - Prior to installation
label | 38c7b763-7106-5ffc-9cab-8f619cc54550 |  | note | Verification Activity - I
label | 9d733ae1-3eec-549d-8aba-40c2e14e2c81 |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | Settlement Pin Design
label | 4993c9e1-6514-5af4-8698-bf4bb1ef0f04 |  | note | Acceptance / Conformance Criteria - Settlement pins are to comprise 32mm diameter Reidbar rods driven a minimum depth of 0.5m into the ground surface. The top of the pin shall be domed to ensure repeatable survey measurements.
label | 8280e55b-aaec-5527-b3ea-2bd24da7ac4e |  | note | Standard / Specification - GWS 6.3
label | 6a86ff42-72c4-56ff-9fe0-eff5fd9492fd |  | note | Verifying Document - Datasheet
label | f069dae9-7360-5fcb-a785-701687cc1afc |  | note | Frequency - Installed within 24 hours of reaching design subgrade level
label | c73ca30a-597f-5a40-b41f-829e4cedbddd |  | note | Verification Activity - I
label | 33be6f18-8792-5920-bf9d-de4009c5069b |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | Settlement Pin Bedding
label | 2e1cfb65-6bc6-5474-a42d-b8ec2e0429ff |  | note | Acceptance / Conformance Criteria - Installation of the settlement markers shall occur at the base of the fill embankment, prior to placement of any fill. They shall be installed on a 100mm thick sand layer to form an even and smooth foundation which will be levelled using a spirit level.
label | 2e80c0cf-b430-5cf6-8078-e90a77e6de23 |  | note | Standard / Specification - GWS 6.2
label | bb88f167-2eac-5ea1-a07a-4edb43311454 |  | note | Verifying Document - Site Record
label | 433e324e-7e70-5607-946b-81fc02328d45 |  | note | Frequency - Prior to placement of fill
label | f0211247-806a-5652-b84e-408b2ce9da48 |  | note | Verification Activity - I
label | 8c69d77c-c146-5a3b-9c0b-2d63827771a2 |  | note | Verification Activity By - SE
checkpoint-group |  |  | section | SECTION 5 – CONSTRUCTION ACTIVITY – CLEARING - 5.01 Demolition / Site Clearance
checkpoint-status |  |  | checkpoint | 5.01.01 - Clearing
label | 78082b3a-e12b-5c21-a358-53d24b788896 |  | note | Acceptance / Conformance Criteria - All surface objects including fences, gates, debris, wood, dumped rubbish, concrete and other protruding obstructions shall be cleared and disposed of
label | 9da1e544-eed3-519d-91c1-83240462c755 |  | note | Standard / Specification - PS 3.1
label | b50dac47-4fde-59b0-813f-56d6371997cc |  | note | Verifying Document - Site Records
label | a64d2405-c9fc-5811-a16d-dfcafa596de9 |  | note | Frequency - Prior to earthworks
label | 1ca5d8fa-084f-53ca-b716-8880263ff1fd |  | note | Verification Activity - C
label | 783b14cd-f41b-5af2-ab9a-9cdee83f416d |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 5.01.02 - Demolition
label | 898e6b66-9ffd-5630-8dcf-66d7cdd5cb4e |  | note | Acceptance / Conformance Criteria - Remove all buildings from the site including foundations, buried services and any other remnants.
label | 1e4b5000-6877-5ca4-84b0-743bc492ac42 |  | note | Standard / Specification - PS 3.2
label | 24b04cf3-b6ce-5360-8034-99e455efb90d |  | note | Verifying Document - Site Records
label | 0f5cac53-5c09-5007-b349-9f02b07fb230 |  | note | Frequency - Prior to earthworks
label | 676ec549-3b82-5463-b42f-70db12e7831d |  | note | Verification Activity - C
label | 0937604e-d956-5db1-bf39-00d54c56fc50 |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 5.01.03 - Septic tanks
label | f8c973f8-deef-5746-94a7-f251b5a2a71d |  | note | Acceptance / Conformance Criteria - Septic tanks shall be pumped out prior to removal and backfilling
label | b49d37c8-cb6e-501b-a4fc-a478b803a512 |  | note | Standard / Specification - PS 3.2
label | df2c9c6a-22a3-5041-8d6d-32a328bfb5ce |  | note | Verifying Document - Site Records
label | c6bf3dbd-30cf-5317-9142-90b0a2dd1c2d |  | note | Frequency - Prior to earthworks
label | f5499a7d-03ba-57c9-b1ef-2012a2864ca5 |  | note | Verification Activity - C
label | c011ed82-15bf-5f55-9f4c-d8313d37f9ce |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 5.01.04 - Plant Clearance
label | 6d4d6e9c-4028-5c04-8cc4-6787c37ba964 |  | note | Acceptance / Conformance Criteria - Vegetation, Tree stumps, shrubs, plants, logs, including any roots greater than 25mm in diameter shall be cleared and disposed of
label | e513f065-fdac-5f75-a44b-2e4108a6638a |  | note | Standard / Specification - GWS 2.5
label | 89f3f0b4-9bed-5b89-9ee8-bc47e57cad46 |  | note | Verifying Document - Site Records
label | dfdf7fa0-228d-51d6-a8d7-2b99f126969c |  | note | Frequency - Prior to earthworks
label | 705917af-f81b-547e-848b-02cbfb8e0005 |  | note | Verification Activity - C
label | 88634bea-cf7c-5452-9202-e6787e9c447d |  | note | Verification Activity By - SE
checkpoint-group |  |  | section | SECTION 6 – CONSTRUCTION ACTIVITY – EARTHWORKS - Earthworks General
checkpoint-status |  |  | checkpoint | 6.1.1 - Groundwater Management
label | eb0e86e5-e733-5223-bbb9-927510d23d9b |  | note | Acceptance / Conformance Criteria - The Contractor shall provide all pumping plant and drainage systems required to ensure excavations are always free from water.
label | 7e7617fa-fae5-5875-b604-3d92f1ae9a02 |  | note | Standard / Specification - PS 3.4
label | e28a6666-2864-58ac-b2be-d03fe009182d |  | note | Verifying Document - Correspondence
label | 3c59ca22-9750-56f4-9528-71508147a1a2 |  | note | Frequency - Prior to excavation
label | 963a9310-1758-5ef2-b107-9ca62263c7a2 |  | note | Verification Activity - W
label | 6dad533d-9d56-562d-a873-7ac544b09ff9 |  | note | Verification Activity By - ENG
checkpoint-status |  |  | checkpoint | 6.1.2 - Cut to Waste Approval
label | 4d18e52c-8158-562d-a166-7fae841d5a02 |  | note | Acceptance / Conformance Criteria - The Contractor shall obtain written approval from the Engineer prior to cutting any material to waste. To include evidence and extents of cut to waste. Topography survey data of all material to leave site, photographs of material and any material test reports.
label | e1a13489-9a5d-55a8-902e-237a7c4a31e1 |  | note | Standard / Specification - GWS 2.4.3
label | f68f05fa-aac4-5343-bc89-5a71a59747d5 |  | note | Verifying Document - Correspondence/Photos/Survey
label | db47406d-a14b-5988-af96-e4bde7d4b0ae |  | note | Frequency - Prior to cut to waste
label | 1f8dfc8b-94b1-5db0-91bf-802c87634719 |  | note | Verification Activity - HP
label | d1e607a9-75e4-5ccc-9495-77974ca634ce |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-status |  |  | checkpoint | 6.1.3 - Foundation Suitability
label | 8f52a174-1f14-5d9c-8f84-53832a38af69 |  | note | Acceptance / Conformance Criteria - The foundation on which filling is to be placed must be observed by the Engineer following clearing and prior to the placement of any filling to confirm the strength of the underlying soils is sufficient.
label | 403a8560-3fe5-5d70-8ba0-4889dd83f554 |  | note | Standard / Specification - GWS 2.7
label | 190f3aa6-7334-5f5f-a3ee-8d073c6c01ad |  | note | Verifying Document - Site Record
label | 9fe9f93a-da52-5774-aa98-f6a1d17205aa |  | note | Frequency - Prior to the placement of any filling
label | 49c4a9bc-2a33-58b4-aa32-18d9c49e9425 |  | note | Verification Activity - HP
label | 55a75d49-9d4c-53ae-b04c-d26ae7dc6395 |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-status |  |  | checkpoint | 6.1.4 - Unsuitable ground
label | f74e983f-b3f1-52d2-a6da-8feacdfc6948 |  | note | Acceptance / Conformance Criteria - Unsuitable ground shall be defined as any pre-existing uncertified filling or natural silts/clays having an undrained shear strength of less than 70kPa or natural sands having less than 3 blows per 100mm penetration when tested with a Scala penetrometer. The contractor shall obtain instruction from Engineer around extent and depth of undercut.
label | 72b8a517-2c2f-576c-ab22-8a5927e27db0 |  | note | Standard / Specification - GWS 2.7
label | 20f3605a-ef82-5349-8b91-838106d91174 |  | note | Verifying Document - Shear Vane / Scala penetrometer
label | 6e495bf5-1e22-523d-9860-9240145d4445 |  | note | Frequency - Prior to the placement of any filling
label | b650b8b5-6206-5b56-9962-d2e1a99ce04e |  | note | Verification Activity - I
label | 5bd7b186-b7b2-5740-b0cd-6b7cd6829b31 |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 6.1.5 - Preparation for Filling
label | a6040fbd-88ee-5361-8734-01f4b7fd8f51 |  | note | Acceptance / Conformance Criteria - Preparation of the firm to stiff / medium dense subgrade beneath the proposed fill areas should comprise stripping of all vegetation, topsoil, any pre-existing fill materials or weak alluvium followed by benching of the exposed subgrade where natural slopes beneath the fill exceed gradients of nominally 1:5 (vertical to horizontal).
label | 7c91a7c3-4bf8-5b9f-be81-ab10b9428ed3 |  | note | Standard / Specification - GWS 2.9.2
label | fc234cf2-875c-50a9-bd15-e27556849159 |  | note | Verifying Document - Site Record
label | 22f53065-82e3-5ab6-ae5a-39840a6267b4 |  | note | Frequency - Prior to placement and compaction of fill
label | 239279e4-1553-5a57-b7d5-a078fa61cec6 |  | note | Verification Activity - I
label | aa3d6ba2-bde8-57a5-aefa-e21d85e5b1ea |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 6.1.6 - Subgrade Conditioning and Proof Rolling
label | bd14a369-a5e5-53fe-af67-b8de5e4943c4 |  | note | Acceptance / Conformance Criteria - The subgrade shall be scarified and moisture conditioned where necessary and then proof rolled to verify the subgrade stiffness and consistency.
label | c9327137-4cde-584e-9d31-f301eced2c4f |  | note | Standard / Specification - GWS 2.9.2
label | 5a215d15-4350-5e0a-b384-5db64abf102b |  | note | Verifying Document - Proof Rolling Sheet
label | 437a76a4-fcbb-5fb8-b9c0-dba79aa678b3 |  | note | Frequency - Prior to the placement of any filling
label | 5e876cd9-e4c1-583b-bce3-5c43af9e35ff |  | note | Verification Activity - V
label | 51ccb122-fc8c-5e98-9471-2075d87f0242 |  | note | Verification Activity By - SE/QE/ENG
checkpoint-status |  |  | checkpoint | 6.1.7 - Undercut Backill Compliance
label | 34b385b3-2355-59e7-876f-ff44ad010bdd |  | note | Acceptance / Conformance Criteria - Test results for undercut backfill prior to bulk fill commencing, NDM, scala penetrometer, shear vane or cleggs, material dependant. TBC instruction from engineer. Undercut backfill QA to be filed/captured separately from bulk earthworks fill QA.
label | f2d5b609-ffe3-5060-90eb-b2aeb2b22cc6 |  | note | Standard / Specification - GWS 2.9.2
label | 2a5ceae4-6204-56b2-af74-f7b852dc82ec |  | note | Verifying Document - Test Results
label | 3d85fe98-17a1-5ba1-8548-1faff69eb73f |  | note | Frequency - Prior to bulk fill commencing
label | ec2b9ddc-86b4-5199-a84a-b585302e0d67 |  | note | Verification Activity - R
label | f06ec382-6ae1-5540-b7b0-49c345564686 |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 6.1.8 - Topographic Survey
label | a5561c5b-ca9e-5395-be42-bdfcd8eb8c4f |  | note | Acceptance / Conformance Criteria - All subgrades and undercuts to be captured via topographic survey (GPS)
label | 972f635b-ad00-5e9d-a764-3df28e80d140 |  | note | Standard / Specification - PS 2.2.12
label | 67096b30-70fa-568b-8ca7-5c4476661a15 |  | note | Verifying Document - Survey Results
label | f665dbf1-e4ae-555a-a155-8f872335b31f |  | note | Frequency - Prior to cutting or filling.
label | 4e3075c0-3f73-5c5e-acea-53b9ff9dc3aa |  | note | Verification Activity - R
label | 0dd85854-02b3-5db4-9210-0eb8f56a5c43 |  | note | Verification Activity By - SE
checkpoint-group |  |  | section | Stockpiles
checkpoint-status |  |  | checkpoint | 6.2.1 - Stockpiles
label | bef39443-7d85-52f7-8d0c-66f2e56b1f58 |  | note | Acceptance / Conformance Criteria - The location of all temporary stockpiles must be approved by the Engineer prior to placement. Where stockpiles cannot be avoided above sloping ground, they should be placed over a wide area with the height restricted under the direction of the Engineer.
label | 25ca6fa2-218e-58ee-bfc3-2c5a7c30c9df |  | note | Standard / Specification - GWS 2.9.3
label | 0234ee50-2cac-5b79-8bc4-e97d89f84622 |  | note | Verifying Document - Stockpile Map
label | db7cde91-35c2-5185-9e3b-b29a79f2176d |  | note | Frequency - Prior to placement.
label | 48298222-1d4e-5d30-932c-06dd5fa4628d |  | note | Verification Activity - HP
label | 1497dad8-abb9-5023-a8ca-f94c8ff694a8 |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-group |  |  | section | Earthfill
checkpoint-status |  |  | checkpoint | 6.3.1 - Earthfill Placement and Compaction
label | 286ede01-a444-59af-8320-caa3012c88cc |  | note | Acceptance / Conformance Criteria - Earthfill must be placed, spread and compacted in controlled lifts under the direction of the Engineer. All earthfill must be placed to ensure adequate knitting of successive fill lifts by ripping any surfaces that have become dry prior to placing the following fill lift.
label | b3cf298a-4b4e-50e8-92bc-e06a06b5c243 |  | note | Standard / Specification - GWS 2.9.4
label | 0ba917b5-eebf-5035-abc0-0e37abe8cbed |  | note | Verifying Document - Site Record
label | 0e81b6c5-9757-515a-b91b-e69f20515b83 |  | note | Frequency - Per lift
label | d3f4f4d1-826c-579d-b32f-e6b543e41cf7 |  | note | Verification Activity - HP
label | 4406eb78-5b4b-5bc2-ac14-4fb5ba61d892 |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-group |  |  | section | Bulk Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
checkpoint-status |  |  | checkpoint | 6.4.1 - Proof roll Testing
label | 81e47988-85b7-532a-bae1-1a12e72c1d69 |  | note | Acceptance / Conformance Criteria - Each layer shall be tested via Proof roll to: 7mm maximum impression
label | 881f0569-d51a-5ef7-8ef0-d3678621cee8 |  | note | Standard / Specification - GWS 2.9.4
label | 71c058e2-0e0e-5335-9f4a-00d696132c0b |  | note | Verifying Document - Proof Rolling Sheet
label | d2cdd97d-44a2-54ec-8461-90172cb8a3be |  | note | Frequency - 100% of each layer
label | a3cf788c-318e-5cbc-adc4-8104048747c7 |  | note | Verification Activity - I
label | a6b88ab0-b9d8-5dd7-8d79-5c1cdfb29ad2 |  | note | Verification Activity By - SE/ENG
checkpoint-status |  |  | checkpoint | 6.4.2 - Compaction Testing
label | 0361ad6d-e77a-5d58-81fe-394dbecd915c |  | note | Acceptance / Conformance Criteria - Bulk fill shall be tested by DT at 300mm probe depth 95% MDD. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick.
label | 702d3671-8874-54ae-904e-c2b546422874 |  | note | Standard / Specification - GWS 2.9.4
label | 84133fc7-b8f9-55b3-a993-09885b7c8b41 |  | note | Verifying Document - Test Results
label | 9d017020-3c0e-553d-b800-f863103cd6c3 |  | note | Frequency - 1 set / 500m3 (1 set to include 1 x 0.5m deep Scala and 1 x DT within a 3m radius)
label | e73f6f4f-173e-5265-a670-bd32cc5dbb1d |  | note | Verification Activity - R
label | 2c57898f-d1f2-505a-abc6-d6dda53bcda1 |  | note | Verification Activity By - SE/ENG
checkpoint-status |  |  | checkpoint | 6.4.3 - Scala Penetrometer Testing
label | f1331738-3f66-562e-aab4-9f1c14cd166a |  | note | Acceptance / Conformance Criteria - Bulk fill shall be tested by Scala Penetrometer every 500m3 to: 4 blows per 100mm. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick.
label | 3ecfb16a-a9fc-5056-9e5c-bed455d0694e |  | note | Standard / Specification - GWS 2.9.4
label | e7df00a3-4bb3-5329-b09e-c11d8a7e7f46 |  | note | Verifying Document - Test Results
label | c5a4782b-328c-5561-92b4-2ad8f96d9ddf |  | note | Frequency - 1 set / 500m3 (1 set to include 1 x 0.5m deep Scala and 1 x NDM within a 3m radius)
label | 3b2bf319-1640-5979-bca2-736dc8f5952c |  | note | Verification Activity - R
label | 11826f75-4718-5556-89d7-4887d9c2d9d7 |  | note | Verification Activity By - SE/ENG
checkpoint-group |  |  | section | Bulk Fill - Cohesive (Imported Silt/Clay and Sand/Silt Blend)
checkpoint-status |  |  | checkpoint | 6.5.1 - Vane Shear Strength Testing
label | dbbc0a18-ae6a-5cf7-9ce0-18ec7a7ed771 |  | note | Acceptance / Conformance Criteria - Bulk fill shall be tested for Vane Shear Strength to: Minimum average 120kPa over 10 tests, minimum single value 110kPa. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
label | 36bcc3d7-db98-5639-af85-741172812629 |  | note | Standard / Specification - GWS 2.9.4
label | 251ea5e9-0ef2-5550-9457-1743ce45a70b |  | note | Verifying Document - Test Results
label | 1d857961-37ac-5b77-a66c-91f514f529e0 |  | note | Frequency - 1 set / 500m3 (1 set to include 5 x shear vanes and 1 x air voids within a 3m radius)
label | 56d13354-9e3c-5cfb-91f0-04b5ea52b5e7 |  | note | Verification Activity - R
label | 2f5aef00-2b4f-5282-a689-66479c32e70b |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 6.5.2 - Air Voids Testing
label | 9901dfd8-8abf-5c33-9555-ffa623f92f70 |  | note | Acceptance / Conformance Criteria - Bulk fill shall be tested for Air Voids to: Maximum average 10% over 10 tests, maximum single value 12%. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
label | f3da272a-2c60-5787-9a8d-72ddfd15ed6c |  | note | Standard / Specification - GWS 2.9.4
label | 36bf09f3-2f3e-56ec-8617-e97bc6b90620 |  | note | Verifying Document - Test Results
label | 0a4d47d7-3840-5c0a-a55d-504f47de1df7 |  | note | Frequency - 1 set / 500m3 (1 set to include 5 x shear vanes and 1 x air voids within a 3m radius)
label | c3c6cc28-d947-5fc1-bac2-97a43d11f29e |  | note | Verification Activity - R
label | 8267f1ef-1ee0-56f7-bf44-85d36163dbe2 |  | note | Verification Activity By - SE
checkpoint-group |  |  | section | Subgrade Fill - Granular (Hinuera Sands or Imported Sand/Gravel)
checkpoint-status |  |  | checkpoint | 6.6.1 - Proof roll Testing
label | b633fc11-6f49-5738-ae16-b70fd989c7e5 |  | note | Acceptance / Conformance Criteria - Each layer shall be tested via Proof roll to: 5mm maximum impression
label | bde7cd76-353a-543d-81ea-5b47ef0877e2 |  | note | Standard / Specification - GWS 2.9.4
label | 2f034ce5-f965-53c1-9f07-ab3c43bb4201 |  | note | Verifying Document - Proof Rolling Sheet
label | bbc95283-876f-534a-a57e-454ecf07ca08 |  | note | Frequency - 100% of each layer
label | b884386a-1912-518f-82fa-88e7ffc3a8ab |  | note | Verification Activity - I
label | a9e47c7c-12af-5d6a-a677-b116b4721333 |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 6.6.2 - Compaction Testing
label | 72f4e1d4-2714-5bad-b61b-a89df2751088 |  | note | Acceptance / Conformance Criteria - Subgrade fill shall be tested by DT every 500m3 to: 98% MDD. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
label | 90c5da6a-fd57-519a-af68-7f03ff4eeae2 |  | note | Standard / Specification - GWS 2.9.4
label | 65582f1c-08a9-5ed4-9cca-7ae57b6fd2b2 |  | note | Verifying Document - Test Results
label | 7d1f3f80-e554-5f08-8f36-5f61dd240c55 |  | note | Frequency - 1 set / 400m3 (1 set to include 1 x 0.5m deep Scala and 1 x NDM within a 3m radius)
label | fb7d72f3-6266-5d2f-a84a-b8ef5a9bfb43 |  | note | Verification Activity - I
label | abf82fab-4d37-580d-834e-df632b56edbd |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 6.6.3 - Scala Penetrometer Testing
label | fa73c0bd-67ed-5c81-b9f6-bcf874f36e76 |  | note | Acceptance / Conformance Criteria - Subgrade fill shall be tested by Scala Penetrometer every 500m3 to: 5 blows per 100mm. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick.
label | b52aed14-7a5f-5c32-b592-ad178c6a4ba8 |  | note | Standard / Specification - GWS 2.9.4
label | cbf75fa7-f933-50e9-81ab-d8fe0557bba2 |  | note | Verifying Document - Test Results
label | 7c9d20af-a460-54be-8d2d-db9494b4edc4 |  | note | Frequency - 1 set / 400m3 (1 set to include 1 x 0.5m deep Scala and 1 x NDM within a 3m radius)
label | d6175d17-dc53-576e-92fe-4c625f891373 |  | note | Verification Activity - I
label | b98e763c-d8e0-5357-ab9e-fbe30cc17c2e |  | note | Verification Activity By - SE
checkpoint-group |  |  | section | Eastern Gully Weir Fill - Cohesive (Imported silt/clay)
checkpoint-status |  |  | checkpoint | 6.7.1 - Shear Vane Testing
label | 97b9b3e5-db79-59b2-b466-0b008ccff789 |  | note | Acceptance / Conformance Criteria - The Cohesive Fill shall be tested by Vane shear strength to: Minimum average 140kPa over 10 tests, minimum single value 120kPa
label | 5caf5c28-8adb-5986-ac40-117c055eb178 |  | note | Standard / Specification - GWS 2.9.4
label | 08babd25-b5e1-5a0e-ab73-99303ff9fc43 |  | note | Verifying Document - Test Results
label | e2d0c240-a3cd-5182-a990-b731d77ba303 |  | note | Frequency - set / 500m3 and every 0.5m lift (1 set comprises 4 x shear vanes and 1 x air voids within 3m radius)
label | 76397b3a-dd0b-59ae-b0c7-b18f4785fcd5 |  | note | Verification Activity - I
label | cb0b7c5b-f49c-59af-ab6f-04fa7cf3847b |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 6.7.2 - Air Voids Testing
label | 4db17005-7815-5b97-af65-a2d559d0b55c |  | note | Acceptance / Conformance Criteria - The Cohesive Fill shall be tested for Air Voids to: Maximum average 5% over 10 tests, maximum single value 6%. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
label | 9e4e2f34-58e8-5cba-8f25-809593f7e3b4 |  | note | Standard / Specification - GWS 2.9.4
label | b94e47d1-f994-5e12-9c5a-ca666b8a440e |  | note | Verifying Document - Test Results
label | 33c1e730-fd7a-5790-b721-486d1a8144f6 |  | note | Frequency - set / 500m3 and every 0.5m lift (1 set comprises 4 x shear vanes and 1 x air voids within 3m radius)
label | 8f1e6d8b-95ee-55cc-ab21-e7ba2bff47aa |  | note | Verification Activity - I
label | b2000c16-2302-5b4f-a14b-e4c0f973756c |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 6.7.3 - Water Content Testing
label | 5a8fb55b-62f9-5e81-87cf-23c8f3f5f47e |  | note | Acceptance / Conformance Criteria - The Cohesive Fill shall be tested for Water Content to: Minimum 2% dry and maximum 6% wet of optimum water content. Survey shot at each test location, point ID to be agreed upon by contractor/sub-contractor to match test number, each test lift not to exceed 500mm thick. NDM direct transmission with probe depth of 300mm.
label | 04845150-aafd-5748-987d-ec3e37a628f5 |  | note | Standard / Specification - GWS 2.9.4
label | a24404f7-d7be-5b60-acf0-37f389166146 |  | note | Verifying Document - Test Results
label | b4089446-2691-5cae-af41-2c84000040ba |  | note | Frequency - set / 500m3 and every 0.5m lift (1 set comprises 4 x shear vanes and 1 x air voids within 3m radius)
label | 607ffd22-9ae7-5e38-92d4-cdfc2d60fd38 |  | note | Verification Activity - I
label | 0eb417e8-c6f3-58b8-9ce6-33a9fbcc8a53 |  | note | Verification Activity By - SE
checkpoint-group |  |  | section | Cut Batter
checkpoint-status |  |  | checkpoint | 6.8.1 - Cut Batter Inspections
label | 4d324204-dd12-5e34-b757-a5805d8ba4ae |  | note | Acceptance / Conformance Criteria - The Contractor will need to regularly inspect the exposed soils and check for any seepages that may occur due to the layered profile of the natural soils. All inspection records are to be submitted to the Engineer within 24 hours.
label | 2759f9f1-0521-5f18-9d18-423ac5f16661 |  | note | Standard / Specification - GWS 2.9.6
label | ce5cab41-2c26-5482-96c2-3d22d43139ce |  | note | Verifying Document - Inspection Programme and Records
label | 5c505c18-e993-51f7-949a-5b47156856cc |  | note | Frequency - Submitted to the Engineer within 24 hours.
label | a43347cf-95d7-5b0a-9e04-e6157f5a29d0 |  | note | Verification Activity - H
label | eb00df9a-b10b-5382-9e6b-464ee4e94717 |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | Cut Batters- temporary cut
label | 82b32635-e0da-5dbe-96c9-9eb5a24df6f3 |  | note | Acceptance / Conformance Criteria - The temporary cut buffer shall be maintained for 2 weeks to see if the seepage drains out, after which it may be cut to the final profile or additional drainage measures installed subject to review by the Engineer.
label | 73e4728b-5fd1-5e00-a3de-757a7f39c0e9 |  | note | Standard / Specification - GWS 2.9.6
label | d4b60330-816d-503d-8f99-630ff7c072c6 |  | note | Verifying Document - Site Record
label | f141fdc1-eaa1-5721-93e2-10a3bf9531bd |  | note | Frequency - Each Cut Batter
label | 08a7b0a1-3bd6-52cb-a687-8fd6eec5a3ed |  | note | Verification Activity - I
label | b7d155b5-2a16-51db-b7e9-418daa45c1cb |  | note | Verification Activity By - SE/ENG
checkpoint-group |  |  | section | Surcharge Fill
checkpoint-status |  |  | checkpoint | 6.9.1 - Surcharge Fill Installation
label | f8d6420c-f10e-5e92-8f1b-1938b79fc563 |  | note | Acceptance / Conformance Criteria - Surcharge filling shall be placed, spread and track rolled in 300mm layers. Surcharge fill will only be required if the settlement monitoring results exceed what was anticipated in the design. Under Engineer’s direction.
label | bea58f9c-832b-54dd-91d1-7738ce2a1847 |  | note | Standard / Specification - GWS 2.9.7
label | 11e1b7c8-63f1-5b19-b041-37ef1a1a8150 |  | note | Verifying Document - Site Record
label | be46eeb9-b88f-5e12-adb3-e15853fa82ea |  | note | Frequency - Per 300mm layer
label | 89c48506-43db-5c3d-aa52-bf114025d184 |  | note | Verification Activity - I
label | ac13cdb7-dc86-52f2-b78a-f98e874d68bc |  | note | Verification Activity By - SE
checkpoint-group |  |  | section | Respread Topsoil
checkpoint-status |  |  | checkpoint | 6.10.1 - Topsoil Respread on Steep Ground
label | 612645e2-276d-5142-9b35-0c856ea5d03c |  | note | Acceptance / Conformance Criteria - On ground steeper than 1V:3H the surface should be roughened under the supervision of the Engineer prior to topsoil placement.
label | 6e7f7b5a-7ed7-5cf2-9964-ab15f2fd2dfc |  | note | Standard / Specification - GWS 2.9.9
label | f6c2c4c1-e3aa-52d0-b069-b8bfb728a650 |  | note | Verifying Document - Site Record
label | 28b6f014-6695-5478-a0ab-d75596c438bf |  | note | Frequency - Prior to topsoil placement
label | 27f50561-beb4-53c0-85fd-f9ca434bb6ec |  | note | Verification Activity - HP
label | b0f3ff82-752c-51a9-aaa9-99a25793f796 |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-group |  |  | section | Subsoil Drainage
checkpoint-status |  |  | checkpoint | 6.11.1 - Filter Cloth Wrap Inspection
label | e85fb9f6-7d2b-513a-bd83-0e4c00c9f8d7 |  | note | Acceptance / Conformance Criteria - Observation of the cloth wrap should form an inspection hold point prior to backfilling over the drain.
label | 246d901e-41b6-508b-a982-d57b285d48f6 |  | note | Standard / Specification - GWS 3.2.2
label | 14272c52-0910-574a-8e68-1a008caaea01 |  | note | Verifying Document - Site Record
label | 4b416b83-4d74-5080-9f4a-780e2dd7ea80 |  | note | Frequency - prior to backfilling
label | b07a666c-cab0-5dc9-b74a-e8928840c5da |  | note | Verification Activity - HP
label | 2a503a6b-ecda-532e-8198-34ada9d17cca |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-status |  |  | checkpoint | 6.11.2 - Trench Backfill
label | 9be62d94-669d-56c5-98df-f0655e525d22 |  | note | Acceptance / Conformance Criteria - Backfilling of all trenches should be to the fill standard above
label | 9943da35-02d8-5462-9871-d8df0642290e |  | note | Standard / Specification - GWS 3.3
label | 14fbb3eb-8b9a-5333-af1a-fb278cb4f91d |  | note | Verifying Document - Site Record
label | 71250cca-3f46-5d4d-8b23-78956c6b7201 |  | note | Frequency - Each trench
label | 63f9d961-89a4-582b-8e63-ba924b5a4aa5 |  | note | Verification Activity - I
label | e9ff29db-9280-5bcb-8127-113818b5c8f5 |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 6.11.3 - Drainage Outlets and Inspection Points
label | e249ae11-1c7d-5447-bc71-995f46050380 |  | note | Acceptance / Conformance Criteria - At least one temporary flush point is required for each subsoil drainage system to enable flushing of the system once the earthworks are complete.
label | e46ceacf-cb8b-505d-8b15-1dc555be327f |  | note | Standard / Specification - GWS 3.6
label | 85052b17-54d4-5a95-9cbb-ef0d6c71f674 |  | note | Verifying Document - Site Records
label | 5ba4c355-4959-5072-8fd9-0aaf4250d5fb |  | note | Frequency - Each Subsoil Line
label | 8a2d0f43-d8cf-5b99-be4a-77de64ccae73 |  | note | Verification Activity - I
label | ee8b451c-21ab-5f86-ba49-8c33a487de18 |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 6.11.4 - Subsoil Flushing
label | ac40c030-449b-542a-af1b-0220426fe171 |  | note | Acceptance / Conformance Criteria - On completion of earthworks the Contractor shall flush the subsoil drainage system. This must be witnessed by the Engineer.
label | b407e655-141b-5767-955c-3c2aa89b6d64 |  | note | Standard / Specification - GWS 3.6
label | e23d0fc8-d955-5bdd-9a2e-739dea834f0e |  | note | Verifying Document - Site Records
label | 08a98415-27ac-5d92-accf-d6f9681783cf |  | note | Frequency - On completion of earthworks
label | 8c87024e-7a19-523d-9d24-d7539bbdb6c3 |  | note | Verification Activity - HP
label | 4f23f32d-52cd-557e-8dc4-002c5a2eda2c |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-status |  |  | checkpoint | 6.11.5 - Survey
label | 157333d0-9f65-58aa-be41-2fc45a3a2cdd |  | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | 1b3f7c5e-1e01-5a0e-a9e7-06bc3b3a5f3a |  | note | Standard / Specification - Downer
label | a335245c-0a90-5993-a7e9-27775cd90fca |  | note | Verifying Document - Records
label | ef32fdb5-96c4-5a3f-8230-c5c1f956c7f7 |  | note | Frequency - Post construction
label | 343e4729-0a43-541b-963c-5e036c02f45f |  | note | Verification Activity - H
label | 74b2f7ff-37a5-576d-8c7d-82789d0323f5 |  | note | Verification Activity By - SV
checkpoint-group |  |  | section | Geotextile and Geogrid
checkpoint-status |  |  | checkpoint | 6.12.1 - Geotextile Installation and Lap Length
label | 76225046-1c0e-5471-957a-bb64165abba8 |  | note | Acceptance / Conformance Criteria - All geotextiles shall be placed in accordance with the Manufacturer’s instructions and installed as specified on the drawings. A minimum overlap of 500mm is required between sheets.
label | 66d8fa5b-a442-549a-bea5-c3cb7452c2ad |  | note | Standard / Specification - GWS 4.1
label | de2fd70a-1a13-5c27-a39c-70f8eed0732e |  | note | Verifying Document - Site Records
label | c2acaba6-1ca8-5cac-8371-503ab5be89c7 |  | note | Frequency - Between each sheet
label | 0067de7e-b9fc-5b67-8136-0342c39ff969 |  | note | Verification Activity - I
label | f5d827bb-f426-5371-a150-e95a31726758 |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 6.12.2 - Geotextile Inspection
label | 5fce79e7-daa5-53c5-ad32-308b9a5bc3c4 |  | note | Acceptance / Conformance Criteria - Before placement of any geotextile should form an Engineers inspection hold point
label | b95f0b90-c3e4-514b-835d-2f189a655d86 |  | note | Standard / Specification - PS 2.2.16
label | f3c2b170-0327-54e3-b456-bc5cc93ab321 |  | note | Verifying Document - Site Records
label | b2d0e962-99a2-5b14-8134-5a715d35b1d2 |  | note | Frequency - Min 48h Notice
label | 4ca5ca69-f231-5784-abee-83eeca3a889b |  | note | Verification Activity - HP
label | a8b167fb-fa63-5a5a-a9b8-2948ec01afe8 |  | note | Verification Activity By - ENG
holdpoint |  |  | signoff | Hold Point (Engineer)
checkpoint-status |  |  | checkpoint | 6.12.3 - Geogrid Prep Inspection
label | 08108f8c-c97e-553e-9698-ffa2ad50e42c |  | note | Acceptance / Conformance Criteria - Prior to placement of the geogrid, verification of the grade, length, orientation and layout is required against the drawings.
label | 5123368d-8f9e-559a-b60f-86578ebb8743 |  | note | Standard / Specification - GWS 4.2
label | 80170ccc-66d3-58b2-b5d7-f14349acad85 |  | note | Verifying Document - Checksheet / Survey
label | 0a1db885-bc81-5f42-85ea-012546cd27bf |  | note | Frequency - Prior to placement
label | d17f58fa-a7fc-5a1b-a210-e9612db174c1 |  | note | Verification Activity - I
label | b5070777-cb7a-5829-bc76-2a395a322d46 |  | note | Verification Activity By - SE
checkpoint-group |  |  | section | Settlement Monitoring
checkpoint-status |  |  | checkpoint | 6.13.1 - Settlement Pin Installation
label | 99a3f15f-8fc2-5bf6-9524-d6389239a71b |  | note | Acceptance / Conformance Criteria - Protective waratahs and coloured flagging shall be installed around all settlement pins for protection. Settlement pins shall be installed within 24 hours of reaching design subgrade level.
label | 2f1d0c7e-7ded-524d-9789-d329ecdea150 |  | note | Standard / Specification - GWS 6.3
label | 7a072403-7d6d-584f-b3d8-2d79756c7e87 |  | note | Verifying Document - Checksheet
label | 248f1536-fe7a-5a91-887f-1bd1ed65900a |  | note | Frequency - within 24 hours of reaching design subgrade level.
label | b4f59ffe-eb6b-5ea4-80c8-cf2ba8ab3538 |  | note | Verification Activity - C
label | 0cef5e12-9dee-51e8-b40d-6b3fb1589e5d |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 6.13.2 - Settlement Survey
label | 112e7f80-767f-5636-946f-3932d2c8e479 |  | note | Acceptance / Conformance Criteria - Survey measurements are to be undertaken regularly by the Contractor as specified on the drawings, to within an accuracy of 2mm. Results must be provided to the Engineer within 24 hours of each reading.
label | 212ea4ee-e52a-546b-808c-745bac8d928a |  | note | Standard / Specification - GWS 6.3
label | f1489eab-003c-5a56-a03f-13ad0877b9b2 |  | note | Verifying Document - Both paper and electronic formats
label | 571d823b-77b5-53aa-8f3b-cc51567a9717 |  | note | Frequency - within 24 hours of each reading.
label | d4b9d21a-a50a-5a45-8ad8-0771fa0b609e |  | note | Verification Activity - H
label | 539fae9f-0f46-5cb7-ac3e-84c6f799cda3 |  | note | Verification Activity By - SV/SE
checkpoint-status |  |  | checkpoint | 6.13.3 - Retaining Wall Settlement Targets
label | b493ddef-686b-59cb-a6fa-20ce8a77e630 |  | note | Acceptance / Conformance Criteria - Targets shall be fixed immediately after completion of the first row of retaining wall blocks at each location and the initial baseline survey reading made prior to the subsequent row of retaining wall blocks placed.
label | 3eeed169-5910-546d-849f-0c6770ded3bc |  | note | Standard / Specification - GWS 6.4
label | 4fa0ca17-2e43-50c7-8881-fe23558af58b |  | note | Verifying Document - Checksheet
label | 90ae0198-a4e3-5455-90ed-a258561cd1fc |  | note | Frequency - prior & after completion of first row of retaining blocks
label | be7c7a7f-d127-535b-ad98-78270c9a6907 |  | note | Verification Activity - I
label | a8e6571c-2ea6-520b-b643-50014469a9b8 |  | note | Verification Activity By - SV/SE
checkpoint-group |  |  | section | SECTION 8 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER) - Site Post Construction Activities
checkpoint-status |  |  | checkpoint | 8.1.1 - Construction Record Compilation
label | 9e865959-c88a-5190-9f5f-9aead8c19ce6 |  | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | f4dfd5a4-d771-5aff-a69f-4c87ca9911bb |  | note | Standard / Specification - Downer
label | 89b72ad1-0a2c-5e13-a797-a0d4a5b77ccf |  | note | Verifying Document - Records
label | 855af0eb-08d2-530f-a975-5f08114d94c3 |  | note | Frequency - Post construction
label | 0c644f99-c56e-54d0-b27f-54f286afe727 |  | note | Verification Activity - H
label | 271d3bf3-544b-50e2-a020-72c91450dfda |  | note | Verification Activity By - SE
checkpoint-status |  |  | checkpoint | 8.1.2 - Survey Records
label | e04a5f03-809c-5321-856b-6c14bbe078c7 |  | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting including, initial subgrade level, all undercuts, all test location points, and final level
label | ea054228-80af-5478-8e11-c723f5ec1539 |  | note | Standard / Specification - Downer
label | fcc41489-f8ba-5261-96c6-b0f25fa9d847 |  | note | Verifying Document - Records
label | 0e8d161d-391b-5bc0-a9cf-621caa90b000 |  | note | Frequency - Post construction
label | 606b5e65-7591-5355-8b6f-2c9e2ee4738f |  | note | Verification Activity - H
label | a10d33be-0636-5363-b915-0104e692bbbe |  | note | Verification Activity By - SV
checkpoint-status |  |  | checkpoint | 8.1.3 - Redline Drawings
label | c8dc263f-8b1e-52a7-beee-97d562069bee |  | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | e3d9d811-9f48-50aa-ad2d-fbcb143b84ad |  | note | Standard / Specification - Downer
label | c8d3d189-33f3-5e6e-a349-a2f6a1c86fce |  | note | Verifying Document - Redlines
label | bb6a84e8-3c2f-500a-8396-acf0711ef71f |  | note | Frequency - Post construction
label | fbb1edf2-dd6f-53ab-abb0-02caa90ae961 |  | note | Verification Activity - H
label | c8c2a577-65bf-5aed-9279-6ba112957dfc |  | note | Verification Activity By - PE
checkpoint-status |  |  | checkpoint | 8.1.4 - Defect, Snag and Punch List
label | cabd4ab6-3f8c-56a6-85c9-b1978f83c065 |  | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | 10adea13-6583-56cf-a47a-74e52be060f2 |  | note | Standard / Specification - Downer
label | ff84c247-59ba-58d6-ab15-87cde05db7b7 |  | note | Verifying Document - Register
label | 7c100c2c-f6d9-5eb5-8a7c-7402ea3850ee |  | note | Frequency - Post construction
label | a81e1351-5432-54e8-9e31-499cb6261f99 |  | note | Verification Activity - H
label | 6924f01b-f7f3-51bf-a1e7-f2c5e75d1ab0 |  | note | Verification Activity By - PE
checkpoint-status |  |  | checkpoint | 8.1.5 - Photos
label | 94e37964-f4ea-55f7-843c-d9cff1cab647 |  | note | Acceptance / Conformance Criteria - Minimum subgrade, undercuts, all service ducting/pipe lines immediately before backfill, warning tape / mag slabs immediately before backfill.
label | 4bbb697c-8d21-5a96-8dda-190c8bb6e3e5 |  | note | Standard / Specification - Downer
label | 613458d8-44b8-5f7b-aa36-ddd3ce4f2886 |  | note | Verifying Document - Photo Records
label | 706b1d90-4936-5f76-ab5e-a6ac12da6b19 |  | note | Frequency - Post construction
label | 88958877-a040-53a7-a425-18f857a2b216 |  | note | Verification Activity - H
label | b80fc67a-8a18-5aef-addc-224f7da47377 |  | note | Verification Activity By - SE
checklist-sectioned |  |  | checklist | ITP - Pavement & Surfacing - AP65 Material - Rev E | itp |  |  |  | Yes | ITP - Pavement & Surfacing - AP65 Material - Rev E | e7231f11-7d8f-4b8c-835c-30dba119e9c9
checkpoint-group |  |  | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.01 General Materials
checkpoint-status |  |  | checkpoint | 5.01.01 - Sampling and testing
label | f587ec91-c904-5aa5-810e-812a47bf658c |  | note | Acceptance / Conformance Criteria - For all aggregates, test information confirming compliance shall be supplied to the Engineer not less than five working days prior to delivery of the material to site.
label | cbd8acf3-e0f5-55db-8156-67ac9226e388 |  | note | Standard / Specification - PS - 7.2.4
label | 93885b9b-13f0-53a3-be48-b4c45fe9878c |  | note | Verifying Document - IANZ Lab Reports
label | 98899682-c28d-54da-9530-1cac6628eb21 |  | note | Frequency - five working days prior to delivery of the material to site.
label | 4bc3cedf-4f02-54f0-99c0-606777acf2c0 |  | note | Activity - HP
label | 1684e61d-f968-5bc6-93c8-d16116aaff01 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.01.02 - Sampling and testing
label | e3222ecf-c962-562e-b51d-a385ea926d99 |  | note | Acceptance / Conformance Criteria - Water to be used in stabilisation - The Contractor shall be responsible for ensuring that the water for stabilisation, construction and curing of stabilised layers is free from impurities that may deleteriously affect the setting, hardening, strength or durability of the bound aggregate layer.
label | 9f24b800-ed24-5e34-9fd0-3a76c6d2158e |  | note | • Water from sources other than public supply may have its suitability established to the satisfaction of the Engineer by repeating the final approved laboratory based mix design tests with the water now being considered for use.
label | 75e0f194-01e2-5647-b89b-d15318f6a4c3 |  | note | • The results of these subsequent mix verification tests shall be greater than 90% of the final results from the previously verified mix design. In addition, work shall be stopped if any discolouration or residue is observed when adding or sprinkling water into or onto the material.”
label | e658a265-fcf3-51b9-b816-6da8f17ff91f |  | note | • Verifying documents to be dockets from fill up station, or proof of using public water supply. Or Lab reports for alternative supply.
label | a3c76a02-e132-5f46-bd9e-b4e2c019c057 |  | note | Standard / Specification - NZTA B/6 item 5
label | de7c7586-7099-5189-b616-4a6a29441748 |  | note | Verifying Document - Lab reports
label | 92d38b6d-5ffe-54da-ae7b-214d1c0bfec0 |  | note | Frequency - Prior to Works start, per source
label | cf34b954-d990-5942-823e-8d5103020e49 |  | note | Activity - HP
label | 9af1c353-0319-5f13-b777-4c09759ce4e8 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING - 5.02 Sub-base aggregate
checkpoint-status |  |  | checkpoint | 5.02.01 - Sub-base MDD and OMC
label | 0a20a9e1-9754-5595-b8be-f26bb33aab64 |  | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
label | dfed941e-c73f-5d66-b1a7-3eeeb24eb7fc |  | note | Standard / Specification - TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
label | 803756db-7d93-5b60-b603-1af60b69ee66 |  | note | Verifying Document - IANZ Lab Reports
label | 74aba5d3-54cb-500c-83d1-edce95b9c997 |  | note | Frequency - 1 test per material type
label | b8db62ec-cc1f-509b-9903-eb4e81b83a44 |  | note | Activity - H
label | 5789a56b-3eb4-5866-9ae7-24d49846f94d |  | note | By - PE
checkpoint-status |  |  | checkpoint | 5.02.02 - Cement for sub-base stabilisation
label | 90aad58e-40f2-5ded-aea7-47f72532c0c1 |  | note | Acceptance / Conformance Criteria - Cement for stabilisation shall meet the requirements of NZTA B6.
label | dbdace18-4d98-5009-8ab6-b14277b731a8 |  | note | Standard / Specification - PS - 7.3.2, PS - 7.2.6
label | e5b34312-89b5-5827-ba09-6bb0fcb8e0c7 |  | note | Verifying Document - Datasheets
label | 4c4b00a1-be0f-5d87-9a3b-54576dcb3ae2 |  | note | Frequency - Prior to Use
label | 47801d41-6821-5e8a-82e3-0184841d09f2 |  | note | Activity - H
label | 04c79bb8-fe77-5de7-8f36-985b35480d08 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 5.02.05 - Crushing Resistance
label | 41f160dc-388f-56b3-b37a-ddf10704fe4b |  | note | Acceptance / Conformance Criteria - The crushing resistance shall not be less than 130kN when the aggregate is tested
label | e2d9fc40-231b-5baf-9d2f-0fbd19fd2833 |  | note | Standard / Specification - NZS 4407: 1991 Test 3.10.
label | 4822f417-d7af-50af-a334-6483bdcbd0bf |  | note | Verifying Document - IANZ Lab Reports
label | 99c76d46-18fd-534a-9fd2-473398ee471a |  | note | Frequency - 2 tests per source 4 weeks before use in the works
label | 7c1c7573-6dae-5717-b1b5-fc54365f8ce0 |  | note | Activity - HP
label | 6977e619-cd8f-5904-a66f-a9a7645f4498 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.02.06 - Weathering Resistance
label | 943638a1-740f-55b4-be99-af0fcc241c16 |  | note | Acceptance / Conformance Criteria - The aggregate shall have a quality index of AA, AB, AC, BA, or CA when tested
label | 9db6d585-f4c9-5f36-859c-3dfb88fe2450 |  | note | Standard / Specification - NZS 4407: 1991 Test 3.11
label | 094254b1-853c-5c3f-8b07-5966870ba227 |  | note | Verifying Document - IANZ Lab Reports
label | ae7cd138-fb2d-5f88-b416-1f78bfa9b31a |  | note | Frequency - 2 tests per source 4 weeks before use in the works
label | 162e4230-64db-5c47-86cb-a0dfc237c92a |  | note | Activity - HP
label | 17931dc9-651a-5859-8652-0f215ae0b1cd |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.02.07 - Particle size distribution
label | e5535789-0a6e-5fe0-af5c-1f047760a453 |  | note | Acceptance / Conformance Criteria - The grading of the aggregate shall fall within the envelopes defined in the Table No. 7.1.
label | 96e0ef6b-e2b6-5d89-be5a-93e58e38be79 |  | note | Standard / Specification - NZS 4407: 1991 Test 3.8.1 Standard Method by Wet Sieving
label | 4873cafd-8d6f-5d61-bc11-6c4e07fee6f7 |  | note | Verifying Document - IANZ Lab Reports
label | b74d783c-e32c-5f19-bd48-ba28e3d805ba |  | note | Frequency - 0 to 400m³ - 2 tests
label | d39f35a7-71b1-5d66-88ed-38a7e132652f |  | note | • 400 to 1,500m³ - 3 tests
label | 68fcfe30-4312-5c70-916f-ddafa39da156 |  | note | • 1,500 to 4,000m³ - 4 tests
label | 009abe47-8c79-5476-bf59-fb711379c37a |  | note | • >4,000m³ - 1 test for each additional 1,000m³
label | 25bb434e-40d3-55e4-bf28-275ab9962c20 |  | note | Activity - HP
label | fb6fab50-41b0-571a-bd3c-9f033205e847 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.02.08 - Sand Equivalent
label | 408360b1-394d-50d2-8cbe-d6a8bf76af41 |  | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 25 when the aggregate is tested
label | ac6fcc4f-6636-515e-b5a3-d5ab9dfa131e |  | note | Standard / Specification - NZS 4407: 1991 Test 3.6 (Wet Method)
label | db322c43-e10c-59b5-86a8-357f5e898528 |  | note | Verifying Document - IANZ Lab Reports
label | 4635a1fe-6265-53b9-bb2f-ebbd287eca12 |  | note | Frequency - 0 to 400m³ - 2 tests
label | d32b7222-3ce6-5d44-8117-8d53245f7295 |  | note | • 400 to 1,500m³ - 3 tests
label | 6012f74f-1ac3-5d23-8a19-9e26cf3fb202 |  | note | • 1,500 to 4,000m³ - 4 tests
label | 4d7c60bb-3bbe-5e64-b3bb-3f11f650b42b |  | note | • >4,000m³ - 1 test for each additional 1,000m³
label | 97d1c748-b110-5bbd-b3a5-66b8a5b9eec5 |  | note | Activity - HP
label | 56d76160-229c-5574-97bb-af898fe419e4 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.02.09 - Liquid Limit
label | b1f61dae-82c3-5e9e-89b9-12aec0d5b5a5 |  | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Liquid Limit shall be ≤ 25 when tested - The LL may also be inferred (where appropriate) from the Cone Penetrometer Limit (CPL).
label | d30e3560-afd1-52a2-8f65-b6d210a42614 |  | note | Standard / Specification - NZS 4402 Test 2.2, NZS4407:2015 Test 3.2.
label | a713b910-3257-556a-9998-d526eb484870 |  | note | Verifying Document - IANZ Lab Reports
label | a5c57916-56d9-5d29-af16-60561b046e11 |  | note | Frequency - 0 to 400m³ - 2 tests
label | 21aff8b0-4190-58e3-b6a3-adfeb9ecaf07 |  | note | • 400 to 1,500m³ - 3 tests
label | 53416fef-9ded-5deb-968d-ff0c84a6ae6e |  | note | • 1,500 to 4,000m³ - 4 tests
label | 9f8f13c3-7929-5ce0-9ab2-e9daeb8a08a1 |  | note | • >4,000m³ - 1 test for each additional 1,000m³
label | 39b78350-5aca-5bbb-adb5-d1db03058103 |  | note | Activity - HP
label | d696f796-fd2c-54a7-ab30-edadea7c98b0 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.02.10 - Plasticity Index
label | adcce8e1-086e-5f16-8b3e-0792d22031b6 |  | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Plasticity Index shall be ≤ 8 when tested
label | 3ae28c04-98fc-56f1-97c4-9da685d1244b |  | note | Standard / Specification - NZS 4407 Test 3.4
label | 62fef554-b15d-5bb2-8b95-655f9be8465b |  | note | Verifying Document - IANZ Lab Reports
label | 115e070d-ecf9-51ea-9828-df026b036f6c |  | note | Frequency - 0 to 400m³ - 2 tests
label | ce1f32af-869e-5563-82da-4c6ea9d83866 |  | note | • 400 to 1,500m³ - 3 tests
label | 2f47e4d6-a598-554b-9088-068be9d6f2a9 |  | note | • 1,500 to 4,000m³ - 4 tests
label | 34a3e50c-cae8-5b0c-b74a-03f4ee673d85 |  | note | • >4,000m³ - 1 test for each additional 1,000m³
label | a1211ea0-d576-5ad0-99b7-8cc957e13c21 |  | note | Activity - HP
label | e436f6c2-4547-52cb-908c-cc19fa506125 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.02.11 - Clay Index
label | b2bbfdd1-90e7-590d-a1f7-de299ec76b03 |  | note | Acceptance / Conformance Criteria - Unless the grading test shows <4% passing the 75-micron sieve, the Clay Index shall be ≤ 5 when tested
label | 093a4d30-4c15-5956-84e0-5830b526ba2d |  | note | Standard / Specification - NZS 4407 Test 3.5
label | dd67cab4-a009-5bce-9ac1-39c19dcb481b |  | note | Verifying Document - IANZ Lab Reports
label | 05b26edc-dd98-518e-b6f6-98acf445836f |  | note | Frequency - 0 to 400m³ - 2 tests
label | d716371f-afa1-5e38-97ee-1ceafba9e5e0 |  | note | • 400 to 1,500m³ - 3 tests
label | cfde53d7-841e-512c-aeba-e555c5bbfc6e |  | note | • 1,500 to 4,000m³ - 4 tests
label | 9487e901-321c-5011-a414-7a0ca08a6e9b |  | note | • >4,000m³ - 1 test for each additional 1,000m³
label | ff882013-d580-5e74-b60d-a144e998ad53 |  | note | Activity - HP
label | b2ba9321-be58-5b53-8cd5-881dd664d718 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.02.12 - Proportion of Broken Rock
label | aa0b256e-7b28-5996-9be2-1f852a1da5a6 |  | note | Acceptance / Conformance Criteria - In each of the aggregate fractions between the 63.0mm and 4.75mm sieves not less than 50% by weight shall have two or more broken faces
label | 482ec926-0b1f-5da2-9eeb-10a9f0030d74 |  | note | Standard / Specification - PS - 7.2.2
label | e333c2ba-7723-57a3-87b9-4d16523a0be3 |  | note | Verifying Document - IANZ Lab Reports
label | 15deb5f3-d612-5476-bd5b-d4b23829a0bb |  | note | Frequency - 1 Test per source of the coarse aggregate. Additional samples if source is changed
label | 4155f610-28fa-546a-9fe8-f175b8d82a56 |  | note | Activity - HP
label | 7617584e-1f14-5d96-9a6e-06795b8d0012 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.02.13 - Organic Matter
label | ce67a179-8cd6-5d21-9f2d-650078b91c33 |  | note | Acceptance / Conformance Criteria - It shall be free of organic matter
label | 91d09f65-eb33-5b6e-a4fd-f93d0a7534e8 |  | note | Standard / Specification - PS - 7.2.2
label | e70cdb01-3c8b-572a-a18f-a87e1e5cb32c |  | note | Verifying Document - Photos
label | 0809aba2-401a-5ffb-b7f0-475f02e5e2e3 |  | note | Frequency - Continuous
label | 1934c074-cd46-5c96-bfb5-f5c8b3778de3 |  | note | Activity - I
label | 51d07c23-348a-50b1-aa98-8690dd477705 |  | note | By - SE/PE
checkpoint-status |  |  | checkpoint | 5.02.14 - Accelerated Weathering Testing
label | 0192bd9c-f10b-5fc5-a61c-ba4f96f4b151 |  | note | Acceptance / Conformance Criteria - If the difference between the tested sample and the control is >30% in the accelerated weathering test, the Contractor shall undertake additional x-ray diffraction analysis
label | b273779b-40d9-52f7-8241-3fbe6fe3df57 |  | note | • The levels of smectite clay minerals are not classified as “abundant”
label | 4c242fa6-3cd2-5be1-9cb0-13424bbc41c6 |  | note | Standard / Specification - In accordance with NZTA Standard Specification T20 Draft Specification
label | 41b3ea5e-a1c6-5310-8a98-443fa930bc3d |  | note | Verifying Document - Lab Reports
label | bc7814fd-f2a7-5b94-85cf-ec53b9af7904 |  | note | Frequency - 2 tests per source 4 weeks before use in the works.
label | 4b884df7-5ea8-59e9-9629-47b4389dc632 |  | note | Activity - HP
label | 18d8d1e0-413c-5580-aef7-de3b62856bd4 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.02.15 - Repeat Load Triaxial Test
label | d09076b1-b61f-5eb2-974a-f781cc4d3ee7 |  | note | Acceptance / Conformance Criteria - In accordance with NZTA T15
label | 013ba046-1451-5298-8bfb-78a4bb304c9f |  | note | Standard / Specification - NZTA T15
label | 8935eef6-8e74-5a06-bfea-84643c31fb0f |  | note | Verifying Document - IANZ Lab Reports
label | dd0ece6a-d4e7-5fe5-8423-8f7e23a191eb |  | note | Frequency - 2 tests per source 4 weeks before use in the works.
label | 8ec6d9e7-5281-5db7-b6ab-613f13e2453e |  | note | Activity - HP
label | 0763efe7-8190-5247-9b7e-fcbced428056 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.02.16 - Unconfined Compressive Strength (UCS)
label | b95df1b9-16bd-5fb4-8380-6ce5ceb43701 |  | note | Acceptance / Conformance Criteria - Unconfined Compressive Strength (UCS) testing of source aggregate for modified layers to test sensitivity to additives.
label | 8cbd082d-b3b6-56f1-845f-7ae5f4d52587 |  | note | Standard / Specification - PS - Table No. 7.2
label | 9a5e5f78-ea85-5d1a-a3e8-bd1050b974a8 |  | note | Verifying Document - IANZ Lab Reports
label | 16412a24-8bb2-55e5-8dd0-893f133e87c8 |  | note | Frequency - 1 set of tests per stockpile at source. Set of tests to include proposed mix plus tests with 0.5% more and 0.5% less additive than proposed.
label | fbc17876-2779-535f-902b-4ff53d219016 |  | note | Activity - HP
label | 76b1b5d9-289e-520d-8bd0-dfa2ec9522d1 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.02.17 - Indirect Tensile Strength (ITS)
label | e47a2fa0-3663-5f12-aad1-d62f108d6350 |  | note | Acceptance / Conformance Criteria - In accordance with draft NZTA T/19 at the rate specified in Table A7.4 using 4.0%, 4.5% and 5.0% cement (with 7 days curing) and results forwarded to the Engineer not less than 7 Working Days prior to construction for confirmation or adjustment of the additive contents.
label | e5bb67bd-1a40-5895-a4f1-d9bb7d80efb6 |  | note | Standard / Specification - NZTA T/19 - Table A7.4
label | e7824d9c-8295-5b65-8434-4efbe8a73f4f |  | note | Verifying Document - IANZ Lab Reports
label | e16db668-c136-5947-82cf-f976b5d3771b |  | note | Frequency - 1 set of tests per stockpile at source. Set of tests to include proposed mix plus tests with 0.5% more and 0.5% less additive than proposed.
label | f1e2d0a3-a3cb-558d-bf43-fbe94d13b4dc |  | note | Activity - HP
label | 397eeebd-78df-50e8-9e26-e4bf565540a5 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Insitu Concrete Construction - Rev D | itp |  |  |  | Yes | ITP - Insitu Concrete Construction - Rev D | f880282a-5303-41c8-b460-de649d8bea41
checkpoint-group |  |  | section | SECTION 1 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT) - 1.01 - Site Requirements
checkpoint-status |  |  | checkpoint | 1.01.01 - Construction Pack
label | 92ceac3b-e1ae-56a9-a8a4-8edc0127429f |  | note | Acceptance / Conformance Criteria - Construction Pack including a Methodology and JESA to be assembled , uploaded and transmitted on InEight before works commence.
label | bb1125af-6e21-585f-b3ed-3c4c432cf7e6 |  | note | Standard / Specification - Downer
label | e10d0142-a1ef-54e1-bff5-a33bf202c455 |  | note | Verifying Document - Construction Pack
label | 99333c1a-e691-5df8-a7b9-21f6e8bf3cab |  | note | Frequency - Prior to Works
label | 97435b0c-f0b6-58db-abfe-8e5b0a0bd701 |  | note | Activity - H
label | 0c8bdd52-22f3-5b18-9e0a-b829f82124db |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.01.02 - Survey Setout
label | f12d670f-e583-5267-b1ec-73154264911d |  | note | Acceptance / Conformance Criteria - The Contractor shall verify the setting out position, level and line of the bridge, prior to commencing construction. The Contractor shall advise the Engineer of any apparent anomalies identified.
label | dcd4f506-5e3d-52ca-8c7e-7de1987a4f82 |  | note | Standard / Specification - Downer PS - 11.2
label | 06f2f8c9-b3bc-59d5-98b7-c265696eca7b |  | note | Verifying Document - Survey Records
label | 9164739e-ae99-5a56-8397-13f6020a5382 |  | note | Frequency - Prior to Works
label | 0ca06d95-790d-5940-ade1-9894060330a4 |  | note | Activity - H
label | b4ab5ab7-90f2-57e9-8bcd-bcb06be329d3 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.01.03 - Internal Permits
label | 80f4840d-3bfa-580f-b6f5-a1f184ba1e1f |  | note | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | b3230b35-0a45-5a98-852f-a3cb25db9056 |  | note | Standard / Specification - Downer
label | 63a94c48-a964-5733-8371-176bd65816ad |  | note | Verifying Document - Internal Permits
label | e851d41e-f372-5742-a5d4-411984d20950 |  | note | Frequency - Prior to activity being undertaken
label | 769fd35b-8009-5aee-afa0-7d2d105d46b9 |  | note | Activity - H
label | b0eb6535-8625-5eff-ad5d-61426d20040a |  | note | By - SE
checkpoint-status |  |  | checkpoint | 1.01.04 - External Permits
label | b0c75fe0-5871-55d2-9b1f-c93f6186803f |  | note | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | c7067bfd-b2ec-5f88-a167-31cc524f3a1b |  | note | Standard / Specification - Downer
label | f74033ef-8e27-5e1f-bc29-48e0f0434f3b |  | note | Verifying Document - External Permits
label | 96f67d5c-0691-5535-b452-3853ad0ec681 |  | note | Frequency - Prior to commencment of activity
label | 346e4749-5e48-5db6-8d19-cd301687a268 |  | note | Activity - H
label | 2920e4a8-56ee-5016-a5c5-749cd6b21c40 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 1.01.05 - Approved Construction Drawings
label | 1ed16a31-6490-5485-9039-47ce50535f64 |  | note | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | 06d2a285-3919-5f61-9baf-f7d2c02c4abc |  | note | Standard / Specification - Downer
label | 1cf5bce5-b4ad-5672-9966-fc2c41fc43a7 |  | note | Verifying Document - IFC Drawings
label | fcbbe479-8bd4-54c4-9734-246047b2673c |  | note | Frequency - Prior to works start
label | d0abc35a-c34b-5578-85df-419f706ec434 |  | note | Activity - H
label | a2940c52-f39d-5cfd-a146-39f060e2476b |  | note | By - PE
checkpoint-status |  |  | checkpoint | 1.01.06 - Construction Methodology
label | 8eee3c74-4023-5582-9897-44ae42bfbd0a |  | note | Acceptance / Conformance Criteria - The Contractor must submit their proposed construction methodology and justification to the Engineer for review at least 10 Working Days prior to commencement of bridge construction.
label | 882e5ba8-77a9-5bd5-b4c9-1ec9d8241c96 |  | note | • The Engineer’s review will be limited to conceptual assessment of any potential impact on critical elements of the structure.
label | 00d9f83f-73be-5def-bdfb-e9a4fe681359 |  | note | Standard / Specification - PS - 11.3, SS 2146 - 3
label | 9480445e-5e55-59a1-addf-b56328b7b136 |  | note | Verifying Document - Methodology
label | 69d03473-6184-5dfa-8b5c-c020156391f3 |  | note | Frequency - At least 10 Working Days prior to commencement
label | e2b4efc1-fe2e-582a-8d9a-5d2b61a7de44 |  | note | Activity - HP
label | ce2cdaed-9009-5812-a323-cf8303dca192 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.01.07 - Stakeholder
label | 8653ddac-a145-5381-a9ff-9b969b62e48b |  | note | Acceptance / Conformance Criteria - Inform stakeholder of upcoming pours. Special considerations to early morning pours, potential for noise monitoring requirements being triggered.
label | 9c757d6e-6cbe-508d-a785-77d359774049 |  | note | *Forward correspondence around notifications of early morning pours to the Engineer and HCC before pours are carried out.
label | 992da153-9644-57b5-94c4-a319384e05e6 |  | note | Standard / Specification - CNVMO / CCCP
label | 8b86c5e5-595d-534d-a339-b2ace543f345 |  | note | Verifying Document - correspondence with stake holders
label | 0b278dae-55be-5246-a23c-f9c3f2038bc7 |  | note | Frequency - per pour
label | c4a21675-edfa-5911-8d04-1562a06eed9b |  | note | Activity - H
label | 415edfef-9a9c-57ac-87fc-4f94ee49c61a |  | note | By - PE
checkpoint-group |  |  | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.01 - Temporary Works
checkpoint-status |  |  | checkpoint | 2.01.01 - Chartered Engineer
label | e97e36ad-9112-57c4-a773-3508113774f1 |  | note | Acceptance / Conformance Criteria - The Contractor shall employ or retain a Chartered Engineer registered with Engineering New Zealand and experienced in the design of temporary works and erection engineering activities to design and provide construction oversight for all temporary works as specified in these Contract Documents and/or as may be necessary to complete the Physical Works.
label | 456287ff-ea34-5f15-a759-0f8f14c8e545 |  | note | Standard / Specification - PS - 11.14
label | 5a08e547-4262-58a4-b85f-336acfd6db64 |  | note | Verifying Document - Chartered Engineer Details
label | 25250fdc-ad9f-57f9-ae22-a717e235e685 |  | note | Frequency - Prior to Temporary Works
label | 790b5b0c-d4a5-5491-b136-26b1fb5a6c95 |  | note | Activity - HP
label | 2cc865f4-e546-55d8-9436-735522a1f6bc |  | note | By - PE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.01.02 - Drawings and calculations
label | 2350bf3c-f010-5c51-8368-cc6c54285425 |  | note | Acceptance / Conformance Criteria - The drawings and calculations for the temporary works and/or erection engineering activities prepared by the Contractor shall be submitted to the Engineer for review in advance of proceeding with any temporary works covered by the drawings and calculations to facilitate construction. In no case shall construction commence until the Engineer has reviewed and accepted the drawings and calculations.
label | 0a98b68b-9e7e-541d-b5d4-5d469fbb9757 |  | note | Standard / Specification - PS - 11.14
label | bcc21c93-ba07-54f1-bd11-8a017d8a35e6 |  | note | Verifying Document - Approved Drawings and calculations
label | 5d324e5b-0b9e-54b2-8789-e57b4208b31d |  | note | Frequency - Prior to Temporary Works
label | 550f05c0-88f8-5f63-9b05-10965ca9cc04 |  | note | Activity - HP
label | b2d473e4-2d4f-559d-b54e-4cde57818eaf |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.02 - Concrete
checkpoint-status |  |  | checkpoint | 2.02.01 - Concrete Mix Design
label | 790b7eed-c78f-5e0f-993b-fba41557f02d |  | note | Acceptance / Conformance Criteria - Concrete mix design to be completed and reviewed by the contractor prior use on site. The following criteria are to be satisfied:
label | c3b8c670-f6d4-5bd1-a913-e38e3172cd9a |  | note | • Strength: 40Mpa
label | e5f4172f-cc4d-5530-a3e8-275c60a80349 |  | note | • Normal maximum aggregate size: 20mm
label | 0c9161ff-5de2-59f3-ad7e-42076f547177 |  | note | • Basic drying shrinkage strain 720 microstain
label | 51267fe0-ec17-5023-83fe-74189f90cc2f |  | note | • Concrete materials and manufacturing are to comply with NZS3109
label | 47d723cb-a3fe-5b9c-90df-a7b21c45b678 |  | note | • All concrete shall contain a minimum of 25kg/m3 of micro silica for enhanced durability.
label | a97ce29e-cdaf-5d86-a982-ca6501886dde |  | note | • Only one brand of cement shall be used throughout the works without prior Engineer’s written acceptance.
label | 6bdfbcc3-9886-5f8a-8a4f-4f9e07d9bba9 |  | note | • Details of the types and rates of application of the admixtures proposed are to be supplied to the Engineer for acceptance.
label | b86a6c62-b95c-5681-9070-5959aefb50e6 |  | note | • Trials undertaken in advance of production to verify outcomes are being achieved in accordance with mix design expectations. This is to include if the mixes will be pumped.
label | c06ac2d0-a25e-5139-a67c-ab8e42565839 |  | note | • The Contractor shall identify appropriate preventive measures and to justify those measures to the Engineer to minimise the risk of Alkali Silica Reaction (ASR).
label | 519e7c0c-f65a-5a52-86dc-44224a35e7b4 |  | note | Standard / Specification - PS - 11.5, SS 2140 - 3, 4, 9, 6.1, 6.3, 6.5
label | 3adcf6a0-65e6-54cf-a535-9ec38c49975e |  | note | Verifying Document - Concrete Mix Design
label | 0a837975-280d-59b2-891c-336379f55662 |  | note | Frequency - All Mix Designs
label | 8f8a16e3-0a0e-5547-9c1c-84bb434365e2 |  | note | Activity - H
label | 084ccac4-c73a-57a5-a2d3-e24a4243fbf2 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 2.02.02 - Concrete Mix Design Checklist
label | 84fb278d-1dd3-5e18-95b4-5d0b32e3dc71 |  | note | Acceptance / Conformance Criteria - Each mix design shall have a completed concrete checklist with supporting data including Trial Results, submitted at least 5 Working Days prior to production of that mix design, for the Engineer’s review and acceptance.
label | 0a1cb2e6-40e2-5c69-b224-fd19fa9a6a23 |  | note | Standard / Specification - PS - 11.5, SS 2140 - 9
label | 6fd63448-1bdd-57a1-8e00-5cdbbf67d7ae |  | note | Verifying Document - Concrete Checklist
label | ece0e023-060c-5d82-9901-18df5ea7534c |  | note | Frequency - 5 Working Days prior to production of that mix design
label | b9dd7f5d-d877-5325-91bc-30955ce392a0 |  | note | Activity - HP
label | 97d25eb7-9bfb-5110-869b-6c2efb5db56b |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | SECTION 2 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - 2.03 - Reinforcement
checkpoint-status |  |  | checkpoint | 2.03.01 - Reinforcement
label | b6afc49f-38e4-5904-ae6f-8f6491a1b94f |  | note | Acceptance / Conformance Criteria - 3D modelling completed, bar bending schedule checked against latest construction drawings and submitted to the Engineeer for review
label | a45f2372-e67f-5aab-966a-d6a5df32ceed |  | note | Standard / Specification - Downer
label | dbfc1de5-5f40-5c17-8e43-593cf9bd9c70 |  | note | Verifying Document - Reinforcment shop drawings
label | 2e80847b-6e1c-5227-96f1-959c89b61a6c |  | note | Frequency - Each batch of reinforcement
label | 3f3826a5-de94-5ec8-aa36-4c24e5a69c81 |  | note | Activity - H
label | b46aeed2-e77b-5800-90ec-2da66b229abb |  | note | By - PE
checkpoint-status |  |  | checkpoint | 2.03.02 - Reinforcement
label | 85787332-8b63-5e76-9aac-b236c533023d |  | note | Acceptance / Conformance Criteria - Mill & test certificates for each batch of reinforcement used to be provided to the Engineer. Unless specifically nominated otherwise on the Drawings, only Grade 500E reinforcement manufactured using the micro-alloyed process is acceptable.
label | 5625c41b-0b31-55e0-9ee5-5803ddc06844 |  | note | Standard / Specification - SS 2142 - 3, PS - 11.6
label | 0a98d2f9-b4f4-5648-b695-7cdff4e1be3c |  | note | Verifying Document - Mill Certs
label | fc16cd7f-c01b-5b9e-990a-a6b9d20bce96 |  | note | Frequency - Each Batch assigned to Each Pour
label | 5b305dee-885d-5738-a898-35da190dff2e |  | note | Activity - R
label | 6be4f6ad-b97d-55be-92b1-4398f8cd43e6 |  | note | By - ENG
checkpoint-status |  |  | checkpoint | 2.03.03 - Welding reinforcing
label | b6b3c536-3468-51a9-b8f2-892b4ae716fd |  | note | Acceptance / Conformance Criteria - Prior to welding reinforcement, approval from the Engineer must be obtained. The person undertaking the weld must hold the relevant certification.
label | 53ec7e11-e6e2-5ae2-8269-7f5dee129cca |  | note | Standard / Specification - SS 2142 - 9
label | f819f84a-616f-554d-89ff-d65ca9ba05ff |  | note | Verifying Document - Approval
label | 89089fd2-0937-5402-9052-d58bcb4d9744 |  | note | Frequency - Prior to welding (if required)
label | 5e77e621-5c03-5233-ba4b-fe1a71a19506 |  | note | Activity - HP
label | b23e7904-b0fb-5346-ad7c-e2ba1f29a831 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.03.04 - Steel supply
label | cd52136a-c9d4-5831-aea8-12213b87de04 |  | note | Acceptance / Conformance Criteria - Certificate of origin for all steel reinforcing supplied
label | c32a9e64-feb2-5357-977c-a0ea690c6f77 |  | note | Standard / Specification - NA
label | a3faaa58-6d64-5bd0-9fd7-32d043112ae0 |  | note | Verifying Document - Certificate
label | ac279921-0b83-5fc6-b65b-6a9661f31e6a |  | note | Frequency - Each batch of reinforcment
label | 6ee83ece-47f2-5f84-a638-f6574082eb9c |  | note | Activity - R
label | a739393c-522c-55bc-82a7-f7848d71108d |  | note | By - ENG
checkpoint-group |  |  | section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.01 - Pre pour
checkpoint-status |  |  | checkpoint | 3.01.01 - Temporary Works
label | 7a89cb0e-af59-5896-a2b9-fb78b0fc3f45 |  | note | Acceptance / Conformance Criteria - Temporary works to be installed as per design drawings. Permit to load to be issued by temporary works inspector prior to loading element
label | 7d72e1c0-8698-5fef-9d3c-00553de45152 |  | note | Standard / Specification - Downer
label | 268ae1b7-092e-5e19-b760-b6280ebf8aed |  | note | Verifying Document - Permit to load
label | d58d1e61-9a2a-5061-8e60-b1f63cec00ce |  | note | Frequency - As defined in the temporary works design
label | b05aa2c5-6bf0-5f53-9fe0-72278009cc84 |  | note | Activity - H
label | 12b21f7c-cbac-5728-bde7-3a3dd01e4f72 |  | note | By - PE
checkpoint-status |  |  | checkpoint | 3.01.02 - Reciept of Reinforcment
label | 29708042-3eb0-50f7-9817-eb1a9ed77b37 |  | note | Acceptance / Conformance Criteria - Reinforcement checked against bending schedule. Bars correct length, size, shape, grade, and free of defects.
label | 9383dd6c-3a23-5736-9b3b-d2a687aa3ac8 |  | note | Standard / Specification - IFC Drawings, SS 2142
label | 8e0a3b5d-f574-58c2-a4b4-139c394a9c31 |  | note | Verifying Document - Photos / delivery dockets
label | b219cff3-ff78-58cf-88c5-f2f1ca7b5ce7 |  | note | Frequency - Each pour
label | f5b65f4c-8970-5e55-b595-61c9db5ef0a2 |  | note | Activity - I
label | 3e1874e7-c0c6-5220-814d-54eb5ab369b2 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.03 - Reinforcing Welding and NDT Inspections
label | 621a163f-01e9-5398-bb79-7869eccdb7c0 |  | note | Acceptance / Conformance Criteria - All reinforcing steel welding should comply with AS/NZS 1554.3; and all welded splices shall also conform with NZS 3109 Clause 3.7.2 or 3.7.3.
label | eafe6a90-fa22-56e6-9054-351ea8087d7b |  | note | Standard / Specification - SS 2142 - 9, AS/NZS 1554:3, NZS 3109 Cl 3.7.2 or 3.7.3
label | f357cc29-75cb-5f9b-9d79-dba20552df1a |  | note | Verifying Document - TPI Report
label | f7185df9-611f-5c96-b8d6-22fc180b0bd5 |  | note | Frequency - Each weld prior to installation
label | 4aafe222-7473-5909-a3ec-9b3cf74c4081 |  | note | Activity - H
label | 49be0430-0e13-529c-8f5e-421ddf8ab1ee |  | note | By - TPI
checkpoint-status |  |  | checkpoint | 3.01.04 - Pre pour inspection
label | f862655c-6cf6-5229-95bf-2a8639fd5515 |  | note | Acceptance / Conformance Criteria - Pre-pour inspection checklist undertaken by the Site Engineer and captured on the ConQA web app. All aspects of the element to be checked against latest construction drawings and specification requirements.
label | 78c31cf3-c538-5847-9598-26e5ea679dc5 |  | note | Standard / Specification - Downer
label | 90c72c06-1fae-5e17-918d-d497af290eb7 |  | note | Verifying Document - Pre Pour
label | 5780eb5a-ac86-56ef-b2f6-012e0edd49b3 |  | note | Frequency - Each Pour
label | 003b6c68-e85d-5ddb-9a70-ece8b19ef48e |  | note | Activity - H
label | 18614d22-a548-5581-8157-f27809e610ce |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.05 - Engineers Inspection
label | 6b41f6ac-e96a-538e-a166-6433c42621c2 |  | note | Acceptance / Conformance Criteria - The Contractor shall advise the Engineer when he intends to commence placing concrete. No concrete shall be placed until the Engineer is satisfied that the requirements of this Specification and the Drawings relating to formwork, reinforcement and construction joints have been complied with entirely.
label | c571cc27-1280-586f-b69c-9bd61ea0feb8 |  | note | • No concrete shall be placed in the absence of the Engineer without prior acceptance.
label | e165b02b-77f5-5280-963d-bbb06b0c5cac |  | note | Standard / Specification - SS 2146 - 6, PS - 2.2.16
label | f9967265-bb1d-5865-a008-8406f0714223 |  | note | Verifying Document - Hold Point Release
label | 1d714eeb-0c46-5abb-8d10-b6ef7993b3b7 |  | note | Frequency - Min 48h Notice
label | 849b583b-8f9a-556f-89f9-972ded875f32 |  | note | Activity - HP
label | 69c2d6b0-7d6f-5418-9431-68fd4cfd6861 |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.01.06 - ESCP
label | ede482ff-3da6-56f9-80af-4253fdfed48b |  | note | Acceptance / Conformance Criteria - All erosion and sediment control measures are to be installed and maintained in accordance with Site Specific ESCP
label | eb0e2b42-e267-5574-8a3b-ac752fabcb0f |  | note | Standard / Specification - Site Specific ESCP
label | 7a68ee6c-90ec-5c9c-bf70-a18db77ce92e |  | note | Verifying Document - Acceptance
label | 164883cb-e145-5c11-abd4-4671c81df430 |  | note | Frequency - Each pour
label | 643b731d-b5f4-5cf6-864d-ad78dae0fea6 |  | note | Activity - I
label | 84d2aafe-d2bc-54ca-8537-7b0ce2e5f43e |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.01.07 - Concrete Cover
label | 2a8cbcdd-8da9-5397-ac26-b9973c34f436 |  | note | Acceptance / Conformance Criteria - Concrete Cover:
label | 473fc378-500c-5a22-b5cc-6bd7fb2b8d81 |  | note | • 75mm - all concrete cast in contact with the ground
label | b48eb42f-85a6-5aa6-b267-165bada20d36 |  | note | • 50mm - where protected from soil contact during casting by formwork or by a suitable damp-proof membrane
label | 38c7e5bf-a7df-5ca4-8c89-66e9dfa47b8b |  | note | • 40mm - standard unless noted otherwise on the drawings
label | d240c507-03e7-59c7-b7e7-7e75e70f775a |  | note | ○ Tolerances:
label | cc729938-3501-5cc3-a045-486d4be17f2f |  | note | i) In slabs and walls ...... +10, -0mm
label | 486ee57a-6b95-54ab-bcb5-62f8e703fab5 |  | note | ii) In beams and columns ...... +10, -0mm
label | 7523290d-4e03-57ff-a80a-fc860642d12e |  | note | iii) At ends of members ....... +25, -0mm
label | 6ac3ed77-c9c6-5483-9468-c40bad194f4c |  | note | Standard / Specification - IFC Drawing, NZS 3109 Secion 3.9
label | 664ad51c-1c8d-57ef-bb07-c9a3e47c5770 |  | note | Verifying Document - Approval
label | dd311c62-4017-5870-ba60-92a97c3e6c17 |  | note | Frequency - Before concreting
label | f1a3cc85-ee7b-5ead-8460-52c1917dbf51 |  | note | Activity - I
label | b833a218-7ebf-579b-8b7e-93d19a0f325b |  | note | By - SE
checkpoint-group |  |  | section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.02 - Concrete Pour
checkpoint-status |  |  | checkpoint | 3.02.01 - Unfavourable Conditions - Cold Weather
label | 6a8560a9-58c6-565f-a814-7cf8aefdf123 |  | note | Acceptance / Conformance Criteria - Concrete shall not be placed in conditions where temperature is below 5°C with temperature decreasing or below 2°C with temperature increasing.
label | 5de8dc23-9812-573d-bfcb-272bd5b75b9d |  | note | Standard / Specification - PS - 11.5, NZS3901 cl 7.2
label | 1159dde7-0450-587a-a76c-4bfb012db192 |  | note | Verifying Document - Pre Pour
label | e339b2d5-99f4-51e4-b667-c48eab201223 |  | note | Frequency - Each Pour
label | 5b24094a-d114-5845-9076-e59f68bd32db |  | note | Activity - R
label | 9cbdec74-f0ef-5b43-b9e2-9a9dd711d1ed |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.02.02 - Unfavourable Conditions - Hot Weather
label | 416f2959-f198-5ce8-b3fc-f41623f6d1c2 |  | note | Acceptance / Conformance Criteria - Concrete shall not be placed in excessively hot dry conditions. Concrete temperature should not be higher than 30°C
label | c4017fc2-5cc6-5ed2-aecc-3cd472cd11ef |  | note | Standard / Specification - NZS3901 Cl. 7.2.1 & Cl. 7.2.2
label | 7cf85b13-fde5-5929-abea-2833a90b1107 |  | note | Verifying Document - Pre Pour
label | 6ea5a23e-f915-56e1-af73-6e75968177d9 |  | note | Frequency - Each Pour
label | d61eb2b7-b7eb-562f-956a-849d87435111 |  | note | Activity - R
label | e53d6810-9de7-51c0-ae49-d6cd3962be32 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.02.03 - Unfavourable Conditions - Rain
label | 5a640c52-faa6-5202-a76e-d4bd4fc98f28 |  | note | Acceptance / Conformance Criteria - Concrete shall not be commenced when heavy rains is falling or threathening and if rain commences during a pour, the work shall be protected as directed to prevent damage to the concrete or to any newly finished surfaces until the concrete has set to such a stage as to withstand leaching of the cement.
label | e38e45b4-26f3-57ea-b1f5-e6e3dfc71346 |  | note | Standard / Specification - BBO SS2146
label | eb5c7bf0-76b5-58ed-a9c4-4eb656bdac7a |  | note | Verifying Document - Pre / During Pour
label | 087aa4bd-c49c-5ac5-bf64-539c410a4ea1 |  | note | Frequency - Each Pour
label | f1d81280-3f14-5896-83a3-f4865e556fa6 |  | note | Activity - R
label | a02e601d-5d77-5dcd-9aad-b1dc81b67ac2 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.02.04 - Construction Joints
label | fffeb533-6edb-5704-8ade-0b8ceee564ff |  | note | Acceptance / Conformance Criteria - Where a concrete surface is to act as a construction joint to receive infill over or adjacent, the contact surface interface shall be prepared to the Engineer’s satisfaction to be clean, free of laitance, and with a peak to trough roughness of not less than 5mm to ensure compliance with Type B construction joints as defined by NZS3109 Section 5.6.
label | 01f58446-97c4-52e4-a945-5eb269dcf007 |  | note | Standard / Specification - PS - 11.5, NZS3109 Section 5.6
label | 89bede1c-86fb-5c84-a3e2-00e8ac30792e |  | note | Verifying Document - Pre / Post Pour
label | e9cedcb0-42e5-57cf-88c1-caf41ca6b7cd |  | note | Frequency - Each Pour
label | 16967cbe-34de-5cd1-89de-23142ad8c8f3 |  | note | Activity - I
label | e4973b09-f7f8-5df5-8195-db593cb80820 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.02.05 - Delivery dockets
label | d98a8ce7-0ca1-5985-bbb1-85afa1598766 |  | note | Acceptance / Conformance Criteria - Each batch delivered shall be accompanied by a delivery docket certifying the cement type, maximum aggregate size, specified strength, slump or spread, date, time mixing completed, and time water added at the plant.
label | f4ef2090-f71b-5210-8d0d-5a144583f357 |  | note | Standard / Specification - SS 2140 - 4
label | 0aecafb4-78a9-502f-81e0-b64d12ece63d |  | note | Verifying Document - Dockets
label | 9bbed5d5-e37b-5ab3-adbd-4f8f4c8afadd |  | note | Frequency - Each Delivery
label | 7fa309d1-bf96-5090-bcbd-1cca35864793 |  | note | Activity - R
label | 755d7aa7-da79-58b0-a4a3-bd7ce82047d1 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.02.06 - Slump tests and spread tests
label | f2441e49-3296-583e-9ce8-e22680f06a24 |  | note | Acceptance / Conformance Criteria - Slump tests or spread tests shall be taken for each delivery of concrete and the results recorded by the Contractor
label | e5fa4ddd-06d0-5cb1-ad88-ce4649aa726c |  | note | – – – – – – – – –
label | 03f753c3-2a28-513d-88ed-3ceadc10f5d4 |  | note | Table 9.1 - Tolerances for nominated slump
label | e08bce48-9bac-5b29-88c3-8bb04ef383cc |  | note | Nominated slump (mm) ¦¦ Tolerance for snatch sample (mm)
label | dcafbe63-35bd-5a1b-a604-704578def0f8 |  | note | – – – – – – – – –
label | 59f54f36-d52d-5e7a-aa04-202f56923ac4 |  | note | 60 or less ¦¦ ±20
label | 232c0dd5-c132-5513-88e8-33442e1837ab |  | note | 70 - 110 ¦¦ ±30
label | ab5f2efa-b0dc-57f5-a59d-0322ffb7152b |  | note | Greater than 110 ¦¦ ±40
label | 45e41b81-25b8-5954-994a-c8bf9bfef2d9 |  | note | – – – – – – – – –
label | d52ab3fe-b28c-59d8-9327-730a4b8683c6 |  | note | Standard / Specification - SS 2140 - 7, NZS3109 Table 9.1
label | f2d69254-ddb3-55ee-8197-8b08070d0f38 |  | note | Verifying Document - Photos or slumps and on-site records
label | 789c6e42-93ec-5498-8f69-fe61dfb33dd9 |  | note | Frequency - Each Delivery
label | 5dddbaae-acbc-52f1-9211-5852dd09874a |  | note | Activity - I
label | 0fd42dd4-87cf-5055-bc83-edc7f9e2a40c |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.02.07 - Time Limits
label | b3091f5d-d71f-5816-80b6-86c2a0670403 |  | note | Acceptance / Conformance Criteria - Concrete not placed and vibrated in forms after 90 minutes have lapsed from the stated time that water was added at the plant, or within 30 minutes after discharge from the mixer or agitator truck, may be rejected by the Engineer.
label | a456db93-00ad-592a-a56c-149b9c53da3a |  | note | • Concrete not placed in its final position in the forms before initial set has occurred shall not be used. For concrete mixes containing set accelerating admixtures the above times shall be halved.
label | d25a023b-75f1-5775-b1c3-3ed1b007a5a4 |  | note | Standard / Specification - SS 2146 - 7
label | 5537c1d4-520f-5a57-b28e-4b1b001a3064 |  | note | Verifying Document - Site Notes, Batching record, Delivery dockets
label | ebb34dd9-ad84-55ca-b132-95e943400b01 |  | note | Frequency - Each Delivery
label | cc16ed49-1224-5b63-9312-84f903825769 |  | note | Activity - R
label | cf396d5c-8453-54d4-bc31-30640606f35a |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.02.08 - Compression Testing
label | 12a81dfc-2735-518f-9f95-89dc89034743 |  | note | Acceptance / Conformance Criteria - Compression testing shall be carried out at an independent laboratory accepted by the Engineer.
label | c7d783a9-365c-53f6-949c-2cb040613a66 |  | note | • A set of specimens for compression tests shall consist of four specimens for each concrete pour, one of which is to be tested at 7 days and the remainder at 28 days. Cylinders are to be cast on-site straight from the truck, not at the batching plant.
label | 66c7fb1f-da87-5bcf-b5c9-ad6c8729ace6 |  | note | • Larger pours greater than 75m^3 will require an additional set of cylunders to be taken.
label | f0a2235e-fd2f-53a4-84b0-dbb67da813d3 |  | note | Standard / Specification - SS 2140 - 4, SS 2140 - 7
label | 661b2ca8-b561-57ab-a20f-bd7617dc146a |  | note | Verifying Document - Compression Tests
label | dd8d6713-8be2-5337-b1ff-0335454cbec7 |  | note | Frequency - Each pour
label | 31fc172e-75a7-54cb-aa92-fcefd81c6e36 |  | note | Activity - R
label | 5d39b2a3-1f62-5f02-a867-1b1eefb8f56a |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.02.09 - Concrete finishes
label | 770204c3-cf45-594e-a884-cba59d9b5e04 |  | note | Acceptance / Conformance Criteria - Concrete finish are to be as specified by NZS3114, scheduled as follows:
label | 80c37f66-0833-5573-8d63-4410d802eae2 |  | note | • Barriers: F5
label | e67cc16d-b274-5f09-8576-d54fe382002d |  | note | • Precast elements - exterior faces : F5, connecting faces to other elements: Type B construction joints to NZS3109
label | ee5e4f73-3490-5ba5-bcdd-ac92d38b36a5 |  | note | • Exposed concrete : F5
label | 0568219d-3ef7-596c-8c35-e10629522bcd |  | note | • Element below ground: F2/U2
label | 1b536b9a-0e6b-521c-aa02-5d824b0c40f2 |  | note | • Top surface of desk: U5
label | e515470c-c59a-5eef-9aa5-46ebe034f185 |  | note | Standard / Specification - NZS3114, NZS3109
label | e208738b-ba48-5e9e-be4f-46bdc6d07cf9 |  | note | Verifying Document - Approval
label | 0b85def7-79c7-5118-bd36-785d474d449d |  | note | Frequency - Post concreting
label | 34150cc9-920a-5e73-b544-e09b5385fc23 |  | note | Activity - R
label | cf5da204-6b8c-5b5c-ada6-11f80e6204ea |  | note | By - ENG
checkpoint-status |  |  | checkpoint | 3.02.10 - Curing
label | 5a0825fb-6bbe-5e63-ae9f-91c81e1c797d |  | note | Acceptance / Conformance Criteria - Minium of 7 days wet curing for all concrete including prestressed concrete after completion of accelerated curing
label | 974a1cc4-2684-5006-89cc-b3ebecc7b10d |  | note | Standard / Specification - SS2146 -11 Construction Drawing
label | ab88c804-4ce9-555b-9084-be490325f69d |  | note | Verifying Document - Acceptance / Repair Details
label | f55a6a61-7f17-5324-b8ee-f16e7432c137 |  | note | Frequency - post concreting
label | 52f72b64-4d1d-58a9-bb16-edad19b78ed1 |  | note | Activity - H
label | 1db4265e-6898-54da-a6f7-e04a20073316 |  | note | By - SE
checkpoint-group |  |  | section | SECTION 3 – CONSTRUCTION ACTIVITY - 3.03 - Post Pour
checkpoint-status |  |  | checkpoint | 3.03.01 - Falsework and Formwork Removal
label | dec414b1-eed3-5792-b204-68a2070abe22 |  | note | Acceptance / Conformance Criteria - Formwork shall not be removed until minimum periods set down in Table 5.3 of NZS3109 have elapsed.
label | c3a30472-0545-5670-9d32-721a967f62f5 |  | note | • The stripping time may be reduced if it is shown by field-cured tests that compressive strength has been attained of twice the stress to which the member will be subjected at the time of stripping or as directed by the temporary works engineer.
label | 0da5f71b-9194-5afc-ad29-138f5866a562 |  | note | Standard / Specification - SS 2144 - 10, NZS3109 Table 5.3 Downer
label | 4b26deef-4ace-5f06-8d86-e0cab898fa1e |  | note | Verifying Document - Approval
label | b43b8365-e58a-5ded-9b7a-6c6a11d3a619 |  | note | Frequency - Before removal of Falsework and Formwork
label | 02d06e25-cdd1-52b5-ad9f-8966c91e5686 |  | note | Activity - H
label | ddfc129c-97cc-5641-b3d6-06df2fa75f54 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.03.02 - Post Pour Inspection
label | 0b181a42-fa10-59a6-81ca-48ba475173a3 |  | note | Acceptance / Conformance Criteria - Post pour inspection undertaken by the site engineer and captured in the ConQA web app. Engineer notified of any defects.
label | 2aff5a62-dc55-5de2-8f1e-68bd2ad456cd |  | note | Standard / Specification - Downer
label | 762c0092-dba1-5f27-a6da-f9d21d17bd6b |  | note | Verifying Document - Site Photos
label | 63b0215c-5fc3-5895-b258-2afd6a5afb14 |  | note | Frequency - Each pour
label | de152083-4e82-5c5b-89df-3aa6966c3d6d |  | note | Activity - H
label | 703189ef-6266-513f-8080-f3aa10c07f00 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 3.03.03 - Concrete Repair
label | 1bdddc29-7007-5de3-b762-31e575623ae6 |  | note | Acceptance / Conformance Criteria - Repair of any minor surface defect or structural defect of concrete shall only be carried out with the Engineer’s acceptance. All repaired concrete shall have the same strength, durability and surface finish as the parent concrete unless otherwise accepted by the Engineer.
label | e8ea1016-5725-5913-87fa-d8f8d68e316a |  | note | Standard / Specification - SS 2146 - 11, PS - 11.5
label | bd095117-f326-526e-98b6-ae8000ddd20b |  | note | Verifying Document - Acceptance / Repair Details
label | 5ca7e0d8-1790-5caa-8305-d19193a3ca9d |  | note | Frequency - Prior to Each Repair
label | a50e1e6f-f2d3-53a4-a30c-b8d6a50966e0 |  | note | Activity - HP
label | daa68760-d745-5e56-99da-3c3019dbefcb |  | note | By - ENG
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | SECTION 4 – POST CONSTRUCTION - 4.01 - Site Post Construction Activities
checkpoint-status |  |  | checkpoint | 4.01.01 - Construction Record Compilation
label | fa54a5fb-70fe-5579-8986-21f71eb84ba6 |  | note | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | 3b97f4fe-707d-51da-9fec-b13c052aade7 |  | note | Standard / Specification - Downer
label | a68ede23-427e-5f8f-80c1-daff6a0b4bf9 |  | note | Verifying Document - Records
label | 4f3869bb-e03a-5c6a-b7f9-577b56010a16 |  | note | Frequency - Post construction
label | 38826559-5404-5117-bba5-164388588f7d |  | note | Activity - H
label | 6b7048a8-8b04-51a8-8c19-bed142084bf1 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 4.01.02 - Survey Records
label | 500135bb-9cef-5337-ac14-f192690029f8 |  | note | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | e7f5a82f-265f-5040-a61f-9736a97d1edc |  | note | Standard / Specification - Downer
label | 97d3b3b3-b255-58a0-949a-7a6e9715afd3 |  | note | Verifying Document - Records
label | 96b52f1c-77c5-5f23-b94f-c39d0692557f |  | note | Frequency - Post construction
label | b547ae6e-ba0b-58be-936a-edfd767d4e44 |  | note | Activity - H
label | 8225d0b9-eeae-5070-9cd3-3ca58bdc7832 |  | note | By - SV
checkpoint-status |  |  | checkpoint | 4.01.03 - Redline Drawings
label | df552f67-9595-5147-8470-d85d458a97c5 |  | note | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | 0696bef3-f497-537b-b93b-6175cd96feed |  | note | Standard / Specification - Downer
label | f3c1c9cd-0020-566d-b289-9fc5aadf7a3c |  | note | Verifying Document - Redlines
label | 77cedc8e-6b60-5514-bca8-5d9867a97457 |  | note | Frequency - Post construction
label | 229b9136-df9d-5d15-b775-d41a69cd622b |  | note | Activity - H
label | 29bd9bb4-29d0-5090-8cbd-e8704572436d |  | note | By - SE
checkpoint-status |  |  | checkpoint | 4.01.04 - Defect, Snag and Punch List
label | 2277c0f7-9c23-56c0-89f3-2aaaf6f44777 |  | note | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | befb1dd1-769f-523f-98eb-a52a9f831694 |  | note | Standard / Specification - Downer
label | c8fff96b-f1a2-55de-bff7-67a2b0ca14df |  | note | Verifying Document - Register
label | fe712a0b-268c-5b2d-aef5-4b0680887445 |  | note | Frequency - Post construction
label | 79382ceb-7c19-5aae-a5e6-6e3c6c5021fc |  | note | Activity - H
label | 2a25e899-1b46-56c9-9e21-eb1b3800c0c2 |  | note | By - SE
checkpoint-status |  |  | checkpoint | 4.01.05 - Delivery dockets
label | e62d23f9-8df3-5761-87aa-0d54b31ef97f |  | note | Acceptance / Conformance Criteria - At the completion of the Contract a schedule of delivery docket numbers for all concrete supplied shall be forwarded to the Engineer.
label | a97e0c17-6693-5ee3-9288-105e7865c27a |  | note | Standard / Specification - SS 2140 - 4
label | 3448efdd-5a80-5913-a8c3-1a2e38df75c6 |  | note | Verifying Document - Dockets
label | eb9fa779-7e94-529d-a4f8-b10575b7a698 |  | note | Frequency - Post construction
label | 474db2fa-1510-5eb4-ac17-126827ef5127 |  | note | Activity - H
label | 5e99b310-752b-5256-bdff-e3220ed45d9d |  | note | By - SE