## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - 134 - Concrete Islands Infill Construction Rev A | itp |  |  |  |  | ITP - 134 - Concrete Islands Infill Construction Rev A
section | 3.01 - Site Requirements
checkpoint | 3.01.01 - Construction Pack
label | Acceptance / Conformance Criteria - Methodology and ITP to be submitted to the Engineer and approved prior to works beginning
label | Standard / Specification - Downer
label | Verifying Document - Construction Pack
label | Frequency - Submit 10 days prior to commencement of works
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.01.02 - Survey Setout
label | Acceptance / Conformance Criteria - Survey Set out as per contract drawings and specification, capturing pre-construction levels where needed.
label | Standard / Specification - Downer
label | Verifying Document - Survey Records
label | Frequency - Prior to Works
label | Activity - H
label | By - SV
checkpoint | 3.01.03 - Service Location
label | Acceptance / Conformance Criteria - Complete the Excavation permit process to identify, locate and protect all services.
label | Standard / Specification - Downer
label | Verifying Document - Excavation Permit
label | Frequency - Prior to Excavation
label | Activity - H
label | By - SE
checkpoint | 3.01.04 - Internal Permits
label | Acceptance / Conformance Criteria - Complete internal Permits as required to complete works including but not limited to: Hot works, concrete saw, lift, confined space, working at height etc.
label | Standard / Specification - Downer
label | Verifying Document - Internal Permits
label | Frequency - Prior to Excavation
label | Activity - H
label | By - SE
checkpoint | 3.01.05 - External Permits
label | Acceptance / Conformance Criteria - Obtain External Permits as required to complete works including but not limited to: Close approach, Worksafe Notice etc.
label | Standard / Specification - Downer
label | Verifying Document - External Permits
label | Frequency - Prior to Excavation
label | Activity - H
label | By - PE
checkpoint | 3.01.06 - Approved Construction Drawings
label | Acceptance / Conformance Criteria - Prior to starting works, Ensure that the construction drawings are both IFC and the Current Version.
label | Standard / Specification - Downer
label | Verifying Document - IFC Drawings
label | Frequency - Prior to works start
label | Activity - H
label | By - PE
checkpoint | 3.01.07 - Previous Completed Work Packs
label | Acceptance / Conformance Criteria - Review previously completed workpacks to ensure work completed meets the contract requirements
label | Standard / Specification - Downer
label | Verifying Document - CONQA
label | Frequency - Prior to works start
label | Activity - H
label | By - PE
section | 4.01 - SUB ACTIVITY
checkpoint | 4.01.01 - GAP20
label | Acceptance / Conformance Criteria - Record material type used and source testing of that material
label | Standard / Specification - BBO
label | Verifying Document - Source Test/Site Notes
label | Frequency - 1 source test per material type
label | Activity - R
label | By - SE
checkpoint | 4.01.02 - Conrete Mix
label | Acceptance / Conformance Criteria - The strength of concrete as defined in NZS 3109 shall be 28-day cured in-place minimum strength 20MPa. With a 13mm size aggregate.
label | Standard / Specification - NZS 3019
label | Verifying Document - Source Test/Site Notes/ Concrete Dockets
label | Frequency - Each Pour
label | Activity - R
label | By - SE
section | 5.01 - Traffic Islands Construction
checkpoint | 5.01.1 - Islands Set-out
label | Acceptance / Conformance Criteria - After set-out and prior to installation of footpaths
label | Standard / Specification - PS - 2.2.16
label | Verifying Document - Hold Point Release
label | Frequency - Min 24h Notice
label | Activity - HP
label | By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.02 - Concrete boxing and Base
label | Acceptance / Conformance Criteria - Surveyor to check boxing for concrete pour, this includes the boxing for slots. For the front side of island aprons top boxing to be 50mm above F.L.
label | Standard / Specification - Downer
label | Verifying Document - Hold Point Release
label | Frequency - Min 24h Notice
label | Activity - HP
label | By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.03 - Concrete Strength & Reinforcing (Island Apron Kerb (mounatble kerb) and Infill)
label | Acceptance / Conformance Criteria - Concrete to be at minimum of 350mm on the back side of the kerb with a max of 400mm thickness for construction tolerance, with 20MPA broom finish. Island Apron/Mountable Kerb reinforcing to be D12 Bars & R5 Stirrups @ 600 centers (min 75mm cover). For the infill, two layers of 665 Mesh (75mm min cover bottom cover and 50mm top cover).
label | Standard / Specification - Downer
label | Verifying Document - Hold Point Release
label | Frequency - Each Pour
label | Activity - HP
label | By - SE
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.04 - Concrete Pre-Pour
label | Acceptance / Conformance Criteria - The Contractor shall give due notice to the Engineer of the time it is intended to place any concrete and no concrete shall be placed until approval has been obtained from BBO. Pre pour check wil includes checks on cover, lap length, spacing and bar sizes are followed per drawings specifications etc.
label | Standard / Specification - RITS - 3.4.5.3
label | Verifying Document - Hold Point Release, Pre-Pour Check
label | Frequency - Min 48h Notice
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.01.05 - Ground Preparation
label | Acceptance / Conformance Criteria - Immediately before placing the concrete, the foundations shall be lightly dampened, and formwork shall be cleaned out. In all cases surplus water shall be removed before concrete is placed. Any foreign or organic material hall be cleaned out.
label | Standard / Specification - RITS - 3.4.5.3
label | Verifying Document - Pre-Pour Check
label | Frequency - Each Pour
label | Activity - H
label | By - SE
checkpoint | 5.01.06 - Frozen Ground & Unfavourable Conditions
label | Acceptance / Conformance Criteria - Concrete shall not be placed on frozen ground nor shall it be placed in unfavourable conditions, which may be detrimental to the quality and finish of the concrete (i.e rainfall)
label | Standard / Specification - RITS - 3.4.5.3
label | Verifying Document - Pre-Pour Check
label | Frequency - Each Pour
label | Activity - I
label | By - SE
checkpoint | 5.01.07 - Curing Of Concrete
label | Acceptance / Conformance Criteria - Immediately after placement, concrete shall be protected from premature drying, excessively high or low temperatures and mechanical damage and shall be maintained with minimal moisture loss for the necessary curing period and hardening of the concrete. In hot dry weather sprinklers or damp covers will need to be used.
label | Standard / Specification - RITS - 3.4.5.5
label | Verifying Document - Post Pour Check
label | Frequency - Each Pour
label | Activity - I
label | By - SE
checkpoint | 5.01.08 - Concrete Compressive Strength
label | Acceptance / Conformance Criteria - Concrete to meet a placed 28-day compressive strength of 20-Mpa
label | Standard / Specification - RITS - D3.3.5
label | Verifying Document - Concrete Dockets
label | Frequency - Each pour
label | Activity - R
label | By - SE
checkpoint | 5.01.09 - Finished Work
label | Acceptance / Conformance Criteria - Methods shall be used that will provide a smooth, clean and even surface on the exposed faces of all concrete work.
label | Standard / Specification - RITS - 3.4.5.7
label | Verifying Document - Post Pour
label | Frequency - Each Pour
label | Activity - I
label | By - SE
checkpoint | 5.01.10 - Contraction/Expansion Joints
label | Acceptance / Conformance Criteria - Contraction/Expansion joints shall be formed or cut along the kerb at a maximum spacing of 3.0m. The slot shall penetrate the concrete by not less than 50mm and the mortar dressed over the cut face. The contractor shall ensure that cold joints are accurately marked and setout via total station so that the subsequent saw cut is in the cold joint. Should cracking occur adjacent to the saw cut a minimum section of 1.5 metres of the traffic island shall be removed and re-cast.
label | Standard / Specification - RITS - 3.4.5.8
label | Verifying Document - Post Pour
label | Frequency - Each Pour
label | Activity - I
label | By - SE
checkpoint | 5.01.11 - Finished Concrete (Surface Finish & Final Levels)
label | Acceptance / Conformance Criteria - All final path and vehicle crossing surfaces shall be true to the lines and levels Specified and ‘broom’ finished. Design considerations aside, the final surface shall not vary by more than 5mm when checked with a 3m straight edge. No finished surface shall hold water.
label | Standard / Specification - RITS - 3.4.5.10
label | Verifying Document - Post Pour Check
label | Frequency - Each Pour
label | Activity - I
label | By - SE
section | 6.01 - General
checkpoint | 6.01.01 - Construction Record Compilation
label | Acceptance / Conformance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Activity - H
label | By - SE
checkpoint | 6.01.02 - Survey Records
label | Acceptance / Conformance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Standard / Specification - Downer
label | Verifying Document - Records
label | Frequency - Post construction
label | Activity - H
label | By - SV
checkpoint | 6.01.03 - Redline Drawings
label | Acceptance / Conformance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. Red line to show any changes to footpath location or basecourse depth.
label | Standard / Specification - Downer
label | Verifying Document - Redlines
label | Frequency - Post construction
label | Activity - H
label | By - PE
checkpoint | 6.01.04 - Defect, Snag and Punch List
label | Acceptance / Conformance Criteria - Update the project Defect, Snag and Punch List Register
label | Standard / Specification - Downer
label | Verifying Document - Register
label | Frequency - Post construction
label | Activity - H
label | By - PE