## WBS x ITP
Project Name: | UGL Hunter Power Plant
CC0375 | 2024-04-23
WBS Code | Description | Inclusions (Works included) to be updated | 01 Bulk Earthworks | 02 Drainage (Pipe Laying) | 03 Drainage (Pre-cast Struct.) | 04 Oily Water (Pipe Laying) | 05 Trade Waste (Pipe Laying) | 06 Kerb and Channel | 07 Open Drains | 08 Conduit & Pit Installation | 09 Unbound Flexible Pavement | 10 Asphalt | 11 Drainage (In-situ Struct.) | 12 Concrete Pavement Construction | 13 CFA Test Piles | 14 Piling | 15 FRP Works | 16 Mass Concrete Subbase | 17 Plain and Reinforced Concrete Base | 18 Conduit Pits (In-situ) | 19 HDPE Pipe Installation | 20 Screw Pile Testing | 21 Screw Piles | 22 Precast Panels | 23 Light & Security Pole Foundations | 24 Pit Works Completion | 25 Minor Concrete Structures | 26 Sewerage System | 27 Guardrail | 28 Spray Seal
01-00-00 | POWER ISLAND 1
01-01-00 | Gas Turbine
01-01-01 | Gas Turbine | Piling, Concrete Works | [13 empty] | X | X
01-01-02 | Fuel Oil System | Concrete Works | [14 empty] | X
01-01-03 | Fuel Gas System | Concrete Works | [14 empty] | X
01-01-04 | Turbine Cooling Air System | Concrete Works | [14 empty] | X
01-01-10 | Lube Oil System | Concrete Works | [14 empty] | X
01-01-12 | GT CO2 Fire Fighting | Concrete Works | [14 empty] | X
01-01-16 | MHI Control Room | Concrete Works | [14 empty] | X
01-02-00 | GT Generator
01-02-05 | SFC Package | Concrete Works | [14 empty] | X
01-02-07 | Rotor Removal Apparatus | Concrete Works | [14 empty] | X
01-03-00 | Exhaust System
01-03-01 | Exhaust Duct | Concrete Works | [14 empty] | X
01-03-02 | Exhaust Stack | Piling, Concrete Works | [13 empty] | X | X
01-04-00 | Inlet Air System
01-04-04 | Inlet Air System Enclosure | Concrete Works | [14 empty] | X
01-05-00 | Fin Fan Coolers
01-05-01 | Fin Fan Cooler | Screw Piling, Concrete Works | [14 empty] | X | [5 empty] | X
01-06-00 | Transformers
01-06-02 | GSUT Transformer | Piling, Concrete Works, Precast Panels | [13 empty] | X | X | [6 empty] | X
01-06-04 | GSUT Neutral Grounding Reactor | Concrete Works | [14 empty] | X
01-06-06 | SFC Transformer | Concrete Works | [14 empty] | X
01-06-07 | Auxiliary Transformer | Concrete Works | [14 empty] | X
01-07-00 | Electrical Control Packages
01-07-01 | Generator Circuit Breaker | Piling, Concrete Works | [13 empty] | X | X
01-07-04 | 6.6kV Switchroom | Concrete Works | [14 empty] | X
01-07-05 | Unit Auxiliary Switchroom | Concrete Works | [14 empty] | X
01-08-00 | Interconnecting Pipework & Cabling
01-08-01 | Interconnecting Pipework | [15 empty] | X
02-00-00 | POWER ISLAND 2
02-01-00 | Gas Turbine
02-01-01 | Gas Turbine | Piling, Concrete Works | [13 empty] | X | X
02-01-02 | Fuel Oil System | Concrete Works | [14 empty] | X
02-01-03 | Fuel Gas System | Concrete Works | [14 empty] | X
02-01-04 | Turbine Cooling Air System | Concrete Works | [14 empty] | X
02-01-10 | Lube Oil System | Concrete Works | [14 empty] | X
40910 | GT CO2 Fire Fighting | Concrete Works | [14 empty] | X
02-01-16 | MHI Control Room | Concrete Works | [14 empty] | X
02-02-00 | GT Generator
02-02-05 | SFC Package | Concrete Works | [14 empty] | X
02-02-07 | Rotor Removal Apparatus | Concrete Works | [14 empty] | X
02-03-00 | Exhaust System
02-03-01 | Exhaust Duct | Concrete Works | [14 empty] | X
02-03-02 | Exhaust Stack | Piling, Concrete Works | [13 empty] | X | X
02-04-00 | Inlet Air System
02-04-04 | Inlet Air System Enclosure | Concrete Works | [14 empty] | X
02-05-00 | Fin Fan Coolers
02-05-01 | Fin Fan Cooler | Piling, Concrete Works | [14 empty] | X | [5 empty] | X
02-06-00 | Transformers
02-06-02 | GSUT Transformer | Piling, Concrete Works, Precast Panels | [13 empty] | X | X | [6 empty] | X
02-06-04 | GSUT Neutral Grounding Reactor | Concrete Works | [14 empty] | X
02-06-06 | SFC Transformer | Concrete Works | [14 empty] | X
02-06-07 | Auxiliary Transformer | Concrete Works | [14 empty] | X
02-07-00 | Electrical Control Packages
02-07-01 | Generator Circuit Breaker | Piling, Concrete Works | [13 empty] | X | X
02-07-04 | 6.6kV Switchroom | Concrete Works | [14 empty] | X
02-07-05 | Unit Auxiliary Switchroom | Concrete Works | [14 empty] | X
02-08-00 | Interconnecting Pipework & Cabling
02-08-01 | Interconnecting Pipework | Concrete Works | [14 empty] | X
03-00-00 | BALANCE OF PLANT
03-01-00 | Fire System
03-01-01 | Tanks | Piling, Concrete Works | [13 empty] | X | X
03-01-02 | Pumps | Concrete Works | [14 empty] | X
03-01-03 | Ring Main & Hydrants | Concrete Works
03-02-00 | Diesel System
03-02-01 | Tanks | Piling, Concrete Works, Precast Pannels | [13 empty] | X | X | [6 empty] | X
03-02-02 | Diesel Unloading Pumps | Concrete Works | [14 empty] | X
03-02-03 | Diesel Forwarding Pumps | Concrete Works | [14 empty] | X
03-03-00 | Demin System
03-03-01 | Tanks | Piling, Concrete Works | [13 empty] | X | X
03-03-02 | Pump | Concrete Works | [14 empty] | X
03-03-03 | Plant | Concrete Works | [14 empty] | X
03-04-00 | Service Water System
03-04-01 | Tanks | Piling, Concrete Works | [13 empty] | X | X
03-05-00 | Plant & Instrument Air
03-05-01 | Plant - Instrument Air Container, Vertical Fuel tank etc | Concrete Works | [14 empty] | X
03-06-00 | Electrical Infrastructure
03-06-02 | LV Switchrooms | Concrete Works | [14 empty] | X
03-06-04 | Aux Transformers | Concrete Works | [14 empty] | X
03-07-00 | Electrical Services
03-07-01 | Power | Conduits, Insitu Pits | [7 empty] | X | [9 empty] | X
03-07-02 | Communications | Conduits, Insitu Pits | [7 empty] | X | [9 empty] | X
03-07-04 | Lighting | Conduits, Base Foundation | [7 empty] | X | [14 empty] | X
03-08-00 | Emergency Generator
03-08-01 | Emergency Generator | Concrete Works | [14 empty] | X
03-09-00 | H2 Storage
03-09-02 | H2 Vent Stack | Concrete Works | [14 empty] | X
04-00-00 | CIVIL INFRASTRUCTURE
04-02-00 | Site Improvement
04-02-01 | Building Pad | Civil Works | [8 empty] | X
04-03-00 | Roads & Pavements
04-03-01 | Roads | Civil Works | [8 empty] | X | X
04-03-02 | Hardstands | Civil Works | [8 empty] | X | X | [17 empty] | X
04-04-00 | Earthing Grid
04-04-01 | Earthing Grid
04-05-00 | Stormwater
04-05-01 | Stormwater System | Pipes, Precast Pits, Insitu Pits |  | X | X | [7 empty] | X | [12 empty] | X
04-05-02 | Outfall | concrete headwall, gabion baskets, landscaping | [6 empty] | X | [7 empty] | X
04-06-00 | Sewer & Water
04-06-01 | Sewer System | Pipes, Pits | [10 empty] | X | [7 empty] | X | [6 empty] | X
04-06-02 | Potable Water System | Pipes, Pits | [18 empty] | X
04-07-00 | Trade Waste
04-07-01 | Trade Waste System | Pipes, Pits |  |  | X |  | X | [5 empty] | X | [12 empty] | X
04-07-02 | Neutralisation Pit | Concrete Works | [14 empty] | X |  |  |  |  | X | X
04-08-00 | Oily Water
04-08-01 | Oily Water System | Pipes, Pits |  |  | X | X | [6 empty] | X | [12 empty] | X
04-08-02 | Interceptor Pit | Concrete Works | [14 empty] | X |  |  |  |  | X | X
04-09-00 | Fencing
04-09-01 | Fencing | N/A | [26 empty] | X
04-09-02 | Gates | N/A | [26 empty] | X
04-10-00 | Common Pipe Trench
04-10-01 | Common Pipe Trench | Concrete Works | [14 empty] | X
05-00-00 | SWITCHYARD
05-01-00 | Power Transmission
05-01-01 | HV Gantry | Concrete Works | [14 empty] | X
05-01-02 | Transmission Lines | Piling, Concrete Works | [13 empty] | X | X
05-01-03 | HV Equipment | Concrete Works | [14 empty] | X
05-02-00 | Protection Switchyard Room
05-02-01 | Protection Switchyard Room | Concrete Works | [14 empty] | X