## Master List Templates
Id | Type | Name | Values | Prompting Name
e0add3f1-2627-4aca-a978-d4ada5dd2479 | checklist | Bath checklist |  | Bath checklist
0a7f00a6-6664-4ef1-a2f7-7b3fab848cb1 | checkpoint | Nogging for all fixtures
db236d30-556a-49fa-bde4-31d7bc92d622 | checkpoint | Check plan to confirm heights and centres
7161fe16-07d5-420d-89af-6a30aaa27d3a | checkpoint | Check water hammer, Silicone pipes
eb752e00-7147-4b51-a846-68a7c55645e6 | checkpoint | Check drainage waste
c0b8b1a9-ac05-45d2-8f4f-b0ae1cc9eaa8 | checklist | Hand Basin |  | Hand Basin
aa8244f6-a538-4f8f-a9e2-200832f50758 | checkpoint | Nogs for all Fixing
1ff2383b-7d2f-4d58-8792-78dd7d79ea22 | checkpoint | Check plan to confirm Heights
d84f88b2-ca99-491b-8db9-45f38716b832 | checkpoint | Check Water Hammering, Silicone Pipes
83ca7832-c4e9-4194-a21f-eea924fca6e2 | checklist | Photos |  | Photos
11881716-d32d-4e98-b218-5de09fe5cbab | checkpoint | Attach Photos

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
903309ff-beb8-4179-b9e9-cc6ecde857ce | checklist | Gas Checklist |  | Gas Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
e85dd8c2-3682-4e3f-b14f-9b29e47fd16f | checkpoint | Pipe Tested To 7Kpa
d6ebd391-caa8-46be-9e3a-62ee0d9cbc1a | checkpoint | Pipe Clearly Labelled Gas
eefe11df-61f8-41d7-b835-2dff64f20894 | checklist | Pressure Testing Checklist |  | Pressure Testing Checklist
76141745-1305-428f-9093-f2d82effdaed | section | Details
f882205e-bd6e-47e5-9423-96245fec2703 | checkpoint | Pump Up To 1500kpa Minimum
78caa1e1-a8ef-44bc-badc-fd3b901fca1b | checkpoint | Take Photos Of Testing
95a22db4-2a54-4782-8418-462439296a14 | checklist | Shower Checklist |  | Shower Checklist
d6e933d1-9801-456a-bc4b-6d5263738925 | section | Details
fabc0bf5-0d25-4ceb-a7ea-6010d748e4c8 | checkpoint | Mixer Sticking Out The Correct Length
2ea3f494-6e67-42b5-b672-3e20f2cef963 | checkpoint | Mixer Wingback Above 1700 To Prevent Backflow
74278300-18f5-4bdd-bb4e-3358f8940fed | checklist | Stacks + Vents Checklist |  | Stacks + Vents Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8158c04a-ad96-4798-a823-c6441bfdda0e | checkpoint | Inspection Junction Installed For Testing
b5c83c88-e2a5-4379-8254-0f3386a9485d | checkpoint | Pipe Labels Installed
2be78d64-8fc5-47f2-b2f3-dd1e6d34f7e4 | checkpoint | Mid Level Supports
42d5f588-8194-45fe-80cc-96b4833c20e4 | checkpoint | Write On Test Cap Date Of Test
2b3efac8-3edd-4a36-833b-b898699e44d0 | checklist | Toilet Checklist |  | Toilet Checklist
0a385ad1-87a5-4aac-b117-90a0ffd1e6cf | section | Details
aa9de65f-61f6-41af-8096-f8db238f98f9 | checkpoint | Wingback Installed To Correct Height
0cdfd80b-10ad-4d28-a5f9-c40c3ae408e2 | checkpoint | Waste Installed Correct Distance From Wall
47c5ac96-523d-40fd-a032-3fce33834df8 | checkpoint | In wall Cistern checked and tested
9015cafc-6320-48fe-bcdc-7278938606ca | checklist | Underslung Pvc |  | Underslung Pvc
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
6a3489dc-50a8-4dd2-aaed-7a15d95bf603 | checkpoint | Pvc installed To Correct Gradient
c4034a9d-abcf-4e09-8d81-a24d6b0e8def | checkpoint | Flood Tested (Add Photos Of Test)
3c1b388a-96b5-45f8-b6a8-129ea69fae41 | checkpoint | Take Photos Of Testing
40de3f33-aec0-41e3-8918-b44926827b01 | checklist | Watermain Pipework |  | Watermain Pipework
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
75f6f0d7-aebc-4244-b3e8-949b7896bfe3 | checkpoint | Bedding Put In At Correct Height
26fb860f-ea17-49ba-8b50-9766b497b27d | checkpoint | Grade Right
c3c0ea2c-59da-4454-b6a1-6bd6ece24543 | checkpoint | Check Pipes Is All The Way In
95cb8ba8-c603-47e6-afdf-03f16ee3a542 | checkpoint | Check Pipe Connections (No Gaps)
82a2bcee-59d2-4a24-8127-828633b1ae95 | checkpoint | Compact Around Pipe
cdd59698-5efb-4ea9-91e6-2c4e72e850b9 | checklist | Watermains Checklist |  | Watermains Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
e42b5af9-8543-4134-9a0f-754e74925ac0 | checkpoint | Support spacing correct
3e7fd879-64bd-4425-8e68-32355f2c9ea7 | checkpoint | Pressure Test
2889ef3c-7f2b-4511-ba57-922ad7426d9d | checkpoint | Waterhammer Mitigation
19d136be-f08e-49b8-8e96-9ff411ef6256 | checkpoint | Aquatherm Site Visit