## Master List Templates
Id | Type | Name | Values | Prompting Name | Resource Id
f9d419f4-62e4-5d04-b051-f82f8bfc9f86 | checklist | QA - Blocklaying |  | QA - Blocklaying | 6c2693ac-26cd-4dcd-afda-38bf68daab86
a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
2257e947-3c82-522b-81bd-57fb7598b5d7 | checkpoint | Approval from Summerset foreman to begin blocklaying
f9341165-01ec-5bf0-8f52-68efaa6cb9e4 | checkpoint | Set up accurate stringline for entire face
f1b8f03f-f1fe-580a-a4ce-93b2100c5187 | section | Blocking Installation
70d016f6-c845-5dda-a676-900b5aded8f2 | checkpoint | Check blocks and any broken ones discarded
e60eb319-80d6-5822-a8d8-7ac686a75f4f | checkpoint | Temporary bracing has been installed as required
1cc22e74-2e0f-50ea-a9ed-32e651560335 | checkpoint | Walls have been properly grouted
c1d01ff5-0ad0-552c-8039-2f3b1ab7a30d | checkpoint | Any openings are temporarily braced / Supported
e96043ce-7631-5d20-9b41-a7a2730886db | checkpoint | Space is warm, with proper air flow to promote drying of mortar
7fdb0dcb-53e5-53f4-ae23-205902d4b160 | checkpoint | Temporary lighting has been installed on both sides of wall(to avoid dark spaces)
78ada4fa-087e-5b9a-aa39-b137e6e0c120 | checkpoint | Any reinforcement including lintels, rebar etc have been installed as per engineering design
667625be-b0df-5674-bc14-c005fc280884 | checkpoint | Wash holes in tidy conditions
5c335cc2-3f7e-570c-afa9-8686fa7e58ed | checkpoint | Wall is installed true / plumb and in line with layout
e1e6b3ca-6022-5347-b7da-2714c76282af | section | Handover
d6dcb24c-296d-5a49-bd81-46a7bccf4741 | checkpoint | Block installation completed to specified satandard & finish

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | QA - Brickwork - Block A |  | QA - Brickwork - Block A | 117c7bad-ceaa-4b75-ae1d-79ed4b890395
| checkpoint | Mortar mixed correctly and colour consistent
| checkpoint | Premium white mortar is used as per specification plan
| checkpoint | Mortar joints are in alignment
| checkpoint | Cavity width correct
| checkpoint | Cavity insulation installed as per plan
| checkpoint | Standard Brick ties used are as per the specifications, correct length and installed correctly – 5 degree
| checkpoint | Fero brick ties installed as per the specifications
| checkpoint | Cavity and brick ties free of mortar and debris
| checkpoint | Weep-holes checked and accurate (required every 3 bricks at base and sills)
| checkpoint | Brick sill installed and checked – 15 degree consistent fall
| checkpoint | Façade bricks are installed as per plan
| checkpoint | Double layers of bricks are installed as per plan
| checklist | QA - Brickwork - Block A v2 |  | QA - Brickwork | 06bf1cb7-5007-495b-abe6-ae2f03b21ba0
| section | Prestart
| checkpoint | Approval from Summerset foreman to begin blocklaying
| checkpoint | Setting out checked back to grid and datum as per architect setting out drawings
| checkpoint | DPC installed and checked before works commence
| section | Brick/ block work Installation
| checkpoint | Mortar mixed correctly and colour consistent
| checkpoint | Premium white mortar is used as per specification plan
| checkpoint | Mortar joints are in alignment
| checkpoint | Cavity width correct
| checkpoint | Cavity insulation installed as per plan
| checkpoint | Standard Brick ties installed as per the specifications with correct spacing
| checkpoint | Fero brick ties and retaining clips installed as per the manufactures recommendations
| checkpoint | Cavity and brick ties free of mortar and debris
| checkpoint | Weep-holes checked and accurate (required every 3 bricks at base and sills)
| checkpoint | Brick sill installed and checked – 15 degree consistent fall
| checkpoint | Façade bricks are installed as per plan
| checkpoint | Double layers of bricks are installed as per plan
| checkpoint | Both Horizontal and vertical fire cavity barrier installed - this is to be offered to Summerset before work scontinue to check and ensure verything is installed correctly*
| checkpoint | Brickwork line and level t ospecification tolerances
| checkpoint | Movement joints installed as pers etting out drawings
| section | Hand over
| checkpoint | Final clean and handover
| section | Brick shelf Angle
| checkpoint | Installed to sepecification and drawings
| checkpoint | Correct Fixing used
| checkpoint | Brick support angle is line and level
| checkpoint | Toque check carried out on fixings and record results on checksheet
| checkpoint | Any damaged to galvanis3 finish has been made good with correct galvanised spray