## Master List Templates
Id | Type | Name | Values | Prompting Name | Resource Id
f9d419f4-62e4-5d04-b051-f82f8bfc9f86 | checklist | QA - Blocklaying |  | QA - Blocklaying | 6c2693ac-26cd-4dcd-afda-38bf68daab86
a252cb89-6720-5010-9702-1d823695c026 | section | Prestart
2257e947-3c82-522b-81bd-57fb7598b5d7 | checkpoint | Approval from Summerset foreman to begin blocklaying
f9341165-01ec-5bf0-8f52-68efaa6cb9e4 | checkpoint | Set up accurate stringline for entire face
f1b8f03f-f1fe-580a-a4ce-93b2100c5187 | section | Blocking Installation
70d016f6-c845-5dda-a676-900b5aded8f2 | checkpoint | Check blocks and any broken ones discarded
e60eb319-80d6-5822-a8d8-7ac686a75f4f | checkpoint | Temporary bracing has been installed as required
1cc22e74-2e0f-50ea-a9ed-32e651560335 | checkpoint | Walls have been properly grouted
c1d01ff5-0ad0-552c-8039-2f3b1ab7a30d | checkpoint | Any openings are temporarily braced / Supported
e96043ce-7631-5d20-9b41-a7a2730886db | checkpoint | Space is warm, with proper air flow to promote drying of mortar
7fdb0dcb-53e5-53f4-ae23-205902d4b160 | checkpoint | Temporary lighting has been installed on both sides of wall(to avoid dark spaces)
78ada4fa-087e-5b9a-aa39-b137e6e0c120 | checkpoint | Any reinforcement including lintels, rebar etc have been installed as per engineering design
667625be-b0df-5674-bc14-c005fc280884 | checkpoint | Wash holes in tidy conditions
5c335cc2-3f7e-570c-afa9-8686fa7e58ed | checkpoint | Wall is installed true / plumb and in line with layout
e1e6b3ca-6022-5347-b7da-2714c76282af | section | Handover
d6dcb24c-296d-5a49-bd81-46a7bccf4741 | checkpoint | Block installation completed to specified satandard & finish
202f6127-34f8-55d5-855a-2c358360918a | checklist | QA - Blockwork |  | QA - Blockwork | 7b399463-2f04-40a1-bb08-8109931318c7
c7747ec0-4906-5968-a990-f21497f95cab | checkpoint | Mortar mixed correctly and colour consistent
7719f766-729c-5958-80ff-c51bd7d1b7ed | checkpoint | Mortar joints are in alignment
05b0a0c8-016b-5fc1-840f-72ada05a19ae | checkpoint | Cavity width correct
0041952a-8b5c-58b4-b73a-5937009c8c4a | checkpoint | Standard Brick ties used are as per the specifications, correct length and installed correctly – 5 degree
55746eb4-b18a-5ee2-a560-5b8194dee363 | checkpoint | Cavity and brick ties free of mortar and debris
edf31a29-bc66-5eb6-9750-b0fcc2986aad | checkpoint | Weep-holes checked and accurate (required every 3 bricks at base and sills)
09146351-be75-5b9c-9e89-9ed2d680bb5c | checkpoint | Façade bricks are installed as per plan
d95173b7-a96e-58ca-9e58-086e3e6451ff | checkpoint | Brick waterproof on foundation head as required
2af98f7b-beec-5180-9aa1-4471ba195699 | checklist | QA - Brickwork |  | QA - Brickwork | dea6e963-2321-4405-841a-285d9c4ca109
c7747ec0-4906-5968-a990-f21497f95cab | checkpoint | Mortar mixed correctly and colour consistent
7719f766-729c-5958-80ff-c51bd7d1b7ed | checkpoint | Mortar joints are in alignment
05b0a0c8-016b-5fc1-840f-72ada05a19ae | checkpoint | Cavity width correct
0041952a-8b5c-58b4-b73a-5937009c8c4a | checkpoint | Standard Brick ties used are as per the specifications, correct length and installed correctly – 5 degree
55746eb4-b18a-5ee2-a560-5b8194dee363 | checkpoint | Cavity and brick ties free of mortar and debris
edf31a29-bc66-5eb6-9750-b0fcc2986aad | checkpoint | Weep-holes checked and accurate (required every 3 bricks at base and sills)
4b714dc1-b8e8-57ea-a886-340891109e11 | checkpoint | Brick sill installed and checked – 15 degree consistent fall
09146351-be75-5b9c-9e89-9ed2d680bb5c | checkpoint | Façade bricks are installed as per plan
d95173b7-a96e-58ca-9e58-086e3e6451ff | checkpoint | Brick waterproof on foundation head as required
bcbf739d-7303-5903-94f4-8a58a8f2b6ee | checklist | QA - Tiling |  | QA - Tiling | 1d6531a9-d820-48e9-bdca-3a3763e1d685
031e4abc-c6b5-5403-b06e-3c0fbe506de8 | checkpoint | Screeding of tiled shower bases.
753df8c1-33df-51df-baa4-934aa0adcf4b | checkpoint | Install and screed/FLC undertile heating where required (supplied, tested and connected by the electrician).
8ded89ac-a72e-5bb5-b3e7-f001495f21ed | checkpoint | Waterproofing on shower areas as requested
b3998aac-cc37-519b-84f9-c3c297412cda | checkpoint | Kitchen splashback
5f1111b2-87e1-54b0-a557-92ea9c6ff4fa | checkpoint | Floor tiling
0b11264b-9704-5e66-9c91-eb28355e3ae6 | checkpoint | Wall tiling
1f495e86-f854-5838-87e3-e79f0154cd10 | checkpoint | Tile skirting

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Passive Fire Checks |  | Passive Fire Checks | 4601e23b-a02c-405b-b38b-4b45f374b6af
| checkpoint | Remove brick from required location
| checkpoint | Photo shows if timber installed
3b48b53a-a279-556e-82e0-8d07982f87c3 | textbox | Timber measurement
| checkpoint | Reinstall bricks
| checklist | QA - Brickwork (Zone 2) |  | QA - Brickwork | 9d361cfd-1b72-46eb-a921-91f7715c4cbd
| checkpoint | Mortar mixed correctly and colour consistent
| checkpoint | Mortar joints are in alignment
| checkpoint | Cavity width correct
| checkpoint | Standard Brick ties used are as per the specifications, correct length and installed correctly – 5 degree
| checkpoint | Cavity and brick ties free of mortar and debris
| checkpoint | Weep-holes checked and accurate (required every 3 bricks at base and sills)
| checkpoint | Brick sill installed and checked – 15 degree consistent fall
| checkpoint | Façade bricks are installed as per plan
| checkpoint | Brick lock installed as required
| checkpoint | Flashing tape for shelf angle/ DPC and flashing tape for lintel above window
| checkpoint | Saddle flashing install on balcony parpet as required by contractor