## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
e5c61005-2783-4abd-b5fc-75b9239983e4 | checklist | Floor Prep Checklist |  | Floor Prep Checklist
5f181fe8-7812-4a25-b8a6-24d2b3524d28 | checkpoint | Carpet Tiles Uplifted
e8393a19-5ffa-4328-a57e-af2d90afbfe1 | checkpoint | Carpet Tiles disposed of in bin
b8468214-8b16-449f-911b-9913246eba79 | checkpoint | Strong Bond X it solution used
cdd2c51e-9a3d-4dfc-b6ec-fd4a7c8842c7 | checkpoint | Adhesive removed
74715320-6194-4206-8b4d-4b46f3bbef79 | checkpoint | Floor clean, tidy, old adhesive removed
8425baae-4421-4314-87dc-ed87085eea9b | checkpoint | Carpet tiles per specification
b3de161d-4c38-4f74-a099-2eb1d59c816e | checkpoint | Floor ready for retuning
3c003ebf-02ba-4d1e-92f8-370c53bb4698 | checkpoint | Any additional photos, comments and observations
0a81bc6c-7383-4f0d-92cc-717835a4a1c1 | checklist | H&S - Pre-start Meeting |  | H&S - Pre-start Meeting
f675ec5a-d495-4098-9a07-e4d774b74dee | section | Project Information
720e68fb-88df-4e5e-bb24-43dc4af86bf7 | checkpoint | Project information
3d47ebd7-e578-5504-a1e9-a2c10d8e1270 | button | Select meeting type: | Site-specific, In-house
f64d0650-f238-52ed-a7a0-00715c3830bd | textbox | Project name/location of site:
43c281e9-25f3-5ff0-b9ff-dca13c484896 | textbox | Name of person running this meeting:
7eb23664-7a63-5ecc-a98c-8f6327a5343e | textbox | Company:
d75697d5-0fb3-5c86-b215-5f3c21971beb | date | Date:
f3424e16-bb76-5d42-b405-cb6f76010ee5 | textbox | Scope of work:
64994096-8d84-52b4-a98e-6bad42e04619 | textbox | People Present
df3a89a6-8a8d-5c65-96d4-df685b9d05b1 | textbox | Any issues raised
fa983cd3-236c-5d83-be34-2cd6d00d73b7 | button | Subcontractors signed in | Yes/No/NA
2c298c74-3efb-5aa8-8d31-b34ce2164759 | button | Exclusion zone set up | Yes/No/NA
6f595be9-2009-47b2-af8b-5b46a1dc3c15 | checklist | H&S - SSSP Documentation |  | H&S - SSSP Documentation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
e2c7edae-ff25-459b-aa9d-ac3c8e5dca4d | checkpoint | Upload SSSP Agreement
962ba7d7-09a3-4659-ac03-59e7d399603d | checkpoint | Upload Site Safe Copies
9b877997-9b00-421c-bb7d-70ef39518c5d | checkpoint | Upload Drug & Alcohol Test Copies
31c2cc9c-f593-45a5-9702-4c1669ed88f0 | checkpoint | Upload Training and Certificate Copies
36fed33e-efd1-482a-8f19-93468d27a9cd | checklist | H&S - Toolbox Minutes |  | H&S - Toolbox Minutes
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
9749a4eb-ed5b-4a3f-8789-a2ed405d977c | checkpoint | Record of attendance and discussions
7931e2df-064a-5a70-857a-127c6b69f3fc | textbox | Date:
c6be4cac-a518-5966-9795-1c96aa5dd70e | textbox | Location:
ba7dbd77-fb4a-5a0f-8cfd-14d1cb0ab1e0 | textbox | Attendees:
a5689077-2ae0-54b5-b287-0367b688e87e | note | (separate attendees with a comma)
eff4447f-bee4-4d65-ae70-c938d6596aa8 | checkpoint | Matters arising from previous minutes
b50456e7-6090-5211-8d12-b01f3e8f98fe | textbox
ad69006c-38d8-47bd-ac7f-6febe380774f | checkpoint | Safe work practices/incidents
957856cd-9195-56fa-bbe6-b01e3dc04180 | textbox
897a50dc-aca8-44e2-a319-baa610b094a8 | checkpoint | New hazards discussed/reviewed
db430f8e-efd8-5410-a3f1-1136bddf130a | textbox
2d25487a-28e3-45ca-930a-5441f9738afe | checkpoint | Training/employee concerns
f15bb4ab-ac69-58a7-adfd-73f0fd954653 | textbox
9ea853bf-a044-47d1-921e-7f9b78908103 | checkpoint | Description of today's work
88056316-3f4a-5c89-9e24-52edbc207ea3 | textbox
1d10835f-d632-422a-9d3e-24e6d79766a9 | checkpoint | Other items
b90bfcd4-6c80-527b-a265-9fd5629045ff | textbox
57a8ff48-9a5d-41a0-a1bc-8c2021a3bbd3 | checklist | Post Flooring Checklist |  | Post Flooring Checklist
a1c86bfe-55f5-4faf-ba8a-14a61e97f82e | checkpoint | Floor Holdpoint signed off
4fe96e9a-26e7-41b3-86bb-5ef2471f29de | checkpoint | Carpet Tiles per specifications
6dc7bbb0-d3a2-4ce5-9fe2-b91cfbc92882 | checkpoint | Zone complete, ready for new zone
c66ac87b-f0b7-4ad5-9f76-26c3bf8a1f59 | checkpoint | Any additional photos, comments and observations
82401290-4a24-5143-b642-153c463f2e0a | textbox | Date of completion, Vidak agree to reintsall funiture
1ed65901-7a3b-492e-a27c-040f1c63121c | checklist | Site Daily Progress |  | Site Daily Progress
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
7c59b51d-df76-4710-a92a-18c30380e781 | checkpoint | Details - Site Daily Progress
a96b5552-b6db-5cd4-921f-7bca9889f8e5 | textbox | Site/job:
651b19c4-3128-518b-b10b-6dd6979914fc | textbox | Persons on site:
f205065b-7be1-5b38-9a9f-821279dd5b8f | date | Date of site visit:
54c77f91-0b4a-576c-a00c-cd9786f242c9 | textbox | Subcontractor on site:
854a139e-f14a-5426-807f-ae2063d0b3d7 | textbox | Verify stage of work (provide comments):
672ce37c-345a-5605-9833-8a64f0873f0c | textbox | Potential issues (provide comments):
421e699d-47f9-48d5-912e-01858557c2c8 | checkpoint | QA - Confirmation of quality of works completed since last site visit/QA
bd1c6a45-efb1-5480-8710-7657371fd61e | tickbox | Walk through site with Lead Hand
d23e6e0d-b29e-52c2-9131-a8ebe96a37d3 | tickbox | Visual check
e49683b6-4a30-5f47-a279-d7ac1e0aa0d5 | tickbox | Query the Lead Hand's Install process/progress of scope of works
9ea0469c-4b0a-50c5-86c7-b85e512c4076 | tickbox | Query the site contact satisfaction with work to date
b28a4351-ec2e-50c2-9cbd-dc8656fe372a | textbox | Other:
4068ffd5-68b2-4c5e-a1f1-0337c9f1f6fd | checkpoint | Photos to upload
b91b9cf7-4133-4e91-9c53-7bd8ad8d44f8 | checkpoint | Tasks completed by EOB
3e51c3f4-e8b9-488f-99f9-227f039ee173 | checkpoint | Labour requirements for upcoming week
68006825-9493-5c93-9ecd-4c22a11e51ad | textbox | Progress on site vs Program
555b901e-bce8-5f76-a9e9-ec77d13318d3 | textbox | Observations, comments
de0be9a7-96b6-4ea6-9c73-9d5ea782771a | checkpoint | Completion
efa18341-f933-4436-8b72-e22dd0fad87d | signoff | Click here to signoff
7d766d9a-38a2-4690-8d5e-073c676cfb6c | checklist | Site Establishment Checklist |  | Site Establishment Checklist
017d0c8d-28c6-4f51-a0b3-14ddaddb6777 | checkpoint | Any relevant dilapidation requirements captured
ca4089dc-5377-44b4-b189-d507afbbc55e | checkpoint | Attach relevant site establishment photos/ documents
fc12cdc7-3f9f-4489-9e05-828ee7189b3f | checkpoint | Appropriate isolation of site (hoardings / fencing)
98e10164-6c8c-4485-81dc-ce12050dc699 | checkpoint | Sufficient & Appropriate site/H&S signage erected
c1151313-67e3-4499-9798-f6d45273bbb1 | checkpoint | Site establishment completed
e045906e-9df6-5294-a803-a27a43a5bd5c | textbox | Comments regarding pre-inspection walk
a9778b18-49d4-4720-bbbe-2a0b0afd6dbd | checklist | Site Visit Report |  | Site Visit Report
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c5dd5890-1b92-49ec-979c-615ed3494f88 | checkpoint | Details - Site Visit
249ac296-b2e3-5a80-a02f-4a625992a166 | textbox | Site/job:
56341dab-a070-50fa-bed4-ceff1c4834cd | textbox | Persons on site:
34e3e9b9-1fa3-5ab7-b044-1e459d354af0 | date | Date of site visit:
59a9b3a5-857e-59a1-a9f2-50cf01e79357 | textbox | Weekly report discussed with Site Manager:
de40182d-3499-5f65-8b0b-e39f16f3a941 | textbox | Verify stage of work (provide comments):
929010b9-4488-5c18-86aa-8eb510763c52 | textbox | Comments (other):
cd375067-5ca6-5812-9929-cc82a85a52f6 | textbox | Potential issues (provide comments):
39820b0e-f806-4751-bcaa-b8d57ffa3d46 | checkpoint | QA - Confirmation of quality of works completed since last site visit/QA
e7d02fd2-c9a5-5323-b686-daa479f5bc32 | tickbox | Walk through site with Lead Hand
d98614ac-307c-564e-af8d-d3ff1a3e8005 | tickbox | Visual check
173d2b8b-472d-5669-971f-9a2da7b70482 | tickbox | Query the Lead Hand's Install process
0fd12039-591f-500b-8622-dab7adf48680 | tickbox | Query the site contact satisfaction with work to date
a7bae721-4b57-5277-8fef-e4765dc42d98 | textbox | Other:
079e4456-c31b-4ed4-9ec6-053b09b17177 | checkpoint | Outstanding RFIs
40ac14a7-964d-4bb2-a235-67fe1d0a67ab | checkpoint | Outstanding VO's for approval
4400fdb0-506b-480c-92b6-ebf03c612814 | checkpoint | Labour requirements for upcoming week
efaf63ae-61bf-4130-b063-635e1b013aa9 | checkpoint | Completion
9459572f-2f7c-41df-8b22-7322c328a2d8 | signoff | Click here to signoff
a79df0e0-45fd-478a-b57c-a128c38e1638 | checklist | Sub Floor Inspection |  | Sub Floor Inspection
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
df3555dc-3686-4700-9887-e6c1b33b6902 | checkpoint | Adhesive removed
2089365e-59a0-4884-acea-121009020516 | checkpoint | Remedial issues identified (pre photo)
3ef313c1-5bd0-4b4b-abe4-b784b4f1ddcc | checkpoint | Remediated subfloor
aa2ca1fa-532d-4713-930a-1addb02fe425 | checkpoint | Any additional photos, comments and observations
1052ebaf-edb9-56fc-b65a-aef3ff5778ef | textbox | Date of remediation