## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
a4863d03-9e09-4046-9af3-e77573f02059 | checklist | 561464-DOW-ITP-PC-002 Installation of Manhole | itp | 561464-DOW-ITP-PC-002 Installation of Manhole
7e6f5f7d-4bb4-413a-a08a-fffe02973fea | section | SECTION 3 – RECEIVING INSPECTIONS
05f48cf8-b9fd-4786-82a2-bc7964cb3dd5 | checkpoint | 3.1 - Material Delivery
eaf02e44-cbb1-58cf-af1c-e393399ad743 | note | Inspection Point: Quality Control Activity - Inspect for damage and wear, Confirm items are correct as per drawings and Specifications
8cad225b-166c-570f-bdb5-bb883711dd08 | note | Acceptance Criteria - Items are approved as per contract specification
091f7d2b-7633-5c38-9986-eb60d7852565 | note | ○ DCC approved
88111bd1-a6e6-58f0-b23d-dc3115237030 | note | Verifying Document - Photos, delivery docket
094ce441-1da0-52f6-bc73-fa92ebc0c26f | note | Frequency - On Delivery
0b388bcc-a60b-5073-9b29-1e8aa3040e42 | note | Inspection Type (Visual, other) - Visual
558b048c-414e-5b71-9e21-d252dd924faa | note | Inspection: Key - C
563f34ee-f0b0-593d-b762-80685e5471eb | note | Inspection: By - SP/QE
0500c46a-a9d4-4b6f-ba60-bfd52482a4bf | checkpoint | 3.2 - Set out
ab9f3525-dd17-55ff-b5ef-d9b0ccf4c735 | note | Inspection Point: Quality Control Activity - Set out completed by an approved surveyor marked allignment
197157ff-b923-56d4-9cdd-fd206b2318cd | note | Acceptance Criteria - - Allignment set out matches drawings or aggreed with the Engineer
b4b74ff4-3790-5f7f-be07-4e7b4fe56a91 | note | Verifying Document - Survey marks, photos
c2624b29-6554-5cf4-b2eb-5e0e558cce36 | note | Frequency - Prior to commencement of works
254ed5cc-a460-512a-b6ea-66eee86d54b8 | note | Inspection Type (Visual, other) - Survey
f229a8d6-92ea-560c-b136-1b5c5ed4f1f6 | note | Inspection: Key - H
08bba13a-fff5-57a2-a8e6-5384831ef0f8 | note | Inspection: By - SV/SP/QE
792abe26-115a-47d2-8edb-07cfabcb1a8e | signoff | AUTHORITY HOLDPOINT
1551629d-f665-4f0b-b54f-8f9a65d2cf9a | section | SECTION 4 – IN-PROCESS INSPECTIONS
7c508862-49d0-4728-a799-d3db91487ea6 | checkpoint | 4.1 - Trench Excavation
28af5014-44c6-5555-8df8-02f59367b9b2 | note | Inspection Point: Quality Control Activity - Excavate to required depth to invert as per drawings
18b0a7fa-a219-5d0d-ba5a-471012bab3cb | note | ○ Floor of trench to be even across width and length
47db84de-6030-5d2d-bbf7-862da7a60096 | note | Acceptance Criteria - - Allow 100mm for bedding
52be0810-d46a-5372-a565-93fec25a0d10 | note | Verifying Document - Photos, measurement checks
4b714825-7038-5b1e-8403-d88f44134381 | note | Frequency - During Installation
d8478c00-6d0a-5006-9fde-c49b6d4bffa8 | note | Inspection Type (Visual, other) - Visual
171ae244-0ad9-5774-90d3-f4fb84e37de7 | note | Inspection: Key - C
75599966-f516-565d-86a6-2aea117452b5 | note | Inspection: By - SP/QE
34ea985c-88b3-4930-beb5-0be2a8310956 | checkpoint | 4.2 - Foundation
074bce11-2b38-561f-b803-4573531b767b | note | Inspection Point: Quality Control Activity - Trench Floor Foundation to be checked it is suitable to support loads
53864fc4-e80a-54e9-abfc-a148e1d1c3a0 | note | Acceptance Criteria - Foundation should avoid very soft clay, saturated soil, or fragmented rock
43f9deb7-dda4-598b-b59b-647859b325eb | note | Verifying Document - Photos
6027f639-56fe-5c64-b452-d1709fbcd36e | note | Frequency - During Installation
8ef78a30-855f-5a7c-930b-e7c5ac5f46ad | note | Inspection Type (Visual, other) - Visual
64719749-53f1-5d1c-9614-9230e178b51b | note | Inspection: Key - H
38587172-158b-554b-a46e-275602227ce8 | note | Inspection: By - SP/QE
c6ed8d0d-2e36-47ef-8c66-988634045425 | signoff | AUTHORITY HOLDPOINT
8fcd0958-9731-4b0a-9b89-3ea38edd385c | checkpoint | 4.3 - MH Installation
7a094cef-180f-5f8a-b288-4f0920587eb3 | note | Inspection Point: Quality Control Activity - MHs to be installed true to the design level
ceb22f4c-5d38-5a6d-862e-7a28d6a286cb | note | Acceptance Criteria - -Final levels are in accordance with the drawings or within tolerance and agreed with the Engineer
d0ce067e-315a-5785-9448-39e28647e3c3 | note | Verifying Document - Photos, As-built
c9ba904b-3420-5114-8025-d8580e08d1a9 | note | Frequency - During installation
0a1ce588-301d-5cc9-80bd-d7dc26cc1c73 | note | Inspection Type (Visual, other) - Survey
1afce87c-365d-503a-a439-10804b8f49df | note | Inspection: Key - H
4d787f75-56c9-5bce-bbef-0ba683eee87b | note | Inspection: By - SP/QE
7af1a344-2754-479a-92e9-0631dc0e197d | signoff | AUTHORITY HOLDPOINT
2cff0d4c-6a2d-4f55-b259-dfc03b735175 | checkpoint | 4.4 - Benching
1501727f-c5ee-5f6b-b184-710acc4f1b8b | note | Inspection Point: Quality Control Activity - Benching concrete shall have a crushing strength of 20MPa at 28 days.
834b1011-fafb-5942-98c1-fb8181070d1a | note | ○ Benching shape to have smooth transitions at bends and junctions
5b6d1aa3-c9ce-55c2-b1c9-f24444624305 | note | Acceptance Criteria - - Benching built up to the specifications
7524a4b7-a74b-5bf7-86f0-caeeb06fbcf7 | note | Verifying Document - Photos
dda97fa4-6fe1-5005-b0a9-7779a7dbaa1b | note | Frequency - During benching contruction
1e1ce97c-8fee-583a-be03-29f155b7b24e | note | Inspection Type (Visual, other) - Visual
b0b93f69-f83d-5d7a-8672-1a0471cf314f | note | Inspection: Key - H
ea5d0a4a-5ced-509c-9fcd-16478da50815 | note | Inspection: By - SP/QE
536d8905-e7a3-4d61-b0ed-403fd4f1867b | signoff | AUTHORITY HOLDPOINT
929c7545-8f15-4fb2-8f74-1db6857b8af7 | checkpoint | 4.5 - Backfill and Compact
a16c68ea-101c-5168-b873-1bbc6081b8df | note | Inspection Point: Quality Control Activity - Backfill in 200mm layers of compacted material
e3e3e80a-bc28-5cfc-a707-6e823b019c1a | note | ○ Compaction testing one test every two layers as required
55173769-c3ba-528d-a075-6f83ea6a22f3 | note | Acceptance Criteria - - 95% MDD in roads, paths, and pavements
66dd2ab1-b916-5535-99ba-6f3bfdb88c8a | note | Verifying Document - Photos, Compaction test results
5fe8ba4c-0bfc-50d8-912d-460b0d5ccbb3 | note | Frequency - During Installation
71ad657f-3edb-5542-b382-9bb99dffe8bf | note | Inspection Type (Visual, other) - Visual, On Site test
8931e8f6-96d5-5ea6-9fab-05ac708dd937 | note | Inspection: Key - H
33784cc0-1f6b-55ff-886d-f21ec3e5821f | note | Inspection: By - SP/QE
fd19e0e3-5ba2-4443-b8c6-8211a19d65b0 | signoff | AUTHORITY HOLDPOINT
3112bd5a-9cd3-4438-86f1-7ae6598f00d2 | checkpoint | 4.6 - Basecourse
cc6b6b52-a889-56b2-8f2b-4e388458975f | note | Inspection Point: Quality Control Activity - 200mm compacted layer of M440
d3c88e11-8c17-59c4-877e-d2623e91ee91 | note | Acceptance Criteria - 98% MDD in roads
9d31119e-b801-5884-bc9c-116276fd59e2 | note | Verifying Document - Photos, Compaction test results
62783151-bba5-5f37-8329-74d363a5569c | note | Frequency - During Installation, compaction testing per 50m of pipeline or per straight section of pipeline
ce71c7cd-5e09-515d-af8a-74317be165c3 | note | Inspection Type (Visual, other) - Visual, On Site test
6041f129-11cc-57a2-b724-9c475019a2cb | note | Inspection: Key - H
ad1d2f03-f22c-5e46-a86d-e69ee5f12541 | note | Inspection: By - SP/QE/CM
15fb340e-affe-4e1d-9148-15dde16e8783 | signoff | AUTHORITY HOLDPOINT
75189e9f-f889-4518-82e8-222024e96501 | section | SECTION 5 – FINAL INSPECTION AND HANDOVER
cfe62015-827d-45aa-bfdc-fa724c0d0350 | checkpoint | 5.1 - Leak Testing
2016f9d0-c180-5723-982e-f986a39a911a | note | Inspection Point: Quality Control Activity - Manholes to be water tested up to within 150mm of the concrete lid level.
0e4b959f-3ae4-58cf-bc83-8b1a2c6bed5c | note | Acceptance Criteria - The amount of water leakage from chamber under test shall not exceed 1/300 of the volume of the chamber during a 30 minute period
5f9f80f3-b68a-5de9-b1c3-fed8b2f938eb | note | Verifying Document - Photos, test records
bd5c3855-59a7-5b77-84e8-b5193265b89f | note | Frequency - For every manhole
e41b6032-8b6f-5927-854c-811b5069475b | note | Inspection Type (Visual, other) - Test, visual
293a5022-cd57-53f2-9dea-8eddc082753c | note | Inspection: Key - H
08a8083b-740a-5988-a06a-312f974ebfcb | note | Inspection: By - SP/QE/PE/CR
c5c34675-2af0-4c9a-8d30-852d37e4e972 | signoff | AUTHORITY HOLDPOINT